December 18, 2022

CONSOR

3904 Corporex Park Drive

STE 125 Tampa, FL 33619

Attn: Matt Lewis,

RE: Project: SR 93 (I-275) from North of Martin Luther King to North of Hillsborough Avenue and SR 93 (I-275) from North of I-4 to North of Martin Luther King.

Contract No.: T7472

**CPM Schedule Update Narrative 12/18/2022**

Dear Mr. Matt Lewis,

# Current Project Schedule Status and Potential Delays

The CPM schedule currently shows 4 day(s) of negative float at Final Completion. There are no identified potential delays being tracked by this submittal.

# Projected Completion: On or Behind Schedule

The project is currently four days behind schedule at completion, reflecting a gain of two days since the last submission. The float deficit is minimal and is trending toward zero, Lane will continue to monitor the float monthly. If needed float may be recovered through dedicating additional resources to the numerous noise wall activities required to move into phase 2 of the project.

# Critical Path Changes Since Previous Submittal

The critical path for the first quarter of 2023 remains similar to the previous submittal, showing that it is critical to progress the work to the point of placing NB Lake and NB Floribraska approach slabs. The critical path to those activities includes has shifted away from the respective bridge construction activities and towards the roadway activities needed to place them.

# Successes and Problems Contributing to Critical Path Changes

* Completing bridge activities in a different sequence than anticipated has contributed to the critical path changes identified above.