## TASK
task_code | status_code | wbs_id | wbs_name | task_name | start_date | end_date | act_start_date | act_end_date | target_drtn_hr_cnt | act_drtn_hr_cnt | remain_drtn_hr_cnt | total_float_hr_cnt | float_path | resource_list | actv_code_crew_type_id | actv_code_work_type_id | delete_record_flag
Activity ID | Activity Status | WBS Code | (*)WBS Name | Activity Name | (*)Start | (*)Finish | Actual Start | Actual Finish | Original Duration(d) | (*)Actual Duration(d) | Remaining Duration(d) | (*)Total Float(d) | (*)Float Path | (*)Resources | CREW TYPE | WORK TYPE | Delete This Row
Admin-1045 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Begin Design | 2022-08-01 08:00 |  | 2022-08-01 08:00 |  | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1070 | Not Started | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Contract Completion (Nov. 3rd 2026) |  | 2026-09-25 16:00 |  |  | 0 | 0 | 0 | 66 | 1 |  | MS | MS
Admin-1060 | Not Started | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Project Punchlist | 2026-07-28 08:00 | 2026-09-25 16:00 |  |  | 60 | 0 | 60 | 66 | 1 |  | MS | MS
Admin-1050 | Not Started | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Substantial Completion (Sept. 4th, 2026) |  | 2026-07-27 16:00 |  |  | 0 | 0 | 0 | 66 | 1 |  | MS | MS
Admin-1010 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Execute Contract | 2022-07-13 08:00 | 2022-07-27 16:00 | 2022-07-13 08:00 | 2022-07-27 16:00 | 15 | 15 | 0 |  |  |  | MS | MS
Admin-1020 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Anticipated Notice to Proceed (Sept. 26th, 2022) | 2022-09-26 08:00 |  | 2022-09-26 08:00 |  | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1030 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Design Mobilization | 2022-07-13 08:00 | 2022-08-01 16:00 | 2022-07-13 08:00 | 2022-08-01 16:00 | 75 | 20 | 0 |  |  |  | MS | MS
Admin-1040 | In Progress | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | LOE - Project Duration | 2022-09-26 08:00 | 2026-09-25 16:00 | 2022-09-26 08:00 |  | 1619 | 66 | 1395 | 66 |  |  | LOE | MS
Admin-1000 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Anticipated Contract Award Date | 2022-07-13 08:00 |  | 2022-07-13 08:00 |  | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1015 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Prepare for Notice to Proceed | 2022-07-29 08:00 | 2022-09-26 16:00 | 2022-07-29 08:00 | 2022-09-26 16:00 | 60 | 60 | 0 |  |  |  | MS | MS
Admin-1080 | Completed | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Anticipated Contract Execution Date |  | 2022-07-27 08:00 |  | 2022-07-27 08:00 | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1100 | Not Started | I-275 - I-4 - IBL(all) - B1.1 | Project Administration | Design Completion |  | 2024-12-16 16:00 |  |  | 0 | 0 | 0 | 654 |  |  | MS | MS
A1000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.1 | Mobilization | Mobilization | 2023-06-22 08:00 | 2023-06-22 16:00 |  |  | 1 | 0 | 1 | 269 |  |  | OFFICE | OFFICE
P1040 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.26 | Noise Management Plan | Develop and Submit - Noise Management Plan | 2022-12-01 08:00 | 2022-12-29 16:00 |  |  | 20 | 0 | 20 | 515 |  |  | OFFICE | OFFICE
P1070 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.26 | Noise Management Plan | Review and Comment - Noise Management Plan | 2022-12-30 08:00 | 2023-01-23 16:00 |  |  | 15 | 0 | 15 | 515 |  |  | OWNER.Design Review | OWNER
P1100 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.26 | Noise Management Plan | Revise and Resubmit - Noise Management Plan | 2023-01-24 08:00 | 2023-01-30 16:00 |  |  | 5 | 0 | 5 | 515 |  |  | OFFICE | OFFICE
P1130 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.26 | Noise Management Plan | Review and Approve - Noise Management Plan | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 515 |  |  | OWNER.Design Review | OWNER
D1000 | Not Started | I-275 - I-4 - IBL(all) - B1.3.5 | Erosion and Sediment Control Plan | Develop and Submit - 90% Erosion and Sediment Control Plan | 2022-12-22 08:00 | 2023-02-06 16:00 |  |  | 30 | 0 | 30 | 340 |  |  | DESIGN | DESIGN
D1120 | Not Started | I-275 - I-4 - IBL(all) - B1.3.5 | Erosion and Sediment Control Plan | Review and Approve - 90% Erosion and Sediment Control Plan | 2023-02-07 08:00 | 2023-02-27 16:00 |  |  | 15 | 0 | 15 | 863 |  |  | OWNER.Design Review | OWNER
D1210 | Not Started | I-275 - I-4 - IBL(all) - B1.3.5 | Erosion and Sediment Control Plan | Develop and Submit - Final Erosion and Sediment Control Plan | 2023-02-28 08:00 | 2023-03-20 16:00 |  |  | 15 | 0 | 15 | 863 |  |  | DESIGN | DESIGN
D1270 | Not Started | I-275 - I-4 - IBL(all) - B1.3.5 | Erosion and Sediment Control Plan | Review and Approve - Final Erosion and Sediment Control Plan | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 863 |  |  | OWNER.Design Review | OWNER
D1640 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Develop and Submit - 90% Signing and Pavement Marking Plan | 2022-12-01 08:00 | 2023-01-30 16:00 |  |  | 40 | 0 | 40 | 773 |  |  | DESIGN | DESIGN
D1860 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Review and Approve - 90% Signing and Pavement Marking Plan | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | OWNER.Design Review | OWNER
D1960 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Develop and Submit - Final Signing and Pavement Marking Plan | 2023-02-21 08:00 | 2023-03-20 16:00 |  |  | 20 | 0 | 20 | 773 |  |  | DESIGN | DESIGN
D2100 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Review and Approve - Final Signing and Pavement Marking Plan | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | OWNER.Design Review | OWNER
D1650 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.22 | Lighting Plans (DRMP) | Develop and Submit - 90% Lighting Plans | 2022-12-01 08:00 | 2023-01-30 16:00 |  |  | 40 | 0 | 40 | 858 |  |  | DESIGN | DESIGN
D1870 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.22 | Lighting Plans (DRMP) | Review and Approve - 90% Lighting Plans | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | OWNER.Design Review | OWNER
D1970 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.22 | Lighting Plans (DRMP) | Develop and Submit - Final Lighting Plans | 2023-02-21 08:00 | 2023-03-20 16:00 |  |  | 20 | 0 | 20 | 858 |  |  | DESIGN | DESIGN
D2110 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.22 | Lighting Plans (DRMP) | Review and Approve - Final Lighting Plans | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | OWNER.Design Review | OWNER
D1660 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.20 | Signalization Plans (ASI) | Develop and Submit - 90% Signalization Plans | 2022-12-01 08:00 | 2023-01-30 16:00 |  |  | 40 | 0 | 40 | 858 |  |  | DESIGN | DESIGN
D1880 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.20 | Signalization Plans (ASI) | Review and Approve - 90% Signalization Plans | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | OWNER.Design Review | OWNER
D1980 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.20 | Signalization Plans (ASI) | Develop and Submit - Final Signalization Plans | 2023-02-21 08:00 | 2023-03-20 16:00 |  |  | 20 | 0 | 20 | 858 |  |  | DESIGN | DESIGN
D2120 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.20 | Signalization Plans (ASI) | Review and Approve - Final Signalization Plans | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | OWNER.Design Review | OWNER
D1700 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.23 | Landscape Opportunity Plans (MDG) | Develop and Submit - 90% Landscaping Opportunity Plan | 2023-07-20 08:00 | 2023-09-14 16:00 |  |  | 40 | 0 | 40 | 698 |  |  | DESIGN | DESIGN
D1930 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.23 | Landscape Opportunity Plans (MDG) | Review and Approve - 90% Landscaping Opportunity Plan | 2023-09-15 08:00 | 2023-10-05 16:00 |  |  | 15 | 0 | 15 | 698 |  |  | OWNER.Design Review | OWNER
D2030 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.23 | Landscape Opportunity Plans (MDG) | Develop and Submit - Final Landscaping Opportunity Plan | 2023-10-06 08:00 | 2023-11-02 16:00 |  |  | 20 | 0 | 20 | 698 |  |  | DESIGN | DESIGN
D2170 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.23 | Landscape Opportunity Plans (MDG) | Review and Approve - Final Landscaping Opportunity Plan | 2023-11-03 08:00 | 2023-11-28 16:00 |  |  | 15 | 0 | 15 | 698 |  |  | OWNER.Design Review | OWNER
D1010 | Completed | I-275 - I-4 - IBL(all) - B1.3.1.1 | Design Quality Management Plan | Develop and Submit - Design Quality Management Plan | 2022-09-13 08:00 | 2022-09-27 16:00 | 2022-09-13 08:00 | 2022-09-27 16:00 | 14 | 11 | 0 |  |  |  | DESIGN | DESIGN
D1080 | Completed | I-275 - I-4 - IBL(all) - B1.3.1.1 | Design Quality Management Plan | Review and Comment - Design Quality Management Plan | 2022-09-27 08:00 | 2022-10-25 16:00 | 2022-09-27 08:00 | 2022-10-25 16:00 | 10 | 21 | 0 |  |  |  | DESIGN | OWNER
D1160 | In Progress | I-275 - I-4 - IBL(all) - B1.3.1.1 | Design Quality Management Plan | Revise and Resubmit - Design Quality Management Plan | 2022-10-25 08:00 | 2022-12-07 16:00 | 2022-10-25 08:00 |  | 5 | 24 | 5 | 100 | 71 |  | DESIGN | DESIGN
D1180 | Not Started | I-275 - I-4 - IBL(all) - B1.3.1.1 | Design Quality Management Plan | Review and Approve - Design Quality Management Plan | 2022-12-08 08:00 | 2022-12-21 16:00 |  |  | 10 | 0 | 10 | 100 | 71 |  | OWNER.Design Review | OWNER
P1000 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.2 | Construction Quality Control Plan | Develop and Submit - Construction Quality Control Plan | 2022-12-01 08:00 | 2022-12-29 16:00 |  |  | 20 | 0 | 20 | 346 |  |  | OFFICE | OFFICE
P1010 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.2 | Construction Quality Control Plan | Review and Comment - Construction Quality Control Plan | 2022-12-30 08:00 | 2023-01-23 16:00 |  |  | 15 | 0 | 15 | 346 |  |  | OWNER.Design Review | OWNER
P1020 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.2 | Construction Quality Control Plan | Revise and Resubmit - Construction Quality Control Plan | 2023-01-24 08:00 | 2023-01-30 16:00 |  |  | 5 | 0 | 5 | 346 |  |  | OFFICE | OFFICE
P1030 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.2 | Construction Quality Control Plan | Review and Approve - Construction Quality Control Plan | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 346 |  |  | OWNER.Design Review | OWNER
D1710 | Not Started | I-275 - I-4 - IBL(all) - B1.3.6.3 | FDEP Environmental Resource Permit (ERP) | Modify and Submit - Environmental Resource Permit (ERP) | 2023-07-20 08:00 | 2023-07-26 16:00 |  |  | 5 | 0 | 5 | 668 |  |  | PERMIT | PERMIT
D1740 | Not Started | I-275 - I-4 - IBL(all) - B1.3.6.3 | FDEP Environmental Resource Permit (ERP) | Review and Comment - Environmental Resource Permit (ERP) | 2023-07-27 08:00 | 2024-02-02 16:00 |  |  | 130 | 0 | 130 | 668 |  |  | 3rd PARTY | 3rd Party
D1030 | Completed | I-275 - I-4 - IBL(all) - B1.3.1.2 | Preliminary IDR Submittal Schedule | Develop and Submit - Preliminary IDR Submittal Schedule | 2022-10-10 08:00 | 2022-10-28 16:00 | 2022-10-10 08:00 | 2022-10-28 16:00 | 15 | 15 | 0 |  |  |  | DESIGN | DESIGN
D1170 | Completed | I-275 - I-4 - IBL(all) - B1.3.1.2 | Preliminary IDR Submittal Schedule | Independent Design Review Kickoff Meeting | 2022-10-25 08:00 | 2022-10-25 16:00 | 2022-10-25 08:00 | 2022-10-25 16:00 | 1 | 1 | 0 |  |  |  | DESIGN | DESIGN
D1560 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.12 | Maintenance of Communication (MoC) Plan (DRMP) | Develop and Submit - 90% MoC Plan | 2022-12-01 08:00 | 2023-01-30 16:00 |  |  | 40 | 0 | 40 | 858 |  |  | DESIGN | DESIGN
D1760 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.12 | Maintenance of Communication (MoC) Plan (DRMP) | Review and Approve - 90% MoC Plan | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | OWNER.Design Review | OWNER
D1820 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.12 | Maintenance of Communication (MoC) Plan (DRMP) | Develop and Submit- Final MoC Plan | 2023-02-21 08:00 | 2023-03-20 16:00 |  |  | 20 | 0 | 20 | 858 |  |  | DESIGN | DESIGN
D1940 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.12 | Maintenance of Communication (MoC) Plan (DRMP) | Review and Approve - Final MoC Plan | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | OWNER.Design Review | OWNER
D1380 | Not Started | I-275 - I-4 - IBL(all) - B1.3.2 | Right of Way | Owner Right Of Way Acquisition Complete / Clear Date (7/1/24) |  | 2024-07-23 16:00 |  |  | 0 | 0 | 0 | 425 |  |  | MS | MS
D1780 | Not Started | I-275 - I-4 - IBL(all) - B1.3.6.3 | FDEP Environmental Resource Permit (ERP) | Resolve Comments and Issue - Environmental Resource Permit (ERP) | 2024-02-05 08:00 | 2024-02-09 16:00 |  |  | 5 | 0 | 5 | 668 |  |  | PERMIT | PERMIT
D1040 | In Progress | I-275 - I-4 - IBL(all) - B1.3.3 | Design Survey/SUE | Perform Design Survey [LoE] | 2022-08-01 08:00 | 2023-04-10 16:00 | 2022-08-01 08:00 |  | 78 | 72 | 74 | 153 |  |  | LOE | SURVEY
D1350 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | 2022-12-22 08:00 | 2023-03-20 16:00 |  |  | 60 | 0 | 60 | 326 |  |  | DESIGN | DESIGN
D1540 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 326 |  |  | OWNER.Design Review | OWNER
D1810 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Develop and Submit - Final Cat1 Brg 08 Plans - R3 | 2023-04-11 08:00 | 2023-05-08 16:00 |  |  | 20 | 0 | 20 | 326 |  |  | DESIGN | DESIGN
D1890 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Review and Approve - Final Cat1 Brg 08 Plans - R3 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 326 |  |  | OWNER.Design Review | OWNER
D1200 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Develop and Submit - 90% Roadway Plans - R1 | 2022-12-01 08:00 | 2023-04-10 16:00 |  |  | 90 | 0 | 90 | 106 |  |  | DESIGN | DESIGN
D1460 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Review and Approve - 90% Roadway Plans - R1 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 229 |  |  | OWNER.Design Review | OWNER
D1490 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Develop and Submit - Final Roadway Plans - R1 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 229 |  |  | DESIGN | DESIGN
D1570 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Review and Approve - Final Roadway Plans - R1 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 229 |  |  | OWNER.Design Review | OWNER
D1610 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Develop and Submit - Sign & Seal Roadway Plans - R1 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 229 |  |  | DESIGN | DESIGN
D1670 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Issue - RFC Roadway Plans - R1 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 229 |  |  | DESIGN | DESIGN
D1680 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-1 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 502 |  |  | DESIGN | DESIGN
D1900 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-1 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 502 |  |  | OWNER.Design Review | OWNER
D1990 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-1 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 502 |  |  | DESIGN | DESIGN
D2130 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-1 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 502 |  |  | OWNER.Design Review | OWNER
D1730 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.11 | Landscape/Irrigation Plans (MDG) | Develop and Submit - 90% Landscape Plans | 2023-07-20 08:00 | 2023-09-14 16:00 |  |  | 40 | 0 | 40 | 698 |  |  | DESIGN | DESIGN
D1950 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.11 | Landscape/Irrigation Plans (MDG) | Review and Approve - 90% Landscape Plans | 2023-09-15 08:00 | 2023-10-05 16:00 |  |  | 15 | 0 | 15 | 698 |  |  | OWNER.Design Review | OWNER
D2040 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.11 | Landscape/Irrigation Plans (MDG) | Develop and Submit - Final Landscape Plans | 2023-10-06 08:00 | 2023-11-02 16:00 |  |  | 20 | 0 | 20 | 698 |  |  | DESIGN | DESIGN
D2180 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.11 | Landscape/Irrigation Plans (MDG) | Review and Approve - Final Landscape Plans | 2023-11-03 08:00 | 2023-11-28 16:00 |  |  | 15 | 0 | 15 | 698 |  |  | OWNER.Design Review | OWNER
LoE100 | In Progress | I-275 - I-4 - IBL(all) - B1.1.1 | Phase Durations | Design Phase [LoE] | 2022-08-01 08:00 | 2024-12-16 16:00 | 2022-08-01 08:00 |  | 783 | 122 | 747 | 654 |  |  | LOE | DESIGN
LoE110 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 1 Stage 1 - Ramp WE-B / Dn-St Ramp NE Construction [LoE] | 2023-06-30 08:00 | 2024-09-12 16:00 |  |  | 441 | 0 | 441 | 175 |  |  | LOE | LOE
LoE120 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 1 Stage 1 - 13th Ave Construction [LoE] | 2023-06-30 08:00 | 2024-06-13 16:00 |  |  | 350 | 0 | 350 | 270 |  |  | LOE | LOE
LoE140 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 1 Stage 2 - Dn-St Ramp NE / I-4 Widening [LoE] | 2024-09-13 08:00 | 2025-02-20 16:00 |  |  | 161 | 0 | 161 | 132 |  |  | LOE | LOE
LoE130 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 2 Stage 1 Step 1 - New Ramp NE-C Substructure [LoE] | 2023-10-02 08:00 | 2024-04-11 16:00 |  |  | 193 | 0 | 193 | 963 |  |  | LOE | LOE
LoE150 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 2 Stage 2 - Up-St Ramp NE Right Construction [LoE] | 2025-06-03 08:00 | 2025-11-04 16:00 |  |  | 155 | 0 | 155 | 150 |  |  | LOE | LOE
D1130 | Not Started | I-275 - I-4 - IBL(all) - B1.3.6.12 | Stormwater Pollution Prevention Plan (SWPPP) | Develop and Submit - SWPPP & NOI | 2023-02-07 08:00 | 2023-02-07 16:00 |  |  | 1 | 0 | 1 | 340 |  |  | PERMIT | PERMIT
D1140 | Not Started | I-275 - I-4 - IBL(all) - B1.3.6.12 | Stormwater Pollution Prevention Plan (SWPPP) | Review and Approve - SWPPP & NOI | 2023-02-08 08:00 | 2023-02-28 16:00 |  |  | 15 | 0 | 15 | 340 |  |  | 3rd PARTY | 3rd Party
D1250 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 2 | 2022-12-30 08:00 | 2023-02-27 16:00 |  |  | 40 | 0 | 40 | 838 |  |  | DESIGN | DESIGN
D1390 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Review and Approve - 90% TTCP Plans - R1 Phase 2 | 2023-02-28 08:00 | 2023-03-20 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | OWNER.Design Review | OWNER
D1410 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - Final TTCP Plans - R1 Phase 2 | 2023-03-21 08:00 | 2023-04-17 16:00 |  |  | 20 | 0 | 20 | 838 |  |  | DESIGN | DESIGN
D1470 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Review and Approve - Final TTCP Plans - R1 Phase 2 | 2023-04-18 08:00 | 2023-05-08 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | OWNER.Design Review | OWNER
D1510 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | DESIGN | DESIGN
D1580 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Issue - RFC TTCP Plans - R1 Phase 2 | 2023-05-31 08:00 | 2023-06-06 16:00 |  |  | 5 | 0 | 5 | 838 |  |  | DESIGN | DESIGN
D1420 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 2022-12-30 08:00 | 2023-02-27 16:00 |  |  | 40 | 0 | 40 | 678 |  |  | DESIGN | DESIGN
D1550 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Review and Approve - 90% TTCP Plans - R2 Phase 1 | 2023-02-28 08:00 | 2023-03-20 16:00 |  |  | 15 | 0 | 15 | 710 |  |  | OWNER.Design Review | OWNER
D1600 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - Final TTCP Plans - R2 Phase 1 | 2023-03-21 08:00 | 2023-04-17 16:00 |  |  | 20 | 0 | 20 | 710 |  |  | DESIGN | DESIGN
D1620 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Review and Approve - Final TTCP Plans - R2 Phase 1 | 2023-04-18 08:00 | 2023-05-08 16:00 |  |  | 15 | 0 | 15 | 710 |  |  | OWNER.Design Review | OWNER
D1770 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 710 |  |  | DESIGN | DESIGN
D1830 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Issue - RFC TTCP Plans - R2 Phase 1 | 2023-05-31 08:00 | 2023-06-06 16:00 |  |  | 5 | 0 | 5 | 710 |  |  | DESIGN | DESIGN
D1910 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | 2023-02-28 08:00 | 2023-04-24 16:00 |  |  | 40 | 0 | 40 | 678 |  |  | DESIGN | DESIGN
D2190 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Review and Approve - 90% TTCP Plans - R2 Phase 2 | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 678 |  |  | OWNER.Design Review | OWNER
D2260 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - Final TTCP Plans - R2 Phase 2 | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 678 |  |  | DESIGN | DESIGN
D2400 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Review and Approve - Final TTCP Plans - R2 Phase 2 | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 678 |  |  | OWNER.Design Review | OWNER
D2430 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 2 | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 678 |  |  | DESIGN | DESIGN
D2460 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Issue - RFC TTCP Plans - R2 Phase 2 | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 678 |  |  | DESIGN | DESIGN
D1260 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | 2022-12-01 08:00 | 2023-03-14 16:00 |  |  | 71 | 0 | 71 | 248 |  |  | DESIGN | DESIGN
D1400 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Review and Approve - 90% TTCP Plans - R1 Phase 1 | 2023-03-15 08:00 | 2023-04-04 16:00 |  |  | 15 | 0 | 15 | 248 |  |  | OWNER.Design Review | OWNER
D1430 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Develop and Submit - Final TTCP Plans - R1 Phase 1 | 2023-04-05 08:00 | 2023-05-02 16:00 |  |  | 20 | 0 | 20 | 248 |  |  | DESIGN | DESIGN
D1480 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Review and Approve - Final TTCP Plans - R1 Phase 1 | 2023-05-03 08:00 | 2023-05-23 16:00 |  |  | 15 | 0 | 15 | 248 |  |  | OWNER.Design Review | OWNER
D1520 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 1 | 2023-05-24 08:00 | 2023-06-14 16:00 |  |  | 15 | 0 | 15 | 248 |  |  | DESIGN | DESIGN
D1590 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Issue - RFC TTCP Plans - R1 Phase 1 | 2023-06-15 08:00 | 2023-06-21 16:00 |  |  | 5 | 0 | 5 | 248 |  |  | DESIGN | DESIGN
D2050 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 08 Plans - R3 | 2023-05-31 08:00 | 2023-06-13 16:00 |  |  | 10 | 0 | 10 | 326 |  |  | DESIGN | DESIGN
D2080 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Issue - RFC Cat1 Brg 08 Plans - R3 | 2023-06-14 08:00 | 2023-06-20 16:00 |  |  | 5 | 0 | 5 | 326 |  |  | DESIGN | DESIGN
D2210 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-1 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 502 |  |  | DESIGN | DESIGN
D2310 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-1 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 502 |  |  | DESIGN | DESIGN
P1060 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.3 | Settlement and Vibration Monitoring Plan | Develop and Submit - Settlement and Vibration Monitoring Plan | 2022-12-01 08:00 | 2022-12-29 16:00 |  |  | 20 | 0 | 20 | 515 |  |  | OFFICE | OFFICE
P1090 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.3 | Settlement and Vibration Monitoring Plan | Review and Comment - Settlement and Vibration Monitoring Plan | 2022-12-30 08:00 | 2023-01-23 16:00 |  |  | 15 | 0 | 15 | 515 |  |  | OWNER.Design Review | OWNER
P1120 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.3 | Settlement and Vibration Monitoring Plan | Revise and Resubmit - Settlement and Vibration Monitoring Plan | 2023-01-24 08:00 | 2023-01-30 16:00 |  |  | 5 | 0 | 5 | 515 |  |  | OFFICE | OFFICE
P1150 | Not Started | I-275 - I-4 - IBL(all) - B1.4.1.3 | Settlement and Vibration Monitoring Plan | Review and Approve - Settlement and Vibration Monitoring Plan | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 515 |  |  | OWNER.Design Review | OWNER
D1310 | Not Started | I-275 - I-4 - IBL(all) - B1.3.5 | Erosion and Sediment Control Plan | Develop and Submit - Sign & Seal Erosion and Sediment Control Plan | 2023-04-11 08:00 | 2023-04-24 16:00 |  |  | 10 | 0 | 10 | 863 |  |  | DESIGN | DESIGN
D1330 | Not Started | I-275 - I-4 - IBL(all) - B1.3.5 | Erosion and Sediment Control Plan | Issue - RFC Erosion and Sediment Control Plan | 2023-04-25 08:00 | 2023-05-01 16:00 |  |  | 5 | 0 | 5 | 863 |  |  | DESIGN | DESIGN
D2320 | Not Started | I-275 - I-4 - IBL(all) - B1.3.16 | Technical Specifications Submittal | Develop and Submit - 90% Technical Specifications | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 773 |  |  | DESIGN | DESIGN
D2420 | Not Started | I-275 - I-4 - IBL(all) - B1.3.16 | Technical Specifications Submittal | Review and Approve - 90% Technical Specifications | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | OWNER.Design Review | OWNER
D2450 | Not Started | I-275 - I-4 - IBL(all) - B1.3.16 | Technical Specifications Submittal | Develop and Submit - Final Technical Specifications | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 773 |  |  | DESIGN | DESIGN
D2470 | Not Started | I-275 - I-4 - IBL(all) - B1.3.16 | Technical Specifications Submittal | Review and Approve - Final Technical Specifications | 2023-07-20 08:00 | 2023-08-09 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | OWNER.Design Review | OWNER
D2490 | Not Started | I-275 - I-4 - IBL(all) - B1.3.16 | Technical Specifications Submittal | Develop and Submit - Sign & Seal Technical Specifications | 2023-08-10 08:00 | 2023-08-30 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | DESIGN | DESIGN
D2500 | Not Started | I-275 - I-4 - IBL(all) - B1.3.16 | Technical Specifications Submittal | Issue - RFP Technical Specifications | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 773 |  |  | DESIGN | DESIGN
D2060 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.12 | Maintenance of Communication (MoC) Plan (DRMP) | Develop and Submit- Sign & Seal MoC Plan | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | DESIGN | DESIGN
D2140 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.12 | Maintenance of Communication (MoC) Plan (DRMP) | Issue - RFC MoC Plan | 2023-05-02 08:00 | 2023-05-08 16:00 |  |  | 5 | 0 | 5 | 858 |  |  | DESIGN | DESIGN
D2220 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.20 | Signalization Plans (ASI) | Develop and Submit - Sign & Seal Signalization Plans | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | DESIGN | DESIGN
D2330 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.20 | Signalization Plans (ASI) | Issue - RFC Signalization Plans | 2023-05-02 08:00 | 2023-05-08 16:00 |  |  | 5 | 0 | 5 | 858 |  |  | DESIGN | DESIGN
D1690 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.14 | ITS Plans (DRMP) | Develop and Submit - 90% ITS Plans | 2022-12-01 08:00 | 2023-01-30 16:00 |  |  | 40 | 0 | 40 | 773 |  |  | DESIGN | DESIGN
D1920 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.14 | ITS Plans (DRMP) | Review and Approve - 90% ITS Plans | 2023-01-31 08:00 | 2023-02-20 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | OWNER.Design Review | OWNER
D2000 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.14 | ITS Plans (DRMP) | Develop and Submit- Final ITS Plans | 2023-02-21 08:00 | 2023-03-20 16:00 |  |  | 20 | 0 | 20 | 773 |  |  | DESIGN | DESIGN
D2150 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.14 | ITS Plans (DRMP) | Review and Approve - Final ITS Plans | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | OWNER.Design Review | OWNER
D2230 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.14 | ITS Plans (DRMP) | Develop and Submit- Sign & Seal ITS Plans | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | DESIGN | DESIGN
D2340 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.14 | ITS Plans (DRMP) | Issue - RFC ITS Plans | 2023-05-02 08:00 | 2023-05-08 16:00 |  |  | 5 | 0 | 5 | 858 |  |  | DESIGN | DESIGN
D2240 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Develop and Submit - Sign & Seal Signing and Pavement Marking Plan | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 773 |  |  | DESIGN | DESIGN
D2350 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Issue - RFC Signing and Pavement Marking Plan | 2023-05-02 08:00 | 2023-05-08 16:00 |  |  | 5 | 0 | 5 | 834 |  |  | DESIGN | DESIGN
D2250 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.22 | Lighting Plans (DRMP) | Develop and Submit - Sign & Seal Lighting Plans | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 858 |  |  | DESIGN | DESIGN
D2360 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.22 | Lighting Plans (DRMP) | Issue - RFC Lighting Plans | 2023-05-02 08:00 | 2023-05-08 16:00 |  |  | 5 | 0 | 5 | 858 |  |  | DESIGN | DESIGN
D2270 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.23 | Landscape Opportunity Plans (MDG) | Develop and Submit - Sign & Seal Landscaping Opportunity Plan | 2023-11-29 08:00 | 2023-12-19 16:00 |  |  | 15 | 0 | 15 | 698 |  |  | DESIGN | DESIGN
D2380 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.23 | Landscape Opportunity Plans (MDG) | Issue - RFC Landscaping Opportunity Plan | 2023-12-20 08:00 | 2023-12-27 16:00 |  |  | 5 | 0 | 5 | 698 |  |  | DESIGN | DESIGN
D2280 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.11 | Landscape/Irrigation Plans (MDG) | Develop and Submit - Sign & Seal Landscape Plans | 2023-11-29 08:00 | 2023-12-19 16:00 |  |  | 15 | 0 | 15 | 698 |  |  | DESIGN | DESIGN
D2390 | Not Started | I-275 - I-4 - IBL(all) - B1.3.18.11 | Landscape/Irrigation Plans (MDG) | Issue - RFC Landscape Plans | 2023-12-20 08:00 | 2023-12-27 16:00 |  |  | 5 | 0 | 5 | 698 |  |  | DESIGN | DESIGN
D2480 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 2022-12-30 08:00 | 2023-02-27 16:00 |  |  | 40 | 0 | 40 | 461 |  |  | DESIGN | DESIGN
D2510 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Review and Approve - 90% TTCP Plans - R3 Phase 1 | 2023-02-28 08:00 | 2023-03-20 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | OWNER.Design Review | OWNER
D2520 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - Final TTCP Plans - R3 Phase 1 | 2023-03-21 08:00 | 2023-04-17 16:00 |  |  | 20 | 0 | 20 | 838 |  |  | DESIGN | DESIGN
D2530 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Review and Approve - Final TTCP Plans - R3 Phase 1 | 2023-04-18 08:00 | 2023-05-08 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | OWNER.Design Review | OWNER
D2540 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 1 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | DESIGN | DESIGN
D2550 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Issue - RFC TTCP Plans - R3 Phase 1 | 2023-05-31 08:00 | 2023-06-06 16:00 |  |  | 5 | 0 | 5 | 838 |  |  | DESIGN | DESIGN
D1220 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 296 |  |  | DESIGN | DESIGN
D1440 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | 2023-09-15 08:00 | 2023-10-26 16:00 |  |  | 30 | 0 | 30 | 341 |  |  | OWNER.Design Review | OWNER
D1450 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | 2023-09-15 08:00 | 2024-01-04 16:00 |  |  | 75 | 0 | 75 | 296 |  |  | DESIGN | DESIGN
D1630 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Review and Approve - 90% Cat2 Brg 10 Plans - R3 | 2024-01-05 08:00 | 2024-03-29 16:00 |  |  | 60 | 0 | 60 | 296 |  |  | OWNER.Design Review | OWNER
D2010 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Develop and Submit - Final Cat2 Brg 10 Plans - R3 | 2024-04-01 08:00 | 2024-04-26 16:00 |  |  | 20 | 0 | 20 | 296 |  |  | DESIGN | DESIGN
D2160 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Review and Approve - Final Cat2 Brg 10 Plans - R3 | 2024-04-29 08:00 | 2024-05-24 16:00 |  |  | 20 | 0 | 20 | 296 |  |  | OWNER.Design Review | OWNER
D2290 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Develop and Submit - Sign & Seal Cat2 Brg 10 Plans - R3 | 2024-05-28 08:00 | 2024-06-10 16:00 |  |  | 10 | 0 | 10 | 296 |  |  | DESIGN | DESIGN
D2370 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Issue - RFC Cat2 Brg 10 Plans - R3 | 2024-06-11 08:00 | 2024-06-17 16:00 |  |  | 5 | 0 | 5 | 296 |  |  | DESIGN | DESIGN
P1270 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.6 | R1- Shop Drawings - Steel Bridge Girders | Develop and Submit - Girder Shop Drawings - Brg 2 - Cat 2 | 2023-10-02 08:00 | 2023-12-28 16:00 |  |  | 60 | 0 | 60 | 114 |  |  | OFFICE | OFFICE
P1300 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.6 | R1- Shop Drawings - Steel Bridge Girders | Review and Comment - Girder Shop Drawings - Brg 2 - Cat 2 | 2023-12-29 08:00 | 2024-01-22 16:00 |  |  | 15 | 0 | 15 | 114 |  |  | OWNER.Design Review | OWNER
P1310 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.6 | R1- Shop Drawings - Steel Bridge Girders | Revise and Resubmit - Girder Shop Drawings - Brg 2 - Cat 2 | 2024-01-23 08:00 | 2024-01-29 16:00 |  |  | 5 | 0 | 5 | 114 |  |  | OFFICE | OFFICE
P1320 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.6 | R1- Shop Drawings - Steel Bridge Girders | Review and Approve - Girder Shop Drawings - Brg 2 - Cat 2 | 2024-01-30 08:00 | 2024-02-19 16:00 |  |  | 15 | 0 | 15 | 114 |  |  | OWNER.Design Review | OWNER
P1200 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 1 - R1 | 2023-06-21 08:00 | 2023-07-05 16:00 |  |  | 10 | 0 | 10 | 605 |  |  | PROCURE | PROCUREMENT
P1280 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.3 | R2 Procurement - Bridge Pile | Procure Pile - Bridge 6 - R2 | 2024-12-17 08:00 | 2024-12-31 16:00 |  |  | 10 | 0 | 10 | 349 |  |  | PROCURE | PROCUREMENT
D1050 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - 60% Dry Utility Relocation Plans | 2022-12-01 08:00 | 2022-12-21 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | DESIGN | DESIGN
D1070 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Review and Approve - 60% Dry Utility Relocation Plans | 2022-12-22 08:00 | 2023-01-13 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | 3rd PARTY | 3rd Party
D1150 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - 90% Dry Utility Relocation Plans | 2023-01-17 08:00 | 2023-02-20 16:00 |  |  | 25 | 0 | 25 | 272 |  |  | DESIGN | DESIGN
D1240 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Review and Approve - 90% Dry Utility Relocation Plans | 2023-02-21 08:00 | 2023-03-13 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | 3rd PARTY | 3rd Party
D1300 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - 100% Dry Utility Relocation Plans | 2023-03-14 08:00 | 2023-03-20 16:00 |  |  | 5 | 0 | 5 | 272 |  |  | DESIGN | DESIGN
D1320 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Review and Approve - 100% Dry Utility Relocation Plans | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | 3rd PARTY | 3rd Party
D1340 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - Sign & Seal Dry Utility Relocation Plans | 2023-04-11 08:00 | 2023-04-17 16:00 |  |  | 5 | 0 | 5 | 272 |  |  | DESIGN | DESIGN
D1370 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.2 | Dry Utility Relocation Plans - TECO/FTR | Issue - RFC Dry Utility Relocation Plans | 2023-04-18 08:00 | 2023-04-24 16:00 |  |  | 5 | 0 | 5 | 272 |  |  | DESIGN | DESIGN
A1010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.1 | Mobilization | Install Erosion Control Devices | 2023-06-30 08:00 | 2023-07-17 16:00 |  |  | 10 | 0 | 10 | 216 |  | Sub - Erosion Control Crew | SUB.EROSION | EROSION
A1020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.1 | Mobilization | Clear and Grub | 2023-07-18 08:00 | 2023-08-09 16:00 |  |  | 15 | 0 | 15 | 216 |  | Sub - Clearing & Grubbing Crew | SUB.EARTH.C&G | EARTH.Clear&Grub
A1030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.1 | R1 - Ph0 - MOT | Install MOT - I-4 Exit Ramp - R1 - P0 | 2023-06-30 08:00 | 2023-06-30 16:00 |  |  | 1 | 0 | 1 | 229 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.1 | R1 - Ph0 - MOT | Shift Traffic - I-4 Exit 1 Ramp Right - R1 - P0 | 2023-07-03 08:00 | 2023-07-03 16:00 |  |  | 1 | 0 | 1 | 229 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Start Construction - R1 | 2023-06-30 08:00 |  |  |  | 0 | 0 | 0 | 257 |  |  | MS | MS
A1060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.3 | R1 - Ph0 - Traffic Shift | Shift Traffic - I-4 Exit 1 Ramp Left - R1 - P0 | 2023-09-11 08:00 | 2023-09-11 16:00 |  |  | 1 | 0 | 1 | 216 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.2 | R1 - Ph0 - Temp Pavement | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | 2023-07-27 08:00 | 2023-08-09 16:00 |  |  | 10 | 0 | 10 | 216 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A1090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.2 | R1 - Ph0 - Temp Pavement | Place Stabilization - 13th Ave Temp Pav - R1 - P0 | 2023-08-10 08:00 | 2023-09-05 16:00 |  |  | 14 | 0 | 14 | 216 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A1100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.2 | R1 - Ph0 - Temp Pavement | Place Asphalt - 13th Ave Temp Pav - R1 - P0 | 2023-09-07 08:00 | 2023-09-07 16:00 |  |  | 1 | 0 | 1 | 216 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A1110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.2 | R1 - Ph0 - Temp Pavement | Temp Striping - 13th Ave Temp Pav - R1 - P0 | 2023-09-08 08:00 | 2023-09-08 16:00 |  |  | 1 | 0 | 1 | 216 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Temp
A1120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp WE Left - R1 - P1.S1 | 2023-07-20 08:00 | 2023-07-20 16:00 |  |  | 1 | 0 | 1 | 195 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Install Temp Barrier - Ramp WE - R1 - P1.S1 | 2023-07-21 08:00 | 2023-07-21 16:00 |  |  | 1 | 0 | 1 | 195 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A1140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp NE Left - R1 - P1.S1 | 2023-07-24 08:00 | 2023-07-24 16:00 |  |  | 1 | 0 | 1 | 236 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Install Temp Barrier - Ramp NE - R1 - P1.S1 | 2023-07-25 08:00 | 2023-07-31 16:00 |  |  | 4 | 0 | 4 | 236 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A1630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | 2023-08-01 08:00 | 2023-08-01 16:00 |  |  | 1 | 0 | 1 | 199 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A1650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | 2023-08-02 08:00 | 2023-08-03 16:00 |  |  | 2 | 0 | 2 | 276 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A1660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | FRP Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | 2023-08-10 08:00 | 2023-08-14 16:00 |  |  | 3 | 0 | 3 | 285 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A1670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Cure/Strip Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | 2023-08-15 08:00 | 2023-08-17 16:00 |  |  | 3 | 0 | 3 | 490 |  |  | CURE | CURE
A14670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | 2023-08-04 08:00 | 2023-08-09 16:00 |  |  | 4 | 0 | 4 | 276 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A14680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Temp Wall or SOE - Brg 100865 - End Bent 1 - R1 - P1.S1 | 2023-07-24 08:00 | 2023-07-31 16:00 |  |  | 5 | 0 | 5 | 199 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A14700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-08-02 08:00 | 2023-08-02 16:00 |  |  | 1 | 0 | 1 | 260 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A14720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-08-03 08:00 | 2023-08-10 16:00 |  |  | 6 | 0 | 6 | 260 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A14730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-08-11 08:00 | 2023-08-15 16:00 |  |  | 3 | 0 | 3 | 260 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A14740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-08-16 08:00 | 2023-08-22 16:00 |  |  | 7 | 0 | 7 | 443 |  |  | CURE | CURE
A14750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Column - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-08-24 08:00 | 2023-08-28 16:00 |  |  | 3 | 0 | 3 | 261 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A14760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Column - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-08-29 08:00 | 2023-09-04 16:00 |  |  | 7 | 0 | 7 | 444 |  |  | CURE | CURE
A14770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-09-05 08:00 | 2023-09-11 16:00 |  |  | 5 | 0 | 5 | 263 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A14780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 7 | 0 | 7 | 450 |  |  | CURE | CURE
A14790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 2023-09-19 08:00 | 2023-09-26 16:00 |  |  | 5 | 0 | 5 | 268 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A14800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install SIP - Brg 100865 - Span 1 - R1 - P1.S1 | 2023-09-28 08:00 | 2023-09-28 16:00 |  |  | 1 | 0 | 1 | 279 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A14810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | 2023-09-28 08:00 | 2023-10-16 16:00 |  |  | 12 | 0 | 12 | 268 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A14820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Reinforce Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 2023-10-17 08:00 | 2023-10-23 16:00 |  |  | 4 | 0 | 4 | 268 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A14830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Place Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 2024-03-28 08:00 | 2024-03-28 16:00 |  |  | 1 | 0 | 1 | 182 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A14840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Cure Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 2024-03-29 08:00 | 2024-04-04 16:00 |  |  | 7 | 0 | 7 | 315 |  |  | CURE | CURE
A14850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install Reinf Barrier - Brg 100865 - Span 1 - R1 - P1.S1 | 2024-04-05 08:00 | 2024-04-08 16:00 |  |  | 2 | 0 | 2 | 181 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A14860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Strip Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | 2024-04-09 08:00 | 2024-04-11 16:00 |  |  | 3 | 0 | 3 | 181 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A14890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | FRPS Approach Slab 1 - Brg 100865 - R1 - P1.S1 | 2024-03-29 08:00 | 2024-04-05 16:00 |  |  | 6 | 0 | 6 | 188 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A14900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | FRPS Approach Slab 2 - Brg 100865 - R1 - P1.S1 | 2024-03-29 08:00 | 2024-04-05 16:00 |  |  | 6 | 0 | 6 | 188 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A14880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Slip Barrier - Brg 100865 - R1 - P1.S1 | 2024-04-15 08:00 | 2024-04-18 16:00 |  |  | 3 | 0 | 3 | 180 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A14910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Grind Deck - Brg 100865 - R1 - P1.S1 | 2024-04-19 08:00 | 2024-04-22 16:00 |  |  | 2 | 0 | 2 | 180 |  | Sub - Diamond Grind Pavement Crew | SUB.CONCRETE.GRIND | CONCRETE PVMT.Diamond Grind
A14920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Groove Deck - Brg 100865 - R1 - P1.S1 | 2024-04-23 08:00 | 2024-04-23 16:00 |  |  | 1 | 0 | 1 | 180 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A14930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Perm Striping - Brg 100865 - R1 - P1.S1 | 2024-04-25 08:00 | 2024-04-25 16:00 |  |  | 1 | 0 | 1 | 180 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A14950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Const MSE Wall & Bkfill - RW 5-1 - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-02-08 08:00 | 2024-02-27 16:00 |  |  | 12 | 0 | 12 | 182 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A14970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Wall Barrier - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-03-21 08:00 | 2024-04-03 16:00 |  |  | 10 | 0 | 10 | 182 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A14960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Junction Slab - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-03-05 08:00 | 2024-03-19 16:00 |  |  | 9 | 0 | 9 | 182 |  | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A14940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Cut/Fill to Grade - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2023-08-10 08:00 | 2023-08-18 16:00 |  |  | 6 | 0 | 6 | 276 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A14980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Stabilization - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-03-04 08:00 | 2024-03-04 16:00 |  |  | 1 | 0 | 1 | 182 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A14990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Asphalt Base - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-04-04 08:00 | 2024-04-04 16:00 |  |  | 1 | 0 | 1 | 182 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Concrete Pav - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-04-05 08:00 | 2024-04-12 16:00 |  |  | 6 | 0 | 6 | 182 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A15010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | 2023-07-24 08:00 | 2023-08-18 16:00 |  |  | 18 | 0 | 18 | 195 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Curb - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-10-27 08:00 | 2023-10-30 16:00 |  |  | 2 | 0 | 2 | 263 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A15050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 2023-08-02 08:00 | 2023-08-02 16:00 |  |  | 1 | 0 | 1 | 199 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A15070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | 2023-08-03 08:00 | 2023-08-04 16:00 |  |  | 2 | 0 | 2 | 199 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A15100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | FRP Abt Cap - Brg 100865 - End Bent 2 - R1 - P1.S1 | 2024-02-16 08:00 | 2024-02-20 16:00 |  |  | 3 | 0 | 3 | 182 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A15110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Cure/Strip Abt Cap - Brg 100865 - End Bent 2- R1 - P1.S1 | 2024-02-21 08:00 | 2024-02-23 16:00 |  |  | 3 | 0 | 3 | 303 |  |  | CURE | CURE
A15080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Const MSE Wall & Bkfill - RW 5-2 / Brg 100865 - End Bent 2 - R1 - P1.S1 | 2024-02-08 08:00 | 2024-02-15 16:00 |  |  | 5 | 0 | 5 | 96 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A15120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-06-30 08:00 | 2023-06-30 16:00 |  |  | 1 | 0 | 1 | 211 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A15140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-07-06 08:00 | 2023-07-14 16:00 |  |  | 6 | 0 | 6 | 209 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A15150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-07-17 08:00 | 2023-07-20 16:00 |  |  | 3 | 0 | 3 | 276 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A15160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-07-21 08:00 | 2023-07-27 16:00 |  |  | 7 | 0 | 7 | 468 |  |  | CURE | CURE
A15170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Column - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-07-28 08:00 | 2023-08-02 16:00 |  |  | 4 | 0 | 4 | 277 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A15180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Column - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-08-03 08:00 | 2023-08-09 16:00 |  |  | 7 | 0 | 7 | 470 |  |  | CURE | CURE
A15190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-08-10 08:00 | 2023-08-17 16:00 |  |  | 5 | 0 | 5 | 276 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A15200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | 2023-08-18 08:00 | 2023-08-24 16:00 |  |  | 7 | 0 | 7 | 475 |  |  | CURE | CURE
A15210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 2023-09-19 08:00 | 2023-09-26 16:00 |  |  | 5 | 0 | 5 | 263 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A15230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install SIP - Brg 100865 - Span 2 - R1 - P1.S1 | 2023-09-28 08:00 | 2023-09-28 16:00 |  |  | 1 | 0 | 1 | 278 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A15240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | 2023-09-28 08:00 | 2023-10-23 16:00 |  |  | 16 | 0 | 16 | 263 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A15250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Reinforce Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 2023-10-24 08:00 | 2023-10-30 16:00 |  |  | 5 | 0 | 5 | 263 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A15260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Place Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 2024-03-28 08:00 | 2024-03-28 16:00 |  |  | 1 | 0 | 1 | 181 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A15270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Cure Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 2024-03-29 08:00 | 2024-04-04 16:00 |  |  | 7 | 0 | 7 | 314 |  |  | CURE | CURE
A15280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install Reinf Barrier - Brg 100865 - Span 2 - R1 - P1.S1 | 2024-04-05 08:00 | 2024-04-08 16:00 |  |  | 2 | 0 | 2 | 180 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A15290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Strip Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | 2024-04-09 08:00 | 2024-04-12 16:00 |  |  | 4 | 0 | 4 | 180 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A15300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Erect Girders - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-02-26 08:00 | 2024-03-01 16:00 |  |  | 5 | 0 | 5 | 181 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A15320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Install SIP - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-03-04 08:00 | 2024-03-04 16:00 |  |  | 1 | 0 | 1 | 191 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A15330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Install Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-03-04 08:00 | 2024-03-21 16:00 |  |  | 11 | 0 | 11 | 181 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A15340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Reinforce Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-03-22 08:00 | 2024-03-27 16:00 |  |  | 4 | 0 | 4 | 181 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A15350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Place Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-03-28 08:00 | 2024-03-28 16:00 |  |  | 1 | 0 | 1 | 182 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A15360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Cure Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-03-29 08:00 | 2024-04-04 16:00 |  |  | 7 | 0 | 7 | 315 |  |  | CURE | CURE
A15370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Install Reinf Barrier - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-04-05 08:00 | 2024-04-08 16:00 |  |  | 2 | 0 | 2 | 181 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A15380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Strip Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | 2024-04-09 08:00 | 2024-04-11 16:00 |  |  | 3 | 0 | 3 | 181 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A15390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Edge Drain - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-04-15 08:00 | 2024-04-18 16:00 |  |  | 3 | 0 | 3 | 182 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Shoulder GAB - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-04-19 08:00 | 2024-04-19 16:00 |  |  | 1 | 0 | 1 | 182 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A15410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Asphalt Shoulder - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-04-22 08:00 | 2024-04-22 16:00 |  |  | 1 | 0 | 1 | 182 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | 2023-07-24 08:00 | 2023-08-18 16:00 |  |  | 18 | 0 | 18 | 195 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | 2023-08-01 08:00 | 2023-08-28 16:00 |  |  | 18 | 0 | 18 | 278 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | 2023-07-24 08:00 | 2023-08-18 16:00 |  |  | 18 | 0 | 18 | 263 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 1 | 2024-03-07 08:00 | 2024-04-22 16:00 |  |  | 30 | 0 | 30 | 109 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A15490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Wall Barrier - Ramp WE Sta 50 to 60 - R1 - P1.S1 | 2024-08-06 08:00 | 2024-08-09 16:00 |  |  | 4 | 0 | 4 | 96 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A15480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Junction Slab - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-06-18 08:00 | 2024-08-05 16:00 |  |  | 29 | 0 | 29 | 96 |  | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A15450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | 2024-02-16 08:00 | 2024-03-27 16:00 |  |  | 25 | 0 | 25 | 96 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A15470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Stabilization - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-06-14 08:00 | 2024-06-17 16:00 |  |  | 2 | 0 | 2 | 96 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A15500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Asphalt Base - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-08-12 08:00 | 2024-08-12 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Concrete Pav - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-08-13 08:00 | 2024-08-29 16:00 |  |  | 10 | 0 | 10 | 96 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A15520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Edge Drain - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-09-03 08:00 | 2024-09-06 16:00 |  |  | 4 | 0 | 4 | 96 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Shoulder GAB - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-09-09 08:00 | 2024-09-10 16:00 |  |  | 2 | 0 | 2 | 96 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A15540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Asphalt Shoulder - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-09-12 08:00 | 2024-09-12 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - left | 2024-03-28 08:00 | 2024-05-07 16:00 |  |  | 27 | 0 | 27 | 99 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A15560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place 3-Pour Barrier - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 2024-02-28 08:00 | 2024-03-01 16:00 |  |  | 3 | 0 | 3 | 182 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A15570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place 3-Pour Barrier - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 2024-05-14 08:00 | 2024-06-13 16:00 |  |  | 20 | 0 | 20 | 96 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A15610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Wall Barrier - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-06-28 08:00 | 2024-07-09 16:00 |  |  | 7 | 0 | 7 | 123 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A15600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Junction Slab - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-06-18 08:00 | 2024-06-27 16:00 |  |  | 6 | 0 | 6 | 123 |  | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A15580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Cut/Fill to Grade - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-05-14 08:00 | 2024-06-13 16:00 |  |  | 20 | 0 | 20 | 123 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A15590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Stabilization - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-06-14 08:00 | 2024-06-17 16:00 |  |  | 2 | 0 | 2 | 123 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A15620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Asphalt Base - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-07-10 08:00 | 2024-07-10 16:00 |  |  | 1 | 0 | 1 | 123 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Concrete Pav - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-07-11 08:00 | 2024-07-18 16:00 |  |  | 5 | 0 | 5 | 123 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A15640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Edge Drain - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-07-19 08:00 | 2024-07-23 16:00 |  |  | 3 | 0 | 3 | 123 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Shoulder GAB - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-07-25 08:00 | 2024-07-25 16:00 |  |  | 1 | 0 | 1 | 123 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A15660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.8 | R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Asphalt Shoulder - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 2024-07-26 08:00 | 2024-07-26 16:00 |  |  | 1 | 0 | 1 | 123 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Grading - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-04-23 08:00 | 2024-04-23 16:00 |  |  | 1 | 0 | 1 | 164 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A15690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Stabilization - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-05-02 08:00 | 2024-05-03 16:00 |  |  | 2 | 0 | 2 | 164 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A15700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Asphalt Base - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-05-06 08:00 | 2024-05-06 16:00 |  |  | 1 | 0 | 1 | 164 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Concrete Pav - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-05-07 08:00 | 2024-05-14 16:00 |  |  | 5 | 0 | 5 | 164 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A15720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Edge Drain - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-05-16 08:00 | 2024-05-17 16:00 |  |  | 2 | 0 | 2 | 164 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Shoulder GAB - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-05-20 08:00 | 2024-05-20 16:00 |  |  | 1 | 0 | 1 | 164 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A15740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Asphalt Shoulder - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-05-21 08:00 | 2024-05-21 16:00 |  |  | 1 | 0 | 1 | 164 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.9 | R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place 3-Pour Barrier - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 2024-04-25 08:00 | 2024-05-01 16:00 |  |  | 5 | 0 | 5 | 164 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A15750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Cut/Fill to Grade - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 - part 1 | 2023-08-21 08:00 | 2023-10-04 16:00 |  |  | 26 | 0 | 26 | 263 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A15770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Stabilization - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-10-26 08:00 | 2023-10-26 16:00 |  |  | 1 | 0 | 1 | 263 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A15780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Asphalt Base - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-10-31 08:00 | 2023-10-31 16:00 |  |  | 1 | 0 | 1 | 263 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Concrete Pav - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-11-01 08:00 | 2023-11-20 16:00 |  |  | 11 | 0 | 11 | 263 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A15800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Edge Drain - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-11-21 08:00 | 2023-11-29 16:00 |  |  | 4 | 0 | 4 | 263 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Shoulder GAB - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-11-30 08:00 | 2023-11-30 16:00 |  |  | 1 | 0 | 1 | 263 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A15820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Asphalt Shoulder - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-12-01 08:00 | 2023-12-01 16:00 |  |  | 1 | 0 | 1 | 263 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place 3-Pour Barrier - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 2023-10-05 08:00 | 2023-10-25 16:00 |  |  | 13 | 0 | 13 | 263 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A15830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Cut/Fill to Grade - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-08-29 08:00 | 2023-10-03 16:00 |  |  | 20 | 0 | 20 | 278 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A15850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Stabilization - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-10-04 08:00 | 2023-10-04 16:00 |  |  | 1 | 0 | 1 | 278 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A15860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Asphalt Base - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-10-05 08:00 | 2023-10-05 16:00 |  |  | 1 | 0 | 1 | 278 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Concrete Pav - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-10-06 08:00 | 2023-10-24 16:00 |  |  | 11 | 0 | 11 | 278 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A15880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Edge Drain - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-10-25 08:00 | 2023-10-31 16:00 |  |  | 5 | 0 | 5 | 278 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Shoulder GAB - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-11-01 08:00 | 2023-11-01 16:00 |  |  | 1 | 0 | 1 | 278 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A15900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.11 | R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Asphalt Shoulder - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 2023-11-02 08:00 | 2023-11-02 16:00 |  |  | 1 | 0 | 1 | 278 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A15910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 1 Stage 1 - R1 - 13th Ave |  | 2024-06-13 16:00 |  |  | 0 | 0 | 0 | 192 |  |  | MS | MS
A15920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE |  | 2024-09-12 16:00 |  |  | 0 | 0 | 0 | 125 |  |  | MS | MS
A15940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.9 | R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Shift Traffic - 13th Ave Right - R1 - P1.S1 Step 1 | 2023-09-12 08:00 | 2023-09-12 16:00 |  |  | 1 | 0 | 1 | 216 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A15950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.9 | R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | 2023-09-14 08:00 | 2023-09-26 16:00 |  |  | 8 | 0 | 8 | 216 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A15970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Const MSE Wall & Bkfill - RW-100 - Left 13th Ave Sta 13 to 16 - R1 - P1.S1 | 2024-02-08 08:00 | 2024-03-12 16:00 |  |  | 21 | 0 | 21 | 151 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A15960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 2023-09-28 08:00 | 2023-10-09 16:00 |  |  | 8 | 0 | 8 | 216 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A15980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place Stabilization - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 2024-03-14 08:00 | 2024-03-14 16:00 |  |  | 1 | 0 | 1 | 151 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A15990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place GAB - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 2024-03-15 08:00 | 2024-03-15 16:00 |  |  | 1 | 0 | 1 | 151 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A16000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place Curb - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 2024-03-18 08:00 | 2024-03-19 16:00 |  |  | 2 | 0 | 2 | 151 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A16010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place Asphalt Surface - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 2024-03-21 08:00 | 2024-03-21 16:00 |  |  | 1 | 0 | 1 | 151 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.1 | R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 2024-03-27 08:00 | 2024-04-09 16:00 |  |  | 10 | 0 | 10 | 155 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A16030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.1 | R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place Stabilization - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 2024-04-10 08:00 | 2024-04-10 16:00 |  |  | 1 | 0 | 1 | 155 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A16040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.1 | R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place GAB - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 2024-04-11 08:00 | 2024-04-11 16:00 |  |  | 1 | 0 | 1 | 155 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A16050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.1 | R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place Curb - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 2024-04-12 08:00 | 2024-04-12 16:00 |  |  | 1 | 0 | 1 | 155 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A16070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.1 | R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place Asphalt Surface - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 2024-04-15 08:00 | 2024-04-15 16:00 |  |  | 1 | 0 | 1 | 155 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 2023-09-28 08:00 | 2023-10-09 16:00 |  |  | 8 | 0 | 8 | 234 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A16090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Stabilization - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 2023-10-10 08:00 | 2023-10-10 16:00 |  |  | 1 | 0 | 1 | 234 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A16100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place GAB - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 2023-10-12 08:00 | 2023-10-12 16:00 |  |  | 1 | 0 | 1 | 234 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A16110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Curb - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 2023-10-13 08:00 | 2023-10-20 16:00 |  |  | 5 | 0 | 5 | 234 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A16130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Asphalt Surface - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 2023-10-23 08:00 | 2023-10-23 16:00 |  |  | 1 | 0 | 1 | 234 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.10 | R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | Shift Traffic - 13th Ave Left - R1 - P1.S1 Step 2 | 2024-03-22 08:00 | 2024-03-22 16:00 |  |  | 1 | 0 | 1 | 151 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A16150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.10 | R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 2 | 2024-03-25 08:00 | 2024-03-26 16:00 |  |  | 2 | 0 | 2 | 151 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A16160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.8 | R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Cut/Fill to Grade - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 2024-03-27 08:00 | 2024-04-09 16:00 |  |  | 10 | 0 | 10 | 151 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A16170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.8 | R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place Stabilization - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 2024-04-10 08:00 | 2024-04-10 16:00 |  |  | 1 | 0 | 1 | 151 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A16180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.8 | R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place GAB - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 2024-04-11 08:00 | 2024-04-11 16:00 |  |  | 1 | 0 | 1 | 151 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A16190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.8 | R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place Curb - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 2024-04-12 08:00 | 2024-04-19 16:00 |  |  | 5 | 0 | 5 | 151 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A16210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.8 | R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place Asphalt Surface - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 2024-04-22 08:00 | 2024-04-22 16:00 |  |  | 1 | 0 | 1 | 151 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.11 | R1 - Ph1, Stg1 - 13th Ave - Finishes | Mill / Resurface - 13th Ave Sta 13 to 35 - R1 - P1.S1 | 2024-05-02 08:00 | 2024-05-03 16:00 |  |  | 2 | 0 | 2 | 151 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.11 | R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Intersection Brick - 13th Ave at 14th & 15th St - R1 - P1.S1 | 2024-05-06 08:00 | 2024-06-13 16:00 |  |  | 25 | 0 | 25 | 151 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A16240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.11 | R1 - Ph1, Stg1 - 13th Ave - Finishes | Remove Temp Barrier - 13th Ave - R1 - P1.S1 | 2024-04-23 08:00 | 2024-05-01 16:00 |  |  | 6 | 0 | 6 | 151 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A16270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Place Brick Sidewalk - Left 14th & 15th St under I-4 - R1 - P1.S1 | 2023-07-25 08:00 | 2023-08-15 16:00 |  |  | 15 | 0 | 15 | 324 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A16250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Left 14th &15th St under I-4 - R1 - P1.S1 | 2023-06-30 08:00 | 2023-07-03 16:00 |  |  | 2 | 0 | 2 | 324 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Flatwork Demo
A16260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Left 14th & 15th St under I-4 - R1 - P1.S1 | 2023-07-17 08:00 | 2023-07-24 16:00 |  |  | 5 | 0 | 5 | 324 |  | Sub - Concrete Flatwork Crew | SUB.FLATWRK | FLATWORK.Ditch Pave
A16280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Const Gravity Wall - Left 14th & 15th St under I-4 - R1 - P1.S1 | 2023-07-05 08:00 | 2023-07-14 16:00 |  |  | 7 | 0 | 7 | 324 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A16290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.11 | R1 - Ph1, Stg1 - 13th Ave - Finishes | Install Fencing - 13th Ave - R1 - P1.S1 | 2023-08-17 08:00 | 2023-08-21 16:00 |  |  | 3 | 0 | 3 | 324 |  | Sub - Fence Installation Crew | SUB.FENCE | FENCE
A16340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.3 | R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 1 | 2024-07-25 08:00 | 2024-08-22 16:00 |  |  | 18 | 0 | 18 | 353 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A16350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.3 | R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place Stabilization - Pond SMF 4A Shared Use Path - R2 - P0 | 2024-08-23 08:00 | 2024-09-03 16:00 |  |  | 5 | 0 | 5 | 353 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A16360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.3 | R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place Asphalt - Pond SMF 4A Shared Use Path - R2 - P0 | 2024-09-23 08:00 | 2024-09-24 16:00 |  |  | 2 | 0 | 2 | 353 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.3 | R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place Curb - Pond SMF 4A Shared Use Path - R2 - P0 | 2024-09-10 08:00 | 2024-09-20 16:00 |  |  | 7 | 0 | 7 | 353 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A16380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-101 to S-105 - I-4 Sta 310 to 314 - R2 - P1 | 2024-07-29 08:00 | 2024-08-26 16:00 |  |  | 18 | 0 | 18 | 419 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-104 to S-113/S-112 - Ramp EN Sta 97 to 103 - R2 - P1 | 2024-07-29 08:00 | 2024-08-26 16:00 |  |  | 18 | 0 | 18 | 387 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-113 to O-101 - Ramp EN Sta 90 to 99 - R2 - P1 | 2024-07-29 08:00 | 2024-08-26 16:00 |  |  | 18 | 0 | 18 | 387 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-118 to S-123 - Pond SMF 4A - R2 - P1 | 2024-08-23 08:00 | 2024-09-24 16:00 |  |  | 18 | 0 | 18 | 353 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-126 to S-134 - Pond SMF 4A to Taliaferro Sta 21 - R2 - P1 | 2024-07-29 08:00 | 2024-08-26 16:00 |  |  | 18 | 0 | 18 | 369 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-136 to S-146 - Taliaferro Ave - R2 - P1 | 2024-07-29 08:00 | 2024-08-26 16:00 |  |  | 18 | 0 | 18 | 361 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.1 | R2 - Ph1 - Ramp EN Lower Drainage | Install DRG S-147 to S-151 - I-275 Sta 715 to 717 - R2 - P1 | 2024-10-01 08:00 | 2024-10-28 16:00 |  |  | 18 | 0 | 18 | 324 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.4 | R2 - Milestones | Start Construction - R2 | 2024-07-24 08:00 |  |  |  | 0 | 0 | 0 | 441 |  |  | MS | MS
A16500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Shift Traffic - Ramp NE Right - R1 - P1.S2 | 2024-09-16 08:00 | 2024-09-16 16:00 |  |  | 1 | 0 | 1 | 96 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A16510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Shift Traffic - Ramp NE Left - R1 - P1.S2 | 2024-09-13 08:00 | 2024-09-13 16:00 |  |  | 1 | 0 | 1 | 96 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A16530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Const MSE Wall & Bkfill - RW 103 - I-4 Sta 311 to 320 - R2 - P1 | 2025-03-25 08:00 | 2025-04-28 16:00 |  |  | 23 | 0 | 23 | 304 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A16560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.2 | R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Stabilization - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 2024-09-17 08:00 | 2024-09-20 16:00 |  |  | 3 | 0 | 3 | 158 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A16590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.2 | R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Asphalt Base - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 2024-09-23 08:00 | 2024-09-23 16:00 |  |  | 1 | 0 | 1 | 158 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.2 | R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Concrete Pav - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 2024-09-24 08:00 | 2024-09-27 16:00 |  |  | 3 | 0 | 3 | 158 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A16610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.2 | R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Edge Drain - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 2024-09-30 08:00 | 2024-09-30 16:00 |  |  | 1 | 0 | 1 | 158 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A16620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.2 | R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Shoulder GAB - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 2024-10-01 08:00 | 2024-10-01 16:00 |  |  | 1 | 0 | 1 | 158 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A16630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.2 | R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Asphalt Shoulder - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 2024-10-02 08:00 | 2024-10-02 16:00 |  |  | 1 | 0 | 1 | 158 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Open Ramp WE-B / Close I-4 EB Exit 1 - R1 - P1.S2 | 2024-09-19 08:00 | 2024-09-19 16:00 |  |  | 1 | 0 | 1 | 96 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A16640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Remove Temp Barrier - Ramp WE-B - R1 - P1.S2 | 2024-09-17 08:00 | 2024-09-17 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A16670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Shift Traffic - I-4 Left - R1 - P1.S2 | 2024-09-20 08:00 | 2024-09-20 16:00 |  |  | 1 | 0 | 1 | 96 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A16660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Install Temp Barrier - I-4 - R1 - P1.S2 | 2024-09-23 08:00 | 2024-10-03 16:00 |  |  | 8 | 0 | 8 | 96 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A16680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Excavate - Brg 100656 - Pier 1 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-04 16:00 |  |  | 1 | 0 | 1 | 118 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A16690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Drive Pile - Brg 100656 - Pier 1 - R1 - P1.S2 | 2024-10-07 08:00 | 2024-10-08 16:00 |  |  | 2 | 0 | 2 | 118 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A16730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | FRP Column - Brg 100656 - Pier 1 - R1 - P1.S2 | 2024-10-10 08:00 | 2024-10-10 16:00 |  |  | 1 | 0 | 1 | 118 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A16740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Cure/Strip Column - Brg 100656 - Pier 1 - R1 - P1.S2 | 2024-10-11 08:00 | 2024-10-17 16:00 |  |  | 7 | 0 | 7 | 209 |  |  | CURE | CURE
A16750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | FRP Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | 2024-10-18 08:00 | 2024-10-22 16:00 |  |  | 3 | 0 | 3 | 118 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A16760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Cure/Strip Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | 2024-10-23 08:00 | 2024-10-25 16:00 |  |  | 3 | 0 | 3 | 209 |  |  | CURE | CURE
A16770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Erect Girders - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-10-29 08:00 | 2024-10-29 16:00 |  |  | 1 | 0 | 1 | 117 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A16780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Install SIP - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-10-30 08:00 | 2024-10-30 16:00 |  |  | 1 | 0 | 1 | 117 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A16790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Install Overhangs - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-10-31 08:00 | 2024-11-06 16:00 |  |  | 5 | 0 | 5 | 117 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A16800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Reinforce Deck - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-11-07 08:00 | 2024-11-07 16:00 |  |  | 1 | 0 | 1 | 117 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A16810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Place Deck - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-11-08 08:00 | 2024-11-08 16:00 |  |  | 1 | 0 | 1 | 117 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A16820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Cure Deck - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-11-09 08:00 | 2024-11-15 16:00 |  |  | 7 | 0 | 7 | 216 |  |  | CURE | CURE
A16830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Install Reinf Barrier - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-11-18 08:00 | 2024-11-18 16:00 |  |  | 1 | 0 | 1 | 122 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A16840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Strip Overhangs - Brg 100656 - Span 1 - R1 - P1.S2 | 2024-11-19 08:00 | 2024-11-19 16:00 |  |  | 1 | 0 | 1 | 122 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A16860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | FRPS Approach Slab 1 - Brg 100656 - R1 - P1.S2 | 2024-11-12 08:00 | 2024-11-15 16:00 |  |  | 3 | 0 | 3 | 117 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A16870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | FRPS Approach Slab 2 - Brg 100656 - R1 - P1.S2 | 2024-11-14 08:00 | 2024-11-19 16:00 |  |  | 4 | 0 | 4 | 116 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A16880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Slip Barrier - Brg 100656 - R1 - P1.S2 | 2024-11-26 08:00 | 2024-11-26 16:00 |  |  | 1 | 0 | 1 | 119 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A16900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Groove Deck - Brg 100656 - R1 - P1.S2 | 2024-11-21 08:00 | 2024-11-21 16:00 |  |  | 1 | 0 | 1 | 126 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A16910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Perm Striping - Brg 100656 - R1 - P1.S2 | 2024-12-09 08:00 | 2024-12-09 16:00 |  |  | 1 | 0 | 1 | 119 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A17010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Erect Girders - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-10-28 08:00 | 2024-10-28 16:00 |  |  | 1 | 0 | 1 | 120 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A17020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Install SIP - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-10-29 08:00 | 2024-10-29 16:00 |  |  | 1 | 0 | 1 | 120 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A17030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Install Overhangs - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-10-30 08:00 | 2024-11-06 16:00 |  |  | 6 | 0 | 6 | 120 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Reinforce Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-11-07 08:00 | 2024-11-07 16:00 |  |  | 1 | 0 | 1 | 120 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Place Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-11-12 08:00 | 2024-11-12 16:00 |  |  | 1 | 0 | 1 | 119 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A17060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Cure Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-11-13 08:00 | 2024-11-19 16:00 |  |  | 7 | 0 | 7 | 211 |  |  | CURE | CURE
A17070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Install Reinf Barrier - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-11-21 08:00 | 2024-11-21 16:00 |  |  | 1 | 0 | 1 | 119 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Strip Overhangs - Brg 100656 - Span 2 - R1 - P1.S2 | 2024-11-22 08:00 | 2024-11-25 16:00 |  |  | 2 | 0 | 2 | 119 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Erect Girders - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-10-29 08:00 | 2024-10-29 16:00 |  |  | 1 | 0 | 1 | 116 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A17110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Install SIP - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-10-30 08:00 | 2024-10-30 16:00 |  |  | 1 | 0 | 1 | 116 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A17120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Install Overhangs - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-10-31 08:00 | 2024-11-07 16:00 |  |  | 6 | 0 | 6 | 116 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Reinforce Deck - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-11-08 08:00 | 2024-11-08 16:00 |  |  | 1 | 0 | 1 | 116 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Place Deck - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-11-12 08:00 | 2024-11-12 16:00 |  |  | 1 | 0 | 1 | 116 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A17150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Cure Deck - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-11-13 08:00 | 2024-11-19 16:00 |  |  | 7 | 0 | 7 | 211 |  |  | CURE | CURE
A17160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Install Reinf Barrier - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-11-21 08:00 | 2024-11-21 16:00 |  |  | 1 | 0 | 1 | 119 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Strip Overhangs - Brg 100656 - Span 3 - R1 - P1.S2 | 2024-11-22 08:00 | 2024-11-25 16:00 |  |  | 2 | 0 | 2 | 119 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Excavate - Brg 100656 - Pier 2 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-04 16:00 |  |  | 1 | 0 | 1 | 117 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A17200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Drive Pile - Brg 100656 - Pier 2 - R1 - P1.S2 | 2024-10-07 08:00 | 2024-10-08 16:00 |  |  | 2 | 0 | 2 | 117 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A17210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | FRP Column - Brg 100656 - Pier 2 - R1 - P1.S2 | 2024-10-10 08:00 | 2024-10-10 16:00 |  |  | 1 | 0 | 1 | 117 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A17220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Cure/Strip Column - Brg 100656 - Pier 2 - R1 - P1.S2 | 2024-10-11 08:00 | 2024-10-17 16:00 |  |  | 7 | 0 | 7 | 207 |  |  | CURE | CURE
A17230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | FRP Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | 2024-10-18 08:00 | 2024-10-22 16:00 |  |  | 3 | 0 | 3 | 117 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A17240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Cure/Strip Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | 2024-10-23 08:00 | 2024-10-25 16:00 |  |  | 3 | 0 | 3 | 208 |  |  | CURE | CURE
A17250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Grading - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-15 08:00 | 2024-10-15 16:00 |  |  | 1 | 0 | 1 | 115 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A17270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Drive Pile - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-21 08:00 | 2024-10-21 16:00 |  |  | 1 | 0 | 1 | 115 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A17280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | FRP Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-24 08:00 | 2024-10-25 16:00 |  |  | 2 | 0 | 2 | 115 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A17290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Cure/Strip Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-26 08:00 | 2024-10-28 16:00 |  |  | 3 | 0 | 3 | 206 |  |  | CURE | CURE
A17300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Const MSE Wall & Bkfill - RW 3-1 / Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-22 08:00 | 2024-10-23 16:00 |  |  | 2 | 0 | 2 | 115 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A17330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Temp Wall or SOE - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-14 16:00 |  |  | 6 | 0 | 6 | 115 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A17340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Grading - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-15 08:00 | 2024-10-15 16:00 |  |  | 1 | 0 | 1 | 96 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A17360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Drive Pile - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-21 08:00 | 2024-10-21 16:00 |  |  | 1 | 0 | 1 | 96 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A17370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | FRP Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-24 08:00 | 2024-10-25 16:00 |  |  | 2 | 0 | 2 | 96 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A17380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Cure/Strip Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-26 08:00 | 2024-10-28 16:00 |  |  | 3 | 0 | 3 | 174 |  |  | CURE | CURE
A17390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Const MSE Wall & Bkfill - RW 3-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | 2024-10-22 08:00 | 2024-10-23 16:00 |  |  | 2 | 0 | 2 | 96 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A17410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Temp Wall or SOE - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-14 16:00 |  |  | 6 | 0 | 6 | 96 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A17420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.7 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Demo | Demo Barrier - Brg 100656 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-07 16:00 |  |  | 2 | 0 | 2 | 129 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A17430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Demo Brick tower - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-17 08:00 | 2024-10-18 16:00 |  |  | 2 | 0 | 2 | 115 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A17440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Demo Brick tower - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-17 08:00 | 2024-10-18 16:00 |  |  | 2 | 0 | 2 | 96 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A17450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 | R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Install Fiberglass Panel on Barrier - Brg 100656 - R1 - P1.S2 | 2024-12-02 08:00 | 2024-12-09 16:00 |  |  | 5 | 0 | 5 | 119 |  | Sub - Bridge Railing Crew | SUB.STRUCTURE.Bridge.Railing | STRUCTURE.Bridge.Railing
A17460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | FRP Brick Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-10-29 08:00 | 2024-11-12 16:00 |  |  | 10 | 0 | 10 | 96 |  | Bridge Crew - Combo | LANE.STRUCTURE.Bridge.All/Combo | STRUCTURE.Bridge.Column
A17470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.9 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Cure/Strip Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | 2024-11-13 08:00 | 2024-11-19 16:00 |  |  | 7 | 0 | 7 | 225 |  |  | CURE | CURE
A17480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | FRP Brick Column - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-10-29 08:00 | 2024-11-12 16:00 |  |  | 10 | 0 | 10 | 127 |  | Bridge Crew - Combo | LANE.STRUCTURE.Bridge.All/Combo | STRUCTURE.Bridge.Column
A17490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.8 | R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Cure/Strip Column - Brg 100656 - End Bent 1 - R1 - P1.S2 | 2024-11-13 08:00 | 2024-11-19 16:00 |  |  | 7 | 0 | 7 | 225 |  |  | CURE | CURE
A17500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening |  | 2025-02-20 16:00 |  |  | 0 | 0 | 0 | 94 | 71 |  | MS | MS
A17510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Excavate - Brg 100657 - Pier 1 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-04 16:00 |  |  | 1 | 0 | 1 | 122 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A17520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Drive Pile - Brg 100657 - Pier 1 - R1 - P1.S2 | 2024-10-07 08:00 | 2024-10-08 16:00 |  |  | 2 | 0 | 2 | 122 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A17530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | FRP Column - Brg 100657 - Pier 1 - R1 - P1.S2 | 2024-10-10 08:00 | 2024-10-11 16:00 |  |  | 2 | 0 | 2 | 122 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A17540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Cure/Strip Column - Brg 100657 - Pier 1 - R1 - P1.S2 | 2024-10-12 08:00 | 2024-10-18 16:00 |  |  | 7 | 0 | 7 | 216 |  |  | CURE | CURE
A17550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | FRP Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | 2024-10-21 08:00 | 2024-10-21 16:00 |  |  | 1 | 0 | 1 | 123 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A17560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Cure/Strip Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | 2024-10-22 08:00 | 2024-10-24 16:00 |  |  | 3 | 0 | 3 | 215 |  |  | CURE | CURE
A17570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Erect Girders - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-01-13 08:00 | 2025-01-13 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A17580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Install SIP - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-01-14 08:00 | 2025-01-14 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A17590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Install Overhangs - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-01-16 08:00 | 2025-01-21 16:00 |  |  | 3 | 0 | 3 | 82 | 71 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Reinforce Deck - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-01-23 08:00 | 2025-01-23 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Place Deck - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-01-24 08:00 | 2025-01-24 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A17620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Cure Deck - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-01-25 08:00 | 2025-01-31 16:00 |  |  | 7 | 0 | 7 | 139 | 82 |  | CURE | CURE
A17630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Install Reinf Barrier - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-02-03 08:00 | 2025-02-03 16:00 |  |  | 1 | 0 | 1 | 86 | 82 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Strip Overhangs - Brg 100657 - Span 1 - R1 - P1.S2 | 2025-02-04 08:00 | 2025-02-04 16:00 |  |  | 1 | 0 | 1 | 86 | 82 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | FRPS Approach Slab 1 - Brg 100657 - R1 - P1.S2 | 2025-01-27 08:00 | 2025-01-30 16:00 |  |  | 3 | 0 | 3 | 82 | 71 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A17670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | FRPS Approach Slab 2 - Brg 100657 - R1 - P1.S2 | 2025-01-27 08:00 | 2025-01-30 16:00 |  |  | 3 | 0 | 3 | 82 | 73 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A17680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Slip Barrier - Brg 100657 - R1 - P1.S2 | 2025-02-05 08:00 | 2025-02-05 16:00 |  |  | 1 | 0 | 1 | 86 | 82 | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A17700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Groove Deck - Brg 100657 - R1 - P1.S2 | 2025-02-03 08:00 | 2025-02-03 16:00 |  |  | 1 | 0 | 1 | 92 | 92 | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A17710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Perm Striping - Brg 100657 - R1 - P1.S2 | 2025-02-13 08:00 | 2025-02-13 16:00 |  |  | 1 | 0 | 1 | 86 | 82 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A17720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Erect Girders - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-10-25 08:00 | 2024-10-25 16:00 |  |  | 1 | 0 | 1 | 125 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A17730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Install SIP - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-10-28 08:00 | 2024-10-28 16:00 |  |  | 1 | 0 | 1 | 125 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A17740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Install Overhangs - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-10-29 08:00 | 2024-10-31 16:00 |  |  | 3 | 0 | 3 | 125 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Reinforce Deck - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-11-01 08:00 | 2024-11-01 16:00 |  |  | 1 | 0 | 1 | 125 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Place Deck - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-11-04 08:00 | 2024-11-04 16:00 |  |  | 1 | 0 | 1 | 125 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A17770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Cure Deck - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-11-05 08:00 | 2024-11-11 16:00 |  |  | 7 | 0 | 7 | 220 |  |  | CURE | CURE
A17780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Install Reinf Barrier - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-11-12 08:00 | 2024-11-12 16:00 |  |  | 1 | 0 | 1 | 125 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Strip Overhangs - Brg 100657 - Span 2 - R1 - P1.S2 | 2024-11-14 08:00 | 2024-11-14 16:00 |  |  | 1 | 0 | 1 | 125 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Erect Girders - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-01-13 08:00 | 2025-01-13 16:00 |  |  | 1 | 0 | 1 | 82 | 73 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A17820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Install SIP - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-01-14 08:00 | 2025-01-14 16:00 |  |  | 1 | 0 | 1 | 82 | 73 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A17830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Install Overhangs - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-01-16 08:00 | 2025-01-21 16:00 |  |  | 3 | 0 | 3 | 82 | 73 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Reinforce Deck - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-01-23 08:00 | 2025-01-23 16:00 |  |  | 1 | 0 | 1 | 82 | 73 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Place Deck - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-01-24 08:00 | 2025-01-24 16:00 |  |  | 1 | 0 | 1 | 82 | 73 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A17860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Cure Deck - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-01-25 08:00 | 2025-01-31 16:00 |  |  | 7 | 0 | 7 | 139 | 83 |  | CURE | CURE
A17870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Install Reinf Barrier - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-02-03 08:00 | 2025-02-03 16:00 |  |  | 1 | 0 | 1 | 86 | 83 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A17880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Strip Overhangs - Brg 100657 - Span 3 - R1 - P1.S2 | 2025-02-04 08:00 | 2025-02-04 16:00 |  |  | 1 | 0 | 1 | 86 | 83 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A17900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Excavate - Brg 100657 - Pier 2 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-04 16:00 |  |  | 1 | 0 | 1 | 122 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A17910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Drive Pile - Brg 100657 - Pier 2 - R1 - P1.S2 | 2024-10-07 08:00 | 2024-10-08 16:00 |  |  | 2 | 0 | 2 | 122 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A17920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | FRP Column - Brg 100657 - Pier 2 - R1 - P1.S2 | 2024-10-10 08:00 | 2024-10-11 16:00 |  |  | 2 | 0 | 2 | 122 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A17930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Cure/Strip Column - Brg 100657 - Pier 2 - R1 - P1.S2 | 2024-10-12 08:00 | 2024-10-18 16:00 |  |  | 7 | 0 | 7 | 216 |  |  | CURE | CURE
A17940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | FRP Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | 2024-10-21 08:00 | 2024-10-21 16:00 |  |  | 1 | 0 | 1 | 123 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A17950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Cure/Strip Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | 2024-10-22 08:00 | 2024-10-24 16:00 |  |  | 3 | 0 | 3 | 215 |  |  | CURE | CURE
A17960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Grading - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2024-11-22 08:00 | 2024-11-22 16:00 |  |  | 1 | 0 | 1 | 96 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A17980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Drive Pile - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2024-12-02 08:00 | 2024-12-02 16:00 |  |  | 1 | 0 | 1 | 96 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A17990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | FRP Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2025-01-07 08:00 | 2025-01-07 16:00 |  |  | 1 | 0 | 1 | 84 | 71 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A18000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Cure/Strip Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2025-01-08 08:00 | 2025-01-10 16:00 |  |  | 3 | 0 | 3 | 137 | 71 |  | CURE | CURE
A18010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Const MSE Wall & Bkfill - RW 4-1 / Brg 100657 - End Bent 1 - R1 - P1.S2 | 2025-01-03 08:00 | 2025-01-06 16:00 |  |  | 2 | 0 | 2 | 84 | 71 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A18030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Temp Wall or SOE - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2024-11-14 08:00 | 2024-11-21 16:00 |  |  | 5 | 0 | 5 | 96 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A18040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Grading - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2024-10-14 08:00 | 2024-10-14 16:00 |  |  | 1 | 0 | 1 | 120 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A18060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Drive Pile - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2024-10-18 08:00 | 2024-10-18 16:00 |  |  | 1 | 0 | 1 | 120 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A18070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | FRP Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2025-01-07 08:00 | 2025-01-08 16:00 |  |  | 2 | 0 | 2 | 83 | 73 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A18080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Cure/Strip Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2025-01-09 08:00 | 2025-01-11 16:00 |  |  | 3 | 0 | 3 | 136 | 73 |  | CURE | CURE
A18090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Const MSE Wall & Bkfill - RW 4-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | 2025-01-03 08:00 | 2025-01-06 16:00 |  |  | 2 | 0 | 2 | 83 | 73 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A18110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Temp Wall or SOE - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-11 16:00 |  |  | 5 | 0 | 5 | 120 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A18120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.7 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Demo | Demo Barrier - Brg 100657 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-07 16:00 |  |  | 2 | 0 | 2 | 132 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A18130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Demo Brick tower - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2024-11-25 08:00 | 2024-11-26 16:00 |  |  | 2 | 0 | 2 | 96 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A18140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Demo Brick tower - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2024-10-15 08:00 | 2024-10-17 16:00 |  |  | 2 | 0 | 2 | 120 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A18150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 | R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Install Fiberglass Panel on Barrier - Brg 100657 - R1 - P1.S2 | 2025-02-06 08:00 | 2025-02-13 16:00 |  |  | 5 | 0 | 5 | 86 | 82 | Sub - Bridge Railing Crew | SUB.STRUCTURE.Bridge.Railing | STRUCTURE.Bridge.Railing
A18160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | FRP Brick Column - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2025-01-13 08:00 | 2025-01-30 16:00 |  |  | 10 | 0 | 10 | 90 |  | Bridge Crew - Combo | LANE.STRUCTURE.Bridge.All/Combo | STRUCTURE.Bridge.Column
A18170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.11 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Cure/Strip Column - Brg 100657 - End Bent 2 - R1 - P1.S2 | 2025-01-31 08:00 | 2025-02-06 16:00 |  |  | 7 | 0 | 7 | 146 |  |  | CURE | CURE
A18180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | FRP Brick Column - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2025-01-13 08:00 | 2025-01-30 16:00 |  |  | 10 | 0 | 10 | 90 |  | Bridge Crew - Combo | LANE.STRUCTURE.Bridge.All/Combo | STRUCTURE.Bridge.Column
A18190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.10 | R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Cure/Strip Column - Brg 100657 - End Bent 1 - R1 - P1.S2 | 2025-01-31 08:00 | 2025-02-06 16:00 |  |  | 7 | 0 | 7 | 146 |  |  | CURE | CURE
A18200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-01-27 08:00 | 2025-01-27 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A18210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Stabilization - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-01-28 08:00 | 2025-02-03 16:00 |  |  | 4 | 0 | 4 | 82 | 71 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A18240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Asphalt Base - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-02-04 08:00 | 2025-02-05 16:00 |  |  | 2 | 0 | 2 | 82 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A18250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Concrete Pav - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-02-06 08:00 | 2025-02-13 16:00 |  |  | 5 | 0 | 5 | 82 | 71 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A18260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Edge Drain - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-02-14 08:00 | 2025-02-14 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A18270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Shoulder GAB - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-02-17 08:00 | 2025-02-18 16:00 |  |  | 2 | 0 | 2 | 82 | 71 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A18280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.5 | R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Asphalt Shoulder - I-4 Sta 250 to 266 - R1 - P1.S2 | 2025-02-20 08:00 | 2025-02-20 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A18320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Place Brick Sidewalk - Right 14th & 15th St under I-4 - R1 - P1.S1 | 2023-07-24 08:00 | 2023-08-14 16:00 |  |  | 15 | 0 | 15 | 325 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A18290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Right 14th &15th St under I-4 - R1 - P1.S1 | 2023-06-30 08:00 | 2023-06-30 16:00 |  |  | 1 | 0 | 1 | 325 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Flatwork Demo
A18300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Right 14th & 15th St under I-4 - R1 - P1.S1 | 2023-07-14 08:00 | 2023-07-21 16:00 |  |  | 5 | 0 | 5 | 325 |  | Sub - Concrete Flatwork Crew | SUB.FLATWRK | FLATWORK.Ditch Pave
A18310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Const Gravity Wall - Right 14th & 15th St under I-4 - R1 - P1.S1 | 2023-07-03 08:00 | 2023-07-13 16:00 |  |  | 7 | 0 | 7 | 325 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A18330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.1.2 | R1 - Ph0 - Temp Pavement | Place GAB - 13th Ave Temp Pav - R1 - P0 | 2023-09-06 08:00 | 2023-09-06 16:00 |  |  | 1 | 0 | 1 | 216 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A18340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.7 | R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Grading - 13th Ave - Right Sta 24 to 40 - R1 - P1.S2 | 2024-09-27 08:00 | 2024-09-27 16:00 |  |  | 1 | 0 | 1 | 156 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A18350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.7 | R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place Stabilization - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 2024-09-30 08:00 | 2024-09-30 16:00 |  |  | 1 | 0 | 1 | 156 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A18360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.7 | R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place GAB - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 2024-10-01 08:00 | 2024-10-01 16:00 |  |  | 1 | 0 | 1 | 156 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A18370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.7 | R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place Curb - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 2024-10-02 08:00 | 2024-10-03 16:00 |  |  | 2 | 0 | 2 | 156 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A18390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.7 | R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place Asphalt Surface - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 2024-10-04 08:00 | 2024-10-04 16:00 |  |  | 1 | 0 | 1 | 156 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A18400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Shift Traffic - 13th Ave Left - R1 - P1.S2 | 2024-09-13 08:00 | 2024-09-13 16:00 |  |  | 1 | 0 | 1 | 146 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A18410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.4.1 | R1 - Ph1, Stg2 - MOT | Install Temp Barrier -13th Ave - R1 - P1.S2 | 2024-09-16 08:00 | 2024-09-26 16:00 |  |  | 7 | 0 | 7 | 146 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A19250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure |  | 2025-06-02 16:00 |  |  | 0 | 0 | 0 | 98 | 71 |  | MS | MS
A20200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.4 | R1 - Ph2, Stg3, Step1 - MOT | Install MOT - Ramp NE Left - R1 - P2.S3 Step 1 | 2025-11-05 08:00 | 2025-11-05 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A20210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.4 | R1 - Ph2, Stg3, Step1 - MOT | Shift Traffic - Ramp NE Left - R1 - P2.S3 Step 1 | 2025-11-06 08:00 | 2025-11-06 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A20270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.5 | R1 - Ph2, Stg3, Step2 - MOT | Shift Traffic - Ramp NE Right - R1 - P2.S3 Step 2 | 2025-12-04 08:00 | 2025-12-04 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A20220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.6 | R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Grading - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 2025-11-07 08:00 | 2025-11-07 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A20230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.6 | R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Place Stabilization - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 2025-11-10 08:00 | 2025-11-21 16:00 |  |  | 7 | 0 | 7 | 81 | 71 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A20250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.6 | R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Place Asphalt - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 2025-12-01 08:00 | 2025-12-01 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A20260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.6 | R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Temp Striping - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 2025-12-02 08:00 | 2025-12-02 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Temp
A20240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.6 | R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Place GAB - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 2025-11-24 08:00 | 2025-11-25 16:00 |  |  | 2 | 0 | 2 | 81 | 71 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A20290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right |  | 2025-11-04 16:00 |  |  | 0 | 0 | 0 | 108 | 71 |  | MS | MS
A20300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left |  | 2026-04-16 16:00 |  |  | 0 | 0 | 0 | 95 | 71 |  | MS | MS
A20310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.10 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | Demo Superstructure - Brg 100864 - R1 - P2.S3 - left | 2025-12-05 08:00 | 2025-12-15 16:00 |  |  | 6 | 0 | 6 | 81 | 71 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A20320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.10 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | Demo Substructure - Brg 100864 - R1 - P2.S3 - left | 2025-12-16 08:00 | 2026-01-09 16:00 |  |  | 10 | 0 | 10 | 81 | 71 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A20340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.1 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Grading - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 2026-01-16 08:00 | 2026-01-16 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A20360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.1 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 2026-01-20 08:00 | 2026-01-23 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A20390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.1 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | FRP Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 2026-01-29 08:00 | 2026-02-04 16:00 |  |  | 5 | 0 | 5 | 97 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A20400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.1 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Cure/Strip Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 2026-02-05 08:00 | 2026-02-07 16:00 |  |  | 3 | 0 | 3 | 159 |  |  | CURE | CURE
A20370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.1 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 2026-01-26 08:00 | 2026-01-27 16:00 |  |  | 2 | 0 | 2 | 81 | 71 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A20330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.1 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Temp Wall or SOE - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 2026-01-12 08:00 | 2026-01-15 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A20420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.2 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Grading - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 2026-01-16 08:00 | 2026-01-16 16:00 |  |  | 1 | 0 | 1 | 93 | 99 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A20440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.2 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 2026-01-20 08:00 | 2026-01-22 16:00 |  |  | 2 | 0 | 2 | 93 | 99 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A20470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.2 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | FRP Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 2026-01-29 08:00 | 2026-02-04 16:00 |  |  | 5 | 0 | 5 | 97 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A20480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.2 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Cure/Strip Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 2026-02-05 08:00 | 2026-02-07 16:00 |  |  | 3 | 0 | 3 | 159 |  |  | CURE | CURE
A20450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.2 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 2026-01-23 08:00 | 2026-01-27 16:00 |  |  | 3 | 0 | 3 | 93 | 99 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A20410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.2 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Temp Wall or SOE - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 2026-01-12 08:00 | 2026-01-15 16:00 |  |  | 3 | 0 | 3 | 93 | 99 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A20580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 97 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A20590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Install SIP - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 97 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A20600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Install Overhangs - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-02-12 08:00 | 2026-02-24 16:00 |  |  | 8 | 0 | 8 | 97 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A20610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Reinforce Deck - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-02-26 08:00 | 2026-03-02 16:00 |  |  | 3 | 0 | 3 | 97 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A20620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Place Deck - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-03-03 08:00 | 2026-03-03 16:00 |  |  | 1 | 0 | 1 | 97 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A20630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-03-04 08:00 | 2026-03-10 16:00 |  |  | 7 | 0 | 7 | 156 |  |  | CURE | CURE
A20640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Install Reinf Barrier - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-03-12 08:00 | 2026-03-13 16:00 |  |  | 2 | 0 | 2 | 96 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A20650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Strip Overhangs - Brg 100864 - Span 1 - R1 - P2.S3 | 2026-03-16 08:00 | 2026-03-17 16:00 |  |  | 2 | 0 | 2 | 96 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A20670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | FRPS Approach Slab 1 - Brg 100864 - R1 - P2.S3 | 2026-03-04 08:00 | 2026-03-12 16:00 |  |  | 6 | 0 | 6 | 100 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A20680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | FRPS Approach Slab 2 - Brg 100864 - R1 - P2.S3 | 2026-03-04 08:00 | 2026-03-10 16:00 |  |  | 5 | 0 | 5 | 101 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A20690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Slip Barrier - Brg 100864 - R1 - P2.S3 | 2026-03-19 08:00 | 2026-03-19 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A20700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Grind Deck - Brg 100864 - R1 - P2.S3 | 2026-03-20 08:00 | 2026-03-20 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Diamond Grind Pavement Crew | SUB.CONCRETE.GRIND | CONCRETE PVMT.Diamond Grind
A20710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Groove Deck - Brg 100864 - R1 - P2.S3 | 2026-03-23 08:00 | 2026-03-23 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A20720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 | R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Perm Striping - Brg 100864 - R1 - P2.S3 | 2026-03-24 08:00 | 2026-03-24 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A21010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-02-10 08:00 | 2026-02-20 16:00 |  |  | 7 | 0 | 7 | 97 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A21050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-03-30 08:00 | 2026-04-03 16:00 |  |  | 5 | 0 | 5 | 81 | 71 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A21040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-03-23 08:00 | 2026-03-27 16:00 |  |  | 4 | 0 | 4 | 81 | 71 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A21000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-01-29 08:00 | 2026-02-09 16:00 |  |  | 8 | 0 | 8 | 81 | 71 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A21030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-03-20 08:00 | 2026-03-20 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A21060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Asphalt Base - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-04-06 08:00 | 2026-04-06 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A21070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Concrete Pav - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-04-07 08:00 | 2026-04-09 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A21080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-04-10 08:00 | 2026-04-13 16:00 |  |  | 2 | 0 | 2 | 81 | 71 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A21090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Shoulder GAB - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-04-14 08:00 | 2026-04-14 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A21100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Asphalt Shoulder - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 2026-04-16 08:00 | 2026-04-16 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A21120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 1 | 2025-09-15 08:00 | 2025-10-09 16:00 |  |  | 16 | 0 | 16 | 84 | 77 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A21150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Wall Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-02-24 08:00 | 2026-03-16 16:00 |  |  | 13 | 0 | 13 | 93 | 99 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A21140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Junction Slab - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-02-05 08:00 | 2026-02-23 16:00 |  |  | 11 | 0 | 11 | 93 | 99 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A21110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-01-29 08:00 | 2026-02-03 16:00 |  |  | 4 | 0 | 4 | 93 | 99 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A21130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Stabilization - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-02-04 08:00 | 2026-02-04 16:00 |  |  | 1 | 0 | 1 | 93 | 99 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A21160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Asphalt Base - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-03-17 08:00 | 2026-03-17 16:00 |  |  | 1 | 0 | 1 | 93 | 99 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A21170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Concrete Pav - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-03-19 08:00 | 2026-03-24 16:00 |  |  | 4 | 0 | 4 | 93 | 99 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A21180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-03-26 08:00 | 2026-03-26 16:00 |  |  | 1 | 0 | 1 | 93 | 99 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A21190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Shoulder GAB - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-03-27 08:00 | 2026-03-27 16:00 |  |  | 1 | 0 | 1 | 93 | 99 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A21200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.8 | R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Asphalt Shoulder - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 2026-03-30 08:00 | 2026-03-30 16:00 |  |  | 1 | 0 | 1 | 93 | 99 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A21220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.9 | R1 - Ph2, Stg3 - NE Shared Use Path | Grading - NE Shared Use Path - R1 - P2.S3 | 2025-10-10 08:00 | 2025-10-13 16:00 |  |  | 2 | 0 | 2 | 146 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A21230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.9 | R1 - Ph2, Stg3 - NE Shared Use Path | Place Stabilization - NE Shared Use Path - R1 - P2.S3 | 2025-12-08 08:00 | 2026-01-08 16:00 |  |  | 14 | 0 | 14 | 133 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A21210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.9 | R1 - Ph2, Stg3 - NE Shared Use Path | Place Asphalt - NE Shared Use Path - R1 - P2.S3 | 2026-01-22 08:00 | 2026-01-22 16:00 |  |  | 1 | 0 | 1 | 133 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A21240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.9 | R1 - Ph2, Stg3 - NE Shared Use Path | Install DRG S-4A5 to S-4B5 - NE Shared UsePath - R1 - P2.S3 | 2025-11-03 08:00 | 2025-12-05 16:00 |  |  | 18 | 0 | 18 | 133 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A21250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.9 | R1 - Ph2, Stg3 - NE Shared Use Path | Place GAB - NE Shared Use Path - R1 - P2.S3 | 2026-01-09 08:00 | 2026-01-12 16:00 |  |  | 2 | 0 | 2 | 133 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A21260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.9 | R1 - Ph2, Stg3 - NE Shared Use Path | Place Curb - NE Shared Use Path - R1 - P2.S3 | 2026-01-13 08:00 | 2026-01-20 16:00 |  |  | 4 | 0 | 4 | 133 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A21280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.5 | R1 - Ph2, Stg2 - MOT | Shift Traffic - Ramp NE Left - R1 - P2.S2 | 2025-06-03 08:00 | 2025-06-03 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A21300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.10 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | Demo Superstructure - Brg 100864 - R1 - P2.S2 - right | 2025-06-04 08:00 | 2025-06-12 16:00 |  |  | 6 | 0 | 6 | 81 | 71 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A21310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.10 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | Demo Substructure - Brg 100864 - R1 - P2.S2 - right | 2025-06-13 08:00 | 2025-06-30 16:00 |  |  | 10 | 0 | 10 | 81 | 71 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A21320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.1 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Grading - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 2025-07-03 08:00 | 2025-07-03 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A21340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.1 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 2025-07-07 08:00 | 2025-07-10 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A21350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.1 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | FRP Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 2025-07-17 08:00 | 2025-07-28 16:00 |  |  | 7 | 0 | 7 | 112 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A21360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.1 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Cure/Strip Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 2025-07-29 08:00 | 2025-07-31 16:00 |  |  | 3 | 0 | 3 | 200 |  |  | CURE | CURE
A21370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.1 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 2025-07-11 08:00 | 2025-07-15 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A21380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.1 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Temp Wall or SOE - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 2025-07-01 08:00 | 2025-07-02 16:00 |  |  | 2 | 0 | 2 | 81 | 71 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A21400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.2 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Grading - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 2025-07-03 08:00 | 2025-07-03 16:00 |  |  | 1 | 0 | 1 | 115 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A21420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.2 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 2025-07-07 08:00 | 2025-07-10 16:00 |  |  | 3 | 0 | 3 | 115 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A21430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.2 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | FRP Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 2025-07-17 08:00 | 2025-07-22 16:00 |  |  | 4 | 0 | 4 | 115 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A21440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.2 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Cure/Strip Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 2025-07-23 08:00 | 2025-07-25 16:00 |  |  | 3 | 0 | 3 | 206 |  |  | CURE | CURE
A21450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.2 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 2025-07-11 08:00 | 2025-07-15 16:00 |  |  | 3 | 0 | 3 | 115 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A21460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.2 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Temp Wall or SOE - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 2025-07-01 08:00 | 2025-07-02 16:00 |  |  | 2 | 0 | 2 | 115 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A21570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-08-01 08:00 | 2025-08-01 16:00 |  |  | 1 | 0 | 1 | 110 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A21580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Install SIP - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-08-04 08:00 | 2025-08-05 16:00 |  |  | 2 | 0 | 2 | 110 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A21590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Install Overhangs - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-08-06 08:00 | 2025-08-18 16:00 |  |  | 8 | 0 | 8 | 110 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A21600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Reinforce Deck - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-08-19 08:00 | 2025-08-26 16:00 |  |  | 5 | 0 | 5 | 110 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A21610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Place Deck - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-08-28 08:00 | 2025-08-28 16:00 |  |  | 1 | 0 | 1 | 110 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A21620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-08-29 08:00 | 2025-09-04 16:00 |  |  | 7 | 0 | 7 | 200 |  |  | CURE | CURE
A21630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Install Reinf Barrier - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-09-05 08:00 | 2025-09-08 16:00 |  |  | 2 | 0 | 2 | 111 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A21640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Strip Overhangs - Brg 100864 - Span 1 - R1 - P2.S2 | 2025-09-09 08:00 | 2025-09-11 16:00 |  |  | 2 | 0 | 2 | 111 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A21660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | FRPS Approach Slab 1 - Brg 100864 - R1 - P2.S2 | 2025-09-02 08:00 | 2025-09-05 16:00 |  |  | 4 | 0 | 4 | 115 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A21670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | FRPS Approach Slab 2 - Brg 100864 - R1 - P2.S2 | 2025-09-02 08:00 | 2025-09-05 16:00 |  |  | 4 | 0 | 4 | 115 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A21680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Slip Barrier - Brg 100864 - R1 - P2.S2 | 2025-09-12 08:00 | 2025-09-12 16:00 |  |  | 1 | 0 | 1 | 111 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A21690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Grind Deck - Brg 100864 - R1 - P2.S2 | 2025-09-15 08:00 | 2025-09-15 16:00 |  |  | 1 | 0 | 1 | 111 |  | Sub - Diamond Grind Pavement Crew | SUB.CONCRETE.GRIND | CONCRETE PVMT.Diamond Grind
A21700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Groove Deck - Brg 100864 - R1 - P2.S2 | 2025-09-16 08:00 | 2025-09-16 16:00 |  |  | 1 | 0 | 1 | 111 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A21710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 | R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Perm Striping - Brg 100864 - R1 - P2.S2 | 2025-09-18 08:00 | 2025-09-18 16:00 |  |  | 1 | 0 | 1 | 111 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A21990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-07-30 08:00 | 2025-08-14 16:00 |  |  | 11 | 0 | 11 | 93 | 100 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A22000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-09-23 08:00 | 2025-10-22 16:00 |  |  | 19 | 0 | 19 | 81 | 71 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A22010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-09-09 08:00 | 2025-10-06 16:00 |  |  | 17 | 0 | 17 | 81 | 71 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A22020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-07-17 08:00 | 2025-07-29 16:00 |  |  | 8 | 0 | 8 | 81 | 71 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A22030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-09-08 08:00 | 2025-09-08 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A22040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Asphalt Base - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-10-23 08:00 | 2025-10-23 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Concrete Pav - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-10-24 08:00 | 2025-10-28 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A22060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-10-29 08:00 | 2025-10-30 16:00 |  |  | 2 | 0 | 2 | 81 | 71 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A22070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Shoulder GAB - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-10-31 08:00 | 2025-10-31 16:00 |  |  | 1 | 0 | 1 | 82 | 74 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A22080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Asphalt Shoulder - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-11-03 08:00 | 2025-11-03 16:00 |  |  | 1 | 0 | 1 | 82 | 74 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place 3-Pour Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-10-10 08:00 | 2025-10-17 16:00 |  |  | 5 | 0 | 5 | 84 | 77 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A22120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-09-08 08:00 | 2025-09-12 16:00 |  |  | 4 | 0 | 4 | 84 | 77 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A22130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Stabilization - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-10-20 08:00 | 2025-10-20 16:00 |  |  | 1 | 0 | 1 | 84 | 77 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A22140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Asphalt Base - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-10-21 08:00 | 2025-10-21 16:00 |  |  | 1 | 0 | 1 | 84 | 77 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Concrete Pav - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-10-22 08:00 | 2025-10-27 16:00 |  |  | 4 | 0 | 4 | 84 | 77 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A22160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-10-31 08:00 | 2025-10-31 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A22170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Shoulder GAB - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-11-03 08:00 | 2025-11-03 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A22180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Asphalt Shoulder - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 2025-11-04 08:00 | 2025-11-04 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.9 | R1 - Phase 3 - Signing / Milling / Pavement Markings | Mill / Resurface Asphalt - R1 - P3 | 2026-04-17 08:00 | 2026-04-24 16:00 |  |  | 5 | 0 | 5 | 81 | 71 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 3 - R1 - Resurface Signs Markings |  | 2026-05-18 16:00 |  |  | 0 | 0 | 0 | 98 | 71 |  | MS | MS
A22210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.9 | R1 - Phase 3 - Signing / Milling / Pavement Markings | Install Perm. Signs - R1 - P3 | 2026-03-17 08:00 | 2026-04-16 16:00 |  |  | 20 | 0 | 20 | 101 |  | Sub - Signing Crew | SUB.SIGN | SIGN.Overhead Sign
A22220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.9 | R1 - Phase 3 - Signing / Milling / Pavement Markings | Perm Striping - R1 - P3 | 2026-04-27 08:00 | 2026-05-18 16:00 |  |  | 15 | 0 | 15 | 81 | 71 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A22230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.3 | R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place GAB - Pond SMF 4A Shared Use Path - R2 - P0 | 2024-09-04 08:00 | 2024-09-09 16:00 |  |  | 4 | 0 | 4 | 353 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
LoE160 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 2 Stage 3 - Up-St Ramp NE Left Construction [LoE] | 2025-11-05 08:00 | 2026-04-16 16:00 |  |  | 163 | 0 | 163 | 133 |  |  | LOE | LOE
LoE170 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 3 - Resurface / Signs / Markings [LoE] | 2026-04-17 08:00 | 2026-05-18 16:00 |  |  | 32 | 0 | 32 | 136 |  |  | LOE | LOE
A22240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.4 | R2 - Milestones | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage |  | 2024-09-24 16:00 |  |  | 0 | 0 | 0 | 437 |  |  | MS | MS
A22250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.4 | R2 - Milestones | Finish Phase 1 - R2 - Left Ramp EN Construction |  | 2025-10-30 16:00 |  |  | 0 | 0 | 0 | 266 |  |  | MS | MS
A22260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.5.4 | R2 - Ph0 - MOT | Install MOT - Ramp EN /I-4 - R2 - P1.S1 | 2024-07-25 08:00 | 2024-07-25 16:00 |  |  | 1 | 0 | 1 | 357 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A22270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.5.4 | R2 - Ph0 - MOT | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | 2024-07-26 08:00 | 2024-07-26 16:00 |  |  | 1 | 0 | 1 | 357 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A22280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.3 | R2 - Ph2, Stp2 - MOT | Shift Traffic - Ramp EN Left - R2 - P2 Stp2 | 2025-10-31 08:00 | 2025-10-31 16:00 |  |  | 1 | 0 | 1 | 216 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A22320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.5.2 | R2 - Ph0 - Ramp EN, I-4 WB - Temp Pavement - Sta. 82 to 95 | Place Temp Asphalt - Ramp EN /I-4 Sta 91 to 101 - R2 - P1 | 2024-07-29 08:00 | 2024-07-29 16:00 |  |  | 1 | 0 | 1 | 357 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.5.2 | R2 - Ph0 - Ramp EN, I-4 WB - Temp Pavement - Sta. 82 to 95 | Temp Striping - Ramp EN /I-4 Sta 91 to 101 - R2 - P1 | 2024-07-30 08:00 | 2024-07-30 16:00 |  |  | 1 | 0 | 1 | 357 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Temp
A22350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.5 | R2 - Ph2, Stp3 - MOT | Shift Traffic - I-4 Right; I-275 Traffic Right - R1 - P2 | 2025-11-05 08:00 | 2025-11-05 16:00 |  |  | 1 | 0 | 1 | 223 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A22410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.1 | R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Grading - Ramp EN /I-4 - R2 - P2 | 2025-11-03 08:00 | 2025-11-03 16:00 |  |  | 1 | 0 | 1 | 216 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A22420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.1 | R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place Stabilization - Ramp EN / I-4 - R2 - P2 | 2025-11-06 08:00 | 2025-11-10 16:00 |  |  | 3 | 0 | 3 | 216 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A22430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.1 | R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place Shoulder GAB - Ramp EN /I-4 - R2 - P2 | 2025-11-13 08:00 | 2025-11-13 16:00 |  |  | 1 | 0 | 1 | 216 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A22440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.1 | R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place Asphalt Shoulder - Ramp EN /I-4 - R2 - P2 | 2025-11-14 08:00 | 2025-11-14 16:00 |  |  | 1 | 0 | 1 | 216 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.1 | R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Install Guardrail - Ramp EN /I-4 - R2 - P2 | 2025-11-17 08:00 | 2025-11-18 16:00 |  |  | 2 | 0 | 2 | 216 |  | Sub - Guardrail Crew | SUB.GRAIL | Guardrail
A22460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.1 | R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place 3-Pour Barrier - Ramp EN / I-4 - R2 - P2 | 2025-11-04 08:00 | 2025-11-05 16:00 |  |  | 2 | 0 | 2 | 216 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A22470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.1.5 | R2 - Ph2, Stp3 - MOT | Remove MOT - I-4 WB & I-275 NB - R2 - P2 | 2025-11-03 08:00 | 2025-11-04 16:00 |  |  | 2 | 0 | 2 | 223 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A22480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.6 | R2 - Ph1 - Ramp EN MOT | Shift Traffic - Ramp EN Left - R2 - P1 | 2024-08-01 08:00 | 2024-08-01 16:00 |  |  | 1 | 0 | 1 | 357 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A22490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.6 | R2 - Ph1 - Ramp EN MOT | Install Temp Barrier - Ramp EN - R2 - P1 | 2024-08-02 08:00 | 2024-08-19 16:00 |  |  | 11 | 0 | 11 | 357 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A22520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.2 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Grading - Brg 100650 - End Bent 1 - R2 - P1 | 2024-08-23 08:00 | 2024-08-23 16:00 |  |  | 1 | 0 | 1 | 361 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A22540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.2 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Drive Pile - Brg 100650 - End Bent 1 - R2 - P1 | 2025-03-13 08:00 | 2025-03-13 16:00 |  |  | 1 | 0 | 1 | 252 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A22550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.2 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | FRP Abt Cap - Brg 100650 - End Bent 1 - R2 - P1 | 2025-03-14 08:00 | 2025-03-17 16:00 |  |  | 2 | 0 | 2 | 338 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A22560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.2 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Cure/Strip Abt Cap - Brg 100650 - End Bent 1 - R2 - P1 | 2025-03-18 08:00 | 2025-03-20 16:00 |  |  | 3 | 0 | 3 | 570 |  |  | CURE | CURE
A22580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.2 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Temp Wall or SOE - Brg 100650 - End Bent 1 - R2 - P1 | 2024-08-20 08:00 | 2024-08-22 16:00 |  |  | 2 | 0 | 2 | 361 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A22600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Excavate - Brg 100650 - Pier 1 - R2 - P1 | 2024-09-03 08:00 | 2024-09-03 16:00 |  |  | 1 | 0 | 1 | 357 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A22620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Drive Pile - Brg 100650 - Pier 1 - R2 - P1 | 2025-03-13 08:00 | 2025-03-18 16:00 |  |  | 4 | 0 | 4 | 316 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A22630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | FRP Footing - Brg 100650 - Pier 1 - R2 - P1 | 2025-03-20 08:00 | 2025-03-24 16:00 |  |  | 3 | 0 | 3 | 316 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A22640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Cure/Strip Footing - Brg 100650 - Pier 1 - R2 - P1 | 2025-03-25 08:00 | 2025-03-31 16:00 |  |  | 7 | 0 | 7 | 534 |  |  | CURE | CURE
A22650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | FRP Column - Brg 100650 - Pier 1 - R2 - P1 | 2025-04-01 08:00 | 2025-04-02 16:00 |  |  | 2 | 0 | 2 | 315 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A22660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Cure/Strip Column - Brg 100650 - Pier 1 - R2 - P1 | 2025-04-03 08:00 | 2025-04-09 16:00 |  |  | 7 | 0 | 7 | 536 |  |  | CURE | CURE
A22670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | FRP Cap - Brg 100650 - Pier 1 - R2 - P1 | 2025-04-10 08:00 | 2025-04-15 16:00 |  |  | 4 | 0 | 4 | 314 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A22680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Cure/Strip Cap - Brg 100650 - Pier 1 - R2 - P1 | 2025-04-16 08:00 | 2025-04-18 16:00 |  |  | 3 | 0 | 3 | 536 |  |  | CURE | CURE
A22690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Erect Girders - Brg 100650 - Span 1 - R2 - P1 | 2025-04-21 08:00 | 2025-04-21 16:00 |  |  | 1 | 0 | 1 | 317 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A22700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Install SIP - Brg 100650 - Span 1 - R2 - P1 | 2025-04-22 08:00 | 2025-04-22 16:00 |  |  | 1 | 0 | 1 | 317 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A22710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Install Overhangs - Brg 100650 - Span 1 - R2 - P1 | 2025-04-24 08:00 | 2025-04-28 16:00 |  |  | 3 | 0 | 3 | 317 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A22720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Reinforce Deck - Brg 100650 - Span 1 - R2 - P1 | 2025-04-29 08:00 | 2025-04-29 16:00 |  |  | 1 | 0 | 1 | 317 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A22730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Place Deck - Brg 100650 - Span 1 - R2 - P1 | 2025-04-30 08:00 | 2025-04-30 16:00 |  |  | 1 | 0 | 1 | 317 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A22740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Cure Deck - Brg 100650 - Span 1 - R2 - P1 | 2025-05-01 08:00 | 2025-05-07 16:00 |  |  | 7 | 0 | 7 | 540 |  |  | CURE | CURE
A22750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Install Reinf Barrier - Brg 100650 - Span 1 - R2 - P1 | 2025-05-08 08:00 | 2025-05-08 16:00 |  |  | 1 | 0 | 1 | 318 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A22760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Strip Overhangs - Brg 100650 - Span 1 - R2 - P1 | 2025-05-09 08:00 | 2025-05-09 16:00 |  |  | 1 | 0 | 1 | 318 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A22780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 | R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | FRPS Approach Slab 1 - Brg 100650 - R2 - P1 | 2025-05-01 08:00 | 2025-05-05 16:00 |  |  | 3 | 0 | 3 | 322 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A22790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 | R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | FRPS Approach Slab 2 - Brg 100650 - R2 - P1 | 2025-05-01 08:00 | 2025-05-05 16:00 |  |  | 3 | 0 | 3 | 322 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A22800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 | R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Slip Barrier - Brg 100650 - R2 - P1 | 2025-05-16 08:00 | 2025-05-16 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A22820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 | R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Groove Deck - Brg 100650 - R2 - P1 | 2025-05-19 08:00 | 2025-05-19 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A22830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 | R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Perm Striping - Brg 100650 - R2 - P1 | 2025-05-20 08:00 | 2025-05-20 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A22840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 1 | 2025-03-31 08:00 | 2025-04-28 16:00 |  |  | 19 | 0 | 19 | 252 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A22850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Wall Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-08-19 08:00 | 2025-09-29 16:00 |  |  | 23 | 0 | 23 | 216 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A22860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Junction Slab - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-07-18 08:00 | 2025-08-18 16:00 |  |  | 20 | 0 | 20 | 216 |  | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A22870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-03-14 08:00 | 2025-03-28 16:00 |  |  | 10 | 0 | 10 | 252 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A22880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Stabilization - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-07-15 08:00 | 2025-07-17 16:00 |  |  | 2 | 0 | 2 | 216 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A22890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Asphalt Base - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-09-30 08:00 | 2025-09-30 16:00 |  |  | 1 | 0 | 1 | 216 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A22900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Concrete Pav - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-10-01 08:00 | 2025-10-21 16:00 |  |  | 13 | 0 | 13 | 216 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A22910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.3 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Grading - Brg 100650 - End Bent 2 - R2 - P1 | 2024-08-23 08:00 | 2024-08-23 16:00 |  |  | 1 | 0 | 1 | 382 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A22930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.3 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Drive Pile - Brg 100650 - End Bent 2 - R2 - P1 | 2025-03-13 08:00 | 2025-03-13 16:00 |  |  | 1 | 0 | 1 | 273 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A22940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.3 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | FRP Abt Cap - Brg 100650 - End Bent 2 - R2 - P1 | 2025-03-24 08:00 | 2025-03-25 16:00 |  |  | 2 | 0 | 2 | 333 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A22950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.3 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Cure/Strip Abt Cap - Brg 100650 - End Bent 2 - R2 - P1 | 2025-03-26 08:00 | 2025-03-28 16:00 |  |  | 3 | 0 | 3 | 562 |  |  | CURE | CURE
A22960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.3 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Const MSE Wall & Bkfill - RW 6-1 / Brg 6 100650 - End Bent 2- R2 - P1 | 2025-03-14 08:00 | 2025-03-21 16:00 |  |  | 5 | 0 | 5 | 273 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A22980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Excavate - Brg 100650 - Pier 2 - R2 - P1 | 2024-12-17 08:00 | 2024-12-17 16:00 |  |  | 1 | 0 | 1 | 359 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A23000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Drive Pile - Brg 100650 - Pier 2 - R2 - P1 | 2025-03-13 08:00 | 2025-03-18 16:00 |  |  | 4 | 0 | 4 | 316 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A23010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | FRP Footing - Brg 100650 - Pier 2 - R2 - P1 | 2025-03-20 08:00 | 2025-03-24 16:00 |  |  | 3 | 0 | 3 | 316 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A23020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Cure/Strip Footing - Brg 100650 - Pier 2 - R2 - P1 | 2025-03-25 08:00 | 2025-03-31 16:00 |  |  | 7 | 0 | 7 | 534 |  |  | CURE | CURE
A23030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | FRP Column - Brg 100650 - Pier 2 - R2 - P1 | 2025-04-01 08:00 | 2025-04-02 16:00 |  |  | 2 | 0 | 2 | 315 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A23040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Cure/Strip Column - Brg 100650 - Pier 2 - R2 - P1 | 2025-04-03 08:00 | 2025-04-09 16:00 |  |  | 7 | 0 | 7 | 536 |  |  | CURE | CURE
A23050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | FRP Cap - Brg 100650 - Pier 2 - R2 - P1 | 2025-04-10 08:00 | 2025-04-15 16:00 |  |  | 4 | 0 | 4 | 314 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A23060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 | R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Cure/Strip Cap - Brg 100650 - Pier 2 - R2 - P1 | 2025-04-16 08:00 | 2025-04-18 16:00 |  |  | 3 | 0 | 3 | 536 |  |  | CURE | CURE
A23070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Erect Girders - Brg 100650 - Span 2 - R2 - P1 | 2025-04-21 08:00 | 2025-04-21 16:00 |  |  | 1 | 0 | 1 | 314 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A23080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Install SIP - Brg 100650 - Span 2 - R2 - P1 | 2025-04-22 08:00 | 2025-04-22 16:00 |  |  | 1 | 0 | 1 | 314 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A23090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Install Overhangs - Brg 100650 - Span 2 - R2 - P1 | 2025-04-24 08:00 | 2025-04-30 16:00 |  |  | 5 | 0 | 5 | 314 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Reinforce Deck - Brg 100650 - Span 2 - R2 - P1 | 2025-05-01 08:00 | 2025-05-01 16:00 |  |  | 1 | 0 | 1 | 314 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Place Deck - Brg 100650 - Span 2 - R2 - P1 | 2025-05-02 08:00 | 2025-05-02 16:00 |  |  | 1 | 0 | 1 | 314 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A23120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Cure Deck - Brg 100650 - Span 2 - R2 - P1 | 2025-05-03 08:00 | 2025-05-09 16:00 |  |  | 7 | 0 | 7 | 537 |  |  | CURE | CURE
A23130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Install Reinf Barrier - Brg 100650 - Span 2 - R2 - P1 | 2025-05-12 08:00 | 2025-05-12 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Strip Overhangs - Brg 100650 - Span 2 - R2 - P1 | 2025-05-13 08:00 | 2025-05-15 16:00 |  |  | 2 | 0 | 2 | 315 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Erect Girders - Brg 100650 - Span 3 - R2 - P1 | 2025-04-21 08:00 | 2025-04-21 16:00 |  |  | 1 | 0 | 1 | 317 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A23170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Install SIP - Brg 100650 - Span 3 - R2 - P1 | 2025-04-22 08:00 | 2025-04-22 16:00 |  |  | 1 | 0 | 1 | 317 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A23180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Install Overhangs - Brg 100650 - Span 3 - R2 - P1 | 2025-04-24 08:00 | 2025-04-28 16:00 |  |  | 3 | 0 | 3 | 317 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Reinforce Deck - Brg 100650 - Span 3 - R2 - P1 | 2025-04-29 08:00 | 2025-04-29 16:00 |  |  | 1 | 0 | 1 | 317 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Place Deck - Brg 100650 - Span 3 - R2 - P1 | 2025-04-30 08:00 | 2025-04-30 16:00 |  |  | 1 | 0 | 1 | 317 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A23210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Cure Deck - Brg 100650 - Span 3 - R2 - P1 | 2025-05-01 08:00 | 2025-05-07 16:00 |  |  | 7 | 0 | 7 | 540 |  |  | CURE | CURE
A23220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Install Reinf Barrier - Brg 100650 - Span 3 - R2 - P1 | 2025-05-08 08:00 | 2025-05-08 16:00 |  |  | 1 | 0 | 1 | 318 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 | R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Strip Overhangs - Brg 100650 - Span 3 - R2 - P1 | 2025-05-09 08:00 | 2025-05-09 16:00 |  |  | 1 | 0 | 1 | 318 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Edge Drain - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-10-22 08:00 | 2025-10-27 16:00 |  |  | 4 | 0 | 4 | 216 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A23260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Shoulder GAB - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-10-28 08:00 | 2025-10-29 16:00 |  |  | 2 | 0 | 2 | 216 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A23270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Asphalt Shoulder - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-10-30 08:00 | 2025-10-30 16:00 |  |  | 1 | 0 | 1 | 216 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A23290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.4 | R2 - Milestones | Finish Phase 2 - R2 - Right Ramp EN Construction |  | 2025-11-18 16:00 |  |  | 0 | 0 | 0 | 269 |  |  | MS | MS
A23300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.7 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Grading - Brg 100652 - End Bent 1 - R2 - P1 | 2024-12-20 08:00 | 2024-12-20 16:00 |  |  | 1 | 0 | 1 | 296 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A23320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.7 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Drive Pile - Brg 100652 - End Bent 1 - R2 - P1 | 2025-01-03 08:00 | 2025-01-03 16:00 |  |  | 1 | 0 | 1 | 295 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A23330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.7 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | FRP Abt Cap - Brg 100652 - End Bent 1 - R2 - P1 | 2025-01-13 08:00 | 2025-01-17 16:00 |  |  | 4 | 0 | 4 | 346 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A23340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.7 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Cure/Strip Abt Cap - Brg 100652 - End Bent 1 - R2 - P1 | 2025-01-18 08:00 | 2025-01-20 16:00 |  |  | 3 | 0 | 3 | 587 |  |  | CURE | CURE
A23350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.7 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Const MSE Wall & Bkfill - RW 7-2 / Brg 100652 - End Bent 1 - R2 - P1 | 2025-01-06 08:00 | 2025-01-10 16:00 |  |  | 5 | 0 | 5 | 295 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A23360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.7 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Temp Wall or SOE - Brg 100652 - End Bent 1 - R2 - P1 | 2024-12-17 08:00 | 2024-12-19 16:00 |  |  | 2 | 0 | 2 | 296 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A23380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Excavate - Brg 100652 - Pier 1 - R2 - P1 | 2025-01-07 08:00 | 2025-01-07 16:00 |  |  | 1 | 0 | 1 | 327 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A23400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Drive Pile - Brg 100652 - Pier 1 - R2 - P1 | 2025-01-08 08:00 | 2025-01-14 16:00 |  |  | 5 | 0 | 5 | 327 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A23410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | FRP Footing - Brg 100652 - Pier 1 - R2 - P1 | 2025-01-16 08:00 | 2025-01-21 16:00 |  |  | 3 | 0 | 3 | 327 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A23420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Cure/Strip Footing - Brg 100652 - Pier 1 - R2 - P1 | 2025-01-22 08:00 | 2025-01-28 16:00 |  |  | 7 | 0 | 7 | 554 |  |  | CURE | CURE
A23430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | FRP Column - Brg 100652 - Pier 1 - R2 - P1 | 2025-01-30 08:00 | 2025-01-31 16:00 |  |  | 2 | 0 | 2 | 328 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A23440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Cure/Strip Column - Brg 100652 - Pier 1 - R2 - P1 | 2025-02-01 08:00 | 2025-02-07 16:00 |  |  | 7 | 0 | 7 | 555 |  |  | CURE | CURE
A23450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | FRP Cap - Brg 100652 - Pier 1 - R2 - P1 | 2025-02-10 08:00 | 2025-02-13 16:00 |  |  | 3 | 0 | 3 | 327 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A23460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Cure/Strip Cap - Brg 100652 - Pier 1 - R2 - P1 | 2025-02-14 08:00 | 2025-02-20 16:00 |  |  | 7 | 0 | 7 | 553 |  |  | CURE | CURE
A23470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Erect Girders - Brg 100652 - Span 1 - R2 - P1 | 2025-03-13 08:00 | 2025-03-13 16:00 |  |  | 1 | 0 | 1 | 317 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A23480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Install SIP - Brg 100652 - Span 1 - R2 - P1 | 2025-03-14 08:00 | 2025-03-14 16:00 |  |  | 1 | 0 | 1 | 317 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A23490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Install Overhangs - Brg 100652 - Span 1 - R2 - P1 | 2025-03-17 08:00 | 2025-03-20 16:00 |  |  | 3 | 0 | 3 | 317 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Reinforce Deck - Brg 100652 - Span 1 - R2 - P1 | 2025-03-21 08:00 | 2025-03-21 16:00 |  |  | 1 | 0 | 1 | 317 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Place Deck - Brg 100652 - Span 1 - R2 - P1 | 2025-03-24 08:00 | 2025-03-24 16:00 |  |  | 1 | 0 | 1 | 317 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A23520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Cure Deck - Brg 100652 - Span 1 - R2 - P1 | 2025-03-25 08:00 | 2025-03-31 16:00 |  |  | 7 | 0 | 7 | 539 |  |  | CURE | CURE
A23530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Install Reinf Barrier - Brg 100652 - Span 1 - R2 - P1 | 2025-04-01 08:00 | 2025-04-01 16:00 |  |  | 1 | 0 | 1 | 318 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Strip Overhangs - Brg 100652 - Span 1 - R2 - P1 | 2025-04-02 08:00 | 2025-04-02 16:00 |  |  | 1 | 0 | 1 | 318 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 | R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | FRPS Approach Slab 1 - Brg 100652 - R2 - P1 | 2025-03-25 08:00 | 2025-03-27 16:00 |  |  | 3 | 0 | 3 | 347 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A23570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 | R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | FRPS Approach Slab 2 - Brg 100652 - R2 - P1 | 2025-03-28 08:00 | 2025-04-01 16:00 |  |  | 3 | 0 | 3 | 344 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A23580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 | R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Slip Barrier - Brg 100652 - R2 - P1 | 2025-04-08 08:00 | 2025-04-08 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A23600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 | R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Groove Deck - Brg 100652 - R2 - P1 | 2025-04-09 08:00 | 2025-04-09 16:00 |  |  | 1 | 0 | 1 | 339 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A23610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 | R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Perm Striping - Brg 100652 - R2 - P1 | 2025-04-10 08:00 | 2025-04-10 16:00 |  |  | 1 | 0 | 1 | 339 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A23620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.8 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Grading - Brg 100652 - End Bent 2 - R2 - P1 | 2024-08-23 08:00 | 2024-08-23 16:00 |  |  | 1 | 0 | 1 | 418 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A23640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.8 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Drive Pile - Brg 100652 - End Bent 2 - R2 - P1 | 2025-01-03 08:00 | 2025-01-03 16:00 |  |  | 1 | 0 | 1 | 349 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A23650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.8 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | FRP Abt Cap - Brg 100652 - End Bent 2 - R2 - P1 | 2025-01-13 08:00 | 2025-01-14 16:00 |  |  | 2 | 0 | 2 | 349 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A23660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.8 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Cure/Strip Abt Cap - Brg 100652 - End Bent 2 - R2 - P1 | 2025-01-15 08:00 | 2025-01-17 16:00 |  |  | 3 | 0 | 3 | 592 |  |  | CURE | CURE
A23670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.8 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Const MSE Wall & Bkfill - RW 7-1 / Brg 100652 - End Bent 2 - R2 - P1 | 2025-01-06 08:00 | 2025-01-10 16:00 |  |  | 5 | 0 | 5 | 349 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A23690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Excavate - Brg 100652 - Pier 2 - R2 - P1 | 2025-01-07 08:00 | 2025-01-07 16:00 |  |  | 1 | 0 | 1 | 327 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A23710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Drive Pile - Brg 100652 - Pier 2 - R2 - P1 | 2025-01-08 08:00 | 2025-01-14 16:00 |  |  | 5 | 0 | 5 | 327 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A23720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | FRP Footing - Brg 100652 - Pier 2 - R2 - P1 | 2025-01-16 08:00 | 2025-01-21 16:00 |  |  | 3 | 0 | 3 | 327 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A23730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Cure/Strip Footing - Brg 100652 - Pier 2 - R2 - P1 | 2025-01-22 08:00 | 2025-01-28 16:00 |  |  | 7 | 0 | 7 | 554 |  |  | CURE | CURE
A23740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | FRP Column - Brg 100652 - Pier 2 - R2 - P1 | 2025-01-30 08:00 | 2025-01-31 16:00 |  |  | 2 | 0 | 2 | 328 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A23750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Cure/Strip Column - Brg 100652 - Pier 2 - R2 - P1 | 2025-02-01 08:00 | 2025-02-07 16:00 |  |  | 7 | 0 | 7 | 555 |  |  | CURE | CURE
A23760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | FRP Cap - Brg 100652 - Pier 2 - R2 - P1 | 2025-02-10 08:00 | 2025-02-13 16:00 |  |  | 3 | 0 | 3 | 327 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A23770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 | R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Cure/Strip Cap - Brg 100652 - Pier 2 - R2 - P1 | 2025-02-14 08:00 | 2025-02-20 16:00 |  |  | 7 | 0 | 7 | 553 |  |  | CURE | CURE
A23780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Erect Girders - Brg 100652 - Span 2 - R2 - P1 | 2025-03-13 08:00 | 2025-03-13 16:00 |  |  | 1 | 0 | 1 | 316 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A23790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Install SIP - Brg 100652 - Span 2 - R2 - P1 | 2025-03-14 08:00 | 2025-03-14 16:00 |  |  | 1 | 0 | 1 | 316 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A23800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Install Overhangs - Brg 100652 - Span 2 - R2 - P1 | 2025-03-17 08:00 | 2025-03-24 16:00 |  |  | 5 | 0 | 5 | 316 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Reinforce Deck - Brg 100652 - Span 2 - R2 - P1 | 2025-03-25 08:00 | 2025-03-25 16:00 |  |  | 1 | 0 | 1 | 316 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Place Deck - Brg 100652 - Span 2 - R2 - P1 | 2025-03-26 08:00 | 2025-03-26 16:00 |  |  | 1 | 0 | 1 | 316 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A23830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Cure Deck - Brg 100652 - Span 2 - R2 - P1 | 2025-03-27 08:00 | 2025-04-02 16:00 |  |  | 7 | 0 | 7 | 536 |  |  | CURE | CURE
A23840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Install Reinf Barrier - Brg 100652 - Span 2 - R2 - P1 | 2025-04-03 08:00 | 2025-04-03 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Strip Overhangs - Brg 100652 - Span 2 - R2 - P1 | 2025-04-04 08:00 | 2025-04-07 16:00 |  |  | 2 | 0 | 2 | 315 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Erect Girders - Brg 100652 - Span 3 - R2 - P1 | 2025-03-13 08:00 | 2025-03-13 16:00 |  |  | 1 | 0 | 1 | 319 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A23880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Install SIP - Brg 100652 - Span 3 - R2 - P1 | 2025-03-14 08:00 | 2025-03-14 16:00 |  |  | 1 | 0 | 1 | 319 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A23890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Install Overhangs - Brg 100652 - Span 3 - R2 - P1 | 2025-03-17 08:00 | 2025-03-20 16:00 |  |  | 3 | 0 | 3 | 319 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Reinforce Deck - Brg 100652 - Span 3 - R2 - P1 | 2025-03-21 08:00 | 2025-03-21 16:00 |  |  | 1 | 0 | 1 | 319 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Place Deck - Brg 100652 - Span 3 - R2 - P1 | 2025-03-27 08:00 | 2025-03-27 16:00 |  |  | 1 | 0 | 1 | 316 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A23920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Cure Deck - Brg 100652 - Span 3 - R2 - P1 | 2025-03-28 08:00 | 2025-04-03 16:00 |  |  | 7 | 0 | 7 | 536 |  |  | CURE | CURE
A23930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Install Reinf Barrier - Brg 100652 - Span 3 - R2 - P1 | 2025-04-04 08:00 | 2025-04-04 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A23940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 | R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Strip Overhangs - Brg 100652 - Span 3 - R2 - P1 | 2025-04-07 08:00 | 2025-04-07 16:00 |  |  | 1 | 0 | 1 | 315 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A23960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.8 | R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Temp Wall or SOE - Brg 100652 - End Bent 2 - R2 - P1 | 2024-08-20 08:00 | 2024-08-22 16:00 |  |  | 2 | 0 | 2 | 418 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A23970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.3 | R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Temp Wall or SOE - Brg 100650 - End Bent 2 - R2 - P1 | 2024-08-20 08:00 | 2024-08-22 16:00 |  |  | 2 | 0 | 2 | 382 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A23980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place 3-Pour Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 2025-06-26 08:00 | 2025-07-14 16:00 |  |  | 11 | 0 | 11 | 216 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A24000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Const MSE Wall & Bkfill - RW 7-2 - Ramp EN Sta 83 to 85 - R2 - P1 | 2025-01-31 08:00 | 2025-02-17 16:00 |  |  | 11 | 0 | 11 | 305 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A24040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Wall Barrier - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-04-10 08:00 | 2025-05-15 16:00 |  |  | 22 | 0 | 22 | 295 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A24030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Junction Slab - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-03-13 08:00 | 2025-04-09 16:00 |  |  | 19 | 0 | 19 | 295 |  | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A23990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-01-13 08:00 | 2025-01-30 16:00 |  |  | 10 | 0 | 10 | 295 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A24020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Stabilization - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-03-07 08:00 | 2025-03-11 16:00 |  |  | 3 | 0 | 3 | 295 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A24050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Asphalt Base - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-05-16 08:00 | 2025-05-16 16:00 |  |  | 1 | 0 | 1 | 295 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A24060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Concrete Pav - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-05-19 08:00 | 2025-06-03 16:00 |  |  | 11 | 0 | 11 | 295 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A24070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Edge Drain - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-06-04 08:00 | 2025-06-05 16:00 |  |  | 2 | 0 | 2 | 295 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A24080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Shoulder GAB - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-06-06 08:00 | 2025-06-09 16:00 |  |  | 2 | 0 | 2 | 301 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A24090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Asphalt Shoulder - Ramp EN Sta 83 to 88 - R2 - P1 | 2025-06-10 08:00 | 2025-06-10 16:00 |  |  | 1 | 0 | 1 | 301 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A24140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Place Sidewalk - 13th St /14th StIntersection - R2 - P1 | 2024-10-10 08:00 | 2024-10-17 16:00 |  |  | 5 | 0 | 5 | 419 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A24100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Grading - 13th St /14th St Intersection - R2 - P1 | 2024-08-27 08:00 | 2024-08-27 16:00 |  |  | 1 | 0 | 1 | 419 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A24110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Place Stabilization - 13th St /14th St Intersection - R2 - P1 | 2024-10-01 08:00 | 2024-10-02 16:00 |  |  | 2 | 0 | 2 | 419 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A24120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Place GAB - 13th St /14th St Intersection - R2 - P1 | 2024-10-03 08:00 | 2024-10-03 16:00 |  |  | 1 | 0 | 1 | 419 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A24130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Place Curb - 13th St /14th St Intersection - R2 - P1 | 2024-10-04 08:00 | 2024-10-08 16:00 |  |  | 3 | 0 | 3 | 419 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A24150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Place Asphalt Surface - 13th St /14th St Intersection - R2 - P1 | 2024-10-18 08:00 | 2024-10-18 16:00 |  |  | 1 | 0 | 1 | 436 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A24160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.11 | R2 - Ph1 - 13th St / 14th Ave Intersection | Install DRG - 13th St / 14th St Intersection - R2 - P1 | 2024-08-29 08:00 | 2024-09-30 16:00 |  |  | 18 | 0 | 18 | 419 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A24170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.4 | R3 - Ph1, Stg1, Stp1 - MOT | Install MOT - Ramp B / C - R3 - P1.S1 | 2024-05-30 08:00 | 2024-05-30 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A24180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.4 | R3 - Ph1, Stg1, Stp1 - MOT | Shift Traffic - Ramp B & C to Outside - R3 - P1.S1 | 2024-05-31 08:00 | 2024-05-31 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A24230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.5 | R3 - Ph1, Stg1, Stp2 - MOT | Open Traffic to Temp Ramp F Close Exist Ramp F - R3 - P1.S1 | 2024-06-13 08:00 | 2024-06-13 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A24280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.1 | R3 - Ph1, Stg1 - Temp Ramp F - Sta. 706 to 711 | Place GAB - Temp Ramp F - R3 - P1.S1 | 2024-06-07 08:00 | 2024-06-07 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A24290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.1 | R3 - Ph1, Stg1 - Temp Ramp F - Sta. 706 to 711 | Place Temp Asphalt - Temp Ramp F - R3 - P1.S1 | 2024-06-10 08:00 | 2024-06-10 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A24350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.3 | R3 - Ph1, Stg2, Stp2 - MOT | Shift Traffic - Ramp B Left - R3 - P1.S2 | 2024-06-21 08:00 | 2024-06-21 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A24360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.3 | R3 - Ph1, Stg2, Stp2 - MOT | Install Temp Barrier - Ramp B - R3 - P1.S2 | 2024-06-24 08:00 | 2024-07-01 16:00 |  |  | 5 | 0 | 5 | 43 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A24390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.5 | R3 - Ph1, Stg2 - Left Ramp B - Temp Pavement - Sta. 600 to 603, 613 to 614 | Place Temp Asphalt - Ramp B - R3 - P1.S2 | 2024-06-17 08:00 | 2024-06-18 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A24400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.5 | R3 - Ph1, Stg2 - Left Ramp B - Temp Pavement - Sta. 600 to 603, 613 to 614 | Temp Striping - Ramp B - R3 - P1.S2 | 2024-06-20 08:00 | 2024-06-20 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Temp
A24470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Grading - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-06-04 08:00 | 2024-06-04 16:00 |  |  | 1 | 0 | 1 | 107 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A24490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Install Drilled Shaft - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-06-05 08:00 | 2024-06-24 16:00 |  |  | 12 | 0 | 12 | 107 |  | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A24500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | FRP Abt Cap - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-07-19 08:00 | 2024-07-30 16:00 |  |  | 7 | 0 | 7 | 129 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A24510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Cure/Strip Abt Cap - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-07-31 08:00 | 2024-08-02 16:00 |  |  | 3 | 0 | 3 | 233 |  |  | CURE | CURE
A24520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Const MSE Wall & Bkfill - RW 8-1 / Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-07-11 08:00 | 2024-07-18 16:00 |  |  | 5 | 0 | 5 | 107 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A24530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Temp Wall or SOE - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-05-30 08:00 | 2024-06-03 16:00 |  |  | 3 | 0 | 3 | 107 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A24550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Prep for Drill Shafts - Brg 100868 - Pier 1 - R3 - P1.S2 | 2024-05-30 08:00 | 2024-05-30 16:00 |  |  | 1 | 0 | 1 | 128 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A24570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Install Drilled Shaft - Brg 100868 - Pier 1 - R3 - P1.S2 | 2024-05-31 08:00 | 2024-06-18 16:00 |  |  | 12 | 0 | 12 | 128 |  | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A24600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | FRP Column - Brg 100868 - Pier 1 - R3 - P1.S2 | 2024-06-20 08:00 | 2024-06-24 16:00 |  |  | 3 | 0 | 3 | 128 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A24610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Cure/Strip Column - Brg 100868 - Pier 1 - R3 - P1.S2 | 2024-06-25 08:00 | 2024-07-01 16:00 |  |  | 7 | 0 | 7 | 230 |  |  | CURE | CURE
A24620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | FRP Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | 2024-07-02 08:00 | 2024-08-01 16:00 |  |  | 19 | 0 | 19 | 128 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A24630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Cure/Strip Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | 2024-08-02 08:00 | 2024-08-04 16:00 |  |  | 3 | 0 | 3 | 231 |  |  | CURE | CURE
A24640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Erect Girders - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-08-05 08:00 | 2024-08-05 16:00 |  |  | 1 | 0 | 1 | 128 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A24650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Install SIP - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-08-06 08:00 | 2024-08-07 16:00 |  |  | 2 | 0 | 2 | 128 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A24660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Install Overhangs - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-08-08 08:00 | 2024-08-23 16:00 |  |  | 10 | 0 | 10 | 128 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A24670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Reinforce Deck - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-08-26 08:00 | 2024-09-03 16:00 |  |  | 4 | 0 | 4 | 128 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A24680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Place Deck - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-09-04 08:00 | 2024-09-04 16:00 |  |  | 1 | 0 | 1 | 128 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A24690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Cure Deck - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-09-05 08:00 | 2024-09-11 16:00 |  |  | 7 | 0 | 7 | 243 |  |  | CURE | CURE
A24700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Install Reinf Barrier - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-09-12 08:00 | 2024-09-13 16:00 |  |  | 2 | 0 | 2 | 139 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A24710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Strip Overhangs - Brg 100868 - Span 1 - R3 - P1.S2 | 2024-09-16 08:00 | 2024-09-19 16:00 |  |  | 3 | 0 | 3 | 139 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A24730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | FRPS Approach Slab 1 - Brg 100868 - R3 - P1.S2 | 2024-09-05 08:00 | 2024-09-26 16:00 |  |  | 13 | 0 | 13 | 128 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A24740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | FRPS Approach Slab 2 - Brg 100868 - R3 - P1.S2 | 2024-10-07 08:00 | 2024-10-23 16:00 |  |  | 11 | 0 | 11 | 122 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A24750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Slip Barrier - Brg 100868 - R3 - P1.S2 | 2024-10-24 08:00 | 2024-10-29 16:00 |  |  | 4 | 0 | 4 | 118 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A24770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Groove Deck - Brg 100868 - R3 - P1.S2 | 2024-10-30 08:00 | 2024-11-01 16:00 |  |  | 3 | 0 | 3 | 118 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A24780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Perm Striping - Brg 100868 - R3 - P1.S2 | 2024-11-04 08:00 | 2024-11-04 16:00 |  |  | 1 | 0 | 1 | 118 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A24820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Cut/Fill to Grade - Ramp G Sta 802 to 805 - R3 - P3 | 2025-10-21 08:00 | 2025-10-23 16:00 |  |  | 3 | 0 | 3 | 156 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A24830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Stabilization - Ramp G Sta 802 to 805 - R3 - P3 | 2025-10-24 08:00 | 2025-10-24 16:00 |  |  | 1 | 0 | 1 | 156 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A24840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Asphalt Base - Ramp G Sta 802 to 805 - R3 - P3 | 2025-10-27 08:00 | 2025-10-27 16:00 |  |  | 1 | 0 | 1 | 156 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A24850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Concrete Pav - Ramp G Sta 802 to 805 - R3 - P3 | 2025-10-28 08:00 | 2025-10-31 16:00 |  |  | 4 | 0 | 4 | 156 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A24860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.13 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Grading - Brg 100868 - End Bent 2 - R3 - P1.S2 | 2024-06-04 08:00 | 2024-06-04 16:00 |  |  | 1 | 0 | 1 | 80 | 47 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A24880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.13 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Drive Pile - Brg 100868 - End Bent 2 - R3 - P1.S2 | 2024-06-05 08:00 | 2024-06-05 16:00 |  |  | 1 | 0 | 1 | 80 | 47 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A24890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.13 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | FRP Abt Cap - Brg 100868 - End Bent 2 - R3 - P1.S2 | 2024-07-23 08:00 | 2024-08-01 16:00 |  |  | 6 | 0 | 6 | 126 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A24900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.13 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Cure/Strip Abt Cap - Brg 100868 - End Bent 2 - R3 - P1.S2 | 2024-08-02 08:00 | 2024-08-04 16:00 |  |  | 3 | 0 | 3 | 228 |  |  | CURE | CURE
A24910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.13 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Const MSE Wall & Bkfill - RW 8-2 / Brg 100868 - End Bent 2 - R3 - P1.S2 | 2024-07-09 08:00 | 2024-07-22 16:00 |  |  | 9 | 0 | 9 | 126 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A24930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Prep for Drill Shafts - Brg 100868 - Pier 2 - R3 - P1.S2 | 2024-05-30 08:00 | 2024-05-30 16:00 |  |  | 1 | 0 | 1 | 119 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A24950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Install Drilled Shaft - Brg 100868 - Pier 2 - R3 - P1.S2 | 2024-05-31 08:00 | 2024-06-18 16:00 |  |  | 12 | 0 | 12 | 119 |  | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A24980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | FRP Column - Brg 100868 - Pier 2 - R3 - P1.S2 | 2024-06-20 08:00 | 2024-06-27 16:00 |  |  | 5 | 0 | 5 | 127 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A24990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Cure/Strip Column - Brg 100868 - Pier 2 - R3 - P1.S2 | 2024-06-28 08:00 | 2024-07-04 16:00 |  |  | 7 | 0 | 7 | 228 |  |  | CURE | CURE
A25000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | FRP Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | 2024-07-05 08:00 | 2024-08-05 16:00 |  |  | 19 | 0 | 19 | 127 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A25010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Cure/Strip Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | 2024-08-06 08:00 | 2024-08-08 16:00 |  |  | 3 | 0 | 3 | 228 |  |  | CURE | CURE
A25020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Erect Girders - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-08-09 08:00 | 2024-08-09 16:00 |  |  | 1 | 0 | 1 | 125 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A25030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Install SIP - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-08-12 08:00 | 2024-08-13 16:00 |  |  | 2 | 0 | 2 | 125 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A25040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Install Overhangs - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-08-15 08:00 | 2024-09-13 16:00 |  |  | 17 | 0 | 17 | 125 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A25050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Reinforce Deck - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-09-16 08:00 | 2024-09-23 16:00 |  |  | 5 | 0 | 5 | 125 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A25060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Place Deck - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-09-24 08:00 | 2024-09-24 16:00 |  |  | 1 | 0 | 1 | 125 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A25070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Cure Deck - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-09-25 08:00 | 2024-10-01 16:00 |  |  | 7 | 0 | 7 | 219 |  |  | CURE | CURE
A25080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Install Reinf Barrier - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-10-02 08:00 | 2024-10-04 16:00 |  |  | 3 | 0 | 3 | 125 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A25090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Strip Overhangs - Brg 100868 - Span 2 - R3 - P1.S2 | 2024-10-07 08:00 | 2024-10-11 16:00 |  |  | 4 | 0 | 4 | 125 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A25110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Erect Girders - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-08-19 08:00 | 2024-08-19 16:00 |  |  | 1 | 0 | 1 | 118 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A25120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Install SIP - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-08-20 08:00 | 2024-08-23 16:00 |  |  | 3 | 0 | 3 | 118 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A25130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Install Overhangs - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-08-26 08:00 | 2024-09-26 16:00 |  |  | 18 | 0 | 18 | 118 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A25140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Reinforce Deck - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-09-27 08:00 | 2024-10-03 16:00 |  |  | 5 | 0 | 5 | 118 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A25150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Place Deck - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-10-04 08:00 | 2024-10-04 16:00 |  |  | 1 | 0 | 1 | 118 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A25160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Cure Deck - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-10-05 08:00 | 2024-10-11 16:00 |  |  | 7 | 0 | 7 | 209 |  |  | CURE | CURE
A25170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Install Reinf Barrier - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-10-14 08:00 | 2024-10-17 16:00 |  |  | 3 | 0 | 3 | 118 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A25180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Strip Overhangs - Brg 100868 - Span 4 - R3 - P1.S2 | 2024-10-18 08:00 | 2024-10-23 16:00 |  |  | 4 | 0 | 4 | 118 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A25200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Edge Drain - Ramp G Sta 802 to 805 - R3 - P3 | 2025-11-03 08:00 | 2025-11-03 16:00 |  |  | 1 | 0 | 1 | 156 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A25210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Shoulder GAB - Ramp G Sta 802 to 805 - R3 - P3 | 2025-11-04 08:00 | 2025-11-04 16:00 |  |  | 1 | 0 | 1 | 156 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A25220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Asphalt Shoulder - Ramp G Sta 802 to 805 - R3 - P3 | 2025-11-05 08:00 | 2025-11-05 16:00 |  |  | 1 | 0 | 1 | 156 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A25230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.11 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Grading - Brg 100869 - End Bent 1 - R3 - P1.S2 | 2024-08-20 08:00 | 2024-08-20 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A25250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.11 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P1.S2 | 2024-08-22 08:00 | 2024-08-29 16:00 |  |  | 5 | 0 | 5 | 102 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A25260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.11 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | FRP Abt Cap - Brg 100869 - End Bent 1 - R3 - P1.S2 | 2024-09-13 08:00 | 2024-09-26 16:00 |  |  | 8 | 0 | 8 | 102 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A25270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.11 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Cure/Strip Abt Cap - Brg 100869 - End Bent 1 - R3 - P1.S2 | 2024-09-27 08:00 | 2024-09-29 16:00 |  |  | 3 | 0 | 3 | 185 |  |  | CURE | CURE
A25280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.11 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P1.S2 | 2024-09-03 08:00 | 2024-09-12 16:00 |  |  | 7 | 0 | 7 | 102 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A25290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.11 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P1.S2 | 2024-08-07 08:00 | 2024-08-19 16:00 |  |  | 8 | 0 | 8 | 43 | 1 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A25400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Erect Girders - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-10-14 08:00 | 2024-10-15 16:00 |  |  | 2 | 0 | 2 | 95 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A25410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Install SIP - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-10-17 08:00 | 2024-10-21 16:00 |  |  | 3 | 0 | 3 | 95 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A25420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Install Overhangs - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-10-22 08:00 | 2024-11-07 16:00 |  |  | 13 | 0 | 13 | 95 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A25430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Reinforce Deck - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-11-08 08:00 | 2024-11-19 16:00 |  |  | 6 | 0 | 6 | 95 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A25440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Place Deck - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-11-21 08:00 | 2024-11-21 16:00 |  |  | 1 | 0 | 1 | 95 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A25450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Cure Deck - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-11-22 08:00 | 2024-11-28 16:00 |  |  | 7 | 0 | 7 | 172 |  |  | CURE | CURE
A25460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Install Reinf Barrier - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-12-02 08:00 | 2024-12-03 16:00 |  |  | 2 | 0 | 2 | 96 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A25470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Strip Overhangs - Brg 100869 - Span 1 - R3 - P1.S2 | 2024-12-05 08:00 | 2024-12-09 16:00 |  |  | 3 | 0 | 3 | 96 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A25490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | FRPS Approach Slab 1 - Brg 100869 - R3 - P1.S2 | 2024-11-22 08:00 | 2024-12-05 16:00 |  |  | 6 | 0 | 6 | 99 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A25500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | FRPS Approach Slab 2 - Brg 100869 - R3 - P1.S2 | 2024-11-22 08:00 | 2024-12-06 16:00 |  |  | 7 | 0 | 7 | 98 |  | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A25510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Slip Barrier - Brg 100869 - R3 - P1.S2 | 2024-12-10 08:00 | 2024-12-10 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A25520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Grind Deck - Brg 100869 - R3 - P1.S2 | 2024-12-12 08:00 | 2024-12-12 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Diamond Grind Pavement Crew | SUB.CONCRETE.GRIND | CONCRETE PVMT.Diamond Grind
A25530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Groove Deck - Brg 100869 - R3 - P1.S2 | 2024-12-13 08:00 | 2024-12-13 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A25540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Perm Striping - Brg 100869 - R3 - P1.S2 | 2024-12-16 08:00 | 2024-12-16 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A25550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.8 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Grading - Brg 100869 - End Bent 2 - R3 - P1.S2 | 2024-09-06 08:00 | 2024-09-06 16:00 |  |  | 1 | 0 | 1 | 46 | 6 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A25570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.8 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P1.S2 | 2024-09-09 08:00 | 2024-09-16 16:00 |  |  | 5 | 0 | 5 | 46 | 6 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A25580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.8 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | FRP Abt Cap - Brg 100869 - End Bent 2 - R3 - P1.S2 | 2024-09-24 08:00 | 2024-10-08 16:00 |  |  | 10 | 0 | 10 | 94 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A25590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.8 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Cure/Strip Abt Cap - Brg 100869 - End Bent 2 - R3 - P1.S2 | 2024-10-09 08:00 | 2024-10-11 16:00 |  |  | 3 | 0 | 3 | 173 |  |  | CURE | CURE
A25600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.8 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P1.S2 | 2024-09-17 08:00 | 2024-09-23 16:00 |  |  | 4 | 0 | 4 | 46 | 6 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A25890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.8 | R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P1.S2 | 2024-08-22 08:00 | 2024-09-05 16:00 |  |  | 8 | 0 | 8 | 46 | 6 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A25900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.13 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Temp Wall or SOE - Brg 100868 - End Bent 2 - R3 - P1.S2 | 2024-05-30 08:00 | 2024-06-03 16:00 |  |  | 3 | 0 | 3 | 80 | 47 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A25920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Const MSE Wall & Bkfill - RW 8-1 / Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-08-05 08:00 | 2024-09-10 16:00 |  |  | 22 | 0 | 22 | 107 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A25930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Wall Barrier - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-10-03 08:00 | 2024-10-23 16:00 |  |  | 13 | 0 | 13 | 107 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A25940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Junction Slab - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-09-16 08:00 | 2024-10-02 16:00 |  |  | 11 | 0 | 11 | 107 |  | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A25950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Cut/Fill to Grade - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-07-19 08:00 | 2024-08-02 16:00 |  |  | 9 | 0 | 9 | 107 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A25960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Stabilization - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-09-12 08:00 | 2024-09-13 16:00 |  |  | 2 | 0 | 2 | 107 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A25970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Asphalt Base - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-10-24 08:00 | 2024-10-24 16:00 |  |  | 1 | 0 | 1 | 107 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A25980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Concrete Pav - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-10-25 08:00 | 2024-11-14 16:00 |  |  | 13 | 0 | 13 | 107 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A25990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Edge Drain - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-11-15 08:00 | 2024-11-18 16:00 |  |  | 2 | 0 | 2 | 107 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A26000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Shoulder GAB - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-11-19 08:00 | 2024-11-21 16:00 |  |  | 2 | 0 | 2 | 107 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A26010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.10 | R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Asphalt Shoulder - Ramp B Sta 601 to 606 - R3 - P1.S2 | 2024-11-22 08:00 | 2024-11-22 16:00 |  |  | 1 | 0 | 1 | 107 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | 2024-07-10 08:00 | 2024-08-19 16:00 |  |  | 25 | 0 | 25 | 119 | 55 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Wall Barrier - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2024-11-14 08:00 | 2024-12-16 16:00 |  |  | 17 | 0 | 17 | 76 | 46 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A26040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Junction Slab - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2024-11-04 08:00 | 2024-11-12 16:00 |  |  | 6 | 0 | 6 | 76 | 46 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A26050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | 2024-06-05 08:00 | 2024-07-09 16:00 |  |  | 21 | 0 | 21 | 119 | 55 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2024-10-31 08:00 | 2024-11-01 16:00 |  |  | 2 | 0 | 2 | 76 | 46 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A26070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Asphalt Base - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2024-12-17 08:00 | 2024-12-17 16:00 |  |  | 1 | 0 | 1 | 76 | 46 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Concrete Pav - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2024-12-19 08:00 | 2025-01-21 16:00 |  |  | 14 | 0 | 14 | 76 | 46 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A26090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Edge Drain - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2025-01-23 08:00 | 2025-01-24 16:00 |  |  | 2 | 0 | 2 | 76 | 46 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A26100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Shoulder GAB - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2025-01-27 08:00 | 2025-01-28 16:00 |  |  | 2 | 0 | 2 | 76 | 46 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A26110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Asphalt Shoulder - Ramp B Sta 614 to 618 - R3 - P1.S2 | 2025-01-30 08:00 | 2025-01-30 16:00 |  |  | 1 | 0 | 1 | 76 | 46 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 1 | 2024-10-03 08:00 | 2024-11-06 16:00 |  |  | 23 | 0 | 23 | 50 | 16 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Wall Barrier - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2025-01-30 08:00 | 2025-03-03 16:00 |  |  | 20 | 0 | 20 | 43 | 1 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A26150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Junction Slab - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2024-12-19 08:00 | 2025-01-28 16:00 |  |  | 18 | 0 | 18 | 43 | 1 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A26160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2024-09-30 08:00 | 2024-10-31 16:00 |  |  | 22 | 0 | 22 | 43 | 1 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2024-12-16 08:00 | 2024-12-17 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A26180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Asphalt Base - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2025-03-04 08:00 | 2025-03-04 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Concrete Pav - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2025-03-06 08:00 | 2025-03-17 16:00 |  |  | 7 | 0 | 7 | 43 | 1 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A26200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Edge Drain - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2025-03-18 08:00 | 2025-03-21 16:00 |  |  | 3 | 0 | 3 | 43 | 1 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A26210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Shoulder GAB - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2025-03-24 08:00 | 2025-03-25 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A26220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Asphalt Shoulder - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2025-03-26 08:00 | 2025-03-26 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 1 | 2024-09-13 08:00 | 2024-10-21 16:00 |  |  | 23 | 0 | 23 | 83 | 49 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Wall Barrier - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2024-11-15 08:00 | 2024-12-19 16:00 |  |  | 18 | 0 | 18 | 83 | 49 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A26260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Junction Slab - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2024-10-23 08:00 | 2024-11-14 16:00 |  |  | 15 | 0 | 15 | 83 | 49 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A26270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Cut/Fill to Grade - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2024-09-06 08:00 | 2024-09-12 16:00 |  |  | 4 | 0 | 4 | 83 | 49 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Stabilization - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2024-10-22 08:00 | 2024-10-22 16:00 |  |  | 1 | 0 | 1 | 83 | 49 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A26290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Asphalt Base - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2024-12-20 08:00 | 2024-12-20 16:00 |  |  | 1 | 0 | 1 | 83 | 49 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Concrete Pav - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2024-12-23 08:00 | 2025-01-09 16:00 |  |  | 6 | 0 | 6 | 83 | 49 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A26310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Edge Drain - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2025-01-10 08:00 | 2025-01-13 16:00 |  |  | 2 | 0 | 2 | 83 | 49 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A26320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Shoulder GAB - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2025-01-14 08:00 | 2025-01-14 16:00 |  |  | 1 | 0 | 1 | 83 | 49 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A26330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Asphalt Shoulder - Ramp F Sta 506 to 511 - R3 - P1.S2 | 2025-01-16 08:00 | 2025-01-16 16:00 |  |  | 1 | 0 | 1 | 83 | 49 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Start Construction - R3 | 2023-06-20 08:00 |  |  |  | 0 | 0 | 0 | 900 |  |  | MS | MS
A26360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.5 | R3 - Ph1, Stg1, Stp2 - MOT | Shift Temp Barrier - Ramp F - R3 - P1.S1 | 2024-06-11 08:00 | 2024-06-11 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A26380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.1.4 | R3 - Ph1, Stg1, Stp1 - MOT | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | 2024-06-03 08:00 | 2024-06-06 16:00 |  |  | 4 | 0 | 4 | 43 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A26390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.4 | R3 - Ph1, Stg2, Stp1 - MOT | Shift Traffic - Ramp B to Right - R3 - P1.S2 | 2024-06-14 08:00 | 2024-06-14 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A26400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Excavate - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-05-30 08:00 | 2024-05-30 16:00 |  |  | 1 | 0 | 1 | 131 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A26420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Drive Pile - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-06-20 08:00 | 2024-06-28 16:00 |  |  | 6 | 0 | 6 | 119 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A26430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | FRP Footing - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-07-01 08:00 | 2024-07-09 16:00 |  |  | 6 | 0 | 6 | 119 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A26440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Cure/Strip Footing - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-07-10 08:00 | 2024-07-16 16:00 |  |  | 7 | 0 | 7 | 215 |  |  | CURE | CURE
A26450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | FRP Column - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-07-18 08:00 | 2024-07-23 16:00 |  |  | 4 | 0 | 4 | 118 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A26460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Cure/Strip Column - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-07-24 08:00 | 2024-07-30 16:00 |  |  | 7 | 0 | 7 | 215 |  |  | CURE | CURE
A26470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | FRP Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-08-01 08:00 | 2024-08-13 16:00 |  |  | 9 | 0 | 9 | 118 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A26480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Cure/Strip Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | 2024-08-14 08:00 | 2024-08-16 16:00 |  |  | 3 | 0 | 3 | 216 |  |  | CURE | CURE
A26490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Erect Girders - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-08-19 08:00 | 2024-08-19 16:00 |  |  | 1 | 0 | 1 | 120 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A26500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Install SIP - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-08-20 08:00 | 2024-08-22 16:00 |  |  | 2 | 0 | 2 | 120 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A26510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Install Overhangs - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-08-23 08:00 | 2024-09-23 16:00 |  |  | 17 | 0 | 17 | 120 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A26520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Reinforce Deck - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-09-24 08:00 | 2024-10-01 16:00 |  |  | 5 | 0 | 5 | 120 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A26530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Place Deck - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-10-02 08:00 | 2024-10-02 16:00 |  |  | 1 | 0 | 1 | 120 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A26540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Cure Deck - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-10-03 08:00 | 2024-10-09 16:00 |  |  | 7 | 0 | 7 | 211 |  |  | CURE | CURE
A26550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Install Reinf Barrier - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-10-10 08:00 | 2024-10-14 16:00 |  |  | 3 | 0 | 3 | 120 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A26560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Strip Overhangs - Brg 100868 - Span 3 - R3 - P1.S2 | 2024-10-15 08:00 | 2024-10-21 16:00 |  |  | 4 | 0 | 4 | 120 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A26580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) |  | 2024-05-29 16:00 |  |  | 0 | 0 | 0 | 50 | 1 |  | MS | MS
A26590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | 2024-05-30 08:00 |  |  |  | 0 | 0 | 0 | 50 | 1 |  | MS | MS
A26660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 1 Stage 1 - R3 - Temp Ramp F |  | 2024-06-13 16:00 |  |  | 0 | 0 | 0 | 51 | 1 |  | MS | MS
A26670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 1 Stage 2 - R3 - Ramp F / B |  | 2025-03-26 16:00 |  |  | 0 | 0 | 0 | 48 | 1 |  | MS | MS
LoE220 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.2 | R2 Phase Durations | R2 Phase 0 - Pond SMF 4A / Lower Drainage [LoE] | 2024-07-24 08:00 | 2024-09-24 16:00 |  |  | 63 | 0 | 63 | 611 |  |  | LOE | LOE
LoE230 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.2 | R2 Phase Durations | R2 Phase 1 - Left Ramp EN Construction [LoE] | 2024-07-24 08:00 | 2025-10-30 16:00 |  |  | 464 | 0 | 464 | 396 |  |  | LOE | LOE
LoE240 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.2 | R2 Phase Durations | R2 Phase 2 - Right Ramp EN Construction [LoE] | 2025-10-31 08:00 | 2025-11-18 16:00 |  |  | 19 | 0 | 19 | 377 |  |  | LOE | LOE
LoE290 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 0 - - 60" Drainage Systeming [LoE] | 2023-06-20 08:00 | 2024-05-29 16:00 |  |  | 345 | 0 | 345 | 70 |  |  | LOE | LOE
LoE300 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 1 Stage 1 - Temp Ramp F [LoE] | 2024-05-30 08:00 | 2024-06-13 16:00 |  |  | 15 | 0 | 15 | 71 |  |  | LOE | LOE
LoE310 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 1 Stage 2 - Ramp F / B [LoE] | 2024-05-30 08:00 | 2025-03-26 16:00 |  |  | 301 | 0 | 301 | 68 |  |  | LOE | LOE
A26680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.1 | R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | Demo Superstructure - Ramp F Brg Over Palm - R3 - P1.S2 | 2024-07-02 08:00 | 2024-07-16 16:00 |  |  | 10 | 0 | 10 | 43 | 1 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A26690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.1 | R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | Demo Substructure - Ramp F Brg Over Palm - R3 - P1.S2 | 2024-07-18 08:00 | 2024-08-06 16:00 |  |  | 12 | 0 | 12 | 43 | 1 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A26700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.4.7 | R2 - Ph1 - Bridge 100650 Ramp EN - Demo | Demo Barrier - Brg 100650 - R2 - P1 | 2024-08-20 08:00 | 2024-08-29 16:00 |  |  | 6 | 0 | 6 | 357 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A26710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.9.7 | R2 - Ph1 - Bridge 100652 Ramp EN - Demo | Demo Barrier - Brg 100652 - R2 - P1 | 2024-12-17 08:00 | 2025-01-06 16:00 |  |  | 6 | 0 | 6 | 327 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A26720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 2 Stage 1 - R3 - Temp I-4 WB Diversion Ramp |  | 2025-05-21 16:00 |  |  | 0 | 0 | 0 | 51 | 1 |  | MS | MS
A26730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P1.S2 | 2024-11-07 08:00 | 2024-12-02 16:00 |  |  | 12 | 0 | 12 | 50 | 16 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A26770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Cut/Fill to Grade - Ramp G / B Gore - R3 - P2.S1 | 2025-04-07 08:00 | 2025-04-09 16:00 |  |  | 3 | 0 | 3 | 60 | 30 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Place Stabilization - Ramp G / B Gore - R3 - P2.S1 | 2025-04-10 08:00 | 2025-04-10 16:00 |  |  | 1 | 0 | 1 | 60 | 30 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A26790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Place Asphalt Base - Ramp G / B Gore - R3 - P2.S1 | 2025-04-11 08:00 | 2025-04-11 16:00 |  |  | 1 | 0 | 1 | 60 | 30 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Place Concrete Pav - Ramp G / B Gore - R3 - P2.S1 | 2025-04-14 08:00 | 2025-04-15 16:00 |  |  | 2 | 0 | 2 | 60 | 30 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A26810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Place Edge Drain - Ramp G / B Gore - R3 - P2.S1 | 2025-04-17 08:00 | 2025-04-17 16:00 |  |  | 1 | 0 | 1 | 60 | 30 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A26820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Place Shoulder GAB - Ramp G / B Gore - R3 - P2.S1 | 2025-04-18 08:00 | 2025-04-18 16:00 |  |  | 1 | 0 | 1 | 60 | 30 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A26830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Place Asphalt Shoulder - Ramp G / B Gore - R3 - P2.S1 | 2025-04-21 08:00 | 2025-04-21 16:00 |  |  | 1 | 0 | 1 | 60 | 30 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A26850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.4 | R3 - Ph2, Stg1 - MOT | Shift Traffic to New Ramp B & F - R3 - P2.S1 | 2025-03-27 08:00 | 2025-03-27 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A26990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.9 | R3 - Ph0 - Ramp B and F Lower Drainage | Install DRG CS-3A to S-117A / S-120 - Pond SMF 3A - R3 - P0 | 2024-06-14 08:00 | 2024-07-12 16:00 |  |  | 18 | 0 | 18 | 284 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.9 | R3 - Ph0 - Ramp B and F Lower Drainage | Install DRG S-123 to S-122/ S-139 to S-137 - Pond SMF 3A - R3 - P0 | 2024-06-07 08:00 | 2024-07-08 16:00 |  |  | 18 | 0 | 18 | 126 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.9 | R3 - Ph0 - Ramp B and F Lower Drainage | Install DRG S-136C to S-133 to S-132 - Pond SMF 3A /Ramp B - R3 - P0 | 2024-06-07 08:00 | 2024-07-08 16:00 |  |  | 18 | 0 | 18 | 134 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.9 | R3 - Ph0 - Ramp B and F Lower Drainage | Install DRG OUT-3 to S-149 to S-153 - Ramp F Sta 504 to 508 - R3 - P0 | 2024-06-14 08:00 | 2024-07-12 16:00 |  |  | 18 | 0 | 18 | 83 | 48 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.9 | R3 - Ph0 - Ramp B and F Lower Drainage | Install DRG S-156 to S-160 - Ramp B Sta 624 to 629 - R3 - P0 | 2024-06-07 08:00 | 2024-07-08 16:00 |  |  | 18 | 0 | 18 | 101 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-03-24 08:00 | 2025-05-06 16:00 |  |  | 30 | 0 | 30 | 273 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A27090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Stabilization - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-06-16 08:00 | 2025-06-17 16:00 |  |  | 2 | 0 | 2 | 273 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Asphalt Base - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-06-19 08:00 | 2025-06-19 16:00 |  |  | 1 | 0 | 1 | 273 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Concrete Pav - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-06-20 08:00 | 2025-07-18 16:00 |  |  | 17 | 0 | 17 | 273 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A27120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Edge Drain - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-07-21 08:00 | 2025-07-25 16:00 |  |  | 4 | 0 | 4 | 273 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Shoulder GAB - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-07-28 08:00 | 2025-07-28 16:00 |  |  | 1 | 0 | 1 | 273 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Asphalt Shoulder - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-07-29 08:00 | 2025-07-29 16:00 |  |  | 1 | 0 | 1 | 273 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.16 | R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place 3-Pour Barrier - Ramp EN Sta 91 to 103 - R2 - P1 | 2025-05-08 08:00 | 2025-06-13 16:00 |  |  | 24 | 0 | 24 | 273 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A27170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Wall Barrier - I-4 Sta 311 to 320 - R2 - P1 | 2025-04-30 08:00 | 2025-05-02 16:00 |  |  | 3 | 0 | 3 | 304 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A27190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Cut/Fill to Grade - I-4 Sta 311 to 320 - R2 - P1 | 2024-08-20 08:00 | 2024-08-20 16:00 |  |  | 1 | 0 | 1 | 422 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A27200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Stabilization - I-4 Sta 311 to 320 - R2 - P1 | 2025-04-29 08:00 | 2025-04-29 16:00 |  |  | 1 | 0 | 1 | 304 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Asphalt Base - I-4 Sta 311 to 320 - R2 - P1 | 2025-05-05 08:00 | 2025-05-05 16:00 |  |  | 1 | 0 | 1 | 304 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Concrete Pav - I-4 Sta 311 to 320 - R2 - P1 | 2025-05-06 08:00 | 2025-05-22 16:00 |  |  | 11 | 0 | 11 | 304 |  | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A27230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Edge Drain - I-4 Sta 311 to 320 - R2 - P1 | 2025-06-06 08:00 | 2025-06-10 16:00 |  |  | 3 | 0 | 3 | 295 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Shoulder GAB - I-4 Sta 311 to 320 - R2 - P1 | 2025-06-12 08:00 | 2025-06-12 16:00 |  |  | 1 | 0 | 1 | 299 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.17 | R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Asphalt Shoulder - I-4 Sta 311 to 320 - R2 - P1 | 2025-06-13 08:00 | 2025-06-13 16:00 |  |  | 1 | 0 | 1 | 299 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.12 | R2 - Ph1 - 10th St / 14th Ave Intersection | Grading - 10th St /14th Ave Intersection - R2 - P1 | 2025-05-08 08:00 | 2025-05-08 16:00 |  |  | 1 | 0 | 1 | 278 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A27290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.12 | R2 - Ph1 - 10th St / 14th Ave Intersection | Place Stabilization - 10th St /14th Ave Intersection - R2 - P1 | 2025-06-06 08:00 | 2025-06-13 16:00 |  |  | 5 | 0 | 5 | 278 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.12 | R2 - Ph1 - 10th St / 14th Ave Intersection | Place GAB - 10th St /14th Ave Intersection - R2 - P1 | 2025-06-16 08:00 | 2025-06-17 16:00 |  |  | 2 | 0 | 2 | 278 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.12 | R2 - Ph1 - 10th St / 14th Ave Intersection | Place Curb - 10th St /14th Ave Intersection - R2 - P1 | 2025-06-19 08:00 | 2025-06-19 16:00 |  |  | 1 | 0 | 1 | 278 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A27330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.12 | R2 - Ph1 - 10th St / 14th Ave Intersection | Place Asphalt Surface - 10th St /14th Ave Intersection - R2 - P1 | 2025-06-20 08:00 | 2025-06-20 16:00 |  |  | 1 | 0 | 1 | 295 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.12 | R2 - Ph1 - 10th St / 14th Ave Intersection | Install DRG - 10th St / 14th Ave Intersection - R2 - P1 | 2025-05-09 08:00 | 2025-06-05 16:00 |  |  | 18 | 0 | 18 | 278 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Sidewalk - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-05-19 08:00 | 2025-05-19 16:00 |  |  | 1 | 0 | 1 | 315 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A27340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Grading - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-04-09 08:00 | 2025-04-09 16:00 |  |  | 1 | 0 | 1 | 315 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A27360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Stabilization - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-05-09 08:00 | 2025-05-09 16:00 |  |  | 1 | 0 | 1 | 315 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place GAB - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-05-12 08:00 | 2025-05-12 16:00 |  |  | 1 | 0 | 1 | 315 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Curb - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-05-13 08:00 | 2025-05-16 16:00 |  |  | 3 | 0 | 3 | 315 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A27400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Asphalt Surface - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-05-20 08:00 | 2025-05-20 16:00 |  |  | 1 | 0 | 1 | 315 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.13 | R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Install DRG - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 2025-04-10 08:00 | 2025-05-08 16:00 |  |  | 18 | 0 | 18 | 315 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A27410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.14 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Grading - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | 2025-02-18 08:00 | 2025-02-18 16:00 |  |  | 1 | 0 | 1 | 356 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A27420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.14 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Place Stabilization - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | 2025-02-20 08:00 | 2025-03-03 16:00 |  |  | 7 | 0 | 7 | 356 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.14 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Place Asphalt - 14th Ave Shared Use Path Nebraska to 15th - R2 - P1 | 2025-03-17 08:00 | 2025-03-17 16:00 |  |  | 1 | 0 | 1 | 356 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.14 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Place GAB - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | 2025-03-04 08:00 | 2025-03-14 16:00 |  |  | 7 | 0 | 7 | 356 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.15 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Grading - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 2025-06-20 08:00 | 2025-06-20 16:00 |  |  | 1 | 0 | 1 | 278 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A27460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.15 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place Stabilization - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 2025-06-23 08:00 | 2025-07-01 16:00 |  |  | 6 | 0 | 6 | 278 |  | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.15 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place Asphalt - 14th Ave Shared Use Path Nebraska to Columbus - R2 - P1 | 2025-07-21 08:00 | 2025-07-21 16:00 |  |  | 1 | 0 | 1 | 278 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.15 | R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place GAB - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 2025-07-02 08:00 | 2025-07-18 16:00 |  |  | 10 | 0 | 10 | 278 |  | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.4 | R3 - Ph2, Stg1 - MOT | Shift/Remove Temp Barrier - Ramp B - R3 - P2.S1 | 2025-03-28 08:00 | 2025-04-04 16:00 |  |  | 6 | 0 | 6 | 43 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A27500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.2 | R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Temp Wall or SOE - I-4 Temp Diversion Ramp - R3 - P2.S1 | 2025-04-15 08:00 | 2025-05-13 16:00 |  |  | 18 | 0 | 18 | 43 | 1 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A27530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.2 | R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Cut/Fill to Grade - I-4 Temp Diversion Ramp - R3 - P2.S1 | 2025-04-07 08:00 | 2025-04-14 16:00 |  |  | 6 | 0 | 6 | 43 | 1 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A27540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.2 | R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Place Stabilization - I-4 Temp Diversion Ramp - R3 - P2.S1 | 2025-05-15 08:00 | 2025-05-16 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A27550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.2 | R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Place Temp Asphalt - I-4 Temp Diversion Ramp - R3 - P2.S1 | 2025-05-21 08:00 | 2025-05-21 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A27620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.2 | R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Place GAB - I-4 Temp Diversion Ramp - R3 - P2.S1 | 2025-05-19 08:00 | 2025-05-20 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A27630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.7 | R3 - Ph2, Stg1 - Ramp G / B Gore | Install Guardrail - Ramp G / B Gore - R3 - P2.S1 | 2025-04-22 08:00 | 2025-04-24 16:00 |  |  | 2 | 0 | 2 | 60 | 30 | Sub - Guardrail Crew | SUB.GRAIL | Guardrail
A27640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.4 | R3 - Ph2, Stg1 - MOT | Shift Traffic - I-275 SB to Inside - R3 - P2.S1 | 2025-04-07 08:00 | 2025-04-07 16:00 |  |  | 1 | 0 | 1 | 47 | 8 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A27650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.3.4 | R3 - Ph2, Stg1 - MOT | Install Temp Barrier - I-275 SB - R3 - P2.S1 | 2025-04-08 08:00 | 2025-04-08 16:00 |  |  | 1 | 0 | 1 | 47 | 8 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A27840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.1 | R3 - Ph2, Stg2 - MOT | Shift Traffic - I-4 WB on to Temp Diversion Ramp - R3 - P2.S2 | 2025-05-22 08:00 | 2025-05-22 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A27860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.1 | R3 - Ph2, Stg2 - MOT | Shift Traffic Left on Ramp G - R3 - P2.S2 | 2025-05-23 08:00 | 2025-05-23 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A27870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.1 | R3 - Ph2, Stg2 - MOT | Shift Barrier - Ramp G - R3 - P2.S2 | 2025-05-27 08:00 | 2025-05-27 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A27880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.1 | R3 - Ph2, Stg2 - MOT | Shift Traffic - I-275 SB Right - R3 - P2.S2 | 2025-05-28 08:00 | 2025-05-28 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A27890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.1 | R3 - Ph2, Stg2 - MOT | Install Temp Barrier - I-275 SB - R3 - P2.S2 | 2025-05-29 08:00 | 2025-06-03 16:00 |  |  | 4 | 0 | 4 | 43 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A27900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Excavate - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-06-13 08:00 | 2025-06-13 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A27910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-06-16 08:00 | 2025-07-10 16:00 |  |  | 15 | 0 | 15 | 43 | 1 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A27920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | FRP Column - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-07-24 08:00 | 2025-07-25 16:00 |  |  | 2 | 0 | 2 | 53 | 14 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A27930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Cure/Strip Column - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-07-26 08:00 | 2025-08-01 16:00 |  |  | 7 | 0 | 7 | 89 | 14 |  | CURE | CURE
A27940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | FRP Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-08-04 08:00 | 2025-08-12 16:00 |  |  | 7 | 0 | 7 | 53 | 14 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A27950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-08-13 08:00 | 2025-08-15 16:00 |  |  | 3 | 0 | 3 | 89 | 14 |  | CURE | CURE
A27960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Erect Girders - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-08-18 08:00 | 2025-08-18 16:00 |  |  | 1 | 0 | 1 | 52 | 14 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A27970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Install SIP - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-08-19 08:00 | 2025-08-19 16:00 |  |  | 1 | 0 | 1 | 52 | 14 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A27980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Install Overhangs - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-08-21 08:00 | 2025-09-02 16:00 |  |  | 6 | 0 | 6 | 52 | 14 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A27990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Reinforce Deck - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-09-03 08:00 | 2025-09-04 16:00 |  |  | 2 | 0 | 2 | 52 | 14 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Place Deck - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-09-05 08:00 | 2025-09-05 16:00 |  |  | 1 | 0 | 1 | 52 | 14 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A28010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Cure Deck - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-09-06 08:00 | 2025-09-12 16:00 |  |  | 7 | 0 | 7 | 93 | 26 |  | CURE | CURE
A28020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Install Reinf Barrier - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-09-15 08:00 | 2025-09-15 16:00 |  |  | 1 | 0 | 1 | 53 | 26 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 | R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Strip Overhangs - Brg 100139 - Span 1 - R3 - P2.S2 | 2025-09-16 08:00 | 2025-09-18 16:00 |  |  | 2 | 0 | 2 | 53 | 26 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 | R3 - Ph2, Stg2 - Bridge 100139 - Finishes | FRPS Approach Slab 1 - Brg 100139 - R3 - P2.S2 | 2025-09-08 08:00 | 2025-09-11 16:00 |  |  | 3 | 0 | 3 | 52 | 14 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A28060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 | R3 - Ph2, Stg2 - Bridge 100139 - Finishes | FRPS Approach Slab 2 - Brg 100139 - R3 - P2.S2 | 2025-09-18 08:00 | 2025-09-22 16:00 |  |  | 3 | 0 | 3 | 46 | 12 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A28070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 | R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Slip Barrier - Brg 100139 - R3 - P2.S2 | 2025-10-10 08:00 | 2025-10-13 16:00 |  |  | 2 | 0 | 2 | 40 | 1 | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A28090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 | R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Groove Deck - Brg 100139 - R3 - P2.S2 | 2025-10-14 08:00 | 2025-10-14 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A28100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 | R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Perm Striping - Brg 100139 - R3 - P2.S2 | 2025-10-16 08:00 | 2025-10-16 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A28110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Erect Girders - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-08-25 08:00 | 2025-08-25 16:00 |  |  | 1 | 0 | 1 | 48 | 18 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A28120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Install SIP - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-08-26 08:00 | 2025-08-26 16:00 |  |  | 1 | 0 | 1 | 48 | 18 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A28130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Install Overhangs - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-08-28 08:00 | 2025-09-09 16:00 |  |  | 7 | 0 | 7 | 48 | 18 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Reinforce Deck - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-09-11 08:00 | 2025-09-12 16:00 |  |  | 2 | 0 | 2 | 48 | 18 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Place Deck - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-09-15 08:00 | 2025-09-15 16:00 |  |  | 1 | 0 | 1 | 48 | 18 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A28160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Cure Deck - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-09-16 08:00 | 2025-09-22 16:00 |  |  | 7 | 0 | 7 | 83 | 18 |  | CURE | CURE
A28170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Install Reinf Barrier - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-09-23 08:00 | 2025-09-23 16:00 |  |  | 1 | 0 | 1 | 48 | 18 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 | R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Strip Overhangs - Brg 100139 - Span 2 - R3 - P2.S2 | 2025-09-25 08:00 | 2025-09-26 16:00 |  |  | 2 | 0 | 2 | 48 | 18 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Erect Girders - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-02 08:00 | 2025-09-02 16:00 |  |  | 1 | 0 | 1 | 46 | 12 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A28210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Install SIP - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-03 08:00 | 2025-09-03 16:00 |  |  | 1 | 0 | 1 | 46 | 12 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A28220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Install Overhangs - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-04 08:00 | 2025-09-12 16:00 |  |  | 6 | 0 | 6 | 46 | 12 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Reinforce Deck - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-15 08:00 | 2025-09-15 16:00 |  |  | 1 | 0 | 1 | 46 | 12 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Place Deck - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-16 08:00 | 2025-09-16 16:00 |  |  | 1 | 0 | 1 | 46 | 12 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A28250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Cure Deck - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-17 08:00 | 2025-09-23 16:00 |  |  | 7 | 0 | 7 | 79 | 13 |  | CURE | CURE
A28260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Install Reinf Barrier - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-25 08:00 | 2025-09-26 16:00 |  |  | 2 | 0 | 2 | 46 | 13 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 | R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Strip Overhangs - Brg 100139 - Span 3 - R3 - P2.S2 | 2025-09-29 08:00 | 2025-09-30 16:00 |  |  | 2 | 0 | 2 | 46 | 13 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.8 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Grading - Brg 100139 - End Bent 1 - R3 - P2.S2 | 2025-06-09 08:00 | 2025-06-09 16:00 |  |  | 1 | 0 | 1 | 81 | 70 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A28370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.8 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P2.S2 | 2025-06-16 08:00 | 2025-06-17 16:00 |  |  | 2 | 0 | 2 | 81 | 70 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A28380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.8 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | FRP Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | 2025-06-19 08:00 | 2025-06-27 16:00 |  |  | 6 | 0 | 6 | 81 | 70 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A28390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.8 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | 2025-06-28 08:00 | 2025-06-30 16:00 |  |  | 3 | 0 | 3 | 135 | 70 |  | CURE | CURE
A28410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.8 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-06 16:00 |  |  | 3 | 0 | 3 | 81 | 70 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A28420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.9 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Grading - Brg 100139 - End Bent 2 - R3 - P2.S2 | 2025-06-09 08:00 | 2025-06-09 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A28440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.9 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P2.S2 | 2025-06-13 08:00 | 2025-06-17 16:00 |  |  | 3 | 0 | 3 | 84 | 42 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A28450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.9 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | FRP Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | 2025-06-19 08:00 | 2025-06-24 16:00 |  |  | 4 | 0 | 4 | 84 | 42 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A28460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.9 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | 2025-06-25 08:00 | 2025-06-27 16:00 |  |  | 3 | 0 | 3 | 139 | 42 |  | CURE | CURE
A28480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.9 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-06 16:00 |  |  | 3 | 0 | 3 | 43 | 1 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A28490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 | R3 - Ph2, Stg2 - Bridge 100139 - Demo | Demo Barrier - Brg 100139 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-09 16:00 |  |  | 4 | 0 | 4 | 93 | 43 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A28500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.8 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Demo Abut - Brg 100139 - End Bent 1 - R3 - P2.S2 | 2025-06-10 08:00 | 2025-06-13 16:00 |  |  | 3 | 0 | 3 | 81 | 70 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A28510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.9 | R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P2.S2 | 2025-06-10 08:00 | 2025-06-12 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A28570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Excavate - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-06-09 08:00 | 2025-06-10 16:00 |  |  | 2 | 0 | 2 | 56 | 23 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A28580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Drive Pile - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-06-12 08:00 | 2025-06-20 16:00 |  |  | 6 | 0 | 6 | 56 | 23 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A28590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | FRP Column - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-07-21 08:00 | 2025-07-24 16:00 |  |  | 3 | 0 | 3 | 57 | 23 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A28600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Cure/Strip Column - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-07-25 08:00 | 2025-07-31 16:00 |  |  | 7 | 0 | 7 | 95 | 23 |  | CURE | CURE
A28610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | FRP Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-08-01 08:00 | 2025-08-11 16:00 |  |  | 7 | 0 | 7 | 57 | 23 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A28620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-08-12 08:00 | 2025-08-14 16:00 |  |  | 3 | 0 | 3 | 97 | 23 |  | CURE | CURE
A28630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Erect Girders - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-08-15 08:00 | 2025-08-15 16:00 |  |  | 1 | 0 | 1 | 57 | 23 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A28640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Install SIP - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-08-18 08:00 | 2025-08-18 16:00 |  |  | 1 | 0 | 1 | 57 | 23 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A28650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Install Overhangs - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-08-19 08:00 | 2025-08-22 16:00 |  |  | 3 | 0 | 3 | 57 | 23 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Reinforce Deck - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-08-25 08:00 | 2025-08-25 16:00 |  |  | 1 | 0 | 1 | 57 | 23 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Place Deck - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-08-26 08:00 | 2025-08-26 16:00 |  |  | 1 | 0 | 1 | 57 | 23 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A28680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Cure Deck - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-08-27 08:00 | 2025-09-02 16:00 |  |  | 7 | 0 | 7 | 104 | 28 |  | CURE | CURE
A28690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Install Reinf Barrier - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-09-03 08:00 | 2025-09-03 16:00 |  |  | 1 | 0 | 1 | 61 | 28 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 | R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Strip Overhangs - Brg 100141 - Span 1 - R3 - P2.S2 | 2025-09-04 08:00 | 2025-09-04 16:00 |  |  | 1 | 0 | 1 | 61 | 28 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 | R3 - Ph2, Stg2 - Bridge 100141 - Finishes | FRPS Approach Slab 1 - Brg 100141 - R3 - P2.S2 | 2025-08-28 08:00 | 2025-09-03 16:00 |  |  | 3 | 0 | 3 | 57 | 23 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A28730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 | R3 - Ph2, Stg2 - Bridge 100141 - Finishes | FRPS Approach Slab 2 - Brg 100141 - R3 - P2.S2 | 2025-08-28 08:00 | 2025-09-03 16:00 |  |  | 3 | 0 | 3 | 57 | 24 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A28740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 | R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Slip Barrier - Brg 100141 - R3 - P2.S2 | 2025-09-15 08:00 | 2025-09-15 16:00 |  |  | 1 | 0 | 1 | 56 | 27 | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A28760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 | R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Groove Deck - Brg 100141 - R3 - P2.S2 | 2025-09-16 08:00 | 2025-09-18 16:00 |  |  | 2 | 0 | 2 | 56 | 27 | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A28770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 | R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Perm Striping - Brg 100141 - R3 - P2.S2 | 2025-09-19 08:00 | 2025-09-19 16:00 |  |  | 1 | 0 | 1 | 56 | 27 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A28780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Erect Girders - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-08-15 08:00 | 2025-08-15 16:00 |  |  | 1 | 0 | 1 | 57 | 27 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A28790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Install SIP - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-08-18 08:00 | 2025-08-18 16:00 |  |  | 1 | 0 | 1 | 57 | 27 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A28800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Install Overhangs - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-08-19 08:00 | 2025-08-25 16:00 |  |  | 4 | 0 | 4 | 57 | 27 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Reinforce Deck - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-08-26 08:00 | 2025-08-28 16:00 |  |  | 2 | 0 | 2 | 57 | 27 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Place Deck - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-09-02 08:00 | 2025-09-02 16:00 |  |  | 1 | 0 | 1 | 57 | 27 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A28830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Cure Deck - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-09-03 08:00 | 2025-09-09 16:00 |  |  | 7 | 0 | 7 | 97 | 27 |  | CURE | CURE
A28840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Install Reinf Barrier - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-09-11 08:00 | 2025-09-11 16:00 |  |  | 1 | 0 | 1 | 56 | 27 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 | R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Strip Overhangs - Brg 100141 - Span 2 - R3 - P2.S2 | 2025-09-12 08:00 | 2025-09-12 16:00 |  |  | 1 | 0 | 1 | 56 | 27 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Erect Girders - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-08-15 08:00 | 2025-08-15 16:00 |  |  | 1 | 0 | 1 | 57 | 24 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A28880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Install SIP - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-08-18 08:00 | 2025-08-18 16:00 |  |  | 1 | 0 | 1 | 57 | 24 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A28890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Install Overhangs - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-08-19 08:00 | 2025-08-22 16:00 |  |  | 3 | 0 | 3 | 57 | 24 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Reinforce Deck - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-08-25 08:00 | 2025-08-25 16:00 |  |  | 1 | 0 | 1 | 57 | 24 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Place Deck - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-08-26 08:00 | 2025-08-26 16:00 |  |  | 1 | 0 | 1 | 57 | 24 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A28920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Cure Deck - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-08-27 08:00 | 2025-09-02 16:00 |  |  | 7 | 0 | 7 | 104 | 29 |  | CURE | CURE
A28930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Install Reinf Barrier - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-09-03 08:00 | 2025-09-03 16:00 |  |  | 1 | 0 | 1 | 61 | 29 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A28940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 | R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Strip Overhangs - Brg 100141 - Span 3 - R3 - P2.S2 | 2025-09-04 08:00 | 2025-09-04 16:00 |  |  | 1 | 0 | 1 | 61 | 29 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A28960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Excavate - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-05 16:00 |  |  | 2 | 0 | 2 | 59 | 25 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A28980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | FRP Column - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-07-21 08:00 | 2025-07-24 16:00 |  |  | 3 | 0 | 3 | 57 | 24 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A28990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Cure/Strip Column - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-07-25 08:00 | 2025-07-31 16:00 |  |  | 7 | 0 | 7 | 95 | 24 |  | CURE | CURE
A29000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | FRP Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-08-01 08:00 | 2025-08-11 16:00 |  |  | 7 | 0 | 7 | 57 | 24 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A29010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-08-12 08:00 | 2025-08-14 16:00 |  |  | 3 | 0 | 3 | 97 | 24 |  | CURE | CURE
A29020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.10 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Grading - Brg 100141 - End Bent 1 - R3 - P2.S2 | 2025-06-05 08:00 | 2025-06-05 16:00 |  |  | 1 | 0 | 1 | 56 | 23 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A29040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.10 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P2.S2 | 2025-06-09 08:00 | 2025-06-10 16:00 |  |  | 2 | 0 | 2 | 56 | 23 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A29050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.10 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | 2025-06-12 08:00 | 2025-06-13 16:00 |  |  | 2 | 0 | 2 | 92 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A29060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.10 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | 2025-06-14 08:00 | 2025-06-16 16:00 |  |  | 3 | 0 | 3 | 156 |  |  | CURE | CURE
A29080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.10 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-04 16:00 |  |  | 1 | 0 | 1 | 56 | 23 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A29090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.11 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Grading - Brg 100141 - End Bent 2 - R3 - P2.S2 | 2025-06-05 08:00 | 2025-06-05 16:00 |  |  | 1 | 0 | 1 | 92 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A29110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.11 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P2.S2 | 2025-06-09 08:00 | 2025-06-10 16:00 |  |  | 2 | 0 | 2 | 92 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A29120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.11 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | FRP Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | 2025-06-12 08:00 | 2025-06-13 16:00 |  |  | 2 | 0 | 2 | 92 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A29130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.11 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | 2025-06-14 08:00 | 2025-06-16 16:00 |  |  | 3 | 0 | 3 | 156 |  |  | CURE | CURE
A29150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.11 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-04 16:00 |  |  | 1 | 0 | 1 | 92 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A29160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.7 | R3 - Ph2, Stg2 - Bridge 100141 - Demo | Demo Barrier - Brg 100141 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-06 16:00 |  |  | 3 | 0 | 3 | 98 | 51 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A29170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.10 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Demo Abut - Brg 100141 - End Bent 1 - R3 - P2.S2 | 2025-06-06 08:00 | 2025-06-06 16:00 |  |  | 1 | 0 | 1 | 56 | 23 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A29180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.11 | R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Demo Abut - Brg 100141 - End Bent 2 - R3 - P2.S2 | 2025-06-06 08:00 | 2025-06-06 16:00 |  |  | 1 | 0 | 1 | 92 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A29240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Wall Barrier - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 2025-09-29 08:00 | 2025-09-29 16:00 |  |  | 1 | 0 | 1 | 46 | 12 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A29250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Junction Slab - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 2025-09-25 08:00 | 2025-09-26 16:00 |  |  | 2 | 0 | 2 | 46 | 12 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A29260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Cut/Fill to Grade - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 2025-09-18 08:00 | 2025-09-19 16:00 |  |  | 2 | 0 | 2 | 46 | 12 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A29270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Stabilization - I-275-SB Sta 411 to 422 - R3 - P2.S2 | 2025-09-22 08:00 | 2025-09-23 16:00 |  |  | 2 | 0 | 2 | 46 | 12 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A29300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Edge Drain - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 2025-09-30 08:00 | 2025-10-01 16:00 |  |  | 2 | 0 | 2 | 46 | 12 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A29310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Shoulder GAB - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 2025-10-02 08:00 | 2025-10-03 16:00 |  |  | 2 | 0 | 2 | 46 | 12 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A29320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.5 | R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Asphalt Shoulder - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 2025-10-06 08:00 | 2025-10-06 16:00 |  |  | 1 | 0 | 1 | 46 | 12 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A29350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening |  | 2025-10-16 16:00 |  |  | 0 | 0 | 0 | 57 | 1 |  | MS | MS
LoE320 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 2 Stage 1 - I-4 Temp Diversion Ramp [LoE] | 2025-03-27 08:00 | 2025-05-21 16:00 |  |  | 56 | 0 | 56 | 71 |  |  | LOE | LOE
LoE330 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 2 Stage 2 - I-275 SB Left Widening [LoE] | 2025-05-22 08:00 | 2025-10-16 16:00 |  |  | 148 | 0 | 148 | 81 |  |  | LOE | LOE
A29370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Cure/Strip Footing - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-07-16 08:00 | 2025-07-22 16:00 |  |  | 7 | 0 | 7 | 90 | 14 |  | CURE | CURE
A29380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Grading - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-07-10 08:00 | 2025-07-10 16:00 |  |  | 1 | 0 | 1 | 43 | 1 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A29390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Drive Pile - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-07-11 08:00 | 2025-07-15 16:00 |  |  | 3 | 0 | 3 | 49 | 18 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A29400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | FRP Column - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-07-29 08:00 | 2025-07-31 16:00 |  |  | 3 | 0 | 3 | 49 | 18 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A29410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Cure/Strip Column - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-08-01 08:00 | 2025-08-07 16:00 |  |  | 7 | 0 | 7 | 83 | 18 |  | CURE | CURE
A29420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | FRP Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-08-08 08:00 | 2025-08-19 16:00 |  |  | 7 | 0 | 7 | 49 | 18 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A29430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-08-20 08:00 | 2025-08-22 16:00 |  |  | 3 | 0 | 3 | 82 | 18 |  | CURE | CURE
A29440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | FRP Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-07-17 08:00 | 2025-07-21 16:00 |  |  | 3 | 0 | 3 | 49 | 18 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A29450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Cure/Strip Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | 2025-07-22 08:00 | 2025-07-28 16:00 |  |  | 7 | 0 | 7 | 83 | 18 |  | CURE | CURE
A29460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Excavate - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-07-11 08:00 | 2025-07-14 16:00 |  |  | 2 | 0 | 2 | 43 | 1 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A29470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-07-15 08:00 | 2025-07-24 16:00 |  |  | 6 | 0 | 6 | 43 | 1 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A29480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | FRP Column - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-08-06 08:00 | 2025-08-07 16:00 |  |  | 2 | 0 | 2 | 46 | 12 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A29490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Cure/Strip Column - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-08-08 08:00 | 2025-08-14 16:00 |  |  | 7 | 0 | 7 | 80 | 12 |  | CURE | CURE
A29500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | FRP Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-08-15 08:00 | 2025-08-25 16:00 |  |  | 6 | 0 | 6 | 47 | 12 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A29510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-08-26 08:00 | 2025-08-28 16:00 |  |  | 3 | 0 | 3 | 77 | 12 |  | CURE | CURE
A29530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Cure/Strip Footing - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-07-30 08:00 | 2025-08-05 16:00 |  |  | 7 | 0 | 7 | 78 | 12 |  | CURE | CURE
A29540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Excavate - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-06-04 08:00 | 2025-06-04 16:00 |  |  | 1 | 0 | 1 | 69 | 39 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A29550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Drive Pile - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-06-05 08:00 | 2025-06-09 16:00 |  |  | 3 | 0 | 3 | 69 | 39 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A29560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | FRP Column - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-08-11 08:00 | 2025-08-12 16:00 |  |  | 2 | 0 | 2 | 42 | 1 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A29570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Cure/Strip Column - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-08-13 08:00 | 2025-08-19 16:00 |  |  | 7 | 0 | 7 | 72 | 1 |  | CURE | CURE
A29580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | FRP Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-08-21 08:00 | 2025-09-02 16:00 |  |  | 6 | 0 | 6 | 43 | 1 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A29590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-09-03 08:00 | 2025-09-05 16:00 |  |  | 3 | 0 | 3 | 68 | 1 |  | CURE | CURE
A29600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | FRP Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-07-25 08:00 | 2025-08-01 16:00 |  |  | 6 | 0 | 6 | 43 | 1 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A29610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Cure/Strip Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | 2025-08-02 08:00 | 2025-08-08 16:00 |  |  | 7 | 0 | 7 | 74 | 1 |  | CURE | CURE
A29620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Grading - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-06-05 08:00 | 2025-06-05 16:00 |  |  | 1 | 0 | 1 | 70 | 41 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A29630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Drive Pile - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-06-06 08:00 | 2025-06-10 16:00 |  |  | 3 | 0 | 3 | 70 | 41 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A29640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | FRP Column - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-06-24 08:00 | 2025-06-27 16:00 |  |  | 3 | 0 | 3 | 70 | 41 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A29650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Cure/Strip Column - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-06-28 08:00 | 2025-07-04 16:00 |  |  | 7 | 0 | 7 | 118 | 41 |  | CURE | CURE
A29660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | FRP Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-07-07 08:00 | 2025-07-15 16:00 |  |  | 6 | 0 | 6 | 71 | 41 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A29670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-07-16 08:00 | 2025-07-18 16:00 |  |  | 3 | 0 | 3 | 117 | 41 |  | CURE | CURE
A29680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | FRP Footing - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-06-12 08:00 | 2025-06-16 16:00 |  |  | 3 | 0 | 3 | 70 | 41 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A29690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Cure/Strip Footing - Brg 100139 - Pier 5 - R3 - P2.S2 | 2025-06-17 08:00 | 2025-06-23 16:00 |  |  | 7 | 0 | 7 | 119 | 41 |  | CURE | CURE
A29860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Erect Girders - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-08 08:00 | 2025-09-08 16:00 |  |  | 1 | 0 | 1 | 47 | 15 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A29870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Install SIP - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-09 08:00 | 2025-09-09 16:00 |  |  | 1 | 0 | 1 | 47 | 15 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A29880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Install Overhangs - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-11 08:00 | 2025-09-12 16:00 |  |  | 2 | 0 | 2 | 47 | 15 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A29890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Reinforce Deck - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-15 08:00 | 2025-09-16 16:00 |  |  | 2 | 0 | 2 | 47 | 15 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A29900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Place Deck - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-18 08:00 | 2025-09-18 16:00 |  |  | 1 | 0 | 1 | 47 | 15 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A29910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Cure Deck - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-19 08:00 | 2025-09-25 16:00 |  |  | 7 | 0 | 7 | 81 | 15 |  | CURE | CURE
A29920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Install Reinf Barrier - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-26 08:00 | 2025-09-26 16:00 |  |  | 1 | 0 | 1 | 47 | 15 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A29930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 | R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Strip Overhangs - Brg 100139 - Span 4 - R3 - P2.S2 | 2025-09-29 08:00 | 2025-09-29 16:00 |  |  | 1 | 0 | 1 | 47 | 15 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A29950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Erect Girders - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-09-08 08:00 | 2025-09-08 16:00 |  |  | 1 | 0 | 1 | 41 | 1 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A29960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Install SIP - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-09-09 08:00 | 2025-09-09 16:00 |  |  | 1 | 0 | 1 | 41 | 1 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A29970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Install Overhangs - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-09-11 08:00 | 2025-09-22 16:00 |  |  | 7 | 0 | 7 | 41 | 1 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A29980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Reinforce Deck - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-09-23 08:00 | 2025-09-23 16:00 |  |  | 1 | 0 | 1 | 41 | 1 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A29990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Place Deck - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-09-25 08:00 | 2025-09-25 16:00 |  |  | 1 | 0 | 1 | 41 | 1 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A30000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Cure Deck - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-09-26 08:00 | 2025-10-02 16:00 |  |  | 7 | 0 | 7 | 73 | 4 |  | CURE | CURE
A30010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Install Reinf Barrier - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-10-03 08:00 | 2025-10-03 16:00 |  |  | 1 | 0 | 1 | 41 | 4 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 | R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Strip Overhangs - Brg 100139 - Span 5 - R3 - P2.S2 | 2025-10-06 08:00 | 2025-10-07 16:00 |  |  | 2 | 0 | 2 | 41 | 4 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-07-21 08:00 | 2025-07-21 16:00 |  |  | 1 | 0 | 1 | 71 | 41 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A30050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install SIP - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-07-22 08:00 | 2025-07-22 16:00 |  |  | 1 | 0 | 1 | 71 | 41 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A30060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install Overhangs - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-07-24 08:00 | 2025-07-31 16:00 |  |  | 6 | 0 | 6 | 71 | 41 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Reinforce Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-08-01 08:00 | 2025-08-04 16:00 |  |  | 2 | 0 | 2 | 71 | 41 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Place Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-09-26 08:00 | 2025-09-26 16:00 |  |  | 1 | 0 | 1 | 41 | 1 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A30090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Cure Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-09-27 08:00 | 2025-10-03 16:00 |  |  | 7 | 0 | 7 | 72 | 1 |  | CURE | CURE
A30100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install Reinf Barrier - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-10-06 08:00 | 2025-10-06 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 | R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Strip Overhangs - Brg 100139 - Span 6 - R3 - P2.S2 | 2025-10-07 08:00 | 2025-10-09 16:00 |  |  | 2 | 0 | 2 | 40 | 1 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Cure/Strip Footing - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-07-12 08:00 | 2025-07-18 16:00 |  |  | 7 | 0 | 7 | 96 | 23 |  | CURE | CURE
A30330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Drive Pile - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-06-06 08:00 | 2025-06-16 16:00 |  |  | 6 | 0 | 6 | 59 | 25 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A30340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | FRP Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-06-23 08:00 | 2025-07-11 16:00 |  |  | 12 | 0 | 12 | 56 | 24 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A30350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Cure/Strip Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | 2025-07-12 08:00 | 2025-07-18 16:00 |  |  | 7 | 0 | 7 | 96 | 24 |  | CURE | CURE
A30360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.1 | R3 - Ph3 - MOT | Shift Traffic - Ramp C Left - R3 - P3 | 2025-10-20 08:00 | 2025-10-20 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A30370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.1 | R3 - Ph3 - MOT | Install Temp Barrier - Ramp C - R3 - P3 | 2025-10-17 08:00 | 2025-10-17 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A30420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | Grading - Brg 100139 - Pier 1 - R3 - P3 | 2025-12-11 08:00 | 2025-12-11 16:00 |  |  | 1 | 0 | 1 | 86 | 62 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A30430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P3 | 2025-12-12 08:00 | 2025-12-16 16:00 |  |  | 3 | 0 | 3 | 86 | 62 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A30440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | FRP Column - Brg 100139 - Pier 1 - R3 - P3 | 2026-01-23 08:00 | 2026-01-23 16:00 |  |  | 1 | 0 | 1 | 87 | 62 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A30450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | Cure/Strip Column - Brg 100139 - Pier 1 - R3 - P3 | 2026-01-24 08:00 | 2026-01-30 16:00 |  |  | 7 | 0 | 7 | 142 | 62 |  | CURE | CURE
A30460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | FRP Cap - Brg 100139 - Pier 1 - R3 - P3 | 2026-02-02 08:00 | 2026-02-05 16:00 |  |  | 4 | 0 | 4 | 87 | 62 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A30470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P3 | 2026-02-06 08:00 | 2026-02-08 16:00 |  |  | 3 | 0 | 3 | 141 | 62 |  | CURE | CURE
A30480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Erect Girders - Brg 100139 - Span 1 - R3 - P3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 87 | 62 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A30490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Install SIP - Brg 100139 - Span 1 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 87 | 62 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A30500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Install Overhangs - Brg 100139 - Span 1 - R3 - P3 | 2026-02-12 08:00 | 2026-02-20 16:00 |  |  | 6 | 0 | 6 | 87 | 62 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Reinforce Deck - Brg 100139 - Span 1 - R3 - P3 | 2026-02-23 08:00 | 2026-02-23 16:00 |  |  | 1 | 0 | 1 | 87 | 62 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Place Deck - Brg 100139 - Span 1 - R3 - P3 | 2026-02-24 08:00 | 2026-02-24 16:00 |  |  | 1 | 0 | 1 | 87 | 62 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A30530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Cure Deck - Brg 100139 - Span 1 - R3 - P3 | 2026-02-25 08:00 | 2026-03-03 16:00 |  |  | 7 | 0 | 7 | 148 | 62 |  | CURE | CURE
A30540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Install Reinf Barrier - Brg 100139 - Span 1 - R3 - P3 | 2026-03-04 08:00 | 2026-03-04 16:00 |  |  | 1 | 0 | 1 | 91 | 62 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 | R3 - Ph3 - Bridge 100139 - Span 1 | Strip Overhangs - Brg 100139 - Span 1 - R3 - P3 | 2026-03-05 08:00 | 2026-03-06 16:00 |  |  | 2 | 0 | 2 | 91 | 62 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 | R3 - Ph3 - Bridge 100139 - Finishes | FRPS Approach Slab 1 - Brg 100139 - R3 - P3 | 2026-02-26 08:00 | 2026-02-27 16:00 |  |  | 2 | 0 | 2 | 87 | 65 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A30580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 | R3 - Ph3 - Bridge 100139 - Finishes | FRPS Approach Slab 2 - Brg 100139 - R3 - P3 | 2026-03-04 08:00 | 2026-03-05 16:00 |  |  | 2 | 0 | 2 | 64 | 36 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A30590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 | R3 - Ph3 - Bridge 100139 - Finishes | Slip Barrier - Brg 100139 - R3 - P3 | 2026-03-20 08:00 | 2026-03-23 16:00 |  |  | 2 | 0 | 2 | 84 | 58 | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A30610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 | R3 - Ph3 - Bridge 100139 - Finishes | Groove Deck - Brg 100139 - R3 - P3 | 2026-03-24 08:00 | 2026-03-24 16:00 |  |  | 1 | 0 | 1 | 84 | 58 | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A30620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 | R3 - Ph3 - Bridge 100139 - Finishes | Perm Striping - Brg 100139 - R3 - P3 | 2026-03-26 08:00 | 2026-03-26 16:00 |  |  | 1 | 0 | 1 | 84 | 58 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A30630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Erect Girders - Brg 100139 - Span 2 - R3 - P3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 90 | 63 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A30640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Install SIP - Brg 100139 - Span 2 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 90 | 63 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A30650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Install Overhangs - Brg 100139 - Span 2 - R3 - P3 | 2026-02-12 08:00 | 2026-02-20 16:00 |  |  | 6 | 0 | 6 | 90 | 63 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Reinforce Deck - Brg 100139 - Span 2 - R3 - P3 | 2026-02-23 08:00 | 2026-02-23 16:00 |  |  | 1 | 0 | 1 | 90 | 63 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Place Deck - Brg 100139 - Span 2 - R3 - P3 | 2026-02-24 08:00 | 2026-02-24 16:00 |  |  | 1 | 0 | 1 | 90 | 63 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A30680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Cure Deck - Brg 100139 - Span 2 - R3 - P3 | 2026-02-25 08:00 | 2026-03-03 16:00 |  |  | 7 | 0 | 7 | 148 | 63 |  | CURE | CURE
A30690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Install Reinf Barrier - Brg 100139 - Span 2 - R3 - P3 | 2026-03-04 08:00 | 2026-03-04 16:00 |  |  | 1 | 0 | 1 | 91 | 63 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 | R3 - Ph3 - Bridge 100139 - Span 2 | Strip Overhangs - Brg 100139 - Span 2 - R3 - P3 | 2026-03-05 08:00 | 2026-03-06 16:00 |  |  | 2 | 0 | 2 | 91 | 63 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Erect Girders - Brg 100139 - Span 3 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A30730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Install SIP - Brg 100139 - Span 3 - R3 - P3 | 2026-02-12 08:00 | 2026-02-12 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A30740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Install Overhangs - Brg 100139 - Span 3 - R3 - P3 | 2026-02-13 08:00 | 2026-02-27 16:00 |  |  | 9 | 0 | 9 | 64 | 36 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Reinforce Deck - Brg 100139 - Span 3 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Place Deck - Brg 100139 - Span 3 - R3 - P3 | 2026-03-03 08:00 | 2026-03-03 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A30770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Cure Deck - Brg 100139 - Span 3 - R3 - P3 | 2026-03-04 08:00 | 2026-03-10 16:00 |  |  | 7 | 0 | 7 | 140 | 59 |  | CURE | CURE
A30780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Install Reinf Barrier - Brg 100139 - Span 3 - R3 - P3 | 2026-03-12 08:00 | 2026-03-12 16:00 |  |  | 1 | 0 | 1 | 85 | 59 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A30790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 | R3 - Ph3 - Bridge 100139 - Span 3 | Strip Overhangs - Brg 100139 - Span 3 - R3 - P3 | 2026-03-13 08:00 | 2026-03-17 16:00 |  |  | 3 | 0 | 3 | 85 | 59 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A30810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.8 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Grading - Brg 100139 - End Bent 1 - R3 - P3 | 2025-12-16 08:00 | 2025-12-16 16:00 |  |  | 1 | 0 | 1 | 103 | 66 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A30830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.8 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P3 | 2025-12-22 08:00 | 2025-12-23 16:00 |  |  | 2 | 0 | 2 | 103 | 66 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A30840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.8 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | FRP Abt Cap - Brg 100139 - End Bent 1 - R3 - P3 | 2026-01-05 08:00 | 2026-01-08 16:00 |  |  | 4 | 0 | 4 | 103 | 66 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A30850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.8 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P3 | 2026-01-09 08:00 | 2026-01-11 16:00 |  |  | 3 | 0 | 3 | 169 | 66 |  | CURE | CURE
A30870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.8 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P3 | 2025-12-11 08:00 | 2025-12-15 16:00 |  |  | 3 | 0 | 3 | 103 | 66 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A30880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.9 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Grading - Brg 100139 - End Bent 2 - R3 - P3 | 2025-12-16 08:00 | 2025-12-16 16:00 |  |  | 1 | 0 | 1 | 97 | 67 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A30900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.9 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P3 | 2025-12-19 08:00 | 2025-12-19 16:00 |  |  | 1 | 0 | 1 | 97 | 67 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A30910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.9 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | FRP Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | 2025-12-22 08:00 | 2026-01-05 16:00 |  |  | 3 | 0 | 3 | 97 | 67 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A30920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.9 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | 2026-01-06 08:00 | 2026-01-08 16:00 |  |  | 3 | 0 | 3 | 157 | 67 |  | CURE | CURE
A30940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.9 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P3 | 2025-12-11 08:00 | 2025-12-15 16:00 |  |  | 3 | 0 | 3 | 97 | 67 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A30960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.8 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Demo Abut - Brg 100139 - End Bent 1 - R3 - P3 | 2025-12-18 08:00 | 2025-12-19 16:00 |  |  | 2 | 0 | 2 | 103 | 66 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A30970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.9 | R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P3 | 2025-12-18 08:00 | 2025-12-18 16:00 |  |  | 1 | 0 | 1 | 97 | 67 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A30980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | Excavate - Brg 100141 - Pier 1 - R3 - P3 | 2025-12-18 08:00 | 2025-12-18 16:00 |  |  | 1 | 0 | 1 | 70 | 38 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A30990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | Drive Pile - Brg 100141 - Pier 1 - R3 - P3 | 2025-12-19 08:00 | 2026-01-07 16:00 |  |  | 6 | 0 | 6 | 70 | 38 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A31000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | FRP Column - Brg 100141 - Pier 1 - R3 - P3 | 2026-01-26 08:00 | 2026-01-26 16:00 |  |  | 1 | 0 | 1 | 71 | 38 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A31010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | Cure/Strip Column - Brg 100141 - Pier 1 - R3 - P3 | 2026-01-27 08:00 | 2026-02-02 16:00 |  |  | 7 | 0 | 7 | 113 | 38 |  | CURE | CURE
A31020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | FRP Cap - Brg 100141 - Pier 1 - R3 - P3 | 2026-02-03 08:00 | 2026-02-05 16:00 |  |  | 3 | 0 | 3 | 70 | 38 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A31030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P3 | 2026-02-06 08:00 | 2026-02-08 16:00 |  |  | 3 | 0 | 3 | 114 | 38 |  | CURE | CURE
A31040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Erect Girders - Brg 100141 - Span 1 - R3 - P3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 71 | 38 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A31050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Install SIP - Brg 100141 - Span 1 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 71 | 38 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A31060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Install Overhangs - Brg 100141 - Span 1 - R3 - P3 | 2026-02-12 08:00 | 2026-02-16 16:00 |  |  | 3 | 0 | 3 | 71 | 38 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A31070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Reinforce Deck - Brg 100141 - Span 1 - R3 - P3 | 2026-02-17 08:00 | 2026-02-17 16:00 |  |  | 1 | 0 | 1 | 71 | 38 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A31080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Place Deck - Brg 100141 - Span 1 - R3 - P3 | 2026-02-19 08:00 | 2026-02-19 16:00 |  |  | 1 | 0 | 1 | 71 | 38 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A31090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Cure Deck - Brg 100141 - Span 1 - R3 - P3 | 2026-02-20 08:00 | 2026-02-26 16:00 |  |  | 7 | 0 | 7 | 154 |  |  | CURE | CURE
A31100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Install Reinf Barrier - Brg 100141 - Span 1 - R3 - P3 | 2026-02-27 08:00 | 2026-02-27 16:00 |  |  | 1 | 0 | 1 | 95 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A31110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 | R3 - Ph3 - Bridge 100141 - Span 1 | Strip Overhangs - Brg 100141 - Span 1 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 95 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A31130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 | R3 - Ph3 - Bridge 100141 - Finishes | FRPS Approach Slab 1 - Brg 100141 - R3 - P3 | 2026-02-20 08:00 | 2026-02-23 16:00 |  |  | 2 | 0 | 2 | 71 | 38 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A31140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 | R3 - Ph3 - Bridge 100141 - Finishes | FRPS Approach Slab 2 - Brg 100141 - R3 - P3 | 2026-02-19 08:00 | 2026-02-20 16:00 |  |  | 2 | 0 | 2 | 89 | 53 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A31150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 | R3 - Ph3 - Bridge 100141 - Finishes | Slip Barrier - Brg 100141 - R3 - P3 | 2026-03-05 08:00 | 2026-03-05 16:00 |  |  | 1 | 0 | 1 | 93 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A31170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 | R3 - Ph3 - Bridge 100141 - Finishes | Groove Deck - Brg 100141 - R3 - P3 | 2026-03-06 08:00 | 2026-03-09 16:00 |  |  | 2 | 0 | 2 | 93 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A31180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 | R3 - Ph3 - Bridge 100141 - Finishes | Perm Striping - Brg 100141 - R3 - P3 | 2026-03-10 08:00 | 2026-03-10 16:00 |  |  | 1 | 0 | 1 | 93 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A31190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Erect Girders - Brg 100141 - Span 2 - R3 - P3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 92 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A31200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Install SIP - Brg 100141 - Span 2 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 92 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A31210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Install Overhangs - Brg 100141 - Span 2 - R3 - P3 | 2026-02-12 08:00 | 2026-02-17 16:00 |  |  | 4 | 0 | 4 | 92 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A31220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Reinforce Deck - Brg 100141 - Span 2 - R3 - P3 | 2026-02-19 08:00 | 2026-02-20 16:00 |  |  | 2 | 0 | 2 | 92 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A31230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Place Deck - Brg 100141 - Span 2 - R3 - P3 | 2026-02-23 08:00 | 2026-02-23 16:00 |  |  | 1 | 0 | 1 | 92 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A31240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Cure Deck - Brg 100141 - Span 2 - R3 - P3 | 2026-02-24 08:00 | 2026-03-02 16:00 |  |  | 7 | 0 | 7 | 150 |  |  | CURE | CURE
A31250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Install Reinf Barrier - Brg 100141 - Span 2 - R3 - P3 | 2026-03-03 08:00 | 2026-03-03 16:00 |  |  | 1 | 0 | 1 | 93 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A31260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 | R3 - Ph3 - Bridge 100141 - Span 2 | Strip Overhangs - Brg 100141 - Span 2 - R3 - P3 | 2026-03-04 08:00 | 2026-03-04 16:00 |  |  | 1 | 0 | 1 | 93 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A31280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Erect Girders - Brg 100141 - Span 3 - R3 - P3 | 2026-02-06 08:00 | 2026-02-06 16:00 |  |  | 1 | 0 | 1 | 89 | 53 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A31290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Install SIP - Brg 100141 - Span 3 - R3 - P3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 89 | 53 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A31300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Install Overhangs - Brg 100141 - Span 3 - R3 - P3 | 2026-02-10 08:00 | 2026-02-13 16:00 |  |  | 3 | 0 | 3 | 89 | 53 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A31310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Reinforce Deck - Brg 100141 - Span 3 - R3 - P3 | 2026-02-16 08:00 | 2026-02-16 16:00 |  |  | 1 | 0 | 1 | 89 | 53 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A31320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Place Deck - Brg 100141 - Span 3 - R3 - P3 | 2026-02-17 08:00 | 2026-02-17 16:00 |  |  | 1 | 0 | 1 | 89 | 53 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A31330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Cure Deck - Brg 100141 - Span 3 - R3 - P3 | 2026-02-18 08:00 | 2026-02-24 16:00 |  |  | 7 | 0 | 7 | 156 |  |  | CURE | CURE
A31340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Install Reinf Barrier - Brg 100141 - Span 3 - R3 - P3 | 2026-02-26 08:00 | 2026-02-26 16:00 |  |  | 1 | 0 | 1 | 96 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A31350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 | R3 - Ph3 - Bridge 100141 - Span 3 | Strip Overhangs - Brg 100141 - Span 3 - R3 - P3 | 2026-02-27 08:00 | 2026-02-27 16:00 |  |  | 1 | 0 | 1 | 96 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A31370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | Excavate - Brg 100141 - Pier 2 - R3 - P3 | 2025-12-18 08:00 | 2025-12-18 16:00 |  |  | 1 | 0 | 1 | 89 | 53 | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A31380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | FRP Column - Brg 100141 - Pier 2 - R3 - P3 | 2026-01-20 08:00 | 2026-01-20 16:00 |  |  | 1 | 0 | 1 | 90 | 53 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A31390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | Cure/Strip Column - Brg 100141 - Pier 2 - R3 - P3 | 2026-01-21 08:00 | 2026-01-27 16:00 |  |  | 7 | 0 | 7 | 146 | 53 |  | CURE | CURE
A31400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | FRP Cap - Brg 100141 - Pier 2 - R3 - P3 | 2026-01-29 08:00 | 2026-02-02 16:00 |  |  | 3 | 0 | 3 | 90 | 53 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A31410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P3 | 2026-02-03 08:00 | 2026-02-05 16:00 |  |  | 3 | 0 | 3 | 145 | 53 |  | CURE | CURE
A31420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.10 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Grading - Brg 100141 - End Bent 1 - R3 - P3 | 2025-12-19 08:00 | 2025-12-19 16:00 |  |  | 1 | 0 | 1 | 87 | 40 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A31440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.10 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P3 | 2026-01-05 08:00 | 2026-01-05 16:00 |  |  | 1 | 0 | 1 | 87 | 40 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A31450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.10 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P3 | 2026-01-06 08:00 | 2026-01-07 16:00 |  |  | 2 | 0 | 2 | 87 | 40 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A31460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.10 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P3 | 2026-01-08 08:00 | 2026-01-10 16:00 |  |  | 3 | 0 | 3 | 143 | 40 |  | CURE | CURE
A31480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.10 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P3 | 2025-12-18 08:00 | 2025-12-18 16:00 |  |  | 1 | 0 | 1 | 87 | 40 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A31490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.11 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Grading - Brg 100141 - End Bent 2 - R3 - P3 | 2025-12-19 08:00 | 2025-12-19 16:00 |  |  | 1 | 0 | 1 | 105 | 54 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A31510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.11 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P3 | 2025-12-23 08:00 | 2025-12-23 16:00 |  |  | 1 | 0 | 1 | 105 | 54 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A31520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.11 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | FRP Abt Cap - Brg 100141 - End Bent 2 - R3 - P3 | 2026-01-05 08:00 | 2026-01-06 16:00 |  |  | 2 | 0 | 2 | 105 | 54 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A31530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.11 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P3 | 2026-01-07 08:00 | 2026-01-09 16:00 |  |  | 3 | 0 | 3 | 172 | 54 |  | CURE | CURE
A31550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.11 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P3 | 2025-12-18 08:00 | 2025-12-18 16:00 |  |  | 1 | 0 | 1 | 105 | 54 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A31570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.10 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Demo Abut - Brg 100141 - End Bent 1 - R3 - P3 | 2025-12-22 08:00 | 2025-12-23 16:00 |  |  | 2 | 0 | 2 | 87 | 40 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A31580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.11 | R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Demo Abut - Brg 100141 - End Bent 2 - R3 - P3 | 2025-12-22 08:00 | 2025-12-22 16:00 |  |  | 1 | 0 | 1 | 105 | 54 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A31590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Wall Barrier - I-275 SB Sta 409 to 413 - R3 - P3 | 2026-03-10 08:00 | 2026-03-12 16:00 |  |  | 2 | 0 | 2 | 87 | 69 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A31600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Junction Slab - I-275 SB Sta 409 to 413 - R3 - P3 | 2026-03-03 08:00 | 2026-03-09 16:00 |  |  | 5 | 0 | 5 | 87 | 69 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A31610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Cut/Fill to Grade - I-275 SB Sta 409 to 413 - R3 - P3 | 2026-02-26 08:00 | 2026-02-27 16:00 |  |  | 2 | 0 | 2 | 87 | 69 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A31620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Stabilization - I-275-SB Sta 409 to 413 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 87 | 69 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A31630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Edge Drain - I-275 SB Sta 409 to 413 - R3 - P3 | 2026-03-13 08:00 | 2026-03-16 16:00 |  |  | 2 | 0 | 2 | 87 | 69 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A31640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Shoulder GAB - I-275 SB Sta 409 to 413 - R3 - P3 | 2026-03-17 08:00 | 2026-03-19 16:00 |  |  | 2 | 0 | 2 | 87 | 69 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A31650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.5 | R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Asphalt Shoulder - I-275 SB Sta 409 to 413 - R3 - P3 | 2026-03-20 08:00 | 2026-03-20 16:00 |  |  | 1 | 0 | 1 | 87 | 69 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A31670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | Cure/Strip Footing - Brg 100139 - Pier 1 - R3 - P3 | 2026-01-16 08:00 | 2026-01-22 16:00 |  |  | 7 | 0 | 7 | 140 | 62 |  | CURE | CURE
A31680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | Grading - Brg 100139 - Pier 2 - R3 - P3 | 2025-12-11 08:00 | 2025-12-11 16:00 |  |  | 1 | 0 | 1 | 64 | 37 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A31690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | Install Drilled Shaft - Brg 100139 - Pier 2 - R3 - P3 | 2025-12-12 08:00 | 2025-12-16 16:00 |  |  | 3 | 0 | 3 | 64 | 37 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A31700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | FRP Column - Brg 100139 - Pier 2 - R3 - P3 | 2026-01-23 08:00 | 2026-01-26 16:00 |  |  | 2 | 0 | 2 | 66 | 37 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A31710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | Cure/Strip Column - Brg 100139 - Pier 2 - R3 - P3 | 2026-01-27 08:00 | 2026-02-02 16:00 |  |  | 7 | 0 | 7 | 105 | 37 |  | CURE | CURE
A31720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | FRP Cap - Brg 100139 - Pier 2 - R3 - P3 | 2026-02-03 08:00 | 2026-02-05 16:00 |  |  | 3 | 0 | 3 | 66 | 37 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A31730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P3 | 2026-02-06 08:00 | 2026-02-08 16:00 |  |  | 3 | 0 | 3 | 106 | 37 |  | CURE | CURE
A31750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | Cure/Strip Footing - Brg 100139 - Pier 2 - R3 - P3 | 2026-01-16 08:00 | 2026-01-22 16:00 |  |  | 7 | 0 | 7 | 105 | 37 |  | CURE | CURE
A31760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | Grading - Brg 100139 - Pier 3 - R3 - P3 | 2025-12-11 08:00 | 2025-12-11 16:00 |  |  | 1 | 0 | 1 | 63 | 36 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A31770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P3 | 2025-12-12 08:00 | 2025-12-16 16:00 |  |  | 3 | 0 | 3 | 63 | 36 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A31780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | FRP Column - Brg 100139 - Pier 3 - R3 - P3 | 2026-01-23 08:00 | 2026-01-26 16:00 |  |  | 2 | 0 | 2 | 65 | 36 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A31790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | Cure/Strip Column - Brg 100139 - Pier 3 - R3 - P3 | 2026-01-27 08:00 | 2026-02-02 16:00 |  |  | 7 | 0 | 7 | 104 | 36 |  | CURE | CURE
A31800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | FRP Cap - Brg 100139 - Pier 3 - R3 - P3 | 2026-02-03 08:00 | 2026-02-06 16:00 |  |  | 4 | 0 | 4 | 65 | 36 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A31810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P3 | 2026-02-07 08:00 | 2026-02-09 16:00 |  |  | 3 | 0 | 3 | 105 | 36 |  | CURE | CURE
A31830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | Cure/Strip Footing - Brg 100139 - Pier 3 - R3 - P3 | 2026-01-16 08:00 | 2026-01-22 16:00 |  |  | 7 | 0 | 7 | 104 | 36 |  | CURE | CURE
A31840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | Grading - Brg 100139 - Pier 4 - R3 - P3 | 2025-12-11 08:00 | 2025-12-11 16:00 |  |  | 1 | 0 | 1 | 81 | 58 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A31850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | Install Drilled Shaft - Brg 100139 - Pier 4 - R3 - P3 | 2025-12-12 08:00 | 2025-12-16 16:00 |  |  | 3 | 0 | 3 | 81 | 58 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A31860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | FRP Column - Brg 100139 - Pier 4 - R3 - P3 | 2026-01-23 08:00 | 2026-01-26 16:00 |  |  | 2 | 0 | 2 | 83 | 58 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A31870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | Cure/Strip Column - Brg 100139 - Pier 4 - R3 - P3 | 2026-01-27 08:00 | 2026-02-02 16:00 |  |  | 7 | 0 | 7 | 133 | 58 |  | CURE | CURE
A31880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | FRP Cap - Brg 100139 - Pier 4 - R3 - P3 | 2026-02-03 08:00 | 2026-02-06 16:00 |  |  | 4 | 0 | 4 | 83 | 58 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A31890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P3 | 2026-02-07 08:00 | 2026-02-09 16:00 |  |  | 3 | 0 | 3 | 136 | 58 |  | CURE | CURE
A31920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | Grading - Brg 100139 - Pier 5 - R3 - P3 | 2025-12-11 08:00 | 2025-12-11 16:00 |  |  | 1 | 0 | 1 | 86 | 61 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A31930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | Install Drilled Shaft - Brg 100139 - Pier 5 - R3 - P3 | 2025-12-12 08:00 | 2025-12-16 16:00 |  |  | 3 | 0 | 3 | 86 | 61 | Sub - Drilled Shaft Crew | SUB.STRUCTURE.DRSF | STRUCTURE.Drilled Shaft
A31940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | FRP Column - Brg 100139 - Pier 5 - R3 - P3 | 2026-01-23 08:00 | 2026-01-26 16:00 |  |  | 2 | 0 | 2 | 87 | 61 | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A31950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | Cure/Strip Column - Brg 100139 - Pier 5 - R3 - P3 | 2026-01-27 08:00 | 2026-02-02 16:00 |  |  | 7 | 0 | 7 | 140 | 61 |  | CURE | CURE
A31960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | FRP Cap - Brg 100139 - Pier 5 - R3 - P3 | 2026-02-03 08:00 | 2026-02-05 16:00 |  |  | 3 | 0 | 3 | 87 | 61 | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A31970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P3 | 2026-02-06 08:00 | 2026-02-08 16:00 |  |  | 3 | 0 | 3 | 142 | 61 |  | CURE | CURE
A31990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | Cure/Strip Footing - Brg 100139 - Pier 5 - R3 - P3 | 2026-01-16 08:00 | 2026-01-22 16:00 |  |  | 7 | 0 | 7 | 140 | 61 |  | CURE | CURE
A32160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Erect Girders - Brg 100139 - Span 4 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 84 | 58 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A32170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Install SIP - Brg 100139 - Span 4 - R3 - P3 | 2026-02-12 08:00 | 2026-02-12 16:00 |  |  | 1 | 0 | 1 | 84 | 58 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A32180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Install Overhangs - Brg 100139 - Span 4 - R3 - P3 | 2026-02-13 08:00 | 2026-03-02 16:00 |  |  | 10 | 0 | 10 | 84 | 58 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Reinforce Deck - Brg 100139 - Span 4 - R3 - P3 | 2026-03-03 08:00 | 2026-03-04 16:00 |  |  | 2 | 0 | 2 | 84 | 58 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Place Deck - Brg 100139 - Span 4 - R3 - P3 | 2026-03-05 08:00 | 2026-03-05 16:00 |  |  | 1 | 0 | 1 | 84 | 58 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A32210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Cure Deck - Brg 100139 - Span 4 - R3 - P3 | 2026-03-06 08:00 | 2026-03-12 16:00 |  |  | 7 | 0 | 7 | 138 | 58 |  | CURE | CURE
A32220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Install Reinf Barrier - Brg 100139 - Span 4 - R3 - P3 | 2026-03-13 08:00 | 2026-03-13 16:00 |  |  | 1 | 0 | 1 | 84 | 58 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 | R3 - Ph3 - Bridge 100139 - Span 4 | Strip Overhangs - Brg 100139 - Span 4 - R3 - P3 | 2026-03-16 08:00 | 2026-03-19 16:00 |  |  | 3 | 0 | 3 | 84 | 58 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Erect Girders - Brg 100139 - Span 5 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 87 | 60 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A32260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Install SIP - Brg 100139 - Span 5 - R3 - P3 | 2026-02-12 08:00 | 2026-02-12 16:00 |  |  | 1 | 0 | 1 | 87 | 60 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A32270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Install Overhangs - Brg 100139 - Span 5 - R3 - P3 | 2026-02-13 08:00 | 2026-02-26 16:00 |  |  | 8 | 0 | 8 | 87 | 60 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Reinforce Deck - Brg 100139 - Span 5 - R3 - P3 | 2026-02-27 08:00 | 2026-02-27 16:00 |  |  | 1 | 0 | 1 | 87 | 60 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Place Deck - Brg 100139 - Span 5 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 87 | 60 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A32300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Cure Deck - Brg 100139 - Span 5 - R3 - P3 | 2026-03-03 08:00 | 2026-03-09 16:00 |  |  | 7 | 0 | 7 | 142 | 60 |  | CURE | CURE
A32310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Install Reinf Barrier - Brg 100139 - Span 5 - R3 - P3 | 2026-03-10 08:00 | 2026-03-10 16:00 |  |  | 1 | 0 | 1 | 87 | 60 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 | R3 - Ph3 - Bridge 100139 - Span 5 | Strip Overhangs - Brg 100139 - Span 5 - R3 - P3 | 2026-03-12 08:00 | 2026-03-13 16:00 |  |  | 2 | 0 | 2 | 87 | 60 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Erect Girders - Brg 100139 - Span 6 - R3 - P3 | 2026-02-09 08:00 | 2026-02-09 16:00 |  |  | 1 | 0 | 1 | 90 | 64 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A32350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Install SIP - Brg 100139 - Span 6 - R3 - P3 | 2026-02-10 08:00 | 2026-02-10 16:00 |  |  | 1 | 0 | 1 | 90 | 64 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A32360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Install Overhangs - Brg 100139 - Span 6 - R3 - P3 | 2026-02-12 08:00 | 2026-02-20 16:00 |  |  | 6 | 0 | 6 | 90 | 64 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Reinforce Deck - Brg 100139 - Span 6 - R3 - P3 | 2026-02-23 08:00 | 2026-02-23 16:00 |  |  | 1 | 0 | 1 | 90 | 64 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Place Deck - Brg 100139 - Span 6 - R3 - P3 | 2026-02-24 08:00 | 2026-02-24 16:00 |  |  | 1 | 0 | 1 | 90 | 64 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A32390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Cure Deck - Brg 100139 - Span 6 - R3 - P3 | 2026-02-25 08:00 | 2026-03-03 16:00 |  |  | 7 | 0 | 7 | 148 | 64 |  | CURE | CURE
A32400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Install Reinf Barrier - Brg 100139 - Span 6 - R3 - P3 | 2026-03-04 08:00 | 2026-03-04 16:00 |  |  | 1 | 0 | 1 | 91 | 64 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 | R3 - Ph3 - Bridge 100139 - Span 6 | Strip Overhangs - Brg 100139 - Span 6 - R3 - P3 | 2026-03-05 08:00 | 2026-03-06 16:00 |  |  | 2 | 0 | 2 | 91 | 64 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | FRP Footing - Brg 100141 - Pier 1 - R3 - P3 | 2026-01-08 08:00 | 2026-01-16 16:00 |  |  | 6 | 0 | 6 | 70 | 38 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A32620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 | R3 - Ph3 - Bridge 100141 - Pier 1 | Cure/Strip Footing - Brg 100141 - Pier 1 - R3 - P3 | 2026-01-17 08:00 | 2026-01-23 16:00 |  |  | 7 | 0 | 7 | 115 | 38 |  | CURE | CURE
A32630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | Drive Pile - Brg 100141 - Pier 2 - R3 - P3 | 2025-12-19 08:00 | 2026-01-07 16:00 |  |  | 6 | 0 | 6 | 89 | 53 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A32640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | FRP Footing - Brg 100141 - Pier 2 - R3 - P3 | 2026-01-08 08:00 | 2026-01-12 16:00 |  |  | 3 | 0 | 3 | 89 | 53 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A32650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 | R3 - Ph3 - Bridge 100141 - Pier 2 | Cure/Strip Footing - Brg 100141 - Pier 2 - R3 - P3 | 2026-01-13 08:00 | 2026-01-19 16:00 |  |  | 7 | 0 | 7 | 146 | 53 |  | CURE | CURE
A32660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.6 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Grading - Brg 100869 - End Bent 1 - R3 - P3 | 2025-12-15 08:00 | 2025-12-15 16:00 |  |  | 1 | 0 | 1 | 71 | 44 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A32680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.6 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P3 | 2025-12-16 08:00 | 2025-12-23 16:00 |  |  | 5 | 0 | 5 | 71 | 44 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A32690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.6 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | FRP Abt Cap - Brg 100869 - End Bent 1 - R3 - P3 | 2026-01-15 08:00 | 2026-01-22 16:00 |  |  | 4 | 0 | 4 | 71 | 44 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A32700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.6 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Cure/Strip Abt Cap - Brg 100869 - End Bent 1 - R3 - P3 | 2026-01-23 08:00 | 2026-01-25 16:00 |  |  | 3 | 0 | 3 | 113 | 44 |  | CURE | CURE
A32710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.6 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P3 | 2026-01-05 08:00 | 2026-01-13 16:00 |  |  | 7 | 0 | 7 | 71 | 44 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A32720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.6 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P3 | 2025-12-01 08:00 | 2025-12-12 16:00 |  |  | 8 | 0 | 8 | 71 | 44 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A32820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Erect Girders - Brg 100869 - Span 1 - R3 - P3 | 2026-01-26 08:00 | 2026-01-27 16:00 |  |  | 2 | 0 | 2 | 71 | 44 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A32830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Install SIP - Brg 100869 - Span 1 - R3 - P3 | 2026-01-29 08:00 | 2026-01-29 16:00 |  |  | 1 | 0 | 1 | 71 | 44 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A32840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Install Overhangs - Brg 100869 - Span 1 - R3 - P3 | 2026-01-30 08:00 | 2026-02-20 16:00 |  |  | 14 | 0 | 14 | 71 | 44 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Reinforce Deck - Brg 100869 - Span 1 - R3 - P3 | 2026-02-23 08:00 | 2026-02-26 16:00 |  |  | 3 | 0 | 3 | 71 | 44 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Place Deck - Brg 100869 - Span 1 - R3 - P3 | 2026-02-27 08:00 | 2026-02-27 16:00 |  |  | 1 | 0 | 1 | 71 | 44 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A32870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Cure Deck - Brg 100869 - Span 1 - R3 - P3 | 2026-02-28 08:00 | 2026-03-06 16:00 |  |  | 7 | 0 | 7 | 143 | 68 |  | CURE | CURE
A32880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Install Reinf Barrier - Brg 100869 - Span 1 - R3 - P3 | 2026-03-09 08:00 | 2026-03-10 16:00 |  |  | 2 | 0 | 2 | 86 | 68 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A32890 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 | R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Strip Overhangs - Brg 100869 - Span 1 - R3 - P3 | 2026-03-12 08:00 | 2026-03-16 16:00 |  |  | 3 | 0 | 3 | 86 | 68 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A32910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 | R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | FRPS Approach Slab 1 - Brg 100869 - R3 - P3 | 2026-03-02 08:00 | 2026-03-09 16:00 |  |  | 6 | 0 | 6 | 83 | 52 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A32920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 | R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | FRPS Approach Slab 2 - Brg 100869 - R3 - P3 | 2026-03-02 08:00 | 2026-03-12 16:00 |  |  | 8 | 0 | 8 | 71 | 44 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A32930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 | R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Slip Barrier - Brg 100869 - R3 - P3 | 2026-03-17 08:00 | 2026-03-17 16:00 |  |  | 1 | 0 | 1 | 86 | 68 | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A32940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 | R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Grind Deck - Brg 100869 - R3 - P3 | 2026-03-19 08:00 | 2026-03-19 16:00 |  |  | 1 | 0 | 1 | 86 | 68 | Sub - Diamond Grind Pavement Crew | SUB.CONCRETE.GRIND | CONCRETE PVMT.Diamond Grind
A32950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 | R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Groove Deck - Brg 100869 - R3 - P3 | 2026-03-20 08:00 | 2026-03-20 16:00 |  |  | 1 | 0 | 1 | 86 | 68 | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A32960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 | R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Perm Striping - Brg 100869 - R3 - P3 | 2026-03-23 08:00 | 2026-03-23 16:00 |  |  | 1 | 0 | 1 | 86 | 68 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A32970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.14 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Grading - Brg 100869 - End Bent 2 - R3 - P3 | 2025-12-15 08:00 | 2025-12-15 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A32990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.14 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P3 | 2025-12-16 08:00 | 2025-12-23 16:00 |  |  | 5 | 0 | 5 | 40 | 1 | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A33000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.14 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | FRP Abt Cap - Brg 100869 - End Bent 2 - R3 - P3 | 2026-01-08 08:00 | 2026-01-13 16:00 |  |  | 4 | 0 | 4 | 75 | 45 | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A33010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.14 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Cure/Strip Abt Cap - Brg 100869 - End Bent 2 - R3 - P3 | 2026-01-14 08:00 | 2026-01-16 16:00 |  |  | 3 | 0 | 3 | 122 | 45 |  | CURE | CURE
A33020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.14 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P3 | 2026-01-05 08:00 | 2026-01-07 16:00 |  |  | 3 | 0 | 3 | 40 | 1 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A33300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.14 | R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P3 | 2025-12-01 08:00 | 2025-12-12 16:00 |  |  | 8 | 0 | 8 | 40 | 1 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A33310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 1 | 2026-01-22 08:00 | 2026-02-27 16:00 |  |  | 23 | 0 | 23 | 40 | 1 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A33320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Wall Barrier - Ramp B Sta 621 to 627 - R3 - P3 | 2026-03-12 08:00 | 2026-04-07 16:00 |  |  | 17 | 0 | 17 | 40 | 1 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A33330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Junction Slab - Ramp B Sta 621 to 627 - R3 - P3 | 2026-03-03 08:00 | 2026-03-10 16:00 |  |  | 6 | 0 | 6 | 40 | 1 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A33340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P3 | 2026-01-08 08:00 | 2026-01-20 16:00 |  |  | 7 | 0 | 7 | 40 | 1 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A33350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A33360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Asphalt Base - Ramp B Sta 621 to 627 - R3 - P3 | 2026-04-08 08:00 | 2026-04-08 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A33370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Concrete Pav - Ramp B Sta 621 to 627 - R3 - P3 | 2026-04-09 08:00 | 2026-05-27 16:00 |  |  | 30 | 0 | 30 | 40 | 1 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A33380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Edge Drain - Ramp B Sta 621 to 627 - R3 - P3 | 2026-05-28 08:00 | 2026-06-01 16:00 |  |  | 3 | 0 | 3 | 40 | 1 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A33390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Shoulder GAB - Ramp B Sta 621 to 627 - R3 - P3 | 2026-06-02 08:00 | 2026-06-02 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A33400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Asphalt Shoulder - Ramp B Sta 621 to 627 - R3 - P3 | 2026-06-03 08:00 | 2026-06-03 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A33410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.4 | R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | Demo Superstructure - Ramp B Brg Over Palm - R3 - P3 | 2025-10-21 08:00 | 2025-11-06 16:00 |  |  | 13 | 0 | 13 | 40 | 1 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A33420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.4 | R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | Demo Substructure - Ramp B Brg Over Palm - R3 - P3 | 2025-11-07 08:00 | 2025-11-25 16:00 |  |  | 10 | 0 | 10 | 40 | 1 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A33430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P3 | 2026-01-22 08:00 | 2026-02-12 16:00 |  |  | 14 | 0 | 14 | 49 | 20 | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A33440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | Grading - Brg 100143 - Pier 1 - R3 - P3 | 2025-10-21 08:00 | 2025-10-21 16:00 |  |  | 1 | 0 | 1 | 126 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A33470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | Cure/Strip Column - Brg 100143 - Pier 1 - R3 - P3 | 2025-11-21 08:00 | 2025-11-27 16:00 |  |  | 7 | 0 | 7 | 223 |  |  | CURE | CURE
A33480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | FRP Cap - Brg 100143 - Pier 1 - R3 - P3 | 2025-12-01 08:00 | 2025-12-01 16:00 |  |  | 1 | 0 | 1 | 127 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A33490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | Cure/Strip Cap - Brg 100143 - Pier 1 - R3 - P3 | 2025-12-02 08:00 | 2025-12-04 16:00 |  |  | 3 | 0 | 3 | 220 |  |  | CURE | CURE
A33500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Erect Girders - Brg 100143 - Span 1 - R3 - P3 | 2025-12-05 08:00 | 2025-12-05 16:00 |  |  | 1 | 0 | 1 | 127 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A33510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Install SIP - Brg 100143 - Span 1 - R3 - P3 | 2025-12-08 08:00 | 2025-12-08 16:00 |  |  | 1 | 0 | 1 | 127 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A33520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Install Overhangs - Brg 100143 - Span 1 - R3 - P3 | 2025-12-09 08:00 | 2025-12-12 16:00 |  |  | 3 | 0 | 3 | 127 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A33530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Reinforce Deck - Brg 100143 - Span 1 - R3 - P3 | 2025-12-15 08:00 | 2025-12-15 16:00 |  |  | 1 | 0 | 1 | 127 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A33540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Place Deck - Brg 100143 - Span 1 - R3 - P3 | 2025-12-16 08:00 | 2025-12-16 16:00 |  |  | 1 | 0 | 1 | 127 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A33550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Cure Deck - Brg 100143 - Span 1 - R3 - P3 | 2025-12-17 08:00 | 2025-12-23 16:00 |  |  | 7 | 0 | 7 | 222 |  |  | CURE | CURE
A33560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Install Reinf Barrier - Brg 100143 - Span 1 - R3 - P3 | 2026-01-05 08:00 | 2026-01-05 16:00 |  |  | 1 | 0 | 1 | 128 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A33570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 | R3 - Ph3 - Bridge 100143 - Span 1 | Strip Overhangs - Brg 100143 - Span 1 - R3 - P3 | 2026-01-06 08:00 | 2026-01-06 16:00 |  |  | 1 | 0 | 1 | 128 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A33610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 | R3 - Ph3 - Bridge 100143 - Finishes | Slip Barrier - Brg 100143 - R3 - P3 | 2026-01-07 08:00 | 2026-01-07 16:00 |  |  | 1 | 0 | 1 | 128 |  | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A33630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 | R3 - Ph3 - Bridge 100143 - Finishes | Groove Deck - Brg 100143 - R3 - P3 | 2026-01-08 08:00 | 2026-01-08 16:00 |  |  | 1 | 0 | 1 | 128 |  | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A33640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 | R3 - Ph3 - Bridge 100143 - Finishes | Perm Striping - Brg 100143 - R3 - P3 | 2026-01-09 08:00 | 2026-01-09 16:00 |  |  | 1 | 0 | 1 | 128 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A33650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Erect Girders - Brg 100143 - Span 2 - R3 - P3 | 2025-12-05 08:00 | 2025-12-05 16:00 |  |  | 1 | 0 | 1 | 126 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A33660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Install SIP - Brg 100143 - Span 2 - R3 - P3 | 2025-12-08 08:00 | 2025-12-08 16:00 |  |  | 1 | 0 | 1 | 126 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A33670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Install Overhangs - Brg 100143 - Span 2 - R3 - P3 | 2025-12-09 08:00 | 2025-12-15 16:00 |  |  | 4 | 0 | 4 | 126 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A33680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Reinforce Deck - Brg 100143 - Span 2 - R3 - P3 | 2025-12-16 08:00 | 2025-12-16 16:00 |  |  | 1 | 0 | 1 | 126 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A33690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Place Deck - Brg 100143 - Span 2 - R3 - P3 | 2025-12-18 08:00 | 2025-12-18 16:00 |  |  | 1 | 0 | 1 | 126 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A33700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Cure Deck - Brg 12 - Span 2 - R3 - P3 | 2025-12-19 08:00 | 2025-12-25 16:00 |  |  | 7 | 0 | 7 | 220 |  |  | CURE | CURE
A33710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Install Reinf Barrier - Brg 100143 - Span 2 - R3 - P3 | 2026-01-05 08:00 | 2026-01-05 16:00 |  |  | 1 | 0 | 1 | 128 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A33720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 | R3 - Ph3 - Bridge 100143 - Span 2 | Strip Overhangs - Brg 100143 - Span 2 - R3 - P3 | 2026-01-06 08:00 | 2026-01-06 16:00 |  |  | 1 | 0 | 1 | 128 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A33740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Erect Girders - Brg 100143 - Span 3 - R3 - P3 | 2025-12-05 08:00 | 2025-12-05 16:00 |  |  | 1 | 0 | 1 | 127 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A33750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Install SIP - Brg 100143 - Span 3 - R3 - P3 | 2025-12-08 08:00 | 2025-12-08 16:00 |  |  | 1 | 0 | 1 | 127 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A33760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Install Overhangs - Brg 100143 - Span 3 - R3 - P3 | 2025-12-09 08:00 | 2025-12-12 16:00 |  |  | 3 | 0 | 3 | 127 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A33770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Reinforce Deck - Brg 100143 - Span 3 - R3 - P3 | 2025-12-15 08:00 | 2025-12-15 16:00 |  |  | 1 | 0 | 1 | 127 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A33780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Place Deck - Brg 100143 - Span 3 - R3 - P3 | 2025-12-16 08:00 | 2025-12-16 16:00 |  |  | 1 | 0 | 1 | 127 |  | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A33790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Cure Deck - Brg 100143 - Span 3 - R3 - P3 | 2025-12-17 08:00 | 2025-12-23 16:00 |  |  | 7 | 0 | 7 | 222 |  |  | CURE | CURE
A33800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Install Reinf Barrier - Brg 100143 - Span 3 - R3 - P3 | 2026-01-05 08:00 | 2026-01-05 16:00 |  |  | 1 | 0 | 1 | 128 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A33810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 | R3 - Ph3 - Bridge 100143 - Span 3 | Strip Overhangs - Brg 100143 - Span 3 - R3 - P3 | 2026-01-06 08:00 | 2026-01-06 16:00 |  |  | 1 | 0 | 1 | 128 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A33830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | Grading - Brg 100143 - Pier 2 - R3 - P3 | 2025-10-21 08:00 | 2025-10-21 16:00 |  |  | 1 | 0 | 1 | 126 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A33850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | Cure/Strip Column - Brg 100143 - Pier 2 - R3 - P3 | 2025-11-21 08:00 | 2025-11-27 16:00 |  |  | 7 | 0 | 7 | 223 |  |  | CURE | CURE
A33860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | FRP Cap - Brg 100143 - Pier 2 - R3 - P3 | 2025-12-01 08:00 | 2025-12-01 16:00 |  |  | 1 | 0 | 1 | 127 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A33870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | Cure/Strip Cap - Brg 100143 - Pier 2 - R3 - P3 | 2025-12-02 08:00 | 2025-12-04 16:00 |  |  | 3 | 0 | 3 | 220 |  |  | CURE | CURE
A33880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.18 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Grading - Brg 100143 - End Bent 1 - R3 - P3 | 2025-10-21 08:00 | 2025-10-21 16:00 |  |  | 1 | 0 | 1 | 146 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A33910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.18 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | FRP Abt Cap - Brg 100143 - End Bent 1 - R3 - P3 | 2025-10-28 08:00 | 2025-10-28 16:00 |  |  | 1 | 0 | 1 | 146 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A33920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.18 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Cure/Strip Abt Cap - Brg 100143 - End Bent 1 - R3 - P3 | 2025-10-29 08:00 | 2025-10-31 16:00 |  |  | 3 | 0 | 3 | 255 |  |  | CURE | CURE
A33950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.19 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Grading - Brg 100143 - End Bent 2 - R3 - P3 | 2025-10-21 08:00 | 2025-10-21 16:00 |  |  | 1 | 0 | 1 | 145 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A33980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.19 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | FRP Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | 2025-10-29 08:00 | 2025-10-29 16:00 |  |  | 1 | 0 | 1 | 145 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A33990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.19 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Cure/Strip Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | 2025-10-30 08:00 | 2025-11-01 16:00 |  |  | 3 | 0 | 3 | 254 |  |  | CURE | CURE
A34020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.7 | R3 - Ph3 - Bridge 100143 - Demo | Demo Barrier - Brg 100143 - R3 - P3 | 2025-10-21 08:00 | 2025-10-28 16:00 |  |  | 6 | 0 | 6 | 146 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A34030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.18 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Demo Abut - Brg 100143 - End Bent 1 - R3 - P3 | 2025-10-22 08:00 | 2025-10-22 16:00 |  |  | 1 | 0 | 1 | 146 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A34040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.19 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Demo Abut - Brg 100143 - End Bent 2 - R3 - P3 | 2025-10-22 08:00 | 2025-10-23 16:00 |  |  | 2 | 0 | 2 | 145 |  | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A34060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | Cure/Strip Footing - Brg 100143 - Pier 1 - R3 - P3 | 2025-11-14 08:00 | 2025-11-20 16:00 |  |  | 7 | 0 | 7 | 223 |  |  | CURE | CURE
A34090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | Cure/Strip Footing - Brg 100143 - Pier 2 - R3 - P3 | 2025-11-14 08:00 | 2025-11-20 16:00 |  |  | 7 | 0 | 7 | 223 |  |  | CURE | CURE
A34100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Const MSE Wall & Bkfill - RW 9-1 - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-03-06 08:00 | 2026-04-08 16:00 |  |  | 21 | 0 | 21 | 64 | 36 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A34110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Wall Barrier - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-16 08:00 | 2026-04-16 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A34120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Junction Slab - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-13 08:00 | 2026-04-14 16:00 |  |  | 2 | 0 | 2 | 64 | 36 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A34130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Cut/Fill to Grade - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-03-04 08:00 | 2026-03-05 16:00 |  |  | 2 | 0 | 2 | 64 | 36 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A34140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Stabilization - I-275-SB Sta 417 to 419 - R3 - P3 | 2026-04-09 08:00 | 2026-04-10 16:00 |  |  | 2 | 0 | 2 | 64 | 36 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A34150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Asphalt Base - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-17 08:00 | 2026-04-17 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Concrete Pav - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-20 08:00 | 2026-04-21 16:00 |  |  | 2 | 0 | 2 | 64 | 36 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A34170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Edge Drain - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-23 08:00 | 2026-04-23 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A34180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Shoulder GAB - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-24 08:00 | 2026-04-24 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A34190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.21 | R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Asphalt Shoulder - I-275 SB Sta 417 to 419 - R3 - P3 | 2026-04-27 08:00 | 2026-04-27 16:00 |  |  | 1 | 0 | 1 | 64 | 36 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Wall Barrier - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-16 08:00 | 2026-03-17 16:00 |  |  | 2 | 0 | 2 | 83 | 52 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A34210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Junction Slab - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-05 08:00 | 2026-03-13 16:00 |  |  | 6 | 0 | 6 | 83 | 52 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A34220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Cut/Fill to Grade - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 83 | 52 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A34230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Stabilization - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-03 08:00 | 2026-03-04 16:00 |  |  | 2 | 0 | 2 | 83 | 52 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A34240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Edge Drain - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-19 08:00 | 2026-03-23 16:00 |  |  | 3 | 0 | 3 | 83 | 52 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A34250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Shoulder GAB - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 2 | 0 | 2 | 83 | 52 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A34260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.22 | R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Asphalt Shoulder - Ramp C Sta 701 to 707 - R3 - P3 | 2026-03-27 08:00 | 2026-03-27 16:00 |  |  | 1 | 0 | 1 | 83 | 52 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Const MSE Wall & Bkfill - RW 102 - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-03 08:00 | 2026-03-09 16:00 |  |  | 5 | 0 | 5 | 71 | 44 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A34280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Wall Barrier - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 2 | 0 | 2 | 71 | 44 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A34290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Junction Slab - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 6 | 0 | 6 | 71 | 44 | CIP Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.CIP Wall
A34300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Cut/Fill to Grade - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-02 08:00 | 2026-03-02 16:00 |  |  | 1 | 0 | 1 | 71 | 44 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A34310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Stabilization - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-10 08:00 | 2026-03-12 16:00 |  |  | 2 | 0 | 2 | 71 | 44 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A34320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Asphalt Base - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-27 08:00 | 2026-03-27 16:00 |  |  | 1 | 0 | 1 | 71 | 44 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Concrete Pav - Ramp C Sta 708 to 715 - R3 - P3 | 2026-03-30 08:00 | 2026-04-06 16:00 |  |  | 6 | 0 | 6 | 71 | 44 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A34340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Edge Drain - Ramp C Sta 708 to 715 - R3 - P3 | 2026-04-07 08:00 | 2026-04-09 16:00 |  |  | 3 | 0 | 3 | 71 | 44 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A34350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Shoulder GAB - Ramp C Sta 708 to 715 - R3 - P3 | 2026-04-10 08:00 | 2026-04-13 16:00 |  |  | 2 | 0 | 2 | 71 | 44 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A34360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.23 | R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Asphalt Shoulder - Ramp C Sta 708 to 715 - R3 - P3 | 2026-04-14 08:00 | 2026-04-14 16:00 |  |  | 1 | 0 | 1 | 71 | 44 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.17 | R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | Demo Superstructure - Ramp B Brg Over 7th Ave - R3 - P3 | 2025-12-01 08:00 | 2025-12-12 16:00 |  |  | 8 | 0 | 8 | 70 | 38 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A34380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.17 | R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | Demo Substructure - Ramp B Brg Over 7th Ave - R3 - P3 | 2025-12-15 08:00 | 2025-12-16 16:00 |  |  | 2 | 0 | 2 | 70 | 38 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A34390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.15 | R3 - Ph3 - Demo Existing Ramp B Over N Central | Demo Superstructure - Ramp B Brg OverN Central - R3 - P3 | 2025-10-21 08:00 | 2025-11-20 16:00 |  |  | 20 | 0 | 20 | 63 | 36 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
A34400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.15 | R3 - Ph3 - Demo Existing Ramp B Over N Central | Demo Substructure - Ramp B Brg N Central - R3 - P3 | 2025-11-21 08:00 | 2025-12-09 16:00 |  |  | 9 | 0 | 9 | 63 | 36 | Demo Bridge Crew | LANE.DEMO.Bridge | DEMO.Bridge Demo
LoE340 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 3 - I-275 SB Right Widening [LoE] | 2025-10-17 08:00 | 2026-06-03 16:00 |  |  | 230 | 0 | 230 | 65 |  |  | LOE | LOE
A34410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 3 - R3 - I-275 SB Right Widening |  | 2026-06-03 16:00 |  |  | 0 | 0 | 0 | 47 | 1 |  | MS | MS
A34430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.1 | R3 - Ph4 - MOT | Shift Traffic - Ramp C Left - R3 - P4 | 2026-06-04 08:00 | 2026-06-04 16:00 |  |  | 1 | 0 | 1 | 45 | 9 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A34440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.7 | R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Install Guardrail - Ramp G Sta 802 to 805 - R3 - P3 | 2025-11-06 08:00 | 2025-11-07 16:00 |  |  | 2 | 0 | 2 | 156 |  | Sub - Guardrail Crew | SUB.GRAIL | Guardrail
A34450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Cut/Fill to Grade - Ramp B / Ramp G Gore - R3 - P3 | 2026-06-05 08:00 | 2026-06-08 16:00 |  |  | 2 | 0 | 2 | 54 | 19 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A34470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Place Stabilization - Ramp B / Ramp G Gore - R3 - P4 | 2026-06-09 08:00 | 2026-06-09 16:00 |  |  | 1 | 0 | 1 | 54 | 19 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A34480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Place Asphalt Base - Ramp B /Ramp G Gore - R3 - P4 | 2026-06-11 08:00 | 2026-06-11 16:00 |  |  | 1 | 0 | 1 | 54 | 19 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Place Concrete Pav - Ramp B /Ramp G Gore - R3 - P4 | 2026-06-12 08:00 | 2026-06-15 16:00 |  |  | 2 | 0 | 2 | 54 | 19 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A34500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Place Edge Drain - Ramp B /Ramp G Gore - R3 - P4 | 2026-07-07 08:00 | 2026-07-07 16:00 |  |  | 1 | 0 | 1 | 45 | 10 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A34510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Place Shoulder GAB - Ramp B / Ramp G Gore - R3 - P4 | 2026-07-09 08:00 | 2026-07-09 16:00 |  |  | 1 | 0 | 1 | 48 | 17 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A34520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Place Asphalt Shoulder - Ramp B /Ramp G Gore - R3 - P4 | 2026-07-10 08:00 | 2026-07-10 16:00 |  |  | 1 | 0 | 1 | 48 | 17 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.2 | R3 - Ph4 - Ramp B / Ramp G Gore | Install Guardrail - Ramp B /Ramp G Gore - R3 - P3 | 2026-07-13 08:00 | 2026-07-13 16:00 |  |  | 1 | 0 | 1 | 48 | 17 | Sub - Guardrail Crew | SUB.GRAIL | Guardrail
A34540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.7 | R3 - Milestones | Finish Phase 4 - R3 - Ramp C & G Gore |  | 2026-07-27 16:00 |  |  | 0 | 0 | 0 | 48 | 1 |  | MS | MS
LoE350 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.3 | R3 Phase Durations | R3 Phase 4 - Ramp C & G Gore [LoE] | 2026-06-04 08:00 | 2026-07-27 16:00 |  |  | 54 | 0 | 54 | 66 |  |  | LOE | LOE
D2560 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | 2023-02-28 08:00 | 2023-04-24 16:00 |  |  | 40 | 0 | 40 | 461 |  |  | DESIGN | DESIGN
D2570 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Review and Approve - 90% TTCP Plans - R3 Phase 2 | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 461 |  |  | OWNER.Design Review | OWNER
D2580 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - Final TTCP Plans - R3 Phase 2 | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 461 |  |  | DESIGN | DESIGN
D2590 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Review and Approve - Final TTCP Plans - R3 Phase 2 | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 461 |  |  | OWNER.Design Review | OWNER
D2600 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 2 | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 461 |  |  | DESIGN | DESIGN
D2610 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Issue - RFC TTCP Plans - R3 Phase 2 | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 461 |  |  | DESIGN | DESIGN
D2620 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | 2023-04-25 08:00 | 2023-06-20 16:00 |  |  | 40 | 0 | 40 | 570 |  |  | DESIGN | DESIGN
D2630 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Review and Approve - 90% TTCP Plans - R3 Phase 3 & 4 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 570 |  |  | OWNER.Design Review | OWNER
D2640 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - Final TTCP Plans - R3 Phase 3 & 4 | 2023-07-13 08:00 | 2023-08-09 16:00 |  |  | 20 | 0 | 20 | 570 |  |  | DESIGN | DESIGN
D2650 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Review and Approve - Final TTCP Plans - R3 Phase 3 & 4 | 2023-08-10 08:00 | 2023-08-30 16:00 |  |  | 15 | 0 | 15 | 570 |  |  | OWNER.Design Review | OWNER
D2660 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 3 & 4 | 2023-08-31 08:00 | 2023-09-21 16:00 |  |  | 15 | 0 | 15 | 570 |  |  | DESIGN | DESIGN
D2670 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Issue - RFC TTCP Plans - R3 Phase 3 & 4 | 2023-09-22 08:00 | 2023-09-28 16:00 |  |  | 5 | 0 | 5 | 570 |  |  | DESIGN | DESIGN
D2680 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Develop and Submit - 90% Roadway Plans - R2 | 2022-12-01 08:00 | 2023-04-10 16:00 |  |  | 90 | 0 | 90 | 376 |  |  | DESIGN | DESIGN
D2690 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Review and Approve - 90% Roadway Plans - R2 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 668 |  |  | OWNER.Design Review | OWNER
D2700 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Develop and Submit - Final Roadway Plans - R2 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 668 |  |  | DESIGN | DESIGN
D2710 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Review and Approve - Final Roadway Plans - R2 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 668 |  |  | OWNER.Design Review | OWNER
D2720 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Develop and Submit - Sign & Seal Roadway Plans - R2 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 668 |  |  | DESIGN | DESIGN
D2730 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Issue - RFC Roadway Plans - R2 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 668 |  |  | DESIGN | DESIGN
D2740 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | 2022-12-01 08:00 | 2023-04-10 16:00 |  |  | 90 | 0 | 90 | 172 |  |  | DESIGN | DESIGN
D2750 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Review and Approve - 90% Roadway Plans - R3 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 566 |  |  | OWNER.Design Review | OWNER
D2760 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Develop and Submit - Final Roadway Plans - R3 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 566 |  |  | DESIGN | DESIGN
D2770 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Review and Approve - Final Roadway Plans - R3 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 566 |  |  | OWNER.Design Review | OWNER
D2780 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Develop and Submit - Sign & Seal Roadway Plans - R3 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 566 |  |  | DESIGN | DESIGN
D2790 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Issue - RFC Roadway Plans - R3 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 566 |  |  | DESIGN | DESIGN
D2800 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 100 | 71 |  | DESIGN | DESIGN
D2810 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 2023-09-15 08:00 | 2023-10-05 16:00 |  |  | 15 | 0 | 15 | 100 | 71 |  | OWNER.Design Review | OWNER
D2820 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Develop and Submit - Final Cat1 Brg 03 Plans - R1 | 2023-10-06 08:00 | 2023-11-02 16:00 |  |  | 20 | 0 | 20 | 100 | 71 |  | DESIGN | DESIGN
D2830 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Review and Approve - Final Cat1 Brg 03 Plans - R1 | 2023-11-03 08:00 | 2023-11-28 16:00 |  |  | 15 | 0 | 15 | 100 | 71 |  | OWNER.Design Review | OWNER
D2840 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 03 Plans - R1 | 2023-11-29 08:00 | 2023-12-12 16:00 |  |  | 10 | 0 | 10 | 100 | 71 |  | DESIGN | DESIGN
D2850 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Issue - RFC Cat1 Brg 03 Plans - R1 | 2023-12-13 08:00 | 2023-12-19 16:00 |  |  | 5 | 0 | 5 | 100 | 71 |  | DESIGN | DESIGN
D2860 | Completed | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | 2022-08-01 08:00 | 2022-11-07 16:00 | 2022-08-01 08:00 | 2022-11-07 16:00 | 60 | 70 | 0 |  |  |  | DESIGN | DESIGN
D2870 | In Progress | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | 2022-11-08 08:00 | 2022-12-29 16:00 | 2022-11-08 08:00 |  | 30 | 14 | 5 | 190 |  |  | OWNER.Design Review | OWNER
D2880 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | 2022-12-22 08:00 | 2023-04-10 16:00 |  |  | 75 | 0 | 75 | 120 |  |  | DESIGN | DESIGN
D2890 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | 2023-04-11 08:00 | 2023-07-05 16:00 |  |  | 60 | 0 | 60 | 120 |  |  | OWNER.Design Review | OWNER
D2900 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | 2023-07-06 08:00 | 2023-08-02 16:00 |  |  | 20 | 0 | 20 | 120 |  |  | DESIGN | DESIGN
D2910 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Review and Approve - Final Cat2 Brg 02 Plans - R1 | 2023-08-03 08:00 | 2023-08-30 16:00 |  |  | 20 | 0 | 20 | 120 |  |  | OWNER.Design Review | OWNER
D2920 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - Sign & Seal Cat2 Brg 02 Plans - R1 | 2023-08-31 08:00 | 2023-09-14 16:00 |  |  | 10 | 0 | 10 | 120 |  |  | DESIGN | DESIGN
D2930 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Issue - RFC Cat2 Brg 02 Plans - R1 | 2023-09-25 08:00 | 2023-09-29 16:00 |  |  | 5 | 0 | 5 | 114 |  |  | DESIGN | DESIGN
A34630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Place Sidewalk - N CentralRoadway - R3 - P4 | 2026-07-21 08:00 | 2026-07-23 16:00 |  |  | 2 | 0 | 2 | 40 | 1 | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A34580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Grading - N Central Roadway - R3 - P4 | 2026-06-04 08:00 | 2026-06-04 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A34600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Place Stabilization - N Central Roadway - R3 - P4 | 2026-07-07 08:00 | 2026-07-09 16:00 |  |  | 2 | 0 | 2 | 40 | 1 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A34610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Place GAB - N Central Roadway - R3 - P4 | 2026-07-10 08:00 | 2026-07-13 16:00 |  |  | 2 | 0 | 2 | 40 | 1 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A34620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Place Curb - N Central Roadway - R3 - P4 | 2026-07-14 08:00 | 2026-07-20 16:00 |  |  | 4 | 0 | 4 | 40 | 1 | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A34640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Place Asphalt Surface - N CentralRoadway - R3 - P4 | 2026-07-24 08:00 | 2026-07-24 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.5 | R3 - Ph4 - N Central Drainage / Roadway | Install DRG S-## to S-103 / OUT-5 - N Central Roadway - R3 - P4 | 2026-06-05 08:00 | 2026-07-06 16:00 |  |  | 18 | 0 | 18 | 40 | 1 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A34700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Sidewalk - Mitchell /RossInter / Palm SUP - R3 - P4 | 2026-07-20 08:00 | 2026-07-21 16:00 |  |  | 2 | 0 | 2 | 42 | 5 | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A34650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Grading - Mitchell /Ross Inter / Palm SUP - R3 - P4 | 2026-06-04 08:00 | 2026-06-04 16:00 |  |  | 1 | 0 | 1 | 42 | 5 | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A34670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Stabilization - Mitchell /RossInter / Palm SUP - R3 - P4 | 2026-07-07 08:00 | 2026-07-13 16:00 |  |  | 4 | 0 | 4 | 42 | 5 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A34680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place GAB - Mitchell /RossInter / Palm SUP - R3 - P4 | 2026-07-14 08:00 | 2026-07-16 16:00 |  |  | 2 | 0 | 2 | 42 | 5 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A34690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Curb - Mitchell /RossInter / Palm SUP - R3 - P4 | 2026-07-17 08:00 | 2026-07-17 16:00 |  |  | 1 | 0 | 1 | 42 | 5 | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A34710 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Asphalt Surface - Mitchell /RossInter / Palm SUP - R3 - P4 | 2026-07-23 08:00 | 2026-07-23 16:00 |  |  | 1 | 0 | 1 | 42 | 5 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A34660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.4 | R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Install DRG S-575 to S-127 - Mitchell /Ross Inter /Palm SUP - R3 - P4 | 2026-06-05 08:00 | 2026-07-06 16:00 |  |  | 18 | 0 | 18 | 42 | 5 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A34720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Excavate - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-10-20 08:00 | 2023-10-23 16:00 |  |  | 2 | 0 | 2 | 292 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A34740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Drive Pile - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-10-24 08:00 | 2023-11-09 16:00 |  |  | 12 | 0 | 12 | 292 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A34750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | FRP Footing - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-11-13 08:00 | 2023-11-16 16:00 |  |  | 3 | 0 | 3 | 325 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A34760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Cure/Strip Footing - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-11-17 08:00 | 2023-11-23 16:00 |  |  | 7 | 0 | 7 | 563 |  |  | CURE | CURE
A34770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | FRP Column - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-11-27 08:00 | 2023-12-05 16:00 |  |  | 7 | 0 | 7 | 327 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A34780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Cure/Strip Column - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-12-06 08:00 | 2023-12-12 16:00 |  |  | 7 | 0 | 7 | 562 |  |  | CURE | CURE
A34790 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | FRP Cap - Brg 2 - Pier 1 - R1 - P2.S1 | 2023-12-14 08:00 | 2024-01-04 16:00 |  |  | 9 | 0 | 9 | 327 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A34800 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.1 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Cure/Strip Cap - Brg 2 - Pier 1 - R1 - P2.S1 | 2024-01-05 08:00 | 2024-01-11 16:00 |  |  | 7 | 0 | 7 | 556 |  |  | CURE | CURE
A34810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.15 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | 2025-02-27 08:00 | 2025-03-06 16:00 |  |  | 5 | 0 | 5 | 85 | 76 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A34820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Install SIP - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-10 16:00 |  |  | 2 | 0 | 2 | 85 | 76 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A34830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Install Overhangs - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-03-11 08:00 | 2025-04-04 16:00 |  |  | 17 | 0 | 17 | 85 | 76 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A34840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Reinforce Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-04-07 08:00 | 2025-04-11 16:00 |  |  | 5 | 0 | 5 | 85 | 76 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A34850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-04-14 08:00 | 2025-04-14 16:00 |  |  | 1 | 0 | 1 | 85 | 76 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A34860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Cure Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-04-15 08:00 | 2025-04-21 16:00 |  |  | 7 | 0 | 7 | 147 | 94 |  | CURE | CURE
A34870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Install Reinf Barrier - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-04-22 08:00 | 2025-04-25 16:00 |  |  | 3 | 0 | 3 | 88 | 94 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A34880 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.3 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Strip Overhangs - Brg 2 - Pour 1 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-22 16:00 |  |  | 4 | 0 | 4 | 86 | 84 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A34900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.6 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | FRPS Approach Slab 1 - Brg 2 - R1 - P2.S1 | 2025-04-15 08:00 | 2025-04-25 16:00 |  |  | 7 | 0 | 7 | 88 | 93 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A34910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.6 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | FRPS Approach Slab 2 - Brg 2 - R1 - P2.S1 | 2025-04-25 08:00 | 2025-05-05 16:00 |  |  | 7 | 0 | 7 | 82 | 75 | Approach Slab Crew | LANE.STRUCTURE.Bridge.Appr | STRUCTURE.Bridge.Approach Slab
A34920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.6 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Slip Barrier - Brg 2 - R1 - P2.S1 | 2025-05-08 08:00 | 2025-05-16 16:00 |  |  | 6 | 0 | 6 | 81 | 71 | Sub - Parapet Wall Crew | SUB.STRUCTURE.Bridge.Parapet | STRUCTURE.Bridge.Parapet
A34930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.6 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Grind Deck - Brg 2 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-23 16:00 |  |  | 5 | 0 | 5 | 81 | 71 | Sub - Diamond Grind Pavement Crew | SUB.CONCRETE.GRIND | CONCRETE PVMT.Diamond Grind
A34940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.6 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Groove Deck - Brg 2 - R1 - P2.S1 | 2025-05-27 08:00 | 2025-05-30 16:00 |  |  | 4 | 0 | 4 | 81 | 71 | Sub - Bridge Deck Grooving Crew | SUB.STRUCTURE.Bridge.Grooving | STRUCTURE.Bridge.Grooving
A34950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.6 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Perm Striping - Brg 2 - R1 - P2.S1 | 2025-06-02 08:00 | 2025-06-02 16:00 |  |  | 1 | 0 | 1 | 81 | 71 | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Perm
A34960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Excavate - Brg 2 - Pier 2 - R1 - P2.S1 | 2023-11-13 08:00 | 2023-11-14 16:00 |  |  | 2 | 0 | 2 | 292 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A34980 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Drive Pile - Brg 2 - Pier 2 - R1 - P2.S1 | 2023-11-16 08:00 | 2023-12-07 16:00 |  |  | 12 | 0 | 12 | 292 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A34990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | FRP Footing - Brg 2 - Pier 2 - R1 - P2.S1 | 2023-12-04 08:00 | 2023-12-07 16:00 |  |  | 3 | 0 | 3 | 307 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A35000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Cure/Strip Footing - Brg 2 - Pier 2 - R1 - P2.S1 | 2023-12-08 08:00 | 2023-12-14 16:00 |  |  | 7 | 0 | 7 | 530 |  |  | CURE | CURE
A35010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | FRP Column - Brg 2 - Pier 2 - R1 - P2.S1 | 2023-12-15 08:00 | 2024-01-08 16:00 |  |  | 10 | 0 | 10 | 307 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A35020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Cure/Strip Column - Brg 2 - Pier 2 - R1 - P2.S1 | 2024-01-09 08:00 | 2024-01-15 16:00 |  |  | 7 | 0 | 7 | 520 |  |  | CURE | CURE
A35030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | FRP Cap - Brg 2 - Pier 2 - R1 - P2.S1 | 2024-01-16 08:00 | 2024-01-30 16:00 |  |  | 9 | 0 | 9 | 307 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A35040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.2 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Cure/Strip Cap - Brg 2 - Pier 2 - R1 - P2.S1 | 2024-01-31 08:00 | 2024-02-06 16:00 |  |  | 7 | 0 | 7 | 519 |  |  | CURE | CURE
A35050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.15 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | 2025-02-27 08:00 | 2025-03-06 16:00 |  |  | 5 | 0 | 5 | 89 | 80 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A35060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Install SIP - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-10 16:00 |  |  | 2 | 0 | 2 | 91 | 97 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A35070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Install Overhangs - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-03-11 08:00 | 2025-04-01 16:00 |  |  | 14 | 0 | 14 | 91 | 97 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35080 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Reinforce Deck - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-04-02 08:00 | 2025-04-08 16:00 |  |  | 5 | 0 | 5 | 91 | 97 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35090 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Place Deck - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-04-09 08:00 | 2025-04-09 16:00 |  |  | 1 | 0 | 1 | 91 | 97 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A35100 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Cure Deck - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-04-10 08:00 | 2025-04-16 16:00 |  |  | 7 | 0 | 7 | 152 | 97 |  | CURE | CURE
A35110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Install Reinf Barrier - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-04-17 08:00 | 2025-04-21 16:00 |  |  | 3 | 0 | 3 | 91 | 97 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.4 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Strip Overhangs - Brg 2 - Pour 2 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-22 16:00 |  |  | 4 | 0 | 4 | 86 | 85 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.15 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | 2025-02-27 08:00 | 2025-03-06 16:00 |  |  | 5 | 0 | 5 | 89 | 81 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A35150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Install SIP - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-10 16:00 |  |  | 2 | 0 | 2 | 91 | 96 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A35160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Install Overhangs - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-03-11 08:00 | 2025-03-31 16:00 |  |  | 13 | 0 | 13 | 91 | 96 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Reinforce Deck - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-04-01 08:00 | 2025-04-07 16:00 |  |  | 5 | 0 | 5 | 91 | 96 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Place Deck - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-04-08 08:00 | 2025-04-08 16:00 |  |  | 1 | 0 | 1 | 91 | 96 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A35190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Cure Deck - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-04-09 08:00 | 2025-04-15 16:00 |  |  | 7 | 0 | 7 | 153 | 98 |  | CURE | CURE
A35200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Install Reinf Barrier - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-04-17 08:00 | 2025-04-21 16:00 |  |  | 3 | 0 | 3 | 91 | 98 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.5 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Strip Overhangs - Brg 2 - Pour 4 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-21 16:00 |  |  | 3 | 0 | 3 | 87 | 90 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35230 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Excavate - Brg 2 - Pier 3 - R1 - P2.S1 | 2023-12-08 08:00 | 2023-12-11 16:00 |  |  | 2 | 0 | 2 | 292 |  | Structural Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.STR Excavation
A35250 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Drive Pile - Brg 2 - Pier 3 - R1 - P2.S1 | 2023-12-12 08:00 | 2024-01-08 16:00 |  |  | 12 | 0 | 12 | 292 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A35260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | FRP Footing - Brg 2 - Pier 3 - R1 - P2.S1 | 2024-01-09 08:00 | 2024-01-11 16:00 |  |  | 3 | 0 | 3 | 292 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A35270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Cure/Strip Footing - Brg 2 - Pier 3 - R1 - P2.S1 | 2024-01-12 08:00 | 2024-01-18 16:00 |  |  | 7 | 0 | 7 | 497 |  |  | CURE | CURE
A35280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | FRP Column - Brg 2 - Pier 3 - R1 - P2.S1 | 2024-01-19 08:00 | 2024-02-01 16:00 |  |  | 8 | 0 | 8 | 293 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A35290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Cure/Strip Column - Brg 2 - Pier 3 - R1 - P2.S1 | 2024-02-02 08:00 | 2024-02-08 16:00 |  |  | 7 | 0 | 7 | 496 |  |  | CURE | CURE
A35300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | FRP Cap - Brg 2 - Pier 3 - R1 - P2.S1 | 2024-02-09 08:00 | 2024-02-23 16:00 |  |  | 9 | 0 | 9 | 293 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A35310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.7 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Cure/Strip Cap - Brg 2 - Pier 3 - R1 - P2.S1 | 2024-02-24 08:00 | 2024-03-01 16:00 |  |  | 7 | 0 | 7 | 495 |  |  | CURE | CURE
A35320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.15 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | 2025-02-27 08:00 | 2025-03-06 16:00 |  |  | 5 | 0 | 5 | 82 | 71 | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A35330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Install SIP - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-02-06 08:00 | 2025-02-07 16:00 |  |  | 2 | 0 | 2 | 105 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A35340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Install Overhangs - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-02-10 08:00 | 2025-03-06 16:00 |  |  | 15 | 0 | 15 | 105 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Reinforce Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-14 16:00 |  |  | 5 | 0 | 5 | 105 |  | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Place Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-04-15 08:00 | 2025-04-15 16:00 |  |  | 1 | 0 | 1 | 85 | 76 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A35370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Cure Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-04-16 08:00 | 2025-04-22 16:00 |  |  | 7 | 0 | 7 | 146 | 91 |  | CURE | CURE
A35380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Install Reinf Barrier - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-04-24 08:00 | 2025-04-28 16:00 |  |  | 3 | 0 | 3 | 87 | 91 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.8 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Strip Overhangs - Brg 2 - Pour 3 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-22 16:00 |  |  | 4 | 0 | 4 | 86 | 86 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.9 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - MOT | Install I-275 NB Detour - R1 - P2.S1 | 2025-02-21 08:00 | 2025-02-25 16:00 |  |  | 3 | 0 | 3 | 82 | 71 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A35430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.14 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Grading - Brg 2 - End Bent 1 - R1 - P2.S1 | 2023-10-13 08:00 | 2023-10-13 16:00 |  |  | 1 | 0 | 1 | 292 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A35450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.14 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Drive Pile - Brg 2 - End Bent 1 - R1 - P2.S1 | 2023-10-16 08:00 | 2023-10-23 16:00 |  |  | 5 | 0 | 5 | 292 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A35460 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.14 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | FRP Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | 2024-03-25 08:00 | 2024-04-08 16:00 |  |  | 11 | 0 | 11 | 270 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A35470 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.14 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Cure/Strip Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | 2024-04-09 08:00 | 2024-04-11 16:00 |  |  | 3 | 0 | 3 | 459 |  |  | CURE | CURE
A35480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.14 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Const MSE Wall & Bkfill - RW 2-1 / Brg 2 - End Bent 1 - R1 - P2.S1 | 2024-02-08 08:00 | 2024-03-22 16:00 |  |  | 27 | 0 | 27 | 270 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A35490 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.14 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Temp Wall or SOE - Brg 2 - End Bent 1 - R1 - P2.S1 | 2023-10-02 08:00 | 2023-10-12 16:00 |  |  | 8 | 0 | 8 | 292 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A35500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.13 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Grading - Brg 2 - End Bent 2 - R1 - P2.S1 | 2023-11-06 08:00 | 2023-11-06 16:00 |  |  | 1 | 0 | 1 | 338 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A35520 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.13 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Drive Pile - Brg 2 - End Bent 2 - R1 - P2.S1 | 2023-11-07 08:00 | 2023-11-16 16:00 |  |  | 5 | 0 | 5 | 338 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A35530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.13 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | FRP Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | 2024-02-16 08:00 | 2024-03-04 16:00 |  |  | 11 | 0 | 11 | 296 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A35540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.13 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Cure/Strip Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | 2024-03-05 08:00 | 2024-03-07 16:00 |  |  | 3 | 0 | 3 | 501 |  |  | CURE | CURE
A35550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.13 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Const MSE Wall & Bkfill - RW 2-4 / Brg 2 - End Bent 2 - R1 - P2.S1 | 2024-02-08 08:00 | 2024-02-15 16:00 |  |  | 5 | 0 | 5 | 296 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A35560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.13 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Temp Wall or SOE - Brg 2 - End Bent 2 - R1 - P2.S1 | 2023-10-02 08:00 | 2023-11-03 16:00 |  |  | 23 | 0 | 23 | 338 |  | Structural Earthwork Crew | LANE.STRUCTURE.Wall.Soldier | EARTH.STR Excavation
A35570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 2023-10-02 08:00 |  |  |  | 0 | 0 | 0 | 364 |  |  | MS | MS
A35580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Start Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | 2025-02-21 08:00 |  |  |  | 0 | 0 | 0 | 94 | 71 |  | MS | MS
A35590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.7 | R1 - Milestones | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure |  | 2024-04-11 16:00 |  |  | 0 | 0 | 0 | 687 |  |  | MS | MS
LoE360 | Not Started | I-275 - I-4 - IBL(all) - B1.1.1.1 | R1 Phase Durations | R1 Phase 2 Stage 1 Step 2 - New Ramp NE-C Superstructure [LoE] | 2025-02-21 08:00 | 2025-06-02 16:00 |  |  | 102 | 0 | 102 | 136 |  |  | LOE | LOE
A35610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Cut/Fill to Grade - Ramp C / I-275 SB Gore - R3 - P3 | 2026-06-05 08:00 | 2026-06-05 16:00 |  |  | 1 | 0 | 1 | 45 | 9 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A35630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place Stabilization - Ramp C / I-275 SB Gore - R3 - P4 | 2026-06-26 08:00 | 2026-06-29 16:00 |  |  | 2 | 0 | 2 | 45 | 9 | Subgrade Stabilization Crew | LANE.EARTH.STR | EARTH.Soil-Stab.Lime
A35640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place Asphalt Base - Ramp C /I-275 SB Gore - R3 - P4 | 2026-06-30 08:00 | 2026-06-30 16:00 |  |  | 1 | 0 | 1 | 45 | 9 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A35650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place Concrete Pav - Ramp C /I-275 SB Gore - R3 - P4 | 2026-07-01 08:00 | 2026-07-07 16:00 |  |  | 4 | 0 | 4 | 45 | 9 | Concrete Pvmt Slipform Crew | LANE.CONCRETE.Slip | CONCRETE PVMT.Slipform Conc Pvmt
A35660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place Edge Drain - Ramp C /I-275 SB Gore - R3 - P4 | 2026-07-09 08:00 | 2026-07-10 16:00 |  |  | 2 | 0 | 2 | 45 | 9 | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A35670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place Shoulder GAB - Ramp C /I-275 SB Gore - R3 - P4 | 2026-07-13 08:00 | 2026-07-14 16:00 |  |  | 2 | 0 | 2 | 45 | 9 | Agg Base Crew | LANE.EARTH.STR | BASE.ABC
A35680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place Asphalt Shoulder - Ramp C /I-275 SB Gore - R3 - P4 | 2026-07-16 08:00 | 2026-07-16 16:00 |  |  | 1 | 0 | 1 | 45 | 9 | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A35620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.3 | R3 - Ph4 - Ramp C / I-275 SB Gore | Place 3-Pour Barrier - Ramp C / I-275 SB Gore - R3 - P3 | 2026-06-08 08:00 | 2026-06-25 16:00 |  |  | 11 | 0 | 11 | 45 | 9 | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A35700 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.6.6 | R3 - Ph4 - Final MOT | Shift Traffic - Ramp C Left - R3 - P4 - Final MOT | 2026-07-27 08:00 | 2026-07-27 16:00 |  |  | 1 | 0 | 1 | 40 | 1 | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A35720 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Install SIP - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-10 16:00 |  |  | 2 | 0 | 2 | 89 | 80 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A35730 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Install Overhangs - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-03-11 08:00 | 2025-04-02 16:00 |  |  | 15 | 0 | 15 | 89 | 80 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35740 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Reinforce Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-04-03 08:00 | 2025-04-09 16:00 |  |  | 5 | 0 | 5 | 89 | 80 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35750 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Place Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-04-17 08:00 | 2025-04-17 16:00 |  |  | 1 | 0 | 1 | 85 | 76 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A35760 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Cure Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-04-18 08:00 | 2025-04-24 16:00 |  |  | 7 | 0 | 7 | 144 | 89 |  | CURE | CURE
A35770 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Install Reinf Barrier - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-04-25 08:00 | 2025-04-29 16:00 |  |  | 3 | 0 | 3 | 86 | 89 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35780 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.10 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Strip Overhangs - Brg 2 - Pour 5 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-22 16:00 |  |  | 4 | 0 | 4 | 86 | 87 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35810 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Install SIP - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-10 16:00 |  |  | 2 | 0 | 2 | 90 | 95 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A35820 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Install Overhangs - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-03-11 08:00 | 2025-04-02 16:00 |  |  | 15 | 0 | 15 | 90 | 95 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35830 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Reinforce Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-04-03 08:00 | 2025-04-09 16:00 |  |  | 5 | 0 | 5 | 90 | 95 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35840 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Place Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-04-10 08:00 | 2025-04-10 16:00 |  |  | 1 | 0 | 1 | 90 | 95 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A35850 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Cure Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-04-11 08:00 | 2025-04-17 16:00 |  |  | 7 | 0 | 7 | 151 | 95 |  | CURE | CURE
A35860 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Install Reinf Barrier - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-04-18 08:00 | 2025-04-22 16:00 |  |  | 3 | 0 | 3 | 90 | 95 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35870 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.11 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Strip Overhangs - Brg 2 - Pour 6 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-22 16:00 |  |  | 4 | 0 | 4 | 86 | 88 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35900 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Install SIP - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-03-07 08:00 | 2025-03-10 16:00 |  |  | 2 | 0 | 2 | 82 | 71 | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A35910 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Install Overhangs - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-03-11 08:00 | 2025-04-08 16:00 |  |  | 19 | 0 | 19 | 82 | 71 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35920 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Reinforce Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-04-09 08:00 | 2025-04-22 16:00 |  |  | 9 | 0 | 9 | 82 | 71 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35930 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Place Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-04-24 08:00 | 2025-04-24 16:00 |  |  | 1 | 0 | 1 | 82 | 71 | Structural Pour Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Pour Deck
A35940 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Cure Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-04-25 08:00 | 2025-05-01 16:00 |  |  | 7 | 0 | 7 | 137 | 71 |  | CURE | CURE
A35950 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Install Reinf Barrier - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-05-02 08:00 | 2025-05-06 16:00 |  |  | 3 | 0 | 3 | 81 | 71 | Sub - Rebar Placement Crew | SUB.STRUCTURE.Rebar | STRUCTURE.Rebar
A35960 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.12 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Strip Overhangs - Brg 2 - Pour 7 - R1 - P2.S1 | 2025-05-19 08:00 | 2025-05-23 16:00 |  |  | 5 | 0 | 5 | 85 | 79 | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A35970 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.15 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Girders - Brg 2 - Spans 3 - R1 - P2.S1 | 2025-01-30 08:00 | 2025-02-05 16:00 |  |  | 5 | 0 | 5 | 105 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A35990 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.3.15 | R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Falsework - Brg 2 - Spans 1-2 - R1 - P2.S1 | 2023-10-02 08:00 | 2023-10-06 16:00 |  |  | 5 | 0 | 5 | 375 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A36000 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-9 - R3 | 2023-05-04 08:00 | 2023-05-25 16:00 |  |  | 15 | 0 | 15 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36010 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-6 - R3 | 2023-07-27 08:00 | 2023-08-17 16:00 |  |  | 15 | 0 | 15 | 97 | 34 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36020 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-5 - R3 | 2023-09-18 08:00 | 2023-10-10 16:00 |  |  | 15 | 0 | 15 | 81 | 33 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36030 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-4 - R3 | 2023-10-17 08:00 | 2023-11-07 16:00 |  |  | 15 | 0 | 15 | 78 | 32 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36040 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-3 - R3 | 2023-11-30 08:00 | 2024-01-02 16:00 |  |  | 15 | 0 | 15 | 68 | 31 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36050 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-2 - R3 | 2024-02-01 08:00 | 2024-02-26 16:00 |  |  | 15 | 0 | 15 | 51 | 11 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36060 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-1 - R3 | 2024-03-05 08:00 | 2024-03-28 16:00 |  |  | 15 | 0 | 15 | 46 | 7 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
D3040 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Develop and Submit - 90% Cat1 Brg 06 Plans - R2 | 2024-06-18 08:00 | 2024-09-11 16:00 |  |  | 60 | 0 | 60 | 295 |  |  | DESIGN | DESIGN
D3050 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Review and Approve - 90% Cat1 Brg 06 Plans - R2 | 2024-09-12 08:00 | 2024-10-02 16:00 |  |  | 15 | 0 | 15 | 295 |  |  | OWNER.Design Review | OWNER
D3060 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Develop and Submit - Final Cat1 Brg 06 Plans - R2 | 2024-10-03 08:00 | 2024-10-30 16:00 |  |  | 20 | 0 | 20 | 295 |  |  | DESIGN | DESIGN
D3070 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Review and Approve - Final Cat1 Brg 06 Plans - R2 | 2024-10-31 08:00 | 2024-11-21 16:00 |  |  | 15 | 0 | 15 | 295 |  |  | OWNER.Design Review | OWNER
D3080 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 06 Plans - R2 | 2024-11-22 08:00 | 2024-12-09 16:00 |  |  | 10 | 0 | 10 | 295 |  |  | DESIGN | DESIGN
D3090 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Issue - RFC Cat1 Brg 06 Plans - R2 | 2024-12-10 08:00 | 2024-12-16 16:00 |  |  | 5 | 0 | 5 | 295 |  |  | DESIGN | DESIGN
D1230 | In Progress | I-275 - I-4 - IBL(all) - B1.3.1.1 | Design Quality Management Plan | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | 2022-10-17 08:00 | 2023-09-29 16:00 | 2022-10-17 08:00 |  | 230 | 30 | 211 | 114 |  |  | DESIGN | DESIGN
P1380 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Brg 2 - Cat 2 - Steel | 2024-02-20 08:00 | 2025-01-28 16:00 |  |  | 240 | 0 | 240 | 114 |  |  | PROCURE | PROCUREMENT
P1430 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 08 | 2023-06-21 08:00 | 2023-07-05 16:00 |  |  | 10 | 0 | 10 | 329 |  |  | PROCURE | PROCUREMENT
A36110 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.5 | R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install Landscaping - Ramp NE / WE | 2024-06-14 08:00 | 2026-05-18 16:00 |  |  | 407 | 0 | 407 | 81 |  |  | LOE | LOE
A36120 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.6 | R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Install Landscaping - Ramp EN | 2024-09-26 08:00 | 2025-11-18 16:00 |  |  | 246 | 0 | 246 | 216 |  |  | LOE | LOE
A36130 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.10 | R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Install Landscaping - Ramp F / Ramp B / Ramp C / Ramp G / I | 2024-05-30 08:00 | 2026-07-27 16:00 |  |  | 458 | 0 | 458 | 40 |  |  | LOE | LOE
A36140 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.5 | R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install Grass - Ramp NE / WE | 2024-06-14 08:00 | 2026-05-18 16:00 |  |  | 407 | 0 | 407 | 81 |  |  | LOE | LOE
A36150 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.6 | R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Install Grass - Ramp EN | 2024-09-26 08:00 | 2025-11-18 16:00 |  |  | 246 | 0 | 246 | 216 |  |  | LOE | LOE
A36160 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.10 | R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Install Grass - Ramp F / Ramp B / Ramp C / Ramp G / I | 2024-05-30 08:00 | 2026-07-27 16:00 |  |  | 458 | 0 | 458 | 40 |  |  | LOE | LOE
A36170 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.5 | R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install ITS - Ramp NE / WE | 2024-06-14 08:00 | 2026-05-18 16:00 |  |  | 407 | 0 | 407 | 81 |  |  | LOE | LOE
A36180 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.6 | R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Install ITS - Ramp EN | 2024-09-26 08:00 | 2025-11-18 16:00 |  |  | 246 | 0 | 246 | 216 |  |  | LOE | LOE
A36190 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.10 | R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Install ITS - Ramp F / Ramp B / Ramp C / Ramp G / I | 2024-05-30 08:00 | 2026-07-27 16:00 |  |  | 458 | 0 | 458 | 40 |  |  | LOE | LOE
A36200 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.5 | R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install LIghting - Ramp NE / WE | 2024-06-14 08:00 | 2026-05-18 16:00 |  |  | 407 | 0 | 407 | 81 |  |  | LOE | LOE
A36210 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.5 | R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install Signals - Ramp NE / WE | 2024-06-14 08:00 | 2026-05-18 16:00 |  |  | 407 | 0 | 407 | 81 |  |  | LOE | LOE
A36220 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.6 | R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Install Lighting - Ramp EN | 2024-09-26 08:00 | 2025-11-18 16:00 |  |  | 246 | 0 | 246 | 216 |  |  | LOE | LOE
A36240 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.10 | R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Install Lighting - Ramp F / Ramp B / Ramp C / Ramp G / I | 2024-05-30 08:00 | 2026-07-27 16:00 |  |  | 458 | 0 | 458 | 40 |  |  | LOE | LOE
A21995 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.7 | R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 2-3 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 2025-07-30 08:00 | 2025-09-05 16:00 |  |  | 23 | 0 | 23 | 81 | 71 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A21015 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 1 | 2026-02-10 08:00 | 2026-03-19 16:00 |  |  | 23 | 0 | 23 | 81 | 71 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A15455 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 2 | 2024-02-16 08:00 | 2024-03-27 16:00 |  |  | 25 | 0 | 25 | 96 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A15465 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.7 | R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 2 | 2024-03-28 08:00 | 2024-05-13 16:00 |  |  | 30 | 0 | 30 | 96 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A36260 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.10 | R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Const MSE Wall & Bkfill - RW 6-1 - Ramp EN Sta 85 to 88 - R2 - P1 | 2025-01-31 08:00 | 2025-03-06 16:00 |  |  | 21 | 0 | 21 | 295 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A36270 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 104 - Ramp EN Sta 68 to 72 - R2 - P1 | 2025-06-04 08:00 | 2025-06-24 16:00 |  |  | 13 | 0 | 13 | 216 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26023 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | 2024-07-10 08:00 | 2024-08-19 16:00 |  |  | 25 | 0 | 25 | 119 | 57 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26026 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | 2024-09-30 08:00 | 2024-10-30 16:00 |  |  | 21 | 0 | 21 | 76 | 46 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26028 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | 2024-09-30 08:00 | 2024-10-30 16:00 |  |  | 21 | 0 | 21 | 43 | 1 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26053 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | 2024-06-05 08:00 | 2024-07-09 16:00 |  |  | 21 | 0 | 21 | 119 | 56 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26056 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | 2024-08-22 08:00 | 2024-09-27 16:00 |  |  | 21 | 0 | 21 | 76 | 46 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26058 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.15 | R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | 2024-08-22 08:00 | 2024-09-27 16:00 |  |  | 21 | 0 | 21 | 43 | 1 | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A26133 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 2 | 2024-11-01 08:00 | 2024-12-13 16:00 |  |  | 23 | 0 | 23 | 43 | 1 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26136 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.16 | R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 3 | 2024-11-01 08:00 | 2024-12-13 16:00 |  |  | 23 | 0 | 23 | 43 | 3 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A26242 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.17 | R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 2 | 2024-09-13 08:00 | 2024-10-21 16:00 |  |  | 23 | 0 | 23 | 83 | 50 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A33314 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.16 | R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 2 | 2026-01-22 08:00 | 2026-02-27 16:00 |  |  | 23 | 0 | 23 | 40 | 2 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A15755 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.2.10 | R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Cut/Fill to Grade - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 - part 2 | 2023-08-21 08:00 | 2023-10-04 16:00 |  |  | 26 | 0 | 26 | 263 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
A16345 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.3 | R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 2 | 2024-07-25 08:00 | 2024-08-22 16:00 |  |  | 18 | 0 | 18 | 353 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.EW-ALL | EARTH.Excavate
D3180 | In Progress | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Develop and Submit - 60% - 60" Drainage System - R3 | 2022-11-01 08:00 | 2022-12-22 16:00 | 2022-11-01 08:00 |  | 24 | 19 | 16 | 49 | 1 |  | DESIGN | DESIGN
D3190 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Review and Approve - 60% - 60" Drainage System - R3 | 2022-12-23 08:00 | 2022-12-30 16:00 |  |  | 5 | 0 | 5 | 49 | 1 |  | OWNER.Design Review | OWNER
D3200 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Develop and Submit - 90% - 60" Drainage System - R3 | 2023-01-03 08:00 | 2023-02-01 16:00 |  |  | 21 | 0 | 21 | 49 | 1 |  | DESIGN | DESIGN
D3210 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Review and Approve - 90% - 60" Drainage System - R3 | 2023-02-02 08:00 | 2023-02-22 16:00 |  |  | 15 | 0 | 15 | 49 | 1 |  | OWNER.Design Review | OWNER
D3220 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Develop and Submit - Final - 60" Drainage System - R3 | 2023-02-23 08:00 | 2023-03-22 16:00 |  |  | 20 | 0 | 20 | 49 | 1 |  | DESIGN | DESIGN
D3230 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Review and Approve - Final - 60" Drainage System - R3 | 2023-03-23 08:00 | 2023-04-12 16:00 |  |  | 15 | 0 | 15 | 49 | 1 |  | OWNER.Design Review | OWNER
D3240 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Develop and Submit - Sign & Seal - 60" Drainage System - R3 | 2023-04-13 08:00 | 2023-04-26 16:00 |  |  | 10 | 0 | 10 | 49 | 1 |  | DESIGN | DESIGN
D3250 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.3 | R3 60" Drainage System Design (DRMP) | Issue - RFC - 60" Drainage System - R3 | 2023-04-27 08:00 | 2023-05-03 16:00 |  |  | 5 | 0 | 5 | 49 | 1 |  | DESIGN | DESIGN
A22845 | Not Started | I-275 - I-4 - IBL(all) - B1.2.3.2.5 | R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 2 | 2025-03-31 08:00 | 2025-04-28 16:00 |  |  | 19 | 0 | 19 | 252 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A36280 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.11.8 | R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 2 | 2025-09-15 08:00 | 2025-10-09 16:00 |  |  | 16 | 0 | 16 | 84 | 78 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A21018 | Not Started | I-275 - I-4 - IBL(all) - B1.2.2.6.7 | R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 2 | 2026-02-10 08:00 | 2026-03-19 16:00 |  |  | 23 | 0 | 23 | 81 | 72 | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
D3260 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | 2023-04-24 08:00 | 2023-07-18 16:00 |  |  | 60 | 0 | 60 | 599 |  |  | DESIGN | DESIGN
D3270 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 599 |  |  | OWNER.Design Review | OWNER
D3280 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Develop and Submit - Final Cat1 Brg 01 Plans - R1 | 2023-04-11 08:00 | 2023-05-08 16:00 |  |  | 20 | 0 | 20 | 599 |  |  | DESIGN | DESIGN
D3290 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Review and Approve - Final Cat1 Brg 01 Plans - R1 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 599 |  |  | OWNER.Design Review | OWNER
D3300 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 01 Plans - R1 | 2023-05-31 08:00 | 2023-06-13 16:00 |  |  | 10 | 0 | 10 | 599 |  |  | DESIGN | DESIGN
D3310 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Issue - RFC Cat1 Brg 01 Plans - R1 | 2023-06-14 08:00 | 2023-06-20 16:00 |  |  | 5 | 0 | 5 | 599 |  |  | DESIGN | DESIGN
D3320 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | 2023-12-20 08:00 | 2024-03-15 16:00 |  |  | 60 | 0 | 60 | 100 | 71 |  | DESIGN | DESIGN
D3330 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Review and Approve - 90% Cat1 Brg 04 Plans - R1 | 2024-03-18 08:00 | 2024-04-05 16:00 |  |  | 15 | 0 | 15 | 177 |  |  | OWNER.Design Review | OWNER
D3340 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Develop and Submit - Final Cat1 Brg 04 Plans - R1 | 2024-04-08 08:00 | 2024-05-03 16:00 |  |  | 20 | 0 | 20 | 177 |  |  | DESIGN | DESIGN
D3350 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Review and Approve - Final Cat1 Brg 04 Plans - R1 | 2024-05-06 08:00 | 2024-05-24 16:00 |  |  | 15 | 0 | 15 | 177 |  |  | OWNER.Design Review | OWNER
D3360 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 04 Plans - R1 | 2024-05-28 08:00 | 2024-06-10 16:00 |  |  | 10 | 0 | 10 | 177 |  |  | DESIGN | DESIGN
D3370 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Issue - RFC Cat1 Brg 04 Plans - R1 | 2024-06-11 08:00 | 2024-06-17 16:00 |  |  | 5 | 0 | 5 | 177 |  |  | DESIGN | DESIGN
D3380 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | 2022-12-22 08:00 | 2023-03-20 16:00 |  |  | 60 | 0 | 60 | 100 | 71 |  | DESIGN | DESIGN
D3390 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 100 | 71 |  | OWNER.Design Review | OWNER
D3400 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Develop and Submit - Final Cat1 Brg 05 Plans - R1 | 2023-04-11 08:00 | 2023-05-08 16:00 |  |  | 20 | 0 | 20 | 100 | 71 |  | DESIGN | DESIGN
D3410 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Review and Approve - Final Cat1 Brg 05 Plans - R1 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 100 | 71 |  | OWNER.Design Review | OWNER
D3420 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 05 Plans - R1 | 2023-05-31 08:00 | 2023-06-13 16:00 |  |  | 10 | 0 | 10 | 100 | 71 |  | DESIGN | DESIGN
D3430 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Issue - RFC Cat1 Brg 05 Plans - R1 | 2023-06-14 08:00 | 2023-06-20 16:00 |  |  | 5 | 0 | 5 | 100 | 71 |  | DESIGN | DESIGN
D3440 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Develop and Submit - 90% Cat1 Brg 07 Plans - R2 | 2024-06-18 08:00 | 2024-09-11 16:00 |  |  | 60 | 0 | 60 | 348 |  |  | DESIGN | DESIGN
D3450 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Review and Approve - 90% Cat1 Brg 07 Plans - R2 | 2024-09-12 08:00 | 2024-10-02 16:00 |  |  | 15 | 0 | 15 | 348 |  |  | OWNER.Design Review | OWNER
D3460 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Develop and Submit - Final Cat1 Brg 07 Plans - R2 | 2024-10-03 08:00 | 2024-10-30 16:00 |  |  | 20 | 0 | 20 | 348 |  |  | DESIGN | DESIGN
D3470 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Review and Approve - Final Cat1 Brg 07 Plans - R2 | 2024-10-31 08:00 | 2024-11-21 16:00 |  |  | 15 | 0 | 15 | 348 |  |  | OWNER.Design Review | OWNER
D3480 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 07 Plans - R2 | 2024-11-22 08:00 | 2024-12-09 16:00 |  |  | 10 | 0 | 10 | 348 |  |  | DESIGN | DESIGN
D3490 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Issue - RFC Cat1 Brg 07 Plans - R2 | 2024-12-10 08:00 | 2024-12-16 16:00 |  |  | 5 | 0 | 5 | 348 |  |  | DESIGN | DESIGN
D3500 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | 2022-12-22 08:00 | 2023-03-20 16:00 |  |  | 60 | 0 | 60 | 296 |  |  | DESIGN | DESIGN
D3510 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | 2023-03-21 08:00 | 2023-04-10 16:00 |  |  | 15 | 0 | 15 | 296 |  |  | OWNER.Design Review | OWNER
D3520 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Develop and Submit - Final Cat1 Brg 09 Plans - R3 | 2023-04-11 08:00 | 2023-05-08 16:00 |  |  | 20 | 0 | 20 | 296 |  |  | DESIGN | DESIGN
D3530 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Review and Approve - Final Cat1 Brg 09 Plans - R3 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 296 |  |  | OWNER.Design Review | OWNER
D3540 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 09 Plans - R3 | 2023-05-31 08:00 | 2023-06-13 16:00 |  |  | 10 | 0 | 10 | 296 |  |  | DESIGN | DESIGN
D3550 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Issue - RFC Cat1 Brg 09 Plans - R3 | 2023-06-14 08:00 | 2023-06-20 16:00 |  |  | 5 | 0 | 5 | 296 |  |  | DESIGN | DESIGN
D3560 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - 90% Cat1 Brg 12 Plans - R3 | 2023-12-20 08:00 | 2024-03-15 16:00 |  |  | 60 | 0 | 60 | 462 |  |  | DESIGN | DESIGN
D3570 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Review and Approve - 90% Cat1 Brg 12 Plans - R3 | 2024-03-18 08:00 | 2024-04-05 16:00 |  |  | 15 | 0 | 15 | 462 |  |  | OWNER.Design Review | OWNER
D3580 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - Final Cat1 Brg 12 Plans - R3 | 2024-04-08 08:00 | 2024-05-03 16:00 |  |  | 20 | 0 | 20 | 462 |  |  | DESIGN | DESIGN
D3590 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Review and Approve - Final Cat1 Brg 12 Plans - R3 | 2024-05-06 08:00 | 2024-05-24 16:00 |  |  | 15 | 0 | 15 | 462 |  |  | OWNER.Design Review | OWNER
D3600 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - Sign & Seal Cat1 Brg 12 Plans - R3 | 2024-05-28 08:00 | 2024-06-10 16:00 |  |  | 10 | 0 | 10 | 462 |  |  | DESIGN | DESIGN
D3610 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Issue - RFC Cat1 Brg 12 Plans - R3 | 2024-06-11 08:00 | 2024-06-17 16:00 |  |  | 5 | 0 | 5 | 462 |  |  | DESIGN | DESIGN
D3620 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 426 |  |  | DESIGN | DESIGN
D3630 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | 2023-09-15 08:00 | 2023-10-05 16:00 |  |  | 15 | 0 | 15 | 426 |  |  | OWNER.Design Review | OWNER
D3640 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - Final Cat1 Brg 11 Plans - R3 | 2023-10-06 08:00 | 2023-11-02 16:00 |  |  | 20 | 0 | 20 | 426 |  |  | DESIGN | DESIGN
D3650 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Review and Approve - Final Cat1 Brg 11 Plans - R3 | 2023-11-03 08:00 | 2023-11-28 16:00 |  |  | 15 | 0 | 15 | 426 |  |  | OWNER.Design Review | OWNER
D3660 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - Sign & Seal Cat1 Brg 11 Plans - R3 | 2023-11-29 08:00 | 2023-12-12 16:00 |  |  | 10 | 0 | 10 | 426 |  |  | DESIGN | DESIGN
D3670 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Issue - RFC Cat1 Brg 11 Plans - R3 | 2023-12-13 08:00 | 2023-12-19 16:00 |  |  | 5 | 0 | 5 | 426 |  |  | DESIGN | DESIGN
D3680 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 488 |  |  | DESIGN | DESIGN
D3690 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 488 |  |  | OWNER.Design Review | OWNER
D3700 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 488 |  |  | DESIGN | DESIGN
D3710 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 488 |  |  | OWNER.Design Review | OWNER
D3720 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 488 |  |  | DESIGN | DESIGN
D3730 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 488 |  |  | DESIGN | DESIGN
D3740 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 317 |  |  | DESIGN | DESIGN
D3750 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 317 |  |  | OWNER.Design Review | OWNER
D3760 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Final MSE Wall RW 2-1 - Br 2 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 317 |  |  | DESIGN | DESIGN
D3770 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - Final MSE Wall RW 2-1 - Br 2 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 317 |  |  | OWNER.Design Review | OWNER
D3780 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-1 - Br 2 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 317 |  |  | DESIGN | DESIGN
D3790 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Issue - RFC MSE Wall RW 2-1 - Br 2 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 317 |  |  | DESIGN | DESIGN
D3800 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 597 |  |  | DESIGN | DESIGN
D3810 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 597 |  |  | OWNER.Design Review | OWNER
D3820 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 597 |  |  | DESIGN | DESIGN
D3830 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 597 |  |  | OWNER.Design Review | OWNER
D3840 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Sign & Seal MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 597 |  |  | DESIGN | DESIGN
D3850 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 597 |  |  | DESIGN | DESIGN
D3860 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 468 |  |  | DESIGN | DESIGN
D3870 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 468 |  |  | OWNER.Design Review | OWNER
D3880 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 468 |  |  | DESIGN | DESIGN
D3890 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 468 |  |  | OWNER.Design Review | OWNER
D3900 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Sign & Seal MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 468 |  |  | DESIGN | DESIGN
D3910 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 468 |  |  | DESIGN | DESIGN
D3980 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 345 |  |  | DESIGN | DESIGN
D3990 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 345 |  |  | OWNER.Design Review | OWNER
D4000 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Final MSE Wall RW 2-4 Br 2 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 345 |  |  | DESIGN | DESIGN
D4010 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - Final MSE Wall RW 2-4 Br 2 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 345 |  |  | OWNER.Design Review | OWNER
D4020 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-4 Br 2 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 345 |  |  | DESIGN | DESIGN
D4030 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Issue - RFC MSE Wall RW 2-4 Br 2 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 345 |  |  | DESIGN | DESIGN
D4040 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 2023-06-21 08:00 | 2023-08-28 16:00 |  |  | 48 | 0 | 48 | 198 |  |  | DESIGN | DESIGN
D4050 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | 2023-08-29 08:00 | 2023-09-19 16:00 |  |  | 15 | 0 | 15 | 220 |  |  | OWNER.Design Review | OWNER
D4060 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | 2023-09-20 08:00 | 2023-10-17 16:00 |  |  | 20 | 0 | 20 | 220 |  |  | DESIGN | DESIGN
D4070 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Review and Approve - Final MSE Wall RW 3-1 Br 3 | 2023-10-18 08:00 | 2023-11-07 16:00 |  |  | 15 | 0 | 15 | 220 |  |  | OWNER.Design Review | OWNER
D4080 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - Sign & Seal MSE Wall RW 3-1 Br 3 | 2023-11-08 08:00 | 2023-12-01 16:00 |  |  | 15 | 0 | 15 | 220 |  |  | DESIGN | DESIGN
D4090 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Issue - RFC MSE Wall RW 3-1 Br 3 | 2023-12-04 08:00 | 2023-12-08 16:00 |  |  | 5 | 0 | 5 | 220 |  |  | DESIGN | DESIGN
D4100 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 2023-06-21 08:00 | 2023-08-28 16:00 |  |  | 48 | 0 | 48 | 198 |  |  | DESIGN | DESIGN
D4110 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | 2023-08-29 08:00 | 2023-09-19 16:00 |  |  | 15 | 0 | 15 | 198 |  |  | OWNER.Design Review | OWNER
D4120 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | 2023-09-20 08:00 | 2023-10-17 16:00 |  |  | 20 | 0 | 20 | 198 |  |  | DESIGN | DESIGN
D4130 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Review and Approve - Final MSE Wall RW 3-2 Br 3 | 2023-10-18 08:00 | 2023-11-07 16:00 |  |  | 15 | 0 | 15 | 198 |  |  | OWNER.Design Review | OWNER
D4140 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - Sign & Seal MSE Wall RW 3-2 Br 3 | 2023-11-08 08:00 | 2023-12-01 16:00 |  |  | 15 | 0 | 15 | 198 |  |  | DESIGN | DESIGN
D4150 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Issue - RFC MSE Wall RW 3-2 Br 3 | 2023-12-04 08:00 | 2023-12-08 16:00 |  |  | 5 | 0 | 5 | 198 |  |  | DESIGN | DESIGN
D4160 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | 2023-12-20 08:00 | 2024-02-28 16:00 |  |  | 48 | 0 | 48 | 100 | 71 |  | DESIGN | DESIGN
D4170 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Review and Approve - 90% MSE Wall RW 4-1 Br 4 | 2024-02-29 08:00 | 2024-03-20 16:00 |  |  | 15 | 0 | 15 | 101 | 71 |  | OWNER.Design Review | OWNER
D4180 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - Final MSE Wall RW 4-1 Br 4 | 2024-03-21 08:00 | 2024-04-17 16:00 |  |  | 20 | 0 | 20 | 101 | 71 |  | DESIGN | DESIGN
D4190 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Review and Approve - Final MSE Wall RW 4-1 Br 4 | 2024-04-18 08:00 | 2024-05-08 16:00 |  |  | 15 | 0 | 15 | 101 | 71 |  | OWNER.Design Review | OWNER
D4200 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - Sign & Seal MSE Wall RW 4-1 Br 4 | 2024-05-09 08:00 | 2024-05-30 16:00 |  |  | 15 | 0 | 15 | 101 | 71 |  | DESIGN | DESIGN
D4210 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Issue - RFC MSE Wall RW 4-1 Br 4 | 2024-05-31 08:00 | 2024-06-06 16:00 |  |  | 5 | 0 | 5 | 101 | 71 |  | DESIGN | DESIGN
D4220 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | 2023-12-20 08:00 | 2024-02-28 16:00 |  |  | 48 | 0 | 48 | 100 | 73 |  | DESIGN | DESIGN
D4230 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Review and Approve - 90% MSE Wall RW 4-2 Br 4 | 2024-02-29 08:00 | 2024-03-20 16:00 |  |  | 15 | 0 | 15 | 100 | 73 |  | OWNER.Design Review | OWNER
D4240 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - Final MSE Wall RW 4-2 Br 4 | 2024-03-21 08:00 | 2024-04-17 16:00 |  |  | 20 | 0 | 20 | 100 | 73 |  | DESIGN | DESIGN
D4250 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Review and Approve - Final MSE Wall RW 4-2 Br 4 | 2024-04-18 08:00 | 2024-05-08 16:00 |  |  | 15 | 0 | 15 | 100 | 73 |  | OWNER.Design Review | OWNER
D4260 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - Sign & Seal MSE Wall RW 4-2 Br 4 | 2024-05-09 08:00 | 2024-05-30 16:00 |  |  | 15 | 0 | 15 | 100 | 73 |  | DESIGN | DESIGN
D4270 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Issue - RFC MSE Wall RW 4-2 Br 4 | 2024-05-31 08:00 | 2024-06-06 16:00 |  |  | 5 | 0 | 5 | 100 | 73 |  | DESIGN | DESIGN
D4280 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 210 |  |  | DESIGN | DESIGN
D4290 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 210 |  |  | OWNER.Design Review | OWNER
D4300 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 210 |  |  | DESIGN | DESIGN
D4310 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 210 |  |  | OWNER.Design Review | OWNER
D4320 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 210 |  |  | DESIGN | DESIGN
D4330 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 210 |  |  | DESIGN | DESIGN
D4340 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 106 |  |  | DESIGN | DESIGN
D4350 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 106 |  |  | OWNER.Design Review | OWNER
D4360 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 106 |  |  | DESIGN | DESIGN
D4370 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 106 |  |  | OWNER.Design Review | OWNER
D4380 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 106 |  |  | DESIGN | DESIGN
D4390 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 106 |  |  | DESIGN | DESIGN
D4400 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 2023-07-20 08:00 | 2023-09-26 16:00 |  |  | 48 | 0 | 48 | 258 |  |  | DESIGN | DESIGN
D4410 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 2023-09-27 08:00 | 2023-10-17 16:00 |  |  | 15 | 0 | 15 | 478 |  |  | OWNER.Design Review | OWNER
D4420 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | 2023-10-18 08:00 | 2023-11-15 16:00 |  |  | 20 | 0 | 20 | 478 |  |  | DESIGN | DESIGN
D4430 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Review and Approve - Final MSE Wall RW 6-1 Ramp EN / Br 6 | 2023-11-16 08:00 | 2023-12-08 16:00 |  |  | 15 | 0 | 15 | 478 |  |  | OWNER.Design Review | OWNER
D4440 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - Sign & Seal MSE Wall RW 6-1 Ramp EN / Br 6 | 2023-12-11 08:00 | 2024-01-02 16:00 |  |  | 15 | 0 | 15 | 478 |  |  | DESIGN | DESIGN
D4450 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Issue - RFC MSE Wall RW 6-1 Ramp EN / Br 6 | 2024-01-03 08:00 | 2024-01-09 16:00 |  |  | 5 | 0 | 5 | 478 |  |  | DESIGN | DESIGN
D4460 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 2023-09-27 08:00 | 2023-12-06 16:00 |  |  | 48 | 0 | 48 | 258 |  |  | DESIGN | DESIGN
D4470 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 2023-12-07 08:00 | 2023-12-28 16:00 |  |  | 15 | 0 | 15 | 472 |  |  | OWNER.Design Review | OWNER
D4480 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - Final MSE Wall RW 7-1 Ramp EN / Br 7 | 2023-12-29 08:00 | 2024-01-29 16:00 |  |  | 20 | 0 | 20 | 472 |  |  | DESIGN | DESIGN
D4490 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Review and Approve - Final MSE Wall RW 7-1 Ramp EN / Br 7 | 2024-01-30 08:00 | 2024-02-19 16:00 |  |  | 15 | 0 | 15 | 472 |  |  | OWNER.Design Review | OWNER
D4500 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - Sign & Seal MSE Wall RW 7-1 Ramp EN / Br 7 | 2024-02-20 08:00 | 2024-03-11 16:00 |  |  | 15 | 0 | 15 | 472 |  |  | DESIGN | DESIGN
D4510 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Issue - RFC MSE Wall RW 7-1 Ramp EN / Br 7 | 2024-03-12 08:00 | 2024-03-18 16:00 |  |  | 5 | 0 | 5 | 472 |  |  | DESIGN | DESIGN
D4520 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 2023-09-27 08:00 | 2023-12-06 16:00 |  |  | 48 | 0 | 48 | 258 |  |  | DESIGN | DESIGN
D4530 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 2023-12-07 08:00 | 2023-12-28 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | OWNER.Design Review | OWNER
D4540 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - Final MSE Wall RW 7-2 Ramp EN / Br 7 | 2023-12-29 08:00 | 2024-01-29 16:00 |  |  | 20 | 0 | 20 | 258 |  |  | DESIGN | DESIGN
D4550 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Review and Approve - Final MSE Wall RW 7-2 Ramp EN / Br 7 | 2024-01-30 08:00 | 2024-02-19 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | OWNER.Design Review | OWNER
D4560 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - Sign & Seal MSE Wall RW 7-2 Ramp EN / Br 7 | 2024-02-20 08:00 | 2024-03-11 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | DESIGN | DESIGN
D4570 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Issue - RFC MSE Wall RW 7-2 Ramp EN / Br 7 | 2024-03-12 08:00 | 2024-03-18 16:00 |  |  | 5 | 0 | 5 | 258 |  |  | DESIGN | DESIGN
D4580 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 242 |  |  | DESIGN | DESIGN
D4590 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 242 |  |  | OWNER.Design Review | OWNER
D4600 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-1 Ramp B / Br 8 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 242 |  |  | DESIGN | DESIGN
D4610 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-1 Ramp B / Br 8 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 242 |  |  | OWNER.Design Review | OWNER
D4620 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-1 Ramp B / Br 8 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 242 |  |  | DESIGN | DESIGN
D4630 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 242 |  |  | DESIGN | DESIGN
D4640 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 262 |  |  | DESIGN | DESIGN
D4650 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 262 |  |  | OWNER.Design Review | OWNER
D4660 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-2 Ramp B / Br 8 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 262 |  |  | DESIGN | DESIGN
D4670 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-2 Ramp B / Br 8 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 262 |  |  | OWNER.Design Review | OWNER
D4680 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-2 Ramp B / Br 8 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 262 |  |  | DESIGN | DESIGN
D4690 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 262 |  |  | DESIGN | DESIGN
D4700 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 272 |  |  | DESIGN | DESIGN
D4710 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | OWNER.Design Review | OWNER
D4720 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Final MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 272 |  |  | DESIGN | DESIGN
D4730 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Review and Approve - Final MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | OWNER.Design Review | OWNER
D4740 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | DESIGN | DESIGN
D4750 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 272 |  |  | DESIGN | DESIGN
D4760 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 209 |  |  | DESIGN | DESIGN
D4770 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 209 |  |  | OWNER.Design Review | OWNER
D4780 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 209 |  |  | DESIGN | DESIGN
D4790 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Review and Approve - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 209 |  |  | OWNER.Design Review | OWNER
D4800 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 209 |  |  | DESIGN | DESIGN
D4810 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 209 |  |  | DESIGN | DESIGN
D4820 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 247 |  |  | DESIGN | DESIGN
D4830 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 247 |  |  | OWNER.Design Review | OWNER
D4840 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 247 |  |  | DESIGN | DESIGN
D4850 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Review and Approve - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 247 |  |  | OWNER.Design Review | OWNER
D4860 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 247 |  |  | DESIGN | DESIGN
D4870 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 247 |  |  | DESIGN | DESIGN
D4880 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 172 |  |  | DESIGN | DESIGN
D4890 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-04-11 08:00 | 2023-05-01 16:00 |  |  | 15 | 0 | 15 | 172 |  |  | OWNER.Design Review | OWNER
D4900 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-05-02 08:00 | 2023-05-30 16:00 |  |  | 20 | 0 | 20 | 172 |  |  | DESIGN | DESIGN
D4910 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 172 |  |  | OWNER.Design Review | OWNER
D4920 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Sign & Seal MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-06-21 08:00 | 2023-07-12 16:00 |  |  | 15 | 0 | 15 | 172 |  |  | DESIGN | DESIGN
D4930 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-07-13 08:00 | 2023-07-19 16:00 |  |  | 5 | 0 | 5 | 172 |  |  | DESIGN | DESIGN
D4940 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 2023-02-02 08:00 | 2023-04-10 16:00 |  |  | 48 | 0 | 48 | 580 |  |  | DESIGN | DESIGN
D4950 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 580 |  |  | OWNER.Design Review | OWNER
D4960 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Final MSE Wall RW 102 Ramp C | 2023-05-31 08:00 | 2023-06-27 16:00 |  |  | 20 | 0 | 20 | 580 |  |  | DESIGN | DESIGN
D4970 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - Final MSE Wall RW 102 Ramp C | 2023-06-28 08:00 | 2023-07-19 16:00 |  |  | 15 | 0 | 15 | 580 |  |  | OWNER.Design Review | OWNER
D4980 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Sign & Seal MSE Wall RW 102 Ramp C | 2023-07-20 08:00 | 2023-08-09 16:00 |  |  | 15 | 0 | 15 | 580 |  |  | DESIGN | DESIGN
D4990 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Issue - RFC MSE Wall RW 102 Ramp C | 2023-08-10 08:00 | 2023-08-16 16:00 |  |  | 5 | 0 | 5 | 580 |  |  | DESIGN | DESIGN
D5000 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | 2024-03-19 08:00 | 2024-05-23 16:00 |  |  | 48 | 0 | 48 | 258 |  |  | DESIGN | DESIGN
D5010 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Review and Approve - 90% MSE Wall RW 103 Ramp EN | 2024-05-24 08:00 | 2024-06-14 16:00 |  |  | 15 | 0 | 15 | 356 |  |  | OWNER.Design Review | OWNER
D5020 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - Final MSE Wall RW 103 Ramp EN | 2024-06-17 08:00 | 2024-07-15 16:00 |  |  | 20 | 0 | 20 | 356 |  |  | DESIGN | DESIGN
D5030 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Review and Approve - Final MSE Wall RW 103 Ramp EN | 2024-07-16 08:00 | 2024-08-05 16:00 |  |  | 15 | 0 | 15 | 356 |  |  | OWNER.Design Review | OWNER
D5040 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 103 Ramp EN | 2024-08-06 08:00 | 2024-08-26 16:00 |  |  | 15 | 0 | 15 | 356 |  |  | DESIGN | DESIGN
D5050 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Issue - RFC MSE Wall RW 103 Ramp EN | 2024-08-27 08:00 | 2024-09-03 16:00 |  |  | 5 | 0 | 5 | 356 |  |  | DESIGN | DESIGN
D5060 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | 2024-05-24 08:00 | 2024-08-01 16:00 |  |  | 48 | 0 | 48 | 258 |  |  | DESIGN | DESIGN
D5070 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Review and Approve - 90% MSE Wall RW 104 Ramp EN | 2024-08-02 08:00 | 2024-08-22 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | OWNER.Design Review | OWNER
D5080 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - Final MSE Wall RW 104 Ramp EN | 2024-08-23 08:00 | 2024-09-20 16:00 |  |  | 20 | 0 | 20 | 258 |  |  | DESIGN | DESIGN
D5090 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Review and Approve - Final MSE Wall RW 104 Ramp EN | 2024-09-23 08:00 | 2024-10-11 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | OWNER.Design Review | OWNER
D5100 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 104 Ramp EN | 2024-10-14 08:00 | 2024-11-01 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | DESIGN | DESIGN
D5110 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Issue - RFC MSE Wall RW 104 Ramp EN | 2024-11-04 08:00 | 2024-11-08 16:00 |  |  | 5 | 0 | 5 | 258 |  |  | DESIGN | DESIGN
SD1000 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 502 |  |  | OFFICE | OFFICE
SD1010 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 502 |  |  | DESIGN | DESIGN
SD1020 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 502 |  |  | OFFICE | OFFICE
SD1030 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 502 |  |  | DESIGN | DESIGN
SD1040 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 502 |  |  | OWNER.Shp Drwg Review | OWNER
SD1050 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 488 |  |  | OFFICE | OFFICE
SD1060 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 488 |  |  | DESIGN | DESIGN
SD1070 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 488 |  |  | OFFICE | OFFICE
SD1080 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 488 |  |  | DESIGN | DESIGN
SD1090 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 488 |  |  | OWNER.Shp Drwg Review | OWNER
SD1100 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Develop & Submit Shp Drwgs - RW 2-1 Br 2 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 317 |  |  | OFFICE | OFFICE
SD1110 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-1 Br 2 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 317 |  |  | DESIGN | DESIGN
SD1120 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Revise & Resubmit Shp Drwgs - RW 2-1 Br 2 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 317 |  |  | OFFICE | OFFICE
SD1130 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-1 Br 2 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 317 |  |  | DESIGN | DESIGN
SD1140 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-1 Br 2 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 317 |  |  | OWNER.Shp Drwg Review | OWNER
SD1150 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Develop & Submit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 597 |  |  | OFFICE | OFFICE
SD1160 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Designer Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 597 |  |  | DESIGN | DESIGN
SD1170 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Revise & Resubmit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 597 |  |  | OFFICE | OFFICE
SD1180 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Design 2nd Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 597 |  |  | DESIGN | DESIGN
SD1190 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | FDOT - Review & Comment Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 597 |  |  | OWNER.Shp Drwg Review | OWNER
SD1200 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Develop & Submit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 468 |  |  | OFFICE | OFFICE
SD1210 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Designer Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 468 |  |  | DESIGN | DESIGN
SD1220 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Revise & Resubmit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 468 |  |  | OFFICE | OFFICE
SD1230 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Design 2nd Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 468 |  |  | DESIGN | DESIGN
SD1240 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | FDOT - Review & Comment Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 468 |  |  | OWNER.Shp Drwg Review | OWNER
SD1250 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Develop & Submit Shp Drwgs - RW 2-4 Br 2 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 345 |  |  | OFFICE | OFFICE
SD1260 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-4 Br 2 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 345 |  |  | DESIGN | DESIGN
SD1270 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-4 Br 2 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 345 |  |  | OFFICE | OFFICE
SD1280 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-4 Br 2 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 345 |  |  | DESIGN | DESIGN
SD1290 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-4 Br 2 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 345 |  |  | OWNER.Shp Drwg Review | OWNER
SD1300 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 | R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Develop & Submit Shp Drwgs - RW 3-1 Br 3 | 2023-12-11 08:00 | 2023-12-22 16:00 |  |  | 10 | 0 | 10 | 220 |  |  | OFFICE | OFFICE
SD1310 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 | R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Designer Review & Comnt Shp Drwgs - RW 3-1 Br 3 | 2023-12-26 08:00 | 2024-01-17 16:00 |  |  | 15 | 0 | 15 | 220 |  |  | DESIGN | DESIGN
SD1320 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 | R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Revise & Resubmit Shp Drwgs - RW 3-1 Br 3 | 2024-01-18 08:00 | 2024-01-24 16:00 |  |  | 5 | 0 | 5 | 220 |  |  | OFFICE | OFFICE
SD1330 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 | R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Design 2nd Review & Comnt Shp Drwgs - RW 3-1 Br 3 | 2024-01-25 08:00 | 2024-01-31 16:00 |  |  | 5 | 0 | 5 | 220 |  |  | DESIGN | DESIGN
SD1340 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 | R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | FDOT - Review & Comment Shp Drwgs - RW 3-1 Br 3 | 2024-02-01 08:00 | 2024-02-21 16:00 |  |  | 15 | 0 | 15 | 220 |  |  | OWNER.Shp Drwg Review | OWNER
SD1350 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 | R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Develop & Submit Shp Drwgs - RW 3-2 Br 3 | 2023-12-11 08:00 | 2023-12-22 16:00 |  |  | 10 | 0 | 10 | 198 |  |  | OFFICE | OFFICE
SD1360 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 | R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Designer Review & Comnt Shp Drwgs - RW 3-2 Br 3 | 2023-12-26 08:00 | 2024-01-17 16:00 |  |  | 15 | 0 | 15 | 198 |  |  | DESIGN | DESIGN
SD1370 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 | R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Revise & Resubmit Shp Drwgs - RW 3-2 Br 3 | 2024-01-18 08:00 | 2024-01-24 16:00 |  |  | 5 | 0 | 5 | 198 |  |  | OFFICE | OFFICE
SD1380 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 | R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Design 2nd Review & Comnt Shp Drwgs - RW 3-2 Br 3 | 2024-01-25 08:00 | 2024-01-31 16:00 |  |  | 5 | 0 | 5 | 198 |  |  | DESIGN | DESIGN
SD1390 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 | R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | FDOT - Review & Comment Shp Drwgs - RW 3-2 Br 3 | 2024-02-01 08:00 | 2024-02-21 16:00 |  |  | 15 | 0 | 15 | 198 |  |  | OWNER.Shp Drwg Review | OWNER
SD1400 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 | R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Develop & Submit Shp Drwgs - RW 4-1 Br 4 | 2024-06-07 08:00 | 2024-06-20 16:00 |  |  | 10 | 0 | 10 | 101 | 71 |  | OFFICE | OFFICE
SD1410 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 | R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Designer Review & Comnt Shp Drwgs - RW 4-1 Br 4 | 2024-06-21 08:00 | 2024-07-12 16:00 |  |  | 15 | 0 | 15 | 101 | 71 |  | DESIGN | DESIGN
SD1420 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 | R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Revise & Resubmit Shp Drwgs - RW 4-1 Br 4 | 2024-07-15 08:00 | 2024-07-19 16:00 |  |  | 5 | 0 | 5 | 101 | 71 |  | OFFICE | OFFICE
SD1430 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 | R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Design 2nd Review & Comnt Shp Drwgs - RW 4-1 Br 4 | 2024-07-22 08:00 | 2024-07-26 16:00 |  |  | 5 | 0 | 5 | 101 | 71 |  | DESIGN | DESIGN
SD1440 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 | R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | FDOT - Review & Comment Shp Drwgs - RW 4-1 Br 4 | 2024-07-29 08:00 | 2024-08-16 16:00 |  |  | 15 | 0 | 15 | 101 | 71 |  | OWNER.Shp Drwg Review | OWNER
SD1450 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 | R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Develop & Submit Shp Drwgs - RW 4-2 Br 4 | 2024-06-07 08:00 | 2024-06-20 16:00 |  |  | 10 | 0 | 10 | 100 | 73 |  | OFFICE | OFFICE
SD1460 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 | R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Designer Review & Comnt Shp Drwgs - RW 4-2 Br 4 | 2024-06-21 08:00 | 2024-07-12 16:00 |  |  | 15 | 0 | 15 | 100 | 73 |  | DESIGN | DESIGN
SD1470 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 | R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Revise & Resubmit Shp Drwgs - RW 4-2 Br 4 | 2024-07-15 08:00 | 2024-07-19 16:00 |  |  | 5 | 0 | 5 | 100 | 73 |  | OFFICE | OFFICE
SD1480 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 | R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Design 2nd Review & Comnt Shp Drwgs - RW 4-2 Br 4 | 2024-07-22 08:00 | 2024-07-26 16:00 |  |  | 5 | 0 | 5 | 100 | 73 |  | DESIGN | DESIGN
SD1490 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 | R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | FDOT - Review & Comment Shp Drwgs - RW 4-2 Br 4 | 2024-07-29 08:00 | 2024-08-16 16:00 |  |  | 15 | 0 | 15 | 100 | 73 |  | OWNER.Shp Drwg Review | OWNER
SD1500 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 210 |  |  | OFFICE | OFFICE
SD1510 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 210 |  |  | DESIGN | DESIGN
SD1520 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 210 |  |  | OFFICE | OFFICE
SD1530 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 210 |  |  | DESIGN | DESIGN
SD1540 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 210 |  |  | OWNER.Shp Drwg Review | OWNER
SD1550 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 106 |  |  | OFFICE | OFFICE
SD1560 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 106 |  |  | DESIGN | DESIGN
SD1570 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 106 |  |  | OFFICE | OFFICE
SD1580 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 106 |  |  | DESIGN | DESIGN
SD1590 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 106 |  |  | OWNER.Shp Drwg Review | OWNER
PC1000 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.1 | R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 494 |  |  | PROCURE | PROCUREMENT
PC1010 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.2 | R1 Procurement - Retaining Wall RW 2-1 - Br 2 | Fab & Deliver - RW 2-1 - Br 2 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 322 |  |  | PROCURE | PROCUREMENT
PC1020 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.4 | R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 606 |  |  | PROCURE | PROCUREMENT
PC1030 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.5 | R1 Procurement - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Fab & Deliver - RW 2-3 - Ramp NE 125 to 130 RT | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 474 |  |  | PROCURE | PROCUREMENT
PC1040 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.7 | R1 Procurement - Retaining Wall RW 2-4 Br 2 | Fab & Deliver - RW 2-4 Br 2 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 351 |  |  | PROCURE | PROCUREMENT
PC1050 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.8 | R1 Procurement - Retaining Wall RW 3-1 Br 3 | Fab & Deliver - RW 3-1 Br 3 | 2024-02-22 08:00 | 2024-06-27 16:00 |  |  | 90 | 0 | 90 | 222 |  |  | PROCURE | PROCUREMENT
PC1060 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.9 | R1 Procurement - Retaining Wall RW 3-2 Br 3 | Fab & Deliver - RW 3-2 Br 3 | 2024-02-22 08:00 | 2024-06-27 16:00 |  |  | 90 | 0 | 90 | 200 |  |  | PROCURE | PROCUREMENT
PC1070 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.10 | R1 Procurement - Retaining Wall RW 4-1 Br 4 | Fab & Deliver - RW 4-1 Br 4 | 2024-08-19 08:00 | 2024-12-24 16:00 |  |  | 90 | 0 | 90 | 103 | 71 |  | PROCURE | PROCUREMENT
PC1080 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.11 | R1 Procurement - Retaining Wall RW 4-2 Br 4 | Fab & Deliver - RW 4-2 Br 4 | 2024-08-19 08:00 | 2024-12-24 16:00 |  |  | 90 | 0 | 90 | 102 | 73 |  | PROCURE | PROCUREMENT
PC1090 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.12 | R1 Procurement - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Fab & Deliver - RW 5-1 Ramp WE-B / Br 5 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 213 |  |  | PROCURE | PROCUREMENT
PC1100 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.13 | R1 Procurement - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Fab & Deliver - RW 5-2 Ramp WE-B / Br 5 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 109 |  |  | PROCURE | PROCUREMENT
PC1110 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.3 | R1 Procurement - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Fab & Deliver - RW 1-1 - Ramp NE / Br 1 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 508 |  |  | PROCURE | PROCUREMENT
SD1600 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 | R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Develop & Submit Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 2024-01-10 08:00 | 2024-01-24 16:00 |  |  | 10 | 0 | 10 | 478 |  |  | OFFICE | OFFICE
SD1610 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 | R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Designer Review & Comnt Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 2024-01-25 08:00 | 2024-02-14 16:00 |  |  | 15 | 0 | 15 | 478 |  |  | DESIGN | DESIGN
SD1620 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 | R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Revise & Resubmit Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 2024-02-15 08:00 | 2024-02-21 16:00 |  |  | 5 | 0 | 5 | 478 |  |  | OFFICE | OFFICE
SD1630 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 | R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Design 2nd Review & Comnt Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 2024-02-22 08:00 | 2024-02-28 16:00 |  |  | 5 | 0 | 5 | 478 |  |  | DESIGN | DESIGN
SD1640 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 | R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | FDOT - Review & Comment Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 2024-02-29 08:00 | 2024-03-20 16:00 |  |  | 15 | 0 | 15 | 478 |  |  | OWNER.Shp Drwg Review | OWNER
SD1650 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 | R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Develop & Submit Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 2024-03-19 08:00 | 2024-04-01 16:00 |  |  | 10 | 0 | 10 | 472 |  |  | OFFICE | OFFICE
SD1660 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 | R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Designer Review & Comnt Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 2024-04-02 08:00 | 2024-04-22 16:00 |  |  | 15 | 0 | 15 | 472 |  |  | DESIGN | DESIGN
SD1670 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 | R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Revise & Resubmit Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 2024-04-23 08:00 | 2024-04-29 16:00 |  |  | 5 | 0 | 5 | 472 |  |  | OFFICE | OFFICE
SD1680 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 | R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Design 2nd Review & Comnt Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 2024-04-30 08:00 | 2024-05-06 16:00 |  |  | 5 | 0 | 5 | 472 |  |  | DESIGN | DESIGN
SD1690 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 | R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | FDOT - Review & Comment Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 2024-05-07 08:00 | 2024-05-28 16:00 |  |  | 15 | 0 | 15 | 472 |  |  | OWNER.Shp Drwg Review | OWNER
SD1700 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 | R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Develop & Submit Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 2024-03-19 08:00 | 2024-04-01 16:00 |  |  | 10 | 0 | 10 | 410 |  |  | OFFICE | OFFICE
SD1710 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 | R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Designer Review & Comnt Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 2024-04-02 08:00 | 2024-04-22 16:00 |  |  | 15 | 0 | 15 | 410 |  |  | DESIGN | DESIGN
SD1720 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 | R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Revise & Resubmit Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 2024-04-23 08:00 | 2024-04-29 16:00 |  |  | 5 | 0 | 5 | 410 |  |  | OFFICE | OFFICE
SD1730 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 | R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Design 2nd Review & Comnt Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 2024-04-30 08:00 | 2024-05-06 16:00 |  |  | 5 | 0 | 5 | 410 |  |  | DESIGN | DESIGN
SD1740 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 | R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | FDOT - Review & Comment Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 2024-05-07 08:00 | 2024-05-28 16:00 |  |  | 15 | 0 | 15 | 410 |  |  | OWNER.Shp Drwg Review | OWNER
SD1750 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 242 |  |  | OFFICE | OFFICE
SD1760 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 242 |  |  | DESIGN | DESIGN
SD1770 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 242 |  |  | OFFICE | OFFICE
SD1780 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 242 |  |  | DESIGN | DESIGN
SD1790 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 242 |  |  | OWNER.Shp Drwg Review | OWNER
SD1800 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 262 |  |  | OFFICE | OFFICE
SD1810 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 262 |  |  | DESIGN | DESIGN
SD1820 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 262 |  |  | OFFICE | OFFICE
SD1830 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 262 |  |  | DESIGN | DESIGN
SD1840 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 262 |  |  | OWNER.Shp Drwg Review | OWNER
SD1850 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Develop & Submit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 272 |  |  | OFFICE | OFFICE
SD1860 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Designer Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | DESIGN | DESIGN
SD1870 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Revise & Resubmit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 272 |  |  | OFFICE | OFFICE
SD1880 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 272 |  |  | DESIGN | DESIGN
SD1890 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 272 |  |  | OWNER.Shp Drwg Review | OWNER
SD1900 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 209 |  |  | OFFICE | OFFICE
SD1910 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 209 |  |  | DESIGN | DESIGN
SD1920 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 209 |  |  | OFFICE | OFFICE
SD1930 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 209 |  |  | DESIGN | DESIGN
SD1940 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 209 |  |  | OWNER.Shp Drwg Review | OWNER
SD1950 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 247 |  |  | OFFICE | OFFICE
SD1960 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 247 |  |  | DESIGN | DESIGN
SD1970 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 247 |  |  | OFFICE | OFFICE
SD1980 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 247 |  |  | DESIGN | DESIGN
SD1990 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 247 |  |  | OWNER.Shp Drwg Review | OWNER
SD2000 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Develop & Submit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 172 |  |  | OFFICE | OFFICE
SD2010 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Designer Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 2023-08-03 08:00 | 2023-08-23 16:00 |  |  | 15 | 0 | 15 | 172 |  |  | DESIGN | DESIGN
SD2020 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Revise & Resubmit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 2023-08-24 08:00 | 2023-08-30 16:00 |  |  | 5 | 0 | 5 | 172 |  |  | OFFICE | OFFICE
SD2030 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Design 2nd Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 2023-08-31 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 172 |  |  | DESIGN | DESIGN
SD2040 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | FDOT - Review & Comment Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 2023-09-08 08:00 | 2023-09-28 16:00 |  |  | 15 | 0 | 15 | 172 |  |  | OWNER.Shp Drwg Review | OWNER
SD2200 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 | R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Develop & Submit Shp Drwgs - RW 103 Ramp EN | 2024-09-04 08:00 | 2024-09-17 16:00 |  |  | 10 | 0 | 10 | 356 |  |  | OFFICE | OFFICE
SD2210 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 | R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Designer Review & Comnt Shp Drwgs - RW 103 Ramp EN | 2024-09-18 08:00 | 2024-10-08 16:00 |  |  | 15 | 0 | 15 | 356 |  |  | DESIGN | DESIGN
SD2220 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 | R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Revise & Resubmit Shp Drwgs - RW 103 Ramp EN | 2024-10-09 08:00 | 2024-10-15 16:00 |  |  | 5 | 0 | 5 | 356 |  |  | OFFICE | OFFICE
SD2230 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 | R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Design 2nd Review & Comnt Shp Drwgs - RW 103 Ramp EN | 2024-10-16 08:00 | 2024-10-22 16:00 |  |  | 5 | 0 | 5 | 356 |  |  | DESIGN | DESIGN
SD2240 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 | R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | FDOT - Review & Comment Shp Drwgs - RW 103 Ramp EN | 2024-10-23 08:00 | 2024-11-13 16:00 |  |  | 15 | 0 | 15 | 356 |  |  | OWNER.Shp Drwg Review | OWNER
SD2250 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 | R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Develop & Submit Shp Drwgs - RW 104 Ramp EN | 2024-11-12 08:00 | 2024-11-25 16:00 |  |  | 10 | 0 | 10 | 258 |  |  | OFFICE | OFFICE
SD2260 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 | R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Designer Review & Comnt Shp Drwgs - RW 104 Ramp EN | 2024-11-26 08:00 | 2024-12-18 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | DESIGN | DESIGN
SD2270 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 | R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Revise & Resubmit Shp Drwgs - RW 104 Ramp EN | 2024-12-19 08:00 | 2024-12-26 16:00 |  |  | 5 | 0 | 5 | 258 |  |  | OFFICE | OFFICE
SD2280 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 | R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Design 2nd Review & Comnt Shp Drwgs - RW 104 Ramp EN | 2024-12-27 08:00 | 2025-01-03 16:00 |  |  | 5 | 0 | 5 | 258 |  |  | DESIGN | DESIGN
SD2290 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 | R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | FDOT - Review & Comment Shp Drwgs - RW 104 Ramp EN | 2025-01-06 08:00 | 2025-01-27 16:00 |  |  | 15 | 0 | 15 | 258 |  |  | OWNER.Shp Drwg Review | OWNER
SD2300 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Develop & Submit Shp Drwgs - RW 102 Ramp C | 2023-08-17 08:00 | 2023-08-30 16:00 |  |  | 10 | 0 | 10 | 580 |  |  | OFFICE | OFFICE
SD2310 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Designer Review & Comnt Shp Drwgs - RW 102 Ramp C | 2023-08-31 08:00 | 2023-09-21 16:00 |  |  | 15 | 0 | 15 | 580 |  |  | DESIGN | DESIGN
SD2320 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Revise & Resubmit Shp Drwgs - RW 102 Ramp C | 2023-09-22 08:00 | 2023-09-28 16:00 |  |  | 5 | 0 | 5 | 580 |  |  | OFFICE | OFFICE
SD2330 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Design 2nd Review & Comnt Shp Drwgs - RW 102 Ramp C | 2023-09-29 08:00 | 2023-10-05 16:00 |  |  | 5 | 0 | 5 | 580 |  |  | DESIGN | DESIGN
SD2340 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | FDOT - Review & Comment Shp Drwgs - RW 102 Ramp C | 2023-10-06 08:00 | 2023-10-26 16:00 |  |  | 15 | 0 | 15 | 580 |  |  | OWNER.Shp Drwg Review | OWNER
PC1120 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.2.1 | R2 Procurement - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Fab & Deliver - RW 7-1 Ramp EN / Br 7 | 2024-05-29 08:00 | 2024-10-03 16:00 |  |  | 90 | 0 | 90 | 478 |  |  | PROCURE | PROCUREMENT
PC1130 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.2.2 | R2 Procurement - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Fab & Deliver - RW 7-2 Ramp EN / Br 7 | 2024-05-29 08:00 | 2024-10-03 16:00 |  |  | 90 | 0 | 90 | 415 |  |  | PROCURE | PROCUREMENT
PC1140 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.2.3 | R2 Procurement - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Fab & Deliver - RW 6-1 Ramp EN / Br 6 | 2024-03-21 08:00 | 2024-07-26 16:00 |  |  | 90 | 0 | 90 | 484 |  |  | PROCURE | PROCUREMENT
PC1150 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.3.4 | R3 Procurement - Retaining Wall RW 8-1 - Ramp B / Br 8 | Fab & Deliver - RW 8-1 - Ramp B / Br 8 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 245 |  |  | PROCURE | PROCUREMENT
PC1160 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.3.1 | R3 Procurement - Retaining Wall RW 8-2 - Ramp B / Br 8 | Fab & Deliver - RW 8-2 - Ramp B / Br 8 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 265 |  |  | PROCURE | PROCUREMENT
PC1170 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.3.2 | R3 Procurement - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Fab & Deliver - RW 9-1 - Ramp B/F / Br 8 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 275 |  |  | PROCURE | PROCUREMENT
PC1180 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.3.3 | R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 212 |  |  | PROCURE | PROCUREMENT
PC1190 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.3.5 | R3 Procurement - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-3 - Ramp B/F / Br 9 | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 250 |  |  | PROCURE | PROCUREMENT
PC1200 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.1.6 | R1 Procurement - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Fab & Deliver - RW 100 I-4 EB (Br 3 & Br 4) | 2023-09-29 08:00 | 2024-02-06 16:00 |  |  | 90 | 0 | 90 | 175 |  |  | PROCURE | PROCUREMENT
PC1210 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.3.7 | R3 Procurement - Retaining Wall RW 102 Ramp C | Fab & Deliver - RW 102 Ramp C | 2023-10-27 08:00 | 2024-03-05 16:00 |  |  | 90 | 0 | 90 | 589 |  |  | PROCURE | PROCUREMENT
PC1220 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.2.8 | R2 Procurement - Retaining Wall RW 103 Ramp EN | Fab & Deliver - RW 103 Ramp EN | 2024-11-14 08:00 | 2025-03-24 16:00 |  |  | 90 | 0 | 90 | 361 |  |  | PROCURE | PROCUREMENT
PC1230 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.2.9 | R2 Procurement - Retaining Wall RW 104 Ramp EN | Fab & Deliver - RW 104 Ramp EN | 2025-01-28 08:00 | 2025-06-03 16:00 |  |  | 90 | 0 | 90 | 261 |  |  | PROCURE | PROCUREMENT
D1500 | In Progress | I-275 - I-4 - IBL(all) - B1.3.2 | Right of Way | Owner Right of Way Acquisition | 2022-07-27 08:00 | 2024-07-23 16:00 | 2022-07-27 08:00 |  | 710 | 127 | 601 | 617 |  |  | ROW | OWNER
A36290 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | FRP Footing - Brg 100139 - Pier 1 - R3 - P2.S2 | 2025-07-11 08:00 | 2025-07-15 16:00 |  |  | 3 | 0 | 3 | 53 | 14 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36300 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 | R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | FRP Footing - Brg 100139 - Pier 3 - R3 - P2.S2 | 2025-07-25 08:00 | 2025-07-29 16:00 |  |  | 3 | 0 | 3 | 46 | 12 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36310 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 | R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | FRP Footing - Brg 100141 - Pier 1 - R3 - P2.S2 | 2025-06-23 08:00 | 2025-07-11 16:00 |  |  | 12 | 0 | 12 | 56 | 23 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36320 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.18 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Drive Pile - Brg 100143 - End Bent 1 - R3 - P3 | 2025-10-23 08:00 | 2025-10-27 16:00 |  |  | 3 | 0 | 3 | 146 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A36330 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.19 | R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Drive Pile - Brg 100143 - End Bent 2 - R3 - P3 | 2025-10-24 08:00 | 2025-10-28 16:00 |  |  | 3 | 0 | 3 | 145 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A36340 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | Drive Pile - Brg 100143 - Pier 1 - R3 - P3 | 2025-10-22 08:00 | 2025-10-24 16:00 |  |  | 3 | 0 | 3 | 126 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A36350 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 | R3 - Ph3 - Bridge 100143 - Pier 1 | FRP Footing - Brg 100143 - Pier 1 - R3 - P3 | 2025-10-27 08:00 | 2025-11-13 16:00 |  |  | 12 | 0 | 12 | 126 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36360 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | Drive Pile - Brg 100143 - Pier 2 - R3 - P3 | 2025-10-22 08:00 | 2025-10-24 16:00 |  |  | 3 | 0 | 3 | 126 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A36370 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 | R3 - Ph3 - Bridge 100143 - Pier 2 | FRP Footing - Brg 100143 - Pier 2 - R3 - P3 | 2025-10-27 08:00 | 2025-11-13 16:00 |  |  | 12 | 0 | 12 | 126 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36380 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 | R3 - Ph3 - Bridge 100139 - Pier 1 | FRP Footing - Brg 100139 - Pier 1 - R3 - P3 | 2025-12-18 08:00 | 2026-01-15 16:00 |  |  | 12 | 0 | 12 | 86 | 62 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36390 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 | R3 - Ph3 - Bridge 100139 - Pier 2 | FRP Footing - Brg 100139 - Pier 2 - R3 - P3 | 2025-12-18 08:00 | 2026-01-15 16:00 |  |  | 12 | 0 | 12 | 64 | 37 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36400 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 | R3 - Ph3 - Bridge 100139 - Pier 3 | FRP Footing - Brg 100139 - Pier 3 - R3 - P3 | 2025-12-18 08:00 | 2026-01-15 16:00 |  |  | 12 | 0 | 12 | 63 | 36 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36410 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | FRP Footing - Brg 100139 - Pier 4 - R3 - P3 | 2025-12-18 08:00 | 2026-01-15 16:00 |  |  | 12 | 0 | 12 | 81 | 58 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A36420 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 | R3 - Ph3 - Bridge 100139 - Pier 4 | Cure/Strip Footing - Brg 100139 - Pier 4 - R3 - P3 | 2026-01-16 08:00 | 2026-01-22 16:00 |  |  | 7 | 0 | 7 | 133 | 58 |  | CURE | CURE
A36430 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 | R3 - Ph3 - Bridge 100139 - Pier 5 | FRP Footing - Brg 100139 - Pier 5 - R3 - P3 | 2025-12-18 08:00 | 2026-01-15 16:00 |  |  | 12 | 0 | 12 | 86 | 61 | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
P1440 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6 | R3 Procurement | Procure 60" Drainage Structures | 2023-07-17 08:00 | 2023-11-20 16:00 |  |  | 90 | 0 | 90 | 79 | 22 |  | PROCURE | PROCUREMENT
SD2350 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Develop & Submit Shp Drwgs - 60" Drainage Str | 2023-05-04 08:00 | 2023-05-17 16:00 |  |  | 10 | 0 | 10 | 79 | 22 |  | OFFICE | OFFICE
SD2360 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Designer Review & Comnt Shp Drwgs - 60" Drainage Str | 2023-05-18 08:00 | 2023-06-08 16:00 |  |  | 15 | 0 | 15 | 79 | 22 |  | DESIGN | DESIGN
SD2370 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Revise & Resubmit Shp Drwgs - 60" Drainage Str | 2023-06-09 08:00 | 2023-06-15 16:00 |  |  | 5 | 0 | 5 | 79 | 22 |  | OFFICE | OFFICE
SD2380 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Design 2nd Review & Comnt Shp Drwgs - 60" Drainage Str | 2023-06-16 08:00 | 2023-06-22 16:00 |  |  | 5 | 0 | 5 | 79 | 22 |  | DESIGN | DESIGN
SD2390 | Not Started | I-275 - I-4 - IBL(all) - B1.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | FDOT - Review & Comment Shp Drwgs - 60" Drainage Str | 2023-06-23 08:00 | 2023-07-14 16:00 |  |  | 15 | 0 | 15 | 79 | 22 |  | OWNER.Shp Drwg Review | OWNER
A36530 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-2 to OUT-1 - R3 | 2024-03-05 08:00 | 2024-04-02 16:00 |  |  | 18 | 0 | 18 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36510 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-3 to OUT-2 - R3 | 2024-02-01 08:00 | 2024-03-04 16:00 |  |  | 20 | 0 | 20 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36480 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | 2023-10-17 08:00 | 2023-11-29 16:00 |  |  | 25 | 0 | 25 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36450 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | 2023-09-18 08:00 | 2023-10-16 16:00 |  |  | 18 | 0 | 18 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36440 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | 2023-05-26 08:00 | 2023-06-12 16:00 |  |  | 10 | 0 | 10 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36500 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-4 to OUT-3 - R3 | 2023-11-30 08:00 | 2024-01-30 16:00 |  |  | 32 | 0 | 32 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36540 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | 2023-07-27 08:00 | 2023-09-15 16:00 |  |  | 31 | 0 | 31 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36550 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | 2023-06-13 08:00 | 2023-07-25 16:00 |  |  | 25 | 0 | 25 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36560 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-8 - R3 | 2023-05-26 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 102 | 35 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36570 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-7 - R3 | 2023-06-22 08:00 | 2023-07-17 16:00 |  |  | 15 | 0 | 15 | 102 | 35 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36580 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-9 - R3 | 2023-11-21 08:00 | 2023-12-05 16:00 |  |  | 8 | 0 | 8 | 61 | 22 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36590 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-6 - R3 | 2024-01-10 08:00 | 2024-01-23 16:00 |  |  | 8 | 0 | 8 | 61 | 22 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36600 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-5 - R3 | 2024-01-25 08:00 | 2024-02-06 16:00 |  |  | 8 | 0 | 8 | 61 | 22 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36610 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-4 - R3 | 2024-02-08 08:00 | 2024-02-20 16:00 |  |  | 8 | 0 | 8 | 61 | 22 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36620 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-3 - R3 | 2024-03-05 08:00 | 2024-03-18 16:00 |  |  | 8 | 0 | 8 | 53 | 21 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36630 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-2 - R3 | 2024-04-03 08:00 | 2024-04-12 16:00 |  |  | 8 | 0 | 8 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36640 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-1 - R3 | 2024-04-15 08:00 | 2024-04-26 16:00 |  |  | 8 | 0 | 8 | 43 | 1 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36650 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-8 - R3 | 2023-12-07 08:00 | 2023-12-19 16:00 |  |  | 8 | 0 | 8 | 61 | 22 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36660 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.3 | R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-7 - R3 | 2023-12-21 08:00 | 2024-01-09 16:00 |  |  | 8 | 0 | 8 | 61 | 22 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36670 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.8.4 | R3 - Ph0 - 60" Drainage - Abandonment | Flow Fill existing 60" Drainage System | 2024-04-29 08:00 | 2024-05-29 16:00 |  |  | 20 | 0 | 20 | 43 | 1 | Drainage Crew - Combo | LANE.DRAIN.Pipe | DRAINAGE.Storm Drain
P1450 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Bridge 5 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 317 |  |  | PROCURE | PROCUREMENT
P1460 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Bridge 4 | 2024-06-18 08:00 | 2024-09-11 16:00 |  |  | 60 | 0 | 60 | 180 |  |  | PROCURE | PROCUREMENT
P1470 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Bridge 3 | 2023-12-20 08:00 | 2024-03-14 16:00 |  |  | 60 | 0 | 60 | 303 |  |  | PROCURE | PROCUREMENT
P1480 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Bridge 1 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 617 |  |  | PROCURE | PROCUREMENT
P1490 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.1 | R2 Procurement - Bridge Girders | Procure Girders - Bridge 6 | 2024-12-17 08:00 | 2025-03-12 16:00 |  |  | 60 | 0 | 60 | 299 |  |  | PROCURE | PROCUREMENT
P1500 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.1 | R2 Procurement - Bridge Girders | Procure Girders - Bridge 7 | 2024-12-17 08:00 | 2025-03-12 16:00 |  |  | 60 | 0 | 60 | 375 |  |  | PROCURE | PROCUREMENT
P1510 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 8 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 386 |  |  | PROCURE | PROCUREMENT
P1520 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 9 | 2023-06-21 08:00 | 2023-09-14 16:00 |  |  | 60 | 0 | 60 | 395 |  |  | PROCURE | PROCUREMENT
P1530 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 10 | 2024-06-18 08:00 | 2024-09-11 16:00 |  |  | 60 | 0 | 60 | 299 |  |  | PROCURE | PROCUREMENT
P1540 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 11 | 2023-12-20 08:00 | 2024-03-14 16:00 |  |  | 60 | 0 | 60 | 430 |  |  | PROCURE | PROCUREMENT
P1550 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 12 | 2024-06-18 08:00 | 2024-09-11 16:00 |  |  | 60 | 0 | 60 | 468 |  |  | PROCURE | PROCUREMENT
P1560 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 2 - R1 | 2023-10-02 08:00 | 2023-10-13 16:00 |  |  | 10 | 0 | 10 | 356 |  |  | PROCURE | PROCUREMENT
P1570 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 3 - R1 | 2023-12-20 08:00 | 2024-01-04 16:00 |  |  | 10 | 0 | 10 | 323 |  |  | PROCURE | PROCUREMENT
P1580 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 4 - R1 | 2024-06-18 08:00 | 2024-07-01 16:00 |  |  | 10 | 0 | 10 | 218 |  |  | PROCURE | PROCUREMENT
P1590 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 5 - R1 | 2023-06-21 08:00 | 2023-07-05 16:00 |  |  | 10 | 0 | 10 | 250 |  |  | PROCURE | PROCUREMENT
P1600 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.5.3 | R2 Procurement - Bridge Pile | Procure Pile - Bridge 7 - R2 | 2024-12-17 08:00 | 2024-12-31 16:00 |  |  | 10 | 0 | 10 | 352 |  |  | PROCURE | PROCUREMENT
A1070 | Not Started | I-275 - I-4 - IBL(all) - B1.2.1 | Mobilization | Install Advanced Warning signs | 2023-06-22 08:00 | 2023-06-29 16:00 |  |  | 5 | 0 | 5 | 211 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
D5120 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.2 | R1 Early Package Design | Develop and Submit - 90% Early Pkg Eros - R1 | 2022-12-01 08:00 | 2023-02-06 16:00 |  |  | 45 | 0 | 45 | 286 |  |  | DESIGN | DESIGN
D5130 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.2 | R1 Early Package Design | Review and Approve - 90% Early Pkg Eros - R1 | 2023-02-07 08:00 | 2023-02-27 16:00 |  |  | 15 | 0 | 15 | 286 |  |  | OWNER.Design Review | OWNER
D5140 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.2 | R1 Early Package Design | Develop and Submit - Final Early Pkg Eros - R1 | 2023-02-28 08:00 | 2023-03-27 16:00 |  |  | 20 | 0 | 20 | 286 |  |  | DESIGN | DESIGN
D5150 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.2 | R1 Early Package Design | Review and Approve - Final Early Pkg Eros - R1 | 2023-03-28 08:00 | 2023-04-17 16:00 |  |  | 15 | 0 | 15 | 286 |  |  | OWNER.Design Review | OWNER
D5160 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.2 | R1 Early Package Design | Develop and Submit - Sign & Seal Early Pkg Eros - R1 | 2023-04-18 08:00 | 2023-05-08 16:00 |  |  | 15 | 0 | 15 | 286 |  |  | DESIGN | DESIGN
D5170 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.2 | R1 Early Package Design | Issue - RFC Early Pkg Eros - R1 | 2023-05-09 08:00 | 2023-05-15 16:00 |  |  | 5 | 0 | 5 | 286 |  |  | DESIGN | DESIGN
P1610 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 09 | 2023-06-21 08:00 | 2023-07-05 16:00 |  |  | 10 | 0 | 10 | 354 |  |  | PROCURE | PROCUREMENT
P1620 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 10 | 2024-06-18 08:00 | 2024-07-01 16:00 |  |  | 10 | 0 | 10 | 318 |  |  | PROCURE | PROCUREMENT
P1630 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 11 | 2023-12-20 08:00 | 2024-01-04 16:00 |  |  | 10 | 0 | 10 | 431 |  |  | PROCURE | PROCUREMENT
P1640 | Not Started | I-275 - I-4 - IBL(all) - B1.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 12 | 2024-06-18 08:00 | 2024-07-01 16:00 |  |  | 10 | 0 | 10 | 488 |  |  | PROCURE | PROCUREMENT
U1000 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1010 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1020 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1030 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1040 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1050 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1060 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1070 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1080 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | 2023-04-25 08:00 | 2023-04-28 16:00 |  |  | 3 | 0 | 3 | 249 |  |  | UTILITIES | UTILITY
U1090 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1100 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1110 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1120 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | 2023-04-25 08:00 | 2023-04-28 16:00 |  |  | 3 | 0 | 3 | 249 |  |  | UTILITIES | UTILITY
U1130 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1140 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.2 | Frontier Florida LLC During Construction | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1150 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1160 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 3" WI GM (E 7th Ave) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1170 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 6" PE GM (SMF 3A) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1180 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | 2023-04-25 08:00 | 2023-05-09 16:00 |  |  | 10 | 0 | 10 | 242 |  |  | UTILITIES | UTILITY
U1190 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 2" BS GM (E Oak Ave) - TPG | 2023-04-25 08:00 | 2023-04-28 16:00 |  |  | 3 | 0 | 3 | 249 |  |  | UTILITIES | UTILITY
U1200 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | 2023-04-25 08:00 | 2023-04-28 16:00 |  |  | 3 | 0 | 3 | 249 |  |  | UTILITIES | UTILITY
U1210 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 8" PE GM (E Columbus Dr) - TPG | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1220 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1230 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | 2023-04-25 08:00 | 2023-05-02 16:00 |  |  | 5 | 0 | 5 | 247 |  |  | UTILITIES | UTILITY
U1240 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1250 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 6" CS GM (Ramp NE) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1260 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.3.2 | Uniti Fiber/Southern Light - During Construction | Adj HH to grade 24x36x36- (256+20, 105' RT) - Uniti | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 713 |  |  | UTILITIES | UTILITY
U1270 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1280 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1290 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1300 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1310 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1320 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1330 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1340 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | 2023-05-25 08:00 | 2023-05-25 16:00 |  |  | 1 | 0 | 1 | 231 |  |  | UTILITIES | UTILITY
U1350 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1360 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | 2023-05-25 08:00 | 2023-05-25 16:00 |  |  | 1 | 0 | 1 | 231 |  |  | UTILITIES | UTILITY
U1370 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1380 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | 2023-05-25 08:00 | 2023-05-25 16:00 |  |  | 1 | 0 | 1 | 231 |  |  | UTILITIES | UTILITY
U1390 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1400 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | 2023-05-25 08:00 | 2023-05-25 16:00 |  |  | 1 | 0 | 1 | 231 |  |  | UTILITIES | UTILITY
U1410 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | 2023-05-25 08:00 | 2023-05-25 16:00 |  |  | 1 | 0 | 1 | 231 |  |  | UTILITIES | UTILITY
U1420 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | 2023-04-25 08:00 | 2023-04-28 16:00 |  |  | 3 | 0 | 3 | 248 |  |  | UTILITIES | UTILITY
U1430 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | 2023-05-01 08:00 | 2023-05-01 16:00 |  |  | 1 | 0 | 1 | 248 |  |  | UTILITIES | UTILITY
U1440 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 317+70, 73 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1450 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 91+25, 40 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1460 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 92+45, 50 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1470 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 93+35, 50 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1480 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 93+80, 60 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1490 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 94+40, 60 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1500 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 95+15, 60 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1510 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 95+95, 60 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1520 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 96+40, 65 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1530 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.2 | City of Tampa Water Dept - During Construction | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | 2023-05-25 08:00 | 2023-06-09 16:00 |  |  | 10 | 0 | 10 | 222 |  |  | UTILITIES | UTILITY
U1540 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.2 | City of Tampa Water Dept - During Construction | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | 2023-05-25 08:00 | 2023-06-09 16:00 |  |  | 10 | 0 | 10 | 222 |  |  | UTILITIES | UTILITY
U1550 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1802+90, 10 R - TECO | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1560 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1803+90, 10 R - TECO | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1570 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1805+30, 25 R - TECO | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1580 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1806+15, 10 R - TECO | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1590 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1806+90, 20 R - TECO | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1600 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | 2023-04-25 08:00 | 2023-04-28 16:00 |  |  | 3 | 0 | 3 | 249 |  |  | UTILITIES | UTILITY
U1610 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1620 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 1802+90, 10 L - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1630 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 1805+55, 130 R - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1640 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 1806+90, 85 R - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1650 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1660 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1670 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | 2023-05-25 08:00 | 2023-06-19 16:00 |  |  | 15 | 0 | 15 | 217 |  |  | UTILITIES | UTILITY
U1680 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | 2023-05-25 08:00 | 2023-06-02 16:00 |  |  | 5 | 0 | 5 | 227 |  |  | UTILITIES | UTILITY
U1690 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | 2023-05-25 08:00 | 2023-06-09 16:00 |  |  | 10 | 0 | 10 | 222 |  |  | UTILITIES | UTILITY
U1700 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | 2023-05-25 08:00 | 2023-06-06 16:00 |  |  | 7 | 0 | 7 | 225 |  |  | UTILITIES | UTILITY
U1710 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | 2023-05-25 08:00 | 2023-06-09 16:00 |  |  | 10 | 0 | 10 | 222 |  |  | UTILITIES | UTILITY
U1720 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install Fiber Distrib HUB - 207+04, 100 L - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1730 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install Fiber XBOX - 207+04, 110 L - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1740 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | 2023-04-25 08:00 | 2023-05-02 16:00 |  |  | 5 | 0 | 5 | 247 |  |  | UTILITIES | UTILITY
U1750 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1760 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1770 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Fiber XBOX - 207+00, 5 L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1780 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1790 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | 2023-04-25 08:00 | 2023-04-25 16:00 |  |  | 1 | 0 | 1 | 251 |  |  | UTILITIES | UTILITY
U1800 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1810 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1820 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install all Copper/Fiber Cables within project limits - FTR | 2023-04-25 08:00 | 2023-05-09 16:00 |  |  | 10 | 0 | 10 | 242 |  |  | UTILITIES | UTILITY
U1830 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.1.1 | Frontier Florida LLC Prior to Construction | Splice/Cutover new facilities within project limits - FTR | 2023-04-25 08:00 | 2023-05-25 16:00 |  |  | 21 | 0 | 21 | 231 |  |  | UTILITIES | UTILITY
U1840 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.1 | TECO Peoples Gas - Prior to Construction | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | 2023-04-25 08:00 | 2023-04-27 16:00 |  |  | 2 | 0 | 2 | 250 |  |  | UTILITIES | UTILITY
U1850 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.1 | TECO Peoples Gas - Prior to Construction | Install 6" PE GM (E Columbus Dr) - TPG | 2023-04-25 08:00 | 2023-05-01 16:00 |  |  | 4 | 0 | 4 | 248 |  |  | UTILITIES | UTILITY
U1860 | Not Started | I-275 - I-4 - IBL(all) - B1.4.2.2.1 | TECO Peoples Gas - Prior to Construction | Install 6" PE GM (N Mitchell Ave) - TPG | 2023-04-25 08:00 | 2023-05-01 16:00 |  |  | 4 | 0 | 4 | 248 |  |  | UTILITIES | UTILITY
A36680 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Cure and Test Drilled shaft - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-06-25 08:00 | 2024-07-02 16:00 |  |  | 5 | 0 | 5 | 107 |  | Sub - Drilled Shaft Crew | CURE | CURE
A36690 | Not Started | I-275 - I-4 - IBL(all) - B1.2.5.2.14 | R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Pour Drilled Shaft Extensions - Brg 100868 - End Bent 1 - R3 - P1.S2 | 2024-07-03 08:00 | 2024-07-10 16:00 |  |  | 5 | 0 | 5 | 107 |  | Sub - Drilled Shaft Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
D5180 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.6 | Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 3 | 2022-12-30 08:00 | 2023-02-27 16:00 |  |  | 40 | 0 | 40 | 838 |  |  | DESIGN | DESIGN
D5190 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.6 | Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Review and Approve - 90% TTCP Plans - R1 Phase 3 | 2023-02-28 08:00 | 2023-03-20 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | OWNER.Design Review | OWNER
D5200 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.6 | Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - Final TTCP Plans - R1 Phase 3 | 2023-03-21 08:00 | 2023-04-17 16:00 |  |  | 20 | 0 | 20 | 838 |  |  | DESIGN | DESIGN
D5210 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.6 | Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Review and Approve - Final TTCP Plans - R1 Phase 3 | 2023-04-18 08:00 | 2023-05-08 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | OWNER.Design Review | OWNER
D5220 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.6 | Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 3 | 2023-05-09 08:00 | 2023-05-30 16:00 |  |  | 15 | 0 | 15 | 838 |  |  | DESIGN | DESIGN
D5230 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.6 | Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Issue - RFC TTCP Plans - R1 Phase 3 | 2023-05-31 08:00 | 2023-06-06 16:00 |  |  | 5 | 0 | 5 | 838 |  |  | DESIGN | DESIGN
D5240 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - 60% Wet Utility Relocation Plans (COT) | 2023-01-03 08:00 | 2023-01-24 16:00 |  |  | 15 | 0 | 15 | 257 |  |  | DESIGN | DESIGN
D5250 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 60% Wet Utility Relocation Plans (COT) | 2023-01-25 08:00 | 2023-02-14 16:00 |  |  | 15 | 0 | 15 | 257 |  |  | 3rd PARTY | 3rd Party
D5260 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - 90% Wet Utility Relocation Plans (COT) | 2023-02-15 08:00 | 2023-03-21 16:00 |  |  | 25 | 0 | 25 | 257 |  |  | DESIGN | DESIGN
D5270 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 90% Wet Utility Relocation Plans (COT) | 2023-03-22 08:00 | 2023-04-11 16:00 |  |  | 15 | 0 | 15 | 257 |  |  | 3rd PARTY | 3rd Party
D5280 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - 100% Wet Utility Relocation Plans (COT) | 2023-04-12 08:00 | 2023-04-18 16:00 |  |  | 5 | 0 | 5 | 257 |  |  | DESIGN | DESIGN
D5290 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 100% Wet Utility Relocation Plans (COT) | 2023-04-19 08:00 | 2023-05-09 16:00 |  |  | 15 | 0 | 15 | 257 |  |  | 3rd PARTY | 3rd Party
D5300 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - Sign & Seal Wet Utility Relocation Plans (COT) | 2023-05-10 08:00 | 2023-05-16 16:00 |  |  | 5 | 0 | 5 | 257 |  |  | DESIGN | DESIGN
D5310 | Not Started | I-275 - I-4 - IBL(all) - B1.3.25.1 | Wet Utility Relocation Plans - City Of Tampa (DRMP) | Issue - RFC Wet Utility Relocation Plans (COT) | 2023-05-17 08:00 | 2023-05-23 16:00 |  |  | 5 | 0 | 5 | 257 |  |  | DESIGN | DESIGN
D5320 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Perform Geotechnical Investigation - Cat2 Brg 10 - R3 | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 381 |  |  | DESIGN | DESIGN
D5330 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 08 - R3 | 2022-12-22 08:00 | 2023-01-23 16:00 |  |  | 20 | 0 | 20 | 366 |  |  | DESIGN | DESIGN
D5340 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 09 - R3 | 2022-12-22 08:00 | 2023-01-23 16:00 |  |  | 20 | 0 | 20 | 336 |  |  | DESIGN | DESIGN
D5350 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.5 | R3 Bridge 11 - Design Category 1 (DRMP) | Perform Geotechnical Investigation - Cat1 Brg 11 - R3 | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 466 |  |  | DESIGN | DESIGN
D5360 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.5.4 | R3 Bridge 12 - Design Category 1 (DRMP) | Perform Geotechnical Investigation - Cat1 Brg 12 - R3 | 2023-12-20 08:00 | 2024-01-19 16:00 |  |  | 20 | 0 | 20 | 502 |  |  | DESIGN | DESIGN
D5370 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.2 | R2 Bridge 07 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 07 - R2 | 2024-06-18 08:00 | 2024-07-16 16:00 |  |  | 20 | 0 | 20 | 388 |  |  | DESIGN | DESIGN
D5380 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.4.1 | R2 Bridge 06 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 06 - R2 | 2024-06-18 08:00 | 2024-07-16 16:00 |  |  | 20 | 0 | 20 | 335 |  |  | DESIGN | DESIGN
D5390 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.3 | R1 Bridge 05 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 05 - R1 | 2022-12-22 08:00 | 2023-01-23 16:00 |  |  | 20 | 0 | 20 | 140 |  |  | DESIGN | DESIGN
D5400 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.4 | R1 Bridge 04 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 04 - R1 | 2023-12-20 08:00 | 2024-01-19 16:00 |  |  | 20 | 0 | 20 | 217 |  |  | DESIGN | DESIGN
D5410 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.6 | R1 Bridge 03 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 03 - R1 | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 140 |  |  | DESIGN | DESIGN
D5420 | Completed | I-275 - I-4 - IBL(all) - B1.3.11.4.2 | R1 Bridge 02 Design Category 2 | Perform Geotechnical Investigation - Cat2 Brg 02 - R1 | 2022-09-14 08:00 | 2022-10-11 16:00 | 2022-09-14 08:00 | 2022-10-11 16:00 | 20 | 20 | 0 |  |  |  | DESIGN | DESIGN
D5430 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.4.1 | R1 Bridge 01 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 01 - R1 | 2022-12-22 08:00 | 2023-01-23 16:00 |  |  | 20 | 0 | 20 | 639 |  |  | DESIGN | DESIGN
D5440 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Perform Geotechnical Investigation - MSE Wall RW 1-1 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 530 |  |  | DESIGN | DESIGN
D5450 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Perform Geotechnical Investigation - MSE Wall RW 1-2 - Ramp NE / Br 1 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 516 |  |  | DESIGN | DESIGN
D5460 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Perform Geotechnical Investigation - MSE Wall RW 2-1 - Br 2 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 345 |  |  | DESIGN | DESIGN
D5470 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Perform Geotechnical Investigation - MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 625 |  |  | DESIGN | DESIGN
D5480 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Perform Geotechnical Investigation - MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 496 |  |  | DESIGN | DESIGN
D5490 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Perform Geotechnical Investigation - MSE Wall RW 2-4 Br 2 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 373 |  |  | DESIGN | DESIGN
D5500 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Perform Geotechnical Investigation - MSE Wall RW 3-1 Br 3 | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 248 |  |  | DESIGN | DESIGN
D5510 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Perform Geotechnical Investigation - MSE Wall RW 3-2 Br 3 | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 226 |  |  | DESIGN | DESIGN
D5520 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.10 | R1 - Retaining Wall Design RW 4-1 Br 4 | Perform Geotechnical Investigation - MSE Wall RW 4-1 Br 4 | 2023-12-20 08:00 | 2024-01-19 16:00 |  |  | 20 | 0 | 20 | 129 |  |  | DESIGN | DESIGN
D5530 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.11 | R1 - Retaining Wall Design RW 4-2 Br 4 | Perform Geotechnical Investigation - MSE Wall RW 4-2 Br 4 | 2023-12-20 08:00 | 2024-01-19 16:00 |  |  | 20 | 0 | 20 | 128 |  |  | DESIGN | DESIGN
D5540 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Perform Geotechnical Investigation - MSE Wall RW 5-1 Ramp WE-B / Br 5 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 238 |  |  | DESIGN | DESIGN
D5550 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Perform Geotechnical Investigation - MSE Wall RW 5-2 Ramp WE-B / Br 5 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 134 |  |  | DESIGN | DESIGN
D5560 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Perform Geotechnical Investigation - MSE Wall RW 100 I-4 EB (Br 3 & 4) | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 200 |  |  | DESIGN | DESIGN
D5570 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Perform Geotechnical Investigation - MSE Wall RW 6-1 Ramp EN / Br 6 | 2023-07-20 08:00 | 2023-08-16 16:00 |  |  | 20 | 0 | 20 | 506 |  |  | DESIGN | DESIGN
D5580 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Perform Geotechnical Investigation - MSE Wall RW 7-1 Ramp EN / Br 7 | 2023-09-27 08:00 | 2023-10-24 16:00 |  |  | 20 | 0 | 20 | 500 |  |  | DESIGN | DESIGN
D5590 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Perform Geotechnical Investigation - MSE Wall RW 7-2 Ramp EN / Br 7 | 2023-09-27 08:00 | 2023-10-24 16:00 |  |  | 20 | 0 | 20 | 286 |  |  | DESIGN | DESIGN
D5600 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.8 | R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 103 Ramp EN | 2024-03-19 08:00 | 2024-04-15 16:00 |  |  | 20 | 0 | 20 | 384 |  |  | DESIGN | DESIGN
D5610 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.1.9 | R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 104 Ramp EN | 2024-05-24 08:00 | 2024-06-21 16:00 |  |  | 20 | 0 | 20 | 286 |  |  | DESIGN | DESIGN
D5620 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Perform Geotechnical Investigation - MSE Wall RW 8-1 Ramp B / Br 8 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 270 |  |  | DESIGN | DESIGN
D5630 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Perform Geotechnical Investigation - MSE Wall RW 8-2 Ramp B / Br 8 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 290 |  |  | DESIGN | DESIGN
D5640 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 9-1 Ramp B/F / Br 9 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 300 |  |  | DESIGN | DESIGN
D5650 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 9-2 Ramp B/F / Br 9 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 237 |  |  | DESIGN | DESIGN
D5660 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 9-3 Ramp B/F / Br 9 | 2023-02-02 08:00 | 2023-03-01 16:00 |  |  | 20 | 0 | 20 | 275 |  |  | DESIGN | DESIGN
D5670 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Perform Geotechnical Investigation - MSE Wall RW 102 Ramp C | 2023-04-11 08:00 | 2023-05-08 16:00 |  |  | 20 | 0 | 20 | 580 |  |  | DESIGN | DESIGN
D5680 | Not Started | I-275 - I-4 - IBL(all) - B1.3.11.19 | R1 Roadway Design (ASI) | Perform Geotechnical Investigation - Roadway - R1 | 2022-12-01 08:00 | 2022-12-29 16:00 |  |  | 20 | 0 | 20 | 299 |  |  | DESIGN | DESIGN
D5690 | Not Started | I-275 - I-4 - IBL(all) - B1.3.12.10 | R2 Roadway Plans (ACP) | Perform Geotechnical Investigation - Roadway - R2 | 2022-12-01 08:00 | 2022-12-29 16:00 |  |  | 20 | 0 | 20 | 738 |  |  | DESIGN | DESIGN
D5700 | Not Started | I-275 - I-4 - IBL(all) - B1.3.10.24 | R3 Roadway Design (DRMP) | Perform Geotechnical Investigation - Roadway - R3 | 2022-12-01 08:00 | 2022-12-29 16:00 |  |  | 20 | 0 | 20 | 636 |  |  | DESIGN | DESIGN

## RSRC
rsrc_short_name | rsrc_name | rsrc_type | unit_id | role_id | def_qty_per_hr
Resource ID | Resource Name | (*)Resource Type | Unit of Measure | (*)Role ID | Default Units / Time(d/d)
CREWS | CREW RESOURCES | Labor |  |  | 1
LANE-CREW | LANE CREWS | Labor |  |  | 1
ASPHALT | Asphalt Paving Crews | Labor |  | Paving Crew | 1
CONCRETE | Concrete Paving Crews | Labor |  | Paving Crew | 1
CP-SLIP | Concrete Pvmt Slipform Crew | Labor |  | Paving Crew | 1
CP-HAND | Concrete Pvmt Handpour Crew | Labor |  | Paving Crew | 1
CP-FORM | Conc Pvmt Form / Prep Crew | Labor |  | Paving Crew | 1
CP-SAW | Conc Pvmt Sawcut Crew | Labor |  | Paving Crew | 1
DEMO | Demolition Crews | Labor |  | Demolition Crew | 1
DM-PAVE | Demo Pavement Crew | Labor |  | Demolition Crew | 1
DM-BLD | Demo Building Crew | Labor |  | Demolition Crew | 1
DM-BRIDGE | Demo Bridge Crew | Labor |  | Demolition Crew | 1
DM-MILL | Asphalt Milling Crew | Labor |  | Demolition Crew | 1
EARTH | EARTHWORK CREWS | Labor |  | Earthwork Crew | 1
EW-C&G | Clearing & Grubbing Crew | Labor |  | Earthwork Crew | 1
EW-EXC | Excavation Crew | Labor |  | Earthwork Crew | 1
EW-EMB | Embankment Crew | Labor |  | Earthwork Crew | 1
EW-FINE | Finegrade Crew | Labor |  | Earthwork Crew | 1
EW-LIME | Lime Subgrade Crew | Labor |  | Earthwork Crew | 1
EW-CEM | Cement Subgrade Crew | Labor |  | Earthwork Crew | 1
EW-ABC | Agg Base Crew | Labor |  | Earthwork Crew | 1
EW-CABC | CABC Crew | Labor |  | Earthwork Crew | 1
DRAINAGE | DRAINAGE CREWS | Labor |  | Drainage Crew | 1
PIPE | Storm Drain Crew | Labor |  | Drainage Crew | 1
UNDR | Underdrain Crew | Labor |  | Drainage Crew | 1
BOX | Box Culvert Crew - PreCast | Labor |  | Drainage Crew | 1
CONC-MISC | Misc Concrete Crews | Labor |  | Misc Concrete Crew | 1
BARRIER | Concrete Barrier Crew | Labor |  | Misc Concrete Crew | 1
FLATWORK | Concrete Flatwork Crew | Labor |  | Misc Concrete Crew | 1
EROSION | Erosion Control Crew | Labor |  |  | 1
STRUCTURE | Structures Crew | Labor |  | Structures Crew | 1
ST-BRIDGE | BRIDGE CREWS | Labor |  | Structures Crew | 1
ST-FOOT | Footing Crew | Labor |  | Structures Crew | 1
ST-COL | Column Crew | Labor |  | Structures Crew | 1
ST-CAP | Cap Crew | Labor |  | Structures Crew | 1
ST-BEAM | Erection Crew | Labor |  | Structures Crew | 1
ST-PANEL | Lagging Crew | Labor |  | Wall Crew | 1
ST-DECK | Deck Crew | Labor |  | Structures Crew | 1
ST-WALL | Wall Crews | Labor |  |  | 1
ST-MSE | MSE Wall Crew | Labor |  | Wall Crew | 1
ST-SEGMENTAL | Segmental Wall Crew | Labor |  | Wall Crew | 1
ST-CIP | CIP Wall Crew | Labor |  | Wall Crew | 1
ST-CULV | CIP Culvert Crew | Labor |  | Structures Crew | 1
ST-REBAR | Rebar Placement Crew | Labor |  | Structures Crew | 1
ST-PILE | Pile Driving Crew | Labor |  | Structures Crew | 1
ST-PTEN | Post Tensioning Crew | Labor |  | Structures Crew | 1
ST-DRSTF | Drilled Shaft Crew | Labor |  | Structures Crew | 1
ST-APPR | Approach Slab Crew | Labor |  | Structures Crew | 1
UTILITY | Utility Installation Crews | Labor |  | Utility Crew | 1
UT-SEWER | Sewer Line Installation Crew | Labor |  | Utility Crew | 1
UT-WATER | Water Line Installation Crew | Labor |  | Utility Crew | 1
TRAFFIC | Traffic Control Crews | Labor |  | Traffic Crew | 1
TC-PCB | TCPB - Barrier Installation Crew | Labor |  | Traffic Crew | 1
SURVEY | Survey Crew | Labor |  |  | 1
SUB-CREW | Sub - Contractor Crews | Labor |  |  | 1
SUB-ASPH | Sub - Asphalt Paving Crew | Labor |  |  | 1
SUB-CONCRETE | Sub - Concrete Paving Crews | Labor |  |  | 1
SUB-CP-SLIP | Sub - Concrete Pvmt Slipform Crew | Labor |  |  | 1
SUB-CP-HAND | Sub - Concrete Pvmt Handpour Crew | Labor |  |  | 1
SUB-CP-FORM | Sub - Conc Pvmt Form / Prep Crew | Labor |  |  | 1
SUB-CP-SAW | Sub - Conc Pvmt Saw/Sealing Crew | Labor |  |  | 1
SUB-CURB | Sub - Concrete Flatwork Crew | Labor |  |  | 1
SUB-DEMO | Sub - Demolition Crews | Labor |  |  | 1
SUB-DM-PAVE | Sub - DEMO Pavement Crew | Labor |  |  | 1
SUB-DM-BLD | Sub - DEMO Building Crew | Labor |  |  | 1
SUB-DM-BRG | Sub - Demo Bridge Crew | Labor |  |  | 1
SUB-MILL | Sub - Asphalt Milling Crew | Labor |  |  | 1
SUB-EARTH | Sub - Earthwork Crew | Labor |  |  | 1
SUB-EW-C&G | Sub - Clearing & Grubbing Crew | Labor |  |  | 1
SUB-EW-EXC | Sub - Excavation Crew | Labor |  |  | 1
SUB-EW-EMB | Sub - Embankment Crew | Labor |  |  | 1
SUB-EW-FINE | Sub - Finegrade Crew | Labor |  |  | 1
SUB-LIME SUBGRADE | Sub - Lime Treated Subgrade Crew | Labor |  |  | 1
SUB-CEM SUBGRADE | Sub - Cement Treated Subgrade Crew | Labor |  |  | 1
SUB-EW-ABC | Sub - Agg Base Crew | Labor |  |  | 1
SUB-EW-CABC | Sub - Cement Treated Stone Base Crew | Labor |  |  | 1
SUB-DRAIN | Sub - Drainage Crews | Labor |  |  | 1
SUB-PIPE | Sub - Storm Drain / Pipe Crew | Labor |  |  | 1
SUB-BOX | Sub - Box Culvert Crew | Labor |  |  | 1
SUB-EROSION | Sub - Erosion Control Crew | Labor |  |  | 1
SUB-STRUC | Sub - Structures Crew | Labor |  |  | 1
SUB-ST-BRIDGE | Sub - Structure Bridge Crews | Labor |  |  | 1
SUB-ST-FOOT | Sub - Footing Crew | Labor |  |  | 1
SUB-ST-COL | Sub - Column Crew | Labor |  |  | 1
SUB-ST-CAP | Sub - Cap Crew | Labor |  |  | 1
SUB-ST-BEAM | Sub - Beam/Erection Crew | Labor |  |  | 1
SUB-ST-PANEL | Sub - Panels/Lagging Crew | Labor |  |  | 1
SUB-ST-DECK | Sub - Deck Crew | Labor |  |  | 1
SUB-ST-WALL | Sub - Retaining Walls Crews | Labor |  |  | 1
SUB-ST-MSE | Sub - MSE Wall Crew | Labor |  |  | 1
SUB-ST-SEGMENTAL | Sub - Segmental Wall Crew | Labor |  |  | 1
SUB-ST-CIP | Sub - CIP Wall Crew | Labor |  |  | 1
SUB-ST-SNAIL | Sub - Soil Nail Wall Crew | Labor |  |  | 1
SUB-ST-CULV | Sub - CIP Culvert Crew | Labor |  |  | 1
SUB-ST-REBAR | Sub - Rebar Placement Crew | Labor |  |  | 1
SUB-ST-PILE | Sub - Pile Driving Crew | Labor |  |  | 1
SUB-ST-PTEN | Sub - Post Tensioning Crew | Labor |  |  | 1
SUB-ST-DRSFT | Sub - Drilled Shaft Crew | Labor |  |  | 1
SUB-ST-APPR | Sub - Approach Slab Crew | Labor |  |  | 1
SUB-SURVEY | Sub - Survey Crew | Labor |  |  | 1
SUB-UTILITY | Sub - Utility Installation Crews | Labor |  |  | 1
SUB-UT-SEWER | Sub - Sewer Line Installation Crew | Labor |  |  | 1
SUB-UT-WATER | Sub - Water Line Installation Crew | Labor |  |  | 1
SUB-UT-ITS | Sub - ITS Installation Crew | Labor |  |  | 1
SUB-UT-COMM | Sub - Phone Line Installation Crew | Labor |  |  | 1
SUB-UT-ELEC | Sub - Electrical Installation Crew | Labor |  |  | 1
SUB-UT-GAS | Sub - Gas Line Installation Crew | Labor |  |  | 1
SUB-UT-FUEL | Sub - Fuel Line Installation Crew | Labor |  |  | 1
SUB-TRAFFIC | Sub - Traffic Control Crews | Labor |  |  | 1
SUB-TC-PCB | Sub - TCPB - Barrier Installation Crew | Labor |  |  | 1
SUB-BARRIER | Sub - Concrete Barrier Crew | Labor |  |  | 1
SUB-DESIGN | Sub - Designer | Labor |  |  | 1
SUB-FENCE | Sub - Fence Installation Crew | Labor |  |  | 1
SUB-GRAIL | Sub - Guardrail Crew | Labor |  |  | 1
SUB-LANDSC | Sub - Landscape Crew | Labor |  |  | 1
SUB-ROW | Sub - Right-Of-Way Crew | Labor |  |  | 1
SUB-SIGN | Sub - Signing Crew | Labor |  |  | 1
SUB-SIGNAL | Sub - Signal Crew | Labor |  |  | 1
SUB-STRIP | Sub - Striping Crew | Labor |  |  | 1
C43-Revenue | C43 - Revenue | Nonlabor |  |  | 1
MAN HOURS | MAN HOURS | Labor |  |  | 1
PROJECT RESOURCES | PROJECT RESOURCES | Labor |  |  | 1
JOB SPECIFIC | Job Specific Resources | Material |  |  | 8
SUB-UDRAIN | Sub - Underdrain Crew | Labor |  |  | 1
SUB-BLAST | Sub - Blasting Crew | Labor |  |  | 1
PREP MEETINGS | PREP MEETINGS | Labor
SUB-DGRIND | Sub - Diamond Grind Pavement Crew | Labor |  |  | 1
SUB-STABALIZATION | Sub - Subgrade Stabilization Crew | Labor |  |  | 1
SUB-TRUCK | Sub - Trucking Crew | Labor |  |  | 1
Drainage-Prep | Drainage Prep Meeting | Labor |  |  | 1
Asphalt-Prep | Asphalt Prep Meeting | Labor |  |  | 1
Conc Pave-Prep | Concrete Paving Prep Meeting | Labor |  |  | 1
Bridge-Prep | Bridge Prep Meeting | Labor |  |  | 1
Beam-Prep | Bridge Beam Prep Meeting | Labor |  |  | 1
Drilled Shaft-Prep | Drilled Shaft Prep Meeting | Labor |  |  | 1
Deck-Prep | Deck Pour Prep Meeting | Labor |  |  | 1
Shoring-Prep | Temp Shoring Prep Meeting | Labor |  |  | 1
Traffic Shift-Prep | Traffic Shift Prep Meeting | Labor |  |  | 1
MSE-Prep | MSE Wall Prep Meeting | Labor |  |  | 1
Earthwork-Prep | Earthwork Prep Meeting | Labor |  |  | 1
DOT/OWNER | DOT/Owner | Labor |  |  | 1
SUB-RUMBLE | Sub - Rumble Strip Crew | Labor |  |  | 1
SUB-JB | Sub - Jack and Bore Pipe Crew | Labor |  |  | 1
SUB-ST-PNT | Sub - Structure Painting Crew | Labor |  |  | 1
SUB-ST-TS | Sub - Temp Shoring Crews | Labor |  |  | 1
3328 | 3328 - I-74 Independence | Nonlabor |  |  | 1
3328 - Pay Items | 3328 - NCDOT Pay Items - Liberty Revenue | Nonlabor |  |  | 0
3328 - 2 | CONSTRUCTION SURVEYING | Material | Lump Sum |  | 1
3328 - 3 | CLEARING & GRUBBING | Material | Cubic Yard |  | 1
3328 - 5 | UNCLASSIFIED EXCAVATION | Material | Cubic Yard |  | 1
3328 - 6 | UNDERCUT EXCAVATION | Material | Cubic Yard |  | 1
3328 - 7 | BORROW EXCAVATION | Material | Cubic Yard |  | 1
3328 - 9 | DRAINAGE DITCH EXCAVATION | Material | Cubic Yard |  | 1
3328 - 10 | BERM DITCH CONSTRUCTION | Material | Linear Feet |  | 1
3328 - 11 | REMOVAL OF EXT ASPHALT PVMT | Material | Square Yard |  | 1
3328 - 12 | BREAKING OF EXT ASPH PVMT | Material | Square Yard |  | 1
3328 - 13 | PROOF ROLLING | Material | Square Yard |  | 1
3328 - 15 | GEOTEXTILE SOIL STABILIZATION | Material | Square Yard |  | 1
3328 - 17 | GEOTEXTILE FOR PAVEMENT STABI-LIZATION | Material | Square Yard |  | 1
3328 - 21 | 15" RC PIPE CULV III | Material | Linear Feet |  | 1
3328 - 26 | 15" RCP CULV CLASS IV | Material | Linear Feet |  | 1
3328 - 27 | 18" RCP CULV CLASS IV | Material | Linear Feet |  | 1
3328 - 28 | 24" RCP CULV CLASS IV | Material | Linear Feet |  | 1
3328 - 29 | 30" RCP CULV CLASS IV | Material | Linear Feet |  | 1
3328 - 30 | 36" RCP CULV CLASS IV | Material | Linear Feet |  | 1
3328 - 37 | PIPE REMOVAL | Material | Linear Feet |  | 1
3328 - 38 | FINE GRADING | Material | Square Yard |  | 1
3328 - 39 | SHALLOW UNDERCUT | Material | Cubic Yard |  | 1
3328 - 40 | CLASS IV SUBGRD STABILIZATION | Material |  |  | 1
3328 - 42 | INCIDENTAL STONE BASE | Material |  |  | 1
3328 - 43 | MILL ASP PVMT *****" DTH [(1-1/2")] | Material | Square Yard |  | 1
3328 - 44 | MILL ASP PVMT *****" DTH [(3")] | Material | Square Yard |  | 1
3328 - 45 | MILL ASP PVMT *****" DTH [(4")] | Material | Square Yard |  | 1
3328 - 48 | ASP CONC BASE CRS B25.0B | Material |  |  | 1
3328 - 49 | ASP CONC BASE CRS B25.0C | Material |  |  | 1
3328 - 50 | ASP CONC INTR CRS I19.0B | Material |  |  | 1
3328 - 51 | ASP CONC INTR CRS I19.0C | Material |  |  | 1
3328 - 52 | ASP CONC SURF CRS S9.5B | Material |  |  | 1
3328 - 53 | ASP CONC SURF CRS S9.5C | Material |  |  | 1
3328 - 55 | ASPH PLT MIX PVMT REPAIR | Material |  |  | 1
3328 - 66 | MASNRY DRAINAGE STRUCT | Material | Each |  | 1
3328 - 67 | MASNRY DRAINAGE STRUCT | Material | Linear Feet |  | 1
3328 - 69 | FRAME W/2GRTS 840.16 STD | Material | Each |  | 1
3328 - 70 | FRAME W/2GRTS 840.24 STD | Material | Each |  | 1
3328 - 71 | FRAME W/2GRTS 840.29 STD | Material | Each |  | 1
3328 - 72 | FRAME-GRT-HD 840.03 ** [(E)] | Material | Each |  | 1
3328 - 73 | FRAME-GRT-HD 840.03 ** [(F)] | Material | Each |  | 1
3328 - 74 | FRAME-GRT-HD 840.03 ** [(G)] | Material | Each |  | 1
3328 - 75 | FRAME W/COVER STD 840.54 | Material | Each |  | 1
3328 - 77 | CONC TRANS SECT FOR DROP INLET | Material | Each |  | 1
3328 - 78 | **"X**" CONCRETE CURB [(8" X 12")] | Material | Linear Feet |  | 1
3328 - 80 | 2'-6" CONC CURB & GUTTER | Material | Linear Feet |  | 1
3328 - 82 | 4" CONCRETE SIDEWALK | Material | Square Yard |  | 1
3328 - 83 | CONCRETE CURB RAMP | Material | Each |  | 1
3328 - 84 | 6" CONCRETE DRIVEWAY | Material | Square Yard |  | 1
3328 - 86 | 5" MONO CONC ISLDS (KEY IN) | Material | Square Yard |  | 1
3328 - 87 | CONC BARRIER TYPE ****** [(T)] | Material | Linear Feet |  | 1
3328 - 88 | CONC BARRIER TYPE ****** [(T1)] | Material | Linear Feet |  | 1
3328 - 89 | CONC BARRIER TYPE ****** [(T2)] | Material | Linear Feet |  | 1
3328 - 90 | CONC BARRIER TRANS SECTN | Material | Each |  | 1
3328 - 91 | PC REINF BARRIER SNGL FC | Material | Linear Feet |  | 1
3328 - 95 | ADJ MANHOLES | Material | Each |  | 1
3328 - 96 | ADJUSTMENT OF JUNCTION BOXES | Material | Each |  | 1
3328 - 97 | CONVERT CB TO DI | Material | Each |  | 1
3328 - 98 | CONVERT CB TO JB W/MH | Material | Each |  | 1
3328 - 99 | CONVERT DI TO JB | Material | Each |  | 1
3328 - 100 | CONVERT DI TO JB W/MH | Material | Each |  | 1
3328 - 101 | CONVERT EXT CATCH BASIN TO TRAFFIC BEARING | Material | Each |  | 1
3328 - 102 | CONVERT EXT TRAFFIC BEARING JUNCTION BOX T | Material | Each |  | 1
3328 - 103 | CONVERT EXT TRAFFIC BEARING DI TO TRAFFIC BE | Material | Each |  | 1
3328 - 104 | IMPACT ATTEN TYPE 350 | Material | Each |  | 1
3328 - 105 | STL BM GUARDRAIL | Material | Linear Feet |  | 1
3328 - 106 | SBGR DOUBLE FACED | Material | Linear Feet |  | 1
3328 - 107 | SBGR TERM SECT | Material | Each |  | 1
3328 - 108 | ADDIT GUARDRAIL POSTS | Material | Each |  | 1
3328 - 109 | GR ANCHOR TYPE ********** [(NJ-25)] | Material | Each |  | 1
3328 - 110 | GR ANCHOR TYPE CAT-1 | Material | Each |  | 1
3328 - 111 | GR ANCHOR TYPE III | Material | Each |  | 1
3328 - 112 | GR ANCHOR TYPE 350 | Material | Each |  | 1
3328 - 113 | CHN LK FENCE 48" FABRIC | Material | Linear Feet |  | 1
3328 - 114 | MET LINE PST 48" CL FEN | Material | Each |  | 1
3328 - 115 | MET TERM PST 48" CL FEN | Material | Each |  | 1
3328 - 118 | PLN CONC FOUNDTN | Material | Cubic Yard |  | 1
3328 - 119 | OVERHEAD FOOTING | Material | Cubic Yard |  | 1
3328 - 120 | SUPPORT, BREAKAWAY STL BM | Material | LB |  | 1
3328 - 121 | SUPPORT, 3-LB STL U-CHAN | Material | Linear Feet |  | 1
3328 - 122 | SUPPORT, BARR SMALL | Material | Each |  | 1
3328 - 123 | SUPPORT, OVRHD SIGN STR **** [(116+30-LLT-)] | Material | Lump Sum |  | 1
3328 - 124 | SUPPORT, OVRHD SIGN STR **** [(23+00-LRT-)] | Material | Lump Sum |  | 1
3328 - 125 | SUPPORT, OVRHD SIGN STR **** [(35+80-LRT-)] | Material | Lump Sum |  | 1
3328 - 126 | SUPPORT, OVRHD SIGN STR **** [(49+10-LLT-)] | Material | Lump Sum |  | 1
3328 - 127 | SUPPORT, OVRHD SIGN STR **** [(61+00-LRT-)] | Material | Lump Sum |  | 1
3328 - 128 | SUPPORT, OVRHD SIGN STR **** [(75+90-LLT-)] | Material | Lump Sum |  | 1
3328 - 129 | SUPPORT, OVRHD SIGN STR **** [(87+50-LRT-)] | Material | Lump Sum |  | 1
3328 - 130 | SUPPORT, OVRHD SIGN STR **** [(92+00-LLT-)] | Material | Lump Sum |  | 1
3328 - 149 | RESET CRASH CUSHION | Material | Each |  | 1
3328 - 153 | RESET PORT CONC BARRIER | Material | Linear Feet |  | 1
3328 - 154 | WATER FILLED BARRIER | Material | Linear Feet |  | 1
3328 - 155 | RESET WATER FILLED BARRIER | Material | Linear Feet |  | 1
3328 - 161 | THERMO PVT MKG LINES 4"90 | Material | Linear Feet |  | 1
3328 - 162 | THERMO PVT MKG LINES 4"120 | Material | Linear Feet |  | 1
3328 - 163 | THERMO PVT MKG LINES 8"90 MILS | Material | Linear Feet |  | 1
3328 - 164 | THERMO PVT MKG LINE 8"120 MILS | Material | Linear Feet |  | 1
3328 - 165 | 24"WIDE THERMO 120 MILS | Material | Linear Feet |  | 1
3328 - 166 | THERMO PVT MKG CHARACTER 120 | Material | Each |  | 1
3328 - 167 | THERMO PVT SYMBOL 90MILS | Material | Each |  | 1
3328 - 168 | 4" COLD APPL PLSTIC LINES TYPE ** [(III)] | Material | Linear Feet |  | 1
3328 - 178 | SNOWPLB PVMT MRKER | Material | Each |  | 1
3328 - 160 | TEMP RAISED PVMT MRKS | Material | Each |  | 1
3328 - 171 | PAINT PVMT MARKINGS 4" | Material | Linear Feet |  | 1
3328 - * 172 | PAINT PVMT MARKINGS 8" | Material | Linear Feet |  | 1
3328 - 173 | PAINT PVT MKG LINES 24" | Material | Linear Feet |  | 1
3328 - 174 | PAINT PVT MKG CHARACTER | Material | Each |  | 1
3328 - 175 | PAINT PVT MKG SYMBOL | Material | Each |  | 1
3328 - 176 | LINE REMOVAL 4" WIDE | Material | Linear Feet |  | 1
3328 - 272 | SEEDING AND MULCHING | Material |  |  | 1
3328 - 277 | FERTILIZER TOPDRESSING | Material |  |  | 1
3328 - 290 | MSE RETAINING WALL NO 2 | Material | Square Feet |  | 1
3328 - 299 | REINF CONCRETE DECK SLAB | Material | Square Feet |  | 1
3328 - 300 | GROOVING BRIDGE FLOORS | Material | Square Feet |  | 1
3328 - 303 | BRG APPR SLAB *********** [(41+57.69-L-)] | Material | Lump Sum |  | 1
3328 - 310 | THREE BAR METAL RAIL | Material | Linear Feet |  | 1
3328 - 311 | 4" SLOPE PROTECTION | Material | Square Yard |  | 1
3328 - 313 | FOAM JOINT SEALS | Material | Lump Sum |  | 1
3328 - 318 SA1 | FIELD OFFICE | Material | Month |  | 1
3328 - * 341 OTH1 | Supplemental Field Surveying - 2012 Specs | Material | Hour |  | 1
3328 - * 342 OTH1 | Supplemental Surveying Office Calculations - 2012 Specs | Material | Gallon |  | 1
3328 - Erosion | EROSION CONTROL PAY ITEMS - COMBO | Material | Unit |  | 1
3328 - ITS | ITS PAY ITEMS - COMBO | Material | Unit |  | 1
3328 - ELEC | ELECTRICAL PAY ITEMS - COMBO | Material | Unit |  | 1
3328 - Traffic | TRAFFIC CONTROL PAY ITEMS - COMBO | Material | Unit |  | 1
3328 - UTILITY | UTILITY PAY ITEMS - COMBO | Material | Unit |  | 1
3328 - CREW COST | 3328 - LANE CREW COST | Nonlabor |  |  | 0
3328 - EW LG | 3328 - Grading Crew - Borrow Load & Place | Material | Day |  | 1
3328 - EW UC | 3328 - Grading Crew - Unclassified & Undercut | Material | Day |  | 1
3328 - EW FG | 3328 - Grading Crew - Fine Grading | Material | Day |  | 1
3328 - EW DW | 3328 - Grading Crew - Driveway / Sidewalk | Material | Day |  | 1
3328 - E&S | 3328 - Erosion Control Crew | Material | Day |  | 1
3328 - TRIM | 3328 - Clean Up Crew | Material | Day |  | 1
3328 - MOT | 3328 - Maintenance Of Trafic Crew | Material | Day |  | 1
3328 - EW SM | 3328 - Grading Crew - Backfill C&G / Sidewalk | Material | Day |  | 1
3328 - PIPE | 3328 - Drainage Crew | Nonlabor |  |  | 0
3328 - EW DEMO | 3328 - Grading Crew - Demo | Material | Day |  | 1
3328 - ADMIN | 3328 - Office Admin Cost | Material | Day |  | 1
3328 - Survey | 3328 - Survey Crew Cost | Material | Day |  | 1
COST - 3328 - 7 | 3328 - COST - BORROW EXCAVATION | Material | Cubic Yard |  | 1
COST - 3328 - 15 | 3328 - COST - GEOTEXTILE SOIL STABILIZATION | Material | Square Yard |  | 1
COST - 3328 - 17 | 3328 - COST - GEOTEXTILE FOR PAVEMENT STABI- | Material | Square Yard |  | 1
3328 COST | Liberty Cost / Lane Revenue | Nonlabor |  |  | 0
3328 - 151 | Port Conc Barrier | Material | Linear Feet |  | 1
3317 | 3317 - Greensboro Eastern | Nonlabor |  |  | 1
3321 | 3321 - Greensboro Western | Nonlabor |  |  | 1
Pay Items | 3294 Pay Items | Material |  |  | 8
Project Budgets | Project Budgets | Material |  |  | 8
R-63 | Peri Single sided formwork | Material | Each |  | 1
R-64 | Peri Double Sided Form | Material | Each |  | 1
3294.BUD | Project Budget | Material |  |  | 1
3294.BL | Betterments | Material |  |  | 1
3294.66 | FINE GRADING | Material | Lump Sum |  | 8
3328 - ACTIVITY COST | PAY ITEM - COST | Nonlabor |  |  | 0
COST - 3328 - 21 | 3328 - COST - 15" RC PIPE CULV III | Material | Linear Feet |  | 1
COST - 3328 - 26 | 3328 - COST - 15" RCP CULV CLASS IV | Material | Linear Feet |  | 1
COST - 3328 - 27 | 3328 - COST - 18" RCP CULV CLASS IV | Material | Linear Feet |  | 1
COST - 3328 - 28 | 3328 - COST - 24" RCP CULV CLASS IV | Material | Linear Feet |  | 1
COST - 3328 - 29 | 3328 - COST - 30" RCP CULV CLASS IV | Material | Linear Feet |  | 1
COST - 3328 - 30 | 3328 - COST - 36" RCP CULV CLASS IV | Material | Linear Feet |  | 1
COST - 3328 - 37 | 3328 - COST - PIPE REMOVAL | Material | Linear Feet |  | 1
COST - 3328 - 40 | 3328 - COST - CL IV SUBGRD STABILIZATION | Material |  |  | 1
COST - 3328 - 42 | 3328 - COST - INCIDENTAL STONE BASE | Material |  |  | 1
COST - 3328 - 43 | 3328 - COST - MILL ASP PVMT *****" DTH [(1-1/2")] | Material | Square Yard |  | 1
COST - 3328 - 44 | 3328 - COST - MILL ASP PVMT *****" DTH [(3")] | Material | Square Yard |  | 1
COST - 3328 - 45 | 3328 - COST - MILL ASP PVMT *****" DTH [(4")] | Material | Square Yard |  | 1
COST - 3328 - 46 | 3328 - COST - MILL ASP PVMT *****" DTH [(4-1/2")] | Material | Square Yard |  | 1
COST - 3328 - 47 | 3328 - COST - INCIDENTAL MILLING | Material | Square Yard |  | 1
COST - 3328 - 48 | 3328 - COST - ASP CONC BASE CRS B25.0B | Material |  |  | 1
COST - 3328 - 49 | 3328 - COST - ASP CONC BASE CRS B25.0C | Material |  |  | 1
COST - 3328 - 50 | 3328 - COST - ASP CONC INTR CRS I19.0B | Material |  |  | 1
COST - 3328 - 51 | 3328 - COST - ASP CONC INTR CRS I19.0C | Material |  |  | 1
COST - 3328 - 52 | 3328 - COST - ASP CONC SURF CRS S9.5B | Material |  |  | 1
COST - 3328 - 53 | 3328 - COST - ASP CONC SURF CRS S9.5C | Material |  |  | 1
COST - 3328 - 54 | 3328 - COST - ASP FOR PLANT MIX | Material |  |  | 1
COST - 3328 - 55 | 3328 - COST - ASPH PLT MIX PVMT REPAIR | Material |  |  | 1
COST - 3328 - 66 | 3328 - COST - MASNRY DRAINAGE STRUCT | Material | Each |  | 1
COST - 3328 - 67 | 3328 - COST - MASNRY DRAINAGE STRUCT | Material | Linear Feet |  | 1
COST - 3328 - 69 | 3328 - COST - FRAME W/2GRTS 840.16 STD | Material | Each |  | 1
COST - 3328 - 70 | 3328 - COST - FRAME W/2GRTS 840.24 STD | Material | Each |  | 1
COST - 3328 - 71 | 3328 - COST - FRAME W/2GRTS 840.29 STD | Material | Each |  | 1
COST - 3328 - 72 | 3328 - COST - FRAME-GRT-HD 840.03 ** [(E)] | Material | Each |  | 1
COST - 3328 - 73 | 3328 - COST - FRAME-GRT-HD 840.03 ** [(F)] | Material | Each |  | 1
COST - 3328 - 74 | 3328 - COST - FRAME-GRT-HD 840.03 ** [(G)] | Material | Each |  | 1
COST - 3328 - 75 | 3328 - COST - FRAME W/COVER STD 840.54 | Material | Each |  | 1
COST - 3328 - 77 | 3328 - COST - CONC TRANS SECT FOR DROP INLET | Material | Each |  | 1
COST - 3328 - 78 | 3328 - COST - **"X**" CONCRETE CURB [(8" X 12")] | Material | Linear Feet |  | 1
COST - 3328 - 80 | 3328 - COST - 2'-6" CONC CURB & GUTTER | Material | Linear Feet |  | 1
COST - 3328 - 82 | 3328 - COST - 4" CONCRETE SIDEWALK | Material | Square Yard |  | 1
COST - 3328 - 83 | 3328 - COST - CONCRETE CURB RAMP | Material | Each |  | 1
COST - 3328 - 84 | 3328 - COST - 6" CONCRETE DRIVEWAY | Material | Square Yard |  | 1
COST - 3328 - 86 | 3328 - COST - 5" MONO CONC ISLDS (KEY IN) | Material | Square Yard |  | 1
COST - 3328 - 87 | 3328 - COST - CONC BARRIER TYPE ****** [(T)] | Material | Linear Feet |  | 1
COST - 3328 - 88 | 3328 - COST - CONC BARRIER TYPE ****** [(T1)] | Material | Linear Feet |  | 1
COST - 3328 - 89 | 3328 - COST - CONC BARRIER TYPE ****** [(T2)] | Material | Linear Feet |  | 1
COST - 3328 - 90 | 3328 - COST - CONC BARRIER TRANS SECTN | Material | Each |  | 1
COST - 3328 - 91 | 3328 - COST - PC REINF BARRIER SNGL FC | Material | Linear Feet |  | 1
COST - 3328 - 92 | 3328 - COST - TEMPORARY 4" CONCRETE SIDEWALK | Material | Square Yard |  | 1
COST - 3328 - 94 | 3328 - COST - TEMPORARY CONCRETE CURB RAMP | Material | Each |  | 1
COST - 3328 - 95 | 3328 - COST - ADJ MANHOLES | Material | Each |  | 1
COST - 3328 - 96 | 3328 - COST - ADJUSTMENT OF JUNCTION BOXES | Material | Each |  | 1
COST - 3328 - 104 | 3328 - COST - IMPACT ATTEN TYPE 350 | Material | Each |  | 1
COST - 3328 - 105 | 3328 - COST - STL BM GUARDRAIL | Material | Linear Feet |  | 1
COST - 3328 - 106 | 3328 - COST - SBGR DOUBLE FACED | Material | Linear Feet |  | 1
COST - 3328 - 107 | 3328 - COST - SBGR TERM SECT | Material | Each |  | 1
COST - 3328 - 108 | 3328 - COST - ADDIT GUARDRAIL POSTS | Material | Each |  | 1
COST - 3328 - 109 | 3328 - COST - GR ANCHOR TYPE ********** [(NJ-25)] | Material | Each |  | 1
COST - 3328 - 110 | 3328 - COST - GR ANCHOR TYPE CAT-1 | Material | Each |  | 1
COST - 3328 - 111 | 3328 - COST - GR ANCHOR TYPE III | Material | Each |  | 1
COST - 3328 - 112 | 3328 - COST - GR ANCHOR TYPE 350 | Material | Each |  | 1
COST - 3328 - 113 | 3328 - COST - CHN LK FENCE 48" FABRIC | Material | Linear Feet |  | 1
COST - 3328 - 114 | 3328 - COST - MET LINE PST 48" CL FEN | Material | Each |  | 1
COST - 3328 - 115 | 3328 - COST - MET TERM PST 48" CL FEN | Material | Each |  | 1
COST - 3328 - 118 | 3328 - COST - PLN CONC FOUNDTN | Material | Cubic Yard |  | 1
COST - 3328 - 119 | 3328 - COST - OVERHEAD FOOTING | Material | Cubic Yard |  | 1
COST - 3328 - 120 | 3328 - COST - SUPPORT, BREAKAWAY STL BM | Material | LB |  | 1
COST - 3328 - 121 | 3328 - COST - SUPPORT, 3-LB STL U-CHAN | Material | Linear Feet |  | 1
COST - 3328 - 122 | 3328 - COST - SUPPORT, BARR SMALL | Material | Each |  | 1
COST - 3328 - 123 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(116+30-LLT-)] | Material | Lump Sum |  | 1
COST - 3328 - 124 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(23+00-LRT-)] | Material | Lump Sum |  | 1
COST - 3328 - 125 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(35+80-LRT-)] | Material | Lump Sum |  | 1
COST - 3328 - 126 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(49+10-LLT-)] | Material | Lump Sum |  | 1
COST - 3328 - 127 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(61+00-LRT-)] | Material | Lump Sum |  | 1
COST - 3328 - 128 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(75+90-LLT-)] | Material | Lump Sum |  | 1
COST - 3328 - 129 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(87+50-LRT-)] | Material | Lump Sum |  | 1
COST - 3328 - 130 | 3328 - COST - SUPPORT, OVRHD SIGN STR **** [(92+00-LLT-)] | Material | Lump Sum |  | 1
COST - 3328 - 149 | 3328 - COST - RESET CRASH CUSHION | Material | Each |  | 1
COST - 3328 - 151 | 3328 - COST - PORT CONC BARRIER | Material | Linear Feet |  | 1
COST - 3328 - 153 | 3328 - COST - RESET PORT CONC BARRIER | Material | Linear Feet |  | 1
COST - 3328 - 154 | 3328 - COST - WATER FILLED BARRIER | Material | Linear Feet |  | 1
COST - 3328 - 155 | 3328 - COST - RESET WATER FILLED BARRIER | Material | Linear Feet |  | 1
COST - 3328 - 160 | 3328 - COST - TEMP RAISED PVMT MRKS | Material | Each |  | 1
COST - 3328 - 161 | 3328 - COST - THERMO PVT MKG LINES 4"90 | Material | Linear Feet |  | 1
COST - 3328 - 162 | 3328 - COST - THERMO PVT MKG LINES 4"120 | Material | Linear Feet |  | 1
COST - 3328 - 163 | 3328 - COST - THERMO PVT MKG LINES 8"90 MILS | Material | Linear Feet |  | 1
COST - 3328 - 164 | 3328 - COST - THERMO PVT MKG LINE 8"120 MILS | Material | Linear Feet |  | 1
COST - 3328 - 165 | 3328 - COST - 24"WIDE THERMO 120 MILS | Material | Linear Feet |  | 1
COST - 3328 - 166 | 3328 - COST - THERMO PVT MKG CHARACTER 120 | Material | Each |  | 1
COST - 3328 - 167 | 3328 - COST - THERMO PVT SYMBOL 90MILS | Material | Each |  | 1
COST - 3328 - 168 | 3328 - COST - 4" COLD APPL PLSTIC LINES TYPE ** [(III)] | Material | Linear Feet |  | 1
COST - 3328 - 171 | 3328 - COST - PAINT PVMT MARKINGS 4" | Material | Linear Feet |  | 1
COST - 3328 - 172 | 3328 - COST - PAINT PVMT MARKINGS 8" | Material | Linear Feet |  | 1
COST - 3328 - 173 | 3328 - COST - PAINT PVT MKG LINES 24" | Material | Linear Feet |  | 1
COST - 3328 - 174 | 3328 - COST - PAINT PVT MKG CHARACTER | Material | Each |  | 1
COST - 3328 - 175 | 3328 - COST - PAINT PVT MKG SYMBOL | Material | Each |  | 1
COST - 3328 - 176 | 3328 - COST - LINE REMOVAL 4" WIDE | Material | Linear Feet |  | 1
COST - 3328 - 178 | 3328 - COST - SNOWPLB PVMT MRKER | Material | Each |  | 1
COST - 3328 - 180 | 3328 - COST - OBJECT MARKERS (END OF RD) | Material | Each |  | 1
COST - 3328 - 272 | 3328 - COST - SEEDING AND MULCHING | Material |  |  | 1
COST - 3328 - 299 | 3328 - COST - REINF CONCRETE DECK SLAB | Material | Square Feet |  | 1
COST - 3328 - 300 | 3328 - COST - GROOVING BRIDGE FLOORS | Material | Square Feet |  | 1
COST - 3328 - 303 | 3328 - COST - BRG APPR SLAB *********** [(41+57.69-L-)] | Material | Lump Sum |  | 1
COST - 3328 - 310 | 3328 - COST - THREE BAR METAL RAIL | Material | Linear Feet |  | 1
COST - 3328 - 311 | 3328 - COST - 4" SLOPE PROTECTION | Material | Square Yard |  | 1
COST - 3328 - 313 | 3328 - COST - FOAM JOINT SEALS | Material | Lump Sum |  | 1
3320 | 3320 - Alliance Airport City of Fort Worth | Nonlabor |  |  | 1
5400558 | 5400558 - Foothills Parkway | Nonlabor |  |  | 1
COST - 3328 - UTILIT | 3328 - COST - UTILITY ITEMS | Material | Unit |  | 8
COST - 3328 - EROSIO | 3328 - COST - EROSION CONTROL ITEMS | Material | Unit |  | 8
COST - 3328 - TRAFFI | 3328 - COST - TRAFFIC CONTROL ITEMS | Material | Unit |  | 8
COST - 3328 - ITS | 3328 - COST - ITS ITEMS | Material | Unit |  | 8
COST - 3328 - ELEC | 3328 - COST - ELECTRICAL ITEMS | Material | Unit |  | 8
3320 Alliance | Alliance Airport Revenue | Material | Lump Sum |  | 1
3328 - 54 | ASP for Plant Mix | Material |  |  | 8
3328 - 131 | SIGN ERECTION, TYPE D | Material | Each |  | 1
3328 - 132 | SIGN ERECTION, TYPE E | Material | Each |  | 1
3328 - 133 | SIGN ERECTION, TYPE F | Material | Each |  | 1
3328 - 134 | SIGN ERECTION, TYPE *** (GRD MTD)[(A)] | Material | Each |  | 1
3328 - 135 | SIGN ERECTION, MILEMARKERS | Material | Each |  | 1
3328 - 136 | DISPOSE SIGN SYST U-CHAN | Material | Each |  | 1
3328 - 137 | DISPOSE SIGN, D,E,F | Material | Each |  | 1
3328 - 179 | 7' U-CHANNEL POST | Material | Each |  | 1
COST - 3328 - 131 | 3328 - COST - SIGN ERECTION, TYPE D | Material | Each |  | 1
COST - 3328 - 132 | 3328 - COST - SIGN ERECTION, TYPE E | Material | Each |  | 1
COST - 3328 - 133 | 3328 - COST - SIGN ERECTION, TYPE F | Material | Each |  | 1
COST - 3328 - 134 | 3328 - COST - SIGN ERECTION, TYPE *** (GRD MTD)[(A)] | Material | Each |  | 1
COST - 3328 - 135 | 3328 - COST - SIGN ERECTION, MILEMARKERS | Material | Each |  | 1
COST - 3328 - 136 | 3328 - COST - DISPOSE SIGN SYST U-CHAN | Material | Each |  | 1
COST - 3328 - 137 | 3328 - COST - DISPOSE SIGN, D,E,F | Material | Each |  | 1
COST - 3328 - 179 | 3328 - COST - 7' U-CHANNEL POSTS | Material | Each |  | 8
COST - 3328 - 277 | 3328 - COST - FERTILIZER TOPDRESSING | Material |  |  | 1
COST - 3328 - 97 | CONVERT CB TO DI | Material |  |  | 8
COST - 3328 - 98 | CONVERT CB TO JB W/ MH | Material |  |  | 8
COST - 3328 - 99 | CONVERT DI TO JB | Material |  |  | 8
COST - 3328 - 100 | CONVERT CB TO JB W/ MH | Material |  |  | 8
COST - 3328 - 101 | CONVERT EXT CATCH BASIN TO TRAFFIC BEARING | Material |  |  | 8
COST - 3328 - 102 | CONVERT EXT TRAFFIC BEARING JUNCTION BOX TO | Material |  |  | 8
COST - 3328 - 103 | CONVERT EXT TRAFFIC BEARING DI TO TRAFFIC BE | Material |  |  | 8
3328 - 293 | MSE RETAINING WALL NO 5 | Material | Square Feet |  | 1
COST - 3328 - 290 | 3228 - COST - MSE RETAINING WALL 2 | Material | Square Feet |  | 1
COST - 3228 - 293 | 3228 - COST - MSE RETAINING WALL 5 | Material | Square Feet |  | 1
COST - 3228 - 312 | 3328 - COST - ELASTOMERIC BEARING | Material | Lump Sum |  | 1
3328 - 312 | ELASTOMARIC BEARINGS | Material | Lump Sum |  | 1
3332 | 3332 - BRT Richmond | Nonlabor |  |  | 1
3300 | 3300 - I-66 / Route 15 Interchange | Nonlabor |  |  | 1
3294 | 3294 - Blueline Ext | Nonlabor |  |  | 1
US64 | US 64 - Asheboro | Labor |  |  | 0
STCR-1 | Bridge Crew | Labor |  |  | 1
3317-1 | 3317 Greensboro Eastern Loop Pay Items | Material |  |  | 8
3317-101 | 101 - Surface Testing PCCP | Material | Lump Sum |  | 8
3317-2 | Mobilization | Material | Lump Sum |  | 8
3317-97 | 97 - 10" With Dowels PCCP | Material |  |  | 8
3317-100 | 100 - 7" to 10" Var. Dep. Shldr | Material |  |  | 8
3317-102 | 102 - 10" No Dowel PCCP Shldr | Material |  |  | 8
3317-103 | 103 - Field Lab Rental | Material | Lump Sum |  | 8
1VG | Mobilization (V&G) | Material | Lump Sum |  | 8
82VG | Diamond Grinding (V&G) | Material |  |  | 8
83VG | Surface Testing PCCP (V&G) | Material | Lump Sum |  | 8
83APAC | Surface Testing (APAC) | Material | Lump Sum |  | 8
82APAC | Diamond Grinding (APAC) | Material |  |  | 8
1APAC | Mobilization (APAC) | Material | Lump Sum |  | 8
3322 | 3322 - I-10 Guadalupe | Nonlabor |  |  | 1
3294.73 | ASPHALT CONCRETE INTERMEDIATE COURSE, TYPE I19.0B | Material |  |  | 8
3294.74 | ASPHALT CONCRETE BASE COURSE, TYPE B25.0C | Material |  |  | 8
3294.76 | ASPHALT CONCRETE SURFACE COURSE, TYPE S9.5C | Material |  |  | 8
3294.88 | 1'-6" CONCRETE CURB AND GUTTER | Material | Linear Feet |  | 8
3294.90 | 2'-6" CONCRETE CURB AND GUTTER | Material | Linear Feet |  | 8
3294.91 | 4" CONCRETE SIDEWALK | Material | Square Yard |  | 8
I3802 | I-85 - I3802B Revenue Resources | Labor |  |  | 1
3236 | 3236 - I-581 VA | Nonlabor |  |  | 1
R-24 | 11-Culvert | Material |  |  | 8
R-39 | 17-Stabilization | Material |  |  | 8
3329 | 3329 - I-85 Rowan County | Nonlabor |  |  | 1
R-48 | 12-Traffic | Material |  |  | 8
R-49 | 16-Flatwork | Material |  |  | 8
R-50 | 13-CIP Barrier | Material |  |  | 8
R-51 | 15-Clearing - Demo | Material |  |  | 8
R-52 | 14-Survey | Material |  |  | 8
R-53 | 10-MSE Wall | Material |  |  | 8
R-54 | 9-Bridge | Material |  |  | 8
R-55 | 8-Concrete | Material |  |  | 8
R-56 | 7-ABC | Material |  |  | 8
R-57 | 6-Asphalt | Material |  |  | 8
R-58 | 5-Drainage | Material |  |  | 8
R-59 | 4-Earthwork | Material |  |  | 8
R-60 | 3-E&S | Material |  |  | 8
R-61 | 2-Design Fee | Material |  |  | 8
R-62 | 1-Mobilization | Material |  |  | 8
R-113 | 18-Guardrail | Material |  |  | 8
R-114 | 19-Seeding | Material |  |  | 8
R-115 | 20-Markings | Material |  |  | 8
R-116 | 21-Rumble | Material |  |  | 8
R-117 | 22-Grinding | Material |  |  | 8
R-118 | 23-Signs | Material |  |  | 8
R-119 | 24-ITS | Material |  |  | 8
R-120 | 25-Access | Material |  |  | 8
R-121 | 26- Wet Utilities | Material |  |  | 8
R-124 | 1.5-DB Mobilization | Material |  |  | 8
9136 | 9136 - Lane Abrams JV SH360 | Nonlabor |  |  | 1
3332-1 | 3332-GRTC Bus Transit Richmond VA | Labor |  |  | 1
C00108069DB87.25593 | QUALITY ASSURANCE | Material | Lump Sum |  | 1
C00108069DB87.25595 | QUALITY CONTROL | Material | Lump Sum |  | 1
C00108069DB87.25561 | FORMAL PARTNERING | Material | Lump Sum |  | 1
C00108069DB87.00110 | CONSTRUCTION MANAGEMENT | Material | Lump Sum |  | 1
C00108069DB87.00104 | PROJECT DESIGN | Material | Lump Sum |  | 1
C00108069DB87.00105 | PUBLIC COMMUNICATION/OUTREACH | Material | Lump Sum |  | 1
C00108069DB87.85130 | BOND | Material | Lump Sum |  | 1
C00108069DB87.25505 | FIELD OFFICE TY. I | Material | Lump Sum |  | 1
C00108069DB87.25567 | PROGRESS SCHEDULE UPDATES | Material | Lump Sum |  | 1
C00108069DB87.00101 | CONSTRUCTION SURVEYING (CONSTRUCTION) | Material | Lump Sum |  | 1
C00108069DB87.00109 | UTILITY LOCATING (TEST PITS) | Material | Each |  | 1
C00108069DB87.00120 | REGULAR EXCAVATION | Material | Cubic Yard |  | 1
C00108069DB87.00250 | UNDERCUT & REFILL | Material | Cubic Yard |  | 1
C00108069DB87.00700 | POST INSTALLATION INSPECTION | Material | Linear Feet |  | 1
C00108069DB87.02026 | STORM DRAINAGE | Material | Lump Sum |  | 1
C00108069DB87.10121 | AGGR. BASE MATL. TY. I NO. 21B, VAR. DEPTH | Material |  |  | 1
C00108069DB87.10499 | NS THIN HOT MIX ASPH CONC OVERLAY, 3/4" (THMACO) | Material | Square Yard |  | 1
C00108069DB87.10609 | ASPHALT CONC. TY. SM-12.5E(76-22), 1.5" DEPTH | Material |  |  | 1
C00108069DB87.10610 | ASPHALT CONCRETE TY. IM-19.0A, 2" DEPTH | Material |  |  | 1
C00108069DB87.10628 | FLEXIBLE PAVE. PLANING 0" - 2" | Material | Square Yard Inch |  | 1
C00108069DB87.10629 | FLEXIBLE PAVE. PLANING ABOVE 2"-4" | Material | Square Yard Inch |  | 1
C00108069DB87.10642 | ASPHALT CONCRETE TY. BM-25.0A, VAR. DEPTH | Material |  |  | 1
C00108069DB87.10881 | REINF. HYDR.CEM.CONC. PAVE. 8" | Material | Square Yard |  | 1
C00108069DB87.12025 | NS CITY OF RICHMOND CURB STD. | Material | Linear Feet |  | 1
C00108069DB87.12720 | NS HENRICO STD. CURB & GUTTER | Material | Linear Feet |  | 1
C00108069DB87.12910 | ENTRANCE GUTTER CG-9A | Material | Square Yard |  | 1
C00108069DB87.13109 | NS CG-12 TY. A | Material | Square Yard |  | 1
C00108069DB87.13110 | NS CG-12 TY. B | Material | Square Yard |  | 1
C00108069DB87.13111 | NS CG-12 TY. M2 | Material | Square Yard |  | 1
C00108069DB87.13112 | NS REPL. RAMP SURF.&DET.WARN.SURF. | Material | Square Yard |  | 1
C00108069DB87.13212 | R/W MONUMENT RM-2 | Material | Each |  | 1
C00108069DB87.13220 | HYDR. CEMENT CONC. SIDEWALK 4" | Material | Square Yard |  | 1
C00108069DB87.13244 | NS SAW-CUT H.C.C. SIDEWALK | Material | Linear Feet |  | 1
C00108069DB87.13244- | NS SAW-CUT ASPH & HCC, 12" | Material | Linear Feet |  | 1
C00108069DB87.13245 | NS BRICK SIDEWALK | Material | Square Yard |  | 1
C00108069DB87.13246 | NS REMOVE & RESET PAVERS | Material | Square Yard |  | 1
C00108069DB87.13630 | IMPACT ATTENUATOR SERVICE TYPE I-A | Material | Each |  | 1
C00108069DB87.21020 | MEDIAN STRIP MS-1 | Material | Square Yard |  | 1
C00108069DB87.21021 | NS MEDIAN STRIP MS-1 MOD. | Material | Square Yard |  | 1
C00108069DB87.23600 | NS TEMPORARY CONSTRUCTION FENCE | Material | Linear Feet |  | 1
C00108069DB87.24152 | TYPE III BARRICADE 8' | Material | Each |  | 1
C00108069DB87.24160 | CONSTRUCTION SIGNS | Material | Square Feet |  | 1
C00108069DB87.24265 | MAINTENANCE OF TRAFFIC (MOT) | Material | Lump Sum |  | 1
C00108069DB87.24278 | GROUP 2 CHANNELIZING DEVICES | Material | Each |  | 1
C00108069DB87.24279 | PORTABLE CHANGEABLE MESSAGE SIGN(PCMS) | Material | Each |  | 1
C00108069DB87.24281 | ELECTRONIC ARROW | Material | Each |  | 1
C00108069DB87.24282 | FLAGGER SERVICE | Material | Hour |  | 1
C00108069DB87.24283 | POLICE PATROL C.O.R. | Material | Hour |  | 1
C00108069DB87.24297 | TRAF.BARR.SER.CONC.DOUBLE FACE | Material | Linear Feet |  | 1
C00108069DB87.24410 | DEMOLITION OF PAVEMENT (RIGID) | Material | Square Yard |  | 1
C00108069DB87.24430 | DEMOLITION OF PAVEMENT (FLEXIBLE) | Material | Square Yard |  | 1
C00108069DB87.24435 | DEMOLISH EXIST. CURB | Material | Linear Feet |  | 1
C00108069DB87.24436 | DEMOLISH EXIST. CONC. SIDEWALK | Material | Square Yard |  | 1
C00108069DB87.24437 | DEMOLISH EXIST. CONC. MEDIAN | Material | Square Yard |  | 1
C00108069DB87.24438 | DEMOLISH EXIST. BRICK SIDEWALK | Material | Square Yard |  | 1
C00108069DB87.25565 | PROGRESS SCHEDULE BASELINE | Material | Lump Sum |  | 1
C00108069DB87.27000 | SELECT TREE AND PLANTER BOX RMVL & TRIMMING | Material | Each |  | 1
C00108069DB87.27022 | TOPSOIL CLASS B 2" | Material |  |  | 1
C00108069DB87.27102 | REGULAR SEED | Material | LB |  | 1
C00108069DB87.27103 | OVERSEEDING | Material | LB |  | 1
C00108069DB87.27106 | TEMP SEEDING | Material |  |  | 1
C00108069DB87.27215 | FERTILIZER (15-30-15) | Material |  |  | 1
C00108069DB87.27250 | LIME | Material |  |  | 1
C00108069DB87.27422 | DEWATERING BASIN | Material | Each |  | 1
C00108069DB87.27461 | INLET PROTECTION, TYPE B | Material | Each |  | 1
C00108069DB87.27505 | TEMP. SILT FENCE | Material | Linear Feet |  | 1
C00108069DB87.29001 | TREES | Material | Each |  | 1
C00108069DB87.29002 | SHRUBS | Material | Each |  | 1
C00108069DB87.29003 | ORNAMENTAL GRASSES | Material | Each |  | 1
C00108069DB87.29004 | GROUND COVER | Material | Each |  | 1
C00108069DB87.29005 | PERENNIALS | Material | Each |  | 1
C00108069DB87.29006 | PLANTING SOIL MIX | Material | Cubic Yard |  | 1
C00108069DB87.29007 | MULCH, 2" | Material | Cubic Yard |  | 1
C00108069DB87.49013 | DRY UTILITY RELOCATION COSTS | Material | Lump Sum |  | 1
C00108069DB87.49014 | WET UTILITY RELOCATION COST(WATER) | Material | Lump Sum |  | 1
C00108069DB87.49015 | WET UTILITY RELOCATION COST(SEWER) | Material | Lump Sum |  | 1
C00108069DB87.50108 | SIGN PANEL | Material | Square Feet |  | 1
C00108069DB87.50434 | SIGN POST STP-1, 2 1/2" | Material | Linear Feet |  | 1
C00108069DB87.50490 | CONCRETE FOUNDATION STP-1 | Material | Each |  | 1
C00108069DB87.50600 | REMOVE TY.I SIGNS | Material | Each |  | 1
C00108069DB87.51030 | CONTROLLER | Material | Each |  | 1
C00108069DB87.51170 | ELECTRICAL SERVICE SE-5 | Material | Each |  | 1
C00108069DB87.51184 | TRAF. SIG. HEAD SEC 12" LED | Material | Each |  | 1
C00108069DB87.51185 | BUS RAPID TRANSIT SIGNAL HEAD | Material | Each |  | 1
C00108069DB87.51198 | PEDESTRIAN ACTUATION PA-2 | Material | Each |  | 1
C00108069DB87.51199 | PEDESTRIAN ACTUATION PA-3 | Material | Each |  | 1
C00108069DB87.51212 | PEDESTAL POLE PF-2 12' | Material | Each |  | 1
C00108069DB87.51238 | CONC. FOUND. SIGNAL POLE PF-8 | Material | Cubic Yard |  | 1
C00108069DB87.51240 | CONC. FOUNDATION PF-2 | Material | Each |  | 1
C00108069DB87.51247 | CONCRETE FOUND. CF-3 | Material | Each |  | 1
C00108069DB87.51307 | SIG. POLE MP-1 20' ONE ARM 20' | Material | Each |  | 1
C00108069DB87.51313 | SIG. POLE MP-1 20' ONE ARM 26' | Material | Each |  | 1
C00108069DB87.51317 | SIG. POLE MP-1 20' ONE ARM 30' | Material | Each |  | 1
C00108069DB87.51323 | SIG. POLE MP-1 20' ONE ARM 36' | Material | Each |  | 1
C00108069DB87.51327 | SIG. POLE MP-1 20' ONE ARM 40' | Material | Each |  | 1
C00108069DB87.51333 | SIG. POLE MP-1 20' ONE ARM 46' | Material | Each |  | 1
C00108069DB87.51344 | SIG. POLE MP-1 20' ONE ARM 56' | Material | Each |  | 1
C00108069DB87.51346 | SIG. POLE MP-1 20' ONE ARM 58' | Material | Each |  | 1
C00108069DB87.51366 | SIG.POLE MP-1 CO.LU.TWO ARMS 34'& 40' | Material | Each |  | 1
C00108069DB87.51408 | SIG.POLE MP-1 CO.LU.ONE ARM 46 | Material | Each |  | 1
C00108069DB87.51412 | SIG.POLE MP-1 CO.LU.ONE ARM 50 | Material | Each |  | 1
C00108069DB87.51420 | SIG.POLE MP-1 CO.LU.ONE ARM 58 | Material | Each |  | 1
C00108069DB87.51602 | 14/2 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.51603 | 14/3 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.51604 | 14/4 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.51605 | 14/5 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.51607 | 14/7 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.51830 | HANGER ASSEMBLY SM-3, ONE WAY | Material | Each |  | 1
C00108069DB87.51838 | HANGER ASSM.SMB-3, ONE WAY | Material | Each |  | 1
C00108069DB87.51942 | RELOCATE EXISTING SIGNAL HEAD | Material | Each |  | 1
C00108069DB87.51943 | REMOVE EXISTING SIGNAL HEADS | Material | Each |  | 1
C00108069DB87.51944 | REMOVE EXISTING CONTROLLER | Material | Each |  | 1
C00108069DB87.51945 | REMOVE EXISTING SIGNAL POLE | Material | Each |  | 1
C00108069DB87.51951 | INSTALL SIGN | Material | Each |  | 1
C00108069DB87.52403 | PEDESTRIAN SIGNAL HEAD SP-8 | Material | Each |  | 1
C00108069DB87.54032 | TY. B CL.I PAVE. LINE MARK. 4" | Material | Linear Feet |  | 1
C00108069DB87.54034 | TY. B CL.I PAVE. LINE MARK. 6" | Material | Linear Feet |  | 1
C00108069DB87.54037 | TY. B CL.I PAVE. LINE MARK. 8" | Material | Linear Feet |  | 1
C00108069DB87.54040 | TY. B CL.I PAVE. LINE MARK. 12" | Material | Linear Feet |  | 1
C00108069DB87.54042 | TY. B CL.I PAVE. LINE MARK. 24" | Material | Linear Feet |  | 1
C00108069DB87.54105 | ERAD. OF EXIST. PAVE. MARKING | Material | Linear Feet |  | 1
C00108069DB87.54300 | PAVE. MESS. MARK. ELONG. ARROW SINGULAR | Material | Each |  | 1
C00108069DB87.54310 | PAVE. MESS. MARK. ELONG. ARROW DOUBLE | Material | Each |  | 1
C00108069DB87.54400 | PAVEMENT MESSAGE MARK. "ONLY" | Material | Each |  | 1
C00108069DB87.54402 | PAVEMENT MESSAGE MARK. "BUS" | Material | Each |  | 1
C00108069DB87.54403 | PAVEMENT MESSAGE MARK. "HOV" | Material | Each |  | 1
C00108069DB87.54404 | PAVEMENT MESSAGE MARK. "95 ROUTE SYMBOL" | Material | Each |  | 1
C00108069DB87.54424 | CONSTR. P.M. TY.D ELONG. ARROW | Material | Each |  | 1
C00108069DB87.54425 | CONSTR. P.M. TY.D ELONG. ARROW DBL. | Material | Each |  | 1
C00108069DB87.54466 | CONS. PAVE. MARK. (TY. E) 6" | Material | Linear Feet |  | 1
C00108069DB87.54510 | CONSTR. PAVE. MARK (TY.D,CL.I) 4" | Material | Linear Feet |  | 1
C00108069DB87.55020 | 2 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.55080 | 8 CONDUCTOR CABLE | Material | Linear Feet |  | 1
C00108069DB87.55140 | CONCRETE FOUNDATION LF-1 TY. A | Material | Each |  | 1
C00108069DB87.55172 | LIGHTING POLE LP-1 30'-12' | Material | Each |  | 1
C00108069DB87.55200 | SIDEWALK LIGHTING POLE - DECORATIVE | Material | Each |  | 1
C00108069DB87.55205 | RELOCATE EXIST. LIGHT POLE | Material | Each |  | 1
C00108069DB87.55504 | LUMINAIRE 400 WATT H.P.S. | Material | Each |  | 1
C00108069DB87.55505 | DECORATIVE LIGHT FIXTURE | Material | Each |  | 1
C00108069DB87.55580 | JUNCTION BOX JB-R1 | Material | Each |  | 1
C00108069DB87.55581 | JUNCTION BOX JB-R2 | Material | Each |  | 1
C00108069DB87.55586 | JUNCTION BOX JB-S1 | Material | Each |  | 1
C00108069DB87.55588 | JUNCTION BOX JB-S3 | Material | Each |  | 1
C00108069DB87.56014 | ELECT. SER. GRD. ELECTRODE(10') | Material | Each |  | 1
C00108069DB87.56034 | 3" CONDUIT | Material | Linear Feet |  | 1
C00108069DB87.56050 | BORED CONDUIT 2-2" | Material | Linear Feet |  | 1
C00108069DB87.56051 | BORED CONDUIT 3" | Material | Linear Feet |  | 1
C00108069DB87.56200 | TRENCH EXCAVATION ECI-1 | Material | Linear Feet |  | 1
C00108069DB87.56205 | TEST BORE | Material | Each |  | 1
C00108069DB87.56210 | TRANSIT SIGNAL PRIORITY | Material | Each |  | 1
C00108069DB87.56215 | 360 DEGREE VIDEO DETECTION | Material | Each |  | 1
C00108069DB87.56220 | UPS | Material | Each |  | 1
C00108069DB87.56225 | REMOVE EXISTING SIGNALS | Material | Each |  | 1
C00108069DB87.56230 | LAYER 2 ETHERNET SWITCH | Material | Each |  | 1
C00108069DB87.56235 | LED BLANKOUT SIGN (NLT 3'X3') | Material | Each |  | 1
C00108069DB87.56240 | FIBER OPTIC CABLE 96 STRAND | Material | Linear Feet |  | 1
C00108069DB87.56245 | FIBER OPTIC CABLE 12 STRAND | Material | Linear Feet |  | 1
C00108069DB87.56246 | FIBER OPTIC SPLICES | Material | Each |  | 1
C00108069DB87.56250 | SYSTEM INTEGRATION | Material | Lump Sum |  | 1
C00108069DB87.56260 | LAYER 3 ETHERNET SWITCH | Material | Each |  | 1
C00108069DB87.70002 | RELOCATE EXIST. BUS STOP & RICHMOND GATEWAY MONUM. | Material | Each |  | 1
C00108069DB87.70003 | REMOVE & SALVAGE EXIST. BUS STOP | Material | Each |  | 1
C00108069DB87.85012 | (BASE BID) STATIONS - "REDUCED SIZE" CURB & MEDIAN | Material | Lump Sum |  | 1
C00108069DB87.OPT-1 | CLAY FACE BRICK (OPTION #1) | Material | Lump Sum |  | 1
C00108069DB87.OPT-2 | 1.5" MILL & OVERLAY (OPTION #2) | Material | Square Yard |  | 1
C00108069DB87.OPT-3 | STATIONS - FULL LENGTH CURB & MEDIAN (OPTION #3) | Material | Lump Sum |  | 1
C00108069DB87.SC.STL | Sucontractor - Steel (Canopies) | Labor |  |  | 1
C00108069DB87.SC.GLZ | Subcontractor - Glazing | Labor |  |  | 1
C00108069DB87.SC.BRK | Subcontractor - Brick Layer | Labor |  |  | 1
C00108069DB87.DEMO | Demolition Crew | Labor |  |  | 1
C00108069DB87.FND | Foundation Crew | Labor |  |  | 1
C00108069DB87.00100 | MOBILIZATION | Material | Lump Sum |  | 1
C00108069DB87.00111 | PROJECT START-UP ADMINISTRATION | Material | Lump Sum |  | 1
3337 | 3337 - SR65-Ft Duq Brdg | Nonlabor |  |  | 1
3337-1 | SR65-Ft Duq Brdg | Labor |  |  | 1
3337-2 | General Revenue Resource | Material |  |  | 1
C00100566DB63_25595 | I-66/15_QC | Material | Lump Sum |  | 1
C00100566DB63_25593 | I-66/15_QA | Material | Lump Sum |  | 1
C00100566DB63_54510 | CONSTR.PAVE.MARK.(TY.D - CL.I)4" | Material | Lump Sum |  | 1
C00100566DB63_54240 | TEMP. PAVE. MARKER 1 WAY | Material | Lump Sum |  | 1
C00100566DB63_54300 | PAVEMENT MESSAGE MARK. ELONGATED ARROW S | Material | Lump Sum |  | 1
C00100566DB63_54310 | PAVEMENT MESSAGE MARK. ELONGATED ARROW D | Material | Lump Sum |  | 1
C00100566DB63_4901-2 | NS UTILITIES TEST BORE, PAVED AREAS | Material | Lump Sum |  | 1
C00100566DB63_4901-3 | NS UTILITIES TEST BORE, UNPAVED | Material | Lump Sum |  | 1
C00100566DB63_4901-4 | NS UTILITIES TEST BORE, PAVED AREAS | Material | Lump Sum |  | 1
C00100566DB63_4901-5 | NS UTILITIES TEST BORE, UNPAVED | Material | Lump Sum |  | 1
C00100566DB63 | I-66/15_General Construction Activities | Material |  |  | 1
C00100566DB63_CA | I-66/15_CONTRACT ADMINISTRATION | Material |  |  | 1
C00100566DB63_PR | I-66/15_Procurment | Material |  |  | 1
C00100566DB63_4901-6 | NS UTILITIES TEST BORE, PAVED AREAS | Material | Lump Sum |  | 1
C00100566DB63_4901-7 | NS UTILITIES TEST BORE, UNPAVED | Material | Lump Sum |  | 1
C00100566DB63_4901-8 | NS UTILITIES TEST BORE, PAVED AREAS | Material | Lump Sum |  | 1
C00100566DB63_4901-9 | NS UTILITIES TEST BORE, UNPAVED | Material | Lump Sum |  | 1
C00100566DB63_STR3 | Structure Crew #3 | Labor |  |  | 1
C00100566DB63_Ex Cr3 | Earthwork Crew #3 | Labor |  |  | 1
C00100566DB63_Ex Cr4 | Earthwork Crew #4 | Labor |  |  | 1
C00100566DB63_CO10 | I-66/15_Change Order #10 | Material | Lump Sum |  | 1
C00100566DB63_CO11 | I-66/15_Change Order #11 | Material | Lump Sum |  | 1
C00100566DB63_CO12 | I-66/15_Change Order #12 | Material | Lump Sum |  | 1
C00100566DB63_CO13 | I-66/15_Change Order #13 | Material | Lump Sum |  | 1
C00100566DB63_CO14 | I-66/15_Change Order #14 | Material | Lump Sum |  | 1
C00100566DB63_CO15 | I-66/15_Change Order #15 | Material | Lump Sum |  | 1
C00100566DB63_CO16 | I-66/15_Change Order #16 | Material | Lump Sum |  | 1
C00100566DB63_CO2 | I-66/15_Change Order #2 | Material | Lump Sum |  | 8
C00100566DB63_Ex Cr | Earthwork Crew #2 | Labor |  |  | 1
C00100566DB63_Sub_Sn | Sub Signs | Labor |  |  | 1
C00100566DB63_SC_LGT | Sub Lighting | Labor |  |  | 1
C00100566DB63_CO3 | I-66/15_Change Order #3 | Material | Lump Sum |  | 1
C00100566DB63_CO4 | I-66/15_Change Order #4 | Material | Lump Sum |  | 1
C00100566DB63_CO5 | I-66/15_Change Order #5 | Material | Lump Sum |  | 1
C00100566DB63_CO6 | I-66/15_Change Order #6 | Material | Lump Sum |  | 1
C00100566DB63_CO7 | I-66/15_Change Order #7 | Material | Lump Sum |  | 1
C00100566DB63_CO8 | I-66/15_Change Order #8 | Material | Lump Sum |  | 1
C00100566DB63_CO9 | I-66/15_Change Order #9 | Material | Lump Sum |  | 1
C00100566DB63_09250 | SLOPE DRAIN | Material | Lump Sum |  | 1
C00100566DB63_27290 | TEMP SEEDING | Material | Lump Sum |  | 1
C00100566DB63_27284 | EROSION CONTROL MULCH | Material | Lump Sum |  | 1
C00100566DB63_27300 | SOD | Material | Lump Sum |  | 1
C00100566DB63_27326 | SOIL STAB. MAT EC-3 TYPE B | Material | Lump Sum |  | 1
C00100566DB63_13170 | CONSTRUCTION ENTRANCES | Material | Lump Sum |  | 1
C00100566DB63_27410 | CHECK DAM - ROCK TY. I | Material | Lump Sum |  | 1
C00100566DB63_27422 | DEWATERING BASIN | Material | Lump Sum |  | 1
C00100566DB63_27430 | SILTATION CONTROL EXCAVATION | Material | Lump Sum |  | 1
C00100566DB63_27451 | INLET PROTECTION - TYPE A | Material | Lump Sum |  | 1
C00100566DB63_27505 | TEMP. SILT FENCE | Material | Lump Sum |  | 1
C00100566DB63_27334 | TEMP.VEHICULAR WATERCOURSE CROSSING | Material | Lump Sum |  | 1
C00100566DB63_24502 | REMOVE EXIST STORM STRUCTURES | Material | Lump Sum |  | 1
C00100566DB63_24600 | REMOVE EXIST GUARDRAIL | Material | Lump Sum |  | 1
C00100566DB63_54105 | ERAD. OF EXIST.PAVE.MARKING | Material | Lump Sum |  | 1
C00100566DB63_24420 | DEMOLITION OF PAVEMENT (RIGID) | Material | Lump Sum |  | 1
C00100566DB63_24430 | DEMOLITION OF PAVEMENT (FLEXIBLE) | Material | Lump Sum |  | 1
C00100566DB63_24501 | NS REMOVE EXIST PIPE | Material | Lump Sum |  | 1
C00100566DB63_00100 | Mobilization | Material | Lump Sum |  | 1
C00100566DB63_49013 | NS DRY UTILITY RELOCATION COSTS | Material | Lump Sum |  | 1
C00100566DB63_13565 | RETAINING WALL EXCAVATION | Material | Lump Sum |  | 1
C00100566DB63_49014 | NS WET UTILITY RELOCATION COSTS | Material | Lump Sum |  | 1
C00100566DB63_49012 | NS TEST PITS FOR UTILITY CONFLICTS | Material | Lump Sum |  | 1
C00100566DB63_00101 | CONSTRUCTION SURVEYING (CONSTR.) | Material | Lump Sum |  | 1
C00100566DB63_00110 | CLEARING AND GRUBBING | Material | Lump Sum |  | 1
C00100566DB63_00118 | NS EXCAVATION DISPOSAL OF UNSUITABLE MAT | Material | Lump Sum |  | 1
C00100566DB63_00128 | NS EXCAVATION UNDERCUT | Material | Lump Sum |  | 1
C00100566DB63_00120 | REGULAR EXCAVATION | Material | Lump Sum |  | 1
C00100566DB63_00355 | GEOTEXTILE (SUBGRADE STAB.) | Material | Lump Sum |  | 1
C00100566DB63_00529 | FLOWABLE BACKFILL | Material | Lump Sum |  | 1
C00100566DB63_00588 | UNDERDRAIN UD-4 | Material | Lump Sum |  | 1
C00100566DB63_00591 | COMB. UNDERDRAIN CD-2 | Material | Lump Sum |  | 1
C00100566DB63_00595 | OUTLET PIPE | Material | Lump Sum |  | 1
C00100566DB63_00700 | POST INSTALLATION INSPECTION | Material | Lump Sum |  | 1
C00100566DB63_01150 | 15" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01180 | 18" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01210 | 21" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01240 | 24" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01300 | 30" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01360 | 36" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01420 | 42" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01480 | 48" PIPE-J&B I-66 WBL | Material | Lump Sum |  | 1
C00100566DB63_01540 | 54" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01600 | 60" PIPE | Material | Lump Sum |  | 1
C00100566DB63_01780 | 78" PIPE | Material | Lump Sum |  | 1
C00100566DB63_06600 | CLEAN STORM PIPE | Material | Lump Sum |  | 1
C00100566DB63_0525-1 | END WALL EW-1 | Material | Lump Sum |  | 1
C00100566DB63_0525-2 | END WALL EW-2 | Material | Lump Sum |  | 1
C00100566DB63_06151 | 15" END SECTION ES-1 | Material | Lump Sum |  | 1
C00100566DB63_06181 | 18" END SECTION ES-1 | Material | Lump Sum |  | 1
C00100566DB63_06241 | 24" END SECTION ES-1 | Material | Lump Sum |  | 1
C00100566DB63_06301 | 30" END SECTION ES-1 | Material | Lump Sum |  | 1
C00100566DB63_06361 | 36" END SECTION ES-1 | Material | Lump Sum |  | 1
C00100566DB63_06481 | 48" END SECTION ES-1 | Material | Lump Sum |  | 1
C00100566DB63_0525-5 | END WALL EW-7 | Material | Lump Sum |  | 1
C00100566DB63_00596 | END WALL EW-12 | Material | Lump Sum |  | 1
C00100566DB63_06700 | DROP INLETS DI-3B | Material | Lump Sum |  | 1
C00100566DB63_07506 | DROP INLET DI-5 | Material | Lump Sum |  | 1
C00100566DB63_27550 | STRUCTURE SWM-1 | Material | Lump Sum |  | 1
C00100566DB63_00560 | JUNCTION BOX JB-1 | Material | Lump Sum |  | 1
C00100566DB63_09060 | YARD INLETS | Material | Lump Sum |  | 1
C00100566DB63_09056 | MANHOLE MH-2 | Material | Lump Sum |  | 1
C00100566DB63_09057 | FRAME & COVER MH-1 | Material | Lump Sum |  | 1
C00100566DB63_42772 | ADJUST SANITARY SEWER COVERS | Material | Lump Sum |  | 1
C00100566DB63_85020 | CONVERT/MOIDIFY EXIST STORM STRUCTURES | Material | Lump Sum |  | 1
C00100566DB63_09148 | EROS.CONTR.STONE CL.I EC-1 | Material | Lump Sum |  | 1
C00100566DB63_10128 | AGGR. BASE MATL. TY. I NO. 21B | Material | Lump Sum |  | 1
C00100566DB63_10610 | ASPHALT CONCRETE TY. IM-19.0A | Material | Lump Sum |  | 1
C00100566DB63_10611 | ASPHALT CONCRETE TY.IM-19.0D | Material | Lump Sum |  | 1
C00100566DB63_10628 | FLEXIBLE PAVE.PLANING 0"-2" | Material | Lump Sum |  | 1
C00100566DB63_10635 | ASPHALT CONCRETE TY. SM-9.5A | Material | Lump Sum |  | 1
C00100566DB63_10651 | ASPHALT CONCRETE TY. SMA-9.5 PG 76-22 | Material | Lump Sum |  | 1
C00100566DB63_10642 | ASPHALT CONCRETE TY. BM-25.0A | Material | Lump Sum |  | 1
C00100566DB63_11070 | NS SAW-CUT ASPH CONC FULL DEPTH | Material | Lump Sum |  | 1
C00100566DB63_10525 | MOT ASPHALT & WIDENING INCIDENTALS | Material | Lump Sum |  | 1
C00100566DB63_12020 | STD. CURB CG-2 | Material | Lump Sum |  | 1
C00100566DB63_12022 | RAD. CURB CG-2 | Material | Lump Sum |  | 1
C00100566DB63_12600 | STD. COMB. CURB & GUTTER CG-6 | Material | Lump Sum |  | 1
C00100566DB63_12610 | RAD. COMB. CURB & GUTTER CG-6 | Material | Lump Sum |  | 1
C00100566DB63_12940 | ENTRANCE GUTTER CG-9D | Material | Lump Sum |  | 1
C00100566DB63_13108 | CG-12 DETECTABLE WARNING SURFACE | Material | Lump Sum |  | 1
C00100566DB63_13212 | R/W MONUMENT RM-2 | Material | Lump Sum |  | 1
C00100566DB63_13245 | NS SIDEWALK- BRICK 5" WIDTH | Material | Lump Sum |  | 1
C00100566DB63_13240 | ASPHALT CONCRETE SHARED USE PATH | Material | Lump Sum |  | 1
C00100566DB63_13320 | GUARDRAIL GR-2 | Material | Lump Sum |  | 1
C00100566DB63_13331 | RADIAL GUARDRAIL GR-2 | Material | Lump Sum |  | 1
C00100566DB63_13345 | ALT.BREAKAWAY CABLE TERM.(GR-9) | Material | Lump Sum |  | 1
C00100566DB63_13392 | FIXED OBJECT ATTACH. GR-FOA-2 TY. I | Material | Lump Sum |  | 1
C00100566DB63_13462 | MEDIAN BARRIER MB-7F | Material | Lump Sum |  | 1
C00100566DB63_13530 | NS RETAINING WALL MOD. RW-2 | Material | Lump Sum |  | 1
C00100566DB63_13755 | SOUND BARRIER WALL | Material | Lump Sum |  | 1
C00100566DB63_13810 | MSE WALLS | Material | Lump Sum |  | 1
C00100566DB63_13604 | IMPACT ATTEN.SER.TY.1(TL-3,> 45 MPH) | Material | Lump Sum |  | 1
C00100566DB63_21020 | MEDIAN STRIP MS-1 | Material | Lump Sum |  | 1
C00100566DB63_22643 | FENCE FE-CL | Material | Lump Sum |  | 1
C00100566DB63_00104 | I-66/15_Design Services | Material | Lump Sum |  | 1
C00100566DB63_85011 | NS Wetland Mitigation Credits | Material | Lump Sum |  | 1
C00100566DB63_25507 | Modified Field Office Type I | Material | Lump Sum |  | 1
C00100566DB63_00108 | I-66/15_NS Environmental Monitoring | Material | Lump Sum |  | 1
C00100566DB63_54400 | PAVEMENT MESSAGE MARK. "ONLY" | Material | Lump Sum |  | 1
C00100566DB63_54404 | PAVE. MESSAGE MARK. R/R CROSSING | Material | Lump Sum |  | 1
C00100566DB63_54254 | PAVEMENT MESSAGE MARK. BICYCLE LANE SYM | Material | Lump Sum |  | 1
C00100566DB63_54402 | NS PAVE. MESSAGE MARK. 66 DIRECTION SYMBOL | Material | Lump Sum |  | 1
C00100566DB63_54403 | NS PAVE. MESSAGE MARK. 66 SYMBOL | Material | Lump Sum |  | 1
C00100566DB63_54217 | SNOW PLOW. RAISED PAVE. MARKER ASPH.CONC | Material | Lump Sum |  | 1
C00100566DB63_54032 | TY.B CL.I PAVE. LINE MARK. 4" | Material | Lump Sum |  | 1
C00100566DB63_54034 | TY.B CL.I PAVE. LINE MARK. 6" | Material | Lump Sum |  | 1
C00100566DB63_54040 | TY.B CL.I PAVE. LINE MARK. 12" | Material | Lump Sum |  | 1
C00100566DB63_54074 | TY.B CL.VI PAVE. LINE MARK CONTRAST 6" | Material | Lump Sum |  | 1
C00100566DB63_54076 | TY.B CL.VI PAVE. LINE MARK. 6" | Material | Lump Sum |  | 1
C00100566DB63_54078 | TY.B CL.VI PAVE. LINE MARK.12" | Material | Lump Sum |  | 1
C00100566DB63_27013 | TOPSOIL CLASS A | Material | Lump Sum |  | 1
C00100566DB63_27102 | REGULAR SEED | Material | Lump Sum |  | 1
C00100566DB63_27215 | FERTILIZER(15-30-15) | Material | Lump Sum |  | 1
C00100566DB63_27250 | LIME | Material | Lump Sum |  | 1
C00100566DB63_22653 | LINE BRACE UNIT FE-CL | Material | Lump Sum |  | 1
C00100566DB63_27103 | OVERSEEDING | Material | Lump Sum |  | 1
C00100566DB63_27546 | PLANTING AQUATIC BENCHES - PONDS 4-1 & 5-1 | Material | Lump Sum |  | 1
C00100566DB63_67090 | NS PED FENCE - ORNAMENTAL WIRE 6' | Material | Lump Sum |  | 1
C00100566DB63_64114 | H-PILE 12x53 | Material | Lump Sum |  | 1
C00100566DB63_64775 | H-PILE 12" POINTS | Material | Lump Sum |  | 1
C00100566DB63_61730 | STRUCTURAL STEEL BEAMS | Material | Lump Sum |  | 1
C00100566DB63_61731 | ERECT STRUCTURAL STEEL | Material | Lump Sum |  | 1
C00100566DB63_50575 | CONC. FOUND. O/H SIGN STRUCTURE | Material | Lump Sum |  | 1
C00100566DB63_50901 | O/H SIGN STRUCTURE LOC. NO. 1 | Material | Lump Sum |  | 1
C00100566DB63_50902 | O/H SIGN STRUCTURE LOC. NO. 2 | Material | Lump Sum |  | 1
C00100566DB63_50903 | O/H SIGN STRUCTURE LOC. NO. 3 | Material | Lump Sum |  | 1
C00100566DB63_50108 | SIGN PANEL | Material | Lump Sum |  | 1
C00100566DB63_50863 | REMOVE EXIST. SIGN STRUCT. TY-V-A | Material | Lump Sum |  | 1
C00100566DB63_50864 | REMOVE EXIST. SIGN STRUCT. TY-VI-A | Material | Lump Sum |  | 1
C00100566DB63_50867 | REMOVE/DISPOSE SIGN STR TY. WP-1 | Material | Lump Sum |  | 1
C00100566DB63_50868 | REMOVE/DISPOSE SIGN STR TY. WP-2 | Material | Lump Sum |  | 1
C00100566DB63_50490 | CONCRETE FOUNDATION STP-1 | Material | Lump Sum |  | 1
C00100566DB63_50502 | CONC. FOUND. 1'-9" X 4'-6" | Material | Lump Sum |  | 1
C00100566DB63_24160 | CONSTRUCTION SIGNS | Material | Lump Sum |  | 1
C00100566DB63_64100 | DYNAMIC PILE TEST | Material | Lump Sum |  | 1
C00100566DB63_55500 | LUMINAIRE DECORATIVE | Material | Lump Sum |  | 1
C00100566DB63_24152 | TYPE III BARRICADE 8' | Material | Lump Sum |  | 1
C00100566DB63_55186 | LIGHTING POLE DECORATIVE | Material | Lump Sum |  | 1
C00100566DB63_50430 | SIGN POST STP-1, 2" | Material | Lump Sum |  | 1
C00100566DB63_50432 | SIGN POST STP-1, 2-3/16" | Material | Lump Sum |  | 1
C00100566DB63_50434 | SIGN POST STP-1, 2-1/2" | Material | Lump Sum |  | 1
C00100566DB63_50404 | SIGN POST STEEL, 4" | Material | Lump Sum |  | 1
C00100566DB63_55140 | CONCRETE FOUNDATION LF-1 TY. A | Material | Lump Sum |  | 1
C00100566DB63_55348 | ELECT. SERVICE SE-6 | Material | Lump Sum |  | 1
C00100566DB63_55353 | CONTROL CENTER CCW-1 TYPE D | Material | Lump Sum |  | 1
C00100566DB63_24278 | GROUP 2 CHANNELIZING DEVICES | Material | Lump Sum |  | 1
C00100566DB63_24279 | PORT.CHANGEABLE MESS. SIGN | Material | Lump Sum |  | 1
C00100566DB63_24281 | ELECTRONIC ARROW | Material | Lump Sum |  | 1
C00100566DB63_24298 | MOT CLOSED CIRCUIT TV CAMERA RENTAL | Material | Lump Sum |  | 1
C00100566DB63_24287 | WARNING LIGHTS or B | Material | Lump Sum |  | 1
C00100566DB63_24260 | CR. RUN AGGR. NO. 25 OR 26 | Material | Lump Sum |  | 1
C00100566DB63_54522 | TEMP 24" STRIPING (STOP LINES) | Material | Lump Sum |  | 1
C00100566DB63_24290 | TRAF. BARR. SER. CONC. DOUBLE FACE | Material | Lump Sum |  | 1
C00100566DB63_51238 | CONC. FOUND. SIGNAL POLE PF-8 | Material | Lump Sum |  | 1
C00100566DB63_51240 | CONC. FOUNDATION PF-2 | Material | Lump Sum |  | 1
C00100566DB63_51247 | CONCRETE FOUND. CF-3 | Material | Lump Sum |  | 1
C00100566DB63_51540 | LOOP DETECTOR AMPLIFIER | Material | Lump Sum |  | 1
C00100566DB63_51598 | 8/3 CONDUCTOR CABLE | Material | Lump Sum |  | 1
C00100566DB63_51600 | 14/2 CONDUCTOR CABLE | Material | Lump Sum |  | 1
C00100566DB63_51607 | 14/7 CONDUCTOR CABLE | Material | Lump Sum |  | 1
C00100566DB63_51615 | 14/1 ENCLOSED COND. CABLE | Material | Lump Sum |  | 1
C00100566DB63_51700 | 14/2 CONDUCTOR CABLE SHIELDED | Material | Lump Sum |  | 1
C00100566DB63_51715 | PREEMPTION CABLE | Material | Lump Sum |  | 1
C00100566DB63_51730 | SPAN WIRE 1/2" | Material | Lump Sum |  | 1
C00100566DB63_51735 | TETHER WIRE, 1/4" | Material | Lump Sum |  | 1
C00100566DB63_51824 | HANGER ASSEMBLY SW-1, ONE WAY | Material | Lump Sum |  | 1
C00100566DB63_51830 | HANGER ASSEMBLY SM-3, ONE WAY | Material | Lump Sum |  | 1
C00100566DB63_51838 | HANGER ASSM.SMB-3, ONE WAY | Material | Lump Sum |  | 1
C00100566DB63_51912 | SAW CUT 3/8" | Material | Lump Sum |  | 1
C00100566DB63_51913 | SAW CUT 5/8" | Material | Lump Sum |  | 1
C00100566DB63_51137 | INSTALL CONTROLLER | Material | Lump Sum |  | 1
C00100566DB63_51170 | ELECTRICAL SERVICE SE-5 | Material | Lump Sum |  | 1
C00100566DB63_51184 | TRAF. SIG. HEAD SEC 12" LED | Material | Lump Sum |  | 1
C00100566DB63_51198 | PEDESTRIAN ACTUATION PA-2 | Material | Lump Sum |  | 1
C00100566DB63_51212 | PEDESTAL POLE PF-2 12' | Material | Lump Sum |  | 1
C00100566DB63_51282 | SIGNAL POLE MP-2 36' | Material | Lump Sum |  | 1
C00100566DB63_51332 | SIG. POLE MP-1 20' ONE ARM 45' | Material | Lump Sum |  | 1
C00100566DB63_51347 | SIG. POLE MP-1 20' ONE ARM 60' | Material | Lump Sum |  | 1
C00100566DB63_51348 | SIG. POLE MP-1 20' ONE ARM 70' | Material | Lump Sum |  | 1
C00100566DB63_51349 | SIG. POLE MP-1 20' ONE ARM 75' | Material | Lump Sum |  | 1
C00100566DB63_55586 | JUNCTION BOX JB-S1 | Material | Lump Sum |  | 1
C00100566DB63_55588 | JUNCTION BOX JB-S3 | Material | Lump Sum |  | 1
C00100566DB63_55580 | JUNCTION BOX JB-R1 | Material | Lump Sum |  | 1
C00100566DB63_55581 | JUNCTION BOX JB-R2 | Material | Lump Sum |  | 1
C00100566DB63_55587 | JUNCTION BOX JB-S2 | Material | Lump Sum |  | 1
C00100566DB63_56026 | 1 1/4" METAL CONDUIT | Material | Lump Sum |  | 1
C00100566DB63_56022 | 1" METAL CONDUIT | Material | Lump Sum |  | 1
C00100566DB63_56030 | 2" CONDUIT | Material | Lump Sum |  | 1
C00100566DB63_56034 | 3" CONDUIT | Material | Lump Sum |  | 1
C00100566DB63_56038 | 4" CONDUIT | Material | Lump Sum |  | 1
C00100566DB63_56052 | BORED CONDUIT 4" | Material | Lump Sum |  | 1
C00100566DB63_56200 | TRENCH EXCAVATION ECI-1 | Material | Lump Sum |  | 1
C00100566DB63_56205 | TEST BORE | Material | Lump Sum |  | 1
C00100566DB63_55020 | 2 CONDUCTOR CABLE | Material | Lump Sum |  | 1
C00100566DB63_55060 | 6 CONDUCTOR CABLE | Material | Lump Sum |  | 1
C00100566DB63_55080 | 8 CONDUCTOR CABLE | Material | Lump Sum |  | 1
C00100566DB63_56014 | ELECT. SER. GRD. ELECTRODE(10') | Material | Lump Sum |  | 1
C00100566DB63_60404 | CONCRETE CLASS A4 SUPERSTR | Material | Lump Sum |  | 1
C00100566DB63_60490 | BRIDGE DECK GROOVING | Material | Lump Sum |  | 1
C00100566DB63_60450 | CONC CL. A4 BRIDGE APPR SLAB | Material | Lump Sum |  | 1
C00100566DB63_60452 | REINF STEEL BRIDGE APPR SLAB | Material | Lump Sum |  | 1
C00100566DB63_62491 | ELASTOMERIC EXPANSION DAM 0-2" | Material | Lump Sum |  | 1
C00100566DB63_62048 | BRIDGE RAILING BR-27D 3-RAILS | Material | Lump Sum |  | 1
C00100566DB63_62046 | BRIDGE RAILING BR-27D 1-RAIL | Material | Lump Sum |  | 1
C00100566DB63_64011 | STRUCTURE EXCAVATION | Material | Lump Sum |  | 1
C00100566DB63_65013 | CONCRETE CLASS A3 SUBSTR | Material | Lump Sum |  | 1
C00100566DB63_65200 | REINF. STEEL - ALL BRIDGE | Material | Lump Sum |  | 1
C00100566DB63_67900 | DISM&REM EXIST STR NO. 19816 | Material | Lump Sum |  | 1
C00100566DB63_65204 | CORR RESIST RESTEEL CL. I ALL BRIDGE | Material | Lump Sum |  | 1
C00100566DB63_51951 | INSTALL SIGN | Material | Lump Sum |  | 1
C00100566DB63_51955 | TEMPORARY TRAFFIC CONTROL SIGNAL | Material | Lump Sum |  | 1
C00100566DB63_51956 | EMERGENCY PREEMPTION | Material | Lump Sum |  | 1
C00100566DB63_51957 | REMOVE EXIST. SIGNAL EQUIPMENT | Material | Lump Sum |  | 1
C00100566DB63_52404 | PEDESTRIAN SIGNAL HEAD SP-9 | Material | Lump Sum |  | 1
C00100566DB63_67051 | ARCHITECTURAL TREATMENT BRIDGE | Material | Lump Sum |  | 1
C00100566DB63_69740 | CONCRETE SLAB SLOPE PROTECTION 4" | Material | Lump Sum |  | 1
C00100566DB63_85154 | STREET SWEEPING OR VACUUMING | Material | Lump Sum |  | 1
C00100566DB63_27400 | EROSION CONTROL MAINTENANCE CREW | Material | Lump Sum |  | 1
C00100566DB63_24100 | ALLAYING DUST | Material | Lump Sum |  | 1
C00100566DB63_27580 | TEMP. SEDIMENT BASIN EXCAVATION | Material | Lump Sum |  | 1
C00100566DB63_50009 | MOT SERVICE CREW | Material | Lump Sum |  | 1
C00100566DB63_24282 | FLAGGER SERVICE | Material | Lump Sum |  | 1
C00100566DB63_22677 | GATE FE-CL L=14' | Material | Lump Sum |  | 1
C00100566DB63_22663 | CORNER BRACE UNIT FE-CL | Material | Lump Sum |  | 1
C00100566DB63_CO1 | I-66/15_Change Order #1 | Material | Lump Sum |  | 1
C00100566DB63_Rd Cre | Earthwork Crew #1 | Labor |  |  | 1
C00100566DB63_STONE | Roadway Crew | Labor |  |  | 1
C00100566DB63_STR1 | Structure Crew #1 | Labor |  |  | 1
C00100566DB63_SUB_DR | Sub Drainage Crew | Labor |  |  | 1
C00100566DB63_SUB_PV | Sub Paving Crew | Labor |  |  | 1
C00100566DB63_SC_Sgn | Sub Signals | Labor |  |  | 1
C00100566DB63_SC_SND | Sub Soundwall | Labor |  |  | 1
C00100566DB63_SC_CON | Sub Concrete | Labor |  |  | 1
C00100566DB63_SC_BF | Sub Bridge Fence | Labor |  |  | 1
C00100566DB63_EXC | Excavator | Nonlabor |  |  | 1
C00100566DB63_DZR | Dozer | Nonlabor |  |  | 1
C00100566DB63_GDR | Grader | Nonlabor |  |  | 1
C00100566DB63_SBX | Stone Box | Nonlabor |  |  | 1
C00100566DB63_LGCR | Large Crane | Nonlabor |  |  | 1
C00100566DB63_HYDCR | Hydraulic Crane | Nonlabor |  |  | 1
C00100566DB63_FORM | Bridge Forms - Reusable | Material | Lump Sum |  | 1
C00100566DB63_FMLR | Form Liner - Reusable | Material | Lump Sum |  | 1
C00100566DB63_STR2 | Structure Crew #2 | Labor |  |  | 1
3319 | 3319 - Oceana | Nonlabor |  |  | 1
9131 | 9131 - Rte 29 Solutions | Nonlabor |  |  | 1
3230 | 3230 - IH-35W Tarrent County | Nonlabor |  |  | 1
3263 | 3263 - Bexar County - IH-35 | Nonlabor |  |  | 1
3304 | 3304 - SR50 from 429 to West Oaks | Nonlabor |  |  | 1
3325 | 3325 - SR 408 / SR 417 Interchange | Nonlabor |  |  | 1
3269 | 3269 - Dupo Levee | Nonlabor |  |  | 1
3341 | 3341 - O'Hare Taxiway NN | Nonlabor |  |  | 1
3334 | 3334 - Innovation Way - Cost / Revenue | Nonlabor |  |  | 1
C00100566DB63_Root | I-66 / Route 15 Interchange Resources | Material |  |  | 1
C00100566DB63_CON | I-66/15_Construction | Material | Lump Sum |  | 1
CL | Cost Loading | Material |  |  | 8
SUB-ST-TB | Sub - Piles Tie-back Crew | Labor |  |  | 1
SUB-QC | Sub - QA/QC | Labor |  |  | 1
SUB-ST-RAILING | Sub - Bridge Railing Crew | Labor |  |  | 1
3308 | 3308 - CH2M Mopac Improvements | Nonlabor |  |  | 1
Mopac-1 | Mopac Project | Nonlabor |  |  | 1
GFI | GFI - Parent | Nonlabor |  |  | 1
Subcontractors | Subcontractors | Labor |  |  | 1
MIP | MOPAC Improvement Project | Labor |  |  | 1
ML | Manlift | Nonlabor |  |  | 1
SS | Steel Subcontractor | Labor |  |  | 1
WNY | Washington Navy Yard | Nonlabor |  |  | 1
MIP SC | MIP Subcontractors | Labor |  |  | 1
MIP LB | MIP Labor | Labor |  |  | 1
MIP EQ | MIP Equipment | Nonlabor |  |  | 1
WT | WT COST | Labor
MIPSCAARON-2 | Aaron Concrete Misc Concrete Crew | Labor |  |  | 6
MIPSCFLASHER | Flasher | Labor |  |  | 7
MIPSCRAMMING | Ramming / Austin Mat'ls Paving Crew | Labor |  |  | 15
LC | Labor Crew - 1 Foreman, 4 Laborers | Labor |  |  | 5
CC | Carpenter Crew - 1 Foreman, 5 Carpenters, 1 Operator | Labor |  |  | 7
DC LG | Dirt Crew Large - 1 Foreman, 5 Operators, 1 Laborer | Labor |  |  | 7
LD | Loader | Nonlabor |  |  | 1
DZ | Dozer | Nonlabor |  |  | 1
RL2 | Roller - Sheeps Foot | Nonlabor |  |  | 1
RL3 | Roller - Pneumatic | Nonlabor |  |  | 1
EX1 | Excavator - Small | Nonlabor |  |  | 1
EX2 | Excavator - Large | Nonlabor |  |  | 1
GD | Motor Grader | Nonlabor |  |  | 1
DC SM | Dirt Crew Small - 1 Foreman, 2 Operators, 1 Laborer | Labor |  |  | 4
MIPSCAARON-1 | Aaron Concrete T-551 Crew | Labor |  |  | 5
MIPSCAARON-3 | Aaron Concrete Milling Crew | Labor |  |  | 3
BHH | Backhoe w/ Hammer | Nonlabor |  |  | 1
MIPSCMORALES | Morales (Electricians) | Labor |  |  | 4
MIPSCSDP | Scott Derr Painting Crew | Labor |  |  | 3
MIPSCTT | Tetra Tech Asbestos Abatement Crew | Labor |  |  | 6
CSB | Barrier Crew - 1 Foreman, 2 Operators, 2 Laborers | Labor |  |  | 5
MIPSCRVI | RVI - Royal Vista | Labor |  |  | 5
MIPSCRAMMINGP | Ramming / Austin Mat'ls Prime Crew | Labor |  |  | 1
MIPSCMBGF | MBGF Removal/Installation Crew | Labor |  |  | 4
R-1 | Demo Crew Small - 1 Operator, 1 Laborer | Labor |  |  | 2
MIPSCAARON4 | Aaron Dirt Crew | Labor |  |  | 5
MIPSCCMCAPS | C&M DS Cap Crew | Labor |  |  | 4
MIPSCCMPNP | C&M Post & Panel Crew | Labor |  |  | 5
MIPSCINCLINE | Incline - Drilled Shaft Crew | Labor |  |  | 5
9700-3341 | Ohare NN | Material |  |  | 1
97-001 | REINFORCED CONCRETE PIPE - TYPE 12", CLASS IV | Material
97-002 | UNDERDRAIN PIPE, 8" SCH 40 PVC, PERFORATED | Material |  |  | 8
97-003 | UNDERDRAIN PIPE, 8" SCH 40 PVC | Material |  |  | 8
97-004 | INSPECTION HOLE - TO BE ADJUSTED | Material | Each |  | 8
97-005 | INSPECTION HOLE | Material | Each |  | 8
97-006 | MANHOLE, ADJUST TO GRADE | Material | Each |  | 8
97-012 | LIGHTING-TAXIWAY, L-867 SURFACE MOUNTED BASE CAN WITH L-861T LED ELEVATED TAXIWAY EDGE LIGHT, COMPLE | Material | Each |  | 8
97-007 | CATCH BASIN | Material | Each |  | 8
97-008 | LIGHTING - TAXIWAY, TYPE 1 MARKER LIGHT BASE WITH L- 86IT LED ELEVATED EDGE LIGHT, COMPLETE | Material | Each |  | 8
97-009 | LIGHTING - TAXIWAY, TYPE 1 MARKER LIGHT BASE WITH STEEL COVER, COMPLETE | Material | Each |  | 8
97-011 | LIGHTING - TAXIWAY, L-868 BASE CAN WITH L-852A LED IN- PAVEMENT TAXIWAY CENTERLINE LIGHT, COMPLETE | Material | Each |  | 8
97-010 | LIGHTING-TAXIWAY, REMOVE AND REPLACE L-86IT LED ELEVATED EDGE LIGHT, FIXTURE AND TRANSFORMER ONLY | Material | Each |  | 8
97-013 | LIGHTING - RUNWAY, L-868 BASE CAN WITH L-852G LED IN- PAVEMENT RUNWAY GUARD LIGHT, COMPLETE | Material | Each |  | 8
97-014 | LIGHTING SYSTEMS - NEW L-858 – LED GUIDANCE SIGN WITH NEW BASE, 3 MODULE(S), SIZE 3, COMPLETE | Material | Each |  | 8
97-015 | POWER CABLE - L-824, TYPE C 5KV, 1/C, SIZE 6 AWG | Material |  |  | 8
97-016 | POWER CABLE - L-824, 600V, 1/C, SIZE 10 AWG | Material |  |  | 8
97-017 | COUNTERPOISE WIRE - 1/C, SIZE 6 AWG, 600V, BARE COPPER | Material |  |  | 8
97-018 | CONCRETE ENCASED DUCTS, 1-WAY, 2" PVC | Material |  |  | 8
97-019 | CONCRETE ENCASED DUCTS, 1-WAY, 2" PVC - SAWKERF | Material |  |  | 8
97-020 | CONCRETE ENCASED DUCTS, 2-WAY, 3" PVC | Material |  |  | 8
97-021 | SURFACE MOUNTED DUCTD, 1-WAY, 1" GRS | Material |  |  | 8
97-022 | MOBILIZATION (TOTAL PRICE FOR MOBILIZATION MUST NOT TO EXCEED 6% OF TOTAL BASE BID) | Material | Lump Sum |  | 8
97-023 | SUPPLEMENTAL TRAFFIC CONTROL AND SAFETY MEASURES | Material | Dollar |  | 8
97-024 | ALLOWANCE FOR SECURITY GUARD INFRASTRUCTURES | Material | Dollar |  | 8
97-025 | STANDBY TIME | Material | Dollar |  | 8
97-026 | PAVEMENT REMOVAL - PCC | Material |  |  | 8
97-027 | PAVEMENT REMOVAL - BITUMINOUS CONCRETE | Material |  |  | 8
97-028 | UNCLASSIFIED EXCAVATION | Material | Cubic Yard |  | 8
97-029 | ALLOWANCE FOR UNCLASSIFIED EXCAVATION, CONTAMINATED MATERIAL | Material | Dollar |  | 8
97-030 | EXCAVATING-UNDERCUT AND BACKFILL WITH CRUSHED STONE | Material | Cubic Yard |  | 8
97-031 | FROST PROTECTION COURSE, CA-6 | Material | Cubic Yard |  | 8
97-032 | FROST PROTECTION COURSE, RCB | Material | Cubic Yard |  | 8
97-033 | INLET AND PIPE PROTECTION | Material | Each |  | 8
97-034 | SEDIMENT LOG AND GEOSYNTHETIC CHECK STRUCTURE | Material | Each |  | 8
97-035 | POLYMERS | Material |  |  | 8
97-036 | EROSION CONTROL BLANKET | Material |  |  | 8
97-037 | SEDIMENT CONTAINMENT FILTER BAG | Material | Each |  | 8
97-038 | TEMPORARY SEEDING | Material |  |  | 8
97-039 | SILT FENCE | Material |  |  | 8
97-040 | STABILIZED CONSTRUCTION ENTRANCE/EXIT | Material |  |  | 8
97-041 | UNFORSEEN EROSION CONTROL MEASURES | Material | Dollar |  | 8
97-042 | BITUMINOUS CONCRETE SURFACE COURSE, FAA | Material |  |  | 8
97-043 | ASPHALT TREATED PERMEABLE BASE COURSE | Material |  |  | 8
97-044 | BITUMINOUS CONCRETE BASE COURSE, IDOT | Material |  |  | 8
97-045 | BITUMINOUS CONCRETE SURFACE COURSE, IDOT | Material |  |  | 8
97-046 | PORTLAND CEMENT CONCRETE PAVEMENT, 19" | Material |  |  | 8
97-047 | BITUMINOUS CONCRETE - PRIME COAT | Material |  |  | 8
97-048 | BITUMINOUS CONCRETE - TACK COAT | Material |  |  | 8
97-049 | SCARIFICATION -BITUMINOUS CONCRETE - 3" | Material |  |  | 8
97-050 | SCARIFICATION -BITUMINOUS CONCRETE - 2" | Material |  |  | 8
97-051 | SCARIFICATION -BITUMINOUS CONCRETE - 0"- 2" | Material |  |  | 8
97-052 | SCARIFICATION - PORTLAND CEMENT CONCRETE - 3" | Material |  |  | 8
97-053 | SCARIFICATION - PORTLAND CEMENT CONCRETE - 0"-3" | Material |  |  | 8
97-054 | PAVEMENT MARKING - TEMPORARY | Material |  |  | 8
97-055 | PAVEMENT MARKING - PERMANENT | Material |  |  | 8
97-056 | PAVEMENT MARKING - REMOVAL | Material |  |  | 8
97-057 | SAW CUT AND SEAL, 2" | Material |  |  | 8
97-058 | SEEDING, PERMANENT | Material |  |  | 8
97-059 | TOPSOILING, 4" | Material |  |  | 8
97-060 | DEMOLITION | Material | Lump Sum |  | 8
97-061 | ALLOWANCE FOR UTILITY CONFLICTS AND UNFORESEEN CONDITIONS | Material | Dollar |  | 8
FL Revenue | Florida Cost / Revenue | Nonlabor |  |  | 0
Mopac-2 | Mopac Project | Nonlabor |  |  | 1
Mopac | Mopac Project | Nonlabor |  |  | 1
Lane CIP | Lane CIP | Labor |  |  | 1
SH360 | SH360 PBS2 | Material |  |  | 8
360.Utility | Utility Cost | Material |  |  | 8
360.AM | Access Midstream | Material |  |  | 8
A2 | Development Design, Design Survey, & Landscape Design | Material | Lump Sum |  | 6
A3-1 | Environmental Permitting Activities | Material | Lump Sum |  | 8
A4 | Utility Locates, Utility Survey, and Utility Adjustment Design | Material | Lump Sum |  | 8
A5-1 | Design Quality Assurance, Construction Quality Acceptance Firm, and Environmental Compliance Team | Material | Lump Sum |  | 8
A6 | Right-of-Way Acquisition Service and ROW Survey/Mapping | Material | Lump Sum |  | 8
B9 | Construction Development Management | Material | Lump Sum |  | 8
B10 | Mobilization | Material | Lump Sum |  | 8
B11 | Traffic Control | Material | Lump Sum |  | 8
B12 | Removals | Material | Lump Sum |  | 8
B13 | Prep ROW | Material | Lump Sum |  | 8
B14 | Earthwork | Material | Lump Sum |  | 8
B15 | Subbase and Base Course | Material | Lump Sum |  | 8
B16 | Pavement | Material | Lump Sum |  | 8
B17 | Permanent Structures | Material | Lump Sum |  | 8
B18 | Temporary Structures | Material | Lump Sum |  | 8
B19 | Drainage | Material | Lump Sum |  | 8
B20 | Lighting | Material | Lump Sum |  | 8
B21 | Traffic Signals | Material | Lump Sum |  | 8
B22 | Signing | Material | Lump Sum |  | 8
B23 | Pavement Markings | Material | Lump Sum |  | 8
B24 | Aesthetics | Material | Lump Sum |  | 8
B25 | Landscaping | Material | Lump Sum |  | 8
B26 | Environmental Mitigation | Material | Lump Sum |  | 8
B27 | Utility Adjustments | Material | Lump Sum |  | 8
B28 | Electronic Communications | Material | Lump Sum |  | 8
B29 | Bond Premiums | Material | Lump Sum |  | 8
B30 | Insurance Premiums | Material | Lump Sum |  | 8
B31 | Miscellaneous Construction Items Not Covered by Lines 9-30 | Material | Lump Sum |  | 8
A1 | Professional Services Development Management & Community Outreach | Material | Lump Sum |  | 8
OPT3 | Option 3 | Material | Lump Sum |  | 8
Emb-1 | Rdwy Embankment | Material | Cubic Yard |  | 8
Excav-1 | Rdwy Excavation | Material | Cubic Yard |  | 8
lane-crews-- | Lane Crews | Labor |  |  | 1
SUB | Sub | Labor |  |  | 1
C0 | Change Orders | Material | Lump Sum |  | 8
CO 01 | Change order 01 - Cross Slope reduction | Material | Lump Sum |  | 8
CO 02 | Change order 02 - Change in fiber optic cables | Material | Lump Sum |  | 8
CO 03 | Change order 03 - Matlock Crossing revisions | Material | Lump Sum |  | 8
CO 05 | Change order 05 - Holland Stubout removal | Material | Lump Sum |  | 8
CO 06 | Change order 06 - USACE permit (Design only) | Material | Lump Sum |  | 8
CO 07 | Change order 07 - TRWD additional cost | Material | Lump Sum |  | 8
Cost Redist | Redistribution of Costs | Material | Lump Sum |  | 8
SUB-ST-GROOVE | Sub - Bridge Deck Grooving Crew | Labor |  |  | 1
SUB-ST-PARAPET | Sub - Parapet Wall Crew | Labor |  |  | 1
5400558-A-103 | PP03(A) - Partnering | Material | Lump Sum |  | 1
5400558-A-110 | PP03(A) - Design | Material | Lump Sum |  | 1
5400558-A-152 | PP03(A) - Construction Survey and Staking | Material | Lump Sum |  | 1
5400558-A-154 | PP03(A) - Contractor QA/QC & Testing | Material | Lump Sum |  | 1
5400558-A-155 | PP03(A) - Schedule | Material | Lump Sum |  | 1
5400558-A-0250-25101 | PP03(A) - Slope Reinforcement and Retaining Walls - Rip Rap Class III | Material | Cubic Yard |  | 1
5400558-A-300 | PP03(A) - Aggregate Courses | Material |  |  | 1
3230-1 | IH-35W Tarrant Cty | Nonlabor |  |  | 0
3230-2 | Drainage Crew # 1 | Labor |  |  | 0
3230-3 | Drainage Crew # 2 | Labor |  |  | 0
3230-4 | Bridge Crew # 1 | Labor |  |  | 0
3230-5 | Bridge Crew # 2 | Labor |  |  | 0
3230-6 | Bridge Crew # 3 | Labor |  |  | 0
3230-7 | RE Wall # 1 | Labor |  |  | 1
3230-8 | Dirt Crew # 1 | Labor |  |  | 0
3230-9 | Dirt Crew # 2 | Labor |  |  | 0
3230-10 | Lime Crew # 1 | Labor |  |  | 0
3230-12 | Flex Base Crew # 1 | Labor |  |  | 0
3230-13 | Lindamood Demo | Labor |  |  | 0
3230-14 | Foundation Drillers (Drill Shafts) | Labor |  |  | 0
3230-15 | Forston Contraction (MBGF) | Labor |  |  | 0
3230-16 | Danridge Construction (Jack & Bore) | Labor |  |  | 0
3230-17 | Antigo Construction (PVMT BRKING) | Labor |  |  | 0
3230-18 | Mica Corporation (Signs, Light, Elec.) | Labor |  |  | 0
3230-19 | Webber Barrier Services (Perm Barrier) | Labor |  |  | 0
3230-21 | Farr Foundation (Temp Shoring) | Labor |  |  | 0
3230-22 | Choctaw Erectors (STR STL) | Labor |  |  | 0
3230-23 | Milling Crew # 1 | Labor |  |  | 1
3230-24 | Demolition Crew # 1 | Labor |  |  | 0
3230-27 | HMAC Crew # 1 | Labor |  |  | 0
3230-28 | Barrier Crew # 1 | Labor |  |  | 0
3230-29 | Concrete Crew | Labor |  |  | 0
3230-30 | CEN (Inlets) | Labor |  |  | 0
3230-32 | Traffic Crew # 1 | Labor |  |  | 0
3230-33 | Lime Crew # 2 | Labor |  |  | 0
3230-35 | Drainage Crew # 3 | Labor |  |  | 0
3230-36 | CAT RM 500 | Nonlabor |  |  | 0
3230-37 | CAT 426 BACKHOE | Nonlabor |  |  | 0
3230-38 | JD 595 | Nonlabor |  |  | 0
3230-39 | BID WELL DECK MACHINE | Nonlabor |  |  | 0
3230-42 | 60TN CRANE | Nonlabor |  |  | 0
3230-43 | D4 DOZER | Nonlabor |  |  | 0
3230-44 | D5 DOZER | Nonlabor |  |  | 0
3230-45 | D6 DOZER | Nonlabor |  |  | 0
3230-46 | CAT 330 | Nonlabor |  |  | 0
3230-47 | CAT 345 | Nonlabor |  |  | 0
3230-48 | CAT 140 GRADER | Nonlabor |  |  | 0
3230-49 | CAT 928 LOADER | Nonlabor |  |  | 0
3230-50 | CAT 950 LOADER | Nonlabor |  |  | 0
3230-51 | CAT 963 TRACK LOADER | Nonlabor |  |  | 0
3230-53 | 40' MAN LIFT | Nonlabor |  |  | 0
3230-54 | 84" ROLLER ICS | Nonlabor |  |  | 0
3230-55 | 84" ROLLER / COMPACTOR | Nonlabor |  |  | 0
3230-56 | SAKAI 48" ROLLER | Nonlabor |  |  | 0
3230-57 | 48" WALK BEHIND | Nonlabor |  |  | 0
3230-58 | CAT 615 | Nonlabor |  |  | 0
3230-59 | BOOM TRUCK | Nonlabor |  |  | 0
3230-60 | Water Truck | Nonlabor |  |  | 0
3230-63 | Belly Dumps | Nonlabor |  |  | 0
3230-64 | Concrete Placer | Nonlabor |  |  | 0
3230-65 | Round Column Forms | Nonlabor |  |  | 0
3230-66 | Rect Column Forms | Nonlabor |  |  | 0
3230-67 | Cap Forms | Nonlabor |  |  | 0
3230-68 | Pump Truck | Nonlabor |  |  | 0
3230-69 | Davis Crane | Nonlabor |  |  | 0
3230-70 | Bridge Work Decks | Nonlabor |  |  | 0
3230-71 | CAT 623 Scraper | Nonlabor |  |  | 0
3230-72 | Pneumatic Roller 25tn | Nonlabor |  |  | 0
3230-73 | 54" Compactor | Nonlabor |  |  | 0
3230-74 | 815 Compactor | Nonlabor |  |  | 0
3230-75 | Power Curber | Nonlabor |  |  | 0
3230-76 | Shore Tower Forms | Nonlabor |  |  | 0
3230-77 | Jackson Consturction | Labor |  |  | 0
3230-78 | Enterprise | Labor |  |  | 0
3230-79 | Atmos | Labor |  |  | 0
3230-80 | AT & T | Labor |  |  | 0
3230-81 | Oncor | Labor |  |  | 0
3230-83 | Fiberlight | Labor |  |  | 0
3230-84 | Charter | Labor |  |  | 0
3230-85 | 980 Loader | Nonlabor |  |  | 0
3230-$$$ | IH-35W - Revenue $ Loading | Material |  |  | 1
SUB.ST-TS | Sub - Temp Shoring Crew | Labor |  |  | 1
PBS 5 | PBS 5 Interim Adjustments | Material | Lump Sum |  | 8
C00108069DB87-PROJEC | PROJECT RESOURCES | Labor |  |  | 1
C00108069DB87-JOB SP | Job Specific Resources | Labor |  |  | 1
C00108069DB87-3332 | 3332 - BRT Richmond | Nonlabor |  |  | 1
3230-11 | IH-35W Tarrant Cty | Nonlabor |  |  | 0
3230-20 | IH-35W Tarrant Cty | Nonlabor |  |  | 0
Rev | Revenue | Nonlabor |  |  | 0
3315-44 | Granite City | Nonlabor |  |  | 0
3304-1 | 3304 Resources | Nonlabor |  |  | 1
3304 Crews | 3304 Crews | Nonlabor |  |  | 1
3304-Cr-Drainage | Drainage Crew | Labor |  |  | 0
3304-Cr-Pile | Pile Crew | Labor |  |  | 0
3304-Cr-Struct | Structure Crew | Labor |  |  | 0
3304-Cr-Earthwork | Earthwork Crew | Labor |  |  | 0
3304-Cr-Grade | Grading Crew | Labor |  |  | 0
3289 | 3289 - FM 973 | Nonlabor |  |  | 1
3289-1 | 3289 FM 973 | Material |  |  | 8
3289.110.2001 | Excavation (Roadway) | Material | Cubic Yard |  | 8
3289.132.2003 | Embankment (Final) (Ord Comp)(TyB) | Material | Cubic Yard |  | 8
3289.160.2003 | Furnishing And Placing Topsoil (4") | Material |  |  | 8
3289.247.2366 | Fl BS (Cmp In Plc)(Ty A Gr 5)(Fnal Pos) | Material | Cubic Yard |  | 8
3289.260.2002 | Lime (Hydrated Lime(Slurry)) | Material |  |  | 8
3289.260.2027 | Lime trt (Exist Mtal)(8") | Material |  |  | 8
3289.310.2005 | Prime Coat (MC-30 or AEP) | Material |  |  | 8
3289.402.2001 | Trench Excavation Protection | Material |  |  | 8
3289.403.2001 | Temporary Spl Shoring | Material |  |  | 8
3289.416.2004 | Drill Shaft (36in) | Material |  |  | 8
3289.416.2006 | Drill Shaft (48in) | Material |  |  | 8
3289.420.2003 | Cl C Conc (Abut) | Material | Cubic Yard |  | 8
3289.420.2004 | CL C Conc (Bent) | Material | Cubic Yard |  | 8
3289.420.2033 | Cl S Conc (Appr Slab) | Material | Cubic Yard |  | 8
3289.422.2001 | Reinf Conc Slab | Material |  |  | 8
3289.423.2001 | Retaining Wall (Mse) | Material |  |  | 8
3289.425.2068 | Prestr Conc Girder (Tx54) | Material |  |  | 8
3289.432.2002 | Rip Rap (Conc) (5In) | Material | Cubic Yard |  | 8
3289.454.2001 | Sealed Expansion Joint (4in)(Sej-A) | Material |  |  | 8
3289.464.2003 | RC Pipe (Cl III) (18 In) | Material |  |  | 8
3289.464.2005 | RC Pipe (Cl III) (24 In) | Material |  |  | 8
3289.464.2007 | RC Pipe (Cl III) (30 In) | Material |  |  | 8
3289.464.2010 | RC Pipe (Cl III) (42 In) | Material |  |  | 8
3289.464.2011 | RC Pipe (Cl III) (48 In) | Material |  |  | 8
3289.465.2003 | Inlet (Comp) (Ty H) | Material |  |  | 8
3289.465.2014 | Manh (Compl) (Junct Box) | Material |  |  | 8
3289.465.2290 | Inlet (Compl) (Curb) (Ty 1) (15') | Material |  |  | 8
3289.496.2010 | Remov Str (Bridge 100-499 Ft Length) | Material |  |  | 8
3289.508.2002 | Constructing Detours | Material |  |  | 8
3289.512.2048 | Port Ctb (Furn & Inst) (F-Shape) (Ty 1) | Material |  |  | 8
3289.512.2050 | Port Ctb (Move) (F-shape) ( Ty 1) | Material |  |  | 8
3289.529.2003 | Conc Curb & Gutter Ty 1 | Material |  |  | 8
3289.531.2005 | Curb Ramps (Ty 1) | Material |  |  | 8
3289.531.2016 | Conc Sidewalks (6') | Material |  |  | 8
3289.531.2041 | Curb Ramps ( Ty 10) | Material |  |  | 8
3289.545.2050 | Crash Cush Atten (Move&Reset) (Work Zone) | Material |  |  | 8
3289.545.2051 | Crash Cush Atten (Remove) (Work Zone) | Material |  |  | 8
3289.545.2095 | Crash Cush Atten (Instl)(S)(N)(TL3) | Material |  |  | 8
3289.3268.2008 | D-GR HMA Ty B Pg64-22 | Material |  |  | 8
3289.3268.2029 | D-GR HMA Ty-C Sac-A PG76-22 | Material |  |  | 8
3289.466.2051 | Wingwall (Pw) (Hw=7Ft) | Material |  |  | 8
3289.466.2054 | Wingwall (Pw) (Hw=10ft) | Material |  |  | 8
3289.466.2290 | Wingwall (Pw) (HW=10.5 Ft) | Material |  |  | 8
3289.540.2001 | Mtl W-Beam Gd Fen (Tim Post) | Material |  |  | 8
3289.432.2021 | Rip Rap Ston Protection 18 In | Material | Cubic Yard |  | 8
3289.432.2039 | Rip Rap Mow Strip 4 In | Material | Cubic Yard |  | 8
3289.442.2048 | Structural Steel (Misc Non-Bridge) | Material |  |  | 8
3289.462.2009 | Conc Box Culv ( 5 Ft x 5 Ft) | Material |  |  | 8
3289.462.2023 | Conc Box Culv (8 Ft x 8 Ft) | Material |  |  | 8
3289.450.2025 | Rail ( Ty PR1) | Material |  |  | 8
3289.450.2143 | Railing ( Ty T551) | Material |  |  | 8
3289.450.2146 | Rail ( Ty T552) | Material |  |  | 8
3289.440 | Reinforcing Steel | Material |  |  | 8
C00077383DB80_Root | Rte 29 Solutions Resources | Material |  |  | 1
C00077383DB80_00104 | Project Design | Material | Lump Sum |  | 1
C00077383DB80_85130 | PERFORMANCE AND PAYMENT BONDS | Material | Lump Sum |  | 1
C00077383DB80_NS1 | INSURANCE | Material | Lump Sum |  | 1
C00077383DB80_001071 | Dry Utility Relocations - Rio Road Intersection | Material | Lump Sum |  | 1
C00077383DB80_25593 | QUALITY CONTROL | Material | Lump Sum |  | 1
C00077383DB80_25595 | QUALITY ASSURANCE | Material | Lump Sum |  | 1
C00077383DB80_001072 | Dry Utility Relocations - Route 29 Widening | Material | Lump Sum |  | 1
C00077383DB80_001073 | Dry Utility Relocations - Berkmar Drive | Material | Lump Sum |  | 1
C00077383DB80_00108 | WET UTILITY RELOCATION COSTS | Material | Lump Sum |  | 1
C00077383DB80_00109 | TEST PITS FOR UTILITY CONFLICTS | Material | Lump Sum |  | 1
C00077383DB80_00100 | MOBILIZATION | Material | Lump Sum |  | 1
C00077383DB80_25505 | CJV PROJECT OFFICE | Material | Lump Sum |  | 1
C00077383DB80_25508 | VDOT FIELD OFFICE SP | Material | Lump Sum |  | 1
C00077383DB80_25565 | PROGRESS SCHEDULE BASELINE | Material | Lump Sum |  | 1
ST-DRSFT | Drilled Shaft Crew | Labor |  |  | 1
C00077383DB80_CONST | RTE 29 CONSTRUCTION | Material |  |  | 1
C00077383DB80_64950 | DRILLED SHAFTS | Material | Lump Sum |  | 1
C00077383DB80_00110 | CLEARING AND GRUBBING | Material | Lump Sum |  | 1
C00077383DB80_12030 | STD. CURB CG-3 | Material | Lump Sum |  | 1
C00077383DB80_12032 | RADIAL CURB CG-3 | Material | Lump Sum |  | 1
C00077383DB80_12700 | STD. COMB. CURB & GUTTER CG-7 | Material | Lump Sum |  | 1
C00077383DB80_12710 | RAD. COMB. CURB & GUTTER CG-7 | Material | Lump Sum |  | 1
C00077383DB80_13108 | CG-12 DETECTABLE WARNING SURFACE | Material | Lump Sum |  | 1
C00077383DB80_13212 | R/W MONUMENT RM-2 | Material | Lump Sum |  | 1
C00077383DB80_13220 | HYDR. CEMENT CONC. CLASS A3 SIDEWALK 4" | Material | Lump Sum |  | 1
C00077383DB80_21020 | MEDIAN STRIP MS-1 | Material | Lump Sum |  | 1
C00077383DB80_21110 | MEDIAN STRIP MS-1A | Material | Lump Sum |  | 1
C00077383DB80_24100 | ALLAYING DUST | Material | Lump Sum |  | 1
C00077383DB80_24152 | TYPE III BARRICADE 8' | Material | Lump Sum |  | 1
C00077383DB80_24160 | CONSTRUCTION SIGNS | Material | Lump Sum |  | 1
C00077383DB80_24272 | TRUCK MOUNTED ATTENUATOR | Material | Lump Sum |  | 1
C00077383DB80_24278 | GROUP 2 CHANNELIZING DEVICES | Material | Lump Sum |  | 1
C00077383DB80_24279 | PORT.CHANGEABLE MESS. SIGN | Material | Lump Sum |  | 1
C00077383DB80_24281 | ELECTRONIC ARROW | Material | Lump Sum |  | 1
C00077383DB80_24283 | POLICE PATROL | Material | Lump Sum |  | 1
C00077383DB80_24290 | TRAFFIC BARRIER SER. CONC. | Material | Lump Sum |  | 1
C00077383DB80_10091 | MOT - STONE 21A | Material | Lump Sum |  | 1
C00077383DB80_10644 | MOT - ASPHALT BM-25.0 | Material | Lump Sum |  | 1
C00077383DB80_10612 | MOT - ASPHALT IM-19.0 | Material | Lump Sum |  | 1
C00077383DB80_12507 | MOT - ASPHALT CURB | Material | Lump Sum |  | 1
C00077383DB80_13241 | MOT - ASPHALT SIDEWALK | Material | Lump Sum |  | 1
C00077383DB80_13605 | IMPACT ATTEN SERV. TYPE 1A | Material | Lump Sum |  | 1
C00077383DB80_50009 | MAINT OF TRAFFIC CREW | Material | Lump Sum |  | 1
C00077383DB80_24430 | DEMO. OF PAVEMENT (FLEXIBLE) | Material | Lump Sum |  | 1
C00077383DB80_24801 | NS REMOVE EXIST. DROP INLET ... | Material | Lump Sum |  | 1
C00077383DB80_24802 | NS REMOVE EXIST. MANHOLE ... | Material | Lump Sum |  | 1
C00077383DB80_27012 | TOPSOIL CLASS A 2" | Material | Lump Sum |  | 1
C00077383DB80_27101 | TEMPORARY SEED | Material | Lump Sum |  | 1
C00077383DB80_27102 | REGULAR SEED | Material | Lump Sum |  | 1
C00077383DB80_27103 | OVERSEEDING | Material | Lump Sum |  | 1
C00077383DB80_27215 | FERTILIZER(15-30-15) | Material | Lump Sum |  | 1
C00077383DB80_27250 | LIME | Material | Lump Sum |  | 1
C00077383DB80_27405 | STABILIZED CONSTRUCTION ENTRANCE | Material | Lump Sum |  | 1
C00077383DB80_27422 | DEWATERING BASIN | Material | Lump Sum |  | 1
C00077383DB80_27451 | INLET PROTECTION , TYPE A | Material | Lump Sum |  | 1
C00077383DB80_27461 | INLET PROTECTION , TYPE B | Material | Lump Sum |  | 1
C00077383DB80_27505 | TEMP. SILT FENCE | Material | Lump Sum |  | 1
C00077383DB80_55040 | LIGHTING RTE. 29 LOCAL LANES | Material | Lump Sum |  | 1
C00077383DB80_54105 | ERAD. OF EXIST. PAVE. MARKING | Material | Lump Sum |  | 1
C00077383DB80_54552 | CONSTR.PAVE.MARK.(TY.F,CL.II)4" | Material | Lump Sum |  | 1
C00077383DB80_54240 | TEMP. PAVE. MARKER 1 WAY | Material | Lump Sum |  | 1
C00077383DB80_65013 | CONCRETE CLASS A3 SUBSTRUCTURE | Material | Lump Sum |  | 1
C00077383DB80_65200 | REINF. STEEL | Material | Lump Sum |  | 1
C00077383DB80_64112 | STEEL PILES | Material | Lump Sum |  | 1
C00077383DB80_64795 | PILE POINT FOR 12" STEEL PILES | Material | Lump Sum |  | 1
C00077383DB80_64005 | SELECT MATL. TY. I MIN. CBR-30 | Material | Lump Sum |  | 1
C00077383DB80_64011 | STRUCTURE EXCAVATION | Material | Lump Sum |  | 1
C00077383DB80_64030 | POROUS BACKFILL | Material | Lump Sum |  | 1
C00077383DB80_64036 | PIPE UNDERDRAIN 6" | Material | Lump Sum |  | 1
C00077383DB80_61654 | PREST.CONC. BOX BEAM 72' | Material | Lump Sum |  | 1
C00077383DB80_60404 | CONCRETE CLASS A4 SUPERSTRUCTURE | Material | Lump Sum |  | 1
C00077383DB80_60490 | BRIDGE DECK GROOVING | Material | Lump Sum |  | 1
C00077383DB80_61701 | CR RE.STEEL LOW CARBON\CHROMIUM | Material | Lump Sum |  | 1
C00077383DB80_61703 | CR REINF. STEEL SOLID STAINLESS | Material | Lump Sum |  | 1
C00077383DB80_62491 | ELASTOMERIC EXPANS. DAM 0"-2" | Material | Lump Sum |  | 1
C00077383DB80_55020 | LIGHTING OF DEPRESSED ROADWAY RTE 29 | Material | Lump Sum |  | 1
C00077383DB80_55030 | UNDERBRIDGE LIGHTING AT RIO RD OVER RTE 29 | Material | Lump Sum |  | 1
C00077383DB80_55010 | PEDESTRIAN LIGHTING AT 29 & RIO RD | Material | Lump Sum |  | 1
C00077383DB80_00580 | UNDERDRAIN UD-1 | Material | Lump Sum |  | 1
C00077383DB80_00588 | UNDERDRAIN UD-4 | Material | Lump Sum |  | 1
C00077383DB80_00591 | COMB. UNDERDRAIN CD-2 | Material | Lump Sum |  | 1
C00077383DB80_00595 | OUTLET PIPE | Material | Lump Sum |  | 1
C00077383DB80_00700 | POST INSTALLATION INSPECTION | Material | Lump Sum |  | 1
C00077383DB80_01122 | 12" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_01152 | 15" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_01182 | 18" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_01242 | 24" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_01362 | 36" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_06821 | DROP INLET DI-3B | Material | Lump Sum |  | 1
C00077383DB80_06836 | DROP INLET, DI-3C | Material | Lump Sum |  | 1
C00077383DB80_07506 | DROP INLET DI-5 | Material | Lump Sum |  | 1
C00077383DB80_08191 | DROP INLET DI-10H (MB-7D) | Material | Lump Sum |  | 1
C00077383DB80_09056 | MANHOLE MH-1 OR 2 | Material | Lump Sum |  | 1
C00077383DB80_09057 | MANHOLE MH-1 FRAME & COVER | Material | Lump Sum |  | 1
C00077383DB80_NS3 | BMP #2 | Material | Lump Sum |  | 1
C00077383DB80_NS2 | BMP #1 | Material | Lump Sum |  | 1
C00077383DB80_10128 | AGGR. BASE MATL. TY. I NO. 21B | Material | Lump Sum |  | 1
C00077383DB80_10642 | ASPHALT CONCRETE TY.BM-25.0A | Material | Lump Sum |  | 1
C00077383DB80_13460 | MB-7D BARRIER | Material | Lump Sum |  | 1
C00077383DB80_13462 | MB-7F BARRIER | Material | Lump Sum |  | 1
C00077383DB80_13606 | IMPACT ATTENUATOR (TL-2, 45 MPH MAX) | Material | Lump Sum |  | 1
C00077383DB80_13465 | MB-8A TYPE 1 | Material | Lump Sum |  | 1
C00077383DB80_13466 | MB-8A TYPE II | Material | Lump Sum |  | 1
C00077383DB80_13467 | MB-8A TYPE III | Material | Lump Sum |  | 1
C00077383DB80_13540 | RETAINING WALL CONC CLASS A3 | Material | Lump Sum |  | 1
C00077383DB80_10610 | ASPHALT CONCRETE TY. IM-19.0A | Material | Lump Sum |  | 1
C00077383DB80_51010 | NEW SIGNALS - ROUTE 29 & RIO ROAD | Material | Lump Sum |  | 1
C00077383DB80_51020 | TEMP SIGNALS - ROUTE 29 & RIO ROAD | Material | Lump Sum |  | 1
C00077383DB80_51030 | NEW SIGNALS - RTE 29 &FASHION SQ/SHOPPERS WORLD | Material | Lump Sum |  | 1
C00077383DB80_51040 | REMOVE SIGNALS - ROUTE 29 & ALBEMARLE SQUARE | Material | Lump Sum |  | 1
C00077383DB80_51050 | NEW SIGNALS - RIO ROAD & BERKMAR DRIVE | Material | Lump Sum |  | 1
C00077383DB80_62043 | RAILING, BR27C 3 RAILS | Material | Lump Sum |  | 1
C00077383DB80_NS | LANDSCAPING REQUIREMENTS | Material | Lump Sum |  | 1
C00077383DB80_50002 | PERMANENT SIGNS | Material | Lump Sum |  | 1
C00077383DB80_10628 | FLEXIBLE PAVEMENT PLANING 0" -2" | Material | Lump Sum |  | 1
C00077383DB80_10608 | ASPHALT CONCRETE TY. SM-12.5D | Material | Lump Sum |  | 1
C00077383DB80_54075 | TY.B CL.VI PAVE. LINE MARK. 4" | Material | Lump Sum |  | 1
C00077383DB80_54077 | TY.B CL.VI PAVE. LINE MARK. 8" | Material | Lump Sum |  | 1
C00077383DB80_54078 | TY.B CL.VI PAVE. LINE MARK. 12" | Material | Lump Sum |  | 1
C00077383DB80_54080 | TY.B CL.VI PAVE. LINE MARK. 24" | Material | Lump Sum |  | 1
C00077383DB80_54079 | TY.B CL.VI PAVE.LINE MARK.4"CONT | Material | Lump Sum |  | 1
C00077383DB80_54217 | SNOW PLOW.RAISED PAVE.MARK. ASPH CONC | Material | Lump Sum |  | 1
C00077383DB80_54300 | PAVE.MESS.MARK.ELONG.ARROW SIN | Material | Lump Sum |  | 1
C00077383DB80_54400 | PAVEMENT MESSAGE MARK. "ONLY" | Material | Lump Sum |  | 1
C00077383DB80_54403 | NS PAVE. MESSAGE MARKING - CARD DIRECTION | Material | Lump Sum |  | 1
C00077383DB80_54404 | NS PAVE MESSAGE MARKING - ROUTE SHIELD | Material | Lump Sum |  | 1
C00077383DB80_00120 | REGULAR EXCAVATION | Material | Lump Sum |  | 1
C00077383DB80_01422 | 42" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_06815 | DROP INLET, DI-3A | Material | Lump Sum |  | 1
C00077383DB80_06828 | DROP INLET, DI-3BB | Material | Lump Sum |  | 1
C00077383DB80_00010 | E&S MAINTENANCE CREW | Material | Lump Sum |  | 1
C00077383DB80_00212 | MINOR STR EXCAV BOX CULV | Material | Lump Sum |  | 1
C00077383DB80_00506 | BEDDING BOX CULV #57 | Material | Lump Sum |  | 1
C00077383DB80_00515 | TEMPORARY SHEETING - ROADWAY | Material | Lump Sum |  | 1
C00077383DB80_00522 | BOX CULVERT CONCRETE CLASS A4 | Material | Lump Sum |  | 1
C00077383DB80_00525 | CONC CLASS A3 MISC | Material | Lump Sum |  | 1
C00077383DB80_00540 | BOX CULVERT REINFORCING STEEL | Material | Lump Sum |  | 1
C00077383DB80_00585 | UNDERDRAIN UD-2 | Material | Lump Sum |  | 1
C00077383DB80_00590 | IL | Material | Lump Sum |  | 1
C00077383DB80_00596 | ENDWALL EW-12 | Material | Lump Sum |  | 1
C00077383DB80_01302 | 30" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_01602 | 60" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_06151 | 15" END SECTION ES-1 | Material | Lump Sum |  | 1
C00077383DB80_06181 | 18" END SECTION ES-1 | Material | Lump Sum |  | 1
C00077383DB80_06241 | 24" END SECTION ES-1 | Material | Lump Sum |  | 1
C00077383DB80_06301 | 30" END SECTION ES-1 | Material | Lump Sum |  | 1
C00077383DB80_06421 | 42" END SECTION ES-1 | Material | Lump Sum |  | 1
C00077383DB80_06751 | DROP INLET, DI-2B | Material | Lump Sum |  | 1
C00077383DB80_06838 | DROP INLET DI-3C, L=12' | Material | Lump Sum |  | 1
C00077383DB80_07507 | DROP INLET DI-5 | Material | Lump Sum |  | 1
C00077383DB80_08400 | DROP INLET DI-12 | Material | Lump Sum |  | 1
C00077383DB80_10608a | ASPHALT CONCRETE TY. SM-12.5D Wedge & Level | Material | Lump Sum |  | 1
C00077383DB80_10610b | ASPHALT CONCRETE TY. IM-19.0A Wedge & Level | Material | Lump Sum |  | 1
C00077383DB80_10635 | ASPHALT CONCRETE TY. SM-9.5A | Material | Lump Sum |  | 1
C00077383DB80_10642b | ASPHALT CONCRETE BM-25.0A Wedge & Level | Material | Lump Sum |  | 1
C00077383DB80_12020 | STD. CURB CG-2 | Material | Lump Sum |  | 1
C00077383DB80_12022 | RADIAL CURB CG-2 | Material | Lump Sum |  | 1
C00077383DB80_13315 | GUARDRAIL TERMINAL GR-11 | Material | Lump Sum |  | 1
C00077383DB80_13320 | GUARDRAIL GR-2 | Material | Lump Sum |  | 1
C00077383DB80_13345 | ALT.BREAKAWAY CABLE TERM.(GR-9) | Material | Lump Sum |  | 1
C00077383DB80_13570 | MOT - WIRE WALL | Material | Lump Sum |  | 1
C00077383DB80_21215 | MEDIAN STRIP MS-2 | Material | Lump Sum |  | 1
C00077383DB80_22581 | CORNER BRACE UNIT FE-CL | Material | Lump Sum |  | 1
C00077383DB80_22643 | FENCE FE-CL | Material | Lump Sum |  | 1
C00077383DB80_22676 | GATE FE-CL L=12' | Material | Lump Sum |  | 1
C00077383DB80_24282 | FLAGGER SERVICE | Material | Lump Sum |  | 1
C00077383DB80_27321 | PROTECTIVE COVERING EC-2 | Material | Lump Sum |  | 1
C00077383DB80_27410 | CHECK DAM, ROCK TY. I | Material | Lump Sum |  | 1
C00077383DB80_27415 | CHECK DAM, ROCK TY. II | Material | Lump Sum |  | 1
C00077383DB80_27430 | SILTATION CONTROL EXCAVATION | Material | Lump Sum |  | 1
C00077383DB80_27432 | TEMPORARY SEDIMENT TRAP | Material | Lump Sum |  | 1
C00077383DB80_27433 | TEMPORARY DIVERSION DIKE | Material | Lump Sum |  | 1
C00077383DB80_27550 | STORMWATER MANAGEMENT STR SWM-1 | Material | Lump Sum |  | 1
C00077383DB80_51010b | PED SIGNALS - ROUTE 29 & TOWNCENTER DR | Material | Lump Sum |  | 1
C00077383DB80_55100 | LIGHTING AT SIGNALIZED INTERSECTIONS | Material | Lump Sum |  | 1
C00077383DB80_01842 | 84" CONC PIPE | Material | Lump Sum |  | 1
C00077383DB80_06740 | DROP INLET, DI-1 | Material | Lump Sum |  | 1
C00077383DB80_06844 | DROP INLET, DI-3CC | Material | Lump Sum |  | 1
C00077383DB80_07510 | DROP INLET DI-7A | Material | Lump Sum |  | 1
C00077383DB80_09150 | EROS CONTR STONE CL. I, EC-1 | Material | Lump Sum |  | 1
C00077383DB80_09152 | EROS CONTR STONE CL. II, EC-1 | Material | Lump Sum |  | 1
C00077383DB80_12600 | STD. COMB. CURB & GUTTER CG-6 | Material | Lump Sum |  | 1
C00077383DB80_12610 | RAD. COMB. CURB & GUTTER CG-6 | Material | Lump Sum |  | 1
C00077383DB80_12945 | CONCRETE TRUCK APRON | Material | Lump Sum |  | 1
C00077383DB80_13392 | FIXED OBJECT ATTACH. GR-FOA-1 TY. I | Material | Lump Sum |  | 1
C00077383DB80_13810 | RETAINING STRUCTURE | Material | Lump Sum |  | 1
C00077383DB80_54082 | TY.B CL.VI PAVE. LINE MARK. 24" | Material | Lump Sum |  | 1
C00077383DB80_60450 | CONC. CL. A4 BRIDGE APPR. SLAB | Material | Lump Sum |  | 1
C00077383DB80_60452 | REINF. STEEL BRIDGE APPR. SLAB | Material | Lump Sum |  | 1
C00077383DB80_61760 | STR. STEEL PLATE GIRDER ERECT | Material | Lump Sum |  | 1
C00077383DB80_61770 | STR. STEEL PLATE GIRDER MATERIAL | Material | Lump Sum |  | 1
C00077383DB80_64955 | DRILLED SHAFTS REINF STEEL | Material | Lump Sum |  | 1
C00077383DB80_67400 | DECK DRAINAGE SYSTEM | Material | Lump Sum |  | 1
C00077383DB80_00101 | CONSTRUCTION SURVEYING (CONSTR.) | Material | Lump Sum |  | 1
C00077383DB80_28551 | Wetland Mitigation Credits | Material | Lump Sum |  | 1
C00077383DB80_51020b | NEW SIGNALS - RTE 29 & HOLLYMEADE DR | Material | Lump Sum |  | 1
C00077383DB80_51030b | NEW SIGNALS - RTE 29 & ASHWOOD BLVD | Material | Lump Sum |  | 1
C00077383DB80_51040b | TEMP SIGNALS - RTE 29 & ASHWOOD BLVD | Material | Lump Sum |  | 1
C00077383DB80_51957 | PORTABLE CCTV CAMERAS | Material | Lump Sum |  | 1
C00077383DB80_28553 | ENVIRONMENTAL MONITORING | Material | Lump Sum |  | 1
C00077383DB80_24279r | PORT.CHANGEABLE MESS. SIGN -REGIONAL | Material | Lump Sum |  | 1
C00077383DB80_25575 | MEDIUM DUTY WRECKER | Material | Lump Sum |  | 1
SUB-ST-STEEL | Sub - Structural Steel Crew | Labor |  |  | 1
C00077383DB80_25561 | FORMAL PARTNERING | Material | Lump Sum |  | 1
C00077383DB80_CO | Rte 29 Change Orders | Material | Lump Sum |  | 1
LN/JV | Lane JV | Labor |  |  | 1
SUB-RAILING | Sub - BR27 Railing | Labor |  |  | 1
5400558-A-600-60801 | PP03(A) - Paved Waterway | Material | Square Yard |  | 1
5400558-A-600-60901 | PP03(A) - Stone Curb | Material | Linear Feet |  | 1
5400558-A-600-61501 | PP03(A) - Concrete Sidewalk | Material | Square Yard |  | 1
5400558-A-620 | PP03(A) - Stone Masonry For Retaining Walls | Material | Lump Sum |  | 1
5400558-A-625-15701 | PP03(A) - Soil Erosion Control | Material | Lump Sum |  | 1
5400558-A-625-15703 | PP03(A) - Temporary Turf Establishment | Material |  |  | 1
5400558-A-625-15801 | PP03(A) - Watering For Dust Control | Material | Lump Sum |  | 1
5400558-A-625-62401 | PP03(A) - Furnishing and Placing Topsoil | Material |  |  | 1
5400558-A-625-62501 | PP03(A) - Turf Establishment | Material |  |  | 1
5400558-A-625-62601 | PP03(A) - Planting Trees and Shrubs | Material | Lump Sum |  | 1
5400558-A-625-62901 | PP03(A) - Rolled Erosion Control Product, Matting | Material | Square Yard |  | 1
5400558-A-635 | PP03(A) - Temporary Traffic Control | Material | Lump Sum |  | 1
5400558-A-637 | PP03(A) - Facilities and Services | Material | Lump Sum |  | 1
5400558 - PP03(A) | 5400558 - PP03(A) Revenue | Nonlabor |  |  | 1
5400558 - PP03(B) | 5400558 - PP03(B) Revenue | Nonlabor |  |  | 1
5400558-B-103 | PP03(B) - Partnering | Material | Lump Sum |  | 1
5400558-B-110 | PP03(B) - Design | Material | Lump Sum |  | 1
5400558-B-152 | PP03(B) - Construction Survey and Staking | Material | Lump Sum |  | 1
5400558-B-154 | PP03(B) - Contractor QA/QC & Testing | Material | Lump Sum |  | 1
5400558-B-155 | PP03(B) - Schedule | Material | Lump Sum |  | 1
5400558-B-0200-20801 | PP03(B) - Earthwork Structure Excavation and Backfill | Material | Cubic Yard |  | 1
5400558-B-250-25101 | PP03(B) - Slope Reinforcement and Retaining Walls - Rip Rap | Material | Cubic Yard |  | 1
5400558-B-250-25501 | PP03(B) - Slope Reinforcement and Retaining Walls - MSE Wall | Material | Square Feet |  | 1
5400558-B-0300-30101 | PP03(B) - Aggregate Base Course | Material |  |  | 1
5400558-B-0550-55201 | PP03(B) - Bridge Construction - Structural concrete | Material | Cubic Yard |  | 1
5400558-B-0550-55202 | PP03(B) - Bridge Construction - High Performance Concrete | Material | Square Yard |  | 1
5400558-B-0550-55304 | PP03(B) - Bridge Construction - Post Tensioning Steel | Material | LB |  | 1
5400558-B-0550-55401 | PP03(B) - Bridge Construction - Reinforcing Steel | Material | LB |  | 1
5400558-B-0550-55503 | PP03(B) - Bridge Construction - Expansion Joints | Material | Linear Feet |  | 1
5400558-B-0550-55601 | PP03(B) - Bridge Construction - Bridge Railing | Material | Linear Feet |  | 1
5400558-B-0550-56201 | PP03(B) - Bridge Construction - Temporary Works and Support System | Material | Lump Sum |  | 1
5400558-B-0550-56401 | PP03(B) - Bridge Construction - Bearing Device | Material | Each |  | 1
5400558-B-0550-62001 | PP03(B) - Bridge Construction - Class B Stone Masonry For Abut and Piers | Material | Cubic Yard |  | 1
5400558-B-600-60201 | PP03(B) - Pipe Culvert | Material | Linear Feet |  | 1
5400558-B-600-60403 | PP03(B) - Inlet | Material | Each |  | 1
5400558-B-600-60501 | PP03(B) - Underdrain | Material | Linear Feet |  | 1
5400558-B-600-60801 | PP03(B) - Paved Waterway | Material | Square Yard |  | 1
5400558-B-0625-15701 | PP03(B) - Soil Erosion Control | Material | Lump Sum |  | 1
5400558-B-0625-15703 | PP03(B) - Temporary Turf Establishment | Material |  |  | 1
5400558-B-0625-15801 | PP03(B) - Watering For Dust Control | Material | Lump Sum |  | 1
5400558-B-0625-62501 | PP03(B) - Turf Establishment | Material |  |  | 1
5400558-B-0625-62901 | PP03(B) - Rolled Erosion Control Product, Matting | Material | Square Yard |  | 1
5400558-B-635 | PP03(B) - Temporary Traffic Control | Material | Lump Sum |  | 1
5400558-B-637 | PP03(B) - Facilities and Services | Material | Lump Sum |  | 1
5400558 - PP03(C) | 5400558 - PP03(C) Revenue | Nonlabor |  |  | 1
5400558-C-103 | PP03(C) - Partnering | Material | Lump Sum |  | 8
5400558-C-110 | PP03(C) - Design | Material | Lump Sum |  | 8
5400558-C-152 | PP03(C) - Construction Survey and Staking | Material | Lump Sum |  | 8
5400558-C-154 | PP03(C) - Contractor QA/QC & Testing | Material | Lump Sum |  | 8
5400558-C-155 | PP03(C) - Schedule | Material | Lump Sum |  | 8
5400558-C-30101 | PP03(C) - Aggregate Base Course | Material |  |  | 8
5400558-C-55202 | PP03(C) - Bridge Construction - High Performance Concrete | Material | Square Yard |  | 8
5400558-C-55401 | PP03(C) - Bridge Construction - Reinforcing Steel | Material | LB |  | 8
5400558-C-55503 | PP03(C) - Bridge Construction - Expansion Joints | Material | Linear Feet |  | 8
5400558-C-55601 | PP03(C) - Bridge Construction - Bridge Railing | Material | Linear Feet |  | 8
5400558-C-60801 | PP03(C) - Paved Waterway | Material | Square Yard |  | 8
5400558-C-15701 | PP03(C) - Soil Erosion Control | Material | Lump Sum |  | 8
5400558-C-15801 | PP03(C) - Watering For Dust Control | Material | Lump Sum |  | 8
5400558-C-62501 | PP03(C) - Turf Establishment | Material |  |  | 8
5400558-C-62601 | PP03(C) - Planting Trees and Shrubs | Material | Lump Sum |  | 8
5400558-C-62901 | PP03(C) - Rolled Erosion Control Product, Matting | Material | Square Yard |  | 8
5400558-C-0635 | PP03(C) - Temporary Traffic Control | Material | Lump Sum |  | 8
5400558-C-0637 | PP03(C) - Facilities and Services | Material | Lump Sum |  | 8
5400558-D-103 | PP03(D) - Partnering | Material | Lump Sum |  | 8
5400558-D-110 | PP03(D) - Design | Material | Lump Sum |  | 8
5400558-D-152 | PP03(D) - Construction Survey and Staking | Material | Lump Sum |  | 8
5400558-D-154 | PP03(D) - Contractor QA/QC & Testing | Material | Lump Sum |  | 8
5400558-D-155 | PP03(D) - Schedule | Material | Lump Sum |  | 8
5400558-D-30101 | PP03(D) - Aggregate Base Course | Material |  |  | 8
5400558-D-25101 | PP03(D) - Rip Rap | Material | Cubic Yard |  | 8
5400558-D-55202 | PP03(D) - Bridge Construction - High Performance Concrete | Material | Square Yard |  | 8
5400558-D-55401 | PP03(D) - Bridge Construction - Reinforcing Steel | Material | LB |  | 8
5400558-D-55503 | PP03(D) - Bridge Construction - Expansion Joints | Material | Linear Feet |  | 8
5400558-D-55601 | PP03(D) - Bridge Construction - Bridge Railing | Material | Linear Feet |  | 8
5400558-D-60801 | PP03(D) - Paved Waterway | Material | Square Yard |  | 8
5400558-D-62010 | PP03(D) - Stone Masonry Guardwall | Material | Linear Feet |  | 8
5400558-D-15701 | PP03(D) - Soil Erosion Control | Material | Lump Sum |  | 8
5400558-D-15801 | PP03(D) - Watering For Dust Control | Material | Lump Sum |  | 8
5400558-D-62501 | PP03(D) - Turf Establishment | Material |  |  | 8
5400558-D-62901 | PP03(D) - Rolled Erosion Control Product, Matting | Material | Square Yard |  | 8
5400558-D-635 | PP03(D) - Temporary Traffic Control | Material | Lump Sum |  | 8
5400558-D-637 | PP03(D) - Facilities and Services | Material | Lump Sum |  | 8
5400558-E-103 | PP03(E) - Partnering | Material | Lump Sum |  | 8
5400558-E-110 | PP03(E) - Design | Material | Lump Sum |  | 8
5400558-E-152 | PP03(E) - Construction Survey and Staking | Material | Lump Sum |  | 8
5400558-E-154 | PP03(E) - Contractor QA/QC & Testing | Material | Lump Sum |  | 8
5400558-E-155 | PP03(E) - Schedule | Material | Lump Sum |  | 8
5400558-E-30101 | PP03(E) - Aggregate Base Course | Material |  |  | 8
5400558-E-25101 | PP03(E) - Rip Rap | Material | Cubic Yard |  | 8
5400558-E-55202 | PP03(E) - Bridge Construction - High Performance Concrete | Material | Square Yard |  | 8
5400558-E-55401 | PP03(E) - Bridge Construction - Reinforcing Steel | Material | LB |  | 8
5400558-E-55503 | PP03(E) - Bridge Construction - Expansion Joints | Material | Linear Feet |  | 8
5400558-E-555601 | PP03(E) - Bridge Construction - Bridge Railing | Material | Linear Feet |  | 8
5400558-E-600-60801 | PP03(E) - Paved Waterway | Material | Square Yard |  | 8
5400558-E-0625-15701 | PP03(E) - Soil Erosion Control | Material | Lump Sum |  | 8
5400558-E-0625-15703 | PP03(E) - Temporary Turf Establishment | Material |  |  | 8
5400558-E-0625-15801 | PP03(E) - Watering For Dust Control | Material | Lump Sum |  | 8
5400558-E-0625-62406 | PP03(E) - Furnishing and Placing Topsoil, 10-inch Depth | Material | Cubic Yard |  | 8
5400558-E-0625-62501 | PP03(E) - Turf Establishment | Material |  |  | 8
5400558-E-62601 | PP03(E) - Planting Trees and Shrubs | Material | Lump Sum |  | 8
5400558-E-0625-62901 | PP03(E) - Rolled Erosion Control Product, Matting | Material | Square Yard |  | 8
5400558-E-635 | PP03(E) - Temporary Traffic Control | Material | Lump Sum |  | 8
5400558-E-637 | PP03(E) - Facilities and Services | Material | Lump Sum |  | 8
5400558-F-103 | PP03(F) - Partnering | Material | Lump Sum |  | 8
5400558-F-110 | PP03(F) - Design | Material | Lump Sum |  | 8
5400558-F-152 | PP03(F) - Construction Survey and Staking | Material | Lump Sum |  | 8
5400558-F-154 | PP03(F) - Contractor QA/QC & Testing | Material | Lump Sum |  | 8
5400558-F-155 | PP03(F) - Schedule | Material | Lump Sum |  | 8
5400558-F-0300-30101 | PP03(F) - Aggregate Base Course | Material |  |  | 8
5400558-F-25101 | PP03(F) - Rip Rap | Material | Cubic Yard |  | 8
5400558-F-0550-55201 | PP03(F) - Bridge Construction - Structural concrete | Material | Cubic Yard |  | 8
5400558-F-0550-55202 | PP03(F) - Bridge Construction - High Performance Concrete | Material | Square Yard |  | 8
5400558-F-0550-55401 | PP03(F) - Bridge Construction - Reinforcing Steel | Material | LB |  | 8
5400558-F-0550-55503 | PP03(F) - Bridge Construction - Expansion Joints | Material | Linear Feet |  | 8
5400558-F-0550-55601 | PP03(F) - Bridge Construction - Bridge Railing | Material | Linear Feet |  | 8
5400558-F-600-60801 | PP03(F) - Paved Waterway | Material | Square Yard |  | 8
5400558-F-62010 | PP03(F) - Stone Masonry Guardwall | Material | Linear Feet |  | 8
5400558-F-0625-15701 | PP03(F) - Soil Erosion Control | Material | Lump Sum |  | 8
5400558-F-0625-15801 | PP03(F) - Watering For Dust Control | Material | Lump Sum |  | 8
5400558-F-0625-62501 | PP03(F) - Turf Establishment | Material |  |  | 8
5400558-F-62601 | PP03(F) - Planting Trees and Shrubs | Material | Lump Sum |  | 8
5400558-F-0625-62901 | PP03(F) - Rolled Erosion Control Product, Matting | Material | Square Yard |  | 8
5400558-F-635 | PP03(F) - Temporary Traffic Control | Material | Lump Sum |  | 8
5400558-F-637 | PP03(F) - Facilities and Services | Material | Lump Sum |  | 8
5400558-G-103 | PP03(G) - Partnering | Material | Lump Sum |  | 8
5400558-G-110 | PP03(G) - Design | Material | Lump Sum |  | 8
5400558-G-152 | PP03(G) - Construction Survey and Staking | Material | Lump Sum |  | 8
5400558-G-154 | PP03(G) - Contractor QA/QC & Testing | Material | Lump Sum |  | 8
5400558-G-155 | PP03(G) - Schedule | Material | Lump Sum |  | 8
5400558-G-0550-55601 | PP03(G) - Bridge Construction - Bridge Railing | Material | Linear Feet |  | 8
5400558-G-66601 | PP03(G) - Bridge 9 and 10 Bridge Repairs CO | Material | Lump Sum |  | 8
5400558-H-110 | PP03(H) - Design | Material | Lump Sum |  | 8
5400558-H-152 | PP03(H) - Construction Survey and Staking | Material | Lump Sum |  | 8
5400558-H-154 | PP03(H) - Contractor QA/QC & Testing | Material | Lump Sum |  | 8
5400558-H-155 | PP03(H) - Schedule | Material | Lump Sum |  | 8
5400558-H-402 | PP03(H) - Hot asphalt Concrete Pavement | Material | Lump Sum |  | 8
5400558-H-62010 | PP03(H) - Stone Masonry Guardwall | Material | Linear Feet |  | 8
5400558 - PP03(D) | 5400558 - PP03(D) Revenue | Nonlabor |  |  | 1
5400558 - PP03(E) | 5400558 - PP03(E) Revenue | Nonlabor |  |  | 1
5400558 - PP03(F) | 5400558 - PP03(F) Revenue | Nonlabor |  |  | 1
5400558 - PP03(G) | 5400558 - PP03(G) Revenue | Nonlabor |  |  | 1
5400558 - PP03(H) | 5400558 - PP03(H) Revenue | Nonlabor |  |  | 1
3329 Bid | 3329 Bid Revenue Resources | Labor |  |  | 1
3329-1 | MOBILIZATION - STD 5% | Material | Lump Sum |  | 1
3329-2 | DESIGN FEE | Material | Unit |  | 1
3329-3 | BONDS, INSURANCES, SUCCESS FEE, D/B TEAM SETUP | Material | Lump Sum |  | 1
3329-4 | MOBILIZE & FURNISH NCDOT FIELD OFFICE | Material | Lump Sum |  | 1
3329-5 | MAINTAIN NCDOT FIELD OFFICE | Material | Month |  | 1
3329-6 | CONSTRUCTION SURVEYING | Material | Unit |  | 1
3329-7 | CLEARING & GRUBBING | Material |  |  | 1
3329-8 | BUILDING DEMO | Material | Each |  | 1
3329-9 | SEALING ABANDONED WELLS | Material | Each |  | 1
3329-10 | REINFORCED BRIDGE APPROACH FILL | Material | Each |  | 1
3329-11 | UNCLASSIFIED EXCAVATION | Material | Cubic Yard |  | 1
3329-12 | UNDERCUT EXCAVATION | Material | Cubic Yard |  | 1
3329-13 | EMBANKMENT SETTLEMENT GAUGES | Material | Each |  | 1
3329-14 | BERM DITCH CONSTRUCTION | Material | Linear Feet |  | 1
3329-15 | REMOVAL OF EXISTING ASPHALT PAVEMENT | Material | Square Yard |  | 1
3329-16 | REMOVAL OF EXISTING MILLED ASPHALT RUMBLE STRIPS | Material | Linear Feet |  | 1
3329-17 | REMOVAL OF EXISTING CONCRETE PAVEMENT | Material | Square Yard |  | 1
3329-18 | REMOVAL OF EXISTING CONCRETE ISLAND | Material | Square Yard |  | 1
3329-19 | FINE GRADING | Material | Square Yard |  | 1
3329-20 | SHALLOW UNDERCUT | Material | Cubic Yard |  | 1
3329-21 | CLASS IV SUBGRADE STABILIZATION | Material |  |  | 1
3329-22 | GEOTEXTILE FOR SOIL STABILIZATION | Material | Square Yard |  | 1
3329-23 | REINFORCED SOIL SLOPES | Material | Square Yard |  | 1
3329-24 | CAMERA EXISTING DRAINAGE PIPE INSPECTION | Material | Linear Feet |  | 1
3329-25 | FND CONDITIONING MATERIAL, MINOR STR | Material |  |  | 1
3329-26 | FOUNDATION CONDITIONING GEOTEXTILE | Material | Square Yard |  | 1
3329-27 | TEMPORARY DRAINAGE - 6" PVC | Material | Linear Feet |  | 1
3329-29 | 15" RC PIPE CULVERTS, CLASS III | Material | Linear Feet |  | 1
3329-30 | 18" RC PIPE CULVERTS, CLASS III | Material | Linear Feet |  | 1
3329-31 | 24" RC PIPE CULVERTS, CLASS III | Material | Linear Feet |  | 1
3329-32 | 30" RC PIPE CULVERTS, CLASS III | Material | Linear Feet |  | 1
3329-33 | 36" RC PIPE CULVERTS, CLASS III | Material | Linear Feet |  | 1
3329-34 | 30" RC PIPE CULVERTS, CLASS III (TRENCHLESS) | Material | Linear Feet |  | 1
3329-35 | 36" RC PIPE CULVERTS, CLASS III (TRENCHLESS) | Material | Linear Feet |  | 1
3329-36 | 60" RC PIPE CULVERTS, CLASS III | Material | Linear Feet |  | 1
3329-38 | 18" RC PIPE CULVERTS, CLASS IV | Material | Linear Feet |  | 1
3329-40 | 36" RC PIPE CULVERTS, CLASS IV | Material | Linear Feet |  | 1
3329-41 | 15" CS PIPE CULVERTS, 0.064" THICK | Material | Linear Feet |  | 1
3329-42 | 18" CS PIPE CULVERTS, 0.064" THICK | Material | Linear Feet |  | 1
3329-43 | 24" CS PIPE CULVERTS, 0.064" THICK | Material | Linear Feet |  | 1
3329-44 | 30" CS PIPE CULVERTS, 0.064" THICK | Material | Linear Feet |  | 1
3329-45 | 48" CS PIPE CULVERTS, 0.064" THICK | Material | Linear Feet |  | 1
3329-47 | PIPE REMOVAL | Material | Linear Feet |  | 1
3329-48 | SHOULDER DRAIN | Material | Linear Feet |  | 1
3329-49 | 4" SHOULDER DRAIN PIPE | Material | Linear Feet |  | 1
3329-50 | 4" OUTLET PIPE FOR SHOULDER DRAINS | Material | Linear Feet |  | 1
3329-51 | CONC PAD FOR SHOULD DR PIPE OUTLET | Material | Each |  | 1
3329-52 | ENDWALLS | Material | Each |  | 1
3329-53 | REINFORCED ENDWALLS | Material | Each |  | 1
3329-54 | PIPE COLLARS | Material | Each |  | 1
3329-55 | PIPE PLUGS | Material | Each |  | 1
3329-56 | PIPE ELBOWS, 0.064" THICK | Material | Each |  | 1
3329-57 | FLOWABLE FILL | Material | Cubic Yard |  | 1
3329-58 | MASONRY DRAINAGE STRUCTURES | Material | Each |  | 1
3329-59 | BDO, STD 850.1 | Material | Each |  | 1
3329-60 | FRAME WITH GRATE, STD 840.16 | Material | Each |  | 1
3329-61 | FRAME WITH TWO GRATES, STD(W.S. FLAT) 840.20 | Material | Each |  | 1
3329-62 | FRAME WITH TWO GRATES, STD(W.S. SAG) 840.22 | Material | Each |  | 1
3329-63 | STEEL FRAME WITH TWO GRATES, STD 840.37 | Material | Each |  | 1
3329-64 | FRAME WITH COVER, STD 840.54 | Material | Each |  | 1
3329-65 | ADJUSTMENT OF DROP INLETS | Material | Each |  | 1
3329-66 | CONV EX DROP INLET TO JB WITH MH | Material | Each |  | 1
3329-67 | RIP RAP, CLASS I | Material |  |  | 1
3329-68 | RIP RAP, CLASS B | Material |  |  | 1
3329-69 | GEOTEXTILE FOR DRAINAGE | Material | Square Yard |  | 1
3329-70 | HAZARDOUS SPILL BASIN | Material | Each |  | 1
3329-71 | SOIL CEMENT BASE | Material | Square Yard |  | 1
3329-72 | PORT CEMENT FOR SOIL CEMENT BASE | Material |  |  | 1
3329-73 | AGGREGATE BASE COURSE | Material |  |  | 1
3329-74 | ASPHALT CURING SEAL | Material | Gallon |  | 1
3329-75 | INCIDENTAL STONE BASE | Material |  |  | 1
3329-76 | PRIME COAT | Material | Gallon |  | 1
3329-77 | ACBC, TYPE B25.0B | Material |  |  | 1
3329-78 | ACBC, TYPE B25.0B WEDGING | Material |  |  | 1
3329-79 | ACBC, TYPE B25.0C | Material |  |  | 1
3329-80 | ACBC, TYPE B25.0C WEDGING | Material |  |  | 1
3329-81 | ACIC TYPE I19B | Material |  |  | 1
3329-82 | ACIC TYPE I19B WEDGING | Material |  |  | 1
3329-83 | ACIC, TYPE I19.0C | Material |  |  | 1
3329-84 | ACIC, TYPE I19.0C WEDGING | Material |  |  | 1
3329-85 | ACSC, TYPE S9.5B | Material |  |  | 1
3329-86 | ACSC, TYPE S9.5B WEDGING | Material |  |  | 1
3329-87 | ACSC, TYPE S9.5C | Material |  |  | 1
3329-88 | ACSC, TYPE S9.5C WEDGING | Material |  |  | 1
3329-89 | ACSC, TYPE SF9.5D | Material |  |  | 1
3329-90 | ACSC, TYPE SF9.5A | Material |  |  | 1
3329-91 | FABRIC UNDER PCCP, REFLECTEX | Material | Square Yard |  | 1
3329-92 | REPAIRING OF JOINTED CONCRETE PAVEMENT SLABS | Material | Square Yard |  | 1
3329-93 | PATCHING CONCRETE PAVEMENT SPALLS | Material | Square Feet |  | 1
3329-94 | MILLED RUMBLE STRIPS (CONCRETE) | Material | Linear Feet |  | 1
3329-95 | 12" PCCP THRU LANES WITH DOWELS | Material | Square Yard |  | 1
3329-96 | 14" PCCP THRU LANES WITH DOWELS | Material | Square Yard |  | 1
3329-97 | 11" PCCP SHOULDERS | Material | Square Yard |  | 1
3329-98 | 12" PCCP SHOULDERS | Material | Square Yard |  | 1
3329-99 | DIAMOND GRIND | Material | Square Yard |  | 1
3329-100 | SURFACE TESTING CONCRETE PAVEMENT | Material | Lump Sum |  | 1
3329-101 | FIELD LAB, PCCP | Material | Lump Sum |  | 1
3329-102 | EROSION CONTROL MAINTENANCE | Material | Month |  | 1
3329-103 | TEMPORARY SILT FENCE | Material | Linear Feet |  | 1
3329-104 | STONE FOR EROSION CONTROL, CLASS A | Material |  |  | 1
3329-105 | STONE FOR EROSION CONTROL, CLASS B | Material |  |  | 1
3329-106 | SEDIMENT CONTROL STONE | Material |  |  | 1
3329-107 | TEMPORARY MULCHING | Material |  |  | 1
3329-108 | SEED FOR TEMPORARY SEEDING | Material | LB |  | 1
3329-109 | FERTILIZER FOR TEMPORARY SEEDING | Material |  |  | 1
3329-110 | TEMPORARY SLOPE DRAINS | Material | Linear Feet |  | 1
3329-111 | SAFETY FENCE | Material | Linear Feet |  | 1
3329-112 | SILT EXCAVATION | Material | Cubic Yard |  | 1
3329-113 | MATTING FOR EROSION CONTROL | Material | Square Yard |  | 1
3329-114 | COIR FIBER MAT | Material | Square Yard |  | 1
3329-115 | PERMANENT SOIL REINFORCEMENT MAT | Material | Square Yard |  | 1
3329-116 | 1/4" HARDWARE CLOTH | Material | Linear Feet |  | 1
3329-117 | STILLING BASINS | Material | Cubic Yard |  | 1
3329-118 | COIR FIBER WATTLE | Material | Linear Feet |  | 1
3329-119 | WATTLE BARRIER | Material | Linear Feet |  | 1
3329-120 | POLYACRYLAMIDE (PAM) | Material | LB |  | 1
3329-121 | COIR FIBER BAFFLE | Material | Linear Feet |  | 1
3329-122 | 1.5" SKIMMER | Material | Each |  | 1
3329-123 | 2" SKIMMER | Material | Each |  | 1
3329-125 | SEEDING & MULCHING | Material |  |  | 1
3329-126 | MOWING | Material |  |  | 1
3329-127 | SPECIALIZED HAND MOWING | Material | Hour |  | 1
3329-128 | SEED FOR REPAIR SEEDING | Material | LB |  | 1
3329-129 | FERTILIZER FOR REPAIR SEEDING | Material |  |  | 1
3329-130 | SEED FOR SUPPLEMENTAL SEEDING | Material | LB |  | 1
3329-131 | FERTILIZER TOPDRESSING | Material |  |  | 1
3329-132 | STREAMBANK REFORESTATION | Material |  |  | 1
3329-133 | TYPE S9.5C TEMPORARY ASPHALT | Material |  |  | 1
3329-134 | TYPE S9.5A TEMPORARY ASPHALT WEDGING | Material |  |  | 1
3329-135 | TEMPORARY SHORING | Material | Square Feet |  | 1
3329-136 | FABRIC FOR TEMPORARY FABRIC WALL | Material | Square Yard |  | 1
3329-137 | TEMPORARY PAVEMENT MARKING REMOVAL | Material | Linear Feet |  | 1
3329-138 | TEMP PATTERN MASKING | Material | Square Yard |  | 1
3329-139 | TEMP SYMBOLS | Material | Linear Feet |  | 1
3329-140 | TEMP 4" WHITE | Material | Linear Feet |  | 1
3329-141 | TEMP 4" YELLOW | Material | Linear Feet |  | 1
3329-142 | TEMP 6" WHITE | Material | Linear Feet |  | 1
3329-143 | TEMP 6" YELLOW | Material | Linear Feet |  | 1
3329-144 | TEMP 8" WHITE | Material | Linear Feet |  | 1
3329-145 | TEMP 12" WHITE | Material | Linear Feet |  | 1
3329-146 | TEMP 24" WHITE | Material | Linear Feet |  | 1
3329-147 | TEMPORARY TRAFFIC CONTROL | Material | Month |  | 1
3329-148 | PORTABLE LIGHTING | Material | Month |  | 1
3329-149 | WORK ZONE SIGNS (STATIONARY) | Material | Square Feet |  | 1
3329-150 | WORK ZONE SIGNS (PORTABLE) | Material | Square Feet |  | 1
3329-151 | WORK ZONE SIGNS (BARRICADE MOUNTED) | Material | Square Feet |  | 1
3329-152 | FLASHING ARROW BOARD | Material | Each |  | 1
3329-153 | PORTABLE CHANGEABLE MESSAGE SIGN | Material | Each |  | 1
3329-154 | DRUMS | Material | Each |  | 1
3329-155 | CONES | Material | Each |  | 1
3329-156 | BARRICADES (TYPE III) | Material | Linear Feet |  | 1
3329-157 | FLAGGER | Material | Day |  | 1
3329-158 | FLAGGER - RAILROAD | Material | Day |  | 1
3329-159 | TEMPORARY CRASH CUSHIONS | Material | Each |  | 1
3329-160 | RELOCATE CRASH CUSHIONS | Material | Each |  | 1
3329-161 | RESET TEMPORARY CRASH CUSHION | Material | Each |  | 1
3329-162 | TMA | Material | Each |  | 1
3329-163 | PORTABLE CONCRETE BARRIER | Material | Linear Feet |  | 1
3329-164 | PORTABLE CONCRETE BARRIER (ANCHORED) | Material | Linear Feet |  | 1
3329-165 | RELOCATE BARRIER | Material | Linear Feet |  | 1
3329-166 | RESET PORT CONC BAR (NO TRUCK) | Material | Linear Feet |  | 1
3329-167 | LAW ENFORCEMENT | Material | Hour |  | 1
3329-168 | SKINNY DRUM | Material | Each |  | 1
3329-169 | RIGHT OF WAY MARKERS | Material | Each |  | 1
3329-170 | 1'-6" CONCRETE CURB & GUTTER | Material | Linear Feet |  | 1
3329-171 | 2'-6" CONCRETE CURB & GUTTER | Material | Linear Feet |  | 1
3329-172 | SHOULDER BERM GUTTER | Material | Linear Feet |  | 1
3329-173 | EXPRESSWAY GUTTER | Material | Linear Feet |  | 1
3329-174 | 8" CONCRETE TRUCK APRON | Material | Square Yard |  | 1
3329-175 | 5" MONOLITHIC CONCRETE ISLANDS | Material | Square Yard |  | 1
3329-176 | CONCRETE BARRIER, TYPE T | Material | Linear Feet |  | 1
3329-177 | CONCRETE BARRIER, TYPE T1 | Material | Linear Feet |  | 1
3329-178 | CONCRETE BARRIER, TYPE T2 | Material | Linear Feet |  | 1
3329-179 | CONCRETE BARRIER TRANSITION SECTION | Material | Each |  | 1
3329-180 | PREC REINF CONC BARRIER, SINGLE FACED | Material | Linear Feet |  | 1
3329-181 | STEEL BM GUARDRAIL | Material | Linear Feet |  | 1
3329-182 | GUARDRAIL ANCHOR UNITS, TYPE CAT-1 | Material | Each |  | 1
3329-183 | GUARDRAIL ANCHOR UNITS, TYPE 350 350 | Material | Each |  | 1
3329-184 | GUARDRAIL ANCHOR UNITS, TYPE B-77 | Material | Each |  | 1
3329-185 | REMOVE EXISTING GUARDRAIL | Material | Linear Feet |  | 1
3329-186 | REMOVE EXISTING CABLEGUIDERAIL | Material | Linear Feet |  | 1
3329-187 | WOVEN WIRE FENCE, 47" FABRIC | Material | Linear Feet |  | 1
3329-188 | 4" TIMBER FENCE POSTS, 7'-6" LONG | Material | Each |  | 1
3329-189 | 5" TIMBER FENCE POSTS, 8'-0" LONG | Material | Each |  | 1
3329-190 | THERMO PVMT MARK LINES (8", 90 MILS) | Material | Linear Feet |  | 1
3329-191 | THERMO PVMT MARK LINES (24", 120 MILS) | Material | Linear Feet |  | 1
3329-192 | THERMO PVMT MARKING SYMBOL (90 MILS) | Material | Each |  | 1
3329-193 | POLYUREA PVMT MARK (4", HIGHLY REFL) | Material | Linear Feet |  | 1
3329-194 | POLYUREA PVMT MARK (6", HIGHLY REFL) | Material | Linear Feet |  | 1
3329-195 | POLYUREA PVMT MARk (8", HIGHLY REFL) | Material | Linear Feet |  | 1
3329-196 | POLYUREA PVMT MARK (12", HIGHLY REFL) | Material | Linear Feet |  | 1
3329-197 | PERMANENT RAISED PAVEMENT MARK | Material | Each |  | 1
3329-198 | SNOWPLOWABLE PAVEMENT MARKERS | Material | Each |  | 1
3329-199 | CONTRACTOR FURNISHED, TYPE A SIGN | Material | Square Feet |  | 1
3329-200 | CONTRACTOR FURNISHED, TYPE B SIGN | Material | Square Feet |  | 1
3329-201 | CONTRACTOR FURNISHED, TYPE D SIGN | Material | Square Feet |  | 1
3329-202 | CONTRACTOR FURNISHED, TYPE E SIGN | Material | Square Feet |  | 1
3329-203 | CONTRACTOR FURNISHED, TYPE F SIGN | Material | Square Feet |  | 1
3329-204 | CONTRACTOR FURNISHED, MILEMARKERS | Material | Square Feet |  | 1
3329-205 | REINF CONCRETE SIGN FOUNDATIONS | Material | Cubic Yard |  | 1
3329-206 | PLAIN CONCRETE SIGN FOUNDATIONS | Material | Cubic Yard |  | 1
3329-207 | SUPPORTS, BREAKAWAY STEEL BEAM | Material | LB |  | 1
3329-208 | SUPPORTS, SIMPLE STEEL BEAM | Material | LB |  | 1
3329-209 | SUPPORTS, 3-LB STEEL U-CHANNEL | Material | Linear Feet |  | 1
3329-210 | SUPPTS, OH SIGN STRUCTURE (54700S-C) | Material | Lump Sum |  | 1
3329-211 | SUPPTS, OH SIGN STRUCTURE (58700N-C) | Material | Lump Sum |  | 1
3329-212 | SUPPTS, OH SIGN STRUCTURE (64700N-C) | Material | Lump Sum |  | 1
3329-213 | SUPPTS, OH SIGN STRUCTURE (70000N-C) | Material | Lump Sum |  | 1
3329-214 | SUPPTS, OH SIGN STRUCTURE (72500S-FS) | Material | Lump Sum |  | 1
3329-215 | SUPPTS, OH SIGN STRUCTURE (73500S-C) | Material | Lump Sum |  | 1
3329-216 | SUPPTS, OH SIGN STRUCTURE (74500S-C) | Material | Lump Sum |  | 1
3329-217 | SUPPTS, OH SIGN STRUCTURE (75950S-FS) | Material | Lump Sum |  | 1
3329-218 | SUPPTS, OH SIGN STRUCTURE (78550S-FS) | Material | Lump Sum |  | 1
3329-219 | SUPPTS, OH SIGN STRUCTURE (81150S-FS) | Material | Lump Sum |  | 1
3329-220 | SUPPTS, OH SIGN STRUCTURE (4250S-FS) | Material | Lump Sum |  | 1
3329-221 | SIGN ERECTION, TYPE D | Material | Each |  | 1
3329-222 | SIGN ERECTION, TYPE E | Material | Each |  | 1
3329-223 | SIGN ERECTION, TYPE F | Material | Each |  | 1
3329-224 | SIGN ERECTION, TYPE A (OVERHEAD) | Material | Each |  | 1
3329-225 | SIGN ERECTION, TYPE B (OVERHEAD) | Material | Each |  | 1
3329-226 | SIGN ERECTION, TYPE A (GR MOUNTED) | Material | Each |  | 1
3329-227 | SIGN ERECTION, TYPE B (GR MOUNTED) | Material | Each |  | 1
3329-228 | SIGN ERECTION, MILEMARKERS | Material | Each |  | 1
3329-229 | SIGN ERECTION, REL, TYPE A (GR MOUNT) | Material | Each |  | 1
3329-230 | DISPOSAL OF SIGN SYSTEM, OVERHEAD | Material | Each |  | 1
3329-231 | DISPOSAL OF SIGN SYSTEM, STEEL BEAM | Material | Each |  | 1
3329-232 | DISPOSAL OF SIGN SYSTEM, U- CHANNEL | Material | Each |  | 1
3329-233 | DISPOSAL OF SIGN, A OR B (OVERHEAD) | Material | Each |  | 1
3329-234 | LIGHTING PER NCDOT PLAN | Material | Lump Sum |  | 1
3329-235 | SIGNAL CABLE | Material | Linear Feet |  | 1
3329-236 | VEHICLE SIGNAL HEAD (12", 3 SECTION) | Material | Each |  | 1
3329-237 | VEHICLE SIGNAL HEAD (12", 4 SECTION) | Material | Each |  | 1
3329-238 | VEHICLE SIGNAL HEAD (12", 5 SECTION) | Material | Each |  | 1
3329-239 | MESSENGER CABLE (1/4") | Material | Linear Feet |  | 1
3329-240 | MESSENGER CABLE (3/8") | Material | Linear Feet |  | 1
3329-241 | TRACER WIRE | Material | Linear Feet |  | 1
3329-242 | UNPAVED TRENCHING (1-2 INCH CONDUIT) | Material | Linear Feet |  | 1
3329-243 | UNPAVED TRENCHING (2-2 INCH CONDUIT) | Material | Linear Feet |  | 1
3329-244 | DIRECTIONAL DRILL (2-2 INCH CONDUIT) | Material | Linear Feet |  | 1
3329-245 | DIRECTIONAL DRILL (4-1.25 INCH CONDUIT) | Material | Linear Feet |  | 1
3329-246 | JUNCTION BOX (STANDARD SIZE) | Material | Each |  | 1
3329-247 | JUNCTION BOX (OVER-SIZED, HEAVY DUTY) | Material | Each |  | 1
3329-248 | WOOD POLE | Material | Each |  | 1
3329-249 | GUY ASSEMBLY | Material | Each |  | 1
3329-250 | 1" RISER WITH WEATHERHEAD | Material | Each |  | 1
3329-251 | 2" RISER WITH WEATHERHEAD | Material | Each |  | 1
3329-252 | HEAT SHRINK TUBING RETROFIT KIT | Material | Each |  | 1
3329-253 | 2" RISER WITH HEAT SHRINK TUBING | Material | Each |  | 1
3329-254 | INDUCTIVE LOOP SAWCUT | Material | Linear Feet |  | 1
3329-255 | LEAD-IN CABLE(14-2) | Material | Linear Feet |  | 1
3329-256 | COMMUNICATIONS CABLE (24 FIBER) | Material | Linear Feet |  | 1
3329-257 | COMMUNICATIONS CABLE (144 FIBER) | Material | Linear Feet |  | 1
3329-258 | DROP CABLE | Material | Linear Feet |  | 1
3329-259 | SPLICE ENCLOSURE | Material | Each |  | 1
3329-260 | DELINEATOR MARKER | Material | Each |  | 1
3329-261 | NEW ELECTRICAL SERVICE | Material | Each |  | 1
3329-262 | METAL STRAIN SIGNAL POLE | Material | Each |  | 1
3329-263 | SOIL TEST | Material | Each |  | 1
3329-264 | DRILLED PIER FOUNDATION | Material | Cubic Yard |  | 1
3329-265 | SIGN FOR SIGNALS | Material | Each |  | 1
3329-266 | SIGNAL CABINET FOUNDATION | Material | Each |  | 1
3329-267 | CONTROLLER WITH CABINET (TYPE 2070L, BASE MOUNTED) | Material | Each |  | 1
3329-268 | DETECTOR CARD (TYPE 2070L) | Material | Each |  | 1
3329-269 | CABINET BASE EXTENDER | Material | Each |  | 1
3329-270 | TRAFFIC SIGNAL REMOVAL | Material | Each |  | 1
3329-271 | NEW PEDESTAL MOUNTED DMS ASSEMBLY | Material | Each |  | 1
3329-272 | CCTV CABINET (TYPE 336S, POL MOUNTED) | Material | Each |  | 1
3329-273 | CCTV CAMERA ASSEMBLY | Material | Each |  | 1
3329-274 | CCTV INTEGRATION AND CONFIGURATION | Material | Each |  | 1
3329-275 | FIELD EQUIPMENT CABINET | Material | Each |  | 1
3329-276 | FIELD ETHERNET SWITCH | Material | Each |  | 1
3329-277 | ETHERNET SWITCH (HEAD END) | Material | Each |  | 1
3329-278 | CENTRAL VIDEO DECODER (HEAD END) | Material | Each |  | 1
3329-279 | UPS | Material | Each |  | 1
3329-280 | 6" WATER LINE | Material | Linear Feet |  | 1
3329-281 | 12" WATER LINE | Material | Linear Feet |  | 1
3329-282 | 24" WATER LINE | Material | Linear Feet |  | 1
3329-283 | 6" GATE VALVE | Material | Each |  | 1
3329-284 | ADJUST VALVE BOX | Material | Each |  | 1
3329-285 | EXTEND VALVE BOX & STEM | Material | Each |  | 1
3329-286 | AIR RELEASE VALVE & MANHOLE - 24" WATER | Material | Each |  | 1
3329-287 | ADJUST 12" BLOWOFF & VALVE BOX | Material | Each |  | 1
3329-288 | Breakdown & Rebuild 5' DIA Water Valve Manhole | Material | Each |  | 1
3329-289 | 12"X6" TAPPING SLEEVE & VALVE ASSEMBLY | Material | Each |  | 1
3329-290 | RELOCATE WATER METER (2") | Material | Each |  | 1
3329-291 | REMOVE WATER METER | Material | Each |  | 1
3329-292 | RELOCATE FIRE HYDRANT | Material | Each |  | 1
3329-293 | 12" SANITARY GRAVITY SEWER | Material | Linear Feet |  | 1
3329-296 | 5' DIA UTILITY MANHOLE | Material | Each |  | 1
3329-297 | PLUG EXISTING SEWER LINE | Material | Each |  | 1
3329-298 | REMOVE UTILITY MANHOLE | Material | Each |  | 1
3329-299 | STILLING BASINS - CULVERT | Material | Cubic Yard |  | 1
3329-300 | IMPERVIOUS DIKE | Material | Linear Feet |  | 1
3329-301 | CULVERT DIVERSION CHANNEL | Material | Cubic Yard |  | 1
3329-302 | REMOVAL OF EXISTING CULVERT NC 152 | Material | Lump Sum |  | 1
3329-303 | REMOVAL OF EXISTING CULVERT OLD BEATTY FORD ROAD | Material | Lump Sum |  | 1
3329-304 | CULVERT EXCAVATION | Material | Cubic Yard |  | 1
3329-305 | FOUND COND MATERIAL, BOX CULV | Material |  |  | 1
3329-306 | CLASS A CONCRETE (CULVERT) | Material | Cubic Yard |  | 1
3329-307 | REINFORCING STEEL (CULVERT) | Material | LB |  | 1
3329-308 | MSE RETAINING WALLS | Material | Square Feet |  | 1
3329-309 | CONST, MAINT, & REM OF TEMP ACCESS RAMP | Material | Each |  | 1
3329-310 | REM OF EX .STRUCT OLD BEATTY FORD RD | Material | Lump Sum |  | 1
3329-311 | REM OF EX .STRUCT DAUGHERTY RD | Material | Lump Sum |  | 1
3329-312 | REM OF EX .STRUCT PINE RIDGE RD | Material | Lump Sum |  | 1
3329-313 | REM OF EX .STRUCTURE LENTZ RD | Material | Lump Sum |  | 1
3329-314 | REM OF EX .STRUCT NC 152 / I-85 | Material | Lump Sum |  | 1
3329-315 | REM OF EX .STRCT US601-29 FLY / I-85 | Material | Lump Sum |  | 1
3329-316 | REM OF EX .STRUCT NC152/UC29 | Material | Lump Sum |  | 1
3329-317 | REM OF EX .STRUCT US 29 / RAILROAD | Material | Lump Sum |  | 1
3329-318 | PILE EXCAVATION | Material | Linear Feet |  | 1
3329-319 | PDA TESTING | Material | Each |  | 1
3329-320 | UNCLASSIFIED STRUCTURE EXCAVATION | Material | Cubic Yard |  | 1
3329-321 | REINFORCED CONCRETE DECK SLAB | Material | Square Feet |  | 1
3329-322 | GROOVING BRIDGE FLOORS | Material | Square Feet |  | 1
3329-323 | CLASS A CONCRETE (BRIDGE) | Material | Cubic Yard |  | 1
3329-324 | BRIDGE APPROACH SLABS | Material | Each |  | 1
3329-325 | REINFORCING STEEL (BRIDGE) | Material | LB |  | 1
3329-326 | 36" FIB - PRESTRESSED CONCRETE GIRDERS | Material | Linear Feet |  | 1
3329-327 | 45" FIB - PRESTRESSED CONCRETE GIRDERS | Material | Linear Feet |  | 1
3329-328 | 45" TYPE III - PRESTRESSED CONCRETE GIRDERS | Material | Linear Feet |  | 1
3329-329 | 54" MBT PRESTRESSED CONCRETE GIRDERS | Material | Linear Feet |  | 1
3329-330 | 63" FIB - PRESTRESSED CONC GIRDERS | Material | Linear Feet |  | 1
3329-331 | 65" MBT - PRESTRESSED CONC GIRDERS | Material | Linear Feet |  | 1
3329-332 | SPIRAL COLUMN REINFORCING STEEL (BRIDGE) | Material | LB |  | 1
3329-333 | HP12X53 STEEL PILES | Material | Linear Feet |  | 1
3329-334 | STEEL PILE POINTS | Material | Each |  | 1
3329-335 | MICROPILE | Material | Linear Feet |  | 1
3329-336 | 42" CONCRETE BARRIER RAIL | Material | Linear Feet |  | 1
3329-337 | VANDAL FENCING ON RR BRIDGE | Material | Linear Feet |  | 1
3329-338 | 4" SLOPE PROTECTION | Material | Square Yard |  | 1
3329-339 | RIP RAP CLASS II | Material |  |  | 1
3329-340 | GEOTEXTILE FOR DRAINAGE | Material | Square Yard |  | 1
3329-341 | ELASTOMERIC BEARINGS | Material | Lump Sum |  | 1
3329-342 | FOAM JOINT SEALS | Material | Lump Sum |  | 1
3329-343 | EXPANSION JOINT SEALS | Material | Lump Sum |  | 1
3329 Revenue Items | 3329 Revenue Items | Nonlabor |  |  | 1
3191 | 3191 - IH 35 McLennan Waco | Nonlabor |  |  | 1
Crew | Crews | Labor |  |  | 0
Cr-26 | Incidental Concrete | Labor |  |  | 0
Waco, TX | Waco, TX Material Resources | Material |  |  | 10
LIME | Lime Treated Subgrade | Material |  |  | 1
CTB | Cement Treated Base | Material |  |  | 1
TRAFCRT | Traffic Control/SWPPP | Material |  |  | 1
CUT-FILL | Earthwork - Cut to Fill | Material |  |  | 1
EXPORT | Earthwork - Export Material | Material |  |  | 1
IMPORT | Earthwork - Import Material | Material |  |  | 1
HMAC D | HMAC Type D | Material |  |  | 1
FB1 | Flexbase 1.0 | Material |  |  | 1
FB3 | Flexbase 3.0 | Material |  |  | 1
RG | Rough Grade | Material |  |  | 1
CRCP | Concrete Paving | Material |  |  | 1
DRG | Drainage | Material |  |  | 1
BXCLV | Box Culverts | Material |  |  | 1
DET | Detours | Material |  |  | 1
SHDLND | Shoulder/Landscape Grading | Material |  |  | 1
HMAC B | HMAC Type B | Material |  |  | 1
HMAC C | HMAC Type C | Material |  |  | 1
PRMCR | Prime/Cure Base | Material |  |  | 1
OCST | Seal Coat | Material |  |  | 1
PREPR | Prep ROW | Material |  |  | 1
DEMO- | Demo | Material |  |  | 1
APRSLB | Approach Slabs | Material |  |  | 1
ABUT | Abutments | Material |  |  | 1
DRSH | Drilled Shafts | Material |  |  | 1
COL | Columns | Material |  |  | 1
CAPS | Caps | Material |  |  | 1
BEAMS | Beams | Material |  |  | 1
BRDGDCK | Bridge Deck | Material |  |  | 1
FOOT | Footing | Material |  |  | 1
CURE | Concrete Cure | Material |  |  | 1
BRDGRL | Bridge Rail | Material |  |  | 1
RE Wall | Variouis Retaining Wall Work | Material |  |  | 1
FARR | Farr | Material |  |  | 1
FREYSSINET | Cable Stays | Material |  |  | 1
WL | Water Line | Material |  |  | 1
SAN | Sanitary Sewer | Material |  |  | 1
FM | Force Main | Material |  |  | 1
SST | Stripe/Switch Traffic | Material |  |  | 1
PSR | Prep/Set/Rmv - Bridge Work | Material |  |  | 1
GSBD | Groove/Seal Bridge Deck | Material |  |  | 1
DECO | Misc. Deco | Material |  |  | 1
POND | Misc @ Pond | Material |  |  | 1
TAJ | TAJ | Material |  |  | 8
MC | Misc Concrete Work | Material |  |  | 8
CREW-Drainage | Drainage Crew | Labor |  |  | 1
CREW-Lime | Lime-Treated Subgrade Crew | Labor |  |  | 0
CREW-CTB | CTB Crew | Labor |  |  | 0
CREW-Flex Base | Flex Base Crew | Labor |  |  | 0
CREW-Asph Pave | Asphalt Paving Crew | Labor |  |  | 0
CREW-Conc Pave | Concrete Paving Crew | Labor |  |  | 1
TWC | TimeWarner | Material |  |  | 8
ATT | AT&T | Material |  |  | 8
Road | Roadway Complete | Material |  |  | 8
STCL | Stone Columns | Material |  |  | 8
BARR | Barrier Wall | Material |  |  | 8
3191 E ML | Excavation Mainlane | Labor |  |  | 1
3191 E FR | Excavation Frontage Rd | Labor |  |  | 1
3191 FB ML | Finish Blade Mainlane | Labor |  |  | 1
3191 FB FR | Finish Blade Frontage Rd | Labor |  |  | 1
Cost Oct Redist | October 16 Redistribution | Material | Lump Sum |  | 8
C00100566DB63_C17 | I-66/15 Change Order #17 | Material | Lump Sum |  | 1
C00100566DB63_C18 | I-66/15 Change Order #18 | Material | Lump Sum |  | 1
C00100566DB63_C19 | I-66/15 Change Order #19 | Material | Lump Sum |  | 1
3328 - CO Pay Item | 3328 - NCDOT Pay Items - Liberty Revenue | Nonlabor |  |  | 1
3328-CO-3 | CLEARING & GRUBBING | Material | Lump Sum |  | 8
3328-CO-5 | UNCLASSIFIED EXCAVATION | Material | Cubic Yard |  | 8
3328-CO-6 | UNDERCUT EXCAVATION | Material | Cubic Yard |  | 8
3328-CO-7 | BORROW EXCAVATION | Material | Cubic Yard |  | 8
3328-CO-11 | REMOVAL EXISTING ASPHALT | Material | Square Yard |  | 8
3328-CO-15 | GEOTEXTILE FOR SOIL STABILIZATION | Material | Square Yard |  | 8
3328-CO-26 | 15"RC PIPE CULVERTS CLASS 4 | Material | Linear Feet |  | 8
3328-CO-27 | 18"RC PIPE CULVERTS CLASS 4 | Material | Linear Feet |  | 8
3328-CO-37 | PIPE REMOVAL | Material | Linear Feet |  | 8
3328-CO-38 | FINE GRADING | Material | Square Yard |  | 8
3328-CO-43 | MILLING ASPHALT PAVEMENT (1.5") | Material | Square Yard |  | 8
3328-CO-XX1 | MILING ASPHALT PAVEMENT (11") | Material | Square Yard |  | 8
3328-CO-49 | ASPHALT CONC.BASE COURSE TYPE B25.0C | Material |  |  | 8
3328-CO-51 | ASPHALT CONC.INTERMEDIATE COURSE TYPE 119.0C | Material |  |  | 8
3328-CO-53 | ASPHALT CONC. SURFACE COURSE TYPE S9.5C | Material |  |  | 8
3328-CO-54 | ASPHALT BINDER FOR PLANT MIX | Material |  |  | 8
3328-CO-66 | MASONARY DRAINAGE STRUCTURES | Material | Each |  | 8
3328-CO-69 | FRAME W/2 GRATES STD 840.16 | Material | Each |  | 8
3328-CO-70 | FRAME W/2 GRATES STD 840.24 | Material | Each |  | 8
3328-CO-71 | FRAME W/2 GRATES STD 840.29 | Material | Each |  | 8
3328-CO-75 | FRAME W/ COVER STD 840.54 | Material | Each |  | 8
3328-CO-XX2 | 2'-9" CONCRETE CURB | Material | Linear Feet |  | 8
3328-CO-82 | 4" SIDEWALK | Material | Square Yard |  | 8
3328-CO-86 | 5" MONO CONCRETE(KEYED IN) | Material | Square Yard |  | 8
3328-CO-98 | CONVERT EXISTING CATCH BASIN TO JB W/MH | Material | Each |  | 8
3328-CO-99 | CONVERT EXISTING DROP INLET TO JUCTION BOX | Material | Each |  | 8
3328-CO-100 | CONVERT EXISTING DROP INLET TO JUCTION BOX W/ MH | Material | Each |  | 8
3328-CO-106 | STEEL BM GUARDRAIL,DOUBLE FACE | Material | Linear Feet |  | 8
3328-CO-121 | SUPPORT 3LB STEEL U-CHANNEL | Material | Linear Feet |  | 8
3328-CO-122 | SUPPORTS,BARRIER (SMALL) | Material | Each |  | 8
3328-CO-131 | SIGN ERECTION TYPE D | Material | Each |  | 8
3328-CO-135 | SIGN ERECTION MILEMARKERS | Material | Each |  | 8
3328-CO-136 | DISPOSAL OF SIGN SYSTEM U CHANEL | Material | Each |  | 8
3328-CO-137 | DISPOSAL OF SIGN D,E,F | Material | Each |  | 8
3328-CO-XX3 | TEMPORARY TRAFFIC CONTROL | Material | Lump Sum |  | 8
3328-CO-148 | TEMPORARY CRASH CUSHION | Material | Each |  | 8
3328-CO-151 | PORTABLE CONCRETE BARRIER | Material | Linear Feet |  | 8
3328-CO-160 | TEMPORARY RAISED PAVEMENT MARKERS | Material | Linear Feet |  | 8
3328-CO-161 | THERMO 4" LINES 90 MILS | Material | Linear Feet |  | 8
3328-CO-162 | THERMO 4 " LINES 120 MILLS | Material | Linear Feet |  | 8
3328-CO-163 | THERMO 8" LINES 90 MILLS | Material | Linear Feet |  | 8
3328-CO-164 | THERMO 8" LINES 120 MILLS | Material | Linear Feet |  | 8
3328-CO-165 | THERMO 24" LINES 120 MILLS | Material | Linear Feet |  | 8
3328-CO-166 | THERMO PAVEMENT CHARACTER 120 MILLS | Material | Linear Feet |  | 8
3328-CO-167 | THERMO MARKING SYMBOL 90 MILLS | Material | Each |  | 8
3328-CO-171 | PAINT PAVEMENT MARKING LINES (4") | Material | Linear Feet |  | 8
3328-CO-172 | PAINT PAVEMENT MARKING LINES (8") | Material | Linear Feet |  | 8
3328-CO-173 | PAINT PAVEMENT MARKING LINES (24") | Material | Linear Feet |  | 8
3328-CO-175 | PAINT PAVEMENT MARKING SYMBOL | Material | Each |  | 8
3328-CO-176 | REMOVAL PAVEMENT MARKINGS 4" | Material | Linear Feet |  | 8
3328-CO-XX4 | REMOVAL OF PAVEMENT MARKINGS 8" | Material | Linear Feet |  | 8
3328-CO-178 | SNOW PLOWABLE MARKERS | Material | Each |  | 8
3328-CO-208 | PORTABLE LIGHTING | Material | Lump Sum |  | 8
3328-CO-XX5 | REMOVAL OF SYMBOL & CHARACTER | Material | Each |  | 8
3328-CO-2 | CONSTRUCTION SURVEY | Material | Lump Sum |  | 8
Cost Nov Redist | November 16 Redistribution | Material | Lump Sum |  | 8
3345 | 3345 - SR 408 Widening | Nonlabor |  |  | 1
3345-11090 | FIBER OPTIC, 6" SPLIT PVC SLEEVE (TRENCH OR PLOW) | Material | Linear Feet |  | 1
3345-11080 | FIBER OPTIC CONDUIT, 8-1" HDPE/SDR 11, TRENCH OR P | Material | Linear Feet |  | 1
3345-11070 | FIBER OPTIC CONDUIT, 1-1" HDPE/SDR 11, TRENCH OR P | Material | Linear Feet |  | 1
3345-11060 | JUNCTION BOX, F&I, MOUNTED | Material | Each |  | 1
3345-11050 | PULL & SPLICE BOX, F&I, 13"X24" COVER SIZE | Material | Each |  | 1
3345-11040 | PULL BOX (F&I) | Material | Each |  | 1
3345-11030 | FO FUSION SPLICE | Material | Each |  | 1
3345-11020 | FO SPLICE ENCLOSURE (RE-ENTRY) | Material | Each |  | 1
3345-11010 | 72SM FO CABLE (REPULL) | Material | Linear Feet |  | 1
3345-11000 | FO CONNECT. HARDWARE, F&I, PRETERM. CONNECTER AS | Material | Each |  | 1
3345-10990 | FO CONNECT. HARDWARE, F&I, SPLICE TRAY | Material | Each |  | 1
3345-10980 | FIBER OPTIC CONNECTION, INSTALL, SPLICE | Material | Each |  | 1
3345-10970 | FIBER OPTIC CABLE, RELOCATE, UNDERGROUND | Material | Linear Feet |  | 1
3345-10960 | FO CONNECT. HARDWARE, F&I, CONNECTOR PANEL | Material | Each |  | 1
3345-10950 | FO CONNECT. HARDWARE, F&I, PATCH PANEL, FIELD TERM | Material | Each |  | 1
3345-10940 | SIGNAL CABLE, REMOVE, INTERSECTION | Material |  |  | 1
3345-10930 | SIGNAL CABLE, NEW OR RECONSTRUCT INTERSECT., F&I | Material |  |  | 1
3345-10920 | FIBER OPTIC SPLICE HOUSING INVENTORY | Material | Each |  | 1
3345-10910 | FIBER OPTIC CABLE INVENTORY | Material | Each |  | 1
3345-10900 | CONDUIT, F&I, BRIDGE MOUNT | Material | Linear Feet |  | 1
3345-10890 | CONDUIT, F&I, ABOVE GROUND | Material | Linear Feet |  | 1
3345-10880 | CONDUIT, F&I, DIRECTIONAL BORE | Material | Linear Feet |  | 1
3345-10870 | CONDUIT, F&I, OPEN TRENCH | Material | Linear Feet |  | 1
3345-10860 | GEOLOCATION OF ITS EQUIPMENT AND INFRASTRUCTURE | Material | Lump Sum |  | 1
3345-10850 | CONTINUOUS OPERATION OF EXISTING ITS DEVICES | Material | Lump Sum |  | 1
3345-10840 | INSPECTOR TRAINING FOR SYSTEM AUXILIARIES | Material | Each |  | 1
3345-10830 | INSPECTOR TRAINING FOR FIBER OPTIC NETWORK | Material | Each |  | 1
3345-10820 | INSPECTOR TRAINING FOR DYNAMIC MESSAGE SIGNS | Material | Each |  | 1
3345-10810 | INSPECTOR TRAINING FOR CCTV AND CAMERA LOWERING DE | Material | Each |  | 1
3345-10800 | INSPECTOR TRAINING FOR DATA COLLECTION SENSORS | Material | Each |  | 1
3345-10790 | INSPECTOR TRAINING FOR TRAFFIC MONITORING STATION | Material | Each |  | 1
3345-10780 | PERFORMANCE TURF, SOD | Material | Square Yard |  | 1
3345-10770 | EXISTING OVERHEAD SIGN STRUCTURE UPRIGHT PAINTING | Material |  |  | 1
3345-10760 | RUMBLE STRIPS, GROUND-IN, 16" MIN. WIDTH | Material | Mile |  | 1
3345-10750 | CRASH CUSHION (QUADGUARD OR TAU II) (70 MPH) | Material | Each |  | 1
3345-10740 | GUARDRAIL - END ANCHORAGE ASSEMBLY, TYPE II | Material | Each |  | 1
3345-10730 | GUARDRAIL ANCHORAGE - CONCRETE BARRIER | Material | Each |  | 1
3345-10720 | GUARDRAIL REMOVAL | Material | Linear Feet |  | 1
3345-10710 | GUARDRAIL - BRIDGE ANCHORAGE ASSEMBLY, F&I | Material | Each |  | 1
3345-10700 | GUARDRAIL - RUBRAIL | Material | Linear Feet |  | 1
3345-10690 | GUARDRAIL -ROADWAY, DOUBLE FACE | Material | Linear Feet |  | 1
3345-10680 | GUARDRAIL -ROADWAY | Material | Linear Feet |  | 1
3345-10670 | SOUND/NOISE BARRIER-INC FOUNDATION, PERMANENT | Material | Square Feet |  | 1
3345-10660 | RIPRAP, SAND-CEMENT | Material | Cubic Yard |  | 1
3345-10650 | DETECTABLE WARNINGS | Material | Square Feet |  | 1
3345-10640 | CONCRETE SLOPE PAVEMENT, NON-REINFORCED, 3" | Material | Square Yard |  | 1
3345-10630 | CONCRETE SIDEWALK, 4" | Material | Square Yard |  | 1
3345-10620 | CONCRETE BARRIER WALL, REMOVAL | Material | Linear Feet |  | 1
3345-10610 | CONCRETE TRAFFIC RAILING-WITH JUNCTION SLAB (32" F | Material | Linear Feet |  | 1
3345-10600 | CONCRETE TRAFFIC RAILING, BRIDGE 32" F - SHAPE | Material | Linear Feet |  | 1
3345-10590 | SHOULDER GUTTER CONCRETE | Material | Linear Feet |  | 1
3345-10580 | BRIDGE DRAIN - POWER CLEAN | Material | Each |  | 1
3345-10570 | BRIDGE DRAIN | Material | Each |  | 1
3345-10560 | BRIDGE DRAIN PIPE | Material | Linear Feet |  | 1
3345-10550 | STRUCTURAL STEEL, LOW ALLOY | Material | Lump Sum |  | 1
3345-10540 | TEST PILES - STEEL, SPECIAL (18 X 204) | Material | Linear Feet |  | 1
3345-10530 | TEST PILES - STEEL, SPECIAL (14" DIAMETER PIPE) (C | Material | Linear Feet |  | 1
3345-10520 | PILES - STEEL, SPECIAL (HP 18 X 204) | Material | Linear Feet |  | 1
3345-10510 | PILES - STEEL, SPECIAL (14"DIAMETER PIPE) (CONCRET | Material | Linear Feet |  | 1
3345-10500 | PRESTRESSED BEAMS, TYPE V | Material | Linear Feet |  | 1
3345-10490 | VIDEO OF EXISTING DRAINAGE SYSTEMS (PRE AND POST C | Material | Linear Feet |  | 1
3345-10480 | U-ENDWALL WITH BAFFLES, STD 261, 1:3 SLOPE, 30" PI | Material | Each |  | 1
3345-10470 | U-ENDWALL WITH BAFFLES, STD 261, 1:3 SLOPE, 18" PI | Material | Each |  | 1
3345-10460 | PIPE CULVERT, RCP, ROUND, 30" S/CD | Material | Linear Feet |  | 1
3345-10450 | PIPE CULVERT, RCP, ROUND, 18" S/CD | Material | Linear Feet |  | 1
3345-10440 | PIPE CULVERT, CMP, ROUND, 18" GD | Material | Linear Feet |  | 1
3345-10430 | DESILTING PIPE, 37" - 48" | Material | Linear Feet |  | 1
3345-10420 | DESILTING PIPE, 25" - 36" | Material | Linear Feet |  | 1
3345-10410 | DESILTING PIPE, 0" - 24" | Material | Linear Feet |  | 1
3345-10400 | INLETS, ADJUST | Material | Each |  | 1
3345-10390 | INLETS, GUTTER TYPE S, J BOT, <10' | Material | Each |  | 1
3345-10380 | INLETS, GUTTER TYPE S, <10' | Material | Each |  | 1
3345-10370 | INLETS, DITCH BOTTOM TYPE E, PARTIAL | Material | Each |  | 1
3345-10360 | INLETS, DITCH BOTTOM TYPE B, PARTIAL | Material | Each |  | 1
3345-10350 | INLETS, DTICH BOTTOM TYPE B, J BOT, <10' | Material | Each |  | 1
3345-10340 | INLETS, DITCH BOTTOM TYPE B, <10' | Material | Each |  | 1
3345-10330 | REINFORCING STEEL - APPROACH SLABS | Material | LB |  | 1
3345-10320 | REINFORCING STEEL - SUBSTRUCTURE | Material | LB |  | 1
3345-10310 | REINFORCING STEEL - SUPERSTRUCTURE | Material | LB |  | 1
3345-10300 | COMPOSITE NEOPRENE PADS | Material | Cubic Feet |  | 1
3345-10290 | CLEANING & COATING CONCRETE SURFACE, CLASS 5 | Material | Square Feet |  | 1
3345-10280 | BRIDGE DECK GROOVING, LESS THAN 8.5" | Material | Square Yard |  | 1
3345-10270 | CONCRETE CLASS IV, MASS SUBSTRUCTURE | Material | Cubic Yard |  | 1
3345-10260 | CONCRETE CLASS IV, SUBSTRUCTURE | Material | Cubic Yard |  | 1
3345-10250 | CONCRETE CLASS II, APPROACH SLABS | Material | Cubic Yard |  | 1
3345-10240 | CONCRETE CLASS II, SUPERSTRUCTURE | Material | Cubic Yard |  | 1
3345-10230 | CONCRETE CLASS NS, GRAVITY WALL | Material | Cubic Yard |  | 1
3345-10220 | MISCELLANEOUS ASPHALT PAVEMENT | Material |  |  | 1
3345-10210 | ASPHALTIC FRICTION COURSE, TRAFFIC C, FC-12.5, PG | Material |  |  | 1
3345-10200 | ASPHALTIC FRICTION COURSE, FC-5, PG 76-22, PMA | Material |  |  | 1
3345-10190 | SUPERPAVE ASPHALTIC CONC., TRAFFIC C, PG 76-22, PM | Material |  |  | 1
3345-10180 | SUPERPAVE ASPHALTIC CONC., TRAFFIC C | Material |  |  | 1
3345-10170 | MILLING EXISTING ASPHALT PAVEMENT 0.75" DEPTH | Material | Square Yard |  | 1
3345-10160 | MILLING EXISTING ASPHALT PAVEMENT 2.75" AVG. DEPTH | Material | Square Yard |  | 1
3345-10150 | MILLING EXISTING ASPHALT PAVEMENT 2.75" DEPTH | Material | Square Yard |  | 1
3345-10140 | MILLING EXISTING ASPHALT PAVEMENT 2.25" DEPTH | Material | Square Yard |  | 1
3345-10130 | MILLING EXISTING ASPHALT PAVEMENT 1.5" DEPTH | Material | Square Yard |  | 1
3345-10120 | MILLING EXISTING ASPHALT PAVEMENT 1" DEPTH | Material | Square Yard |  | 1
3345-10110 | BASE GROUP 9 (LIMEROCK 10") | Material | Square Yard |  | 1
3345-10100 | BASE GROUP 2 (LIMEROCK 5") | Material | Square Yard |  | 1
3345-10090 | BASE GROUP 1 (LIMEROCK 4") | Material | Square Yard |  | 1
3345-10070 | EMBANKMENT | Material | Cubic Yard |  | 1
3345-10060 | REGULAR EXCAVATION | Material | Cubic Yard |  | 1
3345-10050 | REMOVAL OF EXISTING STRUCTURE | Material | Lump Sum |  | 1
3345-10040 | CLEARING AND GRUBBING | Material | Lump Sum |  | 1
3345-10030 | MOWING | Material | Lump Sum |  | 1
3345-10020 | EROSION CONTROL | Material | Lump Sum |  | 1
3345-10010 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 1
3345-10000 | MOBILIZATION | Material | Lump Sum |  | 1
3345-10080 | TYPE B STABILIZATION | Material | Square Yard |  | 1
3345-11100 | FIBER GLASS SUPPORT HANGERS FOR BRIDGEMOUNT CONDUI | Material | Each |  | 1
3345-11110 | ELEC. POWER SERVICE, F&I, UG, METER FURN. BY PWER | Material |  |  | 1
3345-11120 | ELECTRICAL SERVICE WIRE | Material | Linear Feet |  | 1
3345-11130 | PRESTRES. CONC. POLE, F&I, TYPE P-II PEDESTAL | Material | Each |  | 1
3345-11140 | PRESTRES. CONC. POLE, COMPLETE POLE REMOVE, PEDEST | Material | Each |  | 1
3345-11150 | ALUMINUM SIGNALS POLE, PEDESTAL | Material | Each |  | 1
3345-11160 | STEEL STRAIN POLE, REMOVE PEDESTAL, COMPLETE | Material | Each |  | 1
3345-11170 | MAST ARM,F&I,WIND SPEED 130,SNGL ARM,W/O LUM, 46 | Material | Each |  | 1
3345-11180 | MAST ARM,F&I,WIND SPEED 130,SNGL ARM,W/O LUM, 60 | Material | Each |  | 1
3345-11190 | MAST ARM,F&I,WIND SPEED 130,SNGL ARM,W/O LUM, 78 | Material | Each |  | 1
3345-11200 | MAST ARM,F&I, WIND SPEED 130,DBL ARM, W/O LUM,46-7 | Material | Each |  | 1
3345-11210 | MAST ARM,F&I, WIND SPEED 130,DBL ARM, W/O LUM,CUST | Material | Each |  | 1
3345-11220 | MAST ARM, REMOVE SHALLOW FOUNDATION, BOLT ON ATTAC | Material | Each |  | 1
3345-11230 | TRAFFIC SIGNAL, F&I, ALUMINUM, 3 SECTION, 1 WAY | Material |  |  | 1
3345-11240 | PEDESTRIAN SIGNAL, F&I, LED COUNTDOWN, 1 WAY | Material |  |  | 1
3345-11250 | LOOP DETECTOR INDUCTIVE, REMOVE-CABINET TO REMAIN | Material | Each |  | 1
3345-11260 | VEH. DETECTION SYS.-VIDEO, F&I, CABINET EQUIPMENT | Material | Each |  | 1
3345-11270 | VEH. DETECTION SYS.-VIDEO, F&I, ABOVE GROUND EQUIP | Material | Each |  | 1
3345-11280 | SIGNAL PRIORITY AND PREEMPTION SYS, F&I, OPTICAL, | Material | Each |  | 1
3345-11290 | SIGNAL PRIORITY AND PREEMPTION SYS, F&I, OPTICAL, | Material | Each |  | 1
3345-11300 | DCS FIELD EQUIPMENT 2 LANES (RELOCATE) | Material | Each |  | 1
3345-11310 | TRAFFIC MONITORING STATION - POLE MOUNTED (F&I) | Material | Each |  | 1
3345-11320 | TRAFFIC MONITORING STATION - POLE MOUNTED (REMOVAL | Material | Each |  | 1
3345-11330 | TRAFFIC MONITORING STATION - POLE MOUNTED (ADJUST/ | Material | Each |  | 1
3345-11340 | PEDESTRIAN DETECTOR, F&I, STANDARD | Material | Each |  | 1
3345-11350 | TYPE 170 CABINET (POLE MOUNTED) (F&I) | Material | Each |  | 1
3345-11360 | TYPE 170 CABINET (POLE MOUNTED) (REMOVAL) | Material | Each |  | 1
3345-11370 | TRAFFIC CONTROLLER AS, F&I, NEMA | Material |  |  | 1
3345-11380 | TRAFF CONTRL AS, REMOVE CONTROLLER WITH CABINET | Material |  |  | 1
3345-11390 | ETHERNET SWITCH (F&I) | Material | Each |  | 1
3345-11400 | TERMINAL SERVER (F&I) | Material | Each |  | 1
3345-11410 | FIBER OPTIC PATCH PANEL-12 PORT (F&I) | Material | Each |  | 1
3345-11420 | CUT-TO-LENGTH FIBER OPTIC JUMPER (F&I) | Material | Each |  | 1
3345-11430 | UNINTERRUPTIBLE POWER SUPPLY (F&I) | Material | Each |  | 1
3345-11440 | REMOTE POWER MANAGER (F&I) | Material | Each |  | 1
3345-11450 | CCTV FIELD ASSEMBLY (RELOCATE) | Material | Each |  | 1
3345-11460 | CAMERA LOWERING SYSTEM (50' POLE) (F&I) | Material | Each |  | 1
3345-11470 | SINGLE POST SIGN (F&I) (LESS THAN 12 SF) | Material |  |  | 1
3345-11480 | SINGLE POST SIGN (F&I) (12-20 SF) | Material |  |  | 1
3345-11490 | SINGLE POST SIGN (F&I) (21-30 SF) | Material |  |  | 1
3345-11500 | SINGLE POST SIGN (F&I) (30+ SF) | Material |  |  | 1
3345-11510 | SINGLE POST SIGN, F&I BARRIER MOUNT INDEX 11871 UP | Material |  |  | 1
3345-11520 | SINGLE POST SIGN, F&I BARRIER MOUNT INDEX 11871 12 | Material |  |  | 1
3345-11530 | SINGLE POST SIGN, F&I BRIDGE MOUNT INDEX 11870, UP | Material |  |  | 1
3345-11540 | SINGLE POST SIGN, F&I BRIDGE MOUNT INDEX 11870, 30 | Material |  |  | 1
3345-11550 | SINGLE POST SIGN, REMOVE | Material |  |  | 1
3345-11560 | MULTI POST SIGN, F&I, GROUND MOUNT, 51-100 SF | Material |  |  | 1
3345-11570 | MULTI POST SIGN, REMOVE, 21-30 SF | Material |  |  | 1
3345-11580 | MULTI POST SIGN, REMOVE, 51-100 SF | Material |  |  | 1
3345-11590 | OVERHEAD SIGN PANEL, F&I, 101-200 SF, W/ LIGHTING | Material | Each |  | 1
3345-11600 | OVERHEAD SIGN PANEL, F&I, 201-300 SF, W/ LIGHTING | Material | Each |  | 1
3345-11610 | OVERHEAD SIGN PANEL, F&I, 301-400 SF, W/ LIGHTING | Material | Each |  | 1
3345-11620 | OVERHEAD SIGN PANEL, RELOCATE, 101-200 SF, W/ LIGH | Material | Each |  | 1
3345-11630 | OVERHEAD SIGN PANEL, REMOVE, 101-200 SF, W/ LIGHTI | Material | Each |  | 1
3345-11640 | OVERHEAD SIGN PANEL, REMOVE, 201-300 SF, W/ LIGHTI | Material | Each |  | 1
3345-11650 | OVERHEAD SIGN STRUCTURE, F&I, CANTILEVER, 31-40 FT | Material | Each |  | 1
3345-11660 | OVERHEAD SIGN STRUCTURE, REMOVE CANTILEVER | Material | Each |  | 1
3345-11670 | INTERNALLY ILLUMINATED SIGN, FURNISH & INSTALL, OV | Material | Each |  | 1
3345-11680 | DELINEATOR, FLEXIBLE TUBULAR | Material | Each |  | 1
3345-11690 | RETRO-REFLECTIVE PAVEMENT MARKINGS | Material |  |  | 1
3345-11700 | THERMOPLASTIC (STANDARD) (WHITE) (6") (SOLID) | Material | Mile |  | 1
3345-11710 | THERMOPLASTIC (STANDARD) (WHITE) (12") (SOLID) | Material | Linear Feet |  | 1
3345-11720 | THERMOPLASTIC (STANDARD) (WHITE) (24") ( SOLID) | Material | Linear Feet |  | 1
3345-11730 | THERMOPLASTIC (STANDARD) (WHITE) (6") (SKIP) (2'- | Material | Mile |  | 1
3345-11740 | THERMOPLASTIC (STANDARD) (WHITE) (MESSAGE) | Material | Each |  | 1
3345-11750 | THERMOPLASTIC (STANDARD) (WHITE) (ARROWS) | Material | Each |  | 1
3345-11760 | THERMOPLASTIC (STANDARD) (WHITE) (OPTION LANE ARR | Material | Each |  | 1
3345-11770 | THERMOPLASTIC (STANDARD) (YELLOW) (6") (SOLID) | Material | Mile |  | 1
3345-11780 | THERMOPLASTIC (STANDARD) (YELLOW) (18") (SOLID) | Material | Linear Feet |  | 1
3345-11790 | THERMOPLASTIC (PREFORMED) (WHITE) (MESSAGE) | Material | Each |  | 1
3345-11800 | THERMOPLASTIC (PREFORMED) (WHITE) (ARROWS) | Material | Each |  | 1
3345-11810 | THERMOPLASTIC (REMOVAL) | Material | Lump Sum |  | 1
3345-11820 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE) (OPTION | Material | Each |  | 1
3345-11830 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE) (SOLID) | Material | Mile |  | 1
3345-11840 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE) (SOLID) | Material | Mile |  | 1
3345-11850 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE) (SOLID) | Material | Linear Feet |  | 1
3345-11860 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE) (SOLID) | Material | Linear Feet |  | 1
3345-11870 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE) (SKIP) ( | Material | Mile |  | 1
3345-11880 | PREFORMED TAPE (HIGH PERFORMANCE) (YELLOW) (SOLID) | Material | Mile |  | 1
3345-11890 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE/BLACK CON | Material | Mile |  | 1
3345-11900 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE/BLACK CON | Material | Linear Feet |  | 1
3345-11910 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE/BLACK) (S | Material | Mile |  | 1
3345-11920 | PREFORMED TAPE (HIGH PERFORMANCE) (WHITE/BLACK CON | Material | Mile |  | 1
3345-11930 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 10 OR < | Material |  |  | 1
3345-11940 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 8-6 | Material | Linear Feet |  | 1
3345-11950 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 4-2 | Material | Linear Feet |  | 1
3345-11960 | CONDUCTORS (F&I) (INSULATED) (NO. 6) | Material | Linear Feet |  | 1
3345-11970 | CONDUCTOR (F&I) (INSULATED) (NO. 12 TONE WIRE) | Material | Linear Feet |  | 1
3345-11980 | CONDUIT (F&I) (UNDERGROUND) (2" SCH 40 PVC) | Material | Linear Feet |  | 1
3345-11990 | 1-2" SCHEDULE 80 PVC CONDUIT (BRIDGEMOUNTED) (F&I) | Material | Linear Feet |  | 1
3345-12000 | 1-2" SCHEDULE 80 PVC CONDUIT (BRIDGEMOUNTED) (REMO | Material | Linear Feet |  | 1
3345-12010 | LIGHT POLE COMPLETE, RELOCATE | Material | Each |  | 1
3345-12020 | LOAD CENTER, F&I, SECONDARY VOLTAGE | Material | Each |  | 1
3345-12030 | LOAD CENTER, REMOVE, SECONDARY VOLTAGE | Material | Each |  | 1
3345-12040 | LUMINAIRE, F&I, ROADWAY, PENDANT HUNG | Material | Each |  | 1
3345-12050 | LUMINAIRE, REMOVE, UNDER DECK | Material | Each |  | 1
3345-12060 | POLE CABLE DISTRIBUTION SYSTEM, CONVENTIONAL | Material | Each |  | 1
3345-12070 | POLE CABLE DISTRIBUTION SYSTEM, WALL MOUNT | Material | Each |  | 1
3345-12080 | ARCHITECTURAL WORK | Material | Lump Sum |  | 1
3345-12090 | TRAFFIC MONITORING STATION CABLE (F&I) | Material | Linear Feet |  | 1
3345-12100 | ALLOWANCE FOR DISPUTES REVIEW BOARD | Material | Lump Sum |  | 1
3345-12110 | WORK ORDER ALLOWANCE | Material | Lump Sum |  | 1
$ | Generic Cost Loading (for Pre-Bid, Estimate, and Proposal Schedules) | Material |  |  | 1
2310010 | 2310010 - CWS | Nonlabor |  |  | 1
CWS | Chathams Ford Noisewalls | Material |  |  | 8
R-75 | Project Record Documents | Material | Lump Sum |  | 8
R-76 | Clearing and Grubbing | Material | Lump Sum |  | 8
R-77 | Pipe (18 inch reinforced concrete) | Material | Linear Feet |  | 8
R-78 | Pipe (24 inch reinforced concrete) | Material | Linear Feet |  | 8
R-79 | Endwall (EW-1 for 18 inch pipe) | Material | Each |  | 8
R-80 | Endwall (EW-2 for 24 inch pipe) | Material | Each |  | 8
R-81 | Drop Inlet (DI-7) | Material | Each |  | 8
R-82 | Concrete Ditch | Material | Square Feet |  | 8
R-83 | Precast Manhole | Material | Each |  | 8
R-84 | Earthwork | Material | Lump Sum |  | 8
R-85 | Asphalt Surface Course | Material |  |  | 8
R-86 | Erosion Control Riprap (Class A1) | Material |  |  | 8
R-87 | Gabion Stone | Material | Cubic Yard |  | 8
R-88 | Guardrail (GR-2A) | Material | Linear Feet |  | 8
R-89 | Guardrail End Terminal Treatment (GR-7) | Material | Each |  | 8
R-90 | Guardrail Trailing End Terminal (GR-11) | Material | Each |  | 8
R-91 | W-Beam Guardrail Fix Object Attachment (GR-FOA-2) | Material | Each |  | 8
R-92 | Chain Link Fence | Material | Linear Feet |  | 8
R-93 | Allaying Dust | Material | Lump Sum |  | 8
R-94 | MOT - Lane Shift | Material | Lump Sum |  | 8
R-95 | MOT - Temporary Barriers | Material | Lump Sum |  | 8
R-96 | MOT - Remove Temporary Barriers | Material | Lump Sum |  | 8
R-97 | Mobilization | Material | Lump Sum |  | 8
R-98 | Flexible Pavement Planing (0-2" depth) | Material | SYD |  | 8
R-99 | Ground Mounted Noise Wall | Material | Square Feet |  | 8
R-100 | Noise Wall Color Coating | Material | SYD |  | 8
R-101 | Class A Topsoil | Material | Cubic Yard |  | 8
R-102 | Class B Topsoil | Material | Cubic Yard |  | 8
R-103 | Turf Establishment | Material | SYD |  | 8
R-104 | Plants | Material | Lump Sum |  | 8
R-105 | Soil Stabilization Matting (Type C) | Material | SYD |  | 8
R-106 | Relocate Existing Ground Mounted Traffic Sign | Material | Square Feet |  | 8
R-107 | Pavement Line Marking (Type B, Class IV or VI) | Material | Linear Feet |  | 8
R-108 | Pavement Marker (Type B, One Way) | Material | Each |  | 8
R-109 | HOV Symbol | Material | Each |  | 8
R-110 | Utility Relocation | Material | Lump Sum |  | 8
R-111 | Stormwater Pollution Prevention | Material | Lump Sum |  | 8
3319 Crews | NAVFAC Oceana Resources | Labor |  |  | 1
EXCA CREW 1 | Excavate/Undercut/Backfill-Crew 1 | Labor |  |  | 1
EXCA CREW 2 | Excavate/Undercut/Backfill-Crew 2 | Labor |  |  | 1
FG-STN 1 | Place & Finegrade Stone Crew 1 | Labor |  |  | 1
MP-1 | Machine Paving Crew 1 | Labor |  |  | 1
HP-1 | Hand Pave Crew 1 | Labor |  |  | 1
C00100566DB63_C20 | I-66/15 Change Order #20 | Material | Lump Sum |  | 1
C00100566DB63_C21 | I-66/15 Change Order #21 | Material | Lump Sum |  | 1
Project Costs | Project Cost Breakdown | Nonlabor |  |  | 1
3346 | 3346 - MD 4 from Forestville Rd to Md Rt 458 | Nonlabor |  |  | 1
DULLESYARD | DULLESYARD - Resources | Labor |  |  | 1
MOB COST HOLDER | Mobilization | Labor |  |  | 1
ENG OFFIC COST HOLDE | Engineer's Office | Material |  |  | 8
ESC COST HOLDER | Environmental Incentive | Material | Lump Sum |  | 8
Design | Design Costs | Labor |  |  | 1
Earthwork | Earthwork Subcontractor | Labor |  |  | 1
Landscaping | Landscaping Subcontractor | Labor |  |  | 1
4SEED | Seeding Sub | Material |  |  | 8
4FUEL | Fuel | Material | Lump Sum |  | 8
Elect S | Electrical Subcontractor | Labor |  |  | 1
SIG COST HOLDER | Signal | Labor |  |  | 1
LIGHT COST HOLDER | Lighting & Electrical | Labor |  |  | 1
MARK COST HOLDER | Pavement Markings | Labor |  |  | 1
STAKEOUT COST HOLDER | Construction Stakeout | Labor |  |  | 1
CONC COST HOLDER | Concrete Flatwork | Labor |  |  | 1
MILL COST HOLDER | Milling Subcontractor | Labor |  |  | 1
3345 Rev | Revenue | Nonlabor |  |  | 0
MIP Lane CIP-1 | Lane CIP Concrete Hours | Labor |  |  | 7
MIP Lane Earth-1 | Lane Earth Hours | Labor |  |  | 8
MIP Lane Barrier-2 | Lane Barrier Hours | Labor |  |  | 14
MIP Lane Blade-2 | Lane Blade Hours | Labor |  |  | 7
MIP Lane Earth-2 | Lane Earth Hours | Labor |  |  | 8
MIP Lane CIP-2 | Lane CIP Concrete Hours | Labor |  |  | 7
MIPSCMBGF-1 | MBGF Removal/Installation Crew Hours | Labor |  |  | 5
MIPSCAARON-1-1 | Aaron Concrete T-551 Crew Hours | Labor |  |  | 15
MIPSCAARON-2-1 | Aaron Concrete Misc Concrete Crew Hours | Labor |  |  | 8
MIPSCRAMMING-1 | Austin Mat'ls Paving Crew Hours | Labor |  |  | 24
MIPSCCMPNP-1 | C&M Post & Panel Crew Hours | Labor |  |  | 5
MIPSCCMCAPS-1 | C&M DS Cap Crew Hours | Labor |  |  | 3
MIPSCFLASHER-1 | Flasher Crew Hours | Labor |  |  | 6
MIPSCINCLINE-1 | Incline - Drilled Shaft Crew Hours | Labor |  |  | 10
LEVY-1 | Levy ITS / Signage Crew Hours | Labor |  |  | 7
MIPSCMORALES-1 | Morales Crew Hours | Labor |  |  | 7
MIPSCRVI-1 | RVI - Royal Vista Crew Hours | Labor |  |  | 6
MIPSCSDP-1 | Scott Derr Painting Crew Hours | Labor |  |  | 2
MIPSCENCINO-1 | Encino Landscaping Hours | Labor |  |  | 5
CO 08 | Change Order 08 - Cost Loading USACE affected items | Material | Lump Sum |  | 8
Cost Jan Redist | January 17 Redistribution | Material | Lump Sum |  | 8
3376 | 3376 - I-395 Express Lanes | Nonlabor |  |  | 1
D-1 | 395 Express Lanes Work | Nonlabor |  |  | 1
D-2 | Additional Department Improvements Work | Nonlabor |  |  | 1
D-1-01 | EARLY WORKS - I-395 Exp Ln | Material | Lump Sum |  | 8
D-1-02 | DESIGN SERVICES | Material | Lump Sum |  | 8
D-1-03 | MOBILIZATION | Material | Lump Sum |  | 8
D-1-04 | CONSTRUCTION MANAGEMENT (QA/QC) | Material | Lump Sum |  | 8
D-1-05 | DEMOLITION | Material | Lump Sum |  | 8
D-1-06 | EARTHWORK | Material | Lump Sum |  | 8
D-1-07 | UNDERCUT UNSUITABLE SUBGRADE | Material | Cubic Yard |  | 8
D-1-08 | REPLACE SUBGRADE UNDERCUT WITH SELECT TYPE 1 FILL | Material |  |  | 8
D-1-09 | SUBGRADE STABILIZATION GEOTEXTILE FABRIC | Material | Square Yard |  | 8
D-1-10 | PAVEMENT | Material | Lump Sum |  | 8
D-1-11 | PERMANET BARRIERS | Material | Lump Sum |  | 8
D-1-12 | TRAFFIC SIGNALS | Material | Lump Sum |  | 8
D-1-13 | MARKING & SIGNING | Material | Lump Sum |  | 8
D-1-14 | LIGHTING | Material | Lump Sum |  | 8
D-1-15 | ITS / TTMS | Material | Lump Sum |  | 8
D-1-16 | DRAINAGE | Material | Lump Sum |  | 8
D-1-17 | UTILITIES | Material | Lump Sum |  | 8
D-1-18 | BRIDGE REPAIRS | Material | Lump Sum |  | 8
D-1-19 | SOUND BARRIERS | Material | Lump Sum |  | 8
D-1-20 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
D-1-21 | RIGHT-OF-WAY | Material | Lump Sum |  | 8
D-1-22 | OTHER PROJECT COST | Material | Lump Sum |  | 8
D-2-1 | EARLY WORKS - DEW | Material | Lump Sum |  | 8
D-2-2 | MOBILIZATION | Material | Lump Sum |  | 8
D-2.1 | DUKE-EDSALL WIDENING TOTAL - PART 2.1 | Nonlabor |  |  | 1
D-2.2 | SEMINARY SOUND BARRIERS TOTAL - PART 2.2 | Nonlabor |  |  | 1
D-2.3 | 395 GP LANES BRIDGES TOTAL - PART 2.3 | Nonlabor |  |  | 1
D-2.4 | PENTAGON SOUTH PARKING TOTAL - PART 2.4 | Nonlabor |  |  | 1
D-2.1-1 | DESIGN SERVICES | Material | Lump Sum |  | 8
D-2.1-2 | CONSTRUCTION MANAGEMENT (QA/QC) | Material | Lump Sum |  | 8
D-2.1-3 | DEMOLITION | Material | Lump Sum |  | 8
D-2.1-4 | EARTHWORK | Material | Lump Sum |  | 8
D-2.1-5 | PAVEMENT | Material | Lump Sum |  | 8
D-2.1-6 | PERMANENT BARRIERS | Material | Lump Sum |  | 8
D-2.1-7 | MARKING & SIGNING | Material | Lump Sum |  | 8
D-2.1-8 | LIGHTING | Material | Lump Sum |  | 8
D-2.1-9 | ITS | Material | Lump Sum |  | 8
D-2.1-10 | DRAINAGE | Material | Lump Sum |  | 8
D-2.1-11 | UTILITIES | Material | Lump Sum |  | 8
D-2.1-12 | TRAFFIC SIGNALS | Material | Lump Sum |  | 8
D-2.1-13 | SOUND BARRIERS | Material | Lump Sum |  | 8
D-2.1-14 | RETAININGS WALLS | Material | Lump Sum |  | 8
D-2.1-15 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
D-2.1-16 | RIGHT-OF-WAY | Material | Lump Sum |  | 8
D-2.1-17 | OTHER PROJECT COST | Material | Lump Sum |  | 8
D-2.2-1 | DESIGN SERVICES | Material | Lump Sum |  | 8
D-2.2-2 | CONSTRUCTION MANAGEMENT (QA/QC) | Material | Lump Sum |  | 8
D-2.2-3 | DEMOLITION | Material | Lump Sum |  | 8
D-2.2-4 | EARTHWORK | Material | Lump Sum |  | 8
D-2.2-5 | PAVEMENT | Material | Lump Sum |  | 8
D-2.2-6 | PERMANENT BARRIERS | Material | Lump Sum |  | 8
D-2.2-7 | MARKING & SIGNING | Material | Lump Sum |  | 8
D-2.2-8 | LIGHTING | Material | Lump Sum |  | 8
D-2.2-9 | ITS | Material | Lump Sum |  | 8
D-2.2-10 | DRAINAGE | Material | Lump Sum |  | 8
D-2.2-11 | UTILITIES | Material | Lump Sum |  | 8
D-2.2-12 | SOUND BARRIERS | Material | Lump Sum |  | 8
D-2.2-13 | RETAININGS WALLS | Material | Lump Sum |  | 8
D-2.2-14 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
D-2.2-15 | RIGHT-OF-WAY | Material | Lump Sum |  | 8
D-2.2-16 | OTHER PROJECT COST | Material | Lump Sum |  | 8
D-2.3-1 | DECK EVALUATION | Material | Lump Sum |  | 8
D-2.3-2 | SUPERSTRUCTURE EVAULATION | Material | Lump Sum |  | 8
D-2.3-3 | SUBSTRUCTURE EVAULATION | Material | Lump Sum |  | 8
D-2.3-4 | PATCHING (TYPE B) | Material | Lump Sum |  | 8
D-2.3-5 | REPLACE EXISTING BRIDGE BARRIER (DECK) | Material | Lump Sum |  | 8
D-2.3-6 | MODIFY APPROACH BARRIER / GUARDRAIL | Material | Lump Sum |  | 8
D-2.3-7 | TYPE A MILLING (1") | Material | Lump Sum |  | 8
D-2.3-8 | TYPE A MILLING (3/4") | Material | Lump Sum |  | 8
D-2.3-9 | TYPE A HYDRO-DEMOLITION (3/4") | Material | Lump Sum |  | 8
D-2.3-10 | FURNISH (VESLM) CONCRETE (1 1/2" TO 2") | Material | Lump Sum |  | 8
D-2.3-11 | PLACE (VESLM) CONCRETE | Material | Lump Sum |  | 8
D-2.3-12 | EXPENSION JOINT RECONSTRUCTION (VESLM) CONCRETE | Material | Lump Sum |  | 8
D-2.3-13 | DECK SLAB CLOSURE (VESLM) CONCRETE | Material | Lump Sum |  | 8
D-2.3-14 | BRIDGE-DECK GROOVING | Material | Lump Sum |  | 8
D-2.3-15 | ULTRASONIC IMPACT TREATMENT | Material | Lump Sum |  | 8
D-2.3-16 | REPLACE BEARINGS | Material | Lump Sum |  | 8
D-2.3-17 | JACKING AND BLOCKING BEAM | Material | Lump Sum |  | 8
D-2.3-18 | ZINC COATING OF EXISTING STRUCTURE NO. 2040-HOV | Material | Lump Sum |  | 8
D-2.3-19 | PREPARE AND OVERCOAT EXISTING STRUCTURE NO. 2805-HOV | Material | Lump Sum |  | 8
D-2.3-20 | PREPARE AND OVERCOAT EXISTING STRUCTURE NO. 2040-NB GP | Material | Lump Sum |  | 8
D-2.3-21 | CRACK REPAIR TYPE B (EPOXY INJECTION) | Material | Lump Sum |  | 8
D-2.3-22 | WATERPROOFING COATING | Material | Lump Sum |  | 8
D-2.3-23 | WATERPROOFING - EPOXY RESIN (TYPE EP-5) | Material | Lump Sum |  | 8
D-2.4-1 | DESIGN SERVICES | Material | Lump Sum |  | 8
D-2.4-2 | CONSTRUCTION MANAGEMENT (QA/QC) | Material | Lump Sum |  | 8
D-2.4-3 | DEMOLITION | Material | Lump Sum |  | 8
D-2.4-4 | EARTHWORK | Material | Lump Sum |  | 8
D-2.4-5 | PAVEMENT | Material | Lump Sum |  | 8
D-2.4-6 | PERMANENT BARRIERS | Material | Lump Sum |  | 8
D-2.4-7 | MARKING & SIGNING | Material | Lump Sum |  | 8
D-2.4-8 | LIGHTING | Material | Lump Sum |  | 8
D-2.4-9 | ITS | Material | Lump Sum |  | 8
D-2.4-10 | DRAINAGE | Material | Lump Sum |  | 8
D-2.4-11 | UTILITIES | Material | Lump Sum |  | 8
D-2.4-12 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
D-2.4-13 | OTHER PROJECT COST | Material | Lump Sum |  | 8
D-2.3-24 | CONCRETE SUBSTRUCTURE SURFACE REPAIR | Material | Lump Sum |  | 8
PRPK | Resources for PRPK | Nonlabor |  |  | 1
Cost Feb Redist | Feburary 17 Redistribution | Material | Lump Sum |  | 8
XXXX | Purple Line | Nonlabor |  |  | 1
2310013 | Holmes Run Bike Trail | Nonlabor |  |  | 1
COST | COST | Labor |  |  | 1
MOPAC-CONST | CONSTRUCTION | Labor |  |  | 1
MIP Lane Demo-2 | Lane Demo Hours | Labor |  |  | 6
MIP Lane Flow Fill-2 | Lane Flow Fill Hours | Labor |  |  | 7
MIP Lane Misc-2 | Lane Misc Hours | Labor |  |  | 6
PFC | PFC | Material |  |  | 8
MIPSCAARON4-1 | Aaron Dirt Crew Hours | Labor |  |  | 6
MIPSCAARON-3-1 | Aaron Concrete Milling Crew Hours | Labor |  |  | 3
Zipper | Zipper Barrier | Nonlabor |  |  | 1
Zip1 | Zipper Barrier - 35th to 45th - Outside | Nonlabor |  |  | 1
Zip2 | Zipper Barrier - 35th to 45th - Inside | Nonlabor |  |  | 1
Zip4 | Zipper Barrier - Enfield to Westover - Inside | Nonlabor |  |  | 1
Zip5 | Zipper Barrier - Westover to 35th Inside | Nonlabor |  |  | 1
Zip3 | Zipper Barrier - 45th to 2222 - Outside | Nonlabor |  |  | 1
Kapsch | CTRMA Subcontractor | Labor |  |  | 1
C00100566DB63_C22 | I-66/15 Change Order #22 | Material | Lump Sum |  | 8
EW- ALL EW | Earthwork Grade Crew - Combo | Labor |  | Earthwork Crew | 1
DRAIN | Drainage Crew - Combo | Labor |  | Drainage Crew | 1
ST-BRIDGE-ALL | Bridge Crew - Combo | Labor |  | Structures Crew | 1
C00108069DB87.WO1 | WORK ORDER #1 | Material | Lump Sum |  | 1
2310013.1000 | Mobilization | Material | Lump Sum |  | 1
2310013.1010 | Maintenance of Traffic | Material | Lump Sum |  | 1
2310013.1020 | Removal of Existing Concrete Trail along Trail A | Material | Lump Sum |  | 1
2310013.1030 | Clearing and Grubbing | Material | Lump Sum |  | 1
2310013.1040 | Regular Excavation | Material | Lump Sum |  | 1
2310013.1050 | Concrete Class A3 Misc | Material | Lump Sum |  | 1
2310013.1060 | Temporary Causeway | Material | Lump Sum |  | 1
2310013.1070 | Aggregate Material Type I No. 21A | Material | Lump Sum |  | 1
2310013.1080 | Asphalt Concrete Type SM-9.5A | Material | Lump Sum |  | 1
2310013.1090 | Asphalt Concrete Type BM-25.0A | Material | Lump Sum |  | 1
2310013.1100 | NS Saw-Cut Asphalt Concrete | Material | Lump Sum |  | 1
2310013.1120 | NS Saw-Cut Hydraulic Cement Concrete Pavement | Material | Lump Sum |  | 1
2310013.1130 | Std. Curb CSCG-1 (Coping Curb) | Material | Lump Sum |  | 1
2310013.1140 | Std. Curb CSCG-1 (Comb. Curb and Gutter) | Material | Lump Sum |  | 1
2310013.1110 | CG-12 Detectable Warning Surface | Material | Lump Sum |  | 1
2310013.1150 | Remove Comb. Curb and Gutter | Material | Lump Sum |  | 1
2310013.1160 | Saw-Cut Sidewalk | Material | Lump Sum |  | 1
2310013.1170 | Fence FE-CL (dark green, PVC coated CL 2b) | Material | Lump Sum |  | 1
2310013.1180 | Demolition of Pavement (Rigid) | Material | Lump Sum |  | 1
2310013.1190 | Demolition of Pavement (Flexible) | Material | Lump Sum |  | 1
2310013.1200 | Weir Demolition | Material | Lump Sum |  | 1
2310013.1210 | Remove Existing Curb | Material | Lump Sum |  | 1
2310013.1220 | Handrail HR-1, Type III | Material | Lump Sum |  | 1
2310013.1230 | Sign Panels | Material | Lump Sum |  | 1
2310013.1240 | Sign Post STP-1, 2 Inch | Material | Lump Sum |  | 1
2310013.1250 | Concrete Foundation STP-1 | Material | Lump Sum |  | 1
2310013.1260 | NS Remove and Dispose of Existing Sign | Material | Lump Sum |  | 1
2310013.1270 | Type B Class I Pavement Line Marking 6-inches | Material | Lump Sum |  | 1
2310013.1280 | Bridge Erection | Material | Lump Sum |  | 1
2310013.1290 | Retaining Wall RW-3 | Material | Lump Sum |  | 1
2310013.1300 | Dry Riprap Class A1 | Material | Lump Sum |  | 1
2310013.1310 | Bridge Superstructure - Elastomeric Bearing Pads | Material | Lump Sum |  | 1
2310013.1320 | Bridge Superstructure - Prefabricated Steel Trusse | Material | Lump Sum |  | 1
2310013.1330 | (New ResourceSelect Material Type I Min CBR 30 | Material | Lump Sum |  | 1
2310013.1340 | Structural Excavation | Material | Lump Sum |  | 1
2310013.1350 | Geocomposite Wall Drain | Material | Lump Sum |  | 1
2310013.1360 | Underdrain - Pipe Underdrain 6" (Non-Perforated Sc | Material | Lump Sum |  | 1
2310013.1370 | Underdrain - Pipe Underdrain 4" (Non-Perforated Sc | Material | Lump Sum |  | 1
2310013.1380 | Pre-Boring in Soil for H-Piles at Retaining Wall 1 | Material | Lump Sum |  | 1
2310013.1390 | Pre-Boring in Rockl for H-Piles at Retaining Wall 1 | Material | Lump Sum |  | 1
2310013.1400 | Pre-Boring in Soil for Drilled Shaft (36-inch Dia. | Material | Lump Sum |  | 1
2310013.1410 | Pre-Boring in Rock for Drilled Shaft (36-inch Dia. | Material | Lump Sum |  | 1
2310013.1420 | Temporary Sheet Piling | Material | Lump Sum |  | 1
2310013.1430 | Steel Piles - 14-inch | Material | Lump Sum |  | 1
2310013.1440 | Concrete Class A3 - Substructure | Material | Lump Sum |  | 1
2310013.1450 | Concrete Class A4 - Augured Shafts at Retaining Wall | Material | Lump Sum |  | 1
2310013.1460 | Reinforcing Steel | Material | Lump Sum |  | 1
2310013.1470 | Precast Concrete Lagging Panel | Material | Lump Sum |  | 1
2310013.1480 | Type B Patching | Material | Lump Sum |  | 1
2310013.1490 | Crack Repair | Material | Lump Sum |  | 1
2310013.1500 | Storm Sewer Pipe 18-inch | Material | Lump Sum |  | 1
2310013.1510 | Class A-3 Concrete (EW-1 18") | Material | Lump Sum |  | 1
2310013.1520 | MH-1 or MH-2 | Material | Lump Sum |  | 1
2310013.1530 | Standard Frame and Cover | Material | Lump Sum |  | 1
2310013.1540 | EC-1 Riprap Class 1 | Material | Lump Sum |  | 1
2310013.1550 | Temporary Inlet Protection | Material | Lump Sum |  | 1
2310013.1560 | Temporary Silt Fence | Material | Lump Sum |  | 1
2310013.1570 | Temporary Tree Protection | Material | Lump Sum |  | 1
2310013.1580 | Root Pruning | Material | Lump Sum |  | 1
2310013.1590 | Temporary Safety Fence | Material | Lump Sum |  | 1
2310013.1600 | Temporary Construction Entrance | Material | Lump Sum |  | 1
2310013.1610 | Temporary Culverts | Material | Lump Sum |  | 1
2310013.1620 | Temporary Pipe Extension | Material | Lump Sum |  | 1
2310013.1630 | Siltation Control Excavation | Material | Lump Sum |  | 1
2310013.1640 | Maintenance of Stream Flow ( Pumps, Pipes, Filter) | Material | Lump Sum |  | 1
2310013.1650 | Dewatering Basin | Material | Lump Sum |  | 1
2310013.1660 | Temporary Seeding | Material | Lump Sum |  | 1
2310013.1670 | Fertilizer | Material | Lump Sum |  | 1
2310013.1680 | Lime | Material | Lump Sum |  | 1
2310013.1690 | Mulch | Material | Lump Sum |  | 1
2310013.1700 | Stream Restoration Excavation | Material | Lump Sum |  | 1
2310013.1710 | Furnished Stream Gravel | Material | Lump Sum |  | 1
2310013.1720 | Boulders | Material | Lump Sum |  | 1
2310013.1730 | Bank Stabilization Matting | Material | Lump Sum |  | 1
2310013.1740 | Invasive Species Treatment | Material | Lump Sum |  | 1
2310013.1750 | Floodplain Seed Mix | Material | Lump Sum |  | 1
2310013.1760 | Adjust Existing Frame & Cover | Material | Lump Sum |  | 1
3347 | 3347 - MD 5 at Brandywine Road | Nonlabor |  |  | 1
3347.DEM.M | Medium Site Demo | Labor |  |  | 1
3347.DEAWDO | Dewater Pond/Trap | Nonlabor |  |  | 1
3347.ESC-2 | Sediment Control Maintenance | Labor |  |  | 1
3347.ESC01 | Erosion & Sediment Control | Labor |  |  | 1
3347.EXC02 | Load Excavation | Labor |  |  | 1
3347.EXC03 | Load Mass Excavation | Labor |  |  | 1
3347.EXC06 | Compact Fill | Labor |  |  | 1
3347.EXC07 | Dozer Excavation | Labor |  |  | 1
3347.EXC09 | Mass Grading | Labor |  |  | 1
3347.EXC10 | Gradall Excavation | Labor |  |  | 1
3347.EXC11 | Respread Topsoil | Labor |  |  | 1
3347.EXC12 | Structural Backfill | Labor |  |  | 1
3347.EXCTP | Test Pit | Labor |  |  | 1
3347.MOT01 | Small MOT Crew (3Men) | Labor |  |  | 1
3347.MOT03 | Large MOT Crew (6Men) | Labor |  |  | 1
3347.MOT10 | Set Barrier Crew (1 Crew) | Labor |  |  | 1
3347.MOT11 | Reset Barrier Crew (2 Crews) | Labor |  |  | 1
3347.MPLCTS | Place Topsoil in Common Area | Labor |  |  | 1
3347.MRGRD | Grade Roads/Pkg Lots | Labor |  |  | 1
3347.MSWMEX | Bioretention Excavation | Labor |  |  | 1
3347.MTEX7 | Roadway Excavation | Labor |  |  | 1
3347.MTEXGR | Small Rough Grading | Labor |  |  | 1
3347.MVO-CO | Core Trench Excavation | Labor |  |  | 1
3347.MVOL-0 | Strip Topsoil w/ End Dumps | Labor |  |  | 1
3347.MVOL-2 | End Dump Medium Haul | Labor |  |  | 1
3347.MVOLPE | Pond Excavation | Labor |  |  | 1
3347.PIL01 | Pile Driving | Labor |  |  | 1
3347.ROUGH | Rough Grading | Labor |  |  | 1
3347.S1 | Concrete Fab, Small (6 Men) | Labor |  |  | 1
3347.S2 | Concrete E/S Forms, Medium (8 Men) | Labor |  |  | 1
3347.S3 | Concrete Pour, Large (12 Men) | Labor |  |  | 1
3347.SCREEN | Screening Crew | Labor |  |  | 1
3347.STONE3 | GAB Placement | Labor |  |  | 1
3347.STONE4 | Sidewalk/Path GAB Placement | Labor |  |  | 1
3347.STR20 | Unload Rebar | Labor |  |  | 1
3347.SUR01 | Survey, 2 Man | Labor |  |  | 1
3347.USD01 | Heavy Utility Crew | Labor |  |  | 1
3347.USD02 | Standard Utility Crew | Labor |  |  | 1
3347.USD03 | Small Utility Crew | Labor |  |  | 1
3347.USD10 | Rip Rap Placement | Labor |  |  | 1
NEORSD#1294 | NEORSD #1294 | Nonlabor |  |  | 1
NEORSD#1294-LAB | NEORSD#1294 Labor | Nonlabor |  |  | 1
NEORSD#1294-MAT | NEORSD#1294-Material | Material | Lump Sum |  | 1
01Fab | Tunnel Fabrication | Material |  |  | 8
02Del | Tunnel Delivery | Material |  |  | 8
03Install | Tunnel Installation | Material |  |  | 8
3364 | 3364 - Fm 1431 Williamson | Nonlabor |  |  | 1
3364.100.6002 | PREPARING ROW | Material | Station |  | 8
3364.104.6015 | REMOVING CONC (SIDEWALKS) | Material | Square Yard |  | 8
3364.104.6017 | REMOVING CONC (DRIVEWAYS) | Material | Square Yard |  | 8
3364.104.6022 | REMOVING CONC CURB AND GUTTER | Material | Linear Feet |  | 8
3364.104.6028 | REMOVING CONC (MISC) | Material | Square Yard |  | 8
3364.104.6040 | REMOVING CONC (PAVERS) | Material | Square Yard |  | 8
3364.104.6054 | REMOVING CONCRETE(MOW STRIP) | Material | Linear Feet |  | 8
3364.110.6001 | EXCAVATION (ROADWAY) | Material | Cubic Yard |  | 8
3364.110.6002 | EXCAVATION (CHANNEL) | Material | Cubic Yard |  | 8
3364.132.6003 | EMBANKMENT FINAL ORD COMP TY C | Material | Cubic Yard |  | 8
3364.160.6003 | FURNISH & PLACING TOPSOIL 4" | Material | Square Yard |  | 8
3364.164.6003 | BROADCAST SEED PERM RURAL CLAY | Material | Square Yard |  | 8
3364.164.6009 | BROADCAST SEED TEMP WARM | Material | Square Yard |  | 8
3364.164.6011 | BROADCAST SEED TEMP COOL | Material | Square Yard |  | 8
3364.168.6001 | VEGETATIVE WATERING | Material | Gallon |  | 8
3364.169.6001 | SOIL RETEN BLANKETS CL 1 TY A | Material | Square Yard |  | 8
3364.247.6366 | FL BS CMP PLC TY A GR 5 FNAL | Material | Cubic Yard |  | 8
3364.310.6027 | PRIME COAT(MC-30 OR AE-P) | Material | Gallon |  | 8
3364.316.6001 | ASPH (MULTI OPTION) | Material | Gallon |  | 8
3364.340.6122 | D-GR HMASQ TY-D PG7022 | Material |  |  | 8
3364.340.6244 | D-GR HMASQ TYC PG6422 LEVELUP | Material |  |  | 8
3364.341.6008 | D-GR HMA TY-B PG64-22 | Material |  |  | 8
3364.347.6003 | TOM (ASPHALT) PG 70-22 | Material |  |  | 8
3364.347.6006 | TOM - C (AGGREGATE) SAC - B | Material |  |  | 8
3364.354.6021 | PLANE ASPH CONC PAV 0" TO 2" | Material | Square Yard |  | 8
3364.400.6005 | CEM STABIL BKFL | Material | Cubic Yard |  | 8
3364.402.6001 | TRENCH EXCAVATION PROTECTION | Material | Linear Feet |  | 8
3364.411.6001 | ROCK NAIL ANCHORS | Material | Linear Feet |  | 8
3364.416.6004 | DRILL SHAFT (36 IN) | Material | Linear Feet |  | 8
3364.416.6005 | DRILL SHAFT (42 IN) | Material | Linear Feet |  | 8
3364.416.6034 | DRILL SHAFT TRF SIG POLE 48 IN | Material | Linear Feet |  | 8
3364.420.6011 | CL B CONC (FLUME) | Material | Cubic Yard |  | 8
3364.420.6013 | CL C CONC (ABUT) | Material | Cubic Yard |  | 8
3364.420.6025 | CL C CONC (BENT) | Material | Cubic Yard |  | 8
3364.422.6001 | REINF CONC SLAB | Material | Square Feet |  | 8
3364.422.6013 | BRIDGE SIDEWALK | Material | Square Feet |  | 8
3364.422.6015 | APPROACH SLAB | Material | Cubic Yard |  | 8
3364.423.6001 | RETAINING WALL (MSE) | Material | Square Feet |  | 8
3364.423.6003 | RETAINING WALL (TEMP WALL) | Material | Square Feet |  | 8
3364.423.6007 | RETAINING WALL DS FACIA | Material | Square Feet |  | 8
3364.423.6023 | RETAINING WALL ROCK NAIL FACIA | Material | Square Feet |  | 8
3364.425.6037 | PRESTR CONC GIRDER (TX40) | Material |  |  | 8
3364.432.6001 | RIPRAP (CONC)(4 IN) | Material | Cubic Yard |  | 8
3364.432.6045 | RIPRAP (MOW STRIP)(4 IN) | Material | Cubic Yard |  | 8
3364.432.6059 | SALVAGED ROCK RIPRAP (DRY) | Material | Square Yard |  | 8
3364.442.6007 | STR STEEL (MISC NON - BRIDGE) | Material | Per Pound |  | 8
3364.450.6004 | RAIL (TY T221) | Material | Linear Feet |  | 8
3364.450.6014 | RAIL (TY T551) | Material | Linear Feet |  | 8
3364.450.6030 | RAIL (TY C221) | Material | Linear Feet |  | 8
3364.450.6042 | RAIL (TY PR1) | Material | Linear Feet |  | 8
3364.454.6004 | ARMOR JOINT (SEALED) | Material | Linear Feet |  | 8
3364.462.6007 | CONC BOX CULV (5 FT X 3 FT) | Material | Linear Feet |  | 8
3364.464.6003 | RC PIPE (CL III)(18 IN) | Material | Linear Feet |  | 8
3364.464.6005 | RC PIPE (CL III)(24 IN) | Material | Linear Feet |  | 8
3364.464.6008 | RC PIPE (CL III)(36 IN) | Material | Linear Feet |  | 8
3364.464.6010 | RC PIPE (CL III)(48 IN) | Material | Linear Feet |  | 8
3364.464.6024 | RC PIPE (CL V)(12 IN) | Material | Linear Feet |  | 8
3364.465.6002 | MANH (COMPL)(PRM)(48IN) | Material | Each |  | 8
3364.465.6008 | JCTBOX(COMPL)(PJB)(4FTX5FT) | Material | Each |  | 8
3364.465.6011 | JCTBOX(COMPL)(PJB)(6FTX6FT) | Material | Each |  | 8
3364.465.6012 | JCTBOX(COMPL)(PJB)(8FTX8FT) | Material | Each |  | 8
3364.465.6014 | INLET (COMPL)(PCO)(3FT)(LEFT) | Material | Each |  | 8
3364.465.6015 | INLET (COMPL)(PCO)(3FT)(RIGHT) | Material | Each |  | 8
3364.465.6016 | INLET (COMPL)(PCO)(3FT)(BOTH) | Material | Each |  | 8
3364.465.6018 | INLET (COMPL)(PCO)(4FT)(LEFT) | Material | Each |  | 8
3364.465.6020 | INLET (COMPL)(PCO)(4FT)(BOTH) | Material | Each |  | 8
3364.465.6130 | INLET COMPL PSL FG 3'x5'-3'x5' | Material | Each |  | 8
3364.465.6147 | INLET COMP PSL SFG 4'x4'-4'x4' | Material | Each |  | 8
3364.465.6256 | INLET(COMPL)(CURB)(SPL) | Material | Each |  | 8
3364.466.6095 | HEADWALL CH - PW - 0 DIA= 18" | Material | Each |  | 8
3364.466.6194 | WINGWALL (PW - 2) (HW=5 FT) | Material | Each |  | 8
3364.467.6319 | SET (TY II) 12" CMP 6: 1 (P) | Material | Each |  | 8
3364.467.6363 | SET (TY II) 18" RCP 6: 1 (P) | Material | Each |  | 8
3364.467.6395 | SET (TY II) 24" RCP 6: 1 (P) | Material | Each |  | 8
3364.467.6454 | SET (TY II) 36" RCP 6: 1 (P) | Material | Each |  | 8
3364.467.6475 | SET (TY II) 48" RCP 3: 1 (P) | Material | Each |  | 8
3364.479.6001 | ADJUST MANHOLES | Material | Each |  | 8
3364.479.6005 | ADJUST MANHOLES WTR VALVE BOX | Material | Each |  | 8
3364.496.6002 | REMOV STR (INLET) | Material | Each |  | 8
3364.496.6004 | REMOV STR (SET) | Material | Each |  | 8
3364.496.6007 | REMOV STR (PIPE) | Material | Linear Feet |  | 8
3364.496.6008 | REMOV STR (BOX CULVERT) | Material | Linear Feet |  | 8
3364.496.6010 | REMOV STR (BRIDGE 100 - 499') | Material | Each |  | 8
3364.500.6001 | MOBILIZATION | Material | Lump Sum |  | 8
3364.502.6001 | BARRICADES, SIGNS & TRAF HANDLE | Material | Month |  | 8
3364.506.6002 | ROCK FILTER DAMS INSTALL TY 2 | Material | Linear Feet |  | 8
3364.506.6011 | ROCK FILTER DAMS (RMV) | Material | Linear Feet |  | 8
3364.506.6020 | CONST EXITS (INST) (TY 1) | Material | Square Yard |  | 8
3364.506.6024 | CONST EXITS (RMV) | Material | Square Yard |  | 8
3364.506.6038 | TEMP SEDMT CONT FENCE INST | Material | Linear Feet |  | 8
3364.506.6039 | TEMP SEDMT CONT FENCE RMV | Material | Linear Feet |  | 8
3364.512.6005 | PORT CTB FUR & INST FSHAPE TY1 | Material | Linear Feet |  | 8
3364.512.6029 | PORT CTB MOVE FSHAPE TY1 | Material | Linear Feet |  | 8
3364.512.6049 | PORT CTB RMV SGL SLP TY1 | Material | Linear Feet |  | 8
3364.512.6053 | PORT CTB RMV F-SHAPE TY 1 | Material | Linear Feet |  | 8
3364.528.6004 | LANDSCAPE PAVERS | Material | Square Yard |  | 8
3364.529.6008 | CONC CURB & GUTTER TY II | Material | Linear Feet |  | 8
3364.529.6015 | CONC CURB (TY C1) | Material | Linear Feet |  | 8
3364.529.6027 | CONC CURB (TY C2) | Material | Linear Feet |  | 8
3364.530.6004 | DRIVEWAYS (CONC) | Material | Square Yard |  | 8
3364.531.6001 | CONC SIDEWALKS (4") | Material | Square Yard |  | 8
3364.531.6003 | CONC SIDEWALKS (6") | Material | Square Yard |  | 8
3364.531.6004 | CURB RAMPS (TY 1) | Material | Each |  | 8
3364.540.6001 | MTL W-BEAM GD FEN (TIM POST) | Material | Linear Feet |  | 8
3364.540.6006 | MTL BEAM GD FEN TRAN TRI-BEAM | Material | Each |  | 8
3364.540.6016 | DOWNSTREAM ANCHOR TERM SECT | Material | Each |  | 8
3364.542.6001 | RMV METAL BEAM GUARD FENCE | Material | Linear Feet |  | 8
3364.542.6003 | RMV DOWNSTREAM ANCHOR TERM | Material | Linear Feet |  | 8
3364.542.6004 | RM MTL BM GD FEN TRAN TRI-BEAM | Material | Each |  | 8
3364.544.6001 | GUARDRAIL END TREATMENT INST | Material | Each |  | 8
3364.544.6003 | GUARDRAIL END TREATMENT RMV | Material | Each |  | 8
3364.545.6001 | CRASH CUSH ATTEN (INSTL) | Material | Each |  | 8
3364.545.6003 | CRASH CUSH ATTEN MOVE & RESET | Material | Each |  | 8
3364.545.6005 | CRASH CUSH ATTEN (REMOVE) | Material | Each |  | 8
3364.550.6001 | CHAIN LINK FENCE (INST) (6') | Material | Linear Feet |  | 8
3364.556.6008 | PIPE UNDERDRAINS (TY 8) (6") | Material | Linear Feet |  | 8
3364.618.6023 | CONDT (PVC) (SCH 40) (2") | Material | Linear Feet |  | 8
3364.618.6029 | CONDT (PVC) (SCH 40) (3") | Material | Linear Feet |  | 8
3364.618.6033 | CONDT (PVC) (SCH 40) (4") | Material | Linear Feet |  | 8
3364.618.6047 | CONDT (PVC) (SCH 80) (2") BORE | Material | Linear Feet |  | 8
3364.618.6054 | CONDT (PVC) (SCH 80) (3") BORE | Material | Linear Feet |  | 8
3364.620.6004 | ELEC CONDR (NO.12) INSULATED | Material | Linear Feet |  | 8
3364.620.6007 | ELEC CONDR (NO.8) BARE | Material | Linear Feet |  | 8
3364.620.6008 | ELEC CONDR (NO.8) INSULATED | Material | Linear Feet |  | 8
3364.620.6009 | ELEC CONDR (NO.6) BARE | Material | Linear Feet |  | 8
3364.620.6010 | ELEC CONDR (NO.6) INSULATED | Material | Linear Feet |  | 8
3364.624.6009 | GROUND BOX TY D 162922 | Material | Each |  | 8
3364.624.6010 | GROUND BOX TY D 162922 W/APRON | Material | Each |  | 8
3364.628.6215 | ELC SRV TY D 120/240 100 NS AL | Material | Each |  | 8
3364.644.6001 | SM RD SN SUP&AM TY10BWG 1 SA P | Material | Each |  | 8
3364.644.6004 | SM RD SN SUP&AM TY10BWG 1 SA T | Material | Each |  | 8
3364.644.6037 | SM RD SN SUP&AM TYS80 1 SA UWC | Material | Each |  | 8
3364.644.6068 | RELCT SM RD SN SUP&AM TY 10BWG | Material | Each |  | 8
3364.644.6070 | RELCT SM RD SN SUP&AM TY S80 | Material | Each |  | 8
3364.644.6076 | REMOVE SM RD SN SUP&AM | Material | Each |  | 8
3364.658.6013 | INST DEL ASSM D-SW SZ BRF CTB | Material | Each |  | 8
3364.658.6015 | INST DEL ASSM D-SW SZ BRF GF1 | Material | Each |  | 8
3364.662.6001 | WK ZN PAV MRK NON-RMV W 4" BRK | Material | Linear Feet |  | 8
3364.662.6002 | WK ZN PAV MRK NON-RMV W 4" DOT | Material | Linear Feet |  | 8
3364.662.6004 | WK ZN PAV MRK NON-RMV W 4" SLD | Material | Linear Feet |  | 8
3364.662.6012 | WK ZN PAV MRK NON-RMV W 8" SLD | Material | Linear Feet |  | 8
3364.662.6016 | WK ZN PAV MRK NON-RMV W 24"SLD | Material | Linear Feet |  | 8
3364.662.6017 | WK ZN PAV MRK NON-RMV W ARROW | Material | Linear Feet |  | 8
3364.662.6029 | WK ZN PAV MRK NON-RMV W WORD | Material | Linear Feet |  | 8
3364.662.6034 | WK ZN PAV MRK NON-RMV Y 4" SLD | Material | Linear Feet |  | 8
3364.662.6060 | WK ZN PAV MRK REMOV (W)4" BRK | Material | Linear Feet |  | 8
3364.662.6063 | WK ZN PAV MRK REMOV (W)4" SLD | Material | Linear Feet |  | 8
3364.662.6095 | WK ZN PAV MRK REMOV (Y)4" SLD | Material | Linear Feet |  | 8
3364.666.6006 | REF PAV MK TYI W 4" DOT 100MIL | Material | Linear Feet |  | 8
3364.666.6036 | REF PAV MK TYI W 8" SLD 100MIL | Material | Linear Feet |  | 8
3364.666.6042 | REF PAV MK TY I W 12" SLD 100MIL | Material | Linear Feet |  | 8
3364.666.6048 | REF PAV MK TY I W 24" SLD 100MIL | Material | Linear Feet |  | 8
3364.666.6054 | REF PAV MK TY I W ARROW 100MIL | Material | Each |  | 8
3364.666.6078 | REF PAV MK TY I W WORD 100MIL | Material | Each |  | 8
3364.666.6099 | REF PAV MK TYI W 18" Y TRI 100 | Material | Linear Feet |  | 8
3364.666.6167 | REFL PAV MRK TY II W 4" BRK | Material | Linear Feet |  | 8
3364.666.6168 | REFL PAV MRK TY II W 4" DOT | Material | Linear Feet |  | 8
3364.666.6170 | REFL PAV MRK TY II W 4" SLD | Material | Linear Feet |  | 8
3364.666.6178 | REFL PAV MRK TY II W 8" SLD | Material | Linear Feet |  | 8
3364.666.6180 | REFL PAV MRK TY II W 12" SLD | Material | Linear Feet |  | 8
3364.666.6182 | REFL PAV MRK TY II W 24" SLD | Material | Linear Feet |  | 8
3364.666.6184 | REFL PAV MRK TY II W ARROW | Material | Each |  | 8
3364.666.6192 | REFL PAV MRK TY II W WORD | Material | Each |  | 8
3364.666.6198 | REFL PAV MRK TY II W 18" YLD TRI | Material | Each |  | 8
3364.666.6207 | REFL PAV MRK TY II Y 4" SLD | Material | Linear Feet |  | 8
3364.666.6300 | RE PM W/RET RE TYI W4"BRK100ML | Material | Linear Feet |  | 8
3364.666.6303 | RE PM W/RET RE TYI W4"SLD100MIL | Material | Linear Feet |  | 8
3364.666.6315 | RE PM W/RET RE TYI Y4"SLD100MIL | Material | Linear Feet |  | 8
3364.672.6007 | REFL PAV MRKR TY I-C | Material | Each |  | 8
3364.672.6009 | REFL PAV MRKR TY II-A-A | Material | Each |  | 8
3364.672.6010 | REFL PAV MRKR TY II-C-R | Material | Each |  | 8
3364.677.6001 | ELIM EXT PAV MRK & MRKS (4") | Material | Linear Feet |  | 8
3364.677.6003 | ELIM EXT PAV MRK & MRKS (8") | Material | Linear Feet |  | 8
3364.677.6005 | ELIM EXT PAV MRK & MRKS (12") | Material | Linear Feet |  | 8
3364.677.6007 | ELIM EXT PAV MRK & MRKS (24") | Material | Linear Feet |  | 8
3364.677.6008 | ELIM EXT PAV MRK & MRKS ARROW | Material | Each |  | 8
3364.677.6012 | ELIM EXT PAV MRK & MRKS WORD | Material | Each |  | 8
3364.680.6002 | INSTALL HWY TRF SIG ISOLATED | Material | Each |  | 8
3364.680.6004 | RMV TRAFFIC SIGNALS | Material | Each |  | 8
3364.681.6001 | TEMP TRAF SIGNALS | Material | Each |  | 8
3364.682.6001 | VEH SIG SEC (12")LED GRN | Material | Each |  | 8
3364.682.6002 | VEH SIG SEC (12")LED GRN ARW | Material | Each |  | 8
3364.682.6003 | VEH SIG SEC (12")LED(YEL) | Material | Each |  | 8
3364.682.6004 | VEH SIG SEC (12")LED(YEL ARW) | Material | Each |  | 8
3364.682.6005 | VEH SIG SEC (12")LED(RED) | Material | Each |  | 8
3364.682.6006 | VEH SIG SEC (12")LED(RED ARW) | Material | Each |  | 8
3364.682.6018 | PED SIG SEC (LED)(COUNTDOWN) | Material | Each |  | 8
3364.682.6023 | BACK PLATE (12")(3 SEC) | Material | Each |  | 8
3364.682.6024 | BACK PLATE (12")(4 SEC) | Material | Each |  | 8
3364.682.6025 | BACK PLATE (12")(5 SEC) | Material | Each |  | 8
3364.684.6031 | TRF SIG CBL TY A 14AWG 5 COND | Material | Each |  | 8
3364.684.6033 | TRF SIG CBL TY A 14AWG 7 COND | Material | Each |  | 8
3364.684.6049 | TRF SIG CBL TY A 16AWG 3 COND | Material | Each |  | 8
3364.684.6079 | TRF SIG CBL TY C 12AWG 2 COND | Material | Each |  | 8
3364.686.6064 | TRF SIG PL AMS1 ARM60'LUM&ILSN | Material | Each |  | 8
3364.686.6068 | TRF SIG PL AMS1 ARM65'LUM&ILSN | Material | Each |  | 8
3364.687.6001 | PED POLE ASSEMBLY | Material | Each |  | 8
3364.688.6001 | PED DETECT PUSH BUTTON APS | Material | Each |  | 8
3364.688.6003 | PED DETECTOR CONTROLLER UNIT | Material | Each |  | 8
3364.6001.6002 | PORT CHANGEABLE MESS SGN | Material | Each |  | 8
3364.6002.6001 | VIVDS PROCESSOR SYSTEM | Material | Each |  | 8
3364.6002.6002 | VIVDS CAMERA ASSEMBLY | Material | Each |  | 8
3364.6002.6003 | VIVDS SET-UP SYSTEM | Material | Each |  | 8
3364.6002.6004 | VIVDS CENTRAL CONTROL | Material | Each |  | 8
3364.6002.6005 | VIVDS COMMUNICATION CBL COAX | Material | Linear Feet |  | 8
3364.6004.6031 | ITS COM CBL ETHERNET | Material | Linear Feet |  | 8
3364.7101.6001 | JELLY FISH FILTER | Material | Each |  | 8
DFW.1.G-300 | INSTALL, MAINTAIN, AND REMOVE TRAFFIC CONTROL AND BARRICADES | Material | Lump Sum |  | 1
DFW.2.G-300 | CONTRACTOR ESCORTS AND FLAGGERS | Material | Lump Sum |  | 1
DFW.3.G-300 | SECURITY SERVICES AND GUARD STRUCTURES WITH UTILITIES | Material | Lump Sum |  | 1
3370 | 3370 - Turnpike Widening | Nonlabor |  |  | 1
3370-Drain | Drainage Crew | Labor |  |  | 0
3370-Dirt | Dirt Crew | Labor |  |  | 0
3370-Grade | Grade Crew | Labor |  |  | 0
3370-Pile | Pile Crew | Labor |  |  | 0
3370-Structure | Structure Crew | Labor |  |  | 0
Elec | Electrical | Material | Lump Sum |  | 1
Cost Mar Redist | March 17 Redistribution | Material | Lump Sum |  | 8
I395 Express | I395 Express - Design (for ABM) | Labor |  |  | 1
I395 Express-Rev | I395 Express - Design Revenue | Nonlabor |  |  | 1
3377 | 3377 - DFW Airport | Nonlabor |  |  | 0
DFW.4.G-500 | MOBILIZATION | Material | Lump Sum |  | 1
DFW.5.01 55 16 | INSTALL, MAINT. AND REMOVE TEMP, ALL-WEATHER HAUL ROAD | Material | Lump Sum |  | 1
DFW.6.L-108 | ELECTRICAL INSTALL AND REMOVE | Material | Lump Sum |  | 1
DFW.7.L-108 | REMOVE EXISTING CABLES FROM EXISTING CONDUIT TO REMAIN | Material | Linear Feet |  | 1
DFW.8.G-700 | DEMO REINFORCED CONCRETE | Material | Square Yard |  | 1
DFW.9.G-700 | DEMO CEMENT TREATED BASE | Material | Square Yard |  | 1
DFW.10.G-700 | DEMO VARIABLE DEPTH ASPHALT PAVEMENT | Material | Square Yard |  | 1
DFW.11.G-700 | DEMO EDGE DRAIN | Material | Linear Feet |  | 1
DFW.12.G-700 | DEMO AIRFIELD LIGHT BASE IN PAVEMENT RECONSTRUCTION | Material | Each |  | 1
DFW.13.G-700 | DEMO AIRFIELD SIGN FOUNDATION | Material | Each |  | 1
DFW.14.G-700 | DEMO JUNCTION CAN | Material | Each |  | 1
DFW.15.G-700 | DEMO MANHOLE/PULLBOX | Material | Each |  | 1
DFW.16.G-700 | REMOVAL OF EXISTING MARKINGS | Material | Square Feet |  | 1
DFW.17.P-151 | CLEARING AND GRUBBING | Material | Square Yard |  | 1
DFW.18.P152 | SOFT SUBGRADE REMOVAL AND REPLACEMENT | Material | Square Yard |  | 1
DFW.19.P-152 | UNCLASSIFIED EXCAVATION | Material | Cubic Yard |  | 1
DFW.20.TX216 | PROOF ROLLING | Material | Hour |  | 1
DFW.21.P-155 | 9" LIME TREATED SUBGRADE (TAXIWAY) | Material | Square Yard |  | 1
DFW.22.P-155 | LIME (8 % BY WEIGHT) | Material |  |  | 1
DFW.23.P-156 | TEMPORARY SWPPP | Material | Lump Sum |  | 1
DFW.24.P-304 | 9" CEMENT-TREATED BASE COURSE (TAXIWAY) | Material | Square Yard |  | 1
DFW.25.P-304 | 6" CEMENT-TREATED BASE COURSE (SHOULDER) | Material | Square Yard |  | 1
DFW.26.TX310 | PRIME COAT | Material | Gallon |  | 1
DFW.27.TX341 | 4" DENSE-GRADED HOT-MIX ASPHALT | Material |  |  | 1
DFW.28.P-501 | 18" PORTLAND CEMENT CONCRETE PAVEMENT | Material | Square Yard |  | 1
DFW.29.P-620 | PAINTED MARKINGS - BLACK (TAXIWAY) | Material | Square Feet |  | 1
DFW.30.P-620 | PAINTED MARKINGS - YELLOW WITH GLASS BEADS (TAXIWAY) | Material | Square Feet |  | 1
DFW.31.P-620 | PAINTED MARKINGS - WHITE (EMERGENCY ROAD) | Material | Square Feet |  | 1
DFW.32.P-620 | PAINTED MARKINGS - BLACK (EMERGENCY ROAD) | Material | Square Feet |  | 1
DFW.33.P-620 | PAINTED MARKINGS - SURFACE MARKING SIGNS | Material | Square Feet |  | 1
DFW.34.P-620 | PAINTED MARKINGS - HOLD BAR | Material | Square Feet |  | 1
DFW.35.D-705 | 6" PERFORATED PVC PIPE | Material | Linear Feet |  | 1
DFW.36.D-705 | 6" NON-PERFORATED PVC PIPE | Material | Linear Feet |  | 1
DFW.37.D-705 | 6" UNDERDRAIN CLEANOUT (SHOULDERS) | Material | Each |  | 1
DFW.38.D-705 | EDGE DRAIN JUNCTION BOX | Material | Each |  | 1
DFW.39.D-751 | 6" PVC CONNECTION TO EXISTING INLET | Material | Each |  | 1
DFW.40.SS-P-751A | ADJUST MANHOLE RISER | Material | Each |  | 1
DFW.41.32 19 23 | SODDING | Material | Square Yard |  | 1
DFW.42.32 19 23 | FERTILIZER | Material | Square Yard |  | 1
DFW.43.T-905 | TOPSOILING | Material | Cubic Yard |  | 1
DFW.44.L-108 | #6 L-824C 5KV CABLE INSTALLED IN DUCT OR CONDUIT | Material | Linear Feet |  | 1
DFW.45.L-108 | #6 SOLID TINNED CU COUNTERPOISE | Material | Linear Feet |  | 1
DFW.46.L-108 | #6 SOLID TINNED CU GROUND | Material | Linear Feet |  | 1
DFW.47.L-108 | UTILITY LOCATES, COMPLETE | Material | Lump Sum |  | 1
DFW.48.L-109 | FURNISH & INSTALL 4 KW L-829 CCR, 6.6A, 480V | Material | Each |  | 1
DFW.49.L-109 | FURNISH & INSTALL 7.5 KW L-829 CCR, 6.6A, 480V | Material | Each |  | 1
DFW.50.L-109 | FURNISH & INSTALL 10 KW L-829 CCR, 6.6A, 480V | Material | Each |  | 1
DFW.51.L-109 | FURNISH & INSTALL 15 KW L-829 CCR, 6.6A, 480V | Material | Each |  | 1
DFW.52.L-109 | NE AIRFIELD VAULT MODIFICATIONS, COMPLETE | Material | Lump Sum |  | 1
DFW.53.L-110 | 1W-1" GRSC IN EXISTING PAVEMENT, INCL. SAWCUT & PATCH | Material | Linear Feet |  | 1
DFW.54.L-110 | 1W-2" SCH. 40 PVC CONDUIT UNDER RIGID PAVEMENT | Material | Linear Feet |  | 1
DFW.55.L-110 | 1W-2" SCH. 40 PVC CONDUIT UNDER FLEXIBLE PAVEMENT | Material | Linear Feet |  | 1
DFW.56.L-110 | 1W-2" SCH. 40 PVC CONDUIT, CONCRETE ENCASED | Material | Linear Feet |  | 1
DFW.57.L-110 | 1W-2" SCH. 40 PVC DRAIN CONDUIT | Material | Linear Feet |  | 1
DFW.58.L-110 | 4W-4" DUCT BANK, INCL. TRENCH & BACKFILL | Material | Linear Feet |  | 1
DFW.59.L-110 | 1W-2" HDPE DIRECTIONAL BORE | Material | Linear Feet |  | 1
DFW.60.L-115 | H-20 RATED PULLBOX | Material | Each |  | 1
DFW.61.L-118 | REMOVE T/W ELEVATED EDGE RETROREFLECTIVE EDGE MARKER | Material | Each |  | 1
DFW.62.L-118 | INSTALL OWNER FURNISHED TAXIWAY EDGE MARKERS | Material | Each |  | 1
DFW.63.L-125 | FURNISH & INSTALL ADJUSTABLE L-867B BASE | Material | Each |  | 1
DFW.64.L-125 | FURNISH & INSTALL 2-PIECE, CLASS I, L-868B W/BAND RING & MULTIHOLE | Material | Each |  | 1
DFW.65.L-125 | FURNISH & INSTALL L-868B 3/4" BLANK COVER | Material | Each |  | 1
DFW.66.L-125 | FURNISH & INSTALL LED L-852C UNI- DIRECTIONAL TAXIWAY CL LT | Material | Each |  | 1
DFW.67.L-125 | INSTALL OWNER FURN. LED L-852C BI-DIRECTIONAL TAXIWAY CL LT | Material | Each |  | 1
DFW.68.L-125 | INSTALL OWNER FURNISHED LED L852F TAXIWAY INTERSECTION CL LT | Material | Each |  | 1
DFW.69.L-125 | FURNISH & INSTALL LED L-852F TAXIWAY INTERSECTION CL LT | Material | Each |  | 1
DFW.70.L-125 | FURNISH & INSTALL L-861T LED TAXIWAY EDGE LIGHT FIXTURE | Material | Each |  | 1
DFW.71.L-125 | FURNISH & INSTALL L-852T LED TAXIWAY EDGE LIGHT FIXTURE | Material | Each |  | 1
DFW.72.L-125 | FURNISH & INSTALL L-858 3-MOD, SIGN & XFORMER | Material | Each |  | 1
DFW.73.L-125 | FURNISH & INSTALL L-858 4-MOD, SIGN & XFORMER | Material | Each |  | 1
DFW.74.L-125 | FURNISH & INSTALL SIGN PANEL | Material | Each |  | 1
DFW.75.L-125 | RELOCATE EXISTING SIGN PANEL | Material | Each |  | 1
DFW.76.L-125 | INSTALL OWNER FURNISHED L-858 3-MOD, SIGN & XFORMER | Material | Each |  | 1
DFW.77.L-125 | INSTALL OWNER FURNISHED L-858 4-MOD, SIGN & XFORMER | Material | Each |  | 1
DFW.78.L-125 | FIBER FORM BLOCKOUT | Material | Each |  | 1
DFW.79.L-125 | REMOVE FIXTURE & XFORMER, RETURN TO OWNER | Material | Each |  | 1
DFW.80.L-125 | REMOVE, STORE & REINSTALL FIXTURE W/NEW XFORMER | Material | Each |  | 1
DFW.81.L-125 | REMOVE SIGN & TRANSFORMER, RETURN TO OWNER | Material | Each |  | 1
DFW.82.L-125 | FURNISH L-861T LED TAXIWAY EDGE FIXTURE (SPARE PARTS) | Material | Each |  | 1
DFW.83.L-125 | FURNISH L-852 LED TAXIWAY BIDIRECTIONAL CL FIXTURE | Material | Each |  | 1
C00100566DB63_C24 | I-66/15 Change Order #24 | Material | Lump Sum |  | 1
Cost April Redist | April 17 Redistribution | Material | Lump Sum |  | 8
EXCA CREW 3 | Excavate/Undercut/Backfill- Crew 3 | Labor |  |  | 1
FG-STN 2 | Place & Finegrade Stone Crew 2 | Labor |  |  | 1
C00100566DB63_C25 | I-66/15 Change Order #25 | Material | Lump Sum |  | 1
C00100566DB63_C26 | I-66/15 Change Order #26 | Material | Lump Sum |  | 1
Garnet | NDOT Garnet | Nonlabor |  |  | 1
Garnet-1 | NTP1 Work | Material |  |  | 8
Garnet-1-1 | Project Management Plan (PMP) | Material |  |  | 8
Garnet-1-1a | Project Administration | Material |  |  | 8
Garnet-1-1b | Quality Management System and Quality Manual | Material |  |  | 8
Garnet-1-1c | Design Quality Management Plan (DQMP) | Material |  |  | 8
Garnet-1-1d | Construction Quality Management Plan (CQMP) | Material |  |  | 8
Garnet-1-1e | Environmental Quality Management Plan (EQMP) | Material |  |  | 8
Garnet-1-1f | Safety Plan | Material |  |  | 8
Garnet-1-1g | Transportation Management Plan (TMP) | Material |  |  | 8
Garnet-1-2 | Interim Project Office | Material |  |  | 8
Garnet-1-3 | Project Office Setup | Material |  |  | 8
Garnet-1-4 | Project Baseline Schedule | Material |  |  | 8
Garnet-1-5 | Documentation of Site | Material |  |  | 8
Garnet-1-6 | Maintenance Work Plan | Material |  |  | 8
Garnet-1-7 | NTP1 Mobilization | Material |  |  | 8
Garnet-A | Professional Services | Material |  |  | 8
Garnet-A-2 | Design Work | Material |  |  | 8
Garnet-A-3 | Public Involvement | Material |  |  | 8
Garnet-A-4 | Environmental permitting and compliance services | Material |  |  | 8
Garnet-A-5 | Design Work for utility relocations | Material |  |  | 8
Garnet-B-6 | NTP2 Mobilization | Material |  |  | 8
Garnet-C | Bonds & Services | Material |  |  | 8
Garnet-C-7 | Payment Bond Premium | Material |  |  | 8
Garnet-C-8 | Performance Bond Premium | Material |  |  | 8
Garnet-C-9 | Insurance Premiums for NTP1 Work Effort | Material |  |  | 8
Garnet-C-10 | Insurance Premiums for NTP2 Work Effort | Material |  |  | 8
Garnet-D | General | Material |  |  | 8
Garnet-D-11 | Site Cleaning | Material |  |  | 8
Garnet-D-12 | Utilities | Material |  |  | 8
Garnet-D-13 | Public Involvement | Material |  |  | 8
Garnet-E | Departments Project Infrastructure | Material |  |  | 8
Garnet-E-14 | Maintenance of Traffic | Material |  |  | 8
Garnet-E-15 | Excavation & Embankment | Material |  |  | 8
Garnet-E-16 | Pavement & Bases | Material |  |  | 8
Garnet-E-17 | Drainage | Material |  |  | 8
Garnet-E-18 | Permanent Signing & Striping | Material |  |  | 8
Garnet-E-19 | Retaining Structures | Material |  |  | 8
Garnet-E-20 | Foundations for Bridges | Material |  |  | 8
Garnet-E-21 | Bridges | Material |  |  | 8
Garnet-E-22 | Electrical | Material |  |  | 8
Garnet-E-23 | Barrier/Cable/Guard Rail and Fencing (Roadway) | Material |  |  | 8
Garnet-E-24 | Landscaping and Aesthetics | Material |  |  | 8
Garnet-E-25 | Maintenance | Material |  |  | 8
Garnet-E-26 | ITS Infrastructure Backbone | Material |  |  | 8
Garnet-E-27 | Miscellaneous Construction Items not covered by Lines 1-26 | Material |  |  | 8
11493 | Purple Line | Labor |  |  | 1
Fluor | Fluor Corporation | Labor |  |  | 8
Project Specific | Project Specific Resources | Labor |  |  | 1
Infra_M.0 | Revenue | Material | Lump Sum |  | 8
IT | Information Technology Group | Labor |  |  | 1
3394 | 3RPort Project | Nonlabor |  |  | 1
2310013.PCO3 | Add Std Guardrail GR-2 | Material | Lump Sum |  | 1
2310013.PCO2 | Quantity Fencing Overrun | Material | Lump Sum |  | 1
Cost June Redist | June 17 Redistribution | Material | Lump Sum |  | 8
3374 | 3374 - Little River Wastewater Plant | Nonlabor |  |  | 1
3374-General | General | Material |  |  | 8
3374-1 | Provide Bonds & Insurance | Material | Unit |  | 8
3374-2 | Mobilization | Material | Unit |  | 8
3374-3 | General Conditions - 36 months | Material | Unit |  | 8
3374-4 | Electrical Mobilization & General Conditions | Material | Unit |  | 8
3374-5 | Sluice & Slide Gate Submittals | Material | Unit |  | 8
3374-6 | Barscreen Submittals | Material | Unit |  | 8
3374-7 | Drum Screen Submittals | Material | Unit |  | 8
3374-8 | Grit Removal Submittals | Material | Unit |  | 8
3374-9 | Mechanical Mixer Submittals | Material | Unit |  | 8
3374-10 | Fine Bubble Diffuer Submittals | Material | Unit |  | 8
3374-11 | MBR Equipment Submittals | Material | Unit |  | 8
3374-12 | Submersible Pumps Submittals | Material | Unit |  | 8
3374-13 | Recessed Impellar Pump Submittals | Material | Unit |  | 8
3374-14 | Multi Stage Blower Submittals | Material | Unit |  | 8
3374-15 | UV Equipment Submittals | Material | Unit |  | 8
3374-16 | FRP Covers Submittals | Material | Unit |  | 8
3374-17 | Odor Control Equipment Submittals | Material | Unit |  | 8
3374-18-Site | SITE | Material | Unit |  | 8
3374-19 | Locate Utilities | Material | Unit |  | 8
3374-20 | Stake Erosion Control | Material | Unit |  | 8
3374-21 | Install silt fence | Material | Unit |  | 8
3374-22 | Stake ponds | Material | Unit |  | 8
3374-23 | Install ponds, outfalls, baffles and dig swells | Material | Unit |  | 8
3374-24 | Install diversion ditch around site | Material | Unit |  | 8
3374-25 | Install inlet protection | Material | Unit |  | 8
3374-26 | Stake clearing limits | Material | Unit |  | 8
3374-27 | Erosion control inspection & maintenance | Material | Unit |  | 8
3374-28 | Clear & grub | Material | Unit |  | 8
3374-29 | Install mulch berm | Material | Unit |  | 8
3374-30 | Install DIP 18" drain - DM H-2, 3, 4, 5, 6 | Material | Unit |  | 8
3374-31 | Install DIP 24" sanitary sewer SS1, SS1.1, SS2, SS3 | Material | Unit |  | 8
3374-32 | Excavate & fine grade retaining wall footing | Material | Unit |  | 8
3374-33 | Form & reinforce retaining wall footing | Material | Unit |  | 8
3374-34 | Pour retaining wall footing | Material | Unit |  | 8
3374-35 | Form & reinforce retaining wall | Material | Unit |  | 8
3374-36 | Pour retaining wall | Material | Unit |  | 8
3374-37 | Install concrete pipe storm drain | Material | Unit |  | 8
3374-38 | Install new fence | Material | Unit |  | 8
3374-39 | Stake site - grid layout | Material | Unit |  | 8
3374-40 | Undercut Treatment Bldg & Fill site to subgrade | Material | Unit |  | 8
3374-41 | Ductbank - Plant Drain Pump Station to Treatment Bldg | Material | Unit |  | 8
3374-42 | Power Pole to Transformer | Material | Unit |  | 8
3374-43 | Ductbank - Transformer to Treatment Bldg | Material | Unit |  | 8
3374-44 | Ductbank - Odor Control to Treatment Bldg | Material | Unit |  | 8
3374-45 | Ductbank - Generators to Treatment Bldg | Material | Unit |  | 8
3374-46 | Ductbank - Membrane PS to Treatment Bldg | Material | Unit |  | 8
3374-47 | Ductbank - Underground @ Post Anox Basins | Material | Unit |  | 8
3374-48 | Ductbank - Blowers to Treatment Plant | Material | Unit |  | 8
3374-49 | Ductbank - Post Anoxic to Treatment Bldg | Material | Unit |  | 8
3374-50 | Data - Utility to Treatment Data Room | Material | Unit |  | 8
3374-51 | Site Light Pole Bases | Material | Unit |  | 8
3374-52 | Site Lighting | Material | Unit |  | 8
3374-53 | Electrical Manholes | Material | Unit |  | 8
3374-54 | Miscellaneous Yard Electrical | Material | Unit |  | 8
3374-55 | Asphalt Paving | Material | Unit |  | 8
3374-56 | Concrete Paving & Curb | Material | Unit |  | 8
3374-57 | Stone Areas | Material | Unit |  | 8
3374-58 | Sidewalk | Material | Unit |  | 8
3374-59 | Demolition | Material | Unit |  | 8
3374-60 | Final Site Grading | Material | Unit |  | 8
3374-61 | Grassing | Material | Unit |  | 8
3374-62 | Landscaping | Material | Unit |  | 8
3374-63-Treatmernt | Treatment Building | Material | Unit |  | 8
3374-64 | Stake auger cast piles | Material | Unit |  | 8
3374-65 | Install auger cast piles | Material | Unit |  | 8
3374-66 | Install shoring at influent channel | Material | Unit |  | 8
3374-67 | Excavate influent channel | Material | Unit |  | 8
3374-68 | Fine grade & stone influent channel 863.5 slab | Material | Unit |  | 8
3374-69 | Form & reinforce influent 863.5 slab | Material | Unit |  | 8
3374-70 | Pour influent 863.5 slab | Material | Unit |  | 8
3374-71 | Fine grade & stone influent channel 867.75 slab | Material | Unit |  | 8
3374-72 | Form & reinforce influent channel 867.75 slab | Material | Unit |  | 8
3374-73 | Pour influent channel 867.75 slab | Material | Unit |  | 8
3374-74 | Form & reinforce influent mass walls | Material | Unit |  | 8
3374-75 | Pour influent mass walls | Material | Unit |  | 8
3374-76 | Form & reinforce 2nd lift influent channel walls | Material | Unit |  | 8
3374-77 | Pour 2nd lift influent channel walls | Material | Unit |  | 8
3374-78 | Waterproofing influent channel | Material | Unit |  | 8
3374-79 | Backfill influent channel | Material | Unit |  | 8
3374-80 | Excavate & fine grade effluent box SOG | Material | Unit |  | 8
3374-81 | Form & reinforce effluent box SOG | Material | Unit |  | 8
3374-82 | Pour effluent box SOG | Material | Unit |  | 8
3374-83 | Form & reinforce effluent box walls to 883.00 slab | Material | Unit |  | 8
3374-84 | Pour effluent box walls to 883.00 slab | Material | Unit |  | 8
3374-85 | Waterproofing effluent box walls to 883.00 slab (if required) | Material | Unit |  | 8
3374-86 | Backfill effluent box walls to 883.00 slab | Material | Unit |  | 8
3374-87 | Install floor/equipment drain pipes throughout building and encase | Material | Unit |  | 8
3374-88 | Install DIP 12" PRM from membrane pumps to back pulse tank and encase | Material | Unit |  | 8
3374-89 | Install DIP 12" drain from membrane tank and encase | Material | Unit |  | 8
3374-90 | Excavate & stone @ grade beams under 883.00 slabs | Material | Unit |  | 8
3374-91 | Form & reinforce grade beams under 883.00 | Material | Unit |  | 8
3374-92 | Pour grade beams under 883.00 | Material | Unit |  | 8
3374-93 | Fine grade & stone SOG 883.00 slab pour #1 | Material | Unit |  | 8
3374-94 | Form & reinforce 883.00 slab pour #1 | Material | Unit |  | 8
3374-95 | Install electrical conduit 883.00 slab pour #1 | Material | Unit |  | 8
3374-96 | Pour 883.00 slab #1 | Material | Unit |  | 8
3374-97 | Fine grade & stone SOG 883.00 slab pour #2 | Material | Unit |  | 8
3374-98 | Form & reinforce slab pour #2 883.00 | Material | Unit |  | 8
3374-99 | Install electrical conduit 883.00 slab pour #2 | Material | Unit |  | 8
3374-100 | Pour 883.00 slab #2 | Material | Unit |  | 8
3374-101 | Form & reinforce knee walls on 883.00 slab(around membrane to 866.67) | Material | Unit |  | 8
3374-102 | Pour knee walls on 883.00 slab(around membrane to 866.67) | Material | Unit |  | 8
3374-103 | Excavate & stone at grade beams under 885.00 chemical room slab | Material | Unit |  | 8
3374-104 | Form & reinforce 885.00 chem room slab grade beams | Material | Unit |  | 8
3374-105 | Pour 885.00 chem room slab grade beams | Material | Unit |  | 8
3374-106 | Fine grade & stone at 885.00 chem room slab | Material | Unit |  | 8
3374-107 | Install electrical conduit in chemical room slab | Material | Unit |  | 8
3374-108 | Form & reinforce at 885.00 chem room slab | Material | Unit |  | 8
3374-109 | Pour 885.00 chem room slab | Material | Unit |  | 8
3374-110 | Form & reinforce knee walls on 885.00 chem rm(b/w mem/chem) | Material | Unit |  | 8
3374-111 | Pour knee walls on 885.00 chem rm slab (b/w mem/chem) | Material | Unit |  | 8
3374-112 | Excavate & stone at grade beams under 888.00 membrane slab | Material | Unit |  | 8
3374-113 | Form & reinforce grade beams under 888.00 membrane slab | Material | Unit |  | 8
3374-114 | Pour grade beams under 888.00 membrane supply | Material | Unit |  | 8
3374-115 | Fine grade & stone 888.00 membrane slab #1 | Material | Unit |  | 8
3374-116 | Form & reinforce 888.00 membrane slab #1 | Material | Unit |  | 8
3374-117 | Pour 888.00 membrane slab #1 | Material | Unit |  | 8
3374-118 | Fine grade & stone 888.00 membrane slab #2 | Material | Unit |  | 8
3374-119 | Form & reinforce 888.00 membrane slab #2 | Material | Unit |  | 8
3374-120 | Pour 888.00 membrane slab #2 | Material | Unit |  | 8
3374-121 | Form & reinforce knee walls on 885.00 chem rm slab (b/w HW/chem) | Material | Unit |  | 8
3374-122 | Pour knee walls on 885.00 chem rm slab (b/w HW/chem) | Material | Unit |  | 8
3374-123 | Excavate & stone grade beams under Headworks slab, 888.00 | Material | Unit |  | 8
3374-124 | Form & reinforce grade beams 888.00, headworks slab | Material | Unit |  | 8
3374-125 | Pour grade beams 888.00, headworks slab | Material | Unit |  | 8
3374-126 | Fine grade & stone headworks slab pour #1, elev. 888.00 | Material | Unit |  | 8
3374-127 | Form & reinforce headworks slab pour #1, elev. 888.00 | Material | Unit |  | 8
3374-128 | Install electrical conduit at headworks slab #1, elev. 888.00 | Material | Unit |  | 8
3374-129 | Pour headworks slab #1, elev. 888.00 | Material | Unit |  | 8
3374-130 | Fine grade & stone headworks slab pour #2, elev. 888.00 | Material | Unit |  | 8
3374-131 | Form & reinforce headworks slab #2, elev. 888.00 | Material | Unit |  | 8
3374-132 | Install electrical conduit at headworks slab #2, elev. 888.00 | Material | Unit |  | 8
3374-133 | Pour headworks slab #2, elev. 888.00 | Material | Unit |  | 8
3374-134 | Form & reinforce wall #1(infl. channel & NEcorner) | Material | Unit |  | 8
3374-135 | Pour wall #1(infl. Channel & Necorner) | Material | Unit |  | 8
3374-136 | Form & reinforce wall #2(exterior cl E2-G2, Nside) | Material | Unit |  | 8
3374-137 | Pour wall #2(exterior cl E2-G2, Nside) | Material | Unit |  | 8
3374-138 | Form & reinforce chemical tanks & equipment pads in citric acid room | Material | Unit |  | 8
3374-139 | Pour chemical tanks & equipment pads in citric acid room | Material | Unit |  | 8
3374-140 | Form & reinforce wall #3(cl G2-L2, Nside) | Material | Unit |  | 8
3374-141 | Pour wall #3(cl G2-L2, Nside) | Material | Unit |  | 8
3374-142 | Form & reinforce wall #4(cl A1-C1, Nside) | Material | Unit |  | 8
3374-143 | Pour wall #4(cl A1-C1, Nside) | Material | Unit |  | 8
3374-144 | Form & reinforce wall #5(cl D1-E2, Nside) | Material | Unit |  | 8
3374-145 | Pour wall #5(cl D1-E2, Nside) | Material | Unit |  | 8
3374-146 | Form & reinforce wall #6(cl A8-B12, Wside) | Material | Unit |  | 8
3374-147 | Pour wall #6(cl A8-B12, Wside) | Material | Unit |  | 8
3374-148 | Form & reinforce wall #7(cl A1-A8, Wside) | Material | Unit |  | 8
3374-149 | Pour wall #7(cl A1-A8, Wside) | Material | Unit |  | 8
3374-150 | Form & reinforce wall #8(cl E12-H12, Sside) | Material | Unit |  | 8
3374-151 | Pour wall #8(cl E12-H12, Sside) | Material | Unit |  | 8
3374-152 | Form & reinforce wall #9(clB12-E12, Sside) | Material | Unit |  | 8
3374-153 | Pour wall #9(cl B12-E12, Sside) | Material | Unit |  | 8
3374-154 | Form & reinforce UV drop box slab & walls to bottom mem. effluent & UV slab | Material | Unit |  | 8
3374-155 | Pour UV drop box slab & walls to bottom membrane effluent & UV slab | Material | Unit |  | 8
3374-156 | Form & reinforce wall #10(cl E3-E11, interior b/w chem area & headworks) | Material | Unit |  | 8
3374-157 | Pour wall #10(cl E3-E11, interior b/w chem area & headworks) | Material | Unit |  | 8
3374-158 | Form & reinforce wall #11(cl L12-P12, Sside) | Material | Unit |  | 8
3374-159 | Pour wall #11(cl L12-P12, Sside) | Material | Unit |  | 8
3374-160 | Form & reinforce wall #12(cl H12-L12, Sside) | Material | Unit |  | 8
3374-161 | Pour wall #12(cl H12-L12, Sside) | Material | Unit |  | 8
3374-162 | Install coatings at chemical tank & equipment pads in citric acid room | Material | Unit |  | 8
3374-163 | Set chemical tank in citric acid room | Material | Unit |  | 8
3374-164 | Shore & reinforce elevated UV slab | Material | Unit |  | 8
3374-165 | Pour elevated UV slab | Material | Unit |  | 8
3374-166 | Form & reinforce UV channel walls | Material | Unit |  | 8
3374-167 | Pour UV channel walls | Material | Unit |  | 8
3374-168 | Form & reinforce parshall flume walls | Material | Unit |  | 8
3374-169 | Pour parshall flume walls | Material | Unit |  | 8
3374-170 | Form & reinforce wall #13(cl P12-Q12-Q11-P12, SEside) | Material | Unit |  | 8
3374-171 | Pour wall #13(cl P12-Q12-Q11-P12, Seside) | Material | Unit |  | 8
3374-172 | Form & reinforce columns K-7, K-5, K-10 at membrane effluent channel | Material | Unit |  | 8
3374-173 | Pour columns K-7, K-5, K-10 at membrane effluent channel | Material | Unit |  | 8
3374-174 | Form & reinforce wall #14(cl L4-N4, int wall b/w sludge thick & holding) | Material | Unit |  | 8
3374-175 | Pour wall #14 ( cl L4-N4, int wall b/w sludge thick & holding) | Material | Unit |  | 8
3374-176 | Grout fill sludge thickner & thickened sludge holding tank | Material | Unit |  | 8
3374-177 | Coating in sludge thickner & thickened sludge holding tank | Material | Unit |  | 8
3374-178 | Form & reinforce wall #15(b/w membrane 2 & 3) | Material | Unit |  | 8
3374-179 | Pour wall #15(b/w membrane 2 & 3) | Material | Unit |  | 8
3374-180 | Form & reinforce columns at chemical area (cl F, G, H) | Material | Unit |  | 8
3374-181 | Pour columns at chemical area (cl F, G, H) | Material | Unit |  | 8
3374-182 | Form & reinforce wall #16(b/w membrane 3 & 4) | Material | Unit |  | 8
3374-183 | Pour wall #16(b/w membrane 3 & 4) | Material | Unit |  | 8
3374-184 | Form & reinforce wall #17(b/w membrane 1 & 2) | Material | Unit |  | 8
3374-185 | Pour wall #17(b/w membrane 1 & 2) | Material | Unit |  | 8
3374-186 | Install parshall flume - UV channels | Material | Unit |  | 8
3374-187 | Install electrical conduit at UV channel concrete fill | Material | Unit |  | 8
3374-188 | Concrete fill at UV channel | Material | Unit |  | 8
3374-189 | Form & reinforce columns at headworks slab (cl B, C, D) | Material | Unit |  | 8
3374-190 | Pour columns at headworks slab (cl B, C, D) | Material | Unit |  | 8
3374-191 | Form & reinforce chemical tanks & equipment pads in chemical room area | Material | Unit |  | 8
3374-192 | Pour chemical tanks & equipment pads in chemical room area | Material | Unit |  | 8
3374-193 | Install coatings at chemical tanks & equipment pads in chemical area | Material | Unit |  | 8
3374-194 | Form & reinforce wall #18(b/w membrane 1 & UV) | Material | Unit |  | 8
3374-195 | Pour Wall #18 | Material | Unit |  | 8
3374-196 | Grout fill membrane tanks | Material | Unit |  | 8
3374-197 | Coatings at membrane tanks | Material | Unit |  | 8
3374-198 | Grout fill influent membrane channel | Material | Unit |  | 8
3374-199 | Coatings at influent membrane channel | Material | Unit |  | 8
3374-200 | Shore & reinforce membrane tank effluent channel slab | Material | Unit |  | 8
3374-201 | Pour membrane tank effluent channel slab | Material | Unit |  | 8
3374-202 | Form & reinforce membrane tank effluent channel walls | Material | Unit |  | 8
3374-203 | Pour membrane tank effluent channel slab | Material | Unit |  | 8
3374-204 | Form & reinforce exterior membrane effluent channel walls | Material | Unit |  | 8
3374-205 | Pour exterior membrane effluent channel walls | Material | Unit |  | 8
3374-206 | Coatings at effluent channel walls | Material | Unit |  | 8
3374-207 | Form & reinforce column and grit collector, 888.00-902.00 | Material | Unit |  | 8
3374-208 | Pour column and grit collector, 888.00-902.00 | Material | Unit |  | 8
3374-209 | Grout fill in grit collector | Material | Unit |  | 8
3374-210 | Shore & reinforce beams, sidewalks, slabs elev. 908.00, col. Line K-Q (slab 1) | Material | Unit |  | 8
3374-211 | Install electrical in 908.00 slab, col. Line K-Q (slab 1) | Material | Unit |  | 8
3374-212 | Pour beams, sidewalks, slabs elev. 908.00, col. Line K-Q (slab 1) | Material | Unit |  | 8
3374-213 | Shore & reinforce beams, sidewalks, slabs elev. 908.00, col. Line K-Q (slab 2) | Material | Unit |  | 8
3374-214 | Install electrical in 908.00 slab, col. Line K-Q (slab 2) | Material | Unit |  | 8
3374-215 | Pour beams, sidewalks, slabs elev. 908.00, col. Line K-Q (slab 2) | Material | Unit |  | 8
3374-216 | Remove shoring from beams, sidewalks, slabs elev. 908.00, col. Line K-Q | Material | Unit |  | 8
3374-217 | Set chemical tanks in chemical area | Material | Unit |  | 8
3374-218 | Shore & reinforce beams, sidewalks, slabs elev. 912.00, col. Line E-K (slab 1) | Material | Unit |  | 8
3374-219 | Install electrical conduit at elevated slab elev. 912.00, col. Line E-K (slab 1) | Material | Unit |  | 8
3374-220 | Pour beams, sidewalks, slabs elev. 912.00, col. Line E-K (slab 1) | Material | Unit |  | 8
3374-221 | Shore & reinforce beams, sidewalks, slabs elev. 912.00, col. Line E-K (slab 2) | Material | Unit |  | 8
3374-222 | Install electrical conduit at elevated slab elev. 912.00, col. Line E-K (slab 2) | Material | Unit |  | 8
3374-223 | Pour beams, sidewalks, slabs elev. 912.00, col. Line E-K (slab 2) | Material | Unit |  | 8
3374-224 | Remove shoring from beams, sidewalks, slabs elev. 912.00, col. Line E-K | Material | Unit |  | 8
3374-225 | Shore & reinforce beams & slabs at col. Lines A1/C1/C8, elev. 903.67 (fine screen) | Material | Unit |  | 8
3374-226 | Install electrical conduit col. Lines A1/C1/C8, elev. 903.67 (fine screen slab) | Material | Unit |  | 8
3374-227 | Pour beams & slabs at col. Lines A1/C1/C8, elev. 903.67 (fine screen slab) | Material | Unit |  | 8
3374-228 | Remove shoring at beams & slabs-col. Line A1/C1/C8, elev. 903.67 (fine screen) | Material | Unit |  | 8
3374-229 | Form & reinforce grit channel walls, 903.67-912.00 | Material | Unit |  | 8
3374-230 | Pour grit channel walls, 903.67-912.00 | Material | Unit |  | 8
3374-231 | Grout fill grit channel | Material | Unit |  | 8
3374-232 | Coatings at grit channel | Material | Unit |  | 8
3374-233 | Shore & reinforce beams and slab (B8-B12, C8-C12, E1-E12) 912.00 | Material | Unit |  | 8
3374-234 | Install slab electrical (B8-B12, C8-C12, E1-E12) 912.00 | Material | Unit |  | 8
3374-235 | Pour beams and slab (B8-B12, C8-C12, E1-E12) 912.00 | Material | Unit |  | 8
3374-236 | Remove shoring from beams and slabs (B8-B12, C8-C12, E1-E12) 912.00 | Material | Unit |  | 8
3374-237 | Form & reinforce columns & pilasters, elev. 912.00 and up (above membrane) | Material | Unit |  | 8
3374-238 | Pour columns & pilasters, elev. 912.00 and up (above membrane) | Material | Unit |  | 8
3374-239 | Shore & reinforce concrete beam around membrane canopy | Material | Unit |  | 8
3374-240 | Pour concrete beams around membrane canopy | Material | Unit |  | 8
3374-241 | Remove shoring at beams around membrane canopy | Material | Unit |  | 8
3374-242 | Hydraulic testing of concrete tanks | Material | Unit |  | 8
3374-243 | Form & reinforce concrete stairs | Material | Unit |  | 8
3374-244 | Pour concrete stairs | Material | Unit |  | 8
3374-245 | Install scum collector in sludge thickener | Material | Unit |  | 8
3374-246 | Install PVC fill and recirc. Lines at chemical tanks | Material | Unit |  | 8
3374-247 | Install OH crane in pump room | Material | Unit |  | 8
3374-248 | Install DIP 12" drain & valves-membrane tanks to floor penetration to plant drain PS | Material | Unit |  | 8
3374-249 | Install permeate membrane pumps | Material | Unit |  | 8
3374-250 | Install DIP 24" PRM membrane pumps to UV drop box - 10" from pump to 24" header | Material | Unit |  | 8
3374-251 | Install DIP 12" PRM from backpulse tank to UV drop box | Material | Unit |  | 8
3374-252 | Install DIP 8" & 6" PRM from mem. to 10" PRM suction-cassettes to pumps(6) | Material | Unit |  | 8
3374-253 | Install blowers | Material | Unit |  | 8
3374-254 | Install suction discharge header on pump 5092 | Material | Unit |  | 8
3374-255 | Install DIP 8" PRM suction from sludge tank to pump 5092 | Material | Unit |  | 8
3374-256 | Install SS 18" AA blowers to 18", 12", 10", 4" - MBR casettes from blowers | Material | Unit |  | 8
3374-257 | Install influent pumps | Material | Unit |  | 8
3374-258 | Install influent discharge header to grit channel (18" & 10") | Material | Unit |  | 8
3374-259 | Install DIP 18" -10" discharge from influent pumps to vortec grit collector | Material | Unit |  | 8
3374-260 | Install SS 18" AA to 6" to sludge thickner and MBR tank Influent cannel | Material | Unit |  | 8
3374-261 | Install sludge holding tank diffusers | Material | Unit |  | 8
3374-262 | Install fine screens | Material | Unit |  | 8
3374-263 | Install DIP 18" & 24" RS hw grit channel to fine screens | Material | Unit |  | 8
3374-264 | Install MBR influent channel diffusers | Material | Unit |  | 8
3374-265 | Install DIP 24" RS/PE from fine screens to bio basin splitter box | Material | Unit |  | 8
3374-266 | Install grit cyclone and grit piping | Material | Unit |  | 8
3374-267 | Install grit pumps | Material | Unit |  | 8
3374-268 | Install vortex grit collector and grit classifier | Material | Unit |  | 8
3374-269 | Install MBR equipment | Material | Unit |  | 8
3374-270 | Install influent channel bar screens | Material | Unit |  | 8
3374-271 | Install UV Equipment | Material | Unit |  | 8
3374-272 | Install Reuse Water Pumps | Material | Unit |  | 8
3374-273 | Install Plant Water Pumps | Material | Unit |  | 8
3374-274 | Install Compressors | Material | Unit |  | 8
3374-275 | Install Samplers | Material | Unit |  | 8
3374-276 | Set chemical feed pumps | Material | Unit |  | 8
3374-277 | Install PVC 1" sodium hydroxide to MBR influent chanel | Material | Unit |  | 8
3374-278 | Install PVC 1" sodium hydroxide to 24" R.S. Post fine screen | Material | Unit |  | 8
3374-279 | Install PVC 1" ferric chloride to MBR influent channel | Material | Unit |  | 8
3374-280 | Install PVC 1" ferric chloride to bio-basin splitter | Material | Unit |  | 8
3374-281 | Install PVC 1" citric acid to MBR pumps 1-5 | Material | Unit |  | 8
3374-282 | Install sodium hpochlorite to suction of MBR pumps 1-5 | Material | Unit |  | 8
3374-283 | Install PVC 1" sodium hypochlorite to W-3 pump room | Material | Unit |  | 8
3374-284 | Install emergency shower/eye wash | Material | Unit |  | 8
3374-285 | Install PVC 1" acedic acid to fermentation basin | Material | Unit |  | 8
3374-286 | Install PVC water to grit pump seal water panels | Material | Unit |  | 8
3374-287 | Install PVC water to fine screens | Material | Unit |  | 8
3374-288 | Install PVC 1" water to vortex | Material | Unit |  | 8
3374-289 | Install SS 1" air to vortex | Material | Unit |  | 8
3374-290 | Install PVC waterlines to pumps/flushing connections | Material | Unit |  | 8
3374-291 | Install gates and operators | Material | Unit |  | 8
3374-292 | Install DIP 4" drain from UV channel overhead | Material | Unit |  | 8
3374-293 | Install odor control duct | Material | Unit |  | 8
3374-294 | Install DIP 6" wall drain sludge holding tank | Material | Unit |  | 8
3374-295 | Install DIP 6" wall drain sludge thickner | Material | Unit |  | 8
3374-296 | Install DIP 4" drain from UV channel, and encase | Material | Unit |  | 8
3374-297 | Install DIP process drains under slab, equip. drains, floor drains, encase | Material | Unit |  | 8
3374-298 | Install DIP - Plant Water Pump Room | Material | Unit |  | 8
3374-299 | Install DIP 6" H2O line to golf course, and encase | Material | Unit |  | 8
3374-300 | Install Miscellaneous Small Pipe | Material | Unit |  | 8
3374-301 | Install OH crane above membranes | Material | Unit |  | 8
3374-302 | Lay CMU block on 2nd level exterior | Material | Unit |  | 8
3374-303 | Lay CMU block on2nd level interior | Material | Unit |  | 8
3374-304 | Dampproofing at masonry | Material | Unit |  | 8
3374-305 | Install Miscellaneous Metals | Material | Unit |  | 8
3374-306 | Erect metal trusses and decking | Material | Unit |  | 8
3374-307 | Install roofing insulation and metal roof | Material | Unit |  | 8
3374-308 | Install exterior windows and doors | Material | Unit |  | 8
3374-309 | Install Translucent Wall Panels | Material | Unit |  | 8
3374-310 | Install interior framing | Material | Unit |  | 8
3374-311 | Install Overhead Doors | Material | Unit |  | 8
3374-312 | Install Surface Conduits | Material | Unit |  | 8
3374-313 | Pull Wire & Terminations | Material | Unit |  | 8
3374-314 | Install Light Fixtures | Material | Unit |  | 8
3374-315 | Connect Switchgear | Material | Unit |  | 8
3374-316 | Install MCCs | Material | Unit |  | 8
3374-317 | Connect MBR MCC | Material | Unit |  | 8
3374-318 | Install Transformer | Material | Unit |  | 8
3374-319 | Install Disconnects | Material | Unit |  | 8
3374-320 | Install Lightning Protection | Material | Unit |  | 8
3374-321 | Install Grounding | Material | Unit |  | 8
3374-322 | Install Junction Boxes | Material | Unit |  | 8
3374-323 | Install Fire Alarm | Material | Unit |  | 8
3374-324 | Connect VFD's | Material | Unit |  | 8
3374-325 | Miscellaneous Electrical | Material | Unit |  | 8
3374-326 | HVAC | Material | Unit |  | 8
3374-327 | Plumbing | Material | Unit |  | 8
3374-328 | Fire Sprinkler | Material | Unit |  | 8
3374-329 | Install aluminum curtainwall | Material | Unit |  | 8
3374-330 | Install and finish drywall | Material | Unit |  | 8
3374-331 | Install ceiling | Material | Unit |  | 8
3374-332 | Install lab equipment & casework | Material | Unit |  | 8
3374-333 | Install millwork | Material | Unit |  | 8
3374-334 | Install toilet accessories & specialties | Material | Unit |  | 8
3374-335 | Install Canopy | Material | Unit |  | 8
3374-336 | Caulking | Material | Unit |  | 8
3374-337 | Install misc. appliances | Material | Unit |  | 8
3374-338 | Deck Coatings | Material | Unit |  | 8
3374-339 | Painting | Material | Unit |  | 8
3374-340 | Install flooring | Material | Unit |  | 8
3374-341 | Start Up Treatment Building | Material | Unit |  | 8
3374-342-MPS | Membrane Pump Station | Material | Unit |  | 8
3374-343 | Install Auger Cast Piles | Material | Unit |  | 8
3374-344 | Excavate membrane influent pump station | Material | Unit |  | 8
3374-345 | Fine grade & stone membrane influent pump station | Material | Unit |  | 8
3374-346 | Form & reinforce membrane influent pump station | Material | Unit |  | 8
3374-347 | Pour membrane influent pump station pad | Material | Unit |  | 8
3374-348 | Form & reinforce membrane influent pump station wall | Material | Unit |  | 8
3374-349 | Pour membrane influent pump station walls | Material | Unit |  | 8
3374-350 | Shore & reinforce influent pump station elevated deck | Material | Unit |  | 8
3374-351 | Pour influent pump station elevated deck | Material | Unit |  | 8
3374-352 | Remove shoring at membrane influent pump station | Material | Unit |  | 8
3374-353 | Grout fill at membrane influent pump station | Material | Unit |  | 8
3374-354 | Form, Reinforce & Pour Stairs | Material | Unit |  | 8
3374-355 | Coatings at membrane influent pump station | Material | Unit |  | 8
3374-356 | Backfill membrane influent pump station | Material | Unit |  | 8
3374-357 | Install misc. metals at membane influent pump station | Material | Unit |  | 8
3374-358 | Install Jib Crane | Material | Unit |  | 8
3374-359 | Install Pumps | Material | Unit |  | 8
3374-360 | Install Pipe & Valves | Material | Unit |  | 8
3374-361 | Electrical | Material | Unit |  | 8
3374-362 | Painting | Material | Unit |  | 8
3374-363-BBSB | Biological Basins Splitter Box | Material | Unit |  | 8
3374-364 | Excavate bio-basin splitter box | Material | Unit |  | 8
3374-365 | Fine grade & stone bio-basin splitter box | Material | Unit |  | 8
3374-366 | Form & reinforce bio-basin splitter box slab | Material | Unit |  | 8
3374-367 | Pour bio-basin splitter box slab | Material | Unit |  | 8
3374-368 | Form & reinforce bio-basin splitter box walls | Material | Unit |  | 8
3374-369 | Pour bio-basin splitter box walls | Material | Unit |  | 8
3374-370 | Install flumes at bio-basin splitter box | Material | Unit |  | 8
3374-371 | Shore & reinforce bio-basin splitter box elevated deck | Material | Unit |  | 8
3374-372 | Pour bio-basin splitter box elevated deck | Material | Unit |  | 8
3374-373 | Remove shoring at bio-basin splitter box elevated deck | Material | Unit |  | 8
3374-374 | Install grout fill at bio-basin splitter box | Material | Unit |  | 8
3374-375 | Coatings at bio-basin splitter box | Material | Unit |  | 8
3374-376 | Install misc. metals at bio-basin splitter box | Material | Unit |  | 8
3374-377 | Install gates at bio-basin splitter box | Material | Unit |  | 8
3374-388-Gen | Generator | Material | Unit |  | 8
3374-379 | Install Auger Cast Piles | Material | Unit |  | 8
3374-380 | Fine grade & stone generator slab | Material | Unit |  | 8
3374-381 | Install precast polymer trench drain | Material | Unit |  | 8
3374-382 | Form & reinforce generator slab | Material | Unit |  | 8
3374-383 | Pour generator slab | Material | Unit |  | 8
3374-384 | Form & reinforce generator pads (2) | Material | Unit |  | 8
3374-385 | Pour generator pads (2) | Material | Unit |  | 8
3374-386 | Form & Place Curbs | Material | Unit |  | 8
3374-387 | Install Generators | Material | Unit |  | 8
3374-388 | Electrical | Material | Unit |  | 8
3374-389-PAT | Post Anoxic Tanks | Material | Unit |  | 8
3374-390 | Excavate piers at existing post anoxic tanks | Material | Unit |  | 8
3374-391 | Form & reinforce support piers at post anoxic trough | Material | Unit |  | 8
3374-392 | Pour support piers at post anoxic trough | Material | Unit |  | 8
3374-393 | Backfill post anoxic trough | Material | Unit |  | 8
3374-343-PDPS | Plant Drain Pump Station | Material | Unit |  | 8
3374-395 | Excavate plant drain pump station | Material | Unit |  | 8
3374-396 | Fine grade & stone plant drain pump station | Material | Unit |  | 8
3374-397 | Form & reinforce plant drain pump station slab | Material | Unit |  | 8
3374-398 | Pour plant drain pump station slab | Material | Unit |  | 8
3374-399 | Set precast plant drain pump station structure | Material | Unit |  | 8
3374-400 | Install grout fill at plant drain pump station | Material | Unit |  | 8
3374-401 | Coatings at plant drain pump station | Material | Unit |  | 8
3374-402 | Install pumps | Material | Unit |  | 8
3374-403 | Install piping | Material | Unit |  | 8
3374-404 | Install misc. metals | Material | Unit |  | 8
3374-405 | Electrical | Material | Unit |  | 8
3374-406 | Painting | Material | Unit |  | 8
3374-407-YP | Yard Piping | Material | Unit |  | 8
3374-408 | Install DIP 24" RAS from membrane PS to membrane treatment infuent channel | Material | Unit |  | 8
3374-409 | Install DIP 24" RS from fine screens to bio-basin splitter box | Material | Unit |  | 8
3374-410 | Install DIP effluent line from treatment building to river | Material | Unit |  | 8
3374-411 | Install DIP 24" ML/30" ML from anoxic tanks to membrane influent PS | Material | Unit |  | 8
3374-412 | Install 24" ML - Bio Basins to Post Anoxic | Material | Unit |  | 8
3374-413 | Install 6" Plant Drain Yard Piping | Material | Unit |  | 8
3374-414 | Install DIP 8" & 4" H2O line down road to site | Material | Unit |  | 8
3374-415 | Install 6" SD from Bldg to SS-1 | Material | Unit |  | 8
3374-416 | Install plant water lines | Material | Unit |  | 8
3374-417 | Tie in 8" drain from bio-basin effluent channel #1 to existing | Material | Unit |  | 8
3374-418 | Tie in 8" drain from bio-basin effluent channel #2 to existing | Material | Unit |  | 8
3374-419 | Pipe Insulation | Material | Unit |  | 8
3374-420 | Pipe Testing | Material | Unit |  | 8
3374-421 | Pipe Support Footings (16 ea) - Finegrade | Material | Unit |  | 8
3374-422 | Pipe Support Footings (16 ea) - Form & Reinforce | Material | Unit |  | 8
3374-423 | Pipe Support Footings (16 ea) - Pour | Material | Unit |  | 8
3374-424 | Pipe Supports (94 ea) - Form & Reinforce | Material | Unit |  | 8
3374-425 | Pipe Supports (94 ea) - Pour | Material | Unit |  | 8
3374-426-Blower | Blowers | Material | Unit |  | 8
3374-427 | Fine grade & stone aeration blower pads 1-3 | Material | Unit |  | 8
3374-428 | Form & reinforce aeration blower pads 1-3 | Material | Unit |  | 8
3374-429 | Pour aeration blower pads 1-3 | Material | Unit |  | 8
3374-430 | Install blowers | Material | Unit |  | 8
3374-431 | Electrical | Material | Unit |  | 8
3374-432-OC | Odor Control | Material | Unit |  | 8
3374-433 | Fine grade & stone odor control pads for bio-basins | Material | Unit |  | 8
3374-434 | Form & reinforce odor control pads for bio-basins | Material | Unit |  | 8
3374-435 | Pour odor control pads for bio-basin | Material | Unit |  | 8
3374-436 | Form & reinforce odor control pipe supports bio-basin/post anoxic | Material | Unit |  | 8
3374-437 | Pour odor control pipe supports bio-basin/post anoxic | Material | Unit |  | 8
3374-438 | Form & Reinforce Equipment Pads | Material | Unit |  | 8
3374-439 | Pour Equipment Pads | Material | Unit |  | 8
3374-440 | Install odor control equipment | Material | Unit |  | 8
3374-441 | Electrical | Material | Unit |  | 8
3374-442-HT | Hydropneumatic Tank | Material | Unit |  | 8
3374-443 | Install augercast piles @ hydropneumatic tank pad | Material | Unit |  | 8
3374-444 | Hydropneumatic Tank Facility - Finegrade SOG | Material | Unit |  | 8
3374-445 | Hydropneumatic Tank Facility - Form & Reinforce SOG | Material | Unit |  | 8
3374-446 | Hydropneumatic Tank Facility - Pour SOG | Material | Unit |  | 8
3374-447 | Hydropneumatic Tank Facility - Finegrade Footings | Material | Unit |  | 8
3374-448 | Hydropneumatic Tank Facility - Form & Reinforce Footings | Material | Unit |  | 8
3374-449 | Hydropneumatic Tank Facility - Pour Footings | Material | Unit |  | 8
3374-450 | Hydropneumatic Tank Facility - Form Walls | Material | Unit |  | 8
3374-451 | Hydropneumatic Tank Facility - Pour Walls | Material | Unit |  | 8
3374-452 | Hydropneumatic Tank Facility - Form & Reinforce Equip Pads/Pedestals | Material | Unit |  | 8
3374-453 | Hydropneumatic Tank Facility - Pour Equip Pads/Pedestals | Material | Unit |  | 8
3374-454 | Stairs - Formwork & Reinforce | Material | Unit |  | 8
3374-455 | Stairs - Place | Material | Unit |  | 8
3374-456 | Relocate hydropneumatic tank | Material | Unit |  | 8
3374-457 | Install piping | Material | Unit |  | 8
3374-458 | Install miscellaneous metals | Material | Unit |  | 8
3374-459-ADPS | Anoxic Drain Pump Station | Material | Unit |  | 8
3374-460 | Excavate anoxic basin drain pump station | Material | Unit |  | 8
3374-461 | Set precast anoxic basin drain pump station structure & valve vault | Material | Unit |  | 8
3374-462 | Install grout fill at anoxic basin drain pump station | Material | Unit |  | 8
3374-463 | Coatings at anoxic basin drain pump station | Material | Unit |  | 8
3374-464 | Install pump | Material | Unit |  | 8
3374-465 | Install piping | Material | Unit |  | 8
3374-466 | Electrical | Material | Unit |  | 8
3374-467-De-Ox | De-Ox Splitter Box | Material | Unit |  | 8
3374-468 | DeOx Splitter Box - Finegrade SOG | Material | Unit |  | 8
3374-469 | DeOx Splitter Box - Form & Reinforce SOG | Material | Unit |  | 8
3374-470 | DeOx Splitter Box - Pour SOG | Material | Unit |  | 8
3374-471 | DeOx Splitter Box - Form & Reinforce Walls | Material | Unit |  | 8
3374-472 | DeOx Splitter Box - Pour Walls | Material | Unit |  | 8
3374-473 | DeOx Splitter Box - Stairs | Material | Unit |  | 8
3374-474 | DeOx Splitter Box - Fill Conc | Material | Unit |  | 8
3374-475-Train 1 | Train 1 Rehab | Material | Unit |  | 8
3374-476 | Clean out bio-basin #1 | Material | Unit |  | 8
3374-477 | Concrete demo bio-basin train #1 | Material | Unit |  | 8
3374-478 | Demo mechanical bio-basin train #1 | Material | Unit |  | 8
3374-479 | Install plug valves in 8" drain from clarifier #1 (post anoxic tank) | Material | Unit |  | 8
3374-480 | Form & reinforce new wall bio-basin #1 | Material | Unit |  | 8
3374-481 | Pour new wall at bio-basin #1 | Material | Unit |  | 8
3374-482 | Form & reinforce elevated slab bio basin 1 | Material | Unit |  | 8
3374-483 | Pour elevated slab bio basin 1 | Material | Unit |  | 8
3374-484 | Clean out post anoxic tank #1 | Material | Unit |  | 8
3374-485 | Demo existing equip. in clarifier #1 (post anoxic) | Material | Unit |  | 8
3374-486 | Sand fill pour slab in effluent box #1 - Post anoxic tank | Material | Unit |  | 8
3374-487 | Coatings on walls & floors bio-basin #1 | Material | Unit |  | 8
3374-488 | Concrete fill post anoxic tank #1 | Material | Unit |  | 8
3374-489 | Install Pump bio-basin #1 | Material | Unit |  | 8
3374-490 | Install mixer post anoxic tank #1 | Material | Unit |  | 8
3374-491 | Install mixers bio-basin #1 | Material | Unit |  | 8
3374-492 | Install covers post anoxic tank #1 | Material | Unit |  | 8
3374-493 | Install fine bubble diffusers bio-basin #1 | Material | Unit |  | 8
3374-494 | Install gates bio basin #1 | Material | Unit |  | 8
3374-495 | Install miscellaneous metals bio-basin #1 | Material | Unit |  | 8
3374-496 | Install 30" ML Transfer line | Material | Unit |  | 8
3374-497 | Install 20" ML line in Aeration Effluent Trough | Material | Unit |  | 8
3374-498 | Install 20" RAS line | Material | Unit |  | 8
3374-499 | Install 16" RS Line | Material | Unit |  | 8
3374-500 | Install SS AA lines from aeration blowers to the diffuser grids at the bio-basin #1 | Material | Unit |  | 8
3374-501 | Install DIP 12" IMLR from aeration 1 back to fermentation tank bio-basin #1 | Material | Unit |  | 8
3374-502 | Install FRP odor control duct | Material | Unit |  | 8
3374-503 | Install covers bio-basin #1 | Material | Unit |  | 8
3374-504 | Electrical | Material | Unit |  | 8
3374-505 | Painting | Material | Unit |  | 8
3374-508-Train 2 | Train 2 Rehab | Material | Unit |  | 8
3374-507 | Clean out bio-basin #2 | Material | Unit |  | 8
3374-508 | Concrete demo bio-basin #2 | Material | Unit |  | 8
3374-509 | Demo mechanical bio-basin train #2 | Material | Unit |  | 8
3374-510 | Install plug valves in 8" drain from clarifier #2 (post anoxic tank) | Material | Unit |  | 8
3374-511 | Form & reinforce new wall bio-basin #2 | Material | Unit |  | 8
3374-512 | Pour new wall at bio-basin #2 | Material | Unit |  | 8
3374-513 | Form & reinforce elevated slab bio basin 2 | Material | Unit |  | 8
3374-514 | Pour elevated slab bio basin 2 | Material | Unit |  | 8
3374-515 | Install Pump bio-basin #2 | Material | Unit |  | 8
3374-516 | Install mixers at bio-basin #2 | Material | Unit |  | 8
3374-517 | Coatings on walls & floors bio-basin #2 | Material | Unit |  | 8
3374-518 | Install fine bubble diffusers bio-basin #2 | Material | Unit |  | 8
3374-519 | Install AA lines bio-basin #2 | Material | Unit |  | 8
3374-520 | Install 30" ML Transfer line | Material | Unit |  | 8
3374-521 | Install 20" RAS line | Material | Unit |  | 8
3374-522 | Install 16" RS Line | Material | Unit |  | 8
3374-523 | Install DIP 12" IMLR from aeration 2 back to fermentation tank bio-basin #2 | Material | Unit |  | 8
3374-524 | Install gates bio basin #2 | Material | Unit |  | 8
3374-525 | Install miscellaneous metals bio-basin #2 | Material | Unit |  | 8
3374-526 | Clean out post anoxic tank #2 | Material | Unit |  | 8
3374-527 | Demo existing equip. in clarifier #2 (post anoxic) | Material | Unit |  | 8
3374-528 | Install covers at bio-basins #2 | Material | Unit |  | 8
3374-529 | Demo existing equipment post anoxic tank #2 | Material | Unit |  | 8
3374-530 | Concrete fill post anoxic tank #2 | Material | Unit |  | 8
3374-531 | Sand fill pour slab in effluent box #2 - Post anoxic tank | Material | Unit |  | 8
3374-532 | Install mixer at post anoxic tank #2 | Material | Unit |  | 8
3374-533 | Install FRP odor control duct | Material | Unit |  | 8
3374-534 | Install covers at post anoxic tank #2 | Material | Unit |  | 8
3374-535 | Electrical | Material | Unit |  | 8
3374-536 | Painting | Material | Unit |  | 8
3374-537-I&C | Instrumentation & Controls | Material | Unit |  | 8
3374-538 | Submittals | Material | Unit |  | 8
3374-539 | In-Line Field Instruments & Accessories | Material | Unit |  | 8
3374-540 | LCP and OIT Panels | Material | Unit |  | 8
3374-541 | SCADA Hardware/Software | Material | Unit |  | 8
3374-542 | Start-Up & Testing | Material | Unit |  | 8
3374-543-Allowance | Allowances | Material | Unit |  | 8
3374-544 | Owner Controlled Rock & Pile Contingency Allowance | Material | Unit |  | 8
3374-545 | General Owner Contingency Allowance | Material | Unit |  | 8
3374-546 | Soils & Concrete Testing Allowance | Material | Unit |  | 8
3374-547 | Hazardous Materials Allowance | Material | Unit |  | 8
3374-548 | Furniture & Miscellaneous Laboratory Furnishings Allowance | Material | Unit |  | 8
C00100566DB63_C27 | I-66/15 Change Order #27 | Material | Lump Sum |  | 1
C00100566DB63_C28 | I-66/15 Change Order #28 | Material | Lump Sum |  | 1
Product Dev | Product Development Resources | Labor |  |  | 1
Material | Material Resources | Material | Cubic Yard |  | 8
MathisL | Lane Mathis, CIO | Labor |  |  | 0
ManufEng | Manufacturing Engineering Group | Labor |  |  | 1
ProductOps | Product Operations Group | Labor |  |  | 1
ProductMktg | Product Marketing Group | Labor |  |  | 1
AndersonG | Glen Anderson, VP Development | Labor |  |  | 0
CharlesM | Mandy Charles, VP IT Ops | Labor |  | EA | 1
RiceB | Barbara Rice, PMO Director | Labor |  | PMO | 0
VincentI | Ian Vincent | Labor |  | DEV | 1
ZhuS | Shannon Zhu | Labor |  | QA | 1
LaffertyV | Vanessa Lafferty | Labor |  | EA | 1
BennettC | Carina Bennett | Labor |  | DEV | 1
PaxsonD | Dan Paxson | Labor |  | EA | 1
SinghD | Deepak Singh | Labor |  | QA | 1
SharpeD | Dan Sharpe | Labor |  | DEV | 1
ITCon | IT Consultant | Labor |  | BA | 1
LiR | Roy Li | Labor |  | PMO | 1
ChopraA | Amit Chopra | Labor |  | DEV | 1
AbrahamM | Molly Abraham | Labor |  | PMO | 1
WrenJ | Jo Wren | Labor |  | PMO | 1
CaseyA | Andrea Casey | Labor |  | Eng | 1
RileyP | Paul Riley | Labor |  | ProdAn | 1
MarshallG | Gary Marshall | Labor |  | ProdAn | 1
LeeC | Cindy Lee | Labor |  | ProdDes | 1
HillF | Frank Hill | Labor |  | ProdMgr | 1
WestL | Larry West | Labor |  | ProdMgr | 1
BaxterS | Sue Baxter | Labor |  | Tester | 1
WynnA | Alice Wynn | Labor |  | Tester | 1
LincolnR | Robert Lincoln | Labor |  | Eng | 1
ShawH | Harry Shaw | Labor |  | LeadEng | 1
JacksonL | Lendell Jackson | Labor |  | MarkMgr | 1
RickelsS | Sam Rickels | Labor |  | MarkMgr | 1
IthanP | Peg Ithan | Labor |  | Sales | 1
3347 - 1001 | CLEARING & GRUBBING | Material | Lump Sum |  | 1
3347 - 1002 | TYPE D ENGINEERS OFFICE | Material | Lump Sum |  | 1
3347 - 1003 | PRICE ADJUSTMENT FOR DIESEL FUEL | Material | Each |  | 1
3347 - 1004 | 5 INCH YELLOW NONTOXIC LEAD FREE WATERBORNE PAVEMENT MARKING PAINT | Material | Linear Feet |  | 1
3347 - 1005 | 5 INCH WHITE NONTOXIC LEAD FREE WATERBORNE PAVEMENT MARKING PAINT | Material | Linear Feet |  | 1
3347 - 1006 | 10 INCH YELLOW NONTOXIC LEAD FREE WATERBORNE PAVEMENT MARKING PAINT | Material | Linear Feet |  | 1
D-1-23 | 395 - CHANGE ORDERS | Material | Lump Sum |  | 8
NCR 24 | NCR 24 Redistribution | Material | Lump Sum |  | 8
NCR 28 | NCR 28 Redistribution | Material | Lump Sum |  | 8
NCR 29 | NCR 29 Redistribution | Material | Lump Sum |  | 8
NCR 30 | NCR 30 Redistribution | Material | Lump Sum |  | 8
NCR 32 | NCR 32 Redistribution | Material | Lump Sum |  | 8
NCR 33 | NCR 33 Redistribution | Material | Lump Sum |  | 8
NCR 34 | NCR 34 Redistribution | Material | Lump Sum |  | 8
NCR 35 | NCR 35 Redistribution | Material | Lump Sum |  | 8
NCR 37 | NCR 37 Redistribution | Material | Lump Sum |  | 8
NCR 40 | NCR 40 Redistribution | Material | Lump Sum |  | 8
NCR 41 | NCR 41 Redistribution | Material | Lump Sum |  | 8
NCR 42 | NCR 42 Redistribution | Material | Lump Sum |  | 8
NCR 46 | NCR 46 Redistribution | Material | Lump Sum |  | 8
NCR 56 | NCR 56 Redistribution | Material | Lump Sum |  | 8
NCR 67 | NCR 67 Redistribution | Material | Lump Sum |  | 8
NCR 73 | NCR 73 Redistribution | Material | Lump Sum |  | 8
NCR 74 | NCR 74 Redistribution | Material | Lump Sum |  | 8
NCR | NCR Redistribution | Material | Lump Sum |  | 8
3329-355 | SA12 - 24" WLD STL PIPE GRAD B IN SOIL(24", 0.500" THICK) (Eliminated) | Material | Linear Feet |  | 8
3329-354 | SA11 - 3804 Hydraulic Upgrades | Material | Lump Sum |  | 8
3329-356 | SA12 - 24" WLD STL PIPE GRAD B NOT IN SOIL(24", 0.500" THICK) (Eliminated) | Material | Linear Feet |  | 8
3329-357 | SA12 - 30" WLD STL PIPE GRAD B IN SOIL(30", 0.500" THICK) (Eliminated) | Material | Linear Feet |  | 8
3329-365 | SA12 - Brick Built Drainage Structures | Material | Each |  | 8
3329-344 | ADJUST EXISTING STEEL BEAM GUARDRAIL | Material |  |  | 8
3329-345 | DIGITAL SPEED LIMIT SIGN | Material |  |  | 8
3329-Supplemental | Suplemental Agreements | Material |  |  | 8
C00100566DB63_C29 | I-66/15 Change Order #29 | Material | Lump Sum |  | 1
C00100566DB63_C30 | I-66/15 Change Order #30 | Material | Lump Sum |  | 1
3329-346 | SA2 - 3804 CE (Environmental) | Material | Lump Sum |  | 8
3329-347 | SA3 - Storm Cleanout | Material | Lump Sum |  | 8
3329-348 | SA4 - Guardrail Maintenance | Material | Unit |  | 8
3329-349 | SA5 - Asbestos Removal | Material | Lump Sum |  | 8
3329-350 | SA7 - Type B Lights | Material | Lump Sum |  | 8
3329-351 | SA8 - I-3804 Design | Material | Lump Sum |  | 8
3329-352 | SA9 - China Grove Sidewalk | Material | Lump Sum |  | 8
3329-353 | SA10 - Rp D Wet Utility Accel | Material | Lump Sum |  | 8
3329-366 | SA13 - Food Lion Improvements | Material | Lump Sum |  | 8
C/O # 2 | Change Order # 2 | Material | Lump Sum |  | 1
DFW.85(CO 02) | Concrete Over-run based on exist CTB grades | Material | Square Yard |  | 1
NCR 83 | NCR 83 Redistribution | Material | Lump Sum |  | 8
NCR 84 | NCR 84 Redistribution | Material | Lump Sum |  | 8
NCR 86 | NCR 86 Redistribution | Material | Lump Sum |  | 8
NCR 87 | NCR 87 Redistribution | Material | Lump Sum |  | 8
3347 - Crew | 3347 - Crew Resources | Nonlabor |  |  | 1
3347-Rev | 3347 - Revenue Resources | Nonlabor |  |  | 1
3347 - 1007 | 12 INCH WHITE NONTOXIC LEAD FREE WATERBORNE PAVEMENT MARKING PAINT | Material | Linear Feet |  | 1
3347 - 1008 | 24 INCH WHITE NONTOXIC LEAD FREE WATERBORNE PAVEMENT MARKING PAINT | Material | Linear Feet |  | 1
3347 - 1009 | 5 INCH YELLOW REMOVABLE PREFORMED PAVEMENT LINE MARKINGS | Material | Linear Feet |  | 1
3347 - 1010 | 5 INCH WHITE REMOVABLE PREFORMED PAVEMENT LINE MARKINGS | Material | Linear Feet |  | 1
3347 - 1011 | 10 INCH YELLOW REMOVABLE PREFORMED PAVEMENT LINE MARKINGS | Material | Linear Feet |  | 1
3347 - 1012 | 10 INCH WHITE REMOVABLE PREFORMED PAVEMENT LINE MARKINGS | Material | Linear Feet |  | 1
3347 - 1013 | 12 INCH WHITE REMOVABLE PREFORMED PAVEMENT LINE MARKINGS | Material | Linear Feet |  | 1
3347 - 1014 | 24 INCH WHITE REMOVABLE PREFORMED PAVEMENT LINE MARKINGS | Material | Linear Feet |  | 1
3347 - 1015 | REMOVABLE PREFORMED LETTERS | Material | Each |  | 1
3347 - 1016 | REMOVABLE PREFORMED ARROWS | Material | Each |  | 1
3347 - 1017 | REMOVAL OF REMOVABLE PREFORMED LETTERS, SYMBOLS, ARROWS AND NUMBERS | Material | Each |  | 1
3347 - 1018 | REMOVAL OF REMOVABLE PREFORMED PAVEMENT MARKINGS - ANY WIDTH | Material | Linear Feet |  | 1
3347 - 1019 | REMOVAL OF EXISTING PAVEMENT LINE MARKINGS, ANY WIDTH | Material | Linear Feet |  | 1
3347 - 1020 | REMOVAL OF EXISTING PAVEMENT LETTERS, SYMBOLS, ARROWS AND NUMBERS | Material | Each |  | 1
3347 - 1021 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 1
3347 - 1022 | GRADED AGGREGATE BASE FOR MAINTENANCE OF TRAFFIC | Material |  |  | 1
3347 - 1023 | ASPHALT FOR MAINTENANCE OF TRAFFIC | Material |  |  | 1
3347 - 1024 | STEEL PLATE 8 FOOT X 12 FOOT X 1 INCH FOR MAINTENANCE OF TRAFFIC RENTAL PER DAY | Material | Each |  | 1
3347 - 1025 | ARROW PANEL | Material | Day |  | 1
3347 - 1026 | TEMPORARY TRAFFIC SIGNS HIGH PERFORMANCE WIDE ANGLE RETROREFLECTIVE SHEETING | Material | Square Feet |  | 1
3347 - 1027 | RESET PRECAST TEMPORARY CONCRETE TRAFFIC BARRIER FOR MAINTENANCE OF TRAFFIC | Material | Linear Feet |  | 1
3347 - 1028 | REFLECTIVE BARRIER MARKERS | Material | Each |  | 1
3347 - 1029 | TYPE III BARRICADE FOR MAINTENANCE OF TRAFFIC | Material | Each |  | 1
3347 - 1030 | TEMPORARY CRASH CUSHION SAND FILLED PLASTIC BARRELS FOR MAINTENANCE OF TRAFFIC | Material | Each |  | 1
3347 - 1031 | REPLACE TEMPORARY CRASH CUSHION SAND FILLED PLASTIC BARRELS FOR MAINTENANCE OF TRAFFIC | Material | Each |  | 1
3347 - 1032 | VERTICAL PANELS | Material | Each |  | 1
3347 - 1033 | RELOCATE SIGN | Material | Square Feet |  | 1
3347 - 1034 | REMOVE SIGN | Material | Square Feet |  | 1
3347 - 1035 | TEMPORARY ORANGE CONSTRUCTION FENCE | Material | Linear Feet |  | 1
3347 - 1036 | REMOVE AND RESET TEMPORARY ORANGE CONSTRUCTION FENCE | Material | Linear Feet |  | 1
3347 - 1037 | DRUMS FOR MAINTENANCE OF TRAFFIC | Material | Each |  | 1
3347 - 1038 | PORTABLE VARIABLE MESSAGE SIGN | Material | Day |  | 1
3347 - 1040 | PROTECTION VEHICLE | Material | Day |  | 1
3347 - 1041 | TEMPORARY TYPE E TRAFFIC BARRIER END TREATMENT FOR 40 MPH, ANY WIDTH | Material | Each |  | 1
3347 - 1042 | TEMPORARY TYPE E TRAFFIC BARRIER END TREATMENT FOR 50 MPH, ANY WIDTH | Material | Each |  | 1
3347 - 1043 | TEMPORARY TYPE E TRAFFIC BARRIER END TREATMENT FOR 65 MPH, ANY WIDTH | Material | Each |  | 1
3347 - 1044 | PRECAST TEMPORARY 32 INCH F SHAPE CONCRETE TRAFFIC BARRIER | Material | Linear Feet |  | 1
3347 - 1045 | CONSTRUCTION STAKEOUT | Material | Lump Sum |  | 1
3347 - 1046 | MOBILIZATION | Material | Lump Sum |  | 1
3347 - 1047 | CPM PROJECT SCHEDULE | Material | Lump Sum |  | 1
3347 - 1048 | TUBULAR MARKERS | Material | Each |  | 1
3347 - 1050 | ON-THE-JOB TRAINING | Material | Hour |  | 1
3347 - 2001 | INCLINOMETER (INCLUDES MONITORING) | Material | Each |  | 1
3347 - 2002 | SETTLEMENT PLATE (INCLUDES MONITORING) | Material | Each |  | 1
3347 - 2003 | CLASS 1 EXCAVATION | Material | Cubic Yard |  | 1
3347 - 2004 | CLASS 1-A EXCAVATION | Material | Cubic Yard |  | 1
3347 - 2005 | GEOSYNTHETIC STABILIZED SUBGRADE USING GRADED AGGREGATE BASE | Material | Cubic Yard |  | 1
3347 - 2006 | UNCLASSIFIED EXCAVATION REINFORCED SLOPE BACKFILL | Material | Cubic Yard |  | 1
3347 - 2007 | SELECT BORROW | Material | Cubic Yard |  | 1
3347 - 2008 | COMMON BORROW | Material | Cubic Yard |  | 1
3347 - 2009 | TEST PIT EXCAVATION | Material | Cubic Yard |  | 1
3347 - 2010 | REMOVAL OF EXISTING PAVEMENT | Material | Cubic Yard |  | 1
3347 - 2011 | REMOVAL OF EXISTING MASONRY | Material | Cubic Yard |  | 1
3347 - 2012 | REMOVE EXISTING MANHOLE | Material | Each |  | 1
3347 - 2013 | GEOTEXTILE INCLUSION, CLASS SD TYPE II (NON WOVEN) | Material | Square Yard |  | 1
3347 - 2014 | REINFORCED SOIL SLOPE | Material | Square Feet |  | 1
3347 - 3001 | MODIFIED TYPE H END WALL | Material | Each |  | 1
3347 - 3002 | MODIFIED TYPE K INLET | Material | Each |  | 1
3347 - 3003 | STABILIZED CONSTRUCTION ENTRANCE | Material | Each |  | 1
3347 - 3004 | 15 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material | Linear Feet |  | 1
3347 - 3005 | 18 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material | Linear Feet |  | 1
3347 - 3006 | 24 INCH REINFORCED CONCRETE PIPE, CUSS IV | Material | Linear Feet |  | 1
3347 - 3007 | 27 INCH REINFORCED CONCRETE PIPE, CUSS IV | Material | Linear Feet |  | 1
3347 - 3008 | 36 INCH REINFORCED CONCRETE PIPE, CUSS IV | Material | Linear Feet |  | 1
3347 - 3009 | 42 INCH REINFORCED CONCRETE PIPE, CUSS IV | Material | Linear Feet |  | 1
3347 - 3010 | 15 INCH REINFORCED CONCRETE PIPE, CLASS V | Material | Linear Feet |  | 1
3347 - 3011 | 18 INCH REINFORCED CONCRETE PIPE, CLASS V | Material | Linear Feet |  | 1
3347 - 3012 | 14 INCH X 23 INCH HORIZONTAL ELLIPTICAL REINFORCED CONCRETE PIPE, CLASS HE IV | Material | Linear Feet |  | 1
3347 - 3013 | 19 INCH X 30 INCH HORIZONTAL ELLIPTICAL REINFORCED CONCRETE PIPE, CLASS HE IV | Material | Linear Feet |  | 1
3347 - 3014 | 22 INCH X 34 INCH HORIZONTAL ELLIPTICAL REINFORCED CONCRETE PIPE, CLASS HE IV | Material | Linear Feet |  | 1
3347 - 3015 | 24 INCH X 36 INCH HORIZONTAL ELLIPTICAL REINFORCED CONCRETE PIPE, CLASS HE IV | Material | Linear Feet |  | 1
3347 - 3016 | 29 INCH X 45 INCH HORIZONTAL ELLIPTICAL REINFORCED CONCRETE PIPE, CLASS HE IV | Material | Linear Feet |  | 1
3347 - 3017 | 34 INCH X 53 INCH HORIZONTAL ELLIPTICAL REINFORCED CONCRETE PIPE, CLASS HE IV | Material | Linear Feet |  | 1
3347 - 3018 | 15 INCH CORRUGATED POLYETHYLENE PIPE, TYPE S | Material | Linear Feet |  | 1
3347 - 3019 | 18 INCH CORRUGATED POLYETHYLENE PIPE, TYPE S | Material | Linear Feet |  | 1
3347 - 3020 | 24 INCH CORRUGATED POLYETHYLENE PIPE, TYPE S | Material | Linear Feet |  | 1
3347 - 3021 | STANDARD TYPE C ENDWALL FOR 18 INCH PIPE | Material | Each |  | 1
3347 - 3022 | STANDARD TYPE H ENDWALL FOR 18 INCH PIPE | Material | Each |  | 1
3347 - 3023 | STANDARD TYPE H ENDWALL FOR 24 INCH PIPE | Material | Each |  | 1
3347 - 3024 | STANDARD TYPE C ENDWALL FOR HORIZONTAL ELLIPTICAL 19 INCH X 30 INCH CONCRETE PIPE | Material | Each |  | 1
3347 - 3025 | STANDARD TYPE C ENDWALL FOR HORIZONTAL ELLIPTICAL 24 INCH X 38 INCH CONCRETE PIPE | Material | Each |  | 1
3347 - 3026 | STANDARD TYPE C ENDWALL FOR HORIZONTAL ELLIPTICAL 29 INCH X 45 INCH CONCRETE PIPE | Material | Each |  | 1
3347 - 3027 | STANDARD TYPE C ENDWALL FOR HORIZONTAL ELLIPTICAL 34 INCH X 53 INCH CONCRETE PIPE | Material | Each |  | 1
3347 - 3028 | 15 INCH STANDARD CONCRETE END SECTION | Material | Each |  | 1
3347 - 3029 | 18 INCH STANDARD CONCRETE END SECTION | Material | Each |  | 1
3347 - 3030 | 24 INCH STANDARD CONCRETE END SECTION | Material | Each |  | 1
3347 - 3031 | 27 INCH STANDARD CONCRETE END SECTION | Material | Each |  | 1
3347 - 3032 | SINGLE WR INLET-MINIMUM DEPTH | Material | Each |  | 1
3347 - 3033 | SINGLE WR INLET-VERTICAL DEPTH | Material | Linear Feet |  | 1
3347 - 3034 | STANDARD 5 FT COG INLETMINIMUMDEPTH | Material | Each |  | 1
3347 - 3035 | STANDARD 10 FT COG INLETMINIMUMDEPTH | Material | Each |  | 1
3347 - 3036 | STANDARD 15 FT COG INLETMINIMUMDEPTH | Material | Each |  | 1
3347 - 3037 | STANDARD COG INLET-VERTICAL DEPTH | Material | Linear Feet |  | 1
3347 - 3040 | STANDARD DOUBLE OPENING TYPE K INLET OPEN END GRATE- MINIMUM DEPTH | Material | Each |  | 1
3347 - 3041 | STANDARD DOUBLE OPENING TYPE K INLET OPEN END GRATEVERTICALDEPTH | Material | Linear Feet |  | 1
3347 - 3042 | STANDARD TYPE S INLET, DOUBLE GRATE TANDEM - MINIMUM DEPTH | Material | Each |  | 1
3347 - 3043 | STANDARD TYPE S INLET, DOUBLE GRATE TANDEM - VERTICAL DEPTH | Material | Linear Feet |  | 1
3347 - 3044 | STANDARD TYPE S COMBINATION INLET, DOUBLE GRATE TANDEM MINIMUMDEPTH | Material | Each |  | 1
3347 - 3045 | STANDARD TYPE S COMBINATION INLET, DOUBLE GRATE TANDEM VERTICALDEPTH | Material | Linear Feet |  | 1
3347 - 3046 | STANDARD YARD INLET - MINIMUM DEPTH | Material | Each |  | 1
3347 - 3047 | STANDARD YARD INLET - VERTICAL DEPTH | Material | Linear Feet |  | 1
3347 - 3048 | 48 INCH DIAMETER MANHOLE FOR 12 INCH TO 24 INCH PIPES - MINIMUM DEPTH | Material | Each |  | 1
3347 - 3049 | 48 INCH DIAMETER MANHOLE VERTICALDEPTH | Material | Linear Feet |  | 1
3347 - 3050 | 60 INCH DIAMETER MANHOLE FOR 27 INCH TO 36 INCH PIPES - MINIMUM DEPTH | Material | Each |  | 1
3347 - 3051 | 60 INCH DIAMETER MANHOLE VERTICALDEPTH | Material | Linear Feet |  | 1
3347 - 3052 | 72 INCH DIAMETER MANHOLE FOR 42 INCH AND 48 INCH PIPES - MINIMUM DEPTH | Material | Each |  | 1
3347 - 3054 | 84 INCH DIAMETER MANHOLE FOR 54 INCH AND 60 INCH PIPES - MINIMUM DEPTH | Material | Each |  | 1
3347 - 3056 | 6 INCH PERFORATED CIRCULAR PIPE LONGITUDINAL UNDERDRAIN | Material | Linear Feet |  | 1
3347 - 3057 | 6 INCH PERFORATED CIRCULAR PIPE UNDERDRAIN | Material | Linear Feet |  | 1
3347 - 3058 | EROSION AND SEDIMENT CONTROL ORIGINAL EXCAVATION | Material | Cubic Yard |  | 1
3347 - 3059 | EROSION AND SEDIMENT CONTROL CLEANOUT EXCAVATION | Material | Cubic Yard |  | 1
3347 - 3060 | EARTH DIKE | Material | Linear Feet |  | 1
3347 - 3061 | INLET PROTECTION | Material | Each |  | 1
3347 - 3062 | REMOVABLE PUMPING STATION | Material | Each |  | 1
3347 - 3063 | QUARTERLY EROSION AND SEDIMENT CONTROL INCENTIVE | Material | Each |  | 1
3347 - 3064 | FINAL EROSION AND SEDIMENT CONTROL INCENTIVE | Material | Lump Sum |  | 1
3347 - 3065 | TEMPORARY GABION OUTLET STRUCTURES | Material | Each |  | 1
3347 - 3066 | GABION INFLOW PROTECTION | Material | Cubic Yard |  | 1
3347 - 3067 | CLASS 1 RIPRAP FOR SLOPE AND CHANNEL PROTECTION | Material | Square Yard |  | 1
3347 - 3068 | RIPRAP FOR SEDIMENT CONTROL | Material |  |  | 1
3347 - 3069 | NO. 57 STONE FOR SEDIMENT CONTROL | Material |  |  | 1
3347 - 3070 | GEOTEXTILE CLASS ST | Material | Square Yard |  | 1
3347 - 3071 | SILT FENCE | Material | Linear Feet |  | 1
3347 - 3072 | SUPER SILT FENCE | Material | Linear Feet |  | 1
3347 - 3073 | NO 2 AGGREGATE FOR STORMWATER MANAGEMENT FACILITIES | Material | Cubic Yard |  | 1
3347 - 3074 | NO 7 AGGREGATE FOR STORMWATER MANAGEMENT FACILITIES | Material | Cubic Yard |  | 1
3347 - 3075 | NO 57 AGGREGATE FOR STORMWATER MANAGEMENT FACILITIES | Material | Cubic Yard |  | 1
3347 - 3076 | 6 INCH SUB-DRAIN PIPE | Material | Linear Feet |  | 1
3347 - 3077 | COARSE SAND FOR STORMWATER MANAGEMENT FACILITIES | Material | Cubic Yard |  | 1
3347 - 3078 | BIORETENTION SOIL MIX | Material | Cubic Yard |  | 1
3347 - 3079 | STORMWATER MANAGEMENT FACILITY AS-BUILT CERTIFICATION | Material | Lump Sum |  | 1
3347 - 3080 | BOTTOM CUTOFF WALLS FOR CLASS I RIPRAP | Material | Linear Feet |  | 1
3347 - 3081 | WICK DRAINS | Material | Linear Feet |  | 1
3347 - 3082 | FLOWABLE BACKFILL FOR PIPE ABANDONMENT | Material | Cubic Yard |  | 1
3347 - 3083 | 12 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material | Linear Feet |  | 1
3347 - 3084 | PORTABLE SEDIMENT TANK | Material | Each |  | 1
3347 - 3085 | TEMPORARY SWALE | Material | Linear Feet |  | 1
3347 - 3086 | SUMP PIT | Material | Each |  | 1
3347 - 3087 | DIVERSION FENCE | Material | Linear Feet |  | 1
3347 - 3088 | 3/4 INCH TO 1 1/2 INCH STONE FOR SEDIMENT CONTROL | Material |  |  | 1
3347 - 3089 | 2 INCH TO 3 INCH STONE FOR SEDIMENT CONTROL | Material |  |  | 1
3347 - 3090 | 4 INCH TO 7 INCH STONE FOR SEDIMENT CONTROL | Material |  |  | 1
3347 - 3091 | CLAY BACKFILL FOR CORE TRENCH | Material | Cubic Yard |  | 1
3347 - 3092 | MODIFIED 72 INCH MANHOLE INLET | Material | Each |  | 1
3347 - 3093 | 18 INCH PIPE SLOPE DRAIN | Material | Linear Feet |  | 1
3347 - 3094 | SANDBAGS | Material | Each |  | 1
3347 - 3095 | ACCESS ROAD WITH CELLULAR CONFINEMENT LOAD SUPPORT SYSYTEM | Material | Square Yard |  | 1
3347 - 3096 | MODIFIED 60 INCH MANHOLE INLET | Material | Each |  | 1
3347 - 3097 | MIX 3 CONCRETE FOR MISCELLANEOUS STRUCTURES | Material | Cubic Yard |  | 1
3347 - 3098 | 18 INCH REINFORCED CONCRETE PIPE, AMERICAN SOCIETY FOR TESTING AND MATERIALS C-361 | Material | Linear Feet |  | 1
3347 - 3099 | 24 INCH REINFORCED CONCRETE PIPE, AMERICAN SOCIETY FOR TESTING AND MATERIALS C-361 | Material | Linear Feet |  | 1
3347 - 3100 | 14 INCH X 23 INCH REINFORCED CONCRETE PIPE, AMERICAN SOCIETY FOR TESTING AND MATERIALS C-361 | Material | Linear Feet |  | 1
3347 - 3101 | STANDARD SINGLE OPENING TYPE K INLET OPEN END GRATE NONTRAFFIC AREAS-MINIMUM DEPTH | Material | Each |  | 1
3347 - 3102 | STANDARD SINGLE OPENING TYPE K INLET OPEN END GRATE NONTRAFFIC AREAS-VERTICAL DEPTH | Material | Linear Feet |  | 1
3347 - 4001 | 17 INCH X 26 INCH HDPE DOUBLE PIPE CULVERTS, BRANDYWINE (SI). DYSON ROAD (S2) | Material | Lump Sum |  | 1
3347 - 4002 | CLASS 3 EXCAVATION | Material | Cubic Yard |  | 1
3347 - 4003 | DYNAMIC PILE MONITORING | Material | Each |  | 1
3347 - 4004 | CAPWAP | Material | Each |  | 1
3347 - 4005 | STEEL HP 12 X 53 BEARING PILE | Material | Linear Feet |  | 1
3347 - 4006 | STEEL HP 12 X 53 BEARING TEST PILE | Material | Linear Feet |  | 1
3347 - 4007 | FOOTING CONCRETE | Material | Cubic Yard |  | 1
3347 - 4008 | SUBSTRUCTURE CONCRETE FOR BRIDGE | Material | Lump Sum |  | 1
3347 - 4009 | SUPERSTRUCTURE CONCRETE FOR BRIDGE | Material | Lump Sum |  | 1
3347 - 4010 | CONCRETE PARAPET | Material | Lump Sum |  | 1
3347 - 4012 | EPOXY COATED REINFORCEMENT STEEL BARS IN SUPERSTRUCTURE | Material | Lump Sum |  | 1
3347 - 4013 | FABRICATED STRUCTURAL STEEL | Material | Lump Sum |  | 1
3347 - 4014 | STEEL STUD SHEAR DEVELOPERS | Material | Lump Sum |  | 1
3347 - 4015 | CHAIN LINK SAFETY FENCE FOR BRIDGE-TYPE I | Material | Linear Feet |  | 1
3347 - 4016 | CHAIN LINK SAFETY FENCE FOR BRIDGE-TYPE II | Material | Linear Feet |  | 1
3347 - 4017 | RIPRAP SLOPE PROTECTION FOR BRIDGE | Material | Square Yard |  | 1
3347 - 5001 | SUPERPAVE ASPHALT MIX 9.5MM FOR SURFACE, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5002 | SUPERPAVE ASPHALT MIX 9.5MM FOR WEDGE/LEVEL, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5003 | GAP-GRADED ASPHALT MIX 12.5MM FOR SURFACE, PG 64E-22, LEVEL 5 | Material |  |  | 1
3347 - 5004 | SUPERPAVE ASPHALT MIX 19.0W1M FOR BASE, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5005 | SUPERPAVE ASPHALT MIX 19.0MM FOR WEDGE/LEVEL, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5006 | SUPERPAVE ASPHALT MIX 25.0MM FOR BASE, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5007 | SUPERPAVE ASPHALT MIX 25.0MM FOR FULL-DEPTH PATCH, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5008 | SUPERPAVE ASPHALT MIX 25.0MM. FOR PARTIAL-DEPTH PATCH, PG 64S-22, LEVEL 2 | Material |  |  | 1
3347 - 5009 | PRICE ADJUSTMENT FOR ASPHALT BINDER | Material | Each |  | 1
3347 - 5010 | PAYMENT ADJUSTMENT FOR PAVEMENT DENSITY | Material | Each |  | 1
3347 - 5011 | PAYMENT ADJUSTMENT FOR ASPHALT MIXTURE | Material | Each |  | 1
3347 - 5012 | 4 INCH GRADED AGGREGATE BASE COURSE | Material | Square Yard |  | 1
3347 - 5013 | 5 INCH GRADED AGGREGATE BASE COURSE | Material | Square Yard |  | 1
3347 - 5014 | 6 INCH GRADED AGGREGATE BASE COURSE | Material | Square Yard |  | 1
3347 - 5015 | GRINDING ASPHALT PAVEMENT 0 INCH TO 2 INCH | Material | Square Yard |  | 1
3347 - 5016 | PAVEMENT SURFACE PROFILE PAY ADJUSTMENT | Material | Each |  | 1
3347 - 5017 | 9 INCH PLAIN PORTLAND CEMENT CONCRETE PAVEMENT MIX 7 | Material | Square Yard |  | 1
3347 - 5018 | REMOVAL OF UNSUITABLE MATERIAL AND REFILL | Material | Cubic Yard |  | 1
3347 - 5019 | SNOWPLOWABLE RAISED PAVEMENT MARKERS | Material | Each |  | 1
3347 - 5020 | 5 INCH WHITE PERMANENT PREFORMED PATTERNED REFLECTIVE PAVEMENT MARKINGS | Material | Linear Feet |  | 1
3347 - 5021 | 5 INCH WHITE PERMANENT PREFORMED PATTERNED REFLECTIVE CONTRAST PAVEMENT MARKINGS (PPPRCP) | Material | Linear Feet |  | 1
3347 - 5022 | 10 INCH WHITE PERMANENT PREFORMED PATTERNED REFLECTIVE PAVEMENT MARKINGS | Material | Linear Feet |  | 1
3347 - 5023 | 5 INCH YELLOW PERMANENT PREFORMED PATTERNED REFLECTIVE PAVEMENT MARKINGS | Material | Linear Feet |  | 1
3347 - 5024 | 5 INCH WHITE PREFORMED THERMOPLASTIC PAVEMENT MARKING LINES | Material | Linear Feet |  | 1
3347 - 5025 | 5 INCH YELLOW PREFORMED THERMOPLASTIC PAVEMENT MARKING LINES | Material | Linear Feet |  | 1
3347 - 5026 | 12 INCH WHITE PREFORMED THERMOPLASTIC PAVEMENT .MARKING LINES | Material | Linear Feet |  | 1
3347 - 5027 | 24 INCH WHITE PREFORMED THERMOPLASTIC PAVEMENT MARKING LINES | Material | Linear Feet |  | 1
3347 - 5028 | WHITE PREFORMED THERMOPLASTIC PAVEMENT MARKING LEGENDS AND SYMBOLS | Material | Square Feet |  | 1
3347 - 5029 | 5 INCH WHITE LEAD FREE REFLECTIVE THERMOPLASTIC PAVEMENT MARKINGS | Material | Linear Feet |  | 1
3347 - 5030 | 5 INCH YELLOW LEAD FREE REFLECTIVE THERMOPLASTIC PAVEMENT MARKINGS | Material | Linear Feet |  | 1
3347 - 5031 | 10 INCH WHITE LEAD FREE REFLECTIVE THERMOPLASTIC PAVEMENT MARKINGS | Material | Linear Feet |  | 1
3347 - 6001 | MODIFIED MONOLITHIC CONCRETE MEDIAN 2' WIDE TYPE A-1 | Material | Linear Feet |  | 1
3347 - 6002 | MODIFIED MONOLITHIC CONCRETE MEDIAN 2' WIDE TYPE C-1 | Material | Linear Feet |  | 1
3347 - 6003 | MODIFIED TYPE A COMB. CURB AND GUTTER, 12"GP/12nDEPTH | Material | Linear Feet |  | 1
3347 - 6004 | MODIFIED TYPE C COMB. CURB AND GUTTER, 12"GP/12"DEPTH | Material | Linear Feet |  | 1
3347 - 6005 | PIPE RAILING | Material | Linear Feet |  | 1
3347 - 6006 | 42 INCH F SHAPE CONCRETE MEDIAN TRAFFIC BARRIER BIFURCATED FROM 0 INCH TO 1 FOOT 6 INCHES | Material | Linear Feet |  | 1
3347 - 6007 | 42 INCH F SHAPE CONCRETE MEDIAN TRAFFIC BARRIER BIFURCATED FROM 1 FOOT 6 INCHES TO 4 FEET 0 INCHES | Material | Linear Feet |  | 1
3347 - 6008 | 42 INCH F SHAPE CONCRETE TRAFFIC BARRIER SINGLE FACE TYPE 2 | Material | Linear Feet |  | 1
3347 - 6009 | 42 INCH F SHAPE CONCRETE TRAFFIC BARRIER SINGLE FACE TYPE 3 | Material | Linear Feet |  | 1
3347 - 6010 | 42 INCH F SHAPE CONCRETE TRAFFIC BARRIER SINGLE FACE END TRANSITION | Material | Each |  | 1
3347 - 6011 | STANDARD TYPE A CURB 8 INCH X 17 INCH | Material | Linear Feet |  | 1
3347 - 6012 | STANDARD TYPE A COMBINATION CURB AND GUTTER 12 INCH GUTTER PAN 9 INCH DEPTH | Material | Linear Feet |  | 1
3347 - 6013 | STANDARD TYPE A COMBINATION CURB AND GUTTER 12 INCH GUTTER PAN 10 INCH DEPTH | Material | Linear Feet |  | 1
3347 - 6014 | STANDARD TYPE C COMBINATION CURB AND GUTTER 12 INCH GUTTER PAN 10 INCH DEPTH | Material | Linear Feet |  | 1
3347 - 6015 | STANDARD TYPE D COMBINATION CURB AND GUTTER 12 INCH GUTTER PAN 9 INCH DEPTH | Material | Linear Feet |  | 1
3347 - 6016 | WHEEL STOPS | Material | Each |  | 1
3347 - 6017 | 5 INCH CONCRETE SIDEWALK | Material | Square Feet |  | 1
3347 - 6018 | DETECTABLE WARNING SURFACE FOR CURB RAMPS | Material | Square Feet |  | 1
3347 - 6019 | TRAFFIC BARRIER W BEAM USING 6 FOOT POST | Material | Linear Feet |  | 1
3347 - 6020 | TRAFFIC BARRIER W BEAM MEDIAN BARRIER | Material | Linear Feet |  | 1
3347 - 6021 | TRAFFIC BARRIER W BEAM ANCHORAGE AT BRIDGE END POST OR CONCRETE TRAFFIC BARRIER SINGLE FACE | Material | Each |  | 1
3347 - 6022 | TRAFFIC BARRIER THRIE BEAM ANCHORAGE AT BRIDGE END POST | Material | Each |  | 1
3347 - 6023 | TYPE C TRAFFIC BARRIER END TREATMENT | Material | Each |  | 1
3347 - 6024 | TYPE D TRAFFIC BARRIER END TREATMENT | Material | Each |  | 1
3347 - 6025 | TYPE K TRAFFIC BARRIER END TREATMENT, ANY OPTION | Material | Each |  | 1
3347 - 6026 | TYPE L TRAFFIC BARRIER ANCHORAGE USING OPTION 2 OR 3 | Material | Each |  | 1
3347 - 6027 | REMOVE AND RESET EXISTING TRAFFIC BARRIER W BEAM | Material | Linear Feet |  | 1
3347 - 6028 | REMOVAL AND DISPOSAL OF EXISTING TRAFFIC BARRIER W BEAM | Material | Linear Feet |  | 1
3347 - 6029 | CONCRETE MEDIAN TRAFFIC BARRIER "TRANSITION AT NEW LIGHT POLE | Material | Each |  | 1
3347 - 7002 | PLACING FURNISHED SUBSOIL 12 INCH DEPTH | Material | Square Yard |  | 1
3347 - 7003 | PLACING FURNISHED SUBSOIL 18 INCH DEPTH | Material | Square Yard |  | 1
3347 - 7005 | PLACING FURNISHED TOPSOIL 4 INCH DEPTH | Material | Square Yard |  | 1
3347 - 7006 | TEMPORARY SEED | Material | Square Yard |  | 1
3347 - 7007 | TEMPORARY MULCH | Material | Square Yard |  | 1
3347 - 7008 | TURFGRASS ESTABLISHMENT | Material | Square Yard |  | 1
3347 - 7009 | UPLAND SHRUB SEEDING | Material | Square Yard |  | 1
3347 - 7010 | UPLAND MEADOW ESTABLISHMENT | Material | Square Yard |  | 1
3347 - 7011 | WET MEADOW ESTABLISHMENT | Material | Square Yard |  | 1
3347 - 7012 | TURFGRASS SOD ESTABLISHMENT | Material | Square Yard |  | 1
3347 - 7013 | TYPE A SOIL STABILIZATION MATTING | Material | Square Yard |  | 1
3347 - 7014 | TYPE D SOIL STABILIZATION MATTING | Material | Square Yard |  | 1
3347 - 7015 | TREE, SHRUB, AND PERENNIAL INSTALLATION AND ESTABLISHMENT | Material | Lump Sum |  | 1
3347 - 7017 | SHREDDED HARDWOOD BARK MULCHING 3 INCH DEPTH | Material | Square Yard |  | 1
3347 - 7018 | TREE ROOT PRUNING | Material | Linear Feet |  | 1
3347 - 7019 | TREE BROADCAST FERTILIZING | Material | Square Yard |  | 1
3347 - 7020 | CONSTRUCTING PLANTING BEDS | Material | Square Yard |  | 1
3347 - 7021 | PLACING FURNISHED TOPSOIL 2 INCH DEPTH | Material | Square Yard |  | 1
3347 - 8001 | 40 FOOT LIGHT STRUCTURE - TWIN 20 FOOT BRACKET ARMS | Material | Each |  | 1
3347 - 8002 | 16 INCH WATER MAIN IN 30 INCH STEEL CASING | Material | Linear Feet |  | 1
3347 - 8003 | 24 INCH WATER MAIN IN 42 INCH STEEL CASING | Material | Linear Feet |  | 1
3347 - 8004 | 30 INCH WATER MAIN IN 48 INCH STEEL CASING | Material | Linear Feet |  | 1
3347 - 8005 | CONCRETE FOUNDATION FOR GROUND MOUNTED SIGNS | Material | Cubic Yard |  | 1
3347 - 8006 | CONCRETE FOR LIGHT FOUNDATION | Material | Cubic Yard |  | 1
3347 - 8007 | CONCRETE FOR SIGNAL FOUNDATION | Material | Cubic Yard |  | 1
3347 - 8008 | CONCRETE FOUNDATION FOR OVERHEAD SIGN STRUCTURES | Material | Cubic Yard |  | 1
3347 - 8009 | WOOD SIGN SUPPORTS 4 INCH X 4 INCH | Material | Linear Feet |  | 1
3347 - 8010 | WOOD SIGN SUPPORTS 4 INCH X 6 INCH | Material | Linear Feet |  | 1
3347 - 8011 | REMOVE EXISTING GROUND MOUNTED SIGNS AND SUPPORTS | Material | Square Feet |  | 1
3347 - 8012 | NO. 6 AWG STRANDED BARE COPPER GROUND WIRE | Material |  |  | 1
3347 - 8013 | NO. 4 AWG STRANDED BARE COPPER GROUND WIRE | Material |  |  | 1
3347 - 8014 | ELECTRICAL CABLE 1-CONDUCTOR, 2/0 AWG, TYPE THHN | Material |  |  | 1
3347 - 8018 | WEATHER HEAD, 3 INCH | Material | Each |  | 1
3347 - 8019 | 4 INCH SCHEDULE 80 RIGID PVC CONDUIT-BORED | Material |  |  | 1
3347 - 8020 | 2 INCH SCHEDULE 80 RIGID PVC CONDUIT-TRENCHED | Material |  |  | 1
3347 - 8021 | 3 INCH SCHEDULE 80 RIGID PVC CONDUIT-TRENCHED | Material |  |  | 1
3347 - 8022 | 4 INCH SCHEDULE 80 RIGID PVC CONDUIT-TRENCHED | Material |  |  | 1
3347 - 8023 | 3 INCH SCHEDULE 80 RIGID PVC CONDUIT-SLOTTED | Material |  |  | 1
3347 - 8024 | LED ROADWAY LUMINAIRE | Material | Each |  | 1
3347 - 8025 | LED SIGN LUMINAIRE | Material | Each |  | 1
3347 - 8027 | ELECTRICAL UTILITY SERVICE EQUIPMENT 120/240 VOLTS 200 AMPS | Material | Each |  | 1
3347 - 8028 | EMBEDDED METERED SERVICE PEDESTAL | Material | Each |  | 1
3347 - 8029 | 40 FOOT LIGHT STRUCTURE - 30 FOOT BRACKET ARM | Material | Each |  | 1
3347 - 8030 | 40 FOOT LIGHT STRUCTURE - 25 FOOT BRACKET ARM | Material | Each |  | 1
3347 - 8031 | 40 FOOT LIGHT STRUCTURE - 20 FOOT BRACKET ARM | Material | Each |  | 1
3347 - 8032 | 40 FOOT LIGHT STRUCTURE - 15 FOOT BRACKET ARM | Material | Each |  | 1
3347 - 8033 | 40 FOOT LIGHT STRUCTURE - 10 FOOT BRACKET ARM | Material | Each |  | 1
3347 - 8034 | ELECTRICAL CABLE 3-CONDUCTOR NO. 12AWG COPPER TYPE T/C | Material | Linear Feet |  | 1
3347 - 8035 | ELECTRICAL CABLE 1-CONDUCTOR NO. 8 AWG-THHN/THWN | Material | Linear Feet |  | 1
3347 - 8036 | NONINVASIVE DETECTOR, 1000 FOOT LEAD IN CABLE | Material | Each |  | 1
3347 - 8037 | FURNISH AND INSTALL ELECTRICAL HANDHOLE | Material | Each |  | 1
3347 - 8038 | FURNISH AND INSTALL ELECTRICAL MANHOLE | Material | Each |  | 1
3347 - 8039 | FIRE HYDRANT | Material | Each |  | 1
3347 - 8040 | 6 INCH FIRE HYDRANT LEAD | Material | Linear Feet |  | 1
3347 - 8041 | TEST STATIONS | Material | Each |  | 1
3347 - 8042 | 3/4 INCH OR 1 INCH WATER HOUSE CONNECTION COPPER | Material | Linear Feet |  | 1
3347 - 8043 | 2 INCH AIR RELIEF VALVE AND MANHOLE | Material | Each |  | 1
3347 - 8044 | BLOWOFF-TYPE A | Material | Each |  | 1
3347 - 8045 | 16 INCH VALVE AND VAULT | Material | Each |  | 1
3347 - 8046 | 24 INCH VALVE AND VAULT | Material | Each |  | 1
3347 - 8047 | 30 INCH VALVE AND VAULT | Material | Each |  | 1
3347 - 8048 | CUT AND CAP EXISTING 30 INCH WATER MAIN | Material | Each |  | 1
3347 - 8049 | 8 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material | Linear Feet |  | 1
3347 - 8050 | 16 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material | Linear Feet |  | 1
3347 - 8051 | 24 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material | Linear Feet |  | 1
3347 - 8052 | 30 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material | Linear Feet |  | 1
3347 - 8053 | PRECAST SEWER MANHOLE (48 INCH) - VERTICAL DEPTH | Material | Linear Feet |  | 1
3347 - 8054 | ABANDON SEWER MANHOLE (48 INCH) | Material | Each |  | 1
3347 - 8055 | 12 INCH DUCTILE IRON PIPE CLASS 54 SEWER LINE | Material | Linear Feet |  | 1
3347 - 8056 | 12 INCH SEWER LINE IN 36 INCH STEEL CASING | Material | Linear Feet |  | 1
3347 - 8060 | IP-BASED VIDEO DETECTION CAMERA & ANY LENGTH LEAD-IN CABLE | Material | Each |  | 1
3347 - 8061 | 10 FOOT BREAKAWAY PEDESTAL POLE | Material | Each |  | 1
3347 - 8062 | 14 FOOT BREAKAWAY PEDESTAL POLE | Material | Each |  | 1
3347 - 8068 | BREAKAWAY BASE SUPPORT SYSTEM FOR STEEL BEAMS | Material | Each |  | 1
3347 - 8069 | BREAKAWAY BASE SUPPORT SYSTEM FOR LIGHTING STRUCTURE | Material | Each |  | 1
3347 - 8070 | DISCONNECT, PULL-BACK AND REROUTE CABLES | Material | Linear Feet |  | 1
3347 - 8071 | DUCT CABLE - 2 CONDUCTOR, NO 4 AWG, 600 V | Material | Linear Feet |  | 1
3347 - 8072 | DUCT CABLE - 4 CONDUCTOR, NO 4 AWG, 600 V | Material | Linear Feet |  | 1
3347 - 8073 | CABLE - 1 CONDUCTOR, NO 4 AWG, TYPE USE, 600V | Material | Linear Feet |  | 1
3347 - 8074 | CABLE -1 CONDUCTOR, NO 10 AWG, TYPE THWN/THHN, 600V | Material | Linear Feet |  | 1
3347 - 8075 | 1 INCH DIAMETER RIGID STEEL CONDUIT, SCHEDULE 40 | Material | Linear Feet |  | 1
3347 - 8076 | 1 INCH DIAMETER FLEXIBLE STEEL CONDUIT | Material | Linear Feet |  | 1
3347 - 8077 | CONNECTOR KIT-TYPE I | Material | Each |  | 1
3347 - 8078 | CONNECTOR KIT - TYPE II | Material | Each |  | 1
3347 - 8079 | CONNECTOR KIT - TYPE III | Material | Each |  | 1
3347 - 8080 | CONNECTOR KIT - TYPE IV | Material | Each |  | 1
3347 - 8081 | GROUND ROD - 3/4 INCH DIAMETER X10 FOOT LENGTH | Material | Each |  | 1
3347 - 8082 | LIGHTING CONTROL CABINET, BASE MOUNT (120/240 VOLTS, 1 PHASE 3 WIRE SYSTEM) | Material | Each |  | 1
3347 - 8083 | LIGHTING CONTROL CABINET, POLE MOUNT (120/240 VOLTS. 1 PHASE 3 WIRE .SYSTEM) | Material | Each |  | 1
3347 - 8085 | GALVANIZED STEEL BEAMS (W6X12) | Material | Linear Feet |  | 1
3347 - 8086 | GALVANIZED STEEL BEAMS (W8X18) | Material | Linear Feet |  | 1
3347 - 8089 | RELOCATE EXISTING SIGNAL HEAD | Material | Each |  | 1
3347 - 8090 | 12 INCH LED VEHICULAR TRAFFIC SIGNAL HEAD SECTION | Material | Each |  | 1
3347 - 8091 | 16 INCH LED COUNTDOWN PEDESTRIAN SIGNAL HEAD | Material | Each |  | 1
3347 - 8092 | CUT, CLEAN, GALVANIZE AND CAP TRAFFIC SIGNAL STRUCTURE | Material | Each |  | 1
3347 - 8093 | ELECTRICAL CABLE - 2 CONDUCTOR (NO. 14AWG) | Material | Linear Feet |  | 1
3347 - 8094 | ELECTRICAL CABLE - 5 CONDUCTOR (NO. 14 AWG) | Material | Linear Feet |  | 1
3347 - 8095 | ELECTRICAL CABLE - 7 CONDUCTOR (NO. 14 AWG) | Material | Linear Feet |  | 1
3347 - 8097 | AUDIBLE/TACTILE PEDESTRIAN PUSHBUTTON STATION AND SIGNS | Material | Each |  | 1
3347 - 8098 | 2-WIRE APS CENTRAL CONTROL UNIT | Material | Each |  | 1
3347 - 8099 | 20 FOOT LIGHTING ARM ON SIGNAL STRUCTURE | Material | Each |  | 1
3347 - 8100 | STEEL SPAN WIRE - 3/8 INCH DIAMETER | Material | Linear Feet |  | 1
3347 - 8102 | INSTALL CONTROLLER AND CABINET - POLE MOUNT | Material | Each |  | 1
3347 - 8103 | REMOVE AND SALVAGE EXISTING EQUIPMENT | Material | Lump Sum |  | 1
3347 - 8104 | REMOVE AND DISPOSE OF EXISTING SIGNAL EQUIPMENT | Material | Lump Sum |  | 1
3347 - 8105 | SHEET ALUMINUM SIGNS | Material | Square Feet |  | 1
3347 - 8106 | EXTRUDED ALUMINUM SIGNS | Material | Square Feet |  | 1
3347 - 8107 | 3 INCH SCHEDULE 80 RIGID PVC CONDUIT-BORED | Material | Linear Feet |  | 1
3347 - 8108 | 1 INCH LIQUID TIGHT FLEXIBLE NONMETALLICCONDUIT FOR DETECTOR SLEEVE | Material | Linear Feet |  | 1
3347 - 8109 | MICROLOOP PROBE, 1000 FOOT LEAD IN CABLE | Material | Each |  | 1
3347 - 8110 | BAND SIGN TO SIGN SUPPORT | Material | Each |  | 1
3347 - 8111 | DISCRIMINATOR MODULE, 4 CHANNEL, NO. 764 | Material | Each |  | 1
3347 - 8112 | OPTICOM EMITTER SYSTEM, 700 SERIES | Material | Each |  | 1
3347 - 8113 | OPTICOM NO. 721 DETECTOR EYE | Material | Each |  | 1
3347 - 8114 | 14" X 32' STRAIN POLE (2 PLY) | Material | Each |  | 1
3347 - 8115 | STEEL POLE WITH A SINGLE 38 FOOT MAST ARM | Material | Each |  | 1
3347 - 8116 | STEEL POLE WITH A SINGLE 50 FOOT MASTARM | Material | Each |  | 1
3347 - 8117 | STEEL POLE WITH A SINGLE 60 FOOT MAST ARM | Material | Each |  | 1
3347 - 8118 | STEEL POLE WITH TWIN 50 FOOT AND 70 FOOT MAST ARMS | Material | Each |  | 1
3347 - 8119 | STEEL POLE WITH SINGLE 70 FOOT MASTARM | Material | Each |  | 1
3347 - 8120 | 12-PAIR COMMUNICATION CABLE (SELF-SUPPORTING OR JELLYFILLED/ UNDERGROUND) | Material | Linear Feet |  | 1
3347 - 8121 | GALVANIZED STEEL BEAMS (W18X40) | Material | Linear Feet |  | 1
3347 - 8122 | CANTILEVER SIGN STRUCTURE C-1 | Material | Each |  | 1
3347 - 8123 | CANTILEVER SIGN STRUCTURE C-2 | Material | Each |  | 1
3347 - 8124 | CANTILEVER SIGN STRUCTURE C-3 | Material | Each |  | 1
3347 - 8125 | CANTILEVER SIGN STRUCTURE C-4 | Material | Each |  | 1
3347 - 8126 | CANTILEVER SIGN STRUCTURE C-5 | Material | Each |  | 1
3347 - 8127 | CANTILEVER SIGN STRUCTURE C-6 | Material | Each |  | 1
3347 - 8128 | FURNISH AND INSTALL 4 CONDUCTOR OPTICOM CABLE | Material | Linear Feet |  | 1
3347 - 8129 | SAW CUT FOR SIGNAL (LOOP DETECTOR) | Material | Linear Feet |  | 1
3347 - 8130 | INSTALL CONTROLLER AND CABINET - BASE MOUNT | Material | Each |  | 1
3347 - 8131 | WOOD SIGN SUPPORT 6 INCH X 8 INCH | Material | Linear Feet |  | 1
3347 - 8132 | RELOCATE EXISTING GROUND MOUNTED SIGNS | Material | Square Feet |  | 1
3347 - 8133 | FURNISH AND INSTALL 8 INCH AIRA/ACUUM VALVE AND VAULT FOR 30 INCH WATER MAIN | Material | Each |  | 1
3347 - 8134 | CUT AND CAP EXISTING 16 INCH WATER MAIN | Material | Each |  | 1
3347 - 8135 | ABANDON VALVE VAULT | Material | Each |  | 1
SUB-Earthquake Drain | Sub - Earthquake Drain Sub Crew | Labor |  |  | 1
SUB-Wick Drain | Sub - Wick Drain Sub Crew | Labor |  |  | 1
CO 04 | Change order 04 - CGP Fiber at Kingswood | Material | Lump Sum |  | 8
CO 09 | Change Order 09 - USACE E/ITS/Signage | Material | Lump Sum |  | 8
CO 10 | Change Order 10 - COM Powder coated poles | Material | Lump Sum |  | 8
Cost Sept Redist | Sept 17 Redistribution | Material | Lump Sum |  | 8
D-2.4-14 | PENTAGON – CHANGE ORDERS | Material | Lump Sum |  | 8
2310013.PCO5 | OTB Steel Drainage Element | Material | Lump Sum |  | 1
NCR 93 | NCR 93 Redistribution | Material | Lump Sum |  | 8
NCR 97 | NCR 97 Redistribution | Material | Lump Sum |  | 8
NCR 98 | NCR 98 Redistribution | Material | Lump Sum |  | 8
NCR 99 | NCR 99 Redistribution | Material | Lump Sum |  | 8
NCR 92 | NCR 92 Redistribution | Material | Lump Sum |  | 8
BUILDING | Building Trades Crew | Labor |  |  | 1
ST-Frame | Concrete Bld Frame Crew | Labor |  |  | 1
ST-BLD-Pour | Concrete Bld Pour Crew | Labor |  |  | 1
ST-BLD-Mech | Building Mechanical Systems Crew | Labor |  |  | 1
SUB-BLD | Sub - Building Trades Crews | Labor |  |  | 1
SUB-BLD-MECH | Sub - Mechanical Systems Crews | Labor |  |  | 1
SUB-BLD-HVAC | Sub - HVAC Crews | Labor |  |  | 1
SUB-BLD-ELEC | Sub - Building Electrical Crews | Labor |  |  | 1
SUB-BLD-PAINT | Sub - Building Painting / Coatings Crew | Labor |  |  | 1
C00100566DB63_C31 | I-66/15 Change Order #31 | Material | Lump Sum |  | 1
3398 | 3398 - Oceana | Nonlabor |  |  | 1
3398-01 | Monderization of Airfield Lighting - Phase 3 | Material | Lump Sum |  | 8
3398-02 | PERFOMANCE AND PAYMENT BONDS | Material | Lump Sum |  | 8
3398-19 | ASBUILT DRAWINGS | Material | Lump Sum |  | 8
3398-20 | PUNCHLIST CLOSEOUT | Material | Lump Sum |  | 8
3398-29 | SUBPHASE 3A | Material |  |  | 8
3398-30 | Guidance / RDM Signs | Material |  |  | 8
3398-31 | Sign Demolition - 3A | Material | Each |  | 8
3398-32 | Signs Stored - 3A | Material | Each |  | 8
3398-33 | Concrete Pads, and Airfield Cans - 3A | Material | Each |  | 8
3398-34 | Sign Installation - 3A | Material | Each |  | 8
3398-35 | Sign Testing - 3A | Material | Each |  | 8
3398-36 | Edge Circuit | Material |  |  | 8
3398-37 | Demolition - 3A | Material | Each |  | 8
3398-38 | Light Cans**Stored - 3A | Material | Each |  | 8
3398-39 | Snow Plow**Stored - 3A | Material | Each |  | 8
3398-40 | Elevated Edge Light ** Stored - 3A | Material | Each |  | 8
3398-41 | Semi Flush Edge Light** Stored - 3A | Material | Each |  | 8
3398-42 | 5L-23R RW Edge Lighting Duct System | Material | Linear Feet |  | 8
3398-43 | 5L-23R RW Airfield Cable - 3A | Material | Linear Feet |  | 8
3398-44 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-45 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-46 | Lighting Fixture | Material | Each |  | 8
3398-47 | Testing - 3A | Material | Each |  | 8
3398-48 | Threshold Bar 5L | Material |  |  | 8
3398-49 | Light Cans**Stored - 3A | Material | Each |  | 8
3398-50 | Snow Plow**Stored - 3A | Material | Each |  | 8
3398-51 | Elevated Threshold Lights*** Stored - 3A | Material | Each |  | 8
3398-52 | Semi-Flush Threshold Lights*** Stored - 3A | Material | Each |  | 8
3398-53 | Forming & Pouring Threshold Left/Right - 3A | Material | Each |  | 8
3398-54 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-55 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-56 | Lighting Fixture | Material | Each |  | 8
3398-57 | Testing | Material | Each |  | 8
3398-58 | Wind Cone | Material |  |  | 8
3398-59 | Wind Cone Demolition | Material | Each |  | 8
3398-60 | Wind Cone Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-61 | Wind Cone Installation | Material | Each |  | 8
3398-62 | Fiber | Material |  |  | 8
3398-63 | Install Fiber Tube | Material | Linear Feet |  | 8
3398-64 | Install Blown Fiber Cabling | Material | Linear Feet |  | 8
3398-65 | Fiber Termination & Testing | Material | Each |  | 8
3398-66 | RWY 5L-23R IFLOLS XFMRs | Material |  |  | 8
3398-67 | Demolition | Material | Each |  | 8
3398-68 | XFMRS **** Stored | Material | Each |  | 8
3398-69 | XFMR Pads | Material | Each |  | 8
3398-70 | Install XFMRs | Material | Each |  | 8
3398-71 | Panels & Rack | Material | Each |  | 8
3398-72 | Start-up & Testing | Material | Each |  | 8
3398-73 | Wave Power System RW 5L | Material |  |  | 8
3398-74 | Demo Wave off Conduit | Material | Linear Feet |  | 8
3398-75 | Demo Wave off Hand-holes | Material | Each |  | 8
3398-76 | Wave Off Demolition | Material | Each |  | 8
3398-77 | Wave Off System ***Stored | Material | Each |  | 8
3398-78 | Install Wave off Equipment | Material | Each |  | 8
3398-79 | Install Wave off Light Fixtures | Material | Each |  | 8
3398-80 | Wave Off RW 5- Install Hand-holes | Material | Each |  | 8
3398-81 | Wave Off RW 5- Duct System | Material | Linear Feet |  | 8
3398-82 | Wave Off RW 5- Wiring | Material | Linear Feet |  | 8
3398-83 | Wave Off RW 5- Junction Cans | Material | Each |  | 8
3398-84 | Testing | Material | Each |  | 8
3398-85 | Medium Voltage | Material |  |  | 8
3398-86 | MV Cable E-1120 to Wave Off RW 5L | Material | Linear Feet |  | 8
3398-87 | Terminations & Testing | Material | Each |  | 8
3398-88 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-89 | Area 3A- Install Manholes | Material | Each |  | 8
3398-90 | Area 3A- Install Duct System | Material | Linear Feet |  | 8
3398-91 | Area 3A-Home Run wiring | Material | Linear Feet |  | 8
3398-92 | Excavation - 3A | Material | Cubic Yard |  | 8
3398-93 | Install RCC - 3A | Material | Cubic Yard |  | 8
3398-94 | Pave Asphalt - 3A | Material |  |  | 8
3398-95 | Pave Concrete - 3A | Material | Cubic Yard |  | 8
3398-96 | Grade Infield - 3A | Material | Square Yard |  | 8
3398-97 | SUBPHASE 3B | Material |  |  | 8
3398-98 | Guidance/RDM Signs | Material |  |  | 8
3398-99 | Sign Demolition - 3B | Material | Each |  | 8
3398-100 | Signs Stored - 3B | Material | Each |  | 8
3398-101 | Concrete Pads, and Airfield Cans - 3B | Material | Each |  | 8
3398-102 | Sign Installation - 3B | Material | Each |  | 8
3398-103 | Sign Testing - 3B | Material | Each |  | 8
3398-104 | Edge Circuit | Material |  |  | 8
3398-105 | Demolition - 3B | Material | Each |  | 8
3398-106 | Light Cans**Stored - 3B | Material | Each |  | 8
3398-107 | Snow Plow**Stored - 3B | Material | Each |  | 8
3398-108 | Semi Flush Edge** Stored - 3B | Material | Each |  | 8
3398-109 | 5L-23R RW Edge Lighting Duct System | Material | Linear Feet |  | 8
3398-110 | 5L-23R RW Airfield Cable - 3B | Material | Linear Feet |  | 8
3398-111 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-112 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-113 | Lighting Fixture | Material | Each |  | 8
3398-114 | Testing - 3B | Material | Each |  | 8
3398-115 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-116 | Area 3B- Install Manholes | Material | Each |  | 8
3398-117 | Area 3B-Home Run wiring | Material | Linear Feet |  | 8
3398-118 | SUBPHASE 3C | Material |  |  | 8
3398-119 | Guidance/RDM Signs | Material |  |  | 8
3398-120 | Sign Demolition - 3C | Material | Each |  | 8
3398-121 | Signs Stored - 3C | Material | Each |  | 8
3398-122 | Concrete Pads, and Airfield Cans - 3C | Material | Each |  | 8
3398-123 | Sign Installation - 3C | Material | Each |  | 8
3398-124 | Sign Testing - 3C | Material | Each |  | 8
3398-125 | Edge Circuit | Material |  |  | 8
3398-126 | Demolition - 3C | Material | Each |  | 8
3398-127 | Light Cans**Stored - 3C | Material | Each |  | 8
3398-128 | Snow Plow**Stored - 3C | Material | Each |  | 8
3398-129 | Elevated Edge ** Stored - 3C | Material | Each |  | 8
3398-130 | Semi Flush Edge** Stored - 3C | Material | Each |  | 8
3398-131 | 5L-23R RW Edge Lighting Duct System - 3C | Material | Linear Feet |  | 8
3398-132 | 5L-23R RW Airfield Cable - 3C | Material | Linear Feet |  | 8
3398-133 | Airfield Cans> Set Can/Bottom Can - 3C | Material | Each |  | 8
3398-134 | Airfield Cans> Core Drill/Extension/Top Can - 3C | Material | Each |  | 8
3398-135 | Lighting Fixture - 3C | Material | Each |  | 8
3398-136 | Testing - 3C | Material | Each |  | 8
3398-137 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-138 | Demolition | Material | Each |  | 8
3398-139 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-140 | Light Cans**Stored | Material | Each |  | 8
3398-141 | Snow Plow**Stored | Material | Each |  | 8
3398-142 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-143 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-144 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-145 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-146 | Lighting Fixture | Material | Each |  | 8
3398-147 | Testing | Material | Each |  | 8
3398-148 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-149 | Area 3C- Install Manholes | Material | Each |  | 8
3398-150 | Area 3C- Install Duct System | Material | Linear Feet |  | 8
3398-151 | Area 3C-Home Run wiring | Material | Linear Feet |  | 8
3398-152 | Excavate CL Pavement - 3C | Material | Cubic Yard |  | 8
3398-153 | Place CL Asphalt - 3C | Material |  |  | 8
3398-154 | Excavate Edge Pavement - 3C | Material | Cubic Yard |  | 8
3398-155 | Install RCC Edge - 3C | Material | Cubic Yard |  | 8
3398-156 | Place Asphalt Edge - 3C | Material |  |  | 8
3398-157 | Grade Infield - 3C | Material | Square Yard |  | 8
3398-158 | SUBPHASE 3D | Material |  |  | 8
3398-159 | Guidance/RDM Signs | Material |  |  | 8
3398-160 | Sign Demolition - 3D | Material | Each |  | 8
3398-161 | Signs Stored - 3D | Material | Each |  | 8
3398-162 | Concrete Pads, and Airfield Cans - 3D | Material | Each |  | 8
3398-163 | Sign Installation - 3D | Material | Each |  | 8
3398-164 | Sign Testing - 3D | Material | Each |  | 8
3398-165 | Edge Circuit | Material |  |  | 8
3398-166 | Demolition - 3D | Material | Each |  | 8
3398-167 | Light Cans**Stored - 3D | Material | Each |  | 8
3398-168 | Elevated Edge ** Stored - 3D | Material | Each |  | 8
3398-169 | 5L-23R RW Edge Lighting Duct System | Material | Linear Feet |  | 8
3398-170 | 5L-23R RW Airfield Cable - 3D | Material | Linear Feet |  | 8
3398-171 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-172 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-173 | Lighting Fixture | Material | Each |  | 8
3398-174 | Testing - 3D | Material | Each |  | 8
3398-175 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-176 | Area 3D- Install Manholes | Material | Each |  | 8
3398-177 | Area 3D- Install Duct System | Material | Linear Feet |  | 8
3398-178 | Area 3D-Home Run wiring | Material | Linear Feet |  | 8
3398-179 | SUBPHASE 3E | Material |  |  | 8
3398-180 | Guidance/RDM Signs | Material |  |  | 8
3398-181 | Sign Demolition - 3E | Material | Each |  | 8
3398-182 | Signs Stored - 3E | Material | Each |  | 8
3398-183 | Concrete Pads, and Airfield Cans - 3E | Material | Each |  | 8
3398-184 | Sign Installation - 3E | Material | Each |  | 8
3398-185 | Sign Testing - 3E | Material | Each |  | 8
3398-186 | Edge Circuit | Material |  |  | 8
3398-187 | Demolition - 3E | Material | Each |  | 8
3398-188 | Light Cans**Stored - 3E | Material | Each |  | 8
3398-189 | Snow Plow**Stored - 3E | Material | Each |  | 8
3398-190 | Elevated Edge ** Stored - 3E | Material | Each |  | 8
3398-191 | Semi Flush Edge** Stored - 3E | Material | Each |  | 8
3398-192 | 5L-23R RW Edge Lighting Duct System | Material | Linear Feet |  | 8
3398-193 | 5L-23R RW Airfield Cable - 3E | Material | Linear Feet |  | 8
3398-194 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-195 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-196 | Lighting Fixture | Material | Each |  | 8
3398-197 | Testing - 3E | Material | Each |  | 8
3398-198 | Threshold Bar 23R | Material |  |  | 8
3398-199 | Light Cans**Stored - 3E | Material | Each |  | 8
3398-200 | Snow Plow**Stored - 3E | Material | Each |  | 8
3398-201 | Elevated Threshold Lights*** Stored - 3E | Material | Each |  | 8
3398-202 | Semi-Flush Threshold Lights*** Stored - 3E | Material | Each |  | 8
3398-203 | Forming & Pouring Threshold Left/Right - 3E | Material | Each |  | 8
3398-204 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-205 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-206 | Lighting Fixture | Material | Each |  | 8
3398-207 | Testing | Material | Each |  | 8
3398-208 | Wind Cone | Material |  |  | 8
3398-209 | Wind Cone Demolition | Material | Each |  | 8
3398-210 | Wind Cone Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-211 | Wind Cone Installation | Material | Each |  | 8
3398-212 | Fiber | Material |  |  | 8
3398-213 | Install Fiber Tube | Material | Linear Feet |  | 8
3398-214 | Install Blown Fiber Cabling | Material | Linear Feet |  | 8
3398-215 | Fiber Termination & Testing | Material | Each |  | 8
3398-216 | RWY 5L-23R IFLOLS XFMRs | Material |  |  | 8
3398-217 | Demolition | Material | Each |  | 8
3398-218 | XFMRS **** Stored | Material | Each |  | 8
3398-219 | XFMR Pads | Material | Each |  | 8
3398-220 | Install XFMRs | Material | Each |  | 8
3398-221 | Panels & Rack | Material | Each |  | 8
3398-222 | Start-up & Testing | Material | Each |  | 8
3398-223 | Wave Power System RW 5L | Material |  |  | 8
3398-224 | Demo Wave off Conduit | Material | Linear Feet |  | 8
3398-225 | Demo Wave off Hand-holes | Material | Each |  | 8
3398-226 | Wave Off Demolition | Material | Each |  | 8
3398-227 | Wave Off System ***Stored | Material | Each |  | 8
3398-228 | Install Wave off Equipment | Material | Each |  | 8
3398-229 | Install Wave off Light Fixtures | Material | Each |  | 8
3398-230 | Wave Off RW 23- Install Hand-holes | Material | Each |  | 8
3398-231 | Wave Off RW 23- Duct System | Material | Linear Feet |  | 8
3398-232 | Wave Off RW 23- Wiring | Material | Linear Feet |  | 8
3398-233 | Wave Off RW 23- Junction Cans | Material | Each |  | 8
3398-234 | Testing | Material | Each |  | 8
3398-235 | Medium Voltage | Material |  |  | 8
3398-236 | MV Cable Wave Off 23L to Wave Off RW 23R | Material | Linear Feet |  | 8
3398-237 | Terminations & Testing | Material | Each |  | 8
3398-238 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-239 | Area 3E- Install Manholes | Material | Each |  | 8
3398-240 | Area 3E - Home Run wiring | Material | Linear Feet |  | 8
3398-241 | Excavation - 3E | Material | Cubic Yard |  | 8
3398-242 | Install RCC - 3E | Material | Cubic Yard |  | 8
3398-243 | Pave Asphalt - 3E | Material |  |  | 8
3398-244 | Place Concrete - 3E | Material | Cubic Yard |  | 8
3398-245 | Grade Infield - 3E | Material | Square Yard |  | 8
3398-246 | SUBPHASE 3F | Material |  |  | 8
3398-247 | Regulator Switchgear FAC# E1200 Demolition | Material | Each |  | 8
3398-248 | Generator FAC# 1201 Demolition | Material | Each |  | 8
3398-249 | Demolition of Existing E-1200 - 3F | Material | Lump Sum |  | 8
3398-250 | Install Fence - 3F | Material | Linear Feet |  | 8
3398-251 | SUBPHASE 3G | Material |  |  | 8
3398-252 | Home Run wiring | Material | Linear Feet |  | 8
3398-253 | Medium Voltage | Material |  |  | 8
3398-254 | MV Cable Wave Off E-1120 to Wave Off 5L | Material | Linear Feet |  | 8
3398-255 | Terminations & Testing | Material | Lump Sum |  | 8
3398-256 | Fiber | Material |  |  | 8
3398-257 | Install Fiber Tube | Material | Linear Feet |  | 8
3398-258 | Install Blown Fiber Cabling | Material | Linear Feet |  | 8
3398-259 | Fiber Termination & Testing | Material | Lump Sum |  | 8
3398-260 | SUBPHASE 3H | Material |  |  | 8
3398-261 | Install Duct System | Material | Linear Feet |  | 8
3398-262 | Home Run wiring | Material | Linear Feet |  | 8
3398-263 | Medium Voltage | Material |  |  | 8
3398-264 | MV Cable Wave Off E-1120 to Wave Off 5L | Material | Linear Feet |  | 8
3398-265 | Terminations & Testing | Material | Lump Sum |  | 8
3398-266 | Fiber | Material |  |  | 8
3398-267 | Install Fiber Tube | Material | Linear Feet |  | 8
3398-268 | Install Blown Fiber Cabling | Material | Linear Feet |  | 8
3398-269 | Fiber Termination & Testing | Material | Lump Sum |  | 8
3398-270 | Testing on Site for Contaminated Soils | Material | Each |  | 8
3398-271 | Remove, Dispose, Replace Contaminated Soils | Material | Cubic Yard |  | 8
3398-272 | Remove, Dispose, Replace Unsuitable Soils | Material | Cubic Yard |  | 8
3398-273 | Grading Outside of 20' Shoulder | Material | Square Yard |  | 8
3398-275 | Monderization of Airfield Lighting - Phase 4 | Material | Lump Sum |  | 8
3398-276 | PERFOMANCE AND PAYMENT BONDS | Material | Lump Sum |  | 8
3398-290 | ASBUILT DRAWINGS | Material | Lump Sum |  | 8
3398-291 | PUNCHLIST CLOSEOUT | Material | Lump Sum |  | 8
3398-300 | SUBPHASE 4A | Material |  |  | 8
3398-301 | Threshold Bar 14R | Material |  |  | 8
3398-302 | Light Cans**Stored | Material | Each |  | 8
3398-303 | Snow Plow**Stored | Material | Each |  | 8
3398-304 | Elevated Threshold Lights*** Stored | Material | Each |  | 8
3398-305 | Semi-Flush Threshold Lights*** Stored | Material | Each |  | 8
3398-306 | Forming & Pouring Threshold Left/Right | Material | Each |  | 8
3398-307 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-308 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-309 | Lighting Fixture | Material | Each |  | 8
3398-310 | Testing | Material | Each |  | 8
3398-311 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-312 | Demolition | Material | Each |  | 8
3398-313 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-314 | Light Cans**Stored | Material | Each |  | 8
3398-315 | Snow Plow Rings***Stored | Material | Each |  | 8
3398-316 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-317 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-318 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-319 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-320 | Lighting Fixture | Material | Each |  | 8
3398-321 | Testing | Material | Each |  | 8
3398-322 | Guidance/RDM Signs | Material |  |  | 8
3398-323 | Sign Demolition | Material | Each |  | 8
3398-324 | Signs Stored | Material | Each |  | 8
3398-325 | Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-326 | Sign Installation | Material | Each |  | 8
3398-327 | Sign Testing | Material | Each |  | 8
3398-328 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-329 | Home Run wiring | Material | Linear Feet |  | 8
3398-330 | Excavate CL Pavement - 4A | Material | Cubic Yard |  | 8
3398-331 | Place CL Concrete Pavement - 4A | Material | Cubic Yard |  | 8
3398-332 | SUBPHASE 4B | Material |  |  | 8
3398-333 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-334 | Demolition | Material | Each |  | 8
3398-335 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-336 | Light Cans**Stored | Material | Each |  | 8
3398-337 | Snow Plow Rings***Stored | Material | Each |  | 8
3398-338 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-339 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-340 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-341 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-342 | Lighting Fixture | Material | Each |  | 8
3398-343 | Testing | Material | Each |  | 8
3398-344 | Guidance/RDM Signs | Material |  |  | 8
3398-345 | Sign Demolition | Material | Each |  | 8
3398-346 | Signs Stored | Material | Each |  | 8
3398-347 | Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-348 | Sign Installation | Material | Each |  | 8
3398-349 | Sign Testing | Material | Each |  | 8
3398-350 | Edge Circuit | Material |  |  | 8
3398-351 | Demolition | Material | Each |  | 8
3398-352 | Light Cans**Stored | Material | Each |  | 8
3398-353 | Snow Plow**Stored | Material | Each |  | 8
3398-354 | Elevated Edge ** Stored | Material | Each |  | 8
3398-355 | Semi Flush Edge** Stored | Material | Each |  | 8
3398-356 | 14R-32L Edge Circuit Duct System | Material | Linear Feet |  | 8
3398-357 | 14R-32L RW Airfield Cable | Material | Linear Feet |  | 8
3398-358 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-359 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-360 | Lighting Fixture | Material | Each |  | 8
3398-361 | Testing | Material | Each |  | 8
3398-362 | Wind Cone | Material |  |  | 8
3398-363 | Wind Cone Demolition | Material | Each |  | 8
3398-364 | Wind Cone Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-365 | Wind Cone Installation | Material | Each |  | 8
3398-366 | Fiber | Material |  |  | 8
3398-367 | Install Fiber Tube | Material | Linear Feet |  | 8
3398-368 | Install Blown Fiber Cabling | Material | Linear Feet |  | 8
3398-369 | Fiber Termination & Testing | Material | Lump Sum |  | 8
3398-370 | RWY 14R-32L IFLOLS XFMRs | Material |  |  | 8
3398-371 | Demolition | Material | Each |  | 8
3398-372 | XFMRS **** Stored | Material | Each |  | 8
3398-373 | XFMR Pads | Material | Each |  | 8
3398-374 | Install XFMRs | Material | Each |  | 8
3398-375 | Panels & Rack | Material | Each |  | 8
3398-376 | Start-up & Testing | Material | Each |  | 8
3398-377 | Wave Power System RW 14R | Material |  |  | 8
3398-378 | Demo Wave off Conduit | Material | Linear Feet |  | 8
3398-379 | Demo Wave off Hand-holes | Material | Each |  | 8
3398-380 | Wave Off Demolition | Material | Each |  | 8
3398-381 | Wave Off System ***Stored | Material | Each |  | 8
3398-382 | Install Wave off Equipment | Material | Each |  | 8
3398-383 | Install Wave off Light Fixtures | Material | Each |  | 8
3398-384 | Wave Off RW 14- Install Hand-holes | Material | Each |  | 8
3398-385 | Wave Off RW 14- Duct System | Material | Linear Feet |  | 8
3398-386 | Wave Off RW 14- Wiring | Material | Linear Feet |  | 8
3398-387 | Wave Off RW 14- Junction Cans | Material | Each |  | 8
3398-388 | Testing | Material | Each |  | 8
3398-389 | Medium Voltage | Material |  |  | 8
3398-390 | MV Cable Wave Off 23L to Wave Off RW 23R | Material | Linear Feet |  | 8
3398-391 | Terminations & Testing | Material | Each |  | 8
3398-392 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-393 | Install Manholes | Material | Each |  | 8
3398-394 | Install Duct System | Material | Linear Feet |  | 8
3398-395 | Home Run Wiring | Material | Linear Feet |  | 8
3398-396 | Excavate CL Pavement - 4B | Material | Cubic Yard |  | 8
3398-397 | Place CL Concrete Pavement - 4B | Material | Cubic Yard |  | 8
3398-398 | Place CL Asphalt - 4B | Material |  |  | 8
3398-399 | Excavate Edge Pavement - 4B | Material | Cubic Yard |  | 8
3398-400 | Install RCC Edge - 4B | Material | Cubic Yard |  | 8
3398-401 | Place Concrete Edge - 4B | Material | Cubic Yard |  | 8
3398-402 | Place Asphalt Edge - 4B | Material |  |  | 8
3398-403 | Grade Infield - 4B | Material | Square Yard |  | 8
3398-404 | SUBPHASE 4C | Material |  |  | 8
3398-405 | Home Run wiring | Material | Linear Feet |  | 8
3398-406 | SUBPHASE 4D | Material |  |  | 8
3398-407 | Guidance/RDM Signs | Material |  |  | 8
3398-408 | Sign Demolition | Material | Each |  | 8
3398-409 | Signs Stored | Material | Each |  | 8
3398-410 | Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-411 | Sign Installation | Material | Each |  | 8
3398-412 | Sign Testing | Material | Each |  | 8
3398-413 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-414 | Demolition | Material | Each |  | 8
3398-415 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-416 | Light Cans**Stored | Material | Each |  | 8
3398-417 | Snow Plow Rings***Stored | Material | Each |  | 8
3398-418 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-419 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-420 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-421 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-422 | Lighting Fixture | Material | Each |  | 8
3398-423 | Testing | Material | Each |  | 8
3398-424 | Edge Circuit | Material |  |  | 8
3398-425 | Demolition | Material | Each |  | 8
3398-426 | Light Cans**Stored | Material | Each |  | 8
3398-427 | Snow Plow**Stored | Material | Each |  | 8
3398-428 | Elevated Edge ** Stored | Material | Each |  | 8
3398-429 | Semi Flush Edge** Stored | Material | Each |  | 8
3398-430 | 14R-32L RW Edge Circuit Duct System | Material | Linear Feet |  | 8
3398-431 | 14R-32L RW Airfield Cable | Material | Linear Feet |  | 8
3398-432 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-433 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-434 | Lighting Fixture | Material | Each |  | 8
3398-435 | Testing | Material | Each |  | 8
3398-436 | Home Run Wiring | Material |  |  | 8
3398-437 | Excavate CL Pavement - 4D | Material | Cubic Yard |  | 8
3398-438 | Place CL Asphalt - 4D | Material |  |  | 8
3398-439 | SUBPHASE 4E | Material |  |  | 8
3398-440 | Guidance/RDM Signs | Material |  |  | 8
3398-441 | Sign Demolition | Material | Each |  | 8
3398-442 | Signs Stored | Material | Each |  | 8
3398-443 | Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-444 | Sign Installation | Material | Each |  | 8
3398-445 | Sign Testing | Material | Each |  | 8
3398-446 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-447 | Demolition | Material | Each |  | 8
3398-448 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-449 | Light Cans**Stored | Material | Each |  | 8
3398-450 | Snow Plow Rings***Stored | Material | Each |  | 8
3398-451 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-452 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-453 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-454 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-455 | Lighting Fixture | Material | Each |  | 8
3398-456 | Testing | Material | Each |  | 8
3398-457 | Edge Circuit | Material |  |  | 8
3398-458 | Demolition | Material | Each |  | 8
3398-459 | Light Cans**Stored | Material | Each |  | 8
3398-460 | Snow Plow**Stored | Material | Each |  | 8
3398-461 | Elevated Edge ** Stored | Material | Each |  | 8
3398-462 | Semi Flush Edge** Stored | Material | Each |  | 8
3398-463 | 14R-32L RW Edge Circuit Duct System | Material | Linear Feet |  | 8
3398-464 | 14R-32L RW Airfield Cable | Material | Linear Feet |  | 8
3398-465 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-466 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-467 | Lighting Fixture | Material | Each |  | 8
3398-468 | Testing | Material | Each |  | 8
3398-469 | Home Run Wiring | Material | Linear Feet |  | 8
3398-470 | Excavate CL Pavement - 4E | Material | Cubic Yard |  | 8
3398-471 | Place CL Asphalt - 4E | Material |  |  | 8
3398-472 | SUBPHASE 4F | Material |  |  | 8
3398-473 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-474 | Demolition | Material | Each |  | 8
3398-475 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-476 | Light Cans**Stored | Material | Each |  | 8
3398-477 | Snow Plow Rings***Stored | Material | Each |  | 8
3398-478 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-479 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-480 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-481 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-482 | Lighting Fixture | Material | Each |  | 8
3398-483 | Testing | Material | Each |  | 8
3398-484 | Guidance/RDM Signs | Material |  |  | 8
3398-485 | Sign Demolition | Material | Each |  | 8
3398-486 | Signs Stored | Material | Each |  | 8
3398-487 | Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-488 | Sign Installation | Material | Each |  | 8
3398-489 | Sign Testing | Material | Each |  | 8
3398-490 | Edge Circuit | Material |  |  | 8
3398-491 | Demolition | Material | Each |  | 8
3398-492 | Light Cans**Stored | Material | Each |  | 8
3398-493 | Snow Plow**Stored | Material | Each |  | 8
3398-494 | Elevated Edge ** Stored | Material | Each |  | 8
3398-495 | Semi Flush Edge** Stored | Material | Each |  | 8
3398-496 | 14R-32L RW Edge Circuit Duct System | Material | Linear Feet |  | 8
3398-497 | 14R-32L RW Airfield Cable | Material | Linear Feet |  | 8
3398-498 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-499 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-500 | Lighting Fixture | Material | Each |  | 8
3398-501 | Testing | Material | Each |  | 8
3398-502 | Wind Cone | Material |  |  | 8
3398-503 | Wind Cone Demolition | Material | Each |  | 8
3398-504 | Wind Cone Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-505 | Wind Cone Installation | Material | Each |  | 8
3398-506 | Fiber | Material |  |  | 8
3398-507 | Install Fiber Tube | Material | Linear Feet |  | 8
3398-508 | Install Blown Fiber Cabling | Material | Linear Feet |  | 8
3398-509 | Fiber Termination & Testing | Material | Each |  | 8
3398-510 | RWY 14R-32L IFLOLS XFMRs | Material |  |  | 8
3398-511 | Demolition | Material | Each |  | 8
3398-512 | XFMRS **** Stored | Material | Each |  | 8
3398-513 | XFMR Pads | Material | Each |  | 8
3398-514 | Install XFMRs | Material | Each |  | 8
3398-515 | Panels & Rack | Material | Each |  | 8
3398-516 | Start-up & Testing | Material | Each |  | 8
3398-517 | Wave Power System RW 14R | Material |  |  | 8
3398-518 | Demo Wave off Conduit | Material | Linear Feet |  | 8
3398-519 | Demo Wave off Hand-holes | Material | Each |  | 8
3398-520 | Wave Off Demolition | Material | Each |  | 8
3398-521 | Wave Off System ***Stored | Material | Each |  | 8
3398-522 | Install Wave off Equipment | Material | Each |  | 8
3398-523 | Install Wave off Light Fixtures | Material | Each |  | 8
3398-524 | Wave Off RW 14- Install Hand-holes | Material | Each |  | 8
3398-525 | Wave Off RW 14- Duct System | Material | Linear Feet |  | 8
3398-526 | Wave Off RW 14- Wiring | Material | Linear Feet |  | 8
3398-527 | Wave Off RW 14- Junction Cans | Material | Each |  | 8
3398-528 | Testing | Material | Each |  | 8
3398-529 | Medium Voltage | Material |  |  | 8
3398-530 | MV Cable Wave Off 32L to Wave Off RW 32R | Material | Linear Feet |  | 8
3398-531 | Terminations & Testing | Material | Each |  | 8
3398-532 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-533 | Install Manholes | Material | Each |  | 8
3398-534 | Install Duct System | Material | Linear Feet |  | 8
3398-535 | Home Run wiring | Material | Linear Feet |  | 8
3398-536 | Excavate CL Pavement - 4F | Material | Cubic Yard |  | 8
3398-537 | Place CL Concrete Pavement - 4F | Material | Cubic Yard |  | 8
3398-538 | Place CL Asphalt - 4F | Material |  |  | 8
3398-539 | Excavate Edge Pavement - 4F | Material | Cubic Yard |  | 8
3398-540 | Install RCC Edge - 4F | Material | Cubic Yard |  | 8
3398-541 | Place Concrete Edge - 4F | Material | Cubic Yard |  | 8
3398-542 | Place Asphalt Edge - 4F | Material |  |  | 8
3398-543 | Grade Infield - 4F | Material | Square Yard |  | 8
3398-544 | SUBPHASE 4G | Material |  |  | 8
3398-545 | Threshold Bar 14R | Material |  |  | 8
3398-546 | Light Cans**Stored | Material | Each |  | 8
3398-547 | Snow Plow**Stored | Material | Each |  | 8
3398-548 | Elevated Threshold Lights*** Stored | Material | Each |  | 8
3398-549 | Semi-Flush Threshold Lights*** Stored | Material | Each |  | 8
3398-550 | Forming & Pouring Threshold Left/Right | Material | Each |  | 8
3398-551 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-552 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-553 | Lighting Fixture | Material | Each |  | 8
3398-554 | Testing | Material | Each |  | 8
3398-555 | RW Center Line Lighting RW 14R-32L | Material |  |  | 8
3398-556 | Demolition | Material | Each |  | 8
3398-557 | RW Center Line Lights*** Stored | Material | Each |  | 8
3398-558 | Light Cans**Stored | Material | Each |  | 8
3398-559 | Snow Plow Rings***Stored | Material | Each |  | 8
3398-560 | 14R-32L Centerline Lighting Duct System | Material | Linear Feet |  | 8
3398-561 | 14R-32L Centerline Airfield Cable | Material | Linear Feet |  | 8
3398-562 | Airfield Cans> Set Can/Bottom Can | Material | Each |  | 8
3398-563 | Airfield Cans> Core Drill/Extension/Top Can | Material | Each |  | 8
3398-564 | Lighting Fixture | Material | Each |  | 8
3398-565 | Testing | Material | Each |  | 8
3398-566 | Guidance/RDM Signs | Material |  |  | 8
3398-567 | Sign Demolition | Material | Each |  | 8
3398-568 | Signs Stored | Material | Each |  | 8
3398-569 | Concrete Pads, and Airfield Cans | Material | Each |  | 8
3398-570 | Sign Installation | Material | Each |  | 8
3398-571 | Sign Testing | Material | Each |  | 8
3398-572 | Home Run Ductbank/Wiring/Manholes | Material |  |  | 8
3398-573 | Home Run wiring | Material | Linear Feet |  | 8
3398-574 | Excavate CL Pavement - 4G | Material | Cubic Yard |  | 8
3398-575 | Place CL Concrete Pavement - 4G | Material | Cubic Yard |  | 8
3398-576 | SUBPHASE 4H | Material |  |  | 8
3398-577 | Approach Power System RW 14R-32L | Material |  |  | 8
3398-578 | Demo Approach Conduit | Material | Linear Feet |  | 8
3398-579 | Approach Install Hand-holes | Material | Each |  | 8
3398-580 | Approach Duct System | Material | Linear Feet |  | 8
3398-581 | Approach Wiring | Material | Linear Feet |  | 8
3398-582 | Approach Airfield Cable | Material | Linear Feet |  | 8
3398-583 | SUBPHASE 4I | Material |  |  | 8
3398-584 | Home Run wiring | Material | Linear Feet |  | 8
3398-585 | SUBPHASE 4J | Material |  |  | 8
3398-586 | Regulator Switchgear FAC# E1200 Demolition | Material | Each |  | 8
3398-587 | Generator FAC# 1201 Demolition | Material | Each |  | 8
3398-588 | Demolition of Existing E-101 / E-108 - 4J | Material | Lump Sum |  | 8
3398-589 | Clear and Grub - 4J | Material | Lump Sum |  | 8
3398-590 | Testing on Site for Contaminated Soils | Material | Each |  | 8
3398-591 | Remove, Dispose, Replace Contaminated Soils | Material | Cubic Yard |  | 8
3398-592 | Remove, Dispose, Replace Unsuitable Soils | Material | Cubic Yard |  | 8
3398-593 | Grading Outside of 20' Shoulder | Material | Square Yard |  | 8
NCR 103 | NCR 103 Redistribution | Material | Lump Sum |  | 8
NCR 104 | NCR 104 Redistribution | Material | Lump Sum |  | 8
NCR 105 | NCR 105 Redistribution | Material | Lump Sum |  | 8
NCR 106 | NCR 106 Redistribution | Material | Lump Sum |  | 8
NCR 107 | NCR 107 Redistribution | Material | Lump Sum |  | 8
3402 | 3402 - Blue River Basin Levee | Nonlabor |  |  | 0
SUB-BLD-FIRE | Sub - Building Fire Systems Crew | Labor |  |  | 1
SUB-BLD-BLOCK | Sub - Block & Brick Crews | Labor |  |  | 1
SUB-BLD-DRYWALL | Sub - Building Drywall Crews | Labor |  |  | 1
SUB-BLD-ROOF | Sub - Building Roof Crews | Labor |  |  | 1
SUB-BLD-GLASS | Sub - Building Glass / Window Crews | Labor |  |  | 1
SUB-BLD-STEEL | Sub - Building Structural Steel Crews | Labor |  |  | 1
NEORSD#1294-1 | NEORSD #1294 | Nonlabor |  |  | 1
NEORSD#1294-2 | NEORSD #1294 | Nonlabor |  |  | 1
3404 | 3404 - I-66 Inside the Beltway Widening | Nonlabor |  |  | 1
EBW | Base Scope | Nonlabor |  |  | 1
EDA | Option 1 - EDA | Nonlabor |  |  | 1
C00108424DB92.00104 | PROJECT DESIGN | Material | Lump Sum |  | 8
C00108424DB92.25595 | QUALITY CONTROL | Material | Lump Sum |  | 8
C00108424DB92.25593 | QUALITY ASSURANCE | Material | Lump Sum |  | 8
C00108424DB92.49013 | DRY UTILITY RELOCATION COSTS | Material | Lump Sum |  | 8
C00108424DB92.49014 | WET UTILITY RELOCATION COSTS (WATER) | Material | Lump Sum |  | 8
C00108424DB92.28553 | ENVIRONMENTAL MONITORING | Material | Lump Sum |  | 8
C00108424DB92.29000 | LANDSCAPING REQUIREMENTS | Material | Lump Sum |  | 8
C00108424DB92.25561 | FORMAL PARTNERING | Material | Lump Sum |  | 8
C00108424DB92.00105 | PUBLIC COMMUNICATION/OUTREACH | Material | Lump Sum |  | 8
C00108424DB92.24330 | INCIDENT MANAGEMENT PLAN | Material | Lump Sum |  | 8
C00108424DB92.25565 | PROGRESS SCHEDULE BASELINE | Material | Lump Sum |  | 8
C00108424DB92.25567 | PROGRESS SCHEDULE UPDATES | Material | Lump Sum |  | 8
C00108424DB92.00100 | MOBILIZATION | Material | Lump Sum |  | 8
C00108424DB92.85130 | PERFORMANCE & PAYMENT BONDS | Material | Lump Sum |  | 8
C00108424DB92.00101 | CONSTRUCTION SURVEYING (CONSTR.) | Material | Lump Sum |  | 8
C00108424DB92.00110 | CLEARING AND GRUBBING | Material | Lump Sum |  | 8
C00108424DB92.00120 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
C00108424DB92.14100 | REMOVE BIKE TRAIL | Material | Cubic Yard |  | 8
C00108424DB92.141001 | REMOVE SIDEWALK | Material | Cubic Yard |  | 8
C00108424DB92.14120 | REMOVE CURB & GUTTER | Material | Linear Feet |  | 8
C00108424DB92.00134 | NS TEST PIT EXCAVATION | Material | Each |  | 8
C00108424DB92.00270 | SELECT MATL. TY. I MIN. CBR-30 | Material |  |  | 8
C00108424DB92.00355 | GEOTEXTILE (SUBGRADE STAB.) | Material | Square Yard |  | 8
C00108424DB92.02111 | REPAIR/REPLACE ESXT. STORM DRANIGE PIPE | Material | Lump Sum |  | 8
C00108424DB92.00588 | UNDERDRAIN UD-4 | Material | Linear Feet |  | 8
C00108424DB92.00595 | OUTLET PIPE | Material | Linear Feet |  | 8
C00108424DB92.00596 | ENDWALL EW-12 | Material | Each |  | 8
C00108424DB92.00700 | POST INSTALLATION INSPECTION | Material | Linear Feet |  | 8
C00108424DB92.01152 | 15" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.01182 | 18" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.01242 | 24" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.01302 | 30" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.01366 | 36" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.06820 | DROP INLET DI-3B,L=10' | Material | Each |  | 8
C00108424DB92.07512 | DROP INLET DI-7B | Material | Each |  | 8
C00108424DB92.08185 | DROP INLET DI-10G | Material | Each |  | 8
C00108424DB92.08240 | DROP INLET DI-10H, L=10' | Material | Each |  | 8
C00108424DB92.082401 | DROP INLET DI-10I, L=10' | Material | Each |  | 8
C00108424DB92.082402 | DROP INLET DI-10J TY. I | Material | Each |  | 8
C00108424DB92.08250 | DROP INLET DI-10K TY. I, L=10' | Material | Each |  | 8
C00108424DB92.08251 | DROP INLET DI-10L TY. I, L=10' | Material | Each |  | 8
C00108424DB92.09125 | EG-1 | Material | Each |  | 8
C00108424DB92.09056 | MANHOLE MH-1 OR 2 | Material | Linear Feet |  | 8
C00108424DB92.09057 | FRAME & COVER MH-1 | Material | Each |  | 8
C00108424DB92.02110 | EBW SWM POND RETROFIT | Material | Lump Sum |  | 8
C00108424DB92.09185 | PAVED DITCH PG-2A | Material | Square Yard |  | 8
C00108424DB92.10035 | CEM.STAB.SUBGRADE,6" | Material | Cubic Yard |  | 8
C00108424DB92.10013 | CEM.STAB.AGGR.MATL.NO.21A,6" | Material |  |  | 8
C00108424DB92.10128 | AGG.BASE MATL. TY.I NO.21B,6"TRAIL | Material |  |  | 8
C00108424DB92.10610 | ASPHALT CONCRETE TY. IM-19.0A,2" | Material |  |  | 8
C00108424DB92.106101 | ASPHALT CONC TY. IM-19.0A,3"TRAIL | Material |  |  | 8
C00108424DB92.10628 | FLEXIBLE PAVE.PLANING 0"-2" | Material | Square Yard |  | 8
C00108424DB92.10609 | ASPHALT CONCRETE TY. SM-12.5E,2" | Material |  |  | 8
C00108424DB92.10638 | ASPHALT CONC TY. SM-4.75A,1"TRAIL | Material |  |  | 8
C00108424DB92.10642 | ASPHALT CONCRETE TY. BM-25.0A,6" | Material |  |  | 8
C00108424DB92.12505 | ASPHALT FOR MC-4 | Material |  |  | 8
C00108424DB92.11070 | NS SAW-CUT ASPH CONC 22" MAX DEPTH | Material | Linear Feet |  | 8
C00108424DB92.12020 | STD. CURB CG-2 | Material | Linear Feet |  | 8
C00108424DB92.13245 | W&OD BIKE TRAIL - PREPARATION | Material | Lump Sum |  | 8
C00108424DB92.132451 | W&OD BIKE TRAIL - FLAT WORK | Material | Lump Sum |  | 8
C00108424DB92.132452 | W&OD BIKE TRAIL - STREET SCAPE | Material | Lump Sum |  | 8
C00108424DB92.13280 | GUARDRAIL GR-MGS1 | Material | Linear Feet |  | 8
C00108424DB92.13286 | GUARDRAIL TERMINAL GR-MGS2 | Material | Each |  | 8
C00108424DB92.13287 | GUARDRAIL TERMINAL GR-MGS3 | Material | Each |  | 8
C00108424DB92.13392 | FIXED OBJECT ATTACH. GR-FOA-2 TY. I | Material | Each |  | 8
C00108424DB92.13393 | FIXED OBJECT ATTACH. GR-FOA-2 TY. II | Material | Each |  | 8
C00108424DB92.13462 | MEDIAN BARRIER MB-7F | Material | Linear Feet |  | 8
C00108424DB92.13561 | STONE BARRIER BACKFILL | Material | Cubic Yard |  | 8
C00108424DB92.13485 | MEDIAN BARRIER MB-8A, TYPE I | Material | Linear Feet |  | 8
C00108424DB92.13486 | MEDIAN BARRIER MB-8A, TYPE II | Material | Linear Feet |  | 8
C00108424DB92.13487 | MEDIAN BARRIER MB-8A, TYPE III | Material | Linear Feet |  | 8
C00108424DB92.13477 | MEDIAN BARRIER MB-12C | Material | Linear Feet |  | 8
C00108424DB92.65710 | PIER PROTECTION, BPPS-1 | Material | Linear Feet |  | 8
C00108424DB92.13530 | RETAINING WALL POST & PANEL, WALLS A&B | Material | Square Feet |  | 8
C00108424DB92.13604 | IMPACT ATTEN.SER. TY. 1 (TL-3,>45 MPH) | Material | Lump Sum |  | 8
C00108424DB92.13752 | STR.MOUNTED SOUND BARR.WALL ABSORPTIVE | Material | Square Feet |  | 8
C00108424DB92.13755 | SOUND BARRIER WALL ABSORPTIVE | Material | Square Feet |  | 8
C00108424DB92.24100 | ALLAYING DUST | Material | Hour |  | 8
C00108424DB92.50009 | MAINTENANCE OF TRAFFIC (MOT) | Material | Lump Sum |  | 8
C00108424DB92.50010 | MAINTAIN PEDESTRIAN TRAFFIC | Material | Lump Sum |  | 8
C00108424DB92.10506 | TEMP PAVEMENT FOR MOT (SHLDR STRENGTH) | Material | Square Yard |  | 8
C00108424DB92.24152 | TYPE III BARRICADE 8' | Material | Each |  | 8
C00108424DB92.24160 | CONSTRUCTION SIGNS | Material | Square Feet |  | 8
C00108424DB92.24272 | TRUCK MOUNTED ATTENUATOR | Material | Hour |  | 8
C00108424DB92.24278 | GROUP 2 CHANNELIZING DEVICES | Material | Day |  | 8
C00108424DB92.24279 | PORT.CHANGEABLE MESS. SIGN | Material | Lump Sum |  | 8
C00108424DB92.24281 | ELECTRONIC ARROW | Material | Hour |  | 8
C00108424DB92.24290 | TRAFFIC BARRIER SER.CONC.MB-7D PC | Material | Linear Feet |  | 8
C00108424DB92.24296 | TRAF.BARR.SER.CONC.SINGLE FACE (PINNED) | Material | Linear Feet |  | 8
C00108424DB92.24297 | TRAF.BARR.SER.CONC.DBL FACE (PINNED) | Material | Linear Feet |  | 8
C00108424DB92.24360 | NS SAFETY TOW WRECKER SERVICE | Material | Lump Sum |  | 8
C00108424DB92.24430 | DEMO. OF PAVEMENT (FLEXIBLE) | Material | Square Yard |  | 8
C00108424DB92.24501 | NS REMOVE EXIST. CONCRETE BARRIER | Material | Linear Feet |  | 8
C00108424DB92.24600 | REMOVE EXISTING GUARDRAIL | Material | Linear Feet |  | 8
C00108424DB92.24602 | NS REMOVE EXIST. FENCE | Material | Linear Feet |  | 8
C00108424DB92.23600 | 6' CHAIN LINK FENCE R.W | Material | Linear Feet |  | 8
C00108424DB92.23602 | 6' CHAIN LINK FENCE R.W | Material | Each |  | 8
C00108424DB92.24702 | NS REMOVE EXIST. DROP INLET | Material | Each |  | 8
C00108424DB92.247021 | NS REMOVE EXIST. HEADWALL | Material | Each |  | 8
C00108424DB92.00529 | NS FLOWABLE FILL (PIPE ABANDONMENT) | Material | Cubic Yard |  | 8
C00108424DB92.24703 | NS REMOVE EXIST SOUND BARRIER WALL | Material | Lump Sum |  | 8
C00108424DB92.24825 | NS MODIFY EXIST. CONVERT EXIST DI TO MH | Material | Each |  | 8
C00108424DB92.25505 | FIELD OFFICE TY.I | Material | Lump Sum |  | 8
C00108424DB92.27000 | SELECTIVE TREE REMOVAL TRIMMING AND CLEA | Material | Linear Feet |  | 8
C00108424DB92.27012 | TOPSOIL CLASS B 2" | Material | Square Yard |  | 8
C00108424DB92.27024 | TOPSOIL CLASS B 4" | Material | Square Yard |  | 8
C00108424DB92.271021 | REGULAR SEED | Material | Lump Sum |  | 8
C00108424DB92.27103 | OVERSEEDING | Material | Lump Sum |  | 8
C00108424DB92.27215 | FERTILIZER(15-30-15) | Material | Lump Sum |  | 8
C00108424DB92.27250 | LIME | Material | Lump Sum |  | 8
C00108424DB92.27284 | EROSION CONTROL MULCH | Material | Square Yard |  | 8
C00108424DB92.27327 | SOIL STABILIZATION MAT EC-3 TYPE C | Material | Square Yard |  | 8
C00108424DB92.27451 | INLET PROTECTION , TYPE A | Material | Each |  | 8
C00108424DB92.27461 | INLET PROTECTION , TYPE B | Material | Each |  | 8
C00108424DB92.27505 | TEMP. SILT FENCE TYPE A | Material | Linear Feet |  | 8
C00108424DB92.27345 | TEMP. DIVERSION DIKE (EC-9) | Material | Linear Feet |  | 8
C00108424DB92.27410 | ROCK CHECK DAM (EC-4) | Material | Each |  | 8
C00108424DB92.50108 | SIGN PANEL | Material | Square Feet |  | 8
C00108424DB92.50402 | SIGN POST STEEL 3" | Material | Linear Feet |  | 8
C00108424DB92.50404 | SIGN POST STEEL 4" | Material | Linear Feet |  | 8
C00108424DB92.50500 | CONC.FOUND.SSP-V A 1' DIA.X 3' DEPTH | Material | Each |  | 8
C00108424DB92.50502 | CONC.FOUND.SSP-V A 1'9" DIA.X 4'6" D | Material | Each |  | 8
C00108424DB92.50575 | CONC.FOUND.O/H SIGN STRUCTURE | Material | Cubic Yard |  | 8
C00108424DB92.56205 | TEST BORES | Material | Each |  | 8
C00108424DB92.509021 | NS TRAFFIC SIGN O.H. LOCATION NO. 1 | Material | Each |  | 8
C00108424DB92.509022 | NS TRAFFIC SIGN O.H. LOCATION NO. 2 | Material | Each |  | 8
C00108424DB92.509023 | NS TRAFFIC SIGN O.H. LOCATION NO. 3 | Material | Each |  | 8
C00108424DB92.509024 | NS TRAFFIC SIGN O.H. LOCATION NO. 4 | Material | Each |  | 8
C00108424DB92.509025 | NS TRAFFIC SIGN O.H. LOCATION NO. 5 | Material | Each |  | 8
C00108424DB92.509026 | NS TRAFFIC SIGN O.H. LOCATION NO. 6 | Material | Each |  | 8
C00108424DB92.51137 | MODIFY TRAFFIC SIGNAL RT29&WASH | Material | Each |  | 8
C00108424DB92.51160 | MODIFY TRAFFIC SIGNAL RT29&FAIRFAX | Material | Each |  | 8
C00108424DB92.54042 | TY.B CL.I PAVE. LINE MARK. 24" | Material | Linear Feet |  | 8
C00108424DB92.54075 | TY.B CL.VI PAVE. LINE MARK. 4" | Material | Linear Feet |  | 8
C00108424DB92.54076 | TY.B CL.VI PAVE. LINE MARK. 6" | Material | Linear Feet |  | 8
C00108424DB92.54077 | TY.B CL.VI PAVE. LINE MARK. 8" | Material | Linear Feet |  | 8
C00108424DB92.54078 | TY.B CL.VI PAVE. LINE MARK. 12" | Material | Linear Feet |  | 8
C00108424DB92.54101 | NS PAVE. MARK MESS. MARK. BICYCLE LANE | Material | Each |  | 8
C00108424DB92.54080 | TY.B CL.VI CONTRAST PVMT MRKG, 6" | Material | Linear Feet |  | 8
C00108424DB92.54105 | ERAD. OF EXIST.PAVE.MARKING | Material | Linear Feet |  | 8
C00108424DB92.54217 | SNOW PLOW.RAISED PAVE.MARK.ASPH.CONC | Material | Each |  | 8
C00108424DB92.54240 | TEMP. PAVE. MARKER 1 WAY | Material | Each |  | 8
C00108424DB92.54300 | PAVE.MESS.MARK.ELONG.ARROW SIN | Material | Each |  | 8
C00108424DB92.54466 | CONS. PAVE. MARK. (TY. D) 6" | Material | Linear Feet |  | 8
C00108424DB92.54510 | CONSTR.PAVE.MARK.(TY.D,CL.I)4" | Material | Linear Feet |  | 8
C00108424DB92.54550 | CONSTR.PAVE.MARK.(TY.F,CL.I)4" | Material | Linear Feet |  | 8
C00108424DB92.55001 | NS 1 CONDUCTOR NO. 4 AWG, TYPE RHW, 600V | Material | Linear Feet |  | 8
C00108424DB92.55120 | EMBEDDED JUNCTION BOX; W&OD | Material | Each |  | 8
C00108424DB92.55140 | CONCRETE FOUNDATION LF-1 TY. A | Material | Each |  | 8
C00108424DB92.55580 | LIGHT POLE FOUNDATION. BARRIER WALL MOUNTED | Material | Each |  | 8
C00108424DB92.55581 | JUNCTION BOX JB-S2 W/ GROUND ROD | Material | Each |  | 8
C00108424DB92.56032 | 2' METAL CONDUIT | Material | Linear Feet |  | 8
C00108424DB92.56055 | NS SCHEDULE 80 RIGID PVC CONDUIT- TRENCH | Material | Linear Feet |  | 8
C00108424DB92.59000 | NS LIGHTING CONTROL CENTER CCW-1 TYPE A | Material | Each |  | 8
C00108424DB92.590001 | LED LUMINAIRE, UNDERDECK, WALL MOUNTED | Material | Each |  | 8
C00108424DB92.590002 | NS LIGHTING ELECTRICAL SERVICE, SE-9 TYPE A | Material | Each |  | 8
C00108424DB92.590003 | STEP DOWN TRANSFORMER | Material | Each |  | 8
C00108424DB92.590004 | LED LUMINAIRE, STEP LIGHTING FOR W&OD BRIDGE | Material | Each |  | 8
C00108424DB92.590005 | LED LUMINAIRE, ROADWAY | Material | Each |  | 8
C00108424DB92.590006 | LED LUMINAIRE, PEDESTRIAN | Material | Each |  | 8
C00108424DB92.590007 | LIGHTING POLE LP-1 30'-12' POWDER CTD | Material | Each |  | 8
C00108424DB92.590008 | LIGHTING POLE LP-1 45'-12' POWDER CTD | Material | Each |  | 8
C00108424DB92.590009 | LIGHTING POLE LP-2 TYPE A POWDER CTD | Material | Each |  | 8
C00108424DB92.590001-1 | NS LIGHTING REMOVE EX LT POLE & JUNC BOX | Material | Each |  | 8
C00108424DB92.59001 | NS LIGHTING BORED CONDUIT 3" | Material | Linear Feet |  | 8
C00108424DB92.59050 | NS COMM EQUIP. 120/240 SE-5 SERVICE | Material | Each |  | 8
C00108424DB92.590501 | NS COMM EQUIP. STEP-DOWN TRANSFORMER | Material | Each |  | 8
C00108424DB92.590502 | NS COMM EQ. CAMERA, 80' POLE, LOWER DEV & FOUND' | Material | Each |  | 8
C00108424DB92.590503 | NS COMMUNICATION EQUIP. EQUIP CABINET | Material | Each |  | 8
C00108424DB92.590504 | NS COMMUNICATION EQUIP. ETHERNET SWITCH L2 | Material | Each |  | 8
C00108424DB92.590506 | NS COMM EQUIP. FO INTERCONNECT CENTER DISTRIBUTION | Material | Each |  | 8
C00108424DB92.590507 | NS COMM EQUIP. FUSED SAFTEY SWITCH | Material | Each |  | 8
C00108424DB92.590508 | NS COMM EQUIP. JUNC BOX POWER | Material | Each |  | 8
C00108424DB92.590509 | NS COMM EQUIP. JUNC BOX COMM | Material | Each |  | 8
C00108424DB92.590510 | NS COMM EQUIP. RELOCATE VEHICLE DETECTOR | Material | Each |  | 8
C00108424DB92.590511 | NS COMM EQUIP. RELOCATE CCTV CAMERA/POLE | Material | Each |  | 8
C00108424DB92.590512 | NS COMM EQUIP. RELOCATE CABINET W/NEW BASES | Material | Each |  | 8
C00108424DB92.590513 | NS COMM EQUIP. RELOCATE DMS W/STRUCTURE | Material | Each |  | 8
C00108424DB92.590514 | NS COMMUNICATION EQUIP. UNINTERRUPTIBLE | Material | Each |  | 8
C00108424DB92.59060 | NS COMM EQUIP. SYSTEM DOCUMENTATION/SUPPORT | Material | Each |  | 8
C00108424DB92.59071 | NS COMMUNICATION EQUIP. 12 FIBER OPTIC C | Material | Linear Feet |  | 8
C00108424DB92.590711 | NS COMM EQ 1 CONDUCTOR NO. 4 AWG, TYPE RHW, 600V | Material | Linear Feet |  | 8
C00108424DB92.590712 | NS COMMUNICATION EQUIP. BORED CONDUIT 3" | Material | Linear Feet |  | 8
C00108424DB92.590713 | NS COMMUNICATION EQUIP. BORED CONDUIT 3" | Material | Linear Feet |  | 8
C00108424DB92.B675 | B675 - I66EB OVER WILLIAMSBURG | Material | Lump Sum |  | 8
C00108424DB92.B677 | B677 - I66EB OVER WESTMORELAND | Material | Lump Sum |  | 8
C00108424DB92.B678 | B678 - I66EB OVER N. SYCAMORE | Material | Lump Sum |  | 8
C00108424DB92.B679 | B679 - I66EB OVER BON AIR PARK | Material | Lump Sum |  | 8
C00108424DB92.B680 | B680 - W&OD PED BRG OVER US29 | Material | Lump Sum |  | 8
C00108424DB92.B681 | B681 - PED BRIDGE OVER I66 | Material | Lump Sum |  | 8
C00108424DB92.B682 | B682 - I66WB OVER WILLIAMSBURG | Material | Lump Sum |  | 8
C00108424DB92.B683 | B683 - I66WB OVER WESTMORELAND | Material | Lump Sum |  | 8
C00108424DB92.B684 | B684 - I66WB OVER BON AIR PARK | Material | Lump Sum |  | 8
C00108424DB92.01.25595 | QUALITY CONTROL | Material | Lump Sum |  | 8
C00108424DB92.01.25593 | QUALITY ASSURANCE | Material | Lump Sum |  | 8
C00108424DB92.01.28553 | ENVIRONMENTAL MONITORING | Material | Lump Sum |  | 8
C00108424DB92.01.29000 | LANDSCAPING REQUIREMENTS | Material | Lump Sum |  | 8
C00108424DB92.01.25561 | FORMAL PARTNERING | Material | Lump Sum |  | 8
C00108424DB92.01.00105 | PUBLIC COMMUNICATION/OUTREACH | Material | Lump Sum |  | 8
C00108424DB92.01.25565 | PROGRESS SCHEDULE BASELINE | Material | Lump Sum |  | 8
C00108424DB92.01.25567 | PROGRESS SCHEDULE UPDATES | Material | Lump Sum |  | 8
C00108424DB92.01.85130 | PERFORMANCE & PAYMENT BONDS | Material | Lump Sum |  | 8
C00108424DB92.01.00101 | CONSTRUCTION SURVEYING (CONSTR.) | Material | Lump Sum |  | 8
C00108424DB92.01.B686 | B686 - RAMP A OF I66EB OVER RT7 | Material | Lump Sum |  | 8
CO 11 | Change Order 11 - Upgrade to ITS Equipment | Material | Lump Sum |  | 8
NEORSD#1294-3 | NEORSD #1294 | Nonlabor |  |  | 1
NEORSD#1294-4 | NEORSD #1294 | Nonlabor |  |  | 1
NEORSD#1294-5 | NEORSD #1294 | Nonlabor |  |  | 1
011 | Arrow Board | Nonlabor |  |  | 1
0001 | Sanitary Sewer Line Relocation | Material | Unit |  | 1
0002 | Sanitary Sewer Line Boring & Sheetpile | Material | Unit |  | 1
0001.1 | (New Resource) | Material | Unit |  | 1
0003 | Waterline Relocation | Material | Unit |  | 1
0004 | Demolition | Material | Unit |  | 1
0005 | Drainage Structures | Material | Unit |  | 1
0006 | I-Wall Transitions | Material | Unit |  | 1
0007 | Levee Preloading | Material | Unit |  | 1
0008 | Dynamic Compaction | Material | Unit |  | 1
0009 | Levee Construction | Material | Unit |  | 1
0010 | Stone Protection | Material | Unit |  | 1
0011 | Mitigation | Material | Unit |  | 1
0012 | Site Restoration | Material | Unit |  | 1
0013 | Unsatisfactory Material Removal & Disposal | Material | Unit |  | 1
3398-29-1 | Inlet Protection - 3A | Material | Each |  | 8
3398-96-1 | Seeding - 3A | Material |  |  | 8
3398-96-3 | Rubber Removal - 3 | Material | Square Feet |  | 8
3398-96-2 | Joint Seal - 3 | Material | Linear Feet |  | 8
3398-96-4 | Pavement Markings - 3 | Material | Square Feet |  | 8
3398-118-1 | Inlet Protection - 3C | Material | Each |  | 8
3398-157-2 | Pavement Marking - 3C | Material | Square Feet |  | 8
3398-157-1 | Seeding - 3C | Material |  |  | 8
3398-179-1 | Inlet Protection - 3E | Material | Each |  | 8
3398-179-2 | Remove Idle Pavement | Material | Square Yard |  | 8
3398-245-1 | Seeding - 3E | Material |  |  | 8
3398-245-2 | Joint Seal - 3E | Material | Linear Feet |  | 8
3398-245-3 | Rubber Removal - 3E | Material | Square Feet |  | 8
3398-245-4 | Pavement - Markings | Material | Square Feet |  | 8
3398-331-1 | Pavement Markings - 4A | Material | Square Feet |  | 8
3398-332-1 | Inlet Protection | Material | Each |  | 8
3398-332-2 | Remove Idle Pavement | Material |  |  | 8
3398-403-1 | Seeding - 4B | Material |  |  | 8
3398-403-2 | Pavement Marking - 4B | Material | Square Feet |  | 8
3398-403-3 | Joint Seal - 4B | Material | Linear Feet |  | 8
3398-403-4 | Rubber Removal - 4B | Material | Square Feet |  | 8
3398-404-1 | Inlet Protection - 4C | Material | Each |  | 8
3398-404-2 | Pavement Markings - 4C | Material | Square Feet |  | 8
3398-438-1 | Pavement Marking - 4D | Material | Square Feet |  | 8
3398-471-1 | Pavement Marking - 4E | Material | Square Feet |  | 8
3398-472-1 | Inlet Protection - 4F | Material | Each |  | 8
3398-543-1 | Pavement Marking - 4F | Material | Square Feet |  | 8
3398-543-2 | Joint Seal - 4F | Material | Linear Feet |  | 8
3398-543-3 | Rubber Removal - 4F | Material | Square Feet |  | 8
3398-543-4 | Seeding - 4F | Material |  |  | 8
3398-575-1 | Pavement Marking - 4G | Material | Square Feet |  | 8
2310013.PCO6 | Quantity Overruns | Material | Lump Sum |  | 1
2310013.PCO7 | Concrete Stair + Sidewalk Toe Wall | Material | Lump Sum |  | 1
2310013.PCO8 | Matting + Rip Rap Stabilization | Material | Lump Sum |  | 1
2310013.PCO9 | Quantity Overruns #2 | Material | Lump Sum |  | 1
2310013.PCO10 | Quantity Overruns #3 | Material | Lump Sum |  | 1
3417 | 3417 - VDOT I264 / Witchduck Road Interchange | Nonlabor |  |  | 1
3417-00100 | MOBILIZATION | Material | Lump Sum |  | 8
3417-00101 | CONSTRUCTION SURVEYING (CONSTR.) | Material | Unit |  | 8
3417-00106-30 | NS MONITORING BENCHMARK | Material | Each |  | 8
3417-00106-40 | NS MONITORING INCLINOMETER | Material | Each |  | 8
3417-00106-50 | NS MONITORING MAGNETIC EXTENSOMETER | Material | Each |  | 8
3417-00106-60 | NS MONITORING TERMINAL BOX | Material | Each |  | 8
3417-00106-70 | NS MONITORING VIBRATING WIRE PIEZOMETER | Material | Each |  | 8
3417-00108 | NS MONITORING VIBRATION | Material | Lump Sum |  | 8
3417-00110 | CLEARING AND GRUBBING | Material | Lump Sum |  | 8
3417-00120 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3417-00134-110 | NS TEST EXCAVATION UTILITY TEST PIT PAVED | Material | Each |  | 8
3417-00134-120 | NS TEST EXCAVATION UTILITY TEST PIT UNPAVED | Material | Each |  | 8
3417-00141 | NS BORROW EXCAVATION MINIMUN CBR 15 | Material | Cubic Yard |  | 8
3417-00154-141 | NS GEOTEXTILE HIGH-STRENGTH GEOSYN REINF HSGR TY 1 | Material | Square Yard |  | 8
3417-00154-142 | NS GEOTEXTILE HIGH-STRENGTH GEOSYN REINF HSGR TY 2 | Material | Square Yard |  | 8
3417-00190 | SURCHARGE PLACEMENT & REMOVAL | Material | Cubic Yard |  | 8
3417-00200 | SETTLEMENT PLATE | Material | Each |  | 8
3417-00211 | MINOR STR. EXCAV. PIPE CULVERT | Material | Cubic Yard |  | 8
3417-00212 | MINOR STR. EXCAV. BOX CULVERT | Material | Cubic Yard |  | 8
3417-00290 | SELECT MATL. TY. II MIN. CBR-30 | Material | Cubic Yard |  | 8
3417-00506-200 | NS BEDDING MATL. AGGR. NO. 57 (PIPE BEDDING) | Material |  |  | 8
3417-00506-220 | NS BEDDING MATL. AGGR. NO. 57 STONE | Material |  |  | 8
3417-00506-230 | NS BEDDING MATL. AGGR. NO. 57 STONE (LOAD TRANSFER | Material |  |  | 8
3417-00522 | CONCRETE CLASS A4 BOX CULVERT MISC. BOX CULVERTS | Material | Cubic Yard |  | 8
3417-00525 | CONCRETE CLASS A3 MISC. | Material | Cubic Yard |  | 8
3417-00529 | FLOWABLE BACKFILL | Material | Cubic Yard |  | 8
3417-00536-260 | NS CONCRETE CLASS A3 MISIC. (TRUCK APRON) | Material | Cubic Yard |  | 8
3417-00536-270 | NS CONCRETE CLASS A4 (PILE CAP) | Material | Cubic Yard |  | 8
3417-00540 | REINF. STEEL | Material | LB |  | 8
3417-01150 | 15" PIPE | Material | Linear Feet |  | 8
3417-01152 | 15" CONC. PIPE | Material | Linear Feet |  | 8
3417-01156 | STORM SEWER PIPE 15" | Material | Linear Feet |  | 8
3417-01180 | 18" PIPE | Material | Linear Feet |  | 8
3417-01182 | 18" CONC. PIPE | Material | Linear Feet |  | 8
3417-01186 | STORM SEWER PIPE 18" | Material | Linear Feet |  | 8
3417-01212 | 21" CONC. PIPE | Material | Linear Feet |  | 8
3417-01240 | 24" PIPE | Material | Linear Feet |  | 8
3417-01241 | JACKED & BORED 24" PIPE | Material | Linear Feet |  | 8
3417-01242 | 24" CONC. PIPE | Material | Linear Feet |  | 8
3417-01246 | STORM SEWER PIPE 24" | Material | Linear Feet |  | 8
3417-01301 | JACKED & BORED 30" PIPE | Material | Linear Feet |  | 8
3417-01306 | STORM SEWER PIPE 30" | Material | Linear Feet |  | 8
3417-01360 | 36" PIPE | Material | Linear Feet |  | 8
3417-01361 | JACKED & BORED 36" PIPE | Material | Linear Feet |  | 8
3417-01366 | STORM SEWER PIPE 36" | Material | Linear Feet |  | 8
3417-01421 | JACKED & BORED 42" PIPE | Material | Linear Feet |  | 8
3417-01426 | STORM SEWER PIPE 42" | Material | Linear Feet |  | 8
3417-01486 | STORM SEWER PIPE 48" | Material | Linear Feet |  | 8
3417-01546 | STORM SEWER PIPE 54" | Material | Linear Feet |  | 8
3417-01601 | JACKED & BORED 60" PIPE | Material | Linear Feet |  | 8
3417-01606 | STORM SEWER PIPE 60" | Material | Linear Feet |  | 8
3417-02090 | NS PIPE INVERSION LINER 60" | Material | Linear Feet |  | 8
3417-02093 | NS SPEC. DESIGN NS PRE-FABRICATED VERTICAL DRAIN | Material | Linear Feet |  | 8
3417-02093-540 | NS SPEC. DESIGN PRE-DRILLING FOR PV DRAINS | Material | Linear Feet |  | 8
3417-02190 | 30" X 19" ELLIPTICAL PIPE | Material | Linear Feet |  | 8
3417-06150 | 15" END SECTION ES-1 OR 2 | Material | Each |  | 8
3417-06151 | 15" END SECTION ES-1 | Material | Each |  | 8
3417-06181 | 18" END SECTION ES-1 | Material | Each |  | 8
3417-06241 | 24" END SECTION ES-1 | Material | Each |  | 8
3417-06301 | 30" END SECTION ES-1 | Material | Each |  | 8
3417-06361 | 36" END SECTION ES-1 | Material | Each |  | 8
3417-06421 | 42" END SECTION ES-1 | Material | Each |  | 8
3417-06481 | 48" END SECTION ES-1 | Material | Each |  | 8
3417-06485 | 54" END SECTION ES-1 | Material | Each |  | 8
3417-06491 | 60" END SECTION ES-1 | Material | Each |  | 8
3417-06740 | DROP INLET DI-1 | Material | Each |  | 8
3417-06749 | DROP INLET DI-2B,L=8' | Material | Each |  | 8
3417-06750 | DROP INLET DI-2B,L=10' | Material | Each |  | 8
3417-06752 | DROP INLET DI-2B,L=14' | Material | Each |  | 8
3417-06758 | DROP INLET DI-2BB,L=8' | Material | Each |  | 8
3417-06759 | DROP INLET DI-2BB,L=10' | Material | Each |  | 8
3417-06762 | DROP INLET DI-2BB,L=16' | Material | Each |  | 8
3417-06765 | DROP INLET DI-2C,L=6' | Material | Each |  | 8
3417-06783 | DROP INLET DI-2E,L=6 | Material | Each |  | 8
3417-06815 | DROP INLET DI-3A | Material | Each |  | 8
3417-06817 | DROP INLET DI-3B,L=4' | Material | Each |  | 8
3417-06818 | DROP INLET DI-3B,L=6' | Material | Each |  | 8
3417-06819 | DROP INLET DI-3B,L=8' | Material | Each |  | 8
3417-06820 | DROP INLET DI-3B,L=10' | Material | Each |  | 8
3417-06821 | DROP INLET DI-3B,L=12' | Material | Each |  | 8
3417-06822 | DROP INLET DI-3B,L=14' | Material | Each |  | 8
3417-06824 | DROP INLET DI-3B,L=18' | Material | Each |  | 8
3417-06827 | DROP INLET DI-3BB,L=6' | Material | Each |  | 8
3417-06828 | DROP INLET DI-3BB,L=8' | Material | Each |  | 8
3417-06833 | DROP INLET DI-3BB,L=18' | Material | Each |  | 8
3417-06835 | DROP INLET DI-3C,L=6' | Material | Each |  | 8
3417-06836 | DROP INLET DI-3C,L=8' | Material | Each |  | 8
3417-06837 | DROP INLET DI-3C,L=10' | Material | Each |  | 8
3417-06838 | DROP INLET DI-3C,L=12' | Material | Each |  | 8
3417-06839 | DROP INLET DI-3C,L=14' | Material | Each |  | 8
3417-06853 | DROP INLET DI-3E,L=4' | Material | Each |  | 8
3417-07004 | DROP INLET DI-3F,L=6' | Material | Each |  | 8
3417-07106 | DROP INLET DI-4A | Material | Each |  | 8
3417-07112 | DROP INLET DI-4B,L=8' | Material | Each |  | 8
3417-07130 | DROP INLET DI-4BB,L=10' | Material | Each |  | 8
3417-07206 | DROP INLET DI-4C,L=8' | Material | Each |  | 8
3417-07214 | DROP INLET DI-4C,L=16' | Material | Each |  | 8
3417-07304 | DROP INLET DI-4D | Material | Each |  | 8
3417-07308 | DROP INLET DI-4E,L=6' | Material | Each |  | 8
3417-07404 | DROP INLET DI-4F,L=6' | Material | Each |  | 8
3417-07506 | DROP INLET DI-5 | Material | Each |  | 8
3417-07508 | DROP INLET DI-7 | Material | Each |  | 8
3417-08190 | DROP INLET DI-10H TY. I,L=10' | Material | Each |  | 8
3417-08198 | DROP INLET DI-10H TY. II,L=8' | Material | Each |  | 8
3417-08201 | DROP INLET DI-10H TY. II,L=14' | Material | Each |  | 8
3417-08222 | DROP INLET DI-10I TY. I,L=10' | Material | Each |  | 8
3417-08270 | DROP INLET DI-10K TY. III,L=4' | Material | Each |  | 8
3417-08271 | DROP INLET DI-10K TY. III,L=6' | Material | Each |  | 8
3417-08273 | DROP INLET DI-10K TY. III,L=10' | Material | Each |  | 8
3417-08275 | DROP INLET DI-10K TY. III,L=14' | Material | Each |  | 8
3417-08276 | DROP INLET DI-10K TY. III,L=16' | Material | Each |  | 8
3417-08303 | DROP INLET DI-10L TY. III,L=12' | Material | Each |  | 8
3417-08304 | DROP INLET DI-10L TY. III,L=14' | Material | Each |  | 8
3417-08511 | DROP INLET DI-14B TY. I,L=8' | Material | Each |  | 8
3417-08513 | DROP INLET DI-14B TY. I,L=12' | Material | Each |  | 8
3417-08515 | DROP INLET DI-14B TY. I,L=16' | Material | Each |  | 8
3417-08517 | DROP INLET DI-14B TY. I,L=20' | Material | Each |  | 8
3417-08531 | DROP INLET DI-14C TY. I,L=8' | Material | Each |  | 8
3417-08532 | DROP INLET DI-14C TY. I,L=10' | Material | Each |  | 8
3417-08533 | DROP INLET DI-14C TY. I,L=12' | Material | Each |  | 8
3417-08540 | DROP INLET DI-14C TY. II,L=6' | Material | Each |  | 8
3417-08560 | DROP INLET DI-14E TY. I,L=4' | Material | Each |  | 8
3417-08561 | DROP INLET DI-14E TY. I,L=6' | Material | Each |  | 8
3417-08562 | DROP INLET DI-14E TY. I,L=8' | Material | Each |  | 8
3417-08571 | DROP INLET DI-14E TY. II,L=6' | Material | Each |  | 8
3417-08572 | DROP INLET DI-14E TY. II,L=8' | Material | Each |  | 8
3417-08573 | DROP INLET DI-14E TY. II,L=10' | Material | Each |  | 8
3417-08574 | DROP INLET DI-14E TY. II,L=12' | Material | Each |  | 8
3417-08576 | DROP INLET DI-14E TY. II,L=16' | Material | Each |  | 8
3417-08578 | DROP INLET DI-14E TY. II,L=20' | Material | Each |  | 8
3417-08602 | DROP INLET DI-14F TY. I,L=8' | Material | Each |  | 8
3417-08608 | DROP INLET DI-14F TY. I,L=20' | Material | Each |  | 8
3417-08962 | DROP INLET DI-13 TY.1 | Material | Each |  | 8
3417-08965 | DROP INLET DI-13 TY.II | Material | Each |  | 8
3417-08990-1350 | NS DROP INLET PRECAST TOP DI-2A | Material | Each |  | 8
3417-08990-1360 | NS DROP INLET PRECAST TOP DI-2B | Material | Each |  | 8
3417-08990-1370 | NS DROP INLET PRECAST TOP DI-2C | Material | Each |  | 8
3417-08990-1380 | NS DROP INLET PRECAST TOP DI-3A | Material | Each |  | 8
3417-08990-1390 | NS DROP INLET PRECAST TOP DI-3B | Material | Each |  | 8
3417-08990-1400 | NS DROP INLET PRECAST TOP DI-4D | Material | Each |  | 8
3417-09056 | MANHOLE MH-1 OR 2 | Material | Linear Feet |  | 8
3417-09057 | FRAME & COVER MH-1 | Material | Each |  | 8
3417-09065 | NS MANHOLE SANITARY SEWER, (5' DIAMETER) | Material | Linear Feet |  | 8
3417-09148 | EROS.CTRL.STONE CL.A1 EC-1 | Material |  |  | 8
3417-09150 | EROS.CTRL.STONE CL. I, EC-1 | Material |  |  | 8
3417-09152 | EROS.CTRL.STONE CL. II, EC-1 | Material |  |  | 8
3417-09215 | PAVED DITCH PG-5 | Material | Square Yard |  | 8
3417-09250 | SLOPE DRAIN | Material | Each |  | 8
3417-10013 | CEM.STAB.AGGR.MATL.NO. 21A | Material |  |  | 8
3417-10017 | CEM.S.AGR.BAS.MATL.TY.I N.21A | Material |  |  | 8
3417-10128 | AGGR. BASE MATL. TY. I NO. 21B | Material |  |  | 8
3417-10250-1530 | NS AGGR. MATERIAL LIGHTWEIGHT FILL | Material |  |  | 8
3417-10250-1540 | NS AGGR. MATERIAL NO. 57 | Material |  |  | 8
3417-10417 | TACK COAT | Material | Gallon |  | 8
3417-10478 | COVER MATL. AGGR. NO. 78 | Material |  |  | 8
3417-10499 | NS PAVEMENT CONCRETE PAVING UNITS | Material | Square Yard |  | 8
3417-10607 | ASPHALT CONCRETE TY. SM-12.5A | Material |  |  | 8
3417-10608 | ASPHALT CONCRETE TY. SM-12.5D | Material |  |  | 8
3417-10610 | ASPHALT CONCRETE TY. IM-19.0A | Material |  |  | 8
3417-10611 | ASPHALT CONCRETE TY. IM-19.0D | Material |  |  | 8
3417-10628 | FLEXIBLE PAVE.PLANING 0"-2" | Material | Square Yard |  | 8
3417-10635 | ASPHALT CONC.TY. SM-9.5A | Material |  |  | 8
3417-10642 | ASPHALT CONC. BASE COURSE TY. BM-25.0A | Material |  |  | 8
3417-11020 | CONC. CL. A4 BRIDGE APPR. SLAB | Material | Cubic Yard |  | 8
3417-11070 | NS SAW-CUT ASPH CONC FULL DEPTH | Material | Linear Feet |  | 8
3417-11071 | NS SAW-CUT HYDR.CEM.CONC.PAVE. FULL DEPTH | Material | Linear Feet |  | 8
3417-12020 | STD. CURB CG-2 | Material | Linear Feet |  | 8
3417-12022 | RADIAL CURB CG-2 | Material | Linear Feet |  | 8
3417-12030 | STD. CURB CG-3 | Material | Linear Feet |  | 8
3417-12032 | RADIAL CURB CG-3 | Material | Linear Feet |  | 8
3417-12322 | ASPHALT CONC. CURB TY. MC-3B | Material | Linear Feet |  | 8
3417-12505 | ASPH.CONC.CURB BACKUP MATL. | Material |  |  | 8
3417-12600 | STD. COMB. CURB & GUTTER CG-6 | Material | Linear Feet |  | 8
3417-12610 | RAD. COMB. CURB & GUTTER CG-6 | Material | Linear Feet |  | 8
3417-12700 | STD. COMB. CURB & GUTTER CG-7 | Material | Linear Feet |  | 8
3417-12940 | ENTRANCE GUTTER CG-9D | Material | Square Yard |  | 8
3417-13102 | RAD. COMB. CURB & GUTTER CG-11 | Material | Linear Feet |  | 8
3417-13108 | CG-12 DETECTABLE WARNING SURFACE | Material | Square Yard |  | 8
3417-13114 | ENTRANCE GUTTER CG-13 | Material | Square Yard |  | 8
3417-13220 | HYDR. CEMENT CONC. SIDEWALK 4" | Material | Square Yard |  | 8
3417-13232 | GEOTEXTILE DRAINAGE FABRIC | Material | Square Yard |  | 8
3417-13312 | GUARDRAIL TERMINAL GR-7 (NCHRP 350) | Material | Each |  | 8
3417-13315 | GUARDRAIL TERMINAL GR-11 | Material | Each |  | 8
3417-13320 | GUARDRAIL GR-2 | Material | Linear Feet |  | 8
3417-13323 | GUARDRAIL GR-2A | Material | Linear Feet |  | 8
3417-13331 | RAD. GUARDRAIL GR-2 | Material | Each |  | 8
3417-13345 | ALT.BREAKAWAY CABLE TERM.(GR-9) | Material | Each |  | 8
3417-13383 | FIXED OBJECT ATTACH. GR-FOA-1 TY. I | Material | Each |  | 8
3417-13392 | FIXED OBJECT ATTACH. GR-FOA-2 TY. I | Material | Each |  | 8
3417-13393 | FIXED OBJECT ATTACH. GR-FOA-2 TY. II | Material | Each |  | 8
3417-13401 | NS GUARDRAIL HAND DIG GUARDRAIL POST HOLE | Material | Each |  | 8
3417-13421 | MEDIAN BARRIER MB-3 | Material | Linear Feet |  | 8
3417-13460 | MEDIAN BARRIER MB-7D | Material | Linear Feet |  | 8
3417-13461 | MEDIAN BARRIER MB-7E | Material | Linear Feet |  | 8
3417-13462 | MEDIAN BARRIER MB-7F | Material | Linear Feet |  | 8
3417-13478 | NS MEDIAN BARRIER TERMINAL WALL | Material | Linear Feet |  | 8
3417-13480 | CABLE BARRICADE CR-1 | Material | Each |  | 8
3417-13485 | MEDIAN BARRIER MB-8A TYPE I | Material | Linear Feet |  | 8
3417-13486 | MEDIAN BARRIER MB-8A TYPE II | Material | Linear Feet |  | 8
3417-13487 | MEDIAN BARRIER MB-8A TYPE III | Material | Linear Feet |  | 8
3417-13496 | TRAF. BARR. SER. CONC. DBL FC PAR.MB-11A | Material | Linear Feet |  | 8
3417-13500 | SIGN ISLAND SI-1 | Material | Each |  | 8
3417-13502 | SIGN ISLAND SI-2 | Material | Square Yard |  | 8
3417-13510 | DIRECTIONAL ISLAND CURB SI-3 | Material | Linear Feet |  | 8
3417-13520 | RETAINING WALL RW-2 | Material | Cubic Yard |  | 8
3417-13561 | POROUS BACKFILL | Material | Cubic Yard |  | 8
3417-13565 | RETAINING WALL EXCAVATION | Material | Cubic Yard |  | 8
3417-13604 | IMPACT ATTEN.SER. TY. 1 (TL-3,>45 MPH) | Material | Each |  | 8
3417-13606 | IMPACT ATTEN.(TL-2, <40 MPH DES.SP) | Material | Each |  | 8
3417-13607 | IMPACT ATTEN.(TL-3,>=40 MPH DES.SP.) | Material | Each |  | 8
3417-13815 | NS RETAINING STRUCTURE MECHANICALLY STABILIZD EART | Material | Square Feet |  | 8
3417-14260 | CRUSHER RUN AGGR. NO. 25 OR 26 | Material |  |  | 8
3417-21020 | MEDIAN STRIP MS-1 | Material | Square Yard |  | 8
3417-21110 | MEDIAN STRIP MS-1A | Material | Square Yard |  | 8
3417-21215 | MEDIAN STRIP MS-2 | Material | Linear Feet |  | 8
3417-22643 | FENCE FE-CL | Material | Linear Feet |  | 8
3417-22653 | LINE BRACE UNIT FE-CL | Material | Each |  | 8
3417-22663 | CORNER BRACE UNIT FE-CL | Material | Each |  | 8
3417-23560 | TEMP. SAFETY FENCE 4' | Material | Linear Feet |  | 8
3417-23600 | NS FENCE HIGH DENSITY MESH PEDESTRIAN FENCE | Material | Linear Feet |  | 8
3417-24100 | ALLAYING DUST | Material | Hour |  | 8
3417-24150 | TYPE 3 BARRICADE 4' | Material | Each |  | 8
3417-24152 | TYPE 3 BARRICADE 8' | Material | Each |  | 8
3417-24160 | TEMPORARY (CONSTRUCTION) SIGN | Material | Square Feet |  | 8
3417-24265 | NS MAINTENANCE OF TRAFFIC WORK ZONE CONTROL MANAG | Material | Unit |  | 8
3417-24267 | TEMPORARY DETECTABLE WARNING STRIP | Material | Linear Feet |  | 8
3417-24272 | TRUCK MOUNTED ATTENUATOR | Material | Hour |  | 8
3417-24278 | GROUP 2 CHANNELIZING DEVICES | Material | Day |  | 8
3417-24279 | PORT.CHANGEABLE MESS. SIGN | Material | Hour |  | 8
3417-24281 | ELECTRONIC ARROW BOARD | Material | Hour |  | 8
3417-24282 | FLAGGER SERVICE | Material | Hour |  | 8
3417-24286 | FLEXIBLE POST DELINEATOR | Material | Each |  | 8
3417-24288 | WARNING LIGHT TY. B | Material | Day |  | 8
3417-24290 | TRAFFIC BARRIER SER. CONC. MB-7D PC | Material | Linear Feet |  | 8
3417-24293 | NS TRAFFIC BARRIER SERVICE RESET | Material | Linear Feet |  | 8
3417-24360-2390 | NS SAFETY TOW WRECKER SERVICE | Material | Hour |  | 8
3417-24360-2400 | NS SAFETY UNIFORMED FLAGGERS - NORFOLK | Material | Hour |  | 8
3417-24360 | NS SAFETY UNIFORMED FLAGGERS - VIRGINIA BEACH | Material | Hour |  | 8
3417-24400 | OBSCURING ROADWAY | Material | Unit |  | 8
3417-24420 | DEMO. OF PAVEMENT (RIGID) | Material | Square Yard |  | 8
3417-24430 | DEMO. OF PAVEMENT (FLEXIBLE) | Material | Square Yard |  | 8
3417-24501-2440 | NS REMOVE EXIST. CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-24501-2450 | NS REMOVE EXIST. EXPOSED CONDUIT AND CABLE | Material | Linear Feet |  | 8
3417-24501-2460 | NS REMOVE EXIST. FIBER OPTIC CABLE | Material | Linear Feet |  | 8
3417-24502-2470 | NS REMOVE EXIST. AND DISPOSE EXIST. ELECTRICAL SER | Material | Each |  | 8
3417-24502-2480 | NS REMOVE EXIST. AND DISPOSE EXISTING CABINET | Material | Each |  | 8
3417-24502-2490 | NS REMOVE EXIST. AND SALVAGE EXISTING CABINET | Material | Each |  | 8
3417-24502-2500 | NS REMOVE EXIST. AND SALVAGE EXISTING LIGHT POLE | Material | Each |  | 8
3417-24502-2510 | NS REMOVE EXIST. DISPOSE O/H STRUCT. TY. CS-1 | Material | Each |  | 8
3417-24502-2520 | NS REMOVE EXIST. DISPOSE O/H STRUCT. TY. DP-5 | Material | Each |  | 8
3417-24502-2530 | NS REMOVE EXIST. DISPOSE SIGN STR. TY V A FROM MED | Material | Each |  | 8
3417-24502-2550 | NS REMOVE EXIST. DISPOSE SIGN TY. SP-1 FROM UTILIT | Material | Each |  | 8
3417-24502-2560 | NS REMOVE EXIST. LIGHTING PHOTO CONTROL ASSEMBLY | Material | Each |  | 8
3417-24502-2570 | NS REMOVE EXIST. SALVAGE DMS | Material | Each |  | 8
3417-24502-2580 | NS REMOVE EXIST. SALVAGE LANE USE CONTROL SIGN | Material | Each |  | 8
3417-24502-2590 | NS REMOVE EXIST. TRAFFIC SIGNALIZATION EQUIPMENT, | Material | Each |  | 8
3417-24502-2600 | NS REMOVE EXIST. TRAFFIC SIGNALIZATION EQUIPMENT, | Material | Each |  | 8
3417-24505-2610 | NS RELOCATE EXIST. DMS | Material | Each |  | 8
3417-24505-2620 | NS RELOCATE EXIST. LANE USE CONTROL SIGN | Material | Each |  | 8
3417-24505-2630 | NS RELOCATE EXIST. SIGN PANEL TY. SP-1 | Material | Each |  | 8
3417-24505-2640 | NS RELOCATE EXIST. SIGN PANEL TY. SP-2 | Material | Each |  | 8
3417-24505-2645 | NS RELOCATE EXIST. SIGN PANEL, TYPE SP-1, FROM O/H | Material | Each |  | 8
3417-24505-2650 | NS RELOCATE EXIST. SIGN PANEL TY. SP-3 | Material | Each |  | 8
3417-24505-2660 | NS RELOCATE EXIST. VEH. DET. | Material | Each |  | 8
3417-24600 | REMOVE EXISTING GUARDRAIL | Material | Linear Feet |  | 8
3417-24602 | NS REMOVE EXIST. FENCE ... | Material | Linear Feet |  | 8
3417-24712-2680 | NS RESET EXIST. EXPOSED CONDUIT | Material | Linear Feet |  | 8
3417-24712-2690 | NS RESET EXIST. FENCE | Material | Linear Feet |  | 8
3417-24825-2700 | NS MODIFY EXIST. CONTROL CENTER | Material | Each |  | 8
3417-24825-2710 | NS MODIFY EXIST. SPLICE ENCLOSURE | Material | Each |  | 8
3417-24825-2720 | NS MODIFY EXIST. STRUCTURE | Material | Each |  | 8
3417-24825-2730 | NS MODIFY EXIST. TMS CABINET | Material | Each |  | 8
3417-25003 | HANDRAIL HR-1 TYPE II | Material | Linear Feet |  | 8
3417-25508 | NS FIELD OFFICE MODIFIED, TYPE 1 | Material | Month |  | 8
3417-25561 | FORMAL PARTNERING | Material | Day |  | 8
3417-25565 | PROGRESS SCHEDULE BASELINE | Material | Lump Sum |  | 8
3417-25567 | PROGRESS SCHEDULE UPDATES | Material | Each |  | 8
3417-27022 | TOPSOIL CLASS B 2" | Material |  |  | 8
3417-27102 | REGULAR SEED | Material | LB |  | 8
3417-27103 | OVERSEEDING | Material | LB |  | 8
3417-27216 | NS FERTILIZER 15-30-15 | Material |  |  | 8
3417-27250 | LIME | Material |  |  | 8
3417-27321 | ROLLED EROSION CTRL EC-2 TYPE 4 | Material | Square Yard |  | 8
3417-27325 | ROLLED EROSION CTRL PRODUCT EC-3 TYPE 1 | Material | Square Yard |  | 8
3417-27327 | ROLLED EROSION CTRL PRODUCT EC-3 TYPE 3 | Material | Square Yard |  | 8
3417-27410 | CHECK DAM, ROCK TY. I | Material | Each |  | 8
3417-27415 | CHECK DAM(ROCK) TY. II | Material | Each |  | 8
3417-27430 | SILTATION CONTROL EXCAVATION | Material | Cubic Yard |  | 8
3417-27440 | MOWING | Material | Hour |  | 8
3417-27451 | INLET PROTECTION , TYPE A | Material | Each |  | 8
3417-27461 | INLET PROTECTION , TYPE B | Material | Each |  | 8
3417-27504 | TEMP. SILT FENCE TYPE B | Material | Linear Feet |  | 8
3417-27505 | TEMP. SILT FENCE TYPE A TYPE A | Material | Linear Feet |  | 8
3417-27526 | TURBIDITY CURTAIN, IMPERVIOUS | Material | Linear Feet |  | 8
3417-27545 | STORM WATER MAN. BASIN EXCAV. | Material | Cubic Yard |  | 8
3417-27550 | STORM WATER MAN.DRAIN.STR.SWM | Material | Linear Feet |  | 8
3417-27551 | NS SWM DR. STR. SWM STR. | Material | Linear Feet |  | 8
3417-27600 | CLOSING WELL | Material | Each |  | 8
3417-38900-3010 | NS PLANT OR TREE BLUE FLAG 2" PLUG | Material | Each |  | 8
3417-38900-3020 | NS PLANT OR TREE HARDSTEM BULRUSH 2" PLUG | Material | Each |  | 8
3417-38900-3030 | NS PLANT OR TREE PICKEREL WEED 2" PLUG | Material | Each |  | 8
3417-38900-3040 | NS PLANT OR TREE TUSSOCK SEDGE 2" PLUG | Material | Each |  | 8
3417-39004 | NS SEED MIXTURE STREAM RELOCATION | Material | LB |  | 8
3417-40002 | 3/4" WATER SERVICE LINE | Material | Linear Feet |  | 8
3417-40003 | 1" WATER SERVICE LINE | Material | Linear Feet |  | 8
3417-40005 | 1 1/2" WATER SERVICE LINE | Material | Linear Feet |  | 8
3417-40006 | 2" WATER SERVICE LINE | Material | Linear Feet |  | 8
3417-40041 | 4" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40061 | 6" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40081 | 8" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40101 | 10" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40121 | 12" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40161 | 16" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40300 | 30" WATER MAIN | Material | Linear Feet |  | 8
3417-40360 | 36" WATER MAIN (TEMP. BYPASS MAIN) | Material | Linear Feet |  | 8
3417-40365 | 42" DI WATER MAIN | Material | Linear Feet |  | 8
3417-40385 | NS MINOR STRUCTURE EXCAV. ... | Material | Cubic Yard |  | 8
3417-40406 | 16" BEND | Material | Each |  | 8
3417-40414 | 30" BEND | Material | Each |  | 8
3417-40417 | 42" BEND | Material | Each |  | 8
3417-40422 | 16" BRANCH | Material | Each |  | 8
3417-40908 | 8" OFFSET EXIST. PIPE | Material | Linear Feet |  | 8
3417-40992-3250 | NS WATER UTILITY 1 1/2" WATER METER VAULT | Material | Each |  | 8
3417-40992-3260 | NS WATER UTILITY 3" WATER METER & VAULT | Material | Each |  | 8
3417-40992-3270 | NS WATER UTILITY 3/4" WATER METER BOX & YOKE | Material | Each |  | 8
3417-40992-3280 | NS WATER UTILITY 30" PVC x PCCP ADAPTER | Material | Each |  | 8
3417-40992-3290 | NS WATER UTILITY 4" WATER METER & VAULT | Material | Each |  | 8
3417-40992-3300 | NS WATER UTILITY 42" DI x PCCP ADAPTER | Material | Each |  | 8
3417-40992-3310 | NS WATER UTILITY 42" LINE STOP | Material | Each |  | 8
3417-40992-3320 | NS WATER UTILITY 8" FLAP VALVE | Material | Each |  | 8
3417-40992-3330 | NS WATER UTILITY ADJUST EXIST. WATER METER VAULT | Material | Each |  | 8
3417-40992-3340 | NS WATER UTILITY DETECTOR CHECK & VAULT | Material | Each |  | 8
3417-40992-3350 | NS WATER UTILITY RELOCATE SIAMESE CONNECTION | Material | Each |  | 8
3417-41006 | 6" GATE VALVE & BOX | Material | Each |  | 8
3417-41008 | 8" GATE VALVE & BOX | Material | Each |  | 8
3417-41010 | 10" GATE VALVE & BOX | Material | Each |  | 8
3417-41012 | 12" GATE VALVE & BOX | Material | Each |  | 8
3417-41018 | 16" BUTTERFLY VALVE & BOX | Material | Each |  | 8
3417-41104 | ADJUST EXIST. VALVE BOX | Material | Each |  | 8
3417-41398 | 8" X 6" TAP.SLEEVE VALVE & BOX | Material | Each |  | 8
3417-41400 | 12"X6" TAPPING SLEEVE VALVE & BOX | Material | Each |  | 8
3417-41820 | FIRE HYDRANT | Material | Each |  | 8
3417-41850 | ADJUST EXIST. AIR RELEASE VALVE BOX | Material | Each |  | 8
3417-41968 | 1" WATER METER BOX & YOKE | Material | Each |  | 8
3417-41970 | 5/8" WATER METER & BOX | Material | Each |  | 8
3417-41972 | 1" WATER METER & BOX | Material | Each |  | 8
3417-41977 | ADJUST EXIST. WATER METER BOX | Material | Each |  | 8
3417-42044 | 4" SANITARY SERVICE LATERAL CONNECTION | Material | Linear Feet |  | 8
3417-42080 | 8" SAN. SEWER PIPE | Material | Linear Feet |  | 8
3417-42082 | 8" DI SANITARY SEWER PIPE | Material | Linear Feet |  | 8
3417-42087 | 8" SANITARY SEWER FORCE MAIN | Material | Linear Feet |  | 8
3417-42242 | 24" DI SANITARY SEWER PIPE | Material | Linear Feet |  | 8
3417-42247 | 24" SANITARY SEWER FORCE MAIN | Material | Linear Feet |  | 8
3417-42367 | 36" SANITARY SEWER FORCE MAIN | Material | Linear Feet |  | 8
3417-42487 | 48" SANITARY SEWER FORCE MAIN | Material | Linear Feet |  | 8
3417-42493 | 24" BEND FORCE MAIN 11-1/4 degrees | Material | Each |  | 8
3417-42496 | 36" BEND FORCE MAIN 45 degrees | Material | Each |  | 8
3417-42498 | 48" BEND FORCE MAIN 22.5 degrees | Material | Each |  | 8
3417-42513 | 24" PLUG OR CAP FORCE MAIN | Material | Each |  | 8
3417-42635 | ADJUST EXISTING VALVE BOX-FORCE MAIN | Material | Each |  | 8
3417-42755 | SANITARY SEWER MANHOLE | Material | Linear Feet |  | 8
3417-42764 | MANHOLE FRAME & COVER F&C-1 | Material | Each |  | 8
3417-42765 | ADJUST EXIST FRAME & COVER | Material | Each |  | 8
3417-42771 | RECONSTRUCT EXISTING SANITARY MANHOLE | Material | Linear Feet |  | 8
3417-42788 | 2" AIR RELEASE VALVE & BOX FORCE MAIN | Material | Each |  | 8
3417-42845 | 4" SEWER CLEANOUT | Material | Each |  | 8
3417-44208 | 8" OFFSET EXIST. PIPE FORCE MAIN | Material | Linear Feet |  | 8
3417-44301 | NS SEWER UTILITY 8" SEWER CLEANOUT | Material | Each |  | 8
3417-45500 | LEAK DETECTOR | Material | Each |  | 8
3417-45602 | 36" STEEL ENCASE. PIPE | Material | Linear Feet |  | 8
3417-45604 | 36" JACKED STEEL ENCASEMENT PIPE | Material | Linear Feet |  | 8
3417-45622 | 48" STEEL ENCASE. PIPE | Material | Linear Feet |  | 8
3417-49000 | NS SANITARY SEWER 8" SANITARY SEWER REHABILITATION | Material | Each |  | 8
3417-49001-3780 | NS SANITARY SEWER 24" LINE STOP, W/O BYPASS | Material | Each |  | 8
3417-49001-3790 | NS SANITARY SEWER 24" SOLID SLEEVE FORCE MAIN | Material | Each |  | 8
3417-49001-3800 | NS SANITARY SEWER 48" LINE STOP, W/ 36" BYPASS | Material | Each |  | 8
3417-49001-3810 | NS SANITARY SEWER 48" SOLID SLEEVE FORCE MAIN | Material | Each |  | 8
3417-49001-3820 | NS SANITARY SEWER 48"x36" TAPPING SLEEVE, VALVE & | Material | Each |  | 8
3417-50108 | SIGN PANEL | Material | Square Feet |  | 8
3417-50110 | OVERLAY SIGN PANEL | Material | Square Feet |  | 8
3417-50402 | VA SIGN POST, S3 x 5.7 | Material | Linear Feet |  | 8
3417-50404 | VA SIGN POST, W4 x 13 | Material | Linear Feet |  | 8
3417-50406 | VA SIGN POST, W6 x 12 | Material | Linear Feet |  | 8
3417-50412 | VIA SIGN POST, W12 X 16 | Material | Linear Feet |  | 8
3417-50430 | SIGN POST STP-1, 2", 14 GAUGE | Material | Linear Feet |  | 8
3417-50432 | SIGN POST STP-1, 2 3/16", 10 GAUGE | Material | Linear Feet |  | 8
3417-50434 | SIGN POST STP-1, 2 1/2", 10 GAUGE | Material | Linear Feet |  | 8
3417-50436 | SIGN POST STP-1, 2 1/2", 12 GAUGE | Material | Linear Feet |  | 8
3417-50485 | CONC. FDN. STP-1 TY.A | Material | Each |  | 8
3417-50486 | CONC. FDN. STP-1 TY.B | Material | Each |  | 8
3417-50500 | CONC.FOUND.SSP-V A 1' DIA.X 3' DEPTH | Material | Each |  | 8
3417-50501 | CONC.FDN.SSP-V A 2'6" DIA.X 7' DEPTH | Material | Each |  | 8
3417-50502 | CONC.FOUND.SSP-V A 1'9" DIA.X 4'6" D | Material | Each |  | 8
3417-50528 | CONC.FOUND.SSP-VI A 3'0" DIA.X 7' DE | Material | Each |  | 8
3417-50575 | CONC.FOUND.O/H SIGN STRUCTURE | Material | Cubic Yard |  | 8
3417-50902-3980 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.1 | Material | Each |  | 8
3417-50902-3990 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.10 | Material | Each |  | 8
3417-50902-4000 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.11 | Material | Each |  | 8
3417-50902-4010 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.2 | Material | Each |  | 8
3417-50902-4020 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.3 | Material | Each |  | 8
3417-50902-4030 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.4 | Material | Each |  | 8
3417-50902-4040 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.5 | Material | Each |  | 8
3417-50902-4050 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.6 | Material | Each |  | 8
3417-50902-4060 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.7 | Material | Each |  | 8
3417-50902-4070 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.8 | Material | Each |  | 8
3417-50902-4080 | NS TRAFFIC SIGN O/H SIGN STRUCTURE LOCATION NO.9 | Material | Each |  | 8
3417-51183 | TRAF.SIG.HEAD SECT.12" SEL.VIEW | Material | Each |  | 8
3417-51184 | TRAF. SIG. HEAD SEC 12" LED | Material | Each |  | 8
3417-51198 | PEDESTRIAN ACTUATION PA-2 | Material | Each |  | 8
3417-51210 | PEDESTAL POLE PF-2 10' | Material | Each |  | 8
3417-51238 | CONC. FOUND. SIGNAL POLE PF-8 | Material | Cubic Yard |  | 8
3417-51240 | CONC. FOUNDATION PF-2 | Material | Each |  | 8
3417-51246 | CONCRETE FOUND. CF-2 | Material | Each |  | 8
3417-51247 | CONCRETE FOUND. CF-3 | Material | Each |  | 8
3417-51248 | CONCRETE FOUNDATION CF-4 | Material | Each |  | 8
3417-51260 | NS CONCRETE FOUNDATION CAMERA POLE | Material | Cubic Yard |  | 8
3417-51425 | NS SIGNAL POLE PEDESTAL POLE PF-2 15' | Material | Each |  | 8
3417-51426 | NS MAST ARM MAST ARM 35' | Material | Each |  | 8
3417-51476 | SIGNAL POLE MP-3, TY. B1 | Material | Each |  | 8
3417-51480 | SIGNAL POLE MP-3, TY. E1 | Material | Each |  | 8
3417-51482 | SIGNAL POLE MP-3, TY. F | Material | Each |  | 8
3417-51486 | MAST ARM 40' | Material | Each |  | 8
3417-51487 | MAST ARM 49' | Material | Each |  | 8
3417-51488 | MAST ARM 60' | Material | Each |  | 8
3417-51489 | MAST ARM 65' | Material | Each |  | 8
3417-51490 | MAST ARM 70' | Material | Each |  | 8
3417-51601 | 14/3 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-51603 | 14/5 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-51614-4320 | NS CONDUCTOR CABLE CABLE CCTV CABLE - N | Material | Linear Feet |  | 8
3417-51614-4330 | NS CONDUCTOR CABLE DMX CABLE | Material | Linear Feet |  | 8
3417-51614-4340 | NS CONDUCTOR CABLE NO. 00 EGC | Material | Linear Feet |  | 8
3417-51614-4350 | NS CONDUCTOR CABLE NO. 1 EGC | Material | Linear Feet |  | 8
3417-51614-4360 | NS CONDUCTOR CABLE NO. 2 EGC | Material | Linear Feet |  | 8
3417-51614-4370 | NS CONDUCTOR CABLE NO. 4 EGC | Material | Linear Feet |  | 8
3417-51614-4380 | NS CONDUCTOR CABLE NO. 6 EGC | Material | Linear Feet |  | 8
3417-51830 | HANGER ASSEMBLY SM-3, ONE WAY | Material | Each |  | 8
3417-51834 | HANGER ASSEMBLY SMB-2, ONE WAY | Material | Each |  | 8
3417-51838 | HANGER ASSM.SMB-3, ONE WAY | Material | Each |  | 8
3417-51911 | NS SAW CUT ASPHALT CONCRETE (FULL DEPTH) | Material | Linear Feet |  | 8
3417-51955 | NS TEMP. TRAFFIC CONTROL SIGNAL NEWTOWN ROAD | Material | Lump Sum |  | 8
3417-51955-4440 | NS TEMP. TRAFFIC CONTROL SIGNAL WITCHDUCK ROAD | Material | Lump Sum |  | 8
3417-51963-4450 | NS REMOVE & DIS. O/H STR. TY. BM | Material | Each |  | 8
3417-51963-4460 | NS REMOVE ,DISPOSE SIGN TY.SP-2 FROM O/H STR. | Material | Each |  | 8
3417-51963-4470 | NS REMOVE ,DISPOSE SIGN TY.SP-3 FROM O/H STR | Material | Each |  | 8
3417-51963-4480 | NS REMOVE -DISPOSE SIGN STRUCT. TY. I | Material | Each |  | 8
3417-51963-4490 | NS REMOVE -DISPOSE SIGN STRUCT. TY. V A | Material | Each |  | 8
3417-51963-4500 | NS REMOVE -DISPOSE SIGN STRUCT. TY. VI A | Material | Each |  | 8
3417-51963-4510 | NS REMOVE -DISPOSE SIGN STRUCT. TY. WP-1 | Material | Each |  | 8
3417-51963-4520 | NS REMOVE -DISPOSE SIGN STRUCT. TY. WP-2 | Material | Each |  | 8
3417-51965 | NS INSTALL WELCOME SIGN | Material | Lump Sum |  | 8
3417-52001-4540 | NS TRAFFIC SIGNALIZATION EMERGENCY PREEMPTION DETE | Material | Linear Feet |  | 8
3417-52001-4550 | NS TRAFFIC SIGNALIZATION EMERGENCY PREEMPTION DETE | Material | Linear Feet |  | 8
3417-52001-4560 | NS TRAFFIC SIGNALIZATION VIDEO DETECTION CABLE - N | Material | Linear Feet |  | 8
3417-52001-4570 | NS TRAFFIC SIGNALIZATION VIDEO DETECTION CABLE - V | Material | Linear Feet |  | 8
3417-52002-4580 | NS TRAFFIC SIGNALIZATION CCTV CAMERA - N | Material | Each |  | 8
3417-52002-4590 | NS TRAFFIC SIGNALIZATION CONTROLLER TYPE A | Material | Each |  | 8
3417-52002-4600 | NS TRAFFIC SIGNALIZATION CONTROLLER TYPE B | Material | Each |  | 8
3417-52002-4610 | NS TRAFFIC SIGNALIZATION EMERGENCY PREEMPTION 4-WA | Material | Each |  | 8
3417-52002-4620 | NS TRAFFIC SIGNALIZATION EMERGENCY PREEMPTION 4-WA | Material | Each |  | 8
3417-52002-4630 | NS TRAFFIC SIGNALIZATION UNINTERRUPTABLE POWER SUP | Material | Each |  | 8
3417-52002-4640 | NS TRAFFIC SIGNALIZATION UNINTERRUPTABLE POWER SUP | Material | Each |  | 8
3417-52002-4650 | NS TRAFFIC SIGNALIZATION VIDEO DETECTION SYSTEM - | Material | Each |  | 8
3417-52002-4660 | NS TRAFFIC SIGNALIZATION VIDEO DETECTION SYSTEM - | Material | Each |  | 8
3417-52403 | PEDESTRIAN SIGNAL HEAD SP-8 | Material | Each |  | 8
3417-52425 | ELECTRICAL SERVICE SE-3 TYPE B | Material | Each |  | 8
3417-54032 | TYPE B CLASS I PVMT LINE MRKG 4" | Material | Linear Feet |  | 8
3417-54034 | TY B CL I PVMT LINE MRKG 6" | Material | Linear Feet |  | 8
3417-54037 | TYPE B CLASS I PVMT LINE MRKG 8" | Material | Linear Feet |  | 8
3417-54040 | TY B CL I PVMT LINE MRKG 12" | Material | Linear Feet |  | 8
3417-54042 | TY.B CL.I PAVE. LINE MARK. 24" | Material | Linear Feet |  | 8
3417-54076 | TY.B CL.VI PVMT LINE MRKG 6" | Material | Linear Feet |  | 8
3417-54077 | TY.B CL.VI PVMT LINE MRKG 8" | Material | Linear Feet |  | 8
3417-54078 | TY.B CL.VI PVMT LINE MRKG12" | Material | Linear Feet |  | 8
3417-54100-4770 | NS PAVEMENT MARKING TMP. PVMT MRKG, TY. A, 6" | Material | Linear Feet |  | 8
3417-54100-4780 | NS PAVEMENT MARKING TYPE B CLASS VI PVMT LINE MRKG | Material | Linear Feet |  | 8
3417-54101 | NS PAVEMENT MARKING YIELD AHEAD TRIANGLE SMALL TY | Material | Each |  | 8
3417-54105 | ERADICATION OF EX. LINEAR PVMT MRKG | Material | Linear Feet |  | 8
3417-54106 | ERAD. OF EXIST.NONLINEAR PVMT MRKG | Material | Square Feet |  | 8
3417-54217 | SNOW PLOW.RAISED PAVE.MARK.ASPH.CONC | Material | Each |  | 8
3417-54242 | TEMP. PAVE. MARKER 2 WAY | Material | Each |  | 8
3417-54260 | PVMT MESSAGE, 8', CHARACTER, TY. A | Material | Each |  | 8
3417-54261 | PVMT MESSAGE, 8', CHARACTER TY. B,CL.I | Material | Each |  | 8
3417-54402-4860 | NS PAVE. MESSAGE MARKING (HOV DIAMOND, ASPH. SURFA | Material | Each |  | 8
3417-54402-4870 | NS PAVE. MESSAGE MARKING (LANE REDUCTION ARROW) TY | Material | Each |  | 8
3417-54428 | TEMP. PVMT MRKG, TY. A, 4" | Material | Linear Feet |  | 8
3417-54432 | TEMP. PVMT MRKG, TY. A, 8" | Material | Linear Feet |  | 8
3417-54436 | TEMP. PVMT MRKG, TY. A, 12" | Material | Linear Feet |  | 8
3417-54440 | TEMP. PVMT MRKG, TY. A, 24" | Material | Linear Feet |  | 8
3417-54570 | (THRU ARROW) TY A | Material | Each |  | 8
3417-54571 | (THRU ARROW) TY B, CL I | Material | Each |  | 8
3417-54573 | (SGL TURN ARROW) TY A | Material | Each |  | 8
3417-54574 | (SGL TURN ARROW) TY B, CL I | Material | Each |  | 8
3417-54576 | (DBL TURN ARROW THRU/LT OR RT) TY A | Material | Each |  | 8
3417-54577 | DBL TURN ARR.THRU/LT OR RT TY B, CL I | Material | Each |  | 8
3417-54588 | (LANE REDUCTION ARROW) TY A | Material | Each |  | 8
3417-54589 | (LANE REDUCTION ARROW) TY B, CL I | Material | Each |  | 8
3417-54597 | (FISH HOOK, LEFT) TY B, C | Material | Each |  | 8
3417-54601 | (FISH HOOK, LEFT/THRU) TY B, CL I | Material | Each |  | 8
3417-54621 | (YIELD 1?x1.5?) TY B, CL I | Material | Each |  | 8
3417-55000 | 00 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55010 | 1 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55020 | 2 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55040 | 4 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55060 | 6 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55080 | 8 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55100 | 10 CONDUCTOR CABLE | Material | Linear Feet |  | 8
3417-55126 | CONDUCTOR CABLE, NO. 8 EGC | Material | Each |  | 8
3417-55140 | CONCRETE FOUNDATION LF-1 TY. A | Material | Each |  | 8
3417-55189 | LIGHTING POLE LP-2 TYPE E | Material | Each |  | 8
3417-55191 | LIGHTING POLE LP-2 TYPE G | Material | Each |  | 8
3417-55193 | LIGHTING POLE LP-2 TYPE I | Material | Each |  | 8
3417-55348 | ELECT. SERVICE SE-9 TYPE A | Material | Each |  | 8
3417-55353 | CONTROL CENTER CCW-1 TYPE D | Material | Linear Feet |  | 8
3417-55586 | JUNCTION BOX JB-S1 | Material | Linear Feet |  | 8
3417-55587 | JUNCTION BOX JB-S2 | Material | Linear Feet |  | 8
3417-55588 | JUNCTION BOX JB-S3 | Material | Linear Feet |  | 8
3417-56014 | ELECT. SER. GRD. ELECTRODE(10') | Material | Linear Feet |  | 8
3417-56042-5220 | NS CONDUIT (2.5" PVC) | Material | Linear Feet |  | 8
3417-56042-5230 | NS CONDUIT 2.5" BORED | Material | Linear Feet |  | 8
3417-56050 | BORED CONDUIT 2" | Material |  |  | 8
3417-56051 | BORED CONDUIT 3" | Material | Linear Feet |  | 8
3417-56052 | BORED CONDUIT 4" | Material | Linear Feet |  | 8
3417-56053 | 2" PVC CONDUIT | Material | Linear Feet |  | 8
3417-56054 | 3" PVC CONDUIT | Material | Linear Feet |  | 8
3417-56055 | 4" PVC CONDUIT | Material | Linear Feet |  | 8
3417-56200 | TRENCH EXCAVATION ECI-1 | Material | Linear Feet |  | 8
3417-57010 | ITS CONTROLLER CABINET (GROUND MOUNTED) ITS CONTRO | Material | Each |  | 8
3417-57050 | UNINTERRUPTIBLE POWER SUPPLY ITS-CC UNITERRUPTABLE | Material | Each |  | 8
3417-57060 | CCTV CAMERA (DIGITAL) CCTV CAMERA (DIGITAL) | Material | Each |  | 8
3417-57080 | NS CCTV COMPOSITE CABLE DIGITAL | Material | Linear Feet |  | 8
3417-57093 | CCTV CAMERA POLE (60') W/ LOWER DEVICE CAMERA POLE | Material | Each |  | 8
3417-57100 | DYNAMIC MSG. SIGN (TYPE 1) (FULL COLOR) DYNAMIC ME | Material | Each |  | 8
3417-57140 | DMS COMMUNICATION CABLE DMS COMMUNICATION CABLE | Material | Linear Feet |  | 8
3417-57165 | VDS COMPOSITE CABLE | Material | Linear Feet |  | 8
3417-57203 | FIBER OPTIC DROP CABLE (12 STRAND) FIBER OPTIC CAB | Material | Linear Feet |  | 8
3417-57221 | MANAGED FIELD ETHERNET SWITCH (Gbps) MANAGED FIELD | Material | Each |  | 8
3417-57227 | DIST.SFP MODULE(1Gbps, LC, SHORT HAUL) DISTRIBUTIO | Material | Each |  | 8
3417-57352 | BORED ITS CONDUIT HDPE 3" BORED ITS CONDUIT, 3" | Material | Linear Feet |  | 8
3417-57361 | ITS CONDUIT HDPE 2" ITS CONDUIT, 2" | Material | Linear Feet |  | 8
3417-59000-5440 | NS LIGHTING CABINET ELECTRICAL SERVICE, 10KVA | Material | Each |  | 8
3417-59000-5450 | NS LIGHTING CABINET ELECTRICAL SERVICE, 15KVA | Material | Each |  | 8
3417-59000-5460 | NS LIGHTING CABINET ELECTRICAL SERVICE, 20KVA | Material | Each |  | 8
3417-59000-5470 | NS LIGHTING CABINET ELECTRICAL SERVICE, 5KVA | Material | Each |  | 8
3417-59000-5480 | NS LIGHTING ELECTRICAL SERVICE CABINET | Material | Each |  | 8
3417-59000-5490 | NS LIGHTING ELECTRICAL SERVICE SE-9 TYPE A MODIFIE | Material | Each |  | 8
3417-59000-5500 | NS LIGHTING FOUNDATION GROUNDING ELECTRODE (10') | Material | Each |  | 8
3417-59000-5510 | NS LIGHTING HIGH MAST LUM. ASSEM. 4-500 WATT LED | Material | Each |  | 8
3417-59000-5520 | NS LIGHTING HIGH MAST LUM. ASSEM. 6-500 WATT LED | Material | Each |  | 8
3417-59000-5530 | NS LIGHTING HIGH MAST LUM. ASSEM. 8-500 WATT LED | Material | Each |  | 8
3417-59000-5540 | NS LIGHTING LUMIN. 150 WATT LED OFFSET | Material | Each |  | 8
3417-59000-5550 | NS LIGHTING LUMIN. 250 WATT LED OFFSET | Material | Each |  | 8
3417-59000-5560 | NS LIGHTING LUMIN. 400 WATT LED OFFSET | Material | Each |  | 8
3417-59000-5570 | NS LIGHTING LUMINAIRE ARM - 12' | Material | Each |  | 8
3417-59000-5580 | NS LIGHTING MODIFIED TEST BORE | Material | Each |  | 8
3417-59000-5590 | NS LIGHTING POLE LP-3, TYPE 7, 130-FT | Material | Each |  | 8
3417-59000-5600 | NS LIGHTING STEP-DOWN TRANSFORMER | Material | Each |  | 8
3417-59000-5610 | NS LIGHTING STEP-UP TRANSFORMER | Material | Each |  | 8
3417-59003-5620 | NS LIGHTING TEMPORARY ROADWAY LIGHTING | Material | Lump Sum |  | 8
3417-59003-5630 | NS LIGHTING U/B LIGHTING SYSTEM, GREENWICH RD/I-26 | Material | Lump Sum |  | 8
3417-59003-5640 | NS LIGHTING U/B LIGHTING SYSTEM, GREENWICH RD/I-26 | Material | Lump Sum |  | 8
3417-59003-5650 | NS LIGHTING U/B LIGHTING SYSTEM, NEWTOWN RD | Material | Lump Sum |  | 8
3417-59003-5660 | NS LIGHTING U/B LIGHTING SYSTEM, WITCHDUCK RD | Material | Lump Sum |  | 8
3417-59050-5670 | NS COMMUNICATION EQUIP. JUNCTION BOX, JB-S5 | Material | Each |  | 8
3417-59050-5680 | NS COMMUNICATION EQUIP. MANAGED FIELD ETHERNET SWI | Material | Each |  | 8
3417-59050-5690 | NS COMMUNICATION EQUIP. MANAGED FIELD ETHERNET SWI | Material | Each |  | 8
3417-59050-5700 | NS COMMUNICATION EQUIP. PRE-TERMINATED FIBER PATCH | Material | Each |  | 8
3417-59050-5710 | NS COMMUNICATION EQUIP. PRE-TERMINATED FIBER PATCH | Material | Each |  | 8
3417-59050-5720 | NS COMMUNICATION EQUIP. UNDERGROUND SPLICE ENCLOSU | Material | Each |  | 8
3417-59050-5730 | NS COMMUNICATION EQUIP. UNDERGROUND SPLICE ENCLOSU | Material | Each |  | 8
3417-59050-5740 | NS COMMUNICATION EQUIP. UNDERGROUND SPLICE ENCLOSU | Material | Each |  | 8
3417-59050-5750 | NS COMMUNICATION EQUIP. UNDERGROUND SPLICE ENCLOSU | Material | Each |  | 8
3417-59050-5760 | NS COMMUNICATION EQUIP. UNITERRUPTABLE POWER SUPPL | Material | Each |  | 8
3417-59071-5770 | NS COMMUNICATION EQUIP. FIBER OPTIC CABLE 96F SMFO | Material | Linear Feet |  | 8
3417-59071-5780 | NS COMMUNICATION EQUIP. RELOCATE EXISTING FIBER OP | Material | Linear Feet |  | 8
3417-59071-5790 | NS COMMUNICATION EQUIP. TRENCH EXCAVATION, ECI-ITS | Material | Linear Feet |  | 8
3417-60120 | STRUCTURE EXCAVATION | Material | Cubic Yard |  | 8
3417-60125-5810 | NS BRIDGE PIER PROTECTION BPPS "A" | Material | Lump Sum |  | 8
3417-60125-5820 | NS BRIDGE PIER PROTECTION BPPS "B" | Material | Lump Sum |  | 8
3417-60125-5830 | NS BRIDGE PIER PROTECTION BPPS "C" | Material | Lump Sum |  | 8
3417-60125-5840 | NS BRIDGE PIER PROTECTION BPPS "D" | Material | Lump Sum |  | 8
3417-60125-5850 | NS BRIDGE PIER PROTECTION BPPS "E" | Material | Lump Sum |  | 8
3417-60200 | STEEL SHEET PILING | Material | Square Feet |  | 8
3417-60403 | CONCRETE CLASS A3 | Material | Cubic Yard |  | 8
3417-60404 | CONCRETE CLASS A4 | Material | Cubic Yard |  | 8
3417-60409 | CONC. CLASS A4 MOD. LOW SHRINKAGE | Material | Cubic Yard |  | 8
3417-60450 | CONC. CL. A4 BRIDGE APPR. SLAB | Material | Cubic Yard |  | 8
3417-60452 | REINF. STEEL BRIDGE APPR. SLAB | Material | LB |  | 8
3417-60490 | BRIDGE DECK GROOVING | Material | Square Yard |  | 8
3417-60495 | COVER DEPTH SURVEY | Material | Square Yard |  | 8
3417-61267 | BEAM,BULB-T 77" DEPTH +120'-130' | Material | Each |  | 8
3417-61269 | PREST.CONC.BEAM,BULB-T77"DEPTH+140'-150' | Material | Each |  | 8
3417-61700 | REINF. STEEL | Material | LB |  | 8
3417-61711 | CORROSION RESISTANT REINF.STEEL CL. I | Material | LB |  | 8
3417-61713 | CORROSION RESISTANT REINF.STEEL CL. III | Material | LB |  | 8
3417-61755 | NS COATING OF NEW METAL ON STRUCTURES STR. NO. 183 | Material | Lump Sum |  | 8
3417-61980 | BEARING DEVICE | Material | LB |  | 8
3417-62000-6010 | NS PARAPET CONCRETE W/ ARCH. TREAT. (B603) | Material | Linear Feet |  | 8
3417-62000-6020 | NS PARAPET CONCRETE, 32" | Material | Linear Feet |  | 8
3417-62000-6023 | NS PARAPET CONCRETE W/ ARCH. TREAT. (MSE WALLS) | Material | Linear Feet |  | 8
3417-62010 | CONCRETE PARAPET | Material | Linear Feet |  | 8
3417-62021-6034 | NS RAILING BR27D 3 RAILS W/ ARCH. TREAT. (B603) | Material | Linear Feet |  | 8
3417-62021-6035 | NS RAILING BR27D 4 RAILS W/ ARCH. TREAT. (B603) | Material | Linear Feet |  | 8
3417-62021-6036 | NS RAILING BR27D 3 RAILS W/ ARCH. TREAT. (B621) | Material | Linear Feet |  | 8
3417-62046 | RAILING, BR27D 3 RAILS | Material | Linear Feet |  | 8
3417-62402 | TOOTH EXP.JT. ASSEMBLY 2" | Material | Linear Feet |  | 8
3417-62536 | NS BRIDGE SUPERSTRUCTURE DECORATIVE STEEL PANELS | Material | Lump Sum |  | 8
3417-64011 | STRUCTURE EXCAVATION | Material | Cubic Yard |  | 8
3417-64015 | SELECT BACKFILL (ABUTMENT ZONE) | Material |  |  | 8
3417-64032 | GEOCOMPOSITE WALL DRAIN | Material | Square Yard |  | 8
3417-64036 | PIPE UNDERDRAIN 6" | Material | Linear Feet |  | 8
3417-64101 | DYNAMIC PILE TEST | Material | Each |  | 8
3417-64412 | PRESTR. CONC CARBON STL PILES 12" | Material | Linear Feet |  | 8
3417-64418 | PRESTR. CONC.CARBON STL STRAND PILES 18" | Material | Linear Feet |  | 8
3417-64424 | PRESTR.CONC. CARBON STL STRAND PILES 24" | Material | Linear Feet |  | 8
3417-64808 | DRIVING TEST FOR 12" PRESTR. CONC. PILE | Material | Linear Feet |  | 8
3417-64828 | DRIVING TEST FOR 18" PRESTR. CONC. PILE | Material | Linear Feet |  | 8
3417-64875 | NS PILE 42" PILE SLEEVE | Material | Linear Feet |  | 8
3417-65013 | CONCRETE CLASS A3 | Material | Cubic Yard |  | 8
3417-65014 | CONCRETE CLASS A4 | Material | Cubic Yard |  | 8
3417-65200 | REINF. STEEL | Material | LB |  | 8
3417-65211 | CORROSION RESISTANT REINF.STEEL CL. I | Material | LB |  | 8
3417-65700 | CONCRETE PARAPET | Material | Linear Feet |  | 8
3417-66720 | CONC. BLOCK SLOPE PROTECTION | Material | Square Yard |  | 8
3417-66740 | CONC. SLAB SLOPE PROTECTION 4" | Material | Square Yard |  | 8
3417-66921-6250 | NS BRIDGE SUBSTRUCTURE BACKWALL RECONSTRUCTION | Material | Linear Feet |  | 8
3417-66921-6259 | NS BRIDGE SUBSTRUCTURE PERMANENT CASING (4'-6") | Material | Linear Feet |  | 8
3417-66921-6260 | NS BRIDGE SUBSTRUCTURE STANDARD DRILLED SHAFTS EXC | Material | Linear Feet |  | 8
3417-66921-6270 | NS BRIDGE SUBSTRUCTURE STANDARD EXCAVATION DRILLE | Material | Linear Feet |  | 8
3417-66921-6280 | NS BRIDGE SUBSTRUCTURE STANDARD EXCAVATION DRILLED | Material | Linear Feet |  | 8
3417-66923 | NS BRIDGE SUBSTRUCTURE DRILLED SHAFT REINFORCING S | Material | LB |  | 8
3417-66924-6300 | NS BRIDGE SUBSTRUCTURE CROSSHOLE SONIC LOGGING (CS | Material | Each |  | 8
3417-66924-6310 | NS BRIDGE SUBSTRUCTURE THERMAL INTEGRITY PROFILING | Material | Each |  | 8
3417-66924-6320 | NS BRIDGE SUBSTRUCTURE THERMAL INTEGRITY PROFILING | Material | Each |  | 8
3417-67053 | NS CONC. SURFACE COLOR COATING CONCRETE SURFACE CO | Material | Lump Sum |  | 8
3417-67260-6340 | NS BRG. CONDUIT SYSTEM AESTHETIC LIGHTING BRIDGE C | Material | Lump Sum |  | 8
3417-67260-6350 | NS BRG. CONDUIT SYSTEM AESTHETIC LIGHTING BRIDGE C | Material | Lump Sum |  | 8
3417-67260-6360 | NS BRG. CONDUIT SYSTEM AESTHETIC LIGHTING BRIDGE C | Material | Lump Sum |  | 8
3417-67260-6370 | NS BRG. CONDUIT SYSTEM B621 | Material | Lump Sum |  | 8
3417-67260-6380 | NS BRG. CONDUIT SYSTEM CONDUIT SYSTEM | Material | Lump Sum |  | 8
3417-67260-6390 | NS BRG. CONDUIT SYSTEM WALL D | Material | Lump Sum |  | 8
3417-67260-6400 | NS BRG. CONDUIT SYSTEM WALL F | Material | Lump Sum |  | 8
3417-67260-6410 | NS BRG. CONDUIT SYSTEM WALL G | Material | Lump Sum |  | 8
3417-67260-6420 | NS BRG. CONDUIT SYSTEM WALL J | Material | Lump Sum |  | 8
3417-67270-6430 | NS BRG.LIGHTING SYSTEM AESTHETIC LIGHTING CONTROLS | Material | Lump Sum |  | 8
3417-67270-6440 | NS BRG.LIGHTING SYSTEM B603 AESTHETIC LUMINAIRES | Material | Lump Sum |  | 8
3417-67270-6450 | NS BRG.LIGHTING SYSTEM REMOVE EXISTING U/B LIGHTIN | Material | Lump Sum |  | 8
3417-67270-6460 | NS BRG.LIGHTING SYSTEM REMOVE EXISTING U/B LIGHTIN | Material | Lump Sum |  | 8
3417-67400 | DECK DRAINAGE SYSTEM | Material | Lump Sum |  | 8
3417-67904-6480 | NS BRIDGE INCIDENTALS CONSTRUCTION ACCESS (B603) | Material | Lump Sum |  | 8
3417-67904-6490 | NS BRIDGE INCIDENTALS CONSTRUCTION ACCESS (B621) | Material | Lump Sum |  | 8
3417-67904-6500 | NS BRIDGE INCIDENTALS INSPECT STRUCTURE (STR. NO. | Material | Lump Sum |  | 8
3417-68043 | CONC. CLASS A4 MOD.LOW SHRINKAGE | Material | Cubic Yard |  | 8
3417-68047 | CONCRETE PARAPET 42" | Material | Linear Feet |  | 8
3417-68091 | CORROSION RESISTANT REINF.STEEL CL. I | Material | LB |  | 8
3417-68108 | STR.STEEL PLATE GIRDER ASTM A709 GR. 50W | Material | Lump Sum |  | 8
3417-68170 | CRACK REPAIR TYPE A | Material | Linear Feet |  | 8
3417-68172 | CRACK REPAIR TYPE B | Material | Linear Feet |  | 8
3417-68174 | CRACK REPAIR TYPE C | Material | Linear Feet |  | 8
3417-68180 | EMBEDDED GALVANIC ANODES | Material | Each |  | 8
3417-68192 | REPLACE BEARING | Material | Each |  | 8
3417-68193 | RESET EXIST. ROCKER EXPN. BEARING | Material | Each |  | 8
3417-68200 | ULTRASONIC IMPACT TREATMENT | Material | Linear Feet |  | 8
3417-68226 | PARAPET CLOSURE TYPE B | Material | Each |  | 8
3417-68312 | H.E.S. PATCHING TYPE A | Material | Square Yard |  | 8
3417-68317 | NS TYPE A MILLING 3/4" | Material | Square Yard |  | 8
3417-68322 | H.E.S. PATCHING TYPE B | Material | Square Yard |  | 8
3417-68339 | DECK SLAB CLOSURE | Material | Square Yard |  | 8
3417-68472 | NS RECOAT EX. STR. (NO. 1832) | Material | Lump Sum |  | 8
3417-68474 | NS ENV. PROT. & HEALTH SAFETY STR. NO. 1832 | Material | Lump Sum |  | 8
3417-68476 | NS ENV.& WORKER PROTECT. STR. NO. 1832 | Material | Lump Sum |  | 8
3417-68490 | NS DISPOSAL OF MATERIAL STR. NO. 832 | Material | Lump Sum |  | 8
3417-68492 | NS MATERIAL DISPOSAL (STR. NO 1832, TYPE B) | Material | Lump Sum |  | 8
3417-68552 | ELASTOMERIC EXP. DAM 2+" TO 3" | Material | Linear Feet |  | 8
3417-68573 | EXPANSION JOINT RECONSTRUCTION (HES) | Material | Linear Feet |  | 8
3417-68575 | EXPANSION JOINT PREPARATION | Material | Linear Feet |  | 8
3417-68590 | JACKING AND BLOCKING BEAM | Material | Each |  | 8
3417-68616 | VERY EARLY MOD.CONC.OVERLAY | Material | Square Yard |  | 8
3417-68619 | NS FURNISH LATEX MOD.CONC. FURNISH VERY EARLY STRE | Material | Cubic Yard |  | 8
3417-68642 | TYPE A HYDRO-DEMOLITION 1/2" | Material | Square Yard |  | 8
3417-68900 | NS REM. PORT.OF EX.STR. REMOVE PORTION OF EXISTING | Material | Lump Sum |  | 8
3417-69007 | FLOWABLE BACKFILL | Material | Cubic Yard |  | 8
3417-69014 | SELECT BACKFILL (ABUTMENT ZONE) | Material |  |  | 8
3417-69427 | DYNAMIC PILE TEST (END BEARING PILES) | Material | Each |  | 8
3417-69430 | DRIVING TEST FOR 12" PRESTR. CONC. PILES | Material | Linear Feet |  | 8
3417-69442 | DRIVING TEST FOR 24" PRESTR. CONC. PILES | Material | Linear Feet |  | 8
3417-69500 | CONCRETE SUBSTRUCT. SURFACE REPAIR | Material | Square Yard |  | 8
3417-69627 | DRY RIPRAP CL. I 26" | Material |  |  | 8
3417-69815 | RECONSTRUCT BRIDGE SEAT TYPE A | Material | Each |  | 8
3417-69816 | RECONSTRUCT BRIDGE SEAT TYPE B | Material | Each |  | 8
3417-69817 | RECONSTRUCT BRIDGE SEAT TYPE C | Material | Each |  | 8
3417-70000-6900 | NS DEMO. OF BLDG. PARCEL 10, D43 | Material | Lump Sum |  | 8
3417-70000-6910 | NS DEMO. OF BLDG. PARCEL 10, D4 | Material | Lump Sum |  | 8
3417-70000-6920 | NS DEMO. OF BLDG. PARCEL 11, D25 | Material | Lump Sum |  | 8
3417-70000-6930 | NS DEMO. OF BLDG. PARCEL 11, D710 | Material | Lump Sum |  | 8
3417-70000-6940 | NS DEMO. OF BLDG. PARCEL 11, D711 | Material | Lump Sum |  | 8
3417-70000-6950 | NS DEMO. OF BLDG. PARCEL 12, D26 | Material | Lump Sum |  | 8
3417-70000-6970 | NS DEMO. OF BLDG. PARCEL 14, D14 | Material | Lump Sum |  | 8
3417-70000-6980 | NS DEMO. OF BLDG. PARCEL 14, D15 | Material | Lump Sum |  | 8
3417-70000-6990 | NS DEMO. OF BLDG. PARCEL 14, D29 | Material | Lump Sum |  | 8
3417-70000-7000 | NS DEMO. OF BLDG. PARCEL 14, D7 | Material | Lump Sum |  | 8
3417-70000-7010 | NS DEMO. OF BLDG. PARCEL 14, D712 | Material | Lump Sum |  | 8
3417-70000-7020 | NS DEMO. OF BLDG. PARCEL 14, D713 | Material | Lump Sum |  | 8
3417-70000-7030 | NS DEMO. OF BLDG. PARCEL 14, D8 | Material | Lump Sum |  | 8
3417-70000-7050 | NS DEMO. OF BLDG. PARCEL 25, D31 | Material | Lump Sum |  | 8
3417-70000-7100 | NS DEMO. OF BLDG. PARCEL 36, D717 | Material | Lump Sum |  | 8
3417-70000-7180 | NS DEMO. OF BLDG. PARCEL 37, D33 | Material | Lump Sum |  | 8
3417-70000-7190 | NS DEMO. OF BLDG. PARCEL 37, D715 | Material | Lump Sum |  | 8
3417-70000-7200 | NS DEMO. OF BLDG. PARCEL 37, D716 | Material | Lump Sum |  | 8
3417-70000-7210 | NS DEMO. OF BLDG. PARCEL 37, D718 | Material | Lump Sum |  | 8
3417-70000-7220 | NS DEMO. OF BLDG. PARCEL 37, D719 | Material | Lump Sum |  | 8
3417-70000-7270 | NS DEMO. OF BLDG. PARCEL 40, D730 | Material | Lump Sum |  | 8
3417-70000-7280 | NS DEMO. OF BLDG. PARCEL 42, D42 | Material | Lump Sum |  | 8
3417-70000-7290 | NS DEMO. OF BLDG. PARCEL 7, D1 | Material | Lump Sum |  | 8
3417-70000-7300 | NS DEMO. OF BLDG. PARCEL 7, D700 | Material | Lump Sum |  | 8
3417-70000-7320 | NS DEMO. OF BLDG. PARCEL 8, D2 | Material | Lump Sum |  | 8
3417-70000-7330 | NS DEMO. OF BLDG. PARCEL 8, D22 | Material | Lump Sum |  | 8
3417-70000-7340 | NS DEMO. OF BLDG. PARCEL 8, D23 | Material | Lump Sum |  | 8
3417-70000-7350 | NS DEMO. OF BLDG. PARCEL 8, D3 | Material | Lump Sum |  | 8
3417-70000-7360 | NS DEMO. OF BLDG. PARCEL 8, D503 | Material | Lump Sum |  | 8
3417-70000-7370 | NS DEMO. OF BLDG. PARCEL 8, D702 | Material | Lump Sum |  | 8
3417-70000-7380 | NS DEMO. OF BLDG. PARCEL 8, D703 | Material | Lump Sum |  | 8
3417-70000-7390 | NS DEMO. OF BLDG. PARCEL 8, D704 | Material | Lump Sum |  | 8
3417-70000-7400 | NS DEMO. OF BLDG. PARCEL 8, D705 | Material | Lump Sum |  | 8
3417-70000-7410 | NS DEMO. OF BLDG. PARCEL 8, D706 | Material | Lump Sum |  | 8
3417-70000-7420 | NS DEMO. OF BLDG. PARCEL 8, D707 | Material | Lump Sum |  | 8
3417-70000-7430 | NS DEMO. OF BLDG. PARCEL 9, D24 | Material | Lump Sum |  | 8
3417-70000-7440 | NS DEMO. OF BLDG. PARCEL 9, D708 | Material | Lump Sum |  | 8
3417-70000-7450 | NS DEMO. OF BLDG. PARCEL 9, D709 | Material | Lump Sum |  | 8
3417-70000-7460 | NS DEMO. OF BLDG. PARCEL13, D28 | Material | Lump Sum |  | 8
3417-70005-7470 | NS DEMOLITION WITH ACM PARCEL 009, D5 | Material | Lump Sum |  | 8
3417-70005-7475 | NS DEMOLITION WITH ACM PARCEL 013, D6 | Material | Lump Sum |  | 8
3417-70005-7480 | NS DEMOLITION WITH ACM PARCEL 016, D9 | Material | Lump Sum |  | 8
3417-70005-7490 | NS DEMOLITION WITH ACM PARCEL 036, D10 | Material | Lump Sum |  | 8
3417-70005-7500 | NS DEMOLITION WITH ACM PARCEL 037, D12 | Material | Lump Sum |  | 8
3417-70005-7510 | NS DEMOLITION WITH ACM PARCEL 12, D13 | Material | Lump Sum |  | 8
3417-70005-7520 | NS DEMOLITION WITH ACM PARCEL 35, D11 | Material | Lump Sum |  | 8
3417-70110 | FRIABLE ACM | Material | Square Feet |  | 8
3417-70112 | CAT II NF ACM | Material | Square Feet |  | 8
3417-70113 | CAT II NF ACM | Material | Linear Feet |  | 8
3417-70200-7560 | NS CLEARING OF PARCEL NO. 004 | Material | Lump Sum |  | 8
3417-70200-7570 | NS CLEARING OF PARCEL NO. 007 | Material | Lump Sum |  | 8
3417-70200-7580 | NS CLEARING OF PARCEL NO. 008 | Material | Lump Sum |  | 8
3417-70200-7590 | NS CLEARING OF PARCEL NO. 009 | Material | Lump Sum |  | 8
3417-70200-7600 | NS CLEARING OF PARCEL NO. 010 | Material | Lump Sum |  | 8
3417-70200-7610 | NS CLEARING OF PARCEL NO. 011 | Material | Lump Sum |  | 8
3417-70200-7620 | NS CLEARING OF PARCEL NO. 012 | Material | Lump Sum |  | 8
3417-70200-7630 | NS CLEARING OF PARCEL NO. 013 | Material | Lump Sum |  | 8
3417-70200-7640 | NS CLEARING OF PARCEL NO. 014 | Material | Lump Sum |  | 8
3417-70200-7650 | NS CLEARING OF PARCEL NO. 015 | Material | Lump Sum |  | 8
3417-70200-7660 | NS CLEARING OF PARCEL NO. 016 | Material | Lump Sum |  | 8
3417-70200-7670 | NS CLEARING OF PARCEL NO. 035 | Material | Lump Sum |  | 8
3417-70200-7680 | NS CLEARING OF PARCEL NO. 036 | Material | Lump Sum |  | 8
3417-70200-7690 | NS CLEARING OF PARCEL NO. 037 | Material | Lump Sum |  | 8
3417-70200-7700 | NS CLEARING OF PARCEL NO. 040 | Material | Lump Sum |  | 8
C00108424DB92.01.00110 | CLEARING AND GRUBBING | Material | Lump Sum |  | 8
C00108424DB92.01.00120 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
C00108424DB92.01.00134 | NS TEST PIT EXCAVATION-DIRT | Material | Each |  | 8
C00108424DB92.01.001341 | NS TEST PIT EXCAVATION-ASPHALT | Material | Each |  | 8
C00108424DB92.01.00270 | SELECT MATL. TY. I MIN. CBR-30 | Material |  |  | 8
C00108424DB92..01.00355 | GEOTEXTILE (SUBGRADE STAB.) | Material | Square Yard |  | 8
C00108424DB92.01.00588 | UNDERDRAIN UD-4 | Material | Linear Feet |  | 8
C00108424DB92.01.00595 | OUTLET PIPE | Material | Linear Feet |  | 8
C00108424DB92.01.00529 | FLOWABLE BACKFILL | Material | Cubic Yard |  | 8
C00108424DB92.01.00700 | POST INSTALLATION | Material | Linear Feet |  | 8
C00108424DB92.01.01152 | 15" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.01.01182 | 18" CONC. PIPE | Material | Linear Feet |  | 8
C00108424DB92.01.01302 | 30" CONC.PIPE | Material | Linear Feet |  | 8
C00108424DB92.01.06150 | 15" END SECTION ES-1 | Material | Each |  | 8
C00108424DB92.01.06300 | 30" END SECTION ES-1 | Material | Each |  | 8
C00108424DB92.01.07510 | DROP INLET DI-7 | Material | Each |  | 8
C00108424DB92.01.075101 | DRIP INLET DI-10H-L=14' | Material | Each |  | 8
C00108424DB92.01.09056 | MANHOLE MH-1 OR2 | Material | Linear Feet |  | 8
C00108424DB92.01.09057 | FRAME & COVER MH-1 | Material | Each |  | 8
C00108424DB92.01.09150 | EROS.CONTR.STONE.CL.I, EC-1 | Material |  |  | 8
C00108424DB92.01.02112 | STORM WATER MAN STR-SWM-1-L=7' | Material | Each |  | 8
C00108424DB92.01.10035 | CEM.STAB.SUBGRADE,6" | Material | Cubic Yard |  | 8
C00108424DB92.01.10013 | CEM.STAB.AGGR.MATL.NO.21A.6" | Material |  |  | 8
C00108424DB92.01.10610 | ASPHALT CONCRETE TY.IM-19.0A.2" | Material |  |  | 8
C00108424DB92.01.10628 | FLEXBLE PAVE.PLANING 0"-2" | Material | Square Yard |  | 8
C00108424DB92.01.10609 | ASPHALT CONCRETE TY.SM-12.5E,2" | Material |  |  | 8
C00108424DB92.01.10642 | ASPHALT CONCRETE TY.BM-25.0A,6" | Material |  |  | 8
C00108424DB92.01.11070 | NS SAW-CUT ASPH CONC 22" MAX DEPTH | Material | Linear Feet |  | 8
C00108424DB92.01.12020 | STD.CURB CG-2 | Material | Linear Feet |  | 8
C00108424DB92.01.13280 | GUARDRAIL GR-MGS1 | Material | Linear Feet |  | 8
C00108424DB92.01.13287 | GUARDRAIL TERMINAL GR-MGS3 | Material | Each |  | 8
C00108424DB92.01.13288 | GUARDRAIL HT.TRANS.GR-MGS-4 | Material | Each |  | 8
C00108424DB92.01.13392 | FIXED OBJECT ATTACH.GR-FOA-2 TY.1 | Material | Each |  | 8
C00108424DB92.01.13393 | FIXED OBJECT ATTACH.GR-FOA-2TY.II | Material | Each |  | 8
C00108424DB92.01.13462 | MEDIAN BARRIER MB-7F | Material | Linear Feet |  | 8
C00108424DB92.01.62710 | PIER PROTECTION, BPPS-1 | Material | Linear Feet |  | 8
C00108424DB92.01.13604 | IMPACT ATTEN.SER. TY.1(TL-3. 45 MPH) | Material | Each |  | 8
C00108424DB92.01.13605 | IMPACT ATTEN.SER. TY.1(TL-2. 45 MPH MAX) | Material | Each |  | 8
C00108424DB92.01.50009 | MAINTEANCE OF TRAFFIC (MOT) | Material | Lump Sum |  | 8
C00108424DB92.01.24160 | CONSTRUCTION SIGNS | Material | Square Feet |  | 8
C00108424DB92.01.24272 | TRUCK MOUNTED ATTENUATOR | Material | Hour |  | 8
C00108424DB92.01.24278 | GROUP 2 CHANNELIZING DEVICES | Material | Lump Sum |  | 8
C00108424DB92.01.24279 | PORT.CHANGEABLE.MESS.SIGN | Material | Hour |  | 8
C00108424DB92.01.24281 | ELECTRONIC ARROW | Material | Lump Sum |  | 8
C00108424DB92.01.24290 | TRAFFIC BARRIER SER.COMC.MB-7D PC | Material | Linear Feet |  | 8
C00108424DB92.01.24296 | TRAF.BARR.SER.CONC.SINGLE FACE (PINNED) | Material | Linear Feet |  | 8
C00108424DB92.01.24360 | NS SAFETY TOW WRECKER SERVICE | Material | Lump Sum |  | 8
C00108424DB92.01.24430 | DEMO. OF PAVEMENT (FLEXIBLE) | Material | Square Yard |  | 8
C00108424DB92.01.24501 | NS REMOVE EXIST. CONCRETE BARRIER | Material | Linear Feet |  | 8
C00108424DB92.01.24600 | REMOVE EXISTING GUARDRAIL | Material | Linear Feet |  | 8
C00108424DB92.01.24703 | NS REMOVE EXIST SOUND BARRIER WALL | Material | Linear Feet |  | 8
C00108424DB92.01.24831 | NS ADJUST EXIST DROP INLET | Material | Each |  | 8
C00108424DB92.01.25505 | FIELD OFFICE TY I | Material | Lump Sum |  | 8
C00108424DB92.01.27000 | SELECTIVE TREE REMOVAL TRIMMING AND CLEA | Material | Linear Feet |  | 8
C00108424DB92.01.27024 | TOPSOIL CLASS B-4" | Material | Square Yard |  | 8
C00108424DB92.01.27102 | REGULAR SEED | Material | LB |  | 8
C00108424DB92.01.27103 | OVERSEEDING | Material | LB |  | 8
C00108424DB92.01.27215 | FERTIZLIZER(15-30-15) | Material |  |  | 8
C00108424DB92.01.27250 | LIME | Material |  |  | 8
C00108424DB92.01.27284 | EROSION CONTROL MULCH | Material | Square Yard |  | 8
C00108424DB92.01.27321 | PROTECTIVE COVERING EC-2 | Material | Square Yard |  | 8
C00108424DB92.01.27327 | SOIL STABILZATION MAT EC-3 TYPE C | Material | Square Yard |  | 8
C00108424DB92.01.27451 | INLET PROTECTION TYPE A | Material | Each |  | 8
C00108424DB92.01.27505 | TEMP SILT FENCE TYPE A | Material | Linear Feet |  | 8
C00108424DB92.01.50108 | SIGN PANEL | Material | Square Feet |  | 8
C00108424DB92.01.50402 | SIGN POST STEEL 3" | Material | Linear Feet |  | 8
C00108424DB92.01.50432 | SIGN POST STEEL STP-1, 2 3/16" | Material | Linear Feet |  | 8
C00108424DB92.01.50500 | CONC.FOUND.SSP-V A 1'DIA.X3'DEPTH | Material | Each |  | 8
C00108424DB92.01.50502 | CONC.FOUND.SSP-V A1'9" DIA.X4'6" D | Material | Each |  | 8
C00108424DB92.01.50575 | CONC.FOUND.O.H LOCATION NO.1 | Material | Cubic Yard |  | 8
C00108424DB92.01.50902 | NS TRAFFIC SIGN O.H. LOCATION NO.1 | Material | Each |  | 8
C00108424DB92.01.54042 | TYB. CL.VI PAVE.LINE MARK 24" | Material | Linear Feet |  | 8
C00108424DB92.01.54075 | TYB. CL.VI PAVE.LINE MARK 4" | Material | Linear Feet |  | 8
C00108424DB92.01.54076 | TYB. CL.VI PAVE.LINE MARK 6" | Material | Linear Feet |  | 8
C00108424DB92.01.54077 | TYB. CL.VI PAVE.LINE MARK 8" | Material | Linear Feet |  | 8
C00108424DB92.01.54105 | ERAD. OF EXIST.PAVE.MARKING | Material | Linear Feet |  | 8
C00108424DB92.01.54217 | SNOW PLOW.RAISED.PAVE.MARK.ASPH.CONC | Material | Each |  | 8
C00108424DB92.01.54240 | TEMP.PAVE.MARKER 1 WAY | Material | Each |  | 8
C00108424DB92.01.54300 | PAVE.MESS.MARK.ELONG.ARROW SIN | Material | Each |  | 8
C00108424DB92.01.54589 | PAVE.MESS.MARK LANE REDUCTION ARROW | Material | Each |  | 8
C00108424DB92.01.54510 | CONSTR.PAVE.MARK.(TY.D.CLI)4" | Material | Linear Feet |  | 8
C00108424DB92.01.55001 | NS 1 CONDUCTOR NO.4 AWG,TYPE RHW, 600V | Material | Linear Feet |  | 8
C00108424DB92.01.55140 | CONCRETE FOUDATION LF-1 TYA | Material | Each |  | 8
C00108424DB92.01.55581 | JUCNTION BOX JB-R2 | Material | Each |  | 8
C00108424DB92.01.56021 | NS SCHEDULE 80 RIGID PVC CONDUIT-TRENCH | Material | Linear Feet |  | 8
C00108424DB92.01.59000 | NS LIGHTING ELECTRICAL SERVICE SE9TYPEA | Material | Each |  | 8
C00108424DB92.01.590001 | CONTROL CNETER CCW-1 TY A | Material | Each |  | 8
C00108424DB92.01.590002 | LED LUMINAIRE ROADWAY | Material | Each |  | 8
C00108424DB92.01.590003 | LIGHITING POLE LP-1 30'-12' | Material | Each |  | 8
C00108424DB92.01.590004 | NS LIGHTING REMOVE LT POLE & JUNC BOX | Material | Each |  | 8
C00108424DB92.01.59001 | NS LIGHTING BORED CONDUIT 3" | Material | Linear Feet |  | 8
C00108424DB92.01.59050 | NS RELOCATE HUT & POLE | Material | Each |  | 8
D-2-3 | ADDITIONAL DEPT IMPROVEMENTS - CHANGE ORDERS | Material | Lump Sum |  | 8
C00108424DB92.01.00104 | PROJECT DESIGN | Material | Lump Sum |  | 8
C00108424DB92.01.00100 | MOBILIZATION | Material | Lump Sum |  | 8
C00108424DB92 | CONSTRUCTION COST (BASE) | Material | Lump Sum |  | 8
3404-01-0500 | CONSTRUCTION COST (OPTION 1) | Material | Lump Sum |  | 8
Westerly OH | Westerly Ohio Tunnel | Nonlabor |  |  | 0
1000 | 25' DIA TUNNEL | Material |  |  | 1
2000 | TUNNELL BORING MACHINE AND APPURTNEAN | Material |  |  | 1
3000 | ADDITIONAL ROCK DOWELS | Material |  |  | 1
4000 | WST -1 SITE WORK | Material |  |  | 1
5000 | WST -1 SHAFT | Material |  |  | 1
6000 | WST -2 SITE WORK | Material |  |  | 1
7000 | WST -2 BAFFLE DROP STRUCTURE | Material |  |  | 1
8000 | WST -2 GROUNDWATER CONTROL | Material |  |  | 1
9000 | WST -2 SHAFT TO TUNNEL ADIT | Material |  |  | 1
10000 | WST -2 GATE CONTROL VAULT | Material |  |  | 1
11000 | WST -2 GATE STRUCTURE | Material |  |  | 1
12000 | WST -2 DIVERSION STRUCTURE | Material |  |  | 1
13000 | WST -2 SEWER FROM SHAFT TO GATE STRUCTURE | Material |  |  | 1
14000 | WST -2 SEWER FROM GATE STRUCTURE TO DIVERSION | Material |  |  | 1
16000 | WST -3 SITE WORK | Material |  |  | 1
17000 | WST -3 BAFFLE DROP STRUCTURE | Material |  |  | 1
18000 | WST -3 GROUNDWATER CONTROL | Material |  |  | 1
19000 | WST -3 GATE CONTROL VAULT | Material |  |  | 1
20000 | WST -3 GATE STRUCTURE | Material |  |  | 1
21000 | EXISTING SEWER MODIFICAITONS (WR-27, UNI) | Material |  |  | 1
22000 | EROSION CONTROL / SWPPP | Material |  |  | 1
23000 | GEOTECHNICAL INSTRUMENTATION AND MONITORING | Material |  |  | 1
24000 | PRE-CONSTRUCTION AND POST- CONSTRUCTION | Material |  |  | 1
25000 | CONSTRUCTION DOCUMENTATION | Material |  |  | 1
26000 | STARTUP, TESTING, AND COMMISSIONING | Material |  |  | 1
27000 | Mobilization & Demobilization (max 5% of subtotal) | Material |  |  | 1
28000 | Bid, Performance & Payment Bonds (max 1% of Unooff | Material |  |  | 1
29000 | GENERAL ALLOWANCE | Material |  |  | 1
30000 | Disputes Resolution Board | Material |  |  | 1
31000 | Standby Due to Gas Encountered During Construction | Material |  |  | 1
32000 | Utility Relocations | Material |  |  | 1
33000 | Additional Road Repaving / Repairs | Material |  |  | 1
34000 | Community Interface and Media Relations | Material |  |  | 1
012 | Broom Tractor | Nonlabor |  |  | 1
Wall 1 | Jose | Labor |  |  | 1
Wall 2 | Beto | Labor |  |  | 1
Wall 3 | Alex | Labor |  |  | 1
Wall 4 | Tacho | Labor |  |  | 1
WOE SSTR | WOE 1 | Labor |  |  | 1
WOE Sidewalk | WOE 2 | Labor |  |  | 1
TEM | TEM | Labor |  |  | 1
Fortson | Fortson 1 | Labor |  |  | 1
Fortson 2 | Fortson 2 | Labor |  |  | 1
SAZ | Stripe a Zone | Labor |  |  | 1
Concrete-1 | SLIP FORM - Lane Crew | Labor |  |  | 1
Earthwork1 | Ricky Blair | Labor |  |  | 1
Earthwork 2 | Jay | Labor |  |  | 1
Earthwork 3 | Thomas | Labor |  |  | 1
Earthwork 4 | Justin | Labor |  |  | 1
Earthwork 5 | Christopher | Labor |  |  | 1
Earthwork 6 | David | Labor |  |  | 1
Flatwork 1 | Juan Del Cid | Labor |  |  | 1
Flatwork 2 | Victor O. | Labor |  |  | 1
Drainage Inlets | Eduardo | Labor |  |  | 1
Drainage Inlets 2 | Richard G. | Labor |  |  | 1
Misc Roadway 1 | Nino | Labor |  |  | 1
Earthwork 15 | Reynaldo | Labor |  |  | 1
Misc Roadway 3 | Jorge | Labor |  |  | 1
Structures Fencing | Luis | Labor |  |  | 1
Drainage 1 | Roberto | Labor |  |  | 1
Structures 1 | Arturo | Labor |  |  | 1
Structures 2 | Kevin | Labor |  |  | 1
Structures 3 | Morris | Labor |  |  | 1
Structures 4 | Eduardo Rubio | Labor |  |  | 1
Structures 5 | Salvador | Labor |  |  | 1
SWPPP | Jeff | Labor |  |  | 1
Urban | Urban | Labor |  |  | 1
Indus 1 | Indus REbar | Labor |  |  | 1
Indus 2 | Indus Bridge | Labor |  |  | 1
Hart | Hart Concrete | Labor |  |  | 1
Mica 1 | Mica 1 | Labor |  |  | 1
Mica 2 | Mica 2 | Labor |  |  | 1
RAC | Reynolds Asphalt Company | Labor |  |  | 1
Universal | Universal Fence | Labor |  |  | 1
TEXOP | TEXOP | Labor |  |  | 1
SUB-BR-HAND | Sub - Concrete Barrier - Hand Pour Crew | Labor |  |  | 1
SUB-BR-SLIP | Sub - Concrete Barrier - Slip Crew | Labor |  |  | 1
SUB-LINE | Sub - Storm Pipe Lining Crew | Labor |  |  | 1
SA-1 | Seg A Crew 1 | Labor |  |  | 1
SA-2 | Seg A Crew 2 | Labor |  |  | 1
SB-1 | Seb B Crew 1 | Labor |  |  | 1
SB-2 | Seg B Crew 2 | Labor |  |  | 1
SB-3 | Seg B Crew 3 | Labor |  |  | 1
SC-1 | Seg C Crew 1 | Labor |  |  | 1
SC-2 | Seg C Crew 2 | Labor |  |  | 1
SC-3 | Seg C Crew 3 | Labor |  |  | 1
SC-4 | Seg C Crew 4 | Labor |  |  | 1
SUB-UT-Illum | Sub- Roadway Illumination Crew | Labor |  |  | 1
Earthwork 7 | JJ | Labor |  |  | 1
Earthwork 8 | Louis | Labor |  |  | 1
Earthwork 9 | Tim P. | Labor |  |  | 1
Earthwork 10 | Gentry | Labor |  |  | 1
Earthwork 11 | Beau | Labor |  |  | 1
Earthwork 12 | Javier | Labor |  |  | 1
Earthwork 13 | Carlos | Labor |  |  | 1
Earthwork 14 | Jerimiah | Labor |  |  | 1
UES | UES | Labor |  |  | 1
Mica 3 | Mica bore Crew | Labor |  |  | 1
Mica 4 | Mica Conduit/conductor | Labor |  |  | 1
Mica 5 | Mica Drill crew | Labor |  |  | 1
Mica 6 | Mica Structure Signs | Labor |  |  | 1
Mica 7 | Mica Structure ITS | Labor |  |  | 1
Mica 8 | Mica Structure Illumination | Labor |  |  | 1
WW | WW Drilling | Labor |  |  | 1
AF | Anchor Fence | Labor |  |  | 1
Concrete - 2 | Hand Pour - Lane Crew 1 | Labor |  |  | 1
Concrete - 3 | Hand Pour - Lane Crew1 Juan | Labor |  |  | 1
Concrete - 4 | Hand Pour - Abrams Hart | Labor |  |  | 1
Concrete - 5 | Hand Pour - Indus Juan | Labor |  |  | 1
Concrete - 6 | Hand Pour - Indus 2 | Labor |  |  | 1
Concrete - 7 | Hand Pour - Sergio | Labor |  |  | 1
Structures 6 | Jose P | Labor |  |  | 1
3364.403.6001 | TEMPORARY SPL SHORING | Material | Square Feet |  | 1
3403 | 3403 - FL Turnpike Suncoast Pkwy | Nonlabor |  |  | 0
Hernando | Hernando County | Nonlabor |  |  | 1
Citrus | Citrus County | Nonlabor |  |  | 1
Citrus(DB) | Citrus County (Dewberry) | Nonlabor |  |  | 1
3403-HC-0400-2-4 | CONC CLASS II, BRIDGE SUPERSTRUCTURE | Material | Cubic Yard |  | 1
3403-HC-0400-2-10 | CONCRETE CLASS II, APPROACH SLABS | Material | Cubic Yard |  | 1
3403-HC-0400-4-5 | CONCRETE CLASS IV, BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 1
3403-HC-0400-4-25 | CONCRETE CLASS IV, MASS, SUBSTRUCTURE | Material | Cubic Yard |  | 1
3403-HC-0400-7 | BRIDGE DECK GROOVING, LESS THAN 8.5" | Material | Square Yard |  | 1
3403-HC-0400-9 | BRIDGE DECK GROOVING & PLANING, DECK 8.5" AND GREA | Material | Square Yard |  | 8
3403-HC-0400147 | COMPOSITE NEOPRENE PADS | Material | Cubic Feet |  | 8
3403-HC-0415-1-4 | REINFORCING STEEL - BRIDGE SUPERSTRUCTURE | Material | Per Pound |  | 8
3403-HC-0415-1-5 | REINFORCING STEEL- BRIDGE SUBSTRUCTURE | Material | Per Pound |  | 8
3403-HC-0415-1-9 | REINFORCING STEEL- APPROACH SLABS | Material | Per Pound |  | 8
3403-HC-0450-2-54 | PREST BEAMS: FLORIDA-I BEAM 54" | Material | Linear Feet |  | 8
3403-HC-0450-2-63 | PREST BEAMS: FLORIDA-I BEAM 63" | Material | Linear Feet |  | 8
3403-HC-0455-34-5 | PRESTRESSED CONCRETE PILING, 24" SQ | Material | Linear Feet |  | 8
3403-HC-0455143-5 | TEST PILES-PRESTRESSED CONCRETE,24" SQ | Material | Linear Feet |  | 8
3403-HC-0458-1-11 | BRIDGE DECK EXPANSION JOINT, NEW CONSTRUCTION, F&I | Material | Linear Feet |  | 8
3403-HC-0459-71 | PILES, POLYETHYLENE SHEETING | Material | Square Yard |  | 8
3403-HC-0515-4-2 | BULLET RAIL, DOUBLE RAIL | Material | Linear Feet |  | 8
3403-HC-0521-5-6 | CONCRETE TRAFFIC RAILING- BRIDGE, CORRAL W/CURB | Material | Linear Feet |  | 8
3403-HC-0521-5-7 | CONCRETE TRAFFIC RAILING, BRIDGE, CORRAL W/O CURB | Material | Linear Feet |  | 8
3403-HC-0521-6-11 | CONCRETE PARAPET, PEDESTRIAN/BICYCLE, 27" HEIGHT | Material | Linear Feet |  | 8
3403-HC-0521-6-31 | CONC PARAPET, RETAIN WALL SYS MTD W/SIDEWALK 27" | Material | Linear Feet |  | 8
3403-HC-0521-8-6 | CONC TRAFF RAIL BARR, W/JCT SLAB CORRAL W/O CURB | Material | Linear Feet |  | 8
3403-HC-0522-2 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THICK (BRIDGE#080058) | Material | Square Yard |  | 8
3403-HC-0524-2-2 | CONCRETE SLOPE PAVEMENT,NON REINFORCED, 4" (BR#080060) | Material | Square Yard |  | 8
3403-HC-0548-12 | RETAINING WALL SYSTEM, PERMANENT, EXCLUDING BARRIER | Material | Square Feet |  | 8
3403-HC-0550-10344 | FENCING, TYPE R, 7.1-8.0, W / PARTIAL ENCLOSURE (BR#080058) | Material | Linear Feet |  | 8
3403-HC-0550-10363 | FENCING, TYPE R, GREATER THAN 10.0', WITH FULL ENC (BR#080058) | Material | Linear Feet |  | 8
3403-HC-0101-1 | MOBILIZATION | Material | Lump Sum |  | 8
3403-HC-0102-1 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
3403-HC-0102-2-1 | SPECIAL DETOUR 1 | Material | Lump Sum |  | 8
3403-HC-0102-2-2 | SPECIAL DETOUR 2 | Material | Lump Sum |  | 8
3403-HC-0102-2-4 | SPECIAL DETOUR 4 | Material | Lump Sum |  | 8
3403-HC-0102-14 | TRAFFIC CONTROL OFFICER | Material | Hour |  | 8
3403-HC-0102-60 | WORK ZONE SIGN | Material | Day |  | 8
3403-HC-0102-71-11 | TEMPORARY BARRIER, F&I, CONCRETE | Material | Linear Feet |  | 8
3403-HC-0102-71-14 | TEMPORARY BARRIER, F & I, TYPE K | Material | Linear Feet |  | 8
3403-HC-0102-71-21 | TEMPORARY BARRIER, RELOCATE, CONCRETE | Material | Linear Feet |  | 8
3403-HC-0102-71-24 | TEMPORARY BARRIER, RELOCATE, TYPE K | Material | Linear Feet |  | 8
3403-HC-0102-74-1 | CHANNELIZING DEVICE- TYPES I, II, DI, VP, DRUM, OR | Material | Day |  | 8
3403-HC-0102-74-2 | CHANNELIZING DEVICE, TYPE III, 6' | Material | Day |  | 8
3403-HC-0102-76 | ARROW BOARD / ADVANCE WARNING ARROW PANEL | Material | Day |  | 8
3403-HC-0102-78 | TEMPORARY RETROREFLECTIVE PAVEMENT MARKER | Material | Each |  | 8
3403-HC-0102-89-1 | TEMPORARY CRASH CUSHION, REDIRECTIVE OPTION | Material | Location |  | 8
3403-HC-0102-99 | PORTABLE CHANGEABLE MESSAGE SIGN, TEMPORARY | Material | Day |  | 8
3403-HC-0102-150-1 | PORTABLE REGULATORY, SIGN | Material | Day |  | 8
3403-HC-0102-150-2 | RADAR SPEED DISPLAY UNIT | Material | Day |  | 8
3403-HC-0104-1 | ARTIFICIAL COVERINGS /ROLLED EROSION CONTROL PRODU | Material | Square Yard |  | 8
3403-HC-0104-10-3 | SEDIMENT BARRIER | Material | Linear Feet |  | 8
3403-HC-0104-15 | SOIL TRACKING PREVENTION DEVICE | Material | Each |  | 8
3403-HC-0104-18 | INLET PROTECTION SYSTEM | Material | Each |  | 8
3403-HC-0107-1 | LITTER REMOVAL | Material |  |  | 8
3403-HC-0107-2 | MOWING | Material |  |  | 8
3403-HC-0108-1 | MONITOR EXISTING STRUCTURES- INSPECTION AND SETTL (Pump Station) | Material | Lump Sum |  | 8
3403-HC-0108-2 | MONITOR EXISTING STRUCTURES- VIBRATION MONITORING (Pump Station) | Material | Lump Sum |  | 8
3403-HC-0110-1-1 | CLEARING & GRUBBING (Hernando County) | Material |  |  | 8
3403-HC-0110-2-2 | SELECTIVE CLEARING AND GRUBBING, AREAS WITH TREES | Material |  |  | 8
3403-HC-0110-4-10 | REMOVAL OF EXISTING CONCRETE | Material | Square Yard |  | 8
3403-HC-0120-1900 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3403-HC-0120-4900 | SUBSOIL EXCAVATION | Material | Cubic Yard |  | 8
3403-HC-0120-6900 | EMBANKMENT | Material | Cubic Yard |  | 8
3403-HC-0121-70 | FLOWABLE FILL | Material | Cubic Yard |  | 8
3403-HC-0160-4900 | TYPE B STABILIZATION | Material | Square Yard |  | 8
3403-HC-0162-1-11 | PREPARED SOIL LAYER, FINISH SOIL LAYER, 6" | Material | Square Yard |  | 8
3403-HC-0173-76 | GROUT PIPE INSTALLATION | Material | Linear Feet |  | 8
3403-HC-0173-77-1 | SUBSURFACE PRESSURE GROUTING, SAND CEMENT | Material | Cubic Yard |  | 8
3403-HC-0285701900 | OPTIONAL BASE, BASE GROUP 01 | Material | Square Yard |  | 8
3403-HC-0285704 | OPTIONAL BASE, BASE GROUP 04 | Material | Square Yard |  | 8
3403-HC-0285709900 | OPTIONAL BASE, BASE GROUP 09 | Material | Square Yard |  | 8
3403-HC-0285711 | OPTIONAL BASE, BASE GROUP 11 | Material | Square Yard |  | 8
3403-HC-0327-70-11 | MILLING EXIST ASPH PAVT, 2 1/4" AVG DEPTH | Material | Square Yard |  | 8
3403-HC-0327-70-12 | MILLING EXIST ASPH PAVT, 1 1/4" AVG DEPTH | Material | Square Yard |  | 8
3403-HC-0327-70-16 | MILLING EXIST ASPH PAVT, 1/2" AVG DEPTH | Material | Square Yard |  | 8
3403-HC-0327-70-19 | MILLING EXIST ASPH PAVT, 3/4" AVG DEPTH | Material | Square Yard |  | 8
3403-HC-0334-1-12 | SUPERPAVE ASPHALTIC CONC, TRAFFIC B | Material |  |  | 8
3403-HC-0334-1-13 | SUPERPAVE ASPHALTIC CONC, TRAFFIC C | Material |  |  | 8
3403-HC-0334-1-52 | SUPERPAVE ASPHALTIC CONCRETE, TRAFFIC B, PG76-22 | Material |  |  | 8
3403-HC-0334-1-53 | SUPERPAVE ASPHALTIC CONCRETE, TRAFFIC C, PG76-22 | Material |  |  | 8
3403-HC-0337-7-25 | ASPHALT CONCRETE FRICTION COURSE, INC BIT, FC-5, | Material |  |  | 8
3403-HC-0339-1 | MISCELLANEOUS ASPHALT PAVEMENT (U/GUARDRAIL,MEDIAN,OTHER) | Material |  |  | 8
3403-HC-0400-1-2 | CONCRETE CLASS I, ENDWALLS | Material | Cubic Yard |  | 8
3403-HC-0425-1511 | INLETS, DT BOT, TYPE B, <10' | Material | Each |  | 8
3403-HC-0425-1541 | INLETS, DT BOT, TYPE D, <10' | Material | Each |  | 8
3403-HC-0425-1701 | INLETS, GUTTER, TYPE S, <10' | Material | Each |  | 8
3403-HC-0425-1711 | INLETS, GUTTER, TYPE V, <10' | Material | Each |  | 8
3403-HC-0425-1801 | INLETS, MEDIAN BARRIER, TYPE 1, <10' | Material | Each |  | 8
3403-HC-0425-1811 | INLETS, MEDIAN BARRIER, TYPE 2, <10' | Material | Each |  | 8
3403-HC-0425-1841 | INLETS, MEDIAN BARRIER, TYPE 3, <10' | Material | Each |  | 8
3403-HC-0425-1891 | INLETS, BARRIER WALL, <10' | Material | Each |  | 8
3403-HC-0425-2-61 | MANHOLES, P-8, <10' | Material | Each |  | 8
3403-HC-0425-2-63 | MANHOLES, P-8, PARTIAL | Material | Each |  | 8
3403-HC-0430-173118 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 18", GD | Material | Linear Feet |  | 8
3403-HC-0430173124 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 24", GD | Material | Linear Feet |  | 8
3403-HC-0430174118 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 18"SD | Material | Linear Feet |  | 8
3403-HC-0430174124 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 24"SD | Material | Linear Feet |  | 8
3403-HC-0430175118 | PIPE CULVERT,OPTIONAL MATERIAL,ROUND, 18"S/CD | Material | Linear Feet |  | 8
3403-HC-0430175124 | PIPE CULVERT,OPTIONAL MATERIAL,ROUND, 24"S/CD | Material | Linear Feet |  | 8
3403-HC-0430175130 | PIPE CULVERT, OPT MATERIAL, ROUND, 30"S/CD | Material | Linear Feet |  | 8
3403-HC-0430175136 | PIPE CULVERT, OPT MATERIAL, ROUND, 36"S/CD | Material | Linear Feet |  | 8
3403-HC-0430611125 | U-ENDWALL WITH BAFFLES, STD 261, 1:4 SLOPE, 18"PIP | Material | Each |  | 8
3403-HC-0430611129 | U-ENDWALL WITH BAFFLES, STD 261, 1:4 SLOPE, 24"PIP | Material | Each |  | 8
3403-HC-0430611225 | U-ENDWALL WITH BAFFLES, STD 261, 1:3 SLOPE, 18"PIP | Material | Each |  | 8
3403-HC-0430611229 | U-ENDWALL WITH BAFFLES, STD 261, 1:3 SLOPE, 24"PIP | Material | Each |  | 8
3403-HC-0430982125 | MITERED END SECTION, OPTIONAL ROUND, 18" CD | Material | Each |  | 8
3403-HC-0430982129 | MITERED END SECTION, OPTIONAL ROUND, 24" CD | Material | Each |  | 8
3403-HC-0430982133 | MITERED END SECTION, OPTIONAL ROUND, 30" CD | Material | Each |  | 8
3403-HC-0430984125 | MITERED END SECTION, OPTIONAL ROUND, 18" SD | Material | Each |  | 8
3403-HC-0430984129 | MITERED END SECTION, OPTIONAL ROUND, 24" SD | Material | Each |  | 8
3403-HC-0519-78 | BOLLARDS | Material | Each |  | 8
3403-HC-0520-1-7 | CONCRETE CURB & GUTTER, TYPE E | Material | Linear Feet |  | 8
3403-HC-0520-2-4 | CONCRETE CURB, TYPE D | Material | Linear Feet |  | 8
3403-HC-0520-6 | SHOULDER GUTTER- CONCRETE | Material | Linear Feet |  | 8
3403-HC-0521-1 | MEDIAN CONCRETE BARRIER WALL | Material | Linear Feet |  | 8
3403-HC-0521-72-3 | SHOULDER CONC BARR, RIGID-SHOULDER 32" | Material | Linear Feet |  | 8
3403-HC-0524-1-1 | CONCRETE DITCH PAVT, NON REINFORCED, 3" | Material | Square Yard |  | 8
3403-HC-0530-3-4 | RIPRAP, RUBBLE, F&I, DITCH LINING | Material |  |  | 8
3403-HC-0536-1-1 | GUARDRAIL -ROADWAY, GENERAL TL-3 | Material | Linear Feet |  | 8
3403-HC-0536-8-11 | APPROACH TRANSITION TO RIGID BARRIER- BRIDGE ANCHORAGE ASSEMBLY | Material | Each |  | 8
3403-HC-0536-73 | GUARDRAIL REMOVAL | Material | Linear Feet |  | 8
3403-HC-0536-85-22 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- FLARED | Material | Each |  | 8
3403-HC-0536-85-25 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- TYPE II | Material | Each |  | 8
3403-HC-0544-75-1 | CRASH CUSHION | Material | Each |  | 8
3403-HC-0546-72-55 | RUMBLE STRIPS, GROUND-IN, 16" SHOULDER | Material | Mile |  | 8
3403-HC-0550-10222 | FENCING, TYPE B, 5.1-6.0, W/ VINYL COATING | Material | Linear Feet |  | 8
3403-HC-0550-10256 | FENCING, TYPE B, 8-10.0', WITH VINYL COATING AND B | Material | Linear Feet |  | 8
3403-HC-0550-60224 | FENCE GATE, TYPE B, DOUBLE, 18.1-20.0' OPENING | Material | Each |  | 8
3403-HC-0550-60225 | FENCE GATE , TYPE B, DOUBLE, 20.1-24' OPENING | Material | Each |  | 8
3403-HC-0550-60226 | FENCE GATE , TYPE B, DOUBLE, 24.1-30.0' OPENING | Material | Each |  | 8
3403-HC-0570-1-1 | PERFORMANCE TURF | Material | Square Yard |  | 8
3403-HC-0570-1-2 | PERFORMANCE TURF, SOD | Material | Square Yard |  | 8
3403-HC-0710-11101 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Mile |  | 8
3403-HC-0710-11102 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Mile |  | 8
3403-HC-0710-11124 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Linear Feet |  | 8
3403-HC-0710-11125 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Linear Feet |  | 8
3403-HC-0710-11131 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SKIP, | Material | Mile |  | 8
3403-HC-0710-11141 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, 2-4 D | Material | Mile |  | 8
3403-HC-0710-11170 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, ARROW | Material | Each |  | 8
3403-HC-0710-11201 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLI | Material | Mile |  | 8
3403-HC-0710-11241 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, 2-4 | Material | Mile |  | 8
3403-HC-0751-42-1 | BIRD HOUSE | Material | Each |  | 8
3403-HC-0999-16 | PARTNERING, DO NOT BID 40527015201 | Material | Lump Sum |  | 8
3403-HC-0999-20-1 | DISPUTES REVIEW BOARD, MEETING- DO NOT BID | Material | Day |  | 8
3403-HC-0999-20-2 | DISPUTES REVIEW BOARD, HEARING- DO NOT BID | Material | Each |  | 8
3403-HC-0999-25 | INITIAL CONTINGENCY AMOUNT, DO NOT BID 405270152 | Material | Lump Sum |  | 8
3403-HC-0700-1-11 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12 SF | Material | Each |  | 8
3403-HC-0700-1-12 | SINGLE POST SIGN, F&I GROUND MOUNT, 12-20 SF | Material | Each |  | 8
3403-HC-0700-1-13 | SINGLE POST SIGN, F&I GROUND MOUNT, 21-30 SF | Material | Each |  | 8
3403-HC-0700-1-50 | SINGLE POST SIGN, RELOCATE | Material | Each |  | 8
3403-HC-0700-1-60 | SINGLE POST SIGN, REMOVE | Material | Each |  | 8
3403-HC-0700-2-14 | MULTI- POST SIGN, F&I GROUND MOUNT, 31-50 SF | Material | Each |  | 8
3403-HC-0700-2-15 | MULTI- POST SIGN, F&I GROUND MOUNT, 51-100 SF | Material | Each |  | 8
3403-HC-0700-2-16 | MULTI- POST SIGN, F&I GROUND MOUNT, 101-200 SF | Material | Each |  | 8
3403-HC-0700-2-18 | MULTI- POST SIGN, F&I GROUND MOUNT, 301-400 SF | Material | Each |  | 8
3403-HC-0700-2-60 | MULTI- POST SIGN, REMOVE | Material | Each |  | 8
3403-HC-0700-3206 | SIGN PANEL, FURNISH & INSTALL OVERHEAD MOUNT, 101- | Material | Each |  | 8
3403-HC-0700-3625 | SIGN PANEL, REMOVE, 51-100 SF WITH LIGHTING | Material | Each |  | 8
3403-HC-0700-3627 | SIGN PANEL, REMOVE PANEL, 201-300 SF WITH LIGHTING | Material | Each |  | 8
3403-HC-0700-4112 | OVERHEAD STATIC SIGN STRUCTURE, FURNISH & INSTALL, | Material | Each |  | 8
3403-HC-0700-4633 | OVERHEAD STATIC SIGN STRUCTURE, REMOVE MONOTUBE, 31-40 FT | Material | Each |  | 8
3403-HC-0700-4635 | OVERHEAD STATIC SIGN STRUCTURE, REMOVE MONOTUBE, 51-100 FT | Material | Each |  | 8
3403-HC-0700-13-12 | RETROREFLECTIVE SIGN STRIP- FURNISH AND INSTALL, 2' | Material | Each |  | 8
3403-HC-0700-13-15 | RETROREFLECTIVE SIGN STRIP- FURNISH AND INSTALL, 5' | Material | Each |  | 8
3403-HC-0705-11-1 | DELINEATOR, FLEXIBLE TUBULAR | Material | Each |  | 8
3403-HC-0710-90 | PAINTED PAVEMENT MARKINGS, FINAL SURFACE 4052701 | Material | Lump Sum |  | 8
3403-HC-0711-11102 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 8" FOR INT | Material | Mile |  | 8
3403-HC-0711-11123 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 12" FOR CRO | Material | Linear Feet |  | 8
3403-HC-0711-11124 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 18" FOR DIA | Material | Linear Feet |  | 8
3403-HC-0711-11125 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 24" FOR STO | Material | Linear Feet |  | 8
3403-HC-0711-11141 | THERMOPLASTIC, STANDARD, WHITE, 2-4 DOTTED GUIDELI | Material | Mile |  | 8
3403-HC-0711-11160 | THERMOPLASTIC, STANDARD, WHITE, MESSAGE OR SYMBOL | Material | Each |  | 8
3403-HC-0711-11170 | THERMOPLASTIC, STANDARD, WHITE, ARROW | Material | Each |  | 8
3403-HC-0711-11241 | THERMOPLASTIC, STANDARD, YELLOW, 2-4 DOTTED GUIDE | Material | Mile |  | 8
3403-HC-0711-11421 | THERMOPLASTIC, STANDARD, BLUE, SOLID,6" | Material | Linear Feet |  | 8
3403-HC-0711-14160 | THERMOPLASTIC, PREFORMED, WHITE, MESSAGE | Material | Each |  | 8
3403-HC-0711-14170 | THERMOPLASTIC, PREFORMED, WHITE, ARROW | Material | Each |  | 8
3403-HC-0711-15101 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-HC-0711-15102 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-HC-0711-15131 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-HC-0711-15201 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-HC-0711-16101 | THERMOPLASTIC, STANDARD-OTHER SURFACES, WHITE, SOL | Material | Mile |  | 8
3403-HC-0711-17 | THERMOPLASTIC, REMOVE EXISTING THERMOPLASTIC PAVEM | Material | Square Feet |  | 8
3403-HC-0713103101 | PERMANENT TAPE, WHITE, SOLID, 6" FOR CONCRETE BRIDES | Material | Mile |  | 8
3403-HC-0713103131 | PERMANENT TAPE, WHITE, SKIP/DOTTED, 6" FOR CONCRE | Material | Mile |  | 8
3403-HC-0713103201 | PERMANENT TAPE, YELLOW, SOLID, 6" FOR CONCRETE BRI | Material | Mile |  | 8
3403-HC-0713103331 | PERMANENT TAPE, BLACK, SKIP/DOTTED, 6" FOR CONCRE | Material | Mile |  | 8
3403-HC-0630-2-11-1 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-HC-0630-2-12-1 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-HC-0630-2-15 | CONDUIT, FURNISH & INSTALL, BRIDGE MOUNT | Material | Linear Feet |  | 8
3403-HC-0635-2-11-2 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-HC-0635-3-11 | JUNCTION BOX, FURNISH & INSTALL, AERIAL | Material | Each |  | 8
3403-HC-0641-2-12-2 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-HC-0715-1-12 | LIGHTING CONDUCTORS, F&I, INSULATED, NO.8 - 6 | Material | Linear Feet |  | 8
3403-HC-0715-1-13 | LIGHTING CONDUCTORS, F&I, INSULATED, NO 4 TO NO 2 | Material | Linear Feet |  | 8
3403-HC-0715-1-60 | LIGHTING CONDUCTORS, REMOVE & DISPOSE, CONTRACTOR | Material | Linear Feet |  | 8
3403-HC-0715-4-14 | LIGHT POLE COMPLETE, FURNISH & INSTALL STANDARD PO | Material | Each |  | 8
3403-HC-0715-4-70 | LIGHT POLE COMPLETE, REMOVE POLE AND FOUNDATION | Material | Each |  | 8
3403-HC-0715-7-11 | LOAD CENTER, F&I, SECONDARY VOLTAGE | Material | Each |  | 8
3403-HC-0715-7-41 | LOAD CENTER, REMOVE, SECONDARY VOLTAGE | Material | Each |  | 8
3403-HC-0715-11125 | LUMINAIRE, F&I, UNDER DECK, WALL MOUNT | Material | Each |  | 8
3403-HC-0715500-1 | POLE CABLE DISTRIBUTION SYSTEM, CONVENTIONAL | Material | Each |  | 8
3403-HC-0715500-3 | POLE CABLE DISTRIBUTION SYSTEM, WALL MOUNT | Material | Each |  | 8
3403-HC-0715516145 | LIGHT POLE COMPLETE- SPECIAL DESIGN, F&I, POLE TOP | Material | Each |  | 8
3403-HC-0715518150 | LIGHT POLE COMP- SPECIAL DESIGN, F&I, DOUBLE ARM, | Material | Each |  | 8
3403-HC-0630-2-11-3 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-HC-0630-2-12-3 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-HC-0632-7-1 | SIGNAL CABLE- NEW OR RECONSTRUCTED INTERSECTION, F | Material | Each |  | 8
3403-HC-0632-7-6 | SIGNAL CABLE, REMOVE- INTERSECTION | Material | Each |  | 8
3403-HC-0635-2-11-1 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-HC-0639-1122-1 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-HC-0639-1620-1 | ELECTRICAL POWER SERVICE, REMOVE UNDERGROUND | Material | Each |  | 8
3403-HC-0639-2-1-1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | Material | Linear Feet |  | 8
3403-HC-0639-3-11-1 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | Material | Each |  | 8
3403-HC-0641-2-12-1 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-HC-0641-2-60-1 | PRESTRESSED CONCRETE POLE, COMPLETE POLE REMOVAL- | Material | Each |  | 8
3403-HC-0649-21-12 | STEEL MAST ARM ASSEMBLY, FURNISH AND INSTALL, DOUB | Material | Each |  | 8
3403-HC-0649-21-21 | STEEL MAST ARM ASSEMBLY, FURNISH AND INSTALL, SING | Material | Each |  | 8
3403-HC-0649-26-5 | STEEL MAST ARM ASSEMBLY, REMOVE, DEEP FOUNDATION- | Material | Each |  | 8
3403-HC-0650-1-14 | TRAFFIC SIGNAL, FURNISH & INSTALL ALUMINUM, 3 SEC | Material | Each |  | 8
3403-HC-0650-1-16 | TRAFFIC SIGNAL, FURNISH & INSTALL ALUMINUM, 4 SEC | Material | Each |  | 8
3403-HC-0670-5110 | TRAFFIC CONTROLLER ASSEMBLY, F&I, NEMA | Material | Each |  | 8
3403-HC-0670-5600 | TRAFFIC CONTROLLER ASSEMBLY, REMOVE CONTROLLER WIT | Material | Each |  | 8
3403-HC-0700-3201 | SIGN PANEL, FURNISH & INSTALL OVERHEAD MOUNT, UP T | Material | Each |  | 8
3403-HC-0700-5-22 | INTERNALLY ILLUMINATED SIGN, FURNISH & INSTALL, O | Material | Each |  | 8
3403-HC-0400-0-11 | CONCRETE CLASS NS, GRAVITY WALL | Material | Cubic Yard |  | 8
3403-HC-0515-1-2 | PIPE HANDRAIL - GUIDERAIL, ALUMINUM | Material | Linear Feet |  | 8
3403-HC-0630-2-11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-HC-0630-2-12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-HC-0630-2-14 | CONDUIT, FURNISH & INSTALL, ABOVEGROUND | Material | Linear Feet |  | 8
3403-HC-0633-1121 | FIBER OPTIC CABLE, F&I, UNDERGROUND,2-12 FIBERS | Material | Linear Feet |  | 8
3403-HC-0633-1124 | FIBER OPTIC CABLE, F&I, UNDERGROUND, 97 - 144 FIB | Material | Linear Feet |  | 8
3403-HC-0633-1620 | FIBER OPTIC CABLE, REMOVE, UNDERGROUND | Material | Linear Feet |  | 8
3403-HC-0633-2-31 | FIBER OPTIC CONNECTION, INSTALL, SPLICE | Material | Each |  | 8
3403-HC-0633-2-32 | FIBER OPTIC CONNECTION, INSTALL, TERMINATION | Material | Each |  | 8
3403-HC-0633-3-11 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE ENCLO | Material | Each |  | 8
3403-HC-0633-3-12 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE TRAY | Material | Each |  | 8
3403-HC-0633-3-14 | FIBER OPTIC CONNECTION HARDWARE, F&I, BUFFER TUBE | Material | Each |  | 8
3403-HC-0633-3-15 | FIBER OPTIC CONNECTION HARDWARE, F&I, PRETERMINATE | Material | Each |  | 8
3403-HC-0633-3-16 | FIBER OPTIC CONNECTION HARDWARE, F&I, PATCH PANEL- | Material | Each |  | 8
3403-HC-0635-2-11 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-HC-0635-2-12 | PULL & SPLICE BOX, F&I, 24" X 36" COVER SIZE | Material | Each |  | 8
3403-HC-0635-2-13 | PULL & SPLICE BOX, F&I, 30" X 60" RECTANGULAR OR | Material | Each |  | 8
3403-HC-0639-1112 | ELECTRICAL POWER SERVICE, F&I, OVERHEAD METER PURC | Material | Each |  | 8
3403-HC-0639-1122 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-HC-0639-1620 | ELECTRICAL POWER SERVICE, REMOVE UNDERGROUND | Material | Each |  | 8
3403-HC-0639-2-1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | Material | Linear Feet |  | 8
3403-HC-0639-2-6 | ELECTRICAL SERVICE WIRE, REMOVE | Material | Linear Feet |  | 8
3403-HC-0639-3-11 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | Material | Each |  | 8
3403-HC-0639-3-60 | ELECTRICAL SERVICE DISCONNECT, REMOVE- POLE OR CAB | Material | Each |  | 8
3403-HC-0639-5-5 | EMERGENCY GENERATOR-PERMANENT, UP TO 25 KW, PROJEC | Material | Each |  | 8
3403-HC-0641-2-12 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-HC-0641-2-19 | PRESTRESSED CONCRETE POLE, F&I, CUSTOM DESIGN | Material | Each |  | 8
3403-HC-0641-2-60 | PRESTRESSED CONCRETE POLE, COMPLETE POLE REMOVAL- | Material | Each |  | 8
3403-HC-0641-2-80 | PRESTRESSED CONCRETE POLE, COMPLETE POLE REMOVAL- | Material | Each |  | 8
3403-HC-0641-3263 | CONCRETE CCTV POLE, FURNISH & INSTALL WITHOUT LOWE | Material | Each |  | 8
3403-HC-0641-3269 | CONCRETE CCTV POLE, FURNISH & INSTALL WITHOUT LOWE | Material | Each |  | 8
3403-HC-0660-3-11 | VEHICLE DETECTION SYSTEM- MICROWAVE, FURNISH & INS | Material | Each |  | 8
3403-HC-0660-3-12 | VEHICLE DETECTION SYSTEM- MICROWAVE, FURNISH & INS | Material | Each |  | 8
3403-HC-0660-3-60 | VEHICLE DETECTION SYSTEM - MICROWAVE, REMOVE, COM | Material | Each |  | 8
3403-HC-0660-6121 | VEHICLE DETECTION SYSTEM- AVI, BLUETOOTH, FURNISH | Material | Each |  | 8
3403-HC-0660-6122 | VEHICLE DETECTION SYSTEM- AVI, BLUETOOTH, FURNISH | Material | Each |  | 8
3403-HC-0660-6600 | VEHICLE DETECTION SYSTEM- AVI, REMOVE COMPLETE SYS | Material | Each |  | 8
3403-HC-0676-2121 | ITS CABINET, FURNISH & INSTALL, POLE MOUNT WITH SU | Material | Each |  | 8
3403-HC-0676-2122 | ITS CABINET, FURNISH & INSTALL, POLE MOUNT WITH SU | Material | Each |  | 8
3403-HC-0676-2144 | ITS CABINET, FURNISH & INSTALL, BASE MOUNT, 340, 4 | Material | Each |  | 8
3403-HC-0676-2500 | ITS CABINET- ADJUST/MODIFY | Material | Each |  | 8
3403-HC-0676-2600 | ITS CABINET- REMOVE | Material | Each |  | 8
3403-HC-0682-1113 | ITS CCTV CAMERA, F&I, DOME PTZ ENCLOSURE - PRESSU | Material | Each |  | 8
3403-HC-0682-1600 | ITS CCTV CAMERA,, REMOVE & DISPOSAL | Material | Each |  | 8
3403-HC-0684-1-1 | MANAGED FIELD ETHERNET SWITCH, FURNISH & INSTALL | Material | Each |  | 8
3403-HC-0684-2-1 | DEVICE SERVER, FURNISH & INSTALL | Material | Each |  | 8
3403-HC-0684-5-1 | MEDIA CONVERTER, FURNISH & INSTALL | Material | Each |  | 8
3403-HC-0685-1-11 | UNINTERRUPTIBLE POWER SUPPLY, FURNISH AND INSTALL, | Material | Each |  | 8
3403-HC-0700-8136 | FRONT ACCESS DYNAMIC MESSAGE SIGN, FURNISH & INSTA | Material | Each |  | 8
3403-HC-0700-9137 | WALK-IN DYNAMIC MESSAGE SIGN, FURNISH & INSTALL- W | Material | Each |  | 8
3403-HC-0700-10116 | DMS SUPPORT STRUCTURE, FURNISH & INSTALL, SPAN, 10 | Material | Each |  | 8
3403-HC-0700-10124 | DMS SUPPORT STRUCTURE, CANTILEVER, 41-50 FT | Material | Each |  | 8
3403-CT-0400-2-4 | CONC CLASS II, BRIDGE SUPERSTRUCTURE | Material | Cubic Yard |  | 8
3403-CT-0400-2-5 | CONCRETE CLASS II, BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 8
3403-CT-0400-2-10 | CONCRETE CLASS II, APPROACH SLABS | Material | Cubic Yard |  | 8
3403-CT-0400-4-5 | CONCRETE CLASS IV, BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 8
3403-CT-0400-4-25 | CONCRETE CLASS IV, MASS, SUBSTRUCTURE | Material | Cubic Yard |  | 8
3403-CT-0400-7 | BRIDGE DECK GROOVING, LESS THAN 8.5" | Material | Square Yard |  | 8
3403-CT-0400-9 | BRIDGE DECK GROOVING & PLANING, DECK 8.5" AND GREA | Material | Square Yard |  | 8
3403-CT-0400147 | COMPOSITE NEOPRENE PADS | Material | Cubic Feet |  | 8
3403-CT-0415-1-4 | REINFORCING STEEL - BRIDGE SUPERSTRUCTURE | Material | Per Pound |  | 8
3403-CT-0415-1-5 | REINFORCING STEEL- BRIDGE SUBSTRUCTURE | Material | Per Pound |  | 8
3403-CT-0415-1-9 | REINFORCING STEEL- APPROACH SLABS | Material | Per Pound |  | 8
3403-CT-0450-2-36 | PREST BEAMS: FLORIDA-I BEAM 36" | Material | Linear Feet |  | 8
3403-CT-0450-2-45 | PREST BEAMS: FLORIDA-I BEAM 45" | Material | Linear Feet |  | 8
3403-CT-0450-2-54 | PREST BEAMS: FLORIDA-I BEAM 54" | Material | Linear Feet |  | 8
3403-CT-0455-34-5 | PRESTRESSED CONCRETE PILING, 24" SQ | Material | Linear Feet |  | 8
3403-CT-0455143-5 | TEST PILES-PRESTRESSED CONCRETE,24" SQ | Material | Linear Feet |  | 8
3403-CT-0458-1-11 | BRIDGE DECK EXPANSION JOINT, NEW CONSTRUCTION, F&I | Material | Linear Feet |  | 8
3403-CT-0459-71 | PILES, POLYETHYLENE SHEETING | Material | Square Yard |  | 8
3403-CT-0520-5-26 | TRAFFIC SEPARATOR CONCRETE- TYPE II, 8.5' WIDE | Material | Linear Feet |  | 8
3403-CT-0521-5-1 | CONCRETE TRAFFIC RAILING, BRIDGE 32" F - SHAPE | Material | Linear Feet |  | 8
3403-CT-0521-5-6 | CONCRETE TRAFFIC RAILING- BRIDGE, CORRAL W/CURB | Material | Linear Feet |  | 8
3403-CT-0521-5-7 | CONCRETE TRAFFIC RAILING, BRIDGE, CORRAL W/O CURB | Material | Linear Feet |  | 8
3403-CT-0521-6-11 | CONCRETE PARAPET, PEDESTRIAN/BICYCLE, 27" HEIGHT | Material | Linear Feet |  | 8
3403-CT-0521-8-5 | CONC TRAFF RAIL BARR, W/JCT SLAB CORRAL W/CURB | Material | Linear Feet |  | 8
3403-CT-0521-8-6 | CONC TRAFF RAIL BARR, W/JCT SLAB CORRAL W/O CURB | Material | Linear Feet |  | 8
3403-CT-0524-2-2 | CONCRETE SLOPE PAVEMENT,NON REINFORCED, 4" | Material | Square Yard |  | 8
3403-CT-0548-12-1 | RETAINING WALL SYSTEM, PERMANENT, EXCLUDING BARRIER | Material | Square Feet |  | 8
3403-CT-0550-10222-1 | FENCING, TYPE B, 5.1-6.0, W/ VINYL COATING | Material | Linear Feet |  | 8
3403-CT-0550-10353 | FENCING, TYPE R, 8.1 - 10.0', WITH FULL ENCLOSURE | Material | Linear Feet |  | 8
3403-CT-0550-10363 | FENCING, TYPE R, GREATER THAN 10.0', WITH FULL ENC | Material | Linear Feet |  | 8
3403-CT-0101-1 | MOBILIZATION | Material | Lump Sum |  | 8
3403-CT-0102-1 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
3403-CT-0102-2-3 | SPECIAL DETOUR 3 | Material | Lump Sum |  | 8
3403-CT-0102-2-5 | SPECIAL DETOUR 5 | Material | Lump Sum |  | 8
3403-CT-0102-3 | COMMERCIAL MATERIAL FOR TEMPORARY DRIVEWAY MAINTEN | Material | Cubic Yard |  | 8
3403-CT-0102-14 | TRAFFIC CONTROL OFFICER | Material | Hour |  | 8
3403-CT-0102-60 | WORK ZONE SIGN | Material | Day |  | 8
3403-CT-0102-71-13 | TEMPORARY BARRIER, F&I, LOW PROFILE, CONCRETE | Material | Linear Feet |  | 8
3403-CT-0102-71-14 | TEMPORARY BARRIER, F & I, TYPE K | Material | Linear Feet |  | 8
3403-CT-0102-71-23 | TEMPORARY BARRIER, RELOCATE, LOW PROFILE, CONCRETE | Material | Linear Feet |  | 8
3403-CT-0102-71-24 | TEMPORARY BARRIER, RELOCATE, TYPE K | Material | Linear Feet |  | 8
3403-CT-0102-74-1 | CHANNELIZING DEVICE- TYPES I, II, DI, VP, DRUM, OR | Material | Day |  | 8
3403-CT-0102-74-2 | CHANNELIZING DEVICE, TYPE III, 6' | Material | Day |  | 8
3403-CT-0102-78 | TEMPORARY RETROREFLECTIVE PAVEMENT MARKER | Material | Each |  | 8
3403-CT-0102-89-1 | TEMPORARY CRASH CUSHION, REDIRECTIVE OPTION | Material | Location |  | 8
3403-CT-0102-99 | PORTABLE CHANGEABLE MESSAGE SIGN, TEMPORARY | Material | Day |  | 8
3403-CT-0102150-1 | PORTABLE REGULATORY, SIGN | Material | Day |  | 8
3403-CT-0102150-2 | RADAR SPEED DISPLAY UNIT | Material | Day |  | 8
3403-CT-0102909 | TEMPORARY RAISED RUMBLE STRIPS- PER DAY, INCLUDES | Material | Day |  | 8
3403-CT-0104-1 | ARTIFICIAL COVERINGS /ROLLED EROSION CONTROL PRODU | Material | Square Yard |  | 8
3403-CT-0104-10-3 | SEDIMENT BARRIER | Material | Linear Feet |  | 8
3403-CT-0104-15 | SOIL TRACKING PREVENTION DEVICE | Material | Each |  | 8
3403-CT-0104-18 | INLET PROTECTION SYSTEM | Material | Each |  | 8
3403-CT-0107-1 | LITTER REMOVAL | Material |  |  | 8
3403-CT-0107-2 | MOWING | Material |  |  | 8
3403-CT-0108-1 | MONITOR EXISTING STRUCTURES- INSPECTION AND SETTL(Cardinal,Pine Meadow) | Material | Lump Sum |  | 8
3403-CT-0110-1-1 | CLEARING & GRUBBING (Citrus County) | Material | Lump Sum |  | 8
3403-CT-0110-2-2 | SELECTIVE CLEARING AND GRUBBING, AREAS WITH TREES | Material |  |  | 8
3403-CT-0110-7-1 | MAILBOX, F&I SINGLE | Material | Each |  | 8
3403-CT-0120-1900 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3403-CT-0120-4900 | SUBSOIL EXCAVATION | Material | Cubic Yard |  | 8
3403-CT-0120-6900 | EMBANKMENT | Material | Cubic Yard |  | 8
3403-CT-0121-70 | FLOWABLE FILL | Material | Cubic Yard |  | 8
3403-CT-0145-2 | GEOSYNTHETIC REINFORCED FOUNDATION OVER SOFT SOIL | Material | Square Yard |  | 8
3403-CT-0160-4900 | TYPE B STABILIZATION | Material | Square Yard |  | 8
3403-CT-0162-1-11 | PREPARED SOIL LAYER, FINISH SOIL LAYER, 6" | Material | Square Yard |  | 8
3403-CT-0173-76 | GROUT PIPE INSTALLATION | Material | Linear Feet |  | 8
3403-CT-0173-77-1 | SUBSURFACE PRESSURE GROUTING, SAND CEMENT | Material | Cubic Yard |  | 8
3403-CT-0285701900 | OPTIONAL BASE, BASE GROUP 01 | Material | Square Yard |  | 8
3403-CT-0285704 | OPTIONAL BASE, BASE GROUP 04 | Material | Square Yard |  | 8
3403-CT-0285709900 | OPTIONAL BASE, BASE GROUP 09 | Material | Square Yard |  | 8
3403-CT-0286-1 | TURNOUT CONSTRUCTION | Material | Square Yard |  | 8
3403-CT-0327-70-1 | MILLING EXIST ASPH PAVT, 1" AVG DEPTH | Material | Square Yard |  | 8
3403-CT-0334-1-12 | SUPERPAVE ASPHALTIC CONC, TRAFFIC B | Material |  |  | 8
3403-CT-0334-1-13 | SUPERPAVE ASPHALTIC CONC, TRAFFIC C | Material |  |  | 8
3403-CT-0334-1-52 | SUPERPAVE ASPHALTIC CONCRETE, TRAFFIC B, PG76-22 | Material |  |  | 8
3403-CT-0334-1-53 | SUPERPAVE ASPHALTIC CONCRETE, TRAFFIC C, PG76-22 | Material |  |  | 8
3403-CT-0337-7-25 | ASPHALT CONCRETE FRICTION COURSE, INC BIT, FC-5, | Material |  |  | 8
3403-CT-0337-7-80 | ASPHALT CONCRETE FRICTION COURSE,TRAFFIC B, FC-9.5 | Material |  |  | 8
3403-CT-0339-1 | MISCELLANEOUS ASPHALT PAVEMENT (U/GUARDRAIL,OTHER) | Material |  |  | 8
3403-CT-0400-1-2 | CONCRETE CLASS I, ENDWALLS | Material | Cubic Yard |  | 8
3403-CT-0425-1351 | INLETS, CURB, TYPE P-5, <10' | Material | Each |  | 8
3403-CT-0425-1511 | INLETS, DT BOT, TYPE B, <10' | Material | Each |  | 8
3403-CT-0425-1513 | INLETS, DT BOT, TYPE B, J BOT, <10' | Material | Each |  | 8
3403-CT-0425-1521 | INLETS, DT BOT, TYPE C,<10' | Material | Each |  | 8
3403-CT-0425-1541 | INLETS, DT BOT, TYPE D, <10' | Material | Each |  | 8
3403-CT-0425-1549 | INLETS, DT BOT, TYPE D, MODIFY | Material | Each |  | 8
3403-CT-0425-1701 | INLETS, GUTTER, TYPE S, <10' | Material | Each |  | 8
3403-CT-0425-1711 | INLETS, GUTTER, TYPE V, <10' | Material | Each |  | 8
3403-CT-0425-1891 | INLETS, BARRIER WALL, <10' | Material | Each |  | 8
3403-CT-0425-2-61 | MANHOLES, P-8, <10' | Material | Each |  | 8
3403-CT-0425-2-62 | MANHOLES, P-8, >10' | Material | Each |  | 8
3403-CT-0425-2-92 | MANHOLES, J-8, >10' | Material | Each |  | 8
3403-CT-0425-2124 | DRAINAGE MANHOLE, PROJECT 405270-3-52-01, J-7 >10 | Material | Each |  | 8
3403-CT-0430-173118 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 18", GD | Material | Linear Feet |  | 8
3403-CT-0430173124 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 24", GD | Material | Linear Feet |  | 8
3403-CT-0430174118 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 18"SD | Material | Linear Feet |  | 8
3403-CT-0430174218 | PIPE CULVERT, OPTIONAL MATERIAL, OTHER SHAPE - ELL,18" SD | Material | Linear Feet |  | 8
3403-CT-0430175118 | PIPE CULVERT,OPTIONAL MATERIAL,ROUND, 18"S/CD | Material | Linear Feet |  | 8
3403-CT-0430175124 | PIPE CULVERT,OPTIONAL MATERIAL,ROUND, 24"S/CD | Material | Linear Feet |  | 8
3403-CT-0430175130 | PIPE CULVERT, OPT MATERIAL, ROUND, 30"S/CD | Material | Linear Feet |  | 8
3403-CT-0430175136 | PIPE CULVERT, OPT MATERIAL, ROUND, 36"S/CD | Material | Linear Feet |  | 8
3403-CT-0430175218 | PIPE CULVERT,OPTIONAL MATERIAL,OTHER-ELIP/ARCH, 18" S/CD | Material | Linear Feet |  | 8
3403-CT-0430175260 | PIPE CULVERT, OPT MATERIAL, OTHER SHAPE - ELIP/ARC 60" S/CD | Material | Linear Feet |  | 8
3403-CT-0430610225 | U-ENDWALL, STD 261, 1:3 SLOPE, 18"PIPE | Material | Each |  | 8
3403-CT-0430611029 | U-ENDWALL, STD 261, BAFFLES, 1:6 SLOPE, 24"PIPE | Material | Each |  | 8
3403-CT-0430611125 | U-ENDWALL WITH BAFFLES, STD 261, 1:4 SLOPE, 18"PIP | Material | Each |  | 8
3403-CT-0430611129 | U-ENDWALL WITH BAFFLES, STD 261, 1:4 SLOPE, 24"PIP | Material | Each |  | 8
3403-CT-0430611133 | U-ENDWALL WITH BAFFLES,STD 261,1:4 SLOPE,30"PIPE | Material | Each |  | 8
3403-CT-0430611225 | U-ENDWALL WITH BAFFLES, STD 261, 1:3 SLOPE, 18"PIP | Material | Each |  | 8
3403-CT-0430611229 | U-ENDWALL WITH BAFFLES, STD 261, 1:3 SLOPE, 24"PIP | Material | Each |  | 8
3403-CT-0430611233 | U-ENDWALL, STD 261, BAFFLES, 1:3 SLOPE, 30"PIPE | Material | Each |  | 8
3403-CT-0430611325 | U-ENDWALL WITH BAFFLES, STD 261, 1:2 SLOPE, 18"PIP | Material | Each |  | 8
3403-CT-0430612025 | U-ENDWALL WITH GRATE, STD 261, 1:6 SLOPE, 18"PIPE | Material | Each |  | 8
3403-CT-0430612029 | U-ENDWALL WITH GRATE, STD 261, 1:6 SLOPE, 24"PIPE | Material | Each |  | 8
3403-CT-0430612033 | U-ENDWALL WITH GRATE, STD 261, 1:6 SLOPE, 30" | Material | Each |  | 8
3403-CT-0430613025 | U-ENDWALL, WITH BAFFLES & GRATE, STD 261,1:6 SLOPE | Material | Each |  | 8
3403-CT-0430613029 | U-ENDWALL, WITH BAFFLES & GRATE, STD 261,1:6 SLOPE | Material | Each |  | 8
3403-CT-0430982125 | MITERED END SECTION, OPTIONAL ROUND, 18" CD | Material | Each |  | 8
3403-CT-0430982129 | MITERED END SECTION, OPTIONAL ROUND, 24" CD | Material | Each |  | 8
3403-CT-0430982133 | MITERED END SECTION, OPTIONAL ROUND, 30" CD | Material | Each |  | 8
3403-CT-0430982625 | MITERED END SECTION, OPTIONAL - ELLIPTICAL / ARCH, 18"CD | Material | Each |  | 8
3403-CT-0430984125 | MITERED END SECTION, OPTIONAL ROUND, 18" SD | Material | Each |  | 8
3403-CT-0430984133 | MITERED END SECTION , OPTIONAL ROUND, 30" SD | Material | Each |  | 8
3403-CT-0430984625 | MITERED END SECT, OPTIONAL - ELLIPTICAL / ARCH, 18" SD | Material | Each |  | 8
3403-CT-0519-78 | BOLLARDS | Material | Each |  | 8
3403-CT-0520-1-7 | CONCRETE CURB & GUTTER, TYPE E | Material | Linear Feet |  | 8
3403-CT-0520-2-4 | CONCRETE CURB, TYPE D | Material | Linear Feet |  | 8
3403-CT-0520-3 | VALLEY GUTTER- CONCRETE | Material | Linear Feet |  | 8
3403-CT-0520-5-16 | TRAFFIC SEPARATOR CONCRETE- TYPE I, 8.5' WIDE | Material | Linear Feet |  | 8
3403-CT-0520-6 | SHOULDER GUTTER- CONCRETE | Material | Linear Feet |  | 8
3403-CT-0521-1 | MEDIAN CONCRETE BARRIER WALL | Material | Linear Feet |  | 8
3403-CT-0521-8-1 | CONC TRAFF RAIL BARR W/ JCT SLAB 32" F | Material | Linear Feet |  | 8
3403-CT-0521-72-3 | SHOULDER CONC BARR, RIGID-SHOULDER 32" | Material | Linear Feet |  | 8
3403-CT-0522-1 | CONCRETE SIDEWALK AND DRIVEWAYS, 4" THICK | Material | Square Yard |  | 8
3403-CT-0522-2 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THICK | Material | Square Yard |  | 8
3403-CT-0524-1-1 | CONCRETE DITCH PAVT, NON REINFORCED, 3" | Material | Square Yard |  | 8
3403-CT-0524-1-29 | CONCRETE DITCH PAVEMENT, 4", REINFORCED | Material | Square Yard |  | 8
3403-CT-0527-2 | DETECTABLE WARNINGS | Material | Square Feet |  | 8
3403-CT-0530-3-4 | RIPRAP, RUBBLE, F&I, DITCH LINING | Material |  |  | 8
3403-CT-0536-1-1 | GUARDRAIL -ROADWAY, GENERAL TL-3 | Material | Linear Feet |  | 8
3403-CT-0536-6 | PIPE RAIL FOR GUARDRAIL | Material | Linear Feet |  | 8
3403-CT-0536-7-2 | SPECIAL GUARDRAIL POST- SPECIAL STEEL POST FOR CON | Material | Each |  | 8
3403-CT-0536-8-11 | APPROACH TRANSITION TO RIGID BARRIER- BRIDGE ANCHORAGE ASSEMBLY | Material | Each |  | 8
3403-CT-0536-8-13 | APPROACH TRANSITION CONNECTION TO RIGID BARRIER, CB | Material | Each |  | 8
3403-CT-0536-73 | GUARDRAIL REMOVAL | Material | Linear Feet |  | 8
3403-CT-0536-85-22 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- FLARED | Material | Each |  | 8
3403-CT-0536-85-25 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- TYPE II | Material | Each |  | 8
3403-CT-0542-70 | BUMPER GUARDS, CONCRETE | Material | Each |  | 8
3403-CT-0544-75-1 | CRASH CUSHION | Material | Each |  | 8
3403-CT-0546-72-55 | RUMBLE STRIPS, GROUND-IN, 16" SHOULDER | Material | Mile |  | 8
3403-CT-0548-12 | RETAINING WALL SYSTEM, PERMANENT, EXCLUDING BARRIER | Material | Square Feet |  | 8
3403-CT-0550-10110 | FENCING, TYPE A, 0.0-5.0', STANDARD | Material | Linear Feet |  | 8
3403-CT-0550-10120 | FENCING, TYPE A, 5.1-6.0, STANDARD | Material | Linear Feet |  | 8
3403-CT-0550-10222 | FENCING, TYPE B, 5.1-6.0, W/ VINYL COATING | Material | Linear Feet |  | 8
3403-CT-0550-10256 | FENCING, TYPE B, 8-10.0', WITH VINYL COATING AND BARBED WIRE | Material | Linear Feet |  | 8
3403-CT-0550-60124 | FENCE GATE, TYPE A, DOUBLE, 18.1-20.0' OPENING | Material | Each |  | 8
3403-CT-0550-60211 | FENCE GATE, TYPE B, SINGLE, 0- 6.0' OPENING | Material | Each |  | 8
3403-CT-0550-60224 | FENCE GATE, TYPE B, DOUBLE, 18.1-20.0' OPENING | Material | Each |  | 8
3403-CT-0570-1-1 | PERFORMANCE TURF | Material | Square Yard |  | 8
3403-CT-0570-1-2 | PERFORMANCE TURF, SOD | Material | Square Yard |  | 8
3403-CT-0710-11101 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Mile |  | 8
3403-CT-0710-11102 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Mile |  | 8
3403-CT-0710-11123 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Linear Feet |  | 8
3403-CT-0710-11125 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID | Material | Linear Feet |  | 8
3403-CT-0710-11170 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, ARROW | Material | Each |  | 8
3403-CT-0710-11201 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLI | Material | Mile |  | 8
3403-CT-0710-11202 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLI | Material | Mile |  | 8
3403-CT-0710-11223 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLI | Material | Linear Feet |  | 8
3403-CT-0710-11224 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLI | Material | Linear Feet |  | 8
3403-CT-0710-11241 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, 2-4 | Material | Mile |  | 8
3403-CT-0751-42-1 | BIRD HOUSE | Material | Each |  | 8
3403-CT-0999-25 | INITIAL CONTINGENCY AMOUNT, DO NOT BID 405270352 | Material | Lump Sum |  | 8
3403-CT-0700-1-11 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12 SF | Material | Each |  | 8
3403-CT-0700-1-12 | SINGLE POST SIGN, F&I GROUND MOUNT, 12-20 SF | Material | Each |  | 8
3403-CT-0700-1-13 | SINGLE POST SIGN, F&I GROUND MOUNT, 21-30 SF | Material | Each |  | 8
3403-CT-0700-1-50 | SINGLE POST SIGN, RELOCATE | Material | Each |  | 8
3403-CT-0700-1-60 | SINGLE POST SIGN, REMOVE | Material | Each |  | 8
3403-CT-0700-2-13 | MULTI- POST SIGN, F&I GROUND MOUNT, 21-30 SF | Material | Each |  | 8
3403-CT-0700-2-14 | MULTI- POST SIGN, F&I GROUND MOUNT, 31-50 SF | Material | Each |  | 8
3403-CT-0700-2-16 | MULTI- POST SIGN, F&I GROUND MOUNT, 101-200 SF | Material | Each |  | 8
3403-CT-0700-2-17 | MULTI- POST SIGN, F&I GROUND MOUNT, 201-300 SF | Material | Each |  | 8
3403-CT-0700-2-18 | MULTI- POST SIGN, F&I GROUND MOUNT, 301-400 SF | Material | Each |  | 8
3403-CT-0700-3601 | SIGN PANEL, REMOVE, UP TO 12 SF | Material | Each |  | 8
3403-CT-0700-13-12 | RETROREFLECTIVE SIGN STRIP- FURNISH AND INSTALL, 2' | Material | Each |  | 8
3403-CT-0705-10-1 | OBJECT MARKER, TYPE 1 | Material | Each |  | 8
3403-CT-0705-10-4 | OBJECT MARKER, TYPE 4 | Material | Each |  | 8
3403-CT-0705-11-1 | DELINEATOR, FLEXIBLE TUBULAR | Material | Each |  | 8
3403-CT-0710-90 | PAINTED PAVEMENT MARKINGS, FINAL SURFACE 4052703 | Material | Lump Sum |  | 8
3403-CT-0711-11102 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 8" FOR INT | Material | Mile |  | 8
3403-CT-0711-11123 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 12" FOR CRO | Material | Linear Feet |  | 8
3403-CT-0711-11124 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 18" FOR DIA | Material | Linear Feet |  | 8
3403-CT-0711-11125 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 24" FOR STO | Material | Linear Feet |  | 8
3403-CT-0711-11141 | THERMOPLASTIC, STANDARD, WHITE, 2-4 DOTTED GUIDELI | Material | Mile |  | 8
3403-CT-0711-11142 | THERMOPLASTIC, STANDARD, WHITE, 2-4 DOTTED GUIDELI | Material | Mile |  | 8
3403-CT-0711-11160 | THERMOPLASTIC, STANDARD, WHITE, MESSAGE OR SYMBOL | Material | Each |  | 8
3403-CT-0711-11170 | THERMOPLASTIC, STANDARD, WHITE, ARROW | Material | Each |  | 8
3403-CT-0711-11180 | THERMOPLASTIC, STANDARD, WHITE, YIELD LINE | Material | Linear Feet |  | 8
3403-CT-0711-11224 | THERMOPLASTIC, STANDARD, YELLOW, SOLID, 18" FOR DI | Material | Linear Feet |  | 8
3403-CT-0711-11241 | THERMOPLASTIC, STANDARD, YELLOW, 2-4 DOTTED GUIDE | Material | Mile |  | 8
3403-CT-0711-11421 | THERMOPLASTIC, STANDARD, BLUE, SOLID,6" | Material | Linear Feet |  | 8
3403-CT-0711-14125 | THERMOPLASTIC, PREFORMED, WHITE, SOLID, 24" FOR C | Material | Linear Feet |  | 8
3403-CT-0711-14160 | THERMOPLASTIC, PREFORMED, WHITE, MESSAGE | Material | Each |  | 8
3403-CT-0711-14170 | THERMOPLASTIC, PREFORMED, WHITE, ARROW | Material | Each |  | 8
3403-CT-0711-15101 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-CT-0711-15102 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-CT-0711-15131 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-CT-0711-15201 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-CT-0711-15202 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-CT-0711-16101 | THERMOPLASTIC, STANDARD-OTHER SURFACES, WHITE, SOL | Material | Mile |  | 8
3403-CT-0711-16201 | THERMOPLASTIC, STANDARD-OTHER SURFACES, YELLOW, SO | Material | Mile |  | 8
3403-CT-0713103101 | PERMANENT TAPE, WHITE, SOLID, 6" FOR CONCRETE BRID | Material | Mile |  | 8
3403-CT-0713103102 | PERMANENT TAPE, WHITE, SOLID, 8" EXIT LANE AT INTE | Material | Mile |  | 8
3403-CT-0713103131 | PERMANENT TAPE, WHITE, SKIP/DOTTED, 6" FOR CONCRE | Material | Mile |  | 8
3403-CT-0713103201 | PERMANENT TAPE, YELLOW, SOLID, 6" FOR CONCRETE BRI | Material | Mile |  | 8
3403-CT-0713103331 | PERMANENT TAPE, BLACK, SKIP/DOTTED, 6" FOR CONCRE | Material | Mile |  | 8
3403-CT-0630-2-11-1 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-CT-0630-2-12-1 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-CT-0630-2-15 | CONDUIT, FURNISH & INSTALL, BRIDGE MOUNT | Material | Linear Feet |  | 8
3403-CT-0635-2-11-2 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-CT-0635-3-11 | JUNCTION BOX, FURNISH & INSTALL, AERIAL | Material | Each |  | 8
3403-CT-0641-2-12-2 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-CT-0715-1-12 | LIGHTING CONDUCTORS, F&I, INSULATED, NO.8 - 6 | Material | Linear Feet |  | 8
3403-CT-0715-1-13 | LIGHTING CONDUCTORS, F&I, INSULATED, NO 4 TO NO 2 | Material | Linear Feet |  | 8
3403-CT-0715-4-12 | LIGHT POLE COMPLETE, FURNISH & INSTALL STANDARD PO | Material | Each |  | 8
3403-CT-0715-4-14 | LIGHT POLE COMPLETE, FURNISH & INSTALL STANDARD PO | Material | Each |  | 8
3403-CT-0715-7-11 | LOAD CENTER, F&I, SECONDARY VOLTAGE | Material | Each |  | 8
3403-CT-0715-11125 | LUMINAIRE, F&I, UNDER DECK, WALL MOUNT | Material | Each |  | 8
3403-CT-0715500-1 | POLE CABLE DISTRIBUTION SYSTEM, CONVENTIONAL | Material | Each |  | 8
3403-CT-0715500-3 | POLE CABLE DISTRIBUTION SYSTEM, WALL MOUNT | Material | Each |  | 8
3403-CT-0715516145 | LIGHT POLE COMPLETE- SPECIAL DESIGN, F&I, POLE TOP | Material | Each |  | 8
3403-CT-0735-74-1 | TOLL PLAZA, LOCATION 1 | Material | Lump Sum |  | 8
3403-CT-0400-0-11 | CONCRETE CLASS NS, GRAVITY WALL | Material | Cubic Yard |  | 8
3403-CT-0515-1-2 | PIPE HANDRAIL - GUIDERAIL, ALUMINUM | Material | Linear Feet |  | 8
3403-CT-0630-2-11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-CT-0630-2-12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-CT-0630-2-14 | CONDUIT, FURNISH & INSTALL, ABOVEGROUND | Material | Linear Feet |  | 8
3403-CT-0633-1121 | FIBER OPTIC CABLE, F&I, UNDERGROUND,2-12 FIBERS | Material | Linear Feet |  | 8
3403-CT-0633-1122 | FIBER OPTIC CABLE, F&I, UNDERGROUND,13-48 FIBERS | Material | Linear Feet |  | 8
3403-CT-0633-1124 | FIBER OPTIC CABLE, F&I, UNDERGROUND, 97 - 144 FIB | Material | Linear Feet |  | 8
3403-CT-0633-1620 | FIBER OPTIC CABLE, REMOVE, UNDERGROUND | Material | Linear Feet |  | 8
3403-CT-0633-2-31 | FIBER OPTIC CONNECTION, INSTALL, SPLICE | Material | Each |  | 8
3403-CT-0633-2-32 | FIBER OPTIC CONNECTION, INSTALL, TERMINATION | Material | Each |  | 8
3403-CT-0633-3-11 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE ENCLO | Material | Each |  | 8
3403-CT-0633-3-12 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE TRAY | Material | Each |  | 8
3403-CT-0633-3-14 | FIBER OPTIC CONNECTION HARDWARE, F&I, BUFFER TUBE | Material | Each |  | 8
3403-CT-0633-3-15 | FIBER OPTIC CONNECTION HARDWARE, F&I, PRETERMINATE | Material | Each |  | 8
3403-CT-0633-3-16 | FIBER OPTIC CONNECTION HARDWARE, F&I, PATCH PANEL- | Material | Each |  | 8
3403-CT-0635-2-11 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-CT-0635-2-12 | PULL & SPLICE BOX, F&I, 24" X 36" COVER SIZE | Material | Each |  | 8
3403-CT-0635-2-13 | PULL & SPLICE BOX, F&I, 30" X 60" RECTANGULAR OR | Material | Each |  | 8
3403-CT-0639-1112 | ELECTRICAL POWER SERVICE, F&I, OVERHEAD METER PURC | Material | Each |  | 8
3403-CT-0639-1122 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-CT-0639-2-1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | Material | Linear Feet |  | 8
3403-CT-0639-3-11 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | Material | Each |  | 8
3403-CT-0639-5-7 | EMERGENCY GENERATOR-PERMANENT, UP TO 25 KW, PROJEC | Material | Each |  | 8
3403-CT-0641-2-12 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-CT-0641-2-19 | PRESTRESSED CONCRETE POLE, F&I, CUSTOM DESIGN | Material | Each |  | 8
3403-CT-0641-3263 | CONCRETE CCTV POLE, FURNISH & INSTALL WITHOUT LOWE | Material | Each |  | 8
3403-CT-0641-3269 | CONCRETE CCTV POLE, FURNISH & INSTALL WITHOUT LOWE | Material | Each |  | 8
3403-CT-0660-3-11 | VEHICLE DETECTION SYSTEM- MICROWAVE, FURNISH & INS | Material | Each |  | 8
3403-CT-0660-3-12 | VEHICLE DETECTION SYSTEM- MICROWAVE, FURNISH & INS | Material | Each |  | 8
3403-CT-0660-6121 | VEHICLE DETECTION SYSTEM- AVI, BLUETOOTH, FURNISH | Material | Each |  | 8
3403-CT-0660-6122 | VEHICLE DETECTION SYSTEM- AVI, BLUETOOTH, FURNISH | Material | Each |  | 8
3403-CT-0676-2121 | ITS CABINET, FURNISH & INSTALL, POLE MOUNT WITH SU | Material | Each |  | 8
3403-CT-0676-2122 | ITS CABINET, FURNISH & INSTALL, POLE MOUNT WITH SU | Material | Each |  | 8
3403-CT-0676-2143 | ITS CABINET, FURNISH & INSTALL, BASE MOUNT, 334, 2 | Material | Each |  | 8
3403-CT-0676-2144 | ITS CABINET, FURNISH & INSTALL, BASE MOUNT, 340, 4 | Material | Each |  | 8
3403-CT-0682-1113 | ITS CCTV CAMERA, F&I, DOME PTZ ENCLOSURE - PRESSU | Material | Each |  | 8
3403-CT-0684-1-1 | MANAGED FIELD ETHERNET SWITCH, FURNISH & INSTALL | Material | Each |  | 8
3403-CT-0684-2-1 | DEVICE SERVER, FURNISH & INSTALL | Material | Each |  | 8
3403-CT-0684-5-1 | MEDIA CONVERTER, FURNISH & INSTALL | Material | Each |  | 8
3403-CT-0685-1-11 | UNINTERRUPTIBLE POWER SUPPLY, FURNISH AND INSTALL, | Material | Each |  | 8
3403-CT-0687-1100 | HIGHWAY ADVISORY RADIO, FURNISH & INSTALL, AC POWE | Material | Each |  | 8
3403-CT-0700-8136 | FRONT ACCESS DYNAMIC MESSAGE SIGN, FURNISH & INSTA | Material | Each |  | 8
3403-CT-0700-10123 | DMS SUPPORT STRUCTURE, CANTILEVER, 31-40 FT | Material | Each |  | 8
3403-CT-0700-10124 | DMS SUPPORT STRUCTURE, CANTILEVER, 41-50 FT | Material | Each |  | 8
3403-DB-0400-2-4 | CONC CLASS II, BRIDGE SUPERSTRUCTURE | Material | Cubic Yard |  | 8
3403-DB-0400-2-5 | CONCRETE CLASS II, BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 8
3403-DB-0400-2-10 | CONCRETE CLASS II, APPROACH SLABS | Material | Cubic Yard |  | 8
3403-DB-0400-4-5 | CONCRETE CLASS IV, BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 8
3403-DB-0400-4-25 | CONCRETE CLASS IV, MASS, SUBSTRUCTURE | Material | Cubic Yard |  | 8
3403-DB-0400-7 | BRIDGE DECK GROOVING, LESS THAN 8.5" | Material | Square Yard |  | 8
3403-DB-0400-9 | BRIDGE DECK GROOVING & PLANING, DECK 8.5" AND GREA | Material | Square Yard |  | 8
3403-DB-0400147 | COMPOSITE NEOPRENE PADS | Material | Cubic Feet |  | 8
3403-DB-0415-1-4 | REINFORCING STEEL - BRIDGE SUPERSTRUCTURE | Material | Per Pound |  | 8
3403-DB-0415-1-5 | REINFORCING STEEL- BRIDGE SUBSTRUCTURE | Material | Per Pound |  | 8
3403-DB-0415-1-9 | REINFORCING STEEL- APPROACH SLABS | Material | Per Pound |  | 8
3403-DB-0450-2-36 | PREST BEAMS: FLORIDA-I BEAM 36" | Material | Linear Feet |  | 8
3403-DB-0450-2-45 | PREST BEAMS: FLORIDA-I BEAM 45" | Material | Linear Feet |  | 8
3403-DB-0450-2-63 | PREST BEAMS: FLORIDA-I BEAM 63" | Material | Linear Feet |  | 8
3403-DB-0455-34-5 | PRESTRESSED CONCRETE PILING, 24" SQ | Material | Linear Feet |  | 8
3403-DB-0455143-5 | TEST PILES-PRESTRESSED CONCRETE,24" SQ | Material | Linear Feet |  | 8
3403-DB-0458-1-11 | BRIDGE DECK EXPANSION JOINT, NEW CONSTRUCTION, F&I | Material | Linear Feet |  | 8
3403-DB-0459-71 | PILES, POLYETHYLENE SHEETING | Material | Square Yard |  | 8
3403-DB-0521-5-1 | CONCRETE TRAFFIC RAILING, BRIDGE 32" F - SHAPE | Material | Linear Feet |  | 8
3403-DB-0521-5-6 | CONCRETE TRAFFIC RAILING- BRIDGE, CORRAL W/CURB | Material | Linear Feet |  | 8
3403-DB-0521-5-7 | CONCRETE TRAFFIC RAILING, BRIDGE, CORRAL W/O CURB (4) | Material | Linear Feet |  | 8
3403-DB-0524-2-2 | CONCRETE SLOPE PAVEMENT,NON REINFORCED, 4" | Material | Square Yard |  | 8
3403-DB-0548-12 | RETAINING WALL SYSTEM, PERMANENT, EXCLUDING BARRIE | Material | Square Feet |  | 8
3403-DB-0101-1 | MOBILIZATION | Material | Lump Sum |  | 8
3403-DB-0102-1 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
3403-DB-0102-2-1 | SPECIAL DETOUR 1 | Material | Lump Sum |  | 8
3403-DB-0102-2-2 | SPECIAL DETOUR 2 | Material | Lump Sum |  | 8
3403-DB-0102-2-3 | SPECIAL DETOUR 3 | Material | Lump Sum |  | 8
3403-DB-0102-2-4 | SPECIAL DETOUR 4 | Material | Lump Sum |  | 8
3403-DB-0102-3 | COMMERCIAL MATERIAL FOR TEMPORARY DRIVEWAY MAINTEN | Material | Cubic Yard |  | 8
3403-DB-0102-14 | TRAFFIC CONTROL OFFICER | Material | Hour |  | 8
3403-DB-0102-60 | WORK ZONE SIGN | Material | Day |  | 8
3403-DB-0102-71-13 | TEMPORARY BARRIER, F&I, LOW PROFILE, CONCRETE | Material | Linear Feet |  | 8
3403-DB-0102-71-14 | TEMPORARY BARRIER, F & I, TYPE K | Material | Linear Feet |  | 8
3403-DB-0102-71-24 | TEMPORARY BARRIER, RELOCATE, TYPE K | Material | Linear Feet |  | 8
3403-DB-0102-74-1 | CHANNELIZING DEVICE- TYPES I, II, DI, VP, DRUM, OR | Material | Day |  | 8
3403-DB-0102-74-2 | CHANNELIZING DEVICE, TYPE III, 6' | Material | Day |  | 8
3403-DB-0102-76 | ARROW BOARD / ADVANCE WARNING ARROW PANEL | Material | Day |  | 8
3403-DB-0102-78 | TEMPORARY RETROREFLECTIVE PAVEMENT MARKER | Material | Each |  | 8
3403-DB-0102-89-1 | TEMPORARY CRASH CUSHION, REDIRECTIVE OPTION | Material | Location |  | 8
3403-DB-0102-99 | PORTABLE CHANGEABLE MESSAGE SIGN, TEMPORARY | Material | Day |  | 8
3403-DB-0102150-1 | PORTABLE REGULATORY, SIGN | Material | Day |  | 8
3403-DB-0102150-2 | RADAR SPEED DISPLAY UNIT | Material | Day |  | 8
3403-DB-0102911-2 | PAVEMENT MARKING REMOVABLE TAPE, WHITE OR BLACK,SO | Material | Linear Feet |  | 8
3403-DB-0104-1 | ARTIFICIAL COVERINGS /ROLLED EROSION CONTROL PRODU | Material | Square Yard |  | 8
3403-DB-0104-10-3 | SEDIMENT BARRIER | Material | Linear Feet |  | 8
3403-DB-0104-15 | SOIL TRACKING PREVENTION DEVICE | Material | Each |  | 8
3403-DB-0104-18 | INLET PROTECTION SYSTEM | Material | Each |  | 8
3403-DB-0107-1 | LITTER REMOVAL | Material |  |  | 8
3403-DB-0107-2 | MOWING | Material |  |  | 8
3403-DB-0110-1-1 | CLEARING & GRUBBING | Material | Lump Sum |  | 8
3403-DB-0110-2-2 | SELECTIVE CLEARING AND GRUBBING, AREAS WITH TREES | Material |  |  | 8
3403-DB-0110-7-1 | MAILBOX, F&I SINGLE | Material | Each |  | 8
3403-DB-0120-1900 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3403-DB-0120-4900 | SUBSOIL EXCAVATION | Material | Cubic Yard |  | 8
3403-DB-0120-6900 | EMBANKMENT | Material | Cubic Yard |  | 8
3403-DB-0145-2 | GEOSYNTHETIC REINFORCED FOUNDATION OVER SOFT SOIL | Material | Square Yard |  | 8
3403-DB-0160-4900 | TYPE B STABILIZATION | Material | Square Yard |  | 8
3403-DB-0162-1-11 | PREPARED SOIL LAYER, FINISH SOIL LAYER, 6" | Material | Square Yard |  | 8
3403-DB-0173-76 | GROUT PIPE INSTALLATION | Material | Linear Feet |  | 8
3403-DB-0173-77-1 | SUBSURFACE PRESSURE GROUTING, SAND CEMENT | Material | Cubic Yard |  | 8
3403-DB-0285701900 | OPTIONAL BASE, BASE GROUP 01 | Material | Square Yard |  | 8
3403-DB-0285704 | OPTIONAL BASE, BASE GROUP 04 | Material | Square Yard |  | 8
3403-DB-0285709900 | OPTIONAL BASE, BASE GROUP 09 | Material | Square Yard |  | 8
3403-DB-0327-70-1 | MILLING EXIST ASPH PAVT, 1" AVG DEPTH | Material | Square Yard |  | 8
3403-DB-0327-70-5 | MILLING EXIST ASPH PAVT, 2" AVG DEPTH | Material | Square Yard |  | 8
3403-DB-0327-70-19 | MILLING EXIST ASPH PAVT, 3/4" AVG DEPTH | Material | Square Yard |  | 8
3403-DB-0334-1-12 | SUPERPAVE ASPHALTIC CONC, TRAFFIC B | Material |  |  | 8
3403-DB-0334-1-13 | SUPERPAVE ASPHALTIC CONC, TRAFFIC C | Material |  |  | 8
3403-DB-0334-1-53 | SUPERPAVE ASPHALTIC CONCRETE, TRAFFIC C, PG76-22 | Material |  |  | 8
3403-DB-0337-7-25 | ASPHALT CONCRETE FRICTION COURSE, INC BIT, FC-5, | Material |  |  | 8
3403-DB-0337-7-80 | ASPHALT CONCRETE FRICTION COURSE,TRAFFIC B, FC-9.5 | Material |  |  | 8
3403-DB-0339-1 | MISCELLANEOUS ASPHALT PAVEMENT | Material |  |  | 8
3403-DB-0400-1-2 | CONCRETE CLASS I, ENDWALLS | Material | Cubic Yard |  | 8
3403-DB-0415-1-1 | REINFORCING STEEL- ROADWAY | Material | Per Pound |  | 8
3403-DB-0425-1511 | INLETS, DT BOT, TYPE B, <10' | Material | Each |  | 8
3403-DB-0425-1512 | INLETS, DT BOT, TYPE B, >10' | Material | Each |  | 8
3403-DB-0425-1513 | INLETS, DT BOT, TYPE B, J BOT, <10' | Material | Each |  | 8
3403-DB-0425-1514 | INLETS, DT BOT, TYPE B, J BOT, >10' | Material | Each |  | 8
3403-DB-0425-1521 | INLETS, DT BOT, TYPE C,<10' | Material | Each |  | 8
3403-DB-0425-1541 | INLETS, DT BOT, TYPE D, <10' | Material | Each |  | 8
3403-DB-0425-1543 | INLETS, DITCH BOTTOM, TYPE D, J BOT, <10' | Material | Each |  | 8
3403-DB-0425-1551 | INLETS, DT BOT, TYPE E, <10' | Material | Each |  | 8
3403-DB-0425-1552 | INLETS, DT BOT, TYPE E, >10' | Material | Each |  | 8
3403-DB-0425-1611 | INLETS, DITCH BOTTOM, TYPE K, <10' | Material | Each |  | 8
3403-DB-0425-1701 | INLETS, GUTTER, TYPE S, <10' | Material | Each |  | 8
3403-DB-0425-1702 | INLETS, GUTTER, TYPE S, >10' | Material | Each |  | 8
3403-DB-0425-1703 | INLETS, GUTTER, TYPE S, J BOTTOM <10' | Material | Each |  | 8
3403-DB-0425-1704 | INLETS, GUTTER, TYPE S, J BOTTOM, >10' | Material | Each |  | 8
3403-DB-0425-1891 | INLETS, BARRIER WALL, <10' | Material | Each |  | 8
3403-DB-0425-1893 | INLETS, BARRIER WALL, J BOT, <10' | Material | Each |  | 8
3403-DB-0425-2-41 | MANHOLES, P-7, <10' | Material | Each |  | 8
3403-DB-0425-2-61 | MANHOLES, P-8, <10' | Material | Each |  | 8
3403-DB-0425-2-91 | MANHOLES, J-8, <10' | Material | Each |  | 8
3403-DB-0425-2-92 | MANHOLES, J-8, >10' | Material | Each |  | 8
3403-DB-0425-2125 | DRAINAGE MANHOLE, PROJECT 405270-4-52-01, J-7 >10 | Material | Each |  | 8
3403-DB-0430-173118 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 18", GD | Material | Linear Feet |  | 8
3403-DB-0430173124 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 24", GD | Material | Linear Feet |  | 8
3403-DB-0430173136 | PIPE CULVERT OPTIONAL MATERIAL, ROUND, 36", GD | Material | Linear Feet |  | 8
3403-DB-0430174218 | PIPE CULVERT, OPTIONAL MATERIAL, OTHER SHAPE - ELL,18" SD | Material | Linear Feet |  | 8
3403-DB-0430175118 | PIPE CULVERT,OPTIONAL MATERIAL,ROUND, 18"S/CD | Material | Linear Feet |  | 8
3403-DB-0430175124 | PIPE CULVERT,OPTIONAL MATERIAL,ROUND, 24"S/CD | Material | Linear Feet |  | 8
3403-DB-0430175130 | PIPE CULVERT, OPT MATERIAL, ROUND, 30"S/CD | Material | Linear Feet |  | 8
3403-DB-0430175136 | PIPE CULVERT, OPT MATERIAL, ROUND, 36"S/CD | Material | Linear Feet |  | 8
3403-DB-0430175142 | PIPE CULVERT, OPT MATERIAL, ROUND, 42"S/CD | Material | Linear Feet |  | 8
3403-DB-0430175148 | PIPE CULVERT, OPT MATERIAL, ROUND, 48"S/CD | Material | Linear Feet |  | 8
3403-DB-0430175218 | PIPE CULVERT,OPTIONAL MATERIAL,OTHER-ELIP/ARCH, 18" S/CD | Material | Linear Feet |  | 8
3403-DB-0430175224 | PIPE CULVERT, OPT MATERIAL,OTHER SHAPE-ELIP/AR 24" S/CD | Material | Linear Feet |  | 8
3403-DB-0430175230 | PIPE CULVERT, OPT MATERIAL, OTHER SHAPE - ELIP/ARC 30" S/CD | Material | Linear Feet |  | 8
3403-DB-0430175236 | PIPE CULVERT, OPT MATERIAL, OTHER SHAPE - ELIP/ARC 36" S/CD | Material | Linear Feet |  | 8
3403-DB-0430175242 | PIPE CULVERT, OPT MATERIAL, OTHER SHAPE - ELIP/ARC 42" S/CD | Material | Linear Feet |  | 8
3403-DB-0430611125 | U-ENDWALL WITH BAFFLES, STD 261, 1:4 SLOPE, 18"PIP | Material | Each |  | 8
3403-DB-0430611129 | U-ENDWALL WITH BAFFLES, STD 261, 1:4 SLOPE, 24"PIP | Material | Each |  | 8
3403-DB-0430982125 | MITERED END SECTION, OPTIONAL ROUND, 18" CD | Material | Each |  | 8
3403-DB-0430982129 | MITERED END SECTION, OPTIONAL ROUND, 24" CD | Material | Each |  | 8
3403-DB-0430982138 | MITERED END SECTION, OPTIONAL ROUND, 36" CD | Material | Each |  | 8
3403-DB-0430982141 | MITERED END SECTION, OPTIONAL ROUND, 48" CD | Material | Each |  | 8
3403-DB-0430982625 | MITERED END SECTION, OPTIONAL - ELLIPTICAL / ARCH, 18"CD | Material | Each |  | 8
3403-DB-0430982629 | MITERED END SECTION, OPTIONAL - ELLIPTICAL / ARCH, 24"CD | Material | Each |  | 8
3403-DB-0430982633 | MITERED END SECTION, OPTIONAL - ELLIPTICAL / ARCH, 30"CD | Material | Each |  | 8
3403-DB-0430982640 | MITERED END SECTION, OPTIONAL - ELLIPTICAL / ARCH, 42"CD | Material | Each |  | 8
3403-DB-0430984625 | MITERED END SECT, OPTIONAL - ELLIPTICAL / ARCH, 18" SD | Material | Each |  | 8
3403-DB-0440-1-10 | UNDERDRAIN, TYPE I | Material | Linear Feet |  | 8
3403-DB-0440-1-20 | UNDERDRAIN, TYPE II | Material | Linear Feet |  | 8
3403-DB-0440-73-2 | UNDERDRAIN OUTLET PIPE, 6" | Material | Linear Feet |  | 8
3403-DB-0519-78 | BOLLARDS | Material | Each |  | 8
3403-DB-0520-1-7 | CONCRETE CURB & GUTTER, TYPE E | Material | Linear Feet |  | 8
3403-DB-0520-2-2 | CONCRETE CURB, TYPE B | Material | Linear Feet |  | 8
3403-DB-0520-6 | SHOULDER GUTTER- CONCRETE | Material | Linear Feet |  | 8
3403-DB-0521-1-1 | MEDIAN BARRIER WALL CONC, PRECAST | Material | Linear Feet |  | 8
3403-DB-0521-8-1 | CONC TRAFF RAIL BARR W/ JCT SLAB 32" F | Material | Linear Feet |  | 8
3403-DB-0521-8-6 | CONC TRAFF RAIL BARR, W/JCT SLAB CORRAL W/O CURB | Material | Linear Feet |  | 8
3403-DB-0521-72-3 | SHOULDER CONC BARR, RIGID-SHOULDER 32" | Material | Linear Feet |  | 8
3403-DB-0521-72-10 | SHLDR CONC BARR, RIGID SHLDR 42" (PIER PROTECT) | Material | Linear Feet |  | 8
3403-DB-0522-1 | CONCRETE SIDEWALK AND DRIVEWAYS, 4" THICK | Material | Square Yard |  | 8
3403-DB-0522-2 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THICK | Material | Square Yard |  | 8
3403-DB-0524-1-1 | CONCRETE DITCH PAVT, NON REINFORCED, 3" | Material | Square Yard |  | 8
3403-DB-0524-1-2 | CONCRETE DITCH PAVEMENT, NON REINFORCED, 4" | Material | Square Yard |  | 8
3403-DB-0527-2 | DETECTABLE WARNINGS | Material | Square Feet |  | 8
3403-DB-0530-1 | RIPRAP, SAND-CEMENT | Material | Cubic Yard |  | 8
3403-DB-0530-3-4 | RIPRAP, RUBBLE, F&I, DITCH LINING | Material |  |  | 8
3403-DB-0536-1-1 | GUARDRAIL -ROADWAY, GENERAL TL-3 | Material | Linear Feet |  | 8
3403-DB-0536-7-3 | SPECIAL GUARDRAIL POST- ENCASED POST FOR SHALLOW M | Material | Each |  | 8
3403-DB-0536-8-11 | APPROACH TRANSITION TO RIGID BARRIER- BRIDGE ANCHO | Material | Each |  | 8
3403-DB-0536-8-13 | APPROACH TRANSITION CONNECTION TO RIGID BARRIER, F | Material | Each |  | 8
3403-DB-0536-85-22 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- FL | Material | Each |  | 8
3403-DB-0536-85-24 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- PA | Material | Each |  | 8
3403-DB-0536-85-25 | GUARDRAIL END ANCHORAGE ASSEMBLY/END TREATMENT- TY | Material | Each |  | 8
3403-DB-0544-75-1 | CRASH CUSHION | Material | Each |  | 8
3403-DB-0546-72-55 | RUMBLE STRIPS, GROUND-IN, 16" SHOULDER | Material | Mile |  | 8
3403-DB-0550-10110 | FENCING, TYPE A, 0.0-5.0', STANDARD | Material | Linear Feet |  | 8
3403-DB-0550-10222 | FENCING, TYPE B, 5.1-6.0, W/ VINYL COATING | Material | Linear Feet |  | 8
3403-DB-0550-10256 | FENCING, TYPE B, 8-10.0', WITH VINYL COATING AND B | Material | Linear Feet |  | 8
3403-DB-0550-60124 | FENCE GATE, TYPE A, DOUBLE, 18.1-20.0' OPENING | Material | Each |  | 8
3403-DB-0550-60212 | FENCE GATE, TYPE B, SINGLE, 6.1 - 12.0' OPENING | Material | Each |  | 8
3403-DB-0550-60224 | FENCE GATE, TYPE B, DOUBLE, 18.1-20.0' OPENING | Material | Each |  | 8
3403-DB-0570-1-1 | PERFORMANCE TURF | Material | Square Yard |  | 8
3403-DB-0570-1-2 | PERFORMANCE TURF, SOD | Material | Square Yard |  | 8
3403-DB-0710-11-101 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID (6") | Material | Mile |  | 8
3403-DB-0710-111-23 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID (12") | Material | Linear Feet |  | 8
3403-DB-0710-11125 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SOLID (24") | Material | Linear Feet |  | 8
3403-DB-0710-11-131 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, SKIP, (6") | Material | Mile |  | 8
3403-DB-0710-11-141 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, 2-4 D (6") | Material | Mile |  | 8
3403-DB-0710-11-160 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, MESSA | Material | Each |  | 8
3403-DB-0710-11-170 | PAINTED PAVEMENT MARKINGS, STANDARD, WHITE, ARROW | Material | Each |  | 8
3403-DB-0710-11-201 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, SOLI (6") | Material | Mile |  | 8
3403-DB-0710-11241 | PAINTED PAVEMENT MARKINGS, STANDARD, YELLOW, 2-4 (6") | Material | Mile |  | 8
3403-DB-0751-42-1 | BIRD HOUSE | Material | Each |  | 8
3403-DB-0999-25 | INITIAL CONTINGENCY AMOUNT, DO NOT BID 405270452 | Material | Lump Sum |  | 8
3403-DB-0630-2-11-1 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-DB-0630-2-12-1 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-DB-0630-2-14-1 | CONDUIT, FURNISH & INSTALL, ABOVEGROUND | Material | Linear Feet |  | 8
3403-DB-0635-2-11-2 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-DB-0639-1122-1 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-DB-0639-2-1-1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | Material | Linear Feet |  | 8
3403-DB-0639-3-11-1 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | Material | Each |  | 8
3403-DB-0641-2-12-1 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-DB-0700-1-11 | SINGLE POST SIGN, F&I GROUND MOUNT, UP TO 12 SF | Material | Each |  | 8
3403-DB-0700-1-12 | SINGLE POST SIGN, F&I GROUND MOUNT, 12-20 SF | Material | Each |  | 8
3403-DB-0700-1-13 | SINGLE POST SIGN, F&I GROUND MOUNT, 21-30 SF | Material | Each |  | 8
3403-DB-0700-1-14 | SINGLE POST SIGN, F&I GROUND MOUNT, 31+ SF | Material | Each |  | 8
3403-DB-0700-1-32 | SINGLE POST SIGN, F&I BRIDGE MOUNT INDEX 11870, 12 | Material | Each |  | 8
3403-DB-0700-1-50 | SINGLE POST SIGN, RELOCATE | Material | Each |  | 8
3403-DB-0700-1-60 | SINGLE POST SIGN, REMOVE | Material | Each |  | 8
3403-DB-0700-2-14 | MULTI- POST SIGN, F&I GROUND MOUNT, 31-50 SF | Material | Each |  | 8
3403-DB-0700-2-15 | MULTI- POST SIGN, F&I GROUND MOUNT, 51-100 SF | Material | Each |  | 8
3403-DB-0700-2-16 | MULTI- POST SIGN, F&I GROUND MOUNT, 101-200 SF | Material | Each |  | 8
3403-DB-0700-2-17 | MULTI- POST SIGN, F&I GROUND MOUNT, 201-300 SF | Material | Each |  | 8
3403-DB-0700-3207 | SIGN PANEL, FURNISH & INSTALL OVERHEAD MOUNT, 201-300 SF | Material | Each |  | 8
3403-DB-0700-4113 | OVERHEAD STATIC SIGN STRUCTURE, FURNISH & INSTALL, | Material | Each |  | 8
3403-DB-0700-4114 | OVERHEAD STATIC SIGN STRUCTURE, FURNISH & INSTALL, | Material | Each |  | 8
3403-DB-0700-12-12 | SIGN BEACON, F&I GROUND MOUNT- AC POWERED, TWO BE | Material | Each |  | 8
3403-DB-0700-12-32 | SIGN BEACON, F&I OVERHEAD MOUNT, TWO BEACONS | Material | Each |  | 8
3403-DB-0700-13-12 | RETROREFLECTIVE SIGN STRIP- FURNISH AND INSTALL, 2 | Material | Each |  | 8
3403-DB-0705-10-1 | OBJECT MARKER, TYPE 1 | Material | Each |  | 8
3403-DB-0705-10-4 | OBJECT MARKER, TYPE 4 | Material | Each |  | 8
3403-DB-0705-11-1 | DELINEATOR, FLEXIBLE TUBULAR | Material | Each |  | 8
3403-DB-0710-90 | PAINTED PAVEMENT MARKINGS, FINAL SURFACE 4052704 | Material | Lump Sum |  | 8
3403-DB-0711-11103 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 12" FOR INT | Material | Mile |  | 8
3403-DB-0711-11125 | THERMOPLASTIC, STANDARD, WHITE, SOLID, 24" FOR STO | Material | Linear Feet |  | 8
3403-DB-0711-11141 | THERMOPLASTIC, STANDARD, WHITE, 2-4 DOTTED GUIDELI | Material | Mile |  | 8
3403-DB-0711-11160 | THERMOPLASTIC, STANDARD, WHITE, MESSAGE OR SYMBOL | Material | Each |  | 8
3403-DB-0711-11170 | THERMOPLASTIC, STANDARD, WHITE, ARROW | Material | Each |  | 8
3403-DB-0711-11224 | THERMOPLASTIC, STANDARD, YELLOW, SOLID, 18" FOR DI | Material | Linear Feet |  | 8
3403-DB-0711-14123 | THERMOPLASTIC, PREFORMED, WHITE, SOLID, 12" FOR C | Material | Linear Feet |  | 8
3403-DB-0711-14125 | THERMOPLASTIC, PREFORMED, WHITE, SOLID, 24" FOR C | Material | Linear Feet |  | 8
3403-DB-0711-14160 | THERMOPLASTIC, PREFORMED, WHITE, MESSAGE | Material | Each |  | 8
3403-DB-0711-14170 | THERMOPLASTIC, PREFORMED, WHITE, ARROW | Material | Each |  | 8
3403-DB-0711-15101 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-DB-0711-15102 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-DB-0711-15131 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-DB-0711-15133 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-DB-0711-15201 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-DB-0711-15202 | THERMOPLASTIC, STANDARD-OPEN GRADED ASPHALT SURFAC | Material | Mile |  | 8
3403-DB-0711-16101 | THERMOPLASTIC, STANDARD-OTHER SURFACES, WHITE, SOL | Material | Mile |  | 8
3403-DB-0711-16201 | THERMOPLASTIC, STANDARD-OTHER SURFACES, YELLOW, SO | Material | Mile |  | 8
3403-DB-0713103101 | PERMANENT TAPE, WHITE, SOLID, 6" FOR CONCRETE BRID | Material | Mile |  | 8
3403-DB-0713103102 | PERMANENT TAPE, WHITE, SOLID, 8" EXIT LANE AT INTE | Material | Mile |  | 8
3403-DB-0713103131 | PERMANENT TAPE, WHITE, SKIP/DOTTED, 6" FOR CONCRE | Material | Mile |  | 8
3403-DB-0713103201 | PERMANENT TAPE, YELLOW, SOLID, 6" FOR CONCRETE BRI | Material | Mile |  | 8
3403-DB-0713103331 | PERMANENT TAPE, BLACK, SKIP/DOTTED, 6" FOR CONCRE | Material | Mile |  | 8
3403-DB-0630-2-11-2 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-DB-0630-2-12-2 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-DB-0630-2-14-2 | CONDUIT, FURNISH & INSTALL, ABOVEGROUND | Material | Linear Feet |  | 8
3403-DB-0635-2-11-1 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-DB-0635-3-12 | JUNCTION BOX, FURNISH & INSTALL, MOUNTED | Material | Each |  | 8
3403-DB-0639-1122-2 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-DB-0641-2-12-2 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-DB-0715-1-11 | LIGHTING CONDUCTORS, F&I, INSULATED, NO. 10 OR < | Material | Linear Feet |  | 8
3403-DB-0715-1-12 | LIGHTING CONDUCTORS, F&I, INSULATED, NO.8 - 6 | Material | Linear Feet |  | 8
3403-DB-0715-1-13 | LIGHTING CONDUCTORS, F&I, INSULATED, NO 4 TO NO 2 | Material | Linear Feet |  | 8
3403-DB-0715-1-15 | LIGHTING CONDUCTORS, F&I, NO.1/0 - 3/0 (0 to 000) | Material | Linear Feet |  | 8
3403-DB-0715-4-13 | LIGHT POLE COMPLETE, FURNISH & INSTALL STANDARD PO | Material | Each |  | 8
3403-DB-0715-7-11 | LOAD CENTER, F&I, SECONDARY VOLTAGE | Material | Each |  | 8
3403-DB-0715-11125 | LUMINAIRE, F&I, UNDER DECK, WALL MOUNT | Material | Each |  | 8
3403-DB-0715500-1 | POLE CABLE DISTRIBUTION SYSTEM, CONVENTIONAL | Material | Each |  | 8
3403-DB-0630-2-11-3 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-DB-0630-2-12-3 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-DB-0632-7-1 | SIGNAL CABLE- NEW OR RECONSTRUCTED INTERSECTION, F | Material | Each |  | 8
3403-DB-0635-2-11-3 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-DB-0639-1122-3 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-DB-0639-2-1-3 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | Material | Linear Feet |  | 8
3403-DB-0639-3-11-3 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | Material | Each |  | 8
3403-DB-0641-2-12-3 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-DB-0646-1-11 | ALUMINUM SIGNALS POLE, PEDESTAL | Material | Each |  | 8
3403-DB-0649-21-6 | STEEL MAST ARM ASSEMBLY, FURNISH AND INSTALL, SING | Material | Each |  | 8
3403-DB-0649-21-10 | STEEL MAST ARM ASSEMBLY, FURNISH AND INSTALL, SING | Material | Each |  | 8
3403-DB-0649-21-21 | STEEL MAST ARM ASSEMBLY, FURNISH AND INSTALL, SING | Material | Each |  | 8
3403-DB-0650-1-14 | TRAFFIC SIGNAL, FURNISH & INSTALL ALUMINUM, 3 SEC | Material | Each |  | 8
3403-DB-0650-1-16 | TRAFFIC SIGNAL, FURNISH & INSTALL ALUMINUM, 4 SEC | Material | Each |  | 8
3403-DB-0653-1-11 | PEDESTRIAN SIGNAL, FURNISH & INSTALL LED COUNTDOWN | Material | Each |  | 8
3403-DB-0660-4-11 | VEHICLE DETECTION SYSTEM- VIDEO, FURNISH & INSTALL | Material | Each |  | 8
3403-DB-0660-4-12 | VEHICLE DETECTION SYSTEM- VIDEO, FURNISH & INSTALL | Material | Each |  | 8
3403-DB-0665-1-11 | PEDESTRIAN DETECTOR, FURNISH & INSTALL, STANDARD | Material | Each |  | 8
3403-DB-0670-5110 | TRAFFIC CONTROLLER ASSEMBLY, F&I, NEMA | Material | Each |  | 8
3403-DB-0685-1-11 | UNINTERRUPTIBLE POWER SUPPLY, FURNISH AND INSTALL, | Material | Each |  | 8
3403-DB-0700-3201 | SIGN PANEL, FURNISH & INSTALL OVERHEAD MOUNT, UP T | Material | Each |  | 8
3403-DB-0700-5-22 | INTERNALLY ILLUMINATED SIGN, FURNISH & INSTALL, O | Material | Each |  | 8
3403-DB-0735-74-2 | TOLL PLAZA, LOCATION 2 | Material | Lump Sum |  | 8
3403-DB-0400-0-11 | CONCRETE CLASS NS, GRAVITY WALL | Material | Cubic Yard |  | 8
3403-DB-0515-1-2 | PIPE HANDRAIL - GUIDERAIL, ALUMINUM | Material | Linear Feet |  | 8
3403-DB-0630-2-11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3403-DB-0630-2-12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL BORE | Material | Linear Feet |  | 8
3403-DB-0630-2-14 | CONDUIT, FURNISH & INSTALL, ABOVEGROUND | Material | Linear Feet |  | 8
3403-DB-0633-1121 | FIBER OPTIC CABLE, F&I, UNDERGROUND,2-12 FIBERS | Material | Linear Feet |  | 8
3403-DB-0633-1122 | FIBER OPTIC CABLE, F&I, UNDERGROUND,13-48 FIBERS | Material | Linear Feet |  | 8
3403-DB-0633-1124 | FIBER OPTIC CABLE, F&I, UNDERGROUND, 97 - 144 FIB | Material | Linear Feet |  | 8
3403-DB-0633-2-31 | FIBER OPTIC CONNECTION, INSTALL, SPLICE | Material | Each |  | 8
3403-DB-0633-2-32 | FIBER OPTIC CONNECTION, INSTALL, TERMINATION | Material | Each |  | 8
3403-DB-0633-3-11 | FIBER OPTIC CONNECTION HARDWARE, F&I, SPLICE ENCLO | Material | Each |  | 8
3403-DB-0633-3-14 | FIBER OPTIC CONNECTION HARDWARE, F&I, BUFFER TUBE | Material | Each |  | 8
3403-DB-0633-3-15 | FIBER OPTIC CONNECTION HARDWARE, F&I, PRETERMINATE | Material | Each |  | 8
3403-DB-0633-3-16 | FIBER OPTIC CONNECTION HARDWARE, F&I, PATCH PANEL- | Material | Each |  | 8
3403-DB-0635-2-11 | PULL & SPLICE BOX, F&I, 13" x 24" COVER SIZE | Material | Each |  | 8
3403-DB-0635-2-12 | PULL & SPLICE BOX, F&I, 24" X 36" COVER SIZE | Material | Each |  | 8
3403-DB-0635-2-13 | PULL & SPLICE BOX, F&I, 30" X 60" RECTANGULAR OR | Material | Each |  | 8
3403-DB-0639-1122 | ELECTRICAL POWER SERVICE, F&I, UNDERGROUND, METER | Material | Each |  | 8
3403-DB-0639-2-1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTALL | Material | Linear Feet |  | 8
3403-DB-0639-3-11 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE MOUNT | Material | Each |  | 8
3403-DB-0639-5-6 | EMERGENCY GENERATOR-PERMANENT, UP TO 25 KW, PROJEC | Material | Each |  | 8
3403-DB-0641-2-12 | PRESTRESSED CONCRETE POLE, F&I, TYPE P-II SERVICE | Material | Each |  | 8
3403-DB-0641-2-19 | PRESTRESSED CONCRETE POLE, F&I, CUSTOM DESIGN | Material | Each |  | 8
3403-DB-0641-3163 | CONCRETE CCTV POLE, FURNISH & INSTALL WITH LOWERIN | Material | Each |  | 8
3403-DB-0641-3169 | CONCRETE CCTV POLE, FURNISH & INSTALL WITH LOWERIN | Material | Each |  | 8
3403-DB-0660-3-11 | VEHICLE DETECTION SYSTEM- MICROWAVE, FURNISH & INS | Material | Each |  | 8
3403-DB-0660-3-12 | VEHICLE DETECTION SYSTEM- MICROWAVE, FURNISH & INS | Material | Each |  | 8
3403-DB-0660-6121 | VEHICLE DETECTION SYSTEM- AVI, BLUETOOTH, FURNISH | Material | Each |  | 8
3403-DB-0660-6122 | VEHICLE DETECTION SYSTEM- AVI, BLUETOOTH, FURNISH | Material | Each |  | 8
3403-DB-0676-2121 | ITS CABINET, FURNISH & INSTALL, POLE MOUNT WITH SU | Material | Each |  | 8
3403-DB-0676-2122 | ITS CABINET, FURNISH & INSTALL, POLE MOUNT WITH SU | Material | Each |  | 8
3403-DB-0676-2143 | ITS CABINET, FURNISH & INSTALL, BASE MOUNT, 334, 2 | Material | Each |  | 8
3403-DB-0682-1113 | ITS CCTV CAMERA, F&I, DOME PTZ ENCLOSURE - PRESSU | Material | Each |  | 8
3403-DB-0684-1-1 | MANAGED FIELD ETHERNET SWITCH, FURNISH & INSTALL | Material | Each |  | 8
3403-DB-0684-2-1 | DEVICE SERVER, FURNISH & INSTALL | Material | Each |  | 8
3403-DB-0684-5-1 | MEDIA CONVERTER, FURNISH & INSTALL | Material | Each |  | 8
3403-DB-0685-1-12 | UNINTERRUPTIBLE POWER SUPPLY, FURNISH AND INSTALL, | Material | Each |  | 8
3403-DB-0687-1100 | HIGHWAY ADVISORY RADIO, FURNISH & INSTALL, AC POWE | Material | Each |  | 8
3403-DB-0700-8136 | FRONT ACCESS DYNAMIC MESSAGE SIGN, FURNISH & INSTA | Material | Each |  | 8
3403-DB-0700-9137 | WALK-IN DYNAMIC MESSAGE SIGN, FURNISH & INSTALL- W | Material | Each |  | 8
3403-DB-0700-10115 | DMS SUPPORT STRUCTURE, FURNISH & INSTALL, SPAN, 51 | Material | Each |  | 8
3403-DB-0700-10124 | DMS SUPPORT STRUCTURE, CANTILEVER, 41-50 FT | Material | Each |  | 8
CO 12 | Change Order 12 - Tarrant Regional Water District Adjustment Work | Material | Lump Sum |  | 8
3329-367 | SA15 - Guardrail Upgrades - MASH | Material | Lump Sum |  | 8
3329-368 | SA16 - Wet Utility Upgrades | Material | Lump Sum |  | 8
3329-369 | SA17 - Replace ABC with Asphalt | Material |  |  | 8
3329-370 | SA17 - Y-19 Ramps - Replace Soil Stabilization with Asphalt | Material | Lump Sum |  | 8
3329-371 | SA18 - Guardrail End Units, Type TL-3 "MASH" | Material | Each |  | 8
3329-372 | SA18 - STL BM Guardrail - MASH Upgrade | Material | Linear Feet |  | 8
3329-373 | SA18 - STL BM Guardrail shop curve - MASH Upgrade | Material | Linear Feet |  | 8
3329-374 | SA18 - Guardrail End Units, TYPE AT-1 | Material | Each |  | 8
3329-375 | SA18 - Guardrail End Units, TYPE CAT-1 | Material | Each |  | 8
3329-376 | SA18 - Remove Existing Guardrail for MASH Upgrade | Material | Linear Feet |  | 8
3329-377 | SA19 - Embankement Acceleration - Y19 - & -Y19RPA- | Material | Lump Sum |  | 8
3329-379 | SA20 - 3804 STR 48" DRILLED SHAFT - IN SOIL | Material | Linear Feet |  | 8
3329-380 | SA20 - 3804 STR 48" DRILLED SHAFT - NOT IN SOIL | Material | Linear Feet |  | 8
3329-381 | SA20 - 3804 STR PERM STEEL CASING FOR 48" DRILLED SHAFT | Material | Linear Feet |  | 8
3329-382 | SA20 - 3804 STR PILE EXCAVATION - NOT IN SOIL (ELIMINATED) | Material | Linear Feet |  | 8
3329-383 | SA20 - 3804 STR DRILLED SHAFT SUPPORT (>85 SHIFTS) (ELIMINATED) | Material | Day |  | 8
3329-384 | SA21 - Soil Modification 20" Depth | Material | Square Yard |  | 8
3329-385 | SA21 - LKD for Soil Modification | Material |  |  | 8
3329-386 | SA21 - Quick Lime for Soil Modification | Material |  |  | 8
3329-358 | SA12 - 30" WLD STL PIPE GRAD B NOT IN SOIL(30", 0.500" THICK) (Eliminated) | Material | Linear Feet |  | 8
3329-359 | SA12 - 36" WLD STL PIPE GRAD B IN SOIL(36", 0.500" THICK) | Material | Linear Feet |  | 8
3329-360 | SA12 -36" WLD STL PIPE GRAD B NOT IN SOIL(36", 0.500" THICK) | Material | Linear Feet |  | 8
3329-361 | SA12 - 42" WLD STL PIPE GRAD B IN SOIL(42", 0.625" THICK) | Material | Linear Feet |  | 8
3329-362 | SA12 - 42" WLD STL PIPE GRAD B NOT IN SOIL(42", 0.625" THICK) | Material | Linear Feet |  | 8
3329-363 | SA12 - 48" WLD STL PIPE GRAD B IN SOIL(48", 0.625" THICK) | Material | Linear Feet |  | 8
3329-364 | SA12 - 48" WLD STL PIPE GRAD B NOT IN SOIL(48", 0.625" THICK) | Material | Linear Feet |  | 8
3329.378 | SA20 - 3804 LS Bridge - NOT USED | Material |  |  | 8
3329-387 | 3804 - 2.5'' Skimmer | Material | Each |  | 8
3329-388 | 3804 - Lane Closures | Material | Each |  | 8
3329-389 | 3804 - Major Traffic Shift - Road Closures | Material | Each |  | 8
3329-390 | 3804 - Bridge Access | Material | Lump Sum |  | 8
3329-391 | 3804 - Concrete Washout | Material | Each |  | 8
3329-392 | 3804 - CSL Testing | Material | Each |  | 8
3329-393 | 3804 - Grinding Bridge Floors | Material | Square Feet |  | 8
3329-394 | 3804 - Str08 - Reinforced Bridge Approach Fill | Material | Lump Sum |  | 8
3329-395 | 3804 - 63'' MBT - Prestressed Conc. Girders | Material | Linear Feet |  | 8
3329-396 | 3804 - Concrete Parapet | Material | Linear Feet |  | 8
3329-397 | 3804 - Two Bar Metal Rail | Material | Linear Feet |  | 8
3329-398 | 3804 - Str08 - Elastomeric Bearing | Material | Lump Sum |  | 8
3329-399 | 3804 - Str08 - Expansion Joint Seals | Material | Lump Sum |  | 8
3329-400 | 3804 - Water Filled Barrier | Material | Linear Feet |  | 8
3329-401 | 3804 - Work Zone Signs | Material | Square Feet |  | 8
R-5 | Paving | Labor |  |  | 1
Cost Mar Redist-1 | Mar 18 Redistribution | Material | Lump Sum |  | 8
CO 13 | Change Order 13 - Incorporate NCR work and Perf Ass. Charges | Material | Lump Sum |  | 8
CO#3 | Bridge Relocation | Material | Lump Sum |  | 1
CO#10 | RW-1 Coping + 3 Weep Holes | Material | Lump Sum |  | 1
3306 | SH360 | Labor |  |  | 1
TC-Maint. | Maintenance of Traffic Crew | Labor |  |  | 1
3403-CT-ILLUM | Illumination | Material | Lump Sum |  | 1
3403-CT-ITS-SIG | ITS Signals | Material | Lump Sum |  | 1
3403-HC-ILLUM | Electrical ILLUM | Material |  |  | 1
3403-HC-SIG-ITS | Electrical - Signals and ITS | Material |  |  | 1
3403-HC-SIGNS | Rdwy Signs | Material |  |  | 1
3403-HC-STRIPE | Rdwy Striping | Material |  |  | 1
3403-DB-ILLUM | Electrical - Illumination | Material |  |  | 1
3403-DB-SIGNS | Rdwy Signage | Material |  |  | 1
3403-DB-SIG-ITS | Electrical - Signals ITS | Material |  |  | 1
3403-DB-STRIPE | Rdwy Striping | Material |  |  | 1
3403-DB-BASE | Limerock Base | Material |  |  | 1
3403-DB-FENCE | ROW fence | Material |  |  | 1
3403-DB-STAB | Stabilize Rdwy | Material |  |  | 1
3403-DB-MBGF | Guardrail | Material |  |  | 1
3403-DB-PVMT | Pavement | Material |  |  | 1
3403-DB-DRG | Rdwy Drainage | Material |  |  | 1
3403-DB-MOT | Maintenance of Traffic | Material |  |  | 1
3403-HC-PVMT | HMA pavement | Material |  |  | 1
3403-HC-MOT | Maintenance of Traffic | Material |  |  | 1
3403-HC-DRG | Storm Drainage | Material |  |  | 1
3403-HC-TEMP -STP | Temporary Striping | Material |  |  | 1
3403-CT-BASE | Limerock Base | Material |  |  | 1
3403-CT-DRG | Storm Drainage | Material |  |  | 1
3403-CT-PVMT | HMA pavement | Material |  |  | 1
3403-CT-MOT | Maintenance of Traffic - Citrus Co | Material |  |  | 1
3403-CT-MBGF | Guardrail | Material |  |  | 1
3403-CT-FENCE | Fence | Material |  |  | 1
3403-CT-TEMP STP | Temporary Rdwy Striping | Material |  |  | 1
3403-CT-SIGNS | Rdwy Signs | Material |  |  | 1
3403-CT-STRIPE | Permanent Rdwy Striping | Material |  |  | 1
3403-DB-TEMP-STP | Tempoary Striping | Material |  |  | 1
3403-DB-FLTWK | Flatwork | Material |  |  | 1
3422 | 3422 - BA5345180 - US 1 Over CSX | Nonlabor |  |  | 1
3422 - 1001 | CLEARING & GRUBBING | Material |  |  | 1
3422 - 1002 | TYPE D ENGINEERS OFFICE | Material |  |  | 1
3422 - 1003 | PRICE ADJUSTMENT FOR DIESEL FUEL | Material |  |  | 1
3422 - 1004 | 5 INCH YELLOW PAVEMENT MARKING PAINT | Material |  |  | 1
3422 - 1005 | 5 INCH WHITE PAVEMENT MARKING PAINT | Material |  |  | 1
3422 - 1006 | 10 INCH WHITE PAVEMENT MARKING PAINT | Material |  |  | 1
3422 - 1007 | 5 INCH YELLOW REMOVABLE PAVEMENT LINE MARKINGS | Material |  |  | 1
3422 - 1008 | 5 INCH WHITE REMOVABLE PAVEMENT LINE MARKINGS | Material |  |  | 1
3422 - 1009 | 24 INCH WHITE REMOVABLE PAVEMENT LINE MARKINGS | Material |  |  | 1
3422 - 1010 | REMOVABLE LETTERS, SYMBOLS, ARROWS, & NUMBERS | Material |  |  | 1
3422 - 1011 | REMOVAL OF REMOVABLE LETTERS, SYMBOLS, ARROWS, & NUMBERS | Material |  |  | 1
3422 - 1012 | REMOVAL OF REMOVABLE PAVEMENT MARKING LINES - ANY WIDTH | Material |  |  | 1
3422 - 1013 | REMOVAL OF EXISTING PAVEMENT LINE MARKINGS, ANY WIDTH | Material |  |  | 1
3422 - 1014 | 8 INCH BLACK OUT TAPE LINES | Material |  |  | 1
3422 - 1015 | REMOVAL OF BLACK OUT TAPE LINES-ANY WIDTH | Material |  |  | 1
3422 - 1016 | MAINTENANCE OF TRAFFIC | Material |  |  | 1
3422 - 1017 | GRADED AGGREGATE BASE FOR MAINTENANCE OF TRAFFIC | Material |  |  | 1
3422 - 1018 | ASPHALT FOR MAINTENANCE OF TRAFFIC | Material |  |  | 1
3422 - 1019 | ARROW PANEL | Material |  |  | 1
3422 - 1020 | TEMP TRAFFIC SIGNS HIGH PERFORMANCE WIDE ANGLE RETROREFLECTIVE SHEETING | Material |  |  | 1
3422 - 1021 | TEMP CONCRETE SINGLE FACE TRAFFIC BARRIER FOR MAINT OF TRAFFIC | Material |  |  | 1
3422 - 1022 | RESET PRECAST TEMP CONCRETE TRAFFIC BARRIER FOR MAINT OF TRAFFIC | Material |  |  | 1
3422 - 1023 | REFLECTIVE BARRIER MARKERS | Material |  |  | 1
3422 - 1024 | TYPE III BARRICADE FOR MAINTENANCE OF TRAFFIC | Material |  |  | 1
3422 - 1025 | TEMP CRASH CUSHION SAND FILLED PLASTIC BARRELS FOR MAINTOF TRAFFIC | Material |  |  | 1
3422 - 1026 | REPLACE TEMP CRASH CUSHION SAND FILLED PLASTIC BARRELS FOR MAINT OF TRAFFIC | Material |  |  | 1
3422 - 1027 | VERTICAL PANELS | Material |  |  | 1
3422 - 1028 | REMOVE & RESET TEMP CRASH CUSHION SAND FILLED PLASTIC BARRELS FOR MAINT OF TRAFFIC | Material |  |  | 1
3422 - 1029 | TEMP ORANGE CONSTRUCTION FENCE | Material |  |  | 1
3422 - 1030 | DRUMS FOR MAINTENANCE OF TRAFFIC | Material |  |  | 1
3422 - 1031 | PORTABLE VARIABLE MESSAGE SIGN | Material |  |  | 1
3422 - 1032 | PROTECTION VEHICLE | Material |  |  | 1
3422 - 1033 | TEMP TYPE E TRAFFIC BARRIER END TREATMENT FOR 50 MPH, ANY WIDTH | Material |  |  | 1
3422 - 1034 | REMOVE & RESET TEMP TYPE E TRAFFIC BARRIER END TREAT, ANY BAYS&WIDTH | Material |  |  | 1
3422 - 1035 | PRECAST TEMP 32 INCH F SHAPE CONCRETE TRAFFIC BARRIER | Material |  |  | 1
3422 - 1036 | CONSTRUCTION STAKEOUT | Material |  |  | 1
3422 - 1037 | MOBILIZATION | Material |  |  | 1
3422 - 1038 | ON-THE-JOB TRAINING | Material |  |  | 1
3422 - 1039 | CPM PROJECT SCHEDULE | Material |  |  | 1
3422 - 2001 | CLASS 1 EXCAVATION | Material |  |  | 1
3422 - 2002 | CLASS 1-A EXCAVATION | Material |  |  | 1
3422 - 2003 | GEOSYNTHETIC STABILIZED SUBGRADE USING GRADED AGG BASE | Material |  |  | 1
3422 - 2004 | SELECT BORROW | Material |  |  | 1
3422 - 2005 | TEST PIT EXCAVATION | Material |  |  | 1
3422 - 2006 | REMOVAL OF EXISTING CURB (ANY TYPE) | Material |  |  | 1
3422 - 2007 | REMOVAL OF EXISTING COMBINATION CURB & GUTTER | Material |  |  | 1
3422 - 2008 | REMOVAL OF EXISTING PAVEMENT | Material |  |  | 1
3422 - 2009 | REMOVAL OF EXISTING SIDEWALK | Material |  |  | 1
3422 - 2010 | REMOVAL OF EXISTING MASONRY | Material |  |  | 1
3422 - 2011 | GEOTEXTILE INCLUSIONS | Material |  |  | 1
3422 - 3001 | FILTER DIAPHRAGM | Material |  |  | 1
3422 - 3002 | SWM RISER STRUCTURE I/24 | Material |  |  | 1
3422 - 3003 | SWM WEIR WALL STRUCTURE S/1 | Material |  |  | 1
3422 - 3004 | 24-INCH PRESSURE-RATED REINFORCED CONCRETE PIPE | Material |  |  | 1
3422 - 3005 | STABILIZED CONSTRUCTION ENTRANCE | Material |  |  | 1
3422 - 3006 | CLASS 3 EXCAVATION FOR INCIDENTAL CONSTRUCTION | Material |  |  | 1
3422 - 3007 | SELECTED BACKFILL USING AASHTO NO57 AGGREGATE | Material |  |  | 1
3422 - 3008 | BRICK MASONRY FOR MISCELLANEOUS STRUCTURES | Material |  |  | 1
3422 - 3009 | MIX 3 CONCRETE FOR MISCELLANEOUS STRUCTURES | Material |  |  | 1
3422 - 3010 | 15 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material |  |  | 1
3422 - 3011 | 18 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material |  |  | 1
3422 - 3012 | 24 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material |  |  | 1
3422 - 3013 | 36 INCH REINFORCED CONCRETE PIPE, CLASS IV | Material |  |  | 1
3422 - 3014 | 18 INCH CONCRETE PIPE CONNECTION | Material |  |  | 1
3422 - 3015 | STANDARD TYPE C ENDWALL FOR 15 INCH PIPE | Material |  |  | 1
3422 - 3016 | STANDARD TYPE C ENDWALL FOR 18 INCH PIPE | Material |  |  | 1
3422 - 3017 | STANDARD TYPE C ENDWALL FOR 24 INCH PIPE | Material |  |  | 1
3422 - 3018 | STANDARD TYPE G ENDWALL FOR 36 INCH PIPE | Material |  |  | 1
3422 - 3019 | 15 INCH STANDARD CONCRETE END SECTION | Material |  |  | 1
3422 - 3020 | 18 INCH STANDARD CONCRETE END SECTION | Material |  |  | 1
3422 - 3021 | 24 INCH STANDARD CONCRETE END SECTION | Material |  |  | 1
3422 - 3022 | SINGLE WR INLET-MIN DEPTH | Material |  |  | 1
3422 - 3023 | SINGLE WR INLET-VERTICAL DEPTH | Material |  |  | 1
3422 - 3024 | STANDARD 10 FT COG INLET-MIN DEPTH | Material |  |  | 1
3422 - 3025 | STANDARD 15 FT COG INLET-MIN DEPTH | Material |  |  | 1
3422 - 3026 | STANDARD COG INLET-VERTICAL DEPTH | Material |  |  | 1
3422 - 3027 | 5 FOOT COG/COS OPENING | Material |  |  | 1
3422 - 3028 | 10 FOOT COG/COS OPENING | Material |  |  | 1
3422 - 3029 | STD SINGLE OPENING TYPE K INLET OPEN END GRATE NONTRAFFIC AREAS-MIN DEPTH | Material |  |  | 1
3422 - 3030 | STD SINGLE OPENING TYPE K INLET OPEN END GRATE- MIN DEPTH | Material |  |  | 1
3422 - 3031 | STD SINGLE OPENING TYPE K INLET OPEN END GRATE- VERTICAL DEPTH | Material |  |  | 1
3422 - 3032 | STD TYPE S INLET, DOUBLE GRATE TANDEM - MIN DEPTH | Material |  |  | 1
3422 - 3033 | 48 INCH DIAMETER MANHOLE FOR 12 INCH TO 24 INCH PIPES - MIN DEPTH | Material |  |  | 1
3422 - 3034 | 48 INCH DIAMETER MANHOLE - VERTICAL DEPTH | Material |  |  | 1
3422 - 3035 | 60 INCH DIAMETER MANHOLE FOR 27 INCH TO 36 INCH PIPES - MIN DEPTH | Material |  |  | 1
3422 - 3036 | 60 INCH DIAMETER MANHOLE - VERTICAL DEPTH | Material |  |  | 1
3422 - 3037 | CONVERT STORMWATER MANAGEMENT RISER FOR SEDIMENT CONTROL | Material |  |  | 1
3422 - 3038 | EROSION & SEDIMENT CONTROL ORIGINAL EXCAVATION | Material |  |  | 1
3422 - 3039 | EROSION & SEDIMENT CONTROL CLEANOUT EXCAVATION | Material |  |  | 1
3422 - 3040 | INLET PROTECTION | Material |  |  | 1
3422 - 3041 | SUMP PIT | Material |  |  | 1
3422 - 3042 | QUARTERLY EROSION & SEDIMENT CONTROL INCENTIVE | Material |  |  | 1
3422 - 3043 | FINAL EROSION & SEDIMENT CONTROL INCENTIVE | Material |  |  | 1
3422 - 3044 | DIVERSION FENCE | Material |  |  | 1
3422 - 3045 | TEMP ASPHALT BERM | Material |  |  | 1
3422 - 3046 | FILTER BAG | Material |  |  | 1
3422 - 3047 | CLASS I RIPRAP FOR SLOPE & CHANNEL PROTECTION | Material |  |  | 1
3422 - 3048 | CLASS II RIPRAP FOR SLOPE & CHANNEL PROTECTION | Material |  |  | 1
3422 - 3049 | RIPRAP FOR SEDIMENT CONTROL | Material |  |  | 1
3422 - 3050 | SUPER SILT FENCE | Material |  |  | 1
3422 - 3051 | NO 7 AGGREGATE FOR STORMWATER MANAGEMENT FACILITIES | Material |  |  | 1
3422 - 3052 | NO 57 AGGREGATE FOR STORMWATER MANAGEMENT FACILITIES | Material |  |  | 1
3422 - 3053 | 6 INCH SUB-DRAIN PIPE | Material |  |  | 1
3422 - 3054 | COARSE SAND FOR STORMWATER MANAGEMENT FACILITIES | Material |  |  | 1
3422 - 3055 | BIORETENTION SOIL MIX | Material |  |  | 1
3422 - 3056 | STORMWATER MANAGEMENT FACILITY AS-BUILT CERTIFICATION | Material |  |  | 1
3422 - 3057 | ACCESS ROAD WITH CELLULAR CONFINEMENT LOAD SUPPORT SYSYTEM | Material |  |  | 1
3422 - 3058 | BOTTOM CUTOFF WALLS FOR CLASS I RIPRAP | Material |  |  | 1
3422 - 3059 | BOTTOM CUTOFF WALLS FOR CLASS II RIPRAP | Material |  |  | 1
3422 - 3060 | 6 INCH PERFORATED CIRCULAR PIPE LONGITUDINAL UNDERDRAIN | Material |  |  | 1
3422 - 3061 | 6 INCH CIRCULAR PIPE UNDERDRAIN OUTLETS | Material |  |  | 1
3422 - 4001 | TEMP SUPPORT OF EXCAVATION | Material |  |  | 1
3422 - 4002 | UTILITY SERVICE LINES ON BRIDGE | Material |  |  | 1
3422 - 4003 | MAINTENANCE OF STREAM FLOW | Material |  |  | 1
3422 - 4004 | MAINTENANCE OF TRAFFIC FOR BRIDGE DECK PATCHING OPERATION | Material |  |  | 1
3422 - 4005 | PATCHING FOR MAINTENANCE OF EXISTING BRIDGE DECK | Material |  |  | 1
3422 - 4006 | REMOVAL OF EXISTING BRIDGE SUPERSTRUCTURE | Material |  |  | 1
3422 - 4007 | REMOVAL OF EXISTING BRIDGE SUBSTRUCTURE | Material |  |  | 1
3422 - 4008 | CLASS 3 EXCAVATION | Material |  |  | 1
3422 - 4009 | SUBFOUNDATION INVESTIGATION | Material |  |  | 1
3422 - 4010 | FOOTING CONCRETE | Material |  |  | 1
3422 - 4011 | SUBSTRUCTURE CONCRETE FOR BRIDGE NO0300800 | Material |  |  | 1
3422 - 4012 | SUPERSTRUCTURE CONCRETE FOR BRIDGE NO0300800 | Material |  |  | 1
3422 - 4013 | CONCRETE PARAPET FOR BRIDGE NO0300800 | Material |  |  | 1
3422 - 4014 | LINSEED OIL PROTECTIVE COATING BRIDGE NO0300800 | Material |  |  | 1
3422 - 4015 | DRILLED SHAFT 48 INCH DIAMETER | Material |  |  | 1
3422 - 4016 | EPOXY COATED REIN STEEL BARS IN SUPERSTR FOR BRIDGE NO0300800 | Material |  |  | 1
3422 - 4017 | FABRICATED STRUCTURAL STEEL FOR BRIDGE NO0300800 | Material |  |  | 1
3422 - 4018 | FABRICATED STRUCTURAL STEEL FOR UTILITY SUPPORTS | Material |  |  | 1
3422 - 4019 | STEEL STUD SHEAR DEVELOPERS FOR BRIDGE NO0300800 | Material |  |  | 1
3422 - 4020 | CHAIN LINK SAFETY FENCE FOR BRIDGE-TYPE II | Material |  |  | 1
3422 - 4021 | CHAIN LINK SAFETY FENCE ANTI-CLIMB SHIELD | Material |  |  | 1
3422 - 4022 | CHAIN LINK FENCE - TYPE III | Material |  |  | 1
3422 - 4023 | RIPRAP SLOPE PROTECTION FOR BRIDGE | Material |  |  | 1
3422 - 4024 | SIDE CUTOFF WALLS FOR RIPRAP SLOPE PROTECTION FOR BRIDGE | Material |  |  | 1
3422 - 4025 | DRILLED SHAFT IN ROCK 48 INCH DIAMETER | Material |  |  | 1
3422 - 5001 | FINE MILLING ASPHALT PAVEMENT (1-2.5" DEPTH) | Material |  |  | 1
3422 - 5002 | SUPERPAVE ASPHALT MIX 9.5MM FOR WEDGE/LEVEL, PG 64S-22, LEVEL 2 | Material |  |  | 1
3422 - 5003 | SUPERPAVE ASPHALT MIX 12.5MM FOR SURFACE, HDFV, PG 64S-22, LEVEL 2 | Material |  |  | 1
3422 - 5004 | SUPERPAVE ASPHALT MIX 19.0MM FOR BASE, PG 64S-22, LEVEL 2 | Material |  |  | 1
3422 - 5005 | SUPERPAVE ASPHALT MIX 19.0MM FOR WEDGE/LEVEL, PG 64S-22, LEVEL 2 | Material |  |  | 1
3422 - 5006 | SUPERPAVE ASPHALT MIX 19.0MM FOR FULL-DEPTH PATCH, PG 64S-22, LEVEL 2 | Material |  |  | 1
3422 - 5007 | SUPERPAVE ASPHALT MIX 19.0MM FOR PARTIAL-DEPTH PATCH , PG 64S-22, LEVEL 2 | Material |  |  | 1
3422 - 5008 | PRICE ADJUSTMENT FOR ASPHALT BINDER | Material |  |  | 1
3422 - 5009 | PAYMENT ADJUSTMENT FOR PAVEMENT DENSITY | Material |  |  | 1
3422 - 5010 | PAYMENT ADJUSTMENT FOR ASPHALT MIXTURE | Material |  |  | 1
3422 - 5011 | 6 INCH GRADED AGGREGATE BASE COURSE | Material |  |  | 1
3422 - 5012 | 5 INCH WHITE CONTRAST PAVEMENT MARKING TAPE | Material |  |  | 1
3422 - 5013 | 5 INCH WHITE PAVEMENT MARKING TAPE | Material |  |  | 1
3422 - 5014 | 5 INCH YELLOW PAVEMENT MARKING TAPE | Material |  |  | 1
3422 - 5015 | 5 INCH WHITE THERMOPLASTIC PAVEMENT MARKINGS | Material |  |  | 1
3422 - 5016 | 5 INCH YELLOW THERMOPLASTIC PAVEMENT MARKINGS | Material |  |  | 1
3422 - 5017 | 10 INCH WHITE THERMOPLASTIC PAVEMENT MARKINGS | Material |  |  | 1
3422 - 5018 | 5 INCH WHITE 40 MIL HIGH BINDER THERMOPLASTIC PAVEMENT MARKINGS | Material |  |  | 1
3422 - 5019 | 5 INCH YELLOW 40 MIL HIGH BINDER THERMOPLASTIC PAVEMENT MARKINGS | Material |  |  | 1
3422 - 5020 | 10 INCH WHITE 40 MIL HIGH BINDER THERMOPLASTIC PAVEMENT MARKINGS | Material |  |  | 1
3422 - 5021 | 12 INCH WHITE PREFORMED THERMOPLASTIC PAVEMENT MARKING LINES | Material |  |  | 1
3422 - 5022 | 24 INCH WHITE PREFORMED THERMOPLASTIC PAVEMENT MARKING LINES | Material |  |  | 1
3422 - 5023 | WHITE PREFORMED THERMOPLASTIC PMT MARKING LEGENDS & SYMBOLS | Material |  |  | 1
3422 - 5024 | SNOWPLOWABLE RAISED PMT MARKER W/ STEEL HOLDER & ONE WAY LENS | Material |  |  | 1
3422 - 5025 | SNOWPLOWABLE RAISED PMT MARKER W/ STEEL HOLDER & TWO WAY LENS | Material |  |  | 1
3422 - 5026 | REMOVAL OF EXIST SNOWPLOWABLE RAISED PMT MARKER LENS & HOLDER | Material |  |  | 1
3422 - 5027 | REMOVAL OF EXISTING PAVEMENT MARKING LINES, ANY WIDTH | Material |  |  | 1
3422 - 5028 | 6 INCH PORTLAND CEMENT CONCRETE PAVEMENT FOR DRIVEWAY MIX 9 | Material |  |  | 1
3422 - 5029 | PORTLAND CEMENT CONCRETE PAVEMENT REPAIRS TYPE I (12 HOURS) | Material |  |  | 1
3422 - 5030 | REMOVAL OF UNSUITABLE MATERIAL & REFILL | Material |  |  | 1
3422 - 6001 | 30 FOOT GATE FOR 5 FOOT GALVANIZED CHAIN LINK FENCE | Material |  |  | 1
3422 - 6002 | STANDARD 7" COMBINATION CURB & GUTTER (BALTCOSTANDARD R-21) | Material |  |  | 1
3422 - 6003 | CONCRETE TRAFFIC BARRIER REFLECTIVE DELINEATORS | Material |  |  | 1
3422 - 6004 | STD TYPE A COMBINATION CURB & GUTTER 12" GUTTER PAN 8"MIN DEPTH | Material |  |  | 1
3422 - 6005 | MONOLITHIC CONCRETE MEDIAN 4 FEET 0 INCH WIDE TYPE A-1 | Material |  |  | 1
3422 - 6006 | 5 INCH CONCRETE SIDEWALK | Material |  |  | 1
3422 - 6007 | DETECTABLE WARNING SURFACE FOR CURB RAMPS | Material |  |  | 1
3422 - 6008 | TRAFFIC BARRIER W BEAM USING 8 FOOT POST | Material |  |  | 1
3422 - 6009 | TYPE B TRAFFIC BARRIER END TREATMENT | Material |  |  | 1
3422 - 6010 | TYPE C TRAFFIC BARRIER END TREATMENT | Material |  |  | 1
3422 - 6011 | TYPE K TRAFFIC BARRIER END TREATMENT, ANY OPTION | Material |  |  | 1
3422 - 6012 | TRAFFIC BARRIER THRIE BEAM ANCHORAGE TO VERT FACE - WOOD POST | Material |  |  | 1
3422 - 6013 | REMOVAL & DISPOSAL OF EXISTING TRAFFIC BARRIER W BEAM | Material |  |  | 1
3422 - 6014 | W BEAM BARRIER REFLECTIVE DELINEATORS | Material |  |  | 1
3422 - 6015 | 5 FOOT GALVANIZED CHAIN LINK FENCE | Material |  |  | 1
3422 - 6016 | 8 FOOT GALVANIZED CHAIN LINK FENCE | Material |  |  | 1
3422 - 6017 | TERMINAL POST FOR 5 FOOT GALVANIZED CHAIN LINK FENCE | Material |  |  | 1
3422 - 6018 | TERMINAL POST FOR 8 FOOT GALVANIZED CHAIN LINK FENCE | Material |  |  | 1
3422 - 6019 | 12 FOOT GATE FOR 5 FOOT GALVANIZED CHAIN LINK FENCE | Material |  |  | 1
3422 - 6020 | REMOVE & DISPOSE OF EXISTING FENCE | Material |  |  | 1
3422 - 6021 | REMOVE & RESET EXISTING FENCE | Material |  |  | 1
3422 - 7001 | HERBICIDE CONCENTRATE GLYPHOSATE | Material |  |  | 1
3422 - 7002 | HERBICIDE CONCENTRATE TRICLOPYR | Material |  |  | 1
3422 - 7003 | RTU HERBICIDE TRICLOPYR | Material |  |  | 1
3422 - 7004 | PLACING SALVAGED SUBSOIL 18 INCH DEPTH | Material |  |  | 1
3422 - 7005 | PLACING FURNISHED TOPSOIL 2 INCH DEPTH | Material |  |  | 1
3422 - 7006 | PLACING FURNISHED TOPSOIL 4 INCH DEPTH | Material |  |  | 1
3422 - 7007 | TEMP SEED | Material |  |  | 1
3422 - 7008 | TEMP MULCH | Material |  |  | 1
3422 - 7009 | TURFGRASS ESTABLISHMENT | Material |  |  | 1
3422 - 7010 | REFERTILIZING | Material |  |  | 1
3422 - 7011 | UPLAND MEADOW ESTABLISHMENT | Material |  |  | 1
3422 - 7012 | LOWLAND MEADOW ESTABLISHMENT | Material |  |  | 1
3422 - 7013 | VEGETATION MANAGEMENT CREW | Material |  |  | 1
3422 - 7014 | TURFGRASS SOD ESTABLISHMENT | Material |  |  | 1
3422 - 7015 | TYPE A SOIL STABILIZATION MATTING | Material |  |  | 1
3422 - 7016 | TYPE B SOIL STABILIZATION MATTING | Material |  |  | 1
3422 - 7017 | TYPE D SOIL STABILIZATION MATTING | Material |  |  | 1
3422 - 7018 | TREE, SHRUB, & PERENNIAL INSTALLATION & ESTABLISHMENT | Material |  |  | 1
3422 - 7019 | TREE FELLING | Material |  |  | 1
3422 - 7020 | SHREDDED HARDWOOD BARK MULCHING 3 INCH DEPTH | Material |  |  | 1
3422 - 7021 | TREE ROOT PRUNING | Material |  |  | 1
3422 - 7022 | TREE BROADCAST FERTILIZING | Material |  |  | 1
3422 - 8001 | WATER METER REPLACEMENT | Material |  |  | 1
3422 - 8002 | CATHODIC PROTECTION | Material |  |  | 1
3422 - 8003 | CONCRETE FOR SIGN FOUNDATION | Material |  |  | 1
3422 - 8004 | CONCRETE FOR SIGNAL FOUNDATION | Material |  |  | 1
3422 - 8005 | WOOD SIGN SUPPORTS 4 INCH X 4 INCH | Material |  |  | 1
3422 - 8006 | WOOD SIGN SUPPORTS 4 INCH X 6 INCH | Material |  |  | 1
3422 - 8007 | SHEET ALUMINUM SIGNS | Material |  |  | 1
3422 - 8008 | INSTALL SHEET ALUMINUM SIGN | Material |  |  | 1
3422 - 8009 | EXTRUDED ALUMINUM SIGNS | Material |  |  | 1
3422 - 8010 | REMOVE EXISTING GROUND MOUNTED SIGNS & SUPPORTS | Material |  |  | 1
3422 - 8011 | REMOVE EXISTING CANTILEVER STR, SIGNS & SUPPORTS | Material |  |  | 1
3422 - 8012 | CANTILEVER SIGN STRUCTURE | Material |  |  | 1
3422 - 8013 | 3 INCH SCHEDULE 80 RIGID PVC CONDUIT-BORED | Material |  |  | 1
3422 - 8014 | 3 INCH SCHEDULE 80 RIGID PVC CONDUIT-TRENCHED | Material |  |  | 1
3422 - 8015 | ELECTRICAL UTILITY SERVICE EQUIPMENT 120/240 VOLTS 200 AMPS | Material |  |  | 1
3422 - 8016 | MICROLOOP PROBE, 500 FOOT LEAD IN CABLE | Material |  |  | 1
3422 - 8017 | FURNISH & INSTALL ELECTRICAL HANDHOLE | Material |  |  | 1
3422 - 8018 | 6 INCH VALVE & VAULT | Material |  |  | 1
3422 - 8019 | 8 INCH VALVE & VAULT | Material |  |  | 1
3422 - 8020 | 12 INCH VALVE & VAULT | Material |  |  | 1
3422 - 8024 | INSTALL AIR RELEASE & ACCESS MANHOLE | Material |  |  | 1
3422 - 8025 | FIRE HYDRANT | Material |  |  | 1
3422 - 8029 | 6 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material |  |  | 1
3422 - 8030 | 8 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material |  |  | 1
3422 - 8031 | 12 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material |  |  | 1
3422 - 8032 | 16 INCH DUCTILE IRON PIPE WATER MAIN CLASS 54 | Material |  |  | 1
3422 - 8033 | RELOCATE EXISTING GROUND MOUNTED SIGNS | Material |  |  | 1
3422 - 8034 | IP-BASED VIDEO DETECTION CAMERA & ANY LENGTH LEAD-IN CABLE | Material |  |  | 1
3422 - 8035 | STEEL POLE WITH A SINGLE 60 FOOT MAST ARM | Material |  |  | 1
3422 - 8036 | DISCONNECT, PULL-BACK & REROUTE CABLES | Material |  |  | 1
3422 - 8037 | GROUND ROD - 3/4 INCH DIAMETER X 10 FOOT LENGTH | Material |  |  | 1
3422 - 8038 | RELOCATE EXISTING SIGNAL HEAD | Material |  |  | 1
3422 - 8039 | 12 INCH LED VEHICULAR TRAFFIC SIGNAL HEAD SECTION | Material |  |  | 1
3422 - 8040 | ELECTRICAL CABLE - 2 CONDUCTOR (NO14 AWG) | Material |  |  | 1
3422 - 8041 | INSTALL TWO CIRCUIT FLASHER & CABINET - POLE MOUNT | Material |  |  | 1
3422 - 8042 | REMOVE & DISPOSE OF EXISTING SIGNAL EQUIPMENT | Material |  |  | 1
3422 - 8043 | #10 SIEVE SAND FOR TRENCH BACKFILL | Material |  |  | 1
3422 - 8044 | GRADED AGGREGATE BASE FOR TRENCH BACKFILL | Material |  |  | 1
3422 - 8045 | 3 INCH WATER SERVICE DUCTILE | Material |  |  | 1
3422 - 8046 | 16 INCH VALVE & VAULT | Material |  |  | 1
3422 - 8047 | 36 X 16 TAPPING SLEEVE VALVE & VAULT | Material |  |  | 1
3422 - 8049 | 3/4 INCH WATER HOUSE CONNECTION COPPER | Material |  |  | 1
3422 - 8050 | 3/4 INCH INSULATING TAP & CORPORATION STOP | Material |  |  | 1
3422 - 8051 | 3 INCH VALVE & SMALL SECTIONAL VAULT | Material |  |  | 1
3422 - 8052 | 6 INCH VALVE & SMALL SECTIONAL VAULT | Material |  |  | 1
3422 - 8053 | RELOCATE 6 INCH METER & VAULT | Material |  |  | 1
9151 | I-10 DB Project | Nonlabor |  |  | 1
3364.420.6066 | CL C CONC (RAIL FOUNDATION) | Material | Cubic Yard |  | 8
3394 - COST | Cost Resource | Material |  |  | 1
SWLRT | SWLRT - Resources | Labor |  |  | 1
3275 | US 17-92 Interchange Project Resources | Labor |  |  | 1
3329-3804I | 3804- Interchange SA - Lump Sum Items | Material | Day |  | 8
3329-402 | 3804-Inter- Mobilization | Material | Lump Sum |  | 8
3329-403 | 3804-Inter- Construction Survey | Material | Lump Sum |  | 8
3329-404 | 3804-Inter- Clear & Grub | Material |  |  | 8
3329-405 | 3804-Inter- Unclassified Excavation | Material | Cubic Yard |  | 8
3329-406 | 3804-Inter- Drainage Ditch Excavation | Material | Cubic Yard |  | 8
3329-407 | 3804-Inter- Embankment Settlement Gauges | Material | Each |  | 8
3329-408 | 3804-Inter- Berm Ditch Construction | Material | Linear Feet |  | 8
3329-409 | 3804-Inter- Proof Rolling | Material | Hour |  | 8
3329-410 | 3804-Inter- Select Granular Material | Material | Cubic Yard |  | 8
3329-411 | 3804-Inter- Fine Grading | Material | Lump Sum |  | 8
3329-412 | 3804-Inter- Foundation Conditioning Material | Material |  |  | 8
3329-413 | 3804-Inter- Foundation Conditioning Geotextile | Material | Square Yard |  | 8
3329-414 | 3804-Inter- 15" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-415 | 3804-Inter- 18" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-416 | 3804-Inter- 24" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-417 | 3804-Inter- 30" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-418 | 3804-Inter- 36" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-419 | 3804-Inter- 42" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-420 | 3804-Inter- 48" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3329-421 | 3804-Inter- 54" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3329-422 | 3804-Inter- 60" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3329-423 | 3804-Inter- 15" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3329-424 | 3804-Inter- 18" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3329-425 | 3804-Inter- 30" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3329-426 | 3804-Inter- 48" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3329-427 | 3804-Inter- Pipe Removal | Material | Linear Feet |  | 8
3329-428 | 3804-Inter- Endwalls | Material | Cubic Yard |  | 8
3329-429 | 3804-Inter- Pipe Collars | Material | Cubic Yard |  | 8
3329-430 | 3804-Inter- Pipe Plugs | Material | Cubic Yard |  | 8
3329-431 | 3804-Inter- 15'' CS Pipe Elbow | Material | Each |  | 8
3329-432 | 3804-Inter- 18'' CS Pipe Elbow | Material | Each |  | 8
3329-433 | 3804-Inter- Flowable Fill | Material | Cubic Yard |  | 8
3329-434 | 3804-Inter- Masonry Drainage Structures | Material | Each |  | 8
3329-435 | 3804-Inter- Masonry Drainage Structures - Additional Height | Material | Linear Feet |  | 8
3329-436 | 3804-Inter- BDO, Std. 850.1 | Material | Each |  | 8
3329-437 | 3804-Inter- Frame with Grate, Std. 840.16 | Material | Each |  | 8
3329-438 | 3804-Inter- Frame with Two Grates, Std(W.S. Flat) 840.20 | Material | Each |  | 8
3329-439 | 3804-Inter- Frame with Two Grates, Std(W.S. Sag) 840.22 | Material | Each |  | 8
3329-440 | 3804-Inter- Steel Frame with Two Grates, Std 840.37 | Material | Each |  | 8
3329-441 | 3804-Inter- Frame with Cover, Std 840.54 | Material | Each |  | 8
3329-442 | 3804-Inter- Adjustment of Drop Inlets | Material | Each |  | 8
3329-443 | 3804-Inter- Conv Ex Drop Inlet to JB with MH | Material | Each |  | 8
3329-444 | 3804-Inter- Rip Rap, Class I | Material |  |  | 8
3329-445 | 3804-Inter- Rip Rap, Class B | Material |  |  | 8
3329-446 | 3804-Inter- Geotextile for Drainage | Material | Square Yard |  | 8
3329-447 | 3804-Inter- Aggregate Base Course | Material |  |  | 8
3329-448 | 3804-Inter- Incidental Stone Base | Material |  |  | 8
3329-449 | 3804-Inter- Incidental Milling | Material | Square Yard |  | 8
3329-450 | 3804-Inter- Fabric Under PCCP, Reflectex | Material | Square Yard |  | 8
3329-451 | 3804-Inter- 12" PCCP Through Lanes | Material | Square Yard |  | 8
3329-452 | 3804-Inter- 12" PCCP Shoulders | Material | Square Yard |  | 8
3329-453 | 3804-Inter- Diamond Grind | Material | Square Yard |  | 8
3329-454 | 3804-Inter- Surface Testing Concrete Pavement | Material | Lump Sum |  | 8
3329-455 | 3804-Inter- Lane Closures | Material | Each |  | 8
3329-456 | 3804-Inter- Construction Access | Material | Lump Sum |  | 8
3329-457 | 3804-Inter- Major Traffic Shifts - (Open Interchange) | Material | Each |  | 8
3329-458 | 3804-Inter- Portable Lighting | Material | Lump Sum |  | 8
3329-459 | 3804-Inter- Work Zone Signs (Portable) | Material | Square Feet |  | 8
3329-460 | 3804-Inter- Flashing Arrow Board | Material | Each |  | 8
3329-461 | 3804-Inter- Portable Changeable Message Sign | Material | Each |  | 8
3329-462 | 3804-Inter- Drums | Material | Each |  | 8
3329-463 | 3804-Inter- Cones | Material | Each |  | 8
3329-464 | 3804-Inter- Flagger - (Crew Days) | Material | Day |  | 8
3329-465 | 3804-Inter- Temp. Crash Cushions | Material | Each |  | 8
3329-466 | 3804-Inter- Reset Crash Cushions | Material | Each |  | 8
3329-467 | 3804-Inter- Truck Mounted Attenuator | Material | Each |  | 8
3329-468 | 3804-Inter- Portable Concrete Barrier | Material | Linear Feet |  | 8
3329-469 | 3804-Inter- Reset Portable Concrete Barrier | Material | Linear Feet |  | 8
3329-470 | 3804-Inter- Law Enforcement | Material | Hour |  | 8
3329-471 | 3804-Inter- Concrete Barrier Transition Section | Material | Each |  | 8
3329-472 | 3804-Inter- Precast Reinforced Concrete Barrier, Single Faced | Material | Linear Feet |  | 8
3329-473 | 3804-Inter- Snowplowable Pavement Markers | Material | Each |  | 8
3329-474 | 3804-Inter- Contractor Furnished, Type A Sign | Material | Square Feet |  | 8
3329-475 | 3804-Inter- Contractor Furnished, Type B Sign | Material | Square Feet |  | 8
3329-476 | 3804-Inter- Contractor Furnished, Type D Sign | Material | Square Feet |  | 8
3329-477 | 3804-Inter- Contractor Furnished, Type E Sign | Material | Square Feet |  | 8
3329-478 | 3804-Inter- Contractor Furnished, Type F Sign | Material | Square Feet |  | 8
3329-479 | 3804-Inter- Overhead Footing | Material | Cubic Yard |  | 8
3329-480 | 3804-Inter- Supports, Breakaway Steel Beam | Material | Per Pound |  | 8
3329-481 | 3804-Inter- Supports, 3-B Steel U-Channel | Material | Linear Feet |  | 8
3329-482 | 3804-Inter- Supports, OH Sign Structure (49300N-C) | Material | Lump Sum |  | 8
3329-483 | 3804-Inter- Supports, OH Sign Structure (51873N-C) | Material | Lump Sum |  | 8
3329-484 | 3804-Inter- Supports, OH Sign Structure (54483N-C) | Material | Lump Sum |  | 8
3329-485 | 3804-Inter- Supports, OH Sign Structure (58750S-C) | Material | Lump Sum |  | 8
3329-486 | 3804-Inter- Supports, OH Sign Structure (61500S-C) | Material | Lump Sum |  | 8
3329-487 | 3804-Inter- Supports, OH Sign Structure (64123S-C) | Material | Lump Sum |  | 8
3329-488 | 3804-Inter- Sign Erection, Type D | Material | Each |  | 8
3329-489 | 3804-Inter- Sign Erection, Type E | Material | Each |  | 8
3329-490 | 3804-Inter- Sign Erection, Type F | Material | Each |  | 8
3329-491 | 3804-Inter- Sign Erection, Type A (Overhead) | Material | Each |  | 8
3329-492 | 3804-Inter- Sign Erection, Type B (Overhead) | Material | Each |  | 8
3329-493 | 3804-Inter- Sign Erection, Type A (Ground Mounted) | Material | Each |  | 8
3329-494 | 3804-Inter- Lighting Per NCDOT Plan | Material | Lump Sum |  | 8
3329-495 | 3804-Inter- Stilling Basins | Material | Cubic Yard |  | 8
3329-496 | 3804-Inter- Impervious Dike | Material | Linear Feet |  | 8
3329-497 | 3804-Inter- Generic Erosion Control Item - Diversion Pumping | Material | Lump Sum |  | 8
3329-498 | 3804-Inter- Culvert Diversion Channel | Material | Cubic Yard |  | 8
3329-499 | 3804-Inter- Culvert Excavation | Material | Lump Sum |  | 8
3329-500 | 3804-Inter- Placement of Natural Streambed Material | Material | Lump Sum |  | 8
3329-501 | 3804-Inter- Foundation Conditioning Material, Box Culvert | Material |  |  | 8
3329-502 | 3804-Inter- Class A Concrete (Culvert) | Material | Cubic Yard |  | 8
3329-503 | 3804-Inter- Reinforcing Steel (Culvert) | Material | Per Pound |  | 8
3329-504 | 3804-Inter- Mod. Removal of Ex. Struct Old Beatty Ford Rd / I-85 | Material | Lump Sum |  | 8
3329-505 | 3804-Inter- Concrete Washout | Material | Each |  | 8
3329-506 | 3804-Inter- CSL Testing | Material | Each |  | 8
3329-507 | 3804-Inter- PDA Testing | Material | Each |  | 8
3329-508 | 3804-Inter- SPT Testing | Material | Each |  | 8
3329-509 | 3804-Inter- Unclassified Structure Excavation - Structure No. 9 | Material | Lump Sum |  | 8
3329-510 | 3804-Inter- Reinforced Concrete Deck Slab | Material | Square Feet |  | 8
3329-511 | 3804-Inter- Grinding Bridge Floors | Material | Square Feet |  | 8
3329-512 | 3804-Inter- Class A Concrete (Bridge) | Material | Cubic Yard |  | 8
3329-513 | 3804-Inter- Reinforced Bridge Approach Slabs | Material | Lump Sum |  | 8
3329-514 | 3804-Inter- Reinforced Bridge Fill | Material | Lump Sum |  | 8
3329-515 | 3804-Inter- Reinforcing Steel (Bridge) | Material | Per Pound |  | 8
3329-516 | 3804-Inter- 36" AASHTO Type II - Prestressed Concrete Girders | Material | Linear Feet |  | 8
3329-517 | 3804-Inter- Spiral Column Reinforcing Steel | Material | Per Pound |  | 8
3329-518 | 3804-Inter- HP 12x53 Steel Piles | Material | Linear Feet |  | 8
3329-519 | 3804-Inter- Steel Pile Points | Material | Each |  | 8
3329-520 | 3804-Inter- Concrete Parapet | Material | Linear Feet |  | 8
3329-521 | 3804-Inter- Rip Rap Class II | Material |  |  | 8
3329-522 | 3804-Inter- Elastomeric Bearing | Material | Lump Sum |  | 8
3329-523 | 3804-Inter- Expansion Joint Seals | Material | Lump Sum |  | 8
3329-524 | 3804-Inter- Undercut Excavation | Material | Cubic Yard |  | 8
3329-525 | 3804-Inter- Shallow Undercut | Material | Cubic Yard |  | 8
3329-526 | 3804-Inter- Class IV Subgrade Stabilization | Material |  |  | 8
3329-527 | 3804-Inter- Geotextile for Soil Stabilization | Material | Square Yard |  | 8
3329-528 | 3804-Inter- Type V Geotextile for Pvmt Stabilizaton | Material | Square Yard |  | 8
3329-529 | 3804-Inter- Add'tl Cost: 36" Jack & Bore - In Soil | Material | Linear Feet |  | 8
3329-530 | 3804-Inter- Add'tl Cost: 36" Jack & Bore - Not In Soil | Material | Linear Feet |  | 8
3329-531 | 3804-Inter- Add'tl Cost: 42" Jack & Bore - In Soil | Material | Linear Feet |  | 8
3329-532 | 3804-Inter- Add'tl Cost: 42" Jack & Bore - Not in Soil | Material | Linear Feet |  | 8
3329-533 | 3804-Inter- Add'tl Cost: 48" Jack & Bore - In Soil | Material | Linear Feet |  | 8
3329-534 | 3804-Inter- Add'tl Cost: 48" Jack & Bore - Not in Soil | Material | Linear Feet |  | 8
3329-535 | 3804-Inter- Soil Cement Base | Material | Square Yard |  | 8
3329-536 | 3804-Inter- Portland Cement For Soil Cement Base | Material |  |  | 8
3329-537 | 3804-Inter- Asphalt Curing Seal | Material | Gallon |  | 8
3329-538 | 3804-Inter- ACBC, Type B25.0B | Material |  |  | 8
3329-539 | 3804-Inter- ACIC, Type I19.0B | Material |  |  | 8
3329-540 | 3804-Inter- ACSC, Type S9.5B | Material |  |  | 8
3329-541 | 3804-Inter- ACSC, Type SF9.5A | Material |  |  | 8
3329-542 | 3804-Inter- Patch Existing Asphalt Pavement | Material |  |  | 8
3329-543 | 3804-Inter- Temp. Silt Fence | Material | Linear Feet |  | 8
3329-544 | 3804-Inter- Stone for Erosion Control, Class A | Material |  |  | 8
3329-545 | 3804-Inter- Stone for Erosion Control, Class B | Material |  |  | 8
3329-546 | 3804-Inter- Sediment Control Stone | Material |  |  | 8
3329-547 | 3804-Inter- Temporary Mulching | Material |  |  | 8
3329-548 | 3804-Inter- Seed for Temporary Seeding | Material | LB |  | 8
3329-549 | 3804-Inter- Fertilizer for Temporary Seeding | Material |  |  | 8
3329-550 | 3804-Inter- Temporary Slope Drains | Material | Linear Feet |  | 8
3329-551 | 3804-Inter- Safety Fence | Material | Linear Feet |  | 8
3329-552 | 3804-Inter- Silt Excavation | Material | Cubic Yard |  | 8
3329-553 | 3804-Inter- Matting for Erosion Control | Material | Square Yard |  | 8
3329-554 | 3804-Inter- Coir Fiber Matting | Material | Square Yard |  | 8
3329-555 | 3804-Inter- Permanent Soil Reinforcement Matting | Material | Square Yard |  | 8
3329-556 | 3804-Inter- 1/4'' Hardware Cloth | Material | Linear Feet |  | 8
3329-557 | 3804-Inter- Wattle Barrier | Material | Linear Feet |  | 8
3329-558 | 3804-Inter- Polyacrylamide | Material | LB |  | 8
3329-559 | 3804-Inter- Coir Fiber Baffle | Material | Linear Feet |  | 8
3329-560 | 3804-Inter- 1.5" Skimmer | Material | Each |  | 8
3329-561 | 3804-Inter- 2" Skimmer | Material | Each |  | 8
3329-562 | 3804-Inter- Seeding and Mulching | Material |  |  | 8
3329-563 | 3804-Inter- Mowing | Material |  |  | 8
3329-564 | 3804-Inter- Specialized Hand Mowing | Material | Hour |  | 8
3329-565 | 3804-Inter- Seed for Repair Seeding | Material | LB |  | 8
3329-566 | 3804-Inter- Fertilizer for Repair Seeding | Material |  |  | 8
3329-567 | 3804-Inter- Seed for Supplemental Seeding | Material | LB |  | 8
3329-568 | 3804-Inter- Fertilizer Top Dressing | Material |  |  | 8
3329-569 | 3804-Inter- Response for Erosion Control | Material | Each |  | 8
3329-570 | 3804-Inter- Paint PVT MKG SYMB | Material | Each |  | 8
3329-571 | 3804-Inter- Paint PVT MKG 4'' | Material | Linear Feet |  | 8
3329-572 | 3804-Inter- Paint PVT MKG 24'' | Material | Linear Feet |  | 8
3329-573 | 3804-Inter- Temp Raised PVT MRK | Material | Each |  | 8
3329-574 | 3804-Inter- Right Of Way Markers | Material | Each |  | 8
3329-575 | 3804-Inter- 2'-6" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3329-576 | 3804-Inter- Shoulder Berm Gutter | Material | Linear Feet |  | 8
3329-577 | 3804-Inter- 5" Concrete Sidewalk | Material | Square Yard |  | 8
3329-578 | 3804-Inter- 5" Monolithic Concrete Islands | Material | Square Yard |  | 8
3329-579 | 3804-Inter- Steel Beam Guardrail, DASH | Material | Linear Feet |  | 8
3329-580 | 3804-Inter- Temporary Steel Beam Guardrail | Material | Linear Feet |  | 8
3329-581 | 3804-Inter- Additional Guardrail Posts | Material | Each |  | 8
3329-582 | 3804-Inter- Guardrail Anchor Units, Type CAT-1, DASH | Material | Each |  | 8
3329-583 | 3804-Inter- Guardrail Anchor Units, Type 350, DASH | Material | Each |  | 8
3329-584 | 3804-Inter- Guardrail Anchor Units, Type B-77 | Material | Each |  | 8
3329-585 | 3804-Inter- Guardrail Anchor Units, Type AT-1 | Material | Each |  | 8
3329-586 | 3804-Inter- Double-Faced Guardrail | Material | Linear Feet |  | 8
3329-587 | 3804-Inter- Curved Steel beam Guardrail | Material | Linear Feet |  | 8
3329-588 | 3804-Inter- Glare Screen | Material | Linear Feet |  | 8
3329-589 | 3804-Inter- Remove Existing Guardrail | Material | Linear Feet |  | 8
3329-590 | 3804-Inter- Woven Wire Fence, 47" Fabric | Material | Linear Feet |  | 8
3329-591 | 3804-Inter- 4'' Timber Fence Posts - 7'-6'' Long | Material | Each |  | 8
3329-592 | 3804-Inter- 5'' Timber Fence Posts - 8' Long | Material | Each |  | 8
3329-593 | 3804-Inter- Thermoplastic Pavement Marking Lines (8", 90 Mils) | Material | Linear Feet |  | 8
3329-594 | 3804-Inter- Thermoplastic Pavement Marking Lines (24", 120 Mils) | Material | Linear Feet |  | 8
3329-595 | 3804-Inter- Polyurea Pavement Markings (4", Highly Reflective) | Material | Linear Feet |  | 8
3329-596 | 3804-Inter- Polyurea Pavement Markings (6" Highly Reflective) | Material | Linear Feet |  | 8
3329-597 | 3804-Inter- Polyurea Pavement Markings (12" Highly Reflective) | Material | Linear Feet |  | 8
3329-598 | 3804-Inter- Permanent Raised Pavement Markers | Material | Each |  | 8
3329-599 | 3804-Inter- 42" Drilled Shaft - In Soil | Material | Linear Feet |  | 8
3329-600 | 3804-Inter- 42" Drilled Shaft - Not In Soil | Material | Linear Feet |  | 8
3329-601 | 3804-Inter- Perm Steel Casing for 42" Drilled Shaft | Material | Linear Feet |  | 8
3329-602 | 3804-Inter- Signal Cable | Material | Linear Feet |  | 8
3329-603 | 3804-Inter- Vehicle Signal Head (12", 3 Section) | Material | Each |  | 8
3329-604 | 3804-Inter- Vehicle Signal Head (12", 4 Section) | Material | Each |  | 8
3329-605 | 3804-Inter- Vehicle Signal Head (12", 5 Section) | Material | Each |  | 8
3329-606 | 3804-Inter- Messenger Cable (3/8") | Material | Linear Feet |  | 8
3329-607 | 3804-Inter- Unpaved Trenching (1-2 Inch Conduit) | Material | Linear Feet |  | 8
3329-608 | 3804-Inter- Junction Box (Standard Size) | Material | Each |  | 8
3329-609 | 3804-Inter- Inductive Loop Sawcut | Material | Linear Feet |  | 8
3329-610 | 3804-Inter- Lead-In Cable (14-2) | Material | Linear Feet |  | 8
3329-611 | 3804-Inter- New Electrical Service | Material | Each |  | 8
3329-612 | 3804-Inter- Metal Strain Signal Pole | Material | Each |  | 8
3329-613 | 3804-Inter- Soil Test | Material | Each |  | 8
3329-614 | 3804-Inter- Drilled Pier Foundation | Material | Cubic Yard |  | 8
3329-615 | 3804-Inter- Sign for Signals | Material | Each |  | 8
3329-616 | 3804-Inter- Signal Cabinet Foundation | Material | Each |  | 8
3329-617 | 3804-Inter- Controller With Cabinet (Type 2070L, Base Mounted) | Material | Each |  | 8
3329-618 | 3804-Inter- Detector Card (Type 2070L) | Material | Each |  | 8
3329-619 | 3804-Inter- Cabinet Base Extender | Material | Each |  | 8
3329-620 | 3804-Inter- Subdrain Excavation | Material | Cubic Yard |  | 8
3329-621 | 3804-Inter- Subdrain Fine Aggregate | Material | Cubic Yard |  | 8
3329-622 | 3804-Inter- Subdrain Pipe Outlet | Material | Each |  | 8
3329-623 | 3804-Inter- 6" Outlet Pipe | Material | Linear Feet |  | 8
3329-624 | 3804-Inter- 6" Perforated Subdrain Pipe | Material | Linear Feet |  | 8
3329-3804I-UP | 3804-Interchange - Unit Price Items | Material |  |  | 8
CO 14 | Change order 14 - NTTA request for CCTV camera at Kingswood/Green Oaks Interchg | Material | Lump Sum |  | 8
3417-Revenue Items | 3417 - Original Contract Revenue Items | Nonlabor |  |  | 1
3417-Supplemental | 3417 - Supplemenatal Revenue Items | Nonlabor |  |  | 1
3417-00115 | NS SOIL CONTAMINATED DISPOSAL | Material |  |  | 1
3417-25577 | NS CONTRACT CONTAMINATED GROWNDWATER DISPOSAL | Material | Gallon |  | 1
3417-85001 | NS CONTAMINATED WATER STORAGE | Material | Lump Sum |  | 1
3417-45584 | 24" JACKED STEEL ENCASEMENT PIPE | Material | Linear Feet |  | 1
I-10 SD_Sub | I-10 Special Design Structures Submital (12 Max/Week) | Nonlabor |  |  | 1
I-10 SS_Sub | I-10 Special Design Sign Structures Submital (4 Max) | Nonlabor |  |  | 1
SCE | SCE Relocations | Nonlabor |  |  | 0
I-10 RevSTR | I-10 Bridge Agg.Review STS, ID & RFC (12 Max/Week) | Nonlabor |  |  | 1
I-10 BRG_Sub | I-10 Bridge Submital (12 Max) | Nonlabor |  |  | 1
I-10 REV FD | I-10 Bridge Submittals Agg. FD Review (6 Max/Week) | Nonlabor |  |  | 1
I-10 RevSub | Roadway Sumittal Agg for Review (12 max/Week) | Nonlabor |  |  | 1
I-10 Rdwysub | Roadway Submittal (2 Max/Week) | Nonlabor |  |  | 1
I-10 B-STS | Bridge - Structure Type Selection (STS) Submittal (5 Max/week) | Nonlabor |  |  | 1
I-10 B-ID | Bridge - Intermediate Design (ID) Submittal (3 Max/Week) | Nonlabor |  |  | 1
I-10 B-FD | Bridge- Final Design (FD) Submittal (2 Max /Week) | Nonlabor |  |  | 1
I-10 B-RFC | Bridge - Release for Construction (RFC) Submittal (2 Max/Week) | Nonlabor |  |  | 1
I-10 SD-STS | SDS - Structure Type Selection (STS) Submittal (5 Max/week) | Nonlabor |  |  | 1
I-10 SD-ID | SDS - Intermediate Design (ID) Submittal (3 Max/Week) | Nonlabor |  |  | 1
I-10 SD-FD | SDS - Final Design (FD) Submittal (2 Max /Week) | Nonlabor |  |  | 1
I-10 SD-RFC | SDS - (RFC) Submittal (2 Max/Week) | Nonlabor |  |  | 1
I-10 SS-FD | SS - Sign Str. Final Design (FD) Submittal (2 Max /Week) | Nonlabor |  |  | 1
I-10 SS-RFC | SS - Sign Str. RFC Submittal (2 Max/Week) | Nonlabor |  |  | 1
3329-625 | SA23 - 24" Encasement Pipe | Material | Linear Feet |  | 8
3329-626 | SA23 - 30" Encasement Pipe | Material | Linear Feet |  | 8
3329-627 | SA23 - Rock Excavation for Utility Encasements | Material | Cubic Yard |  | 8
3329-628 | SA23 - 24" Trenchless install (In soil) | Material | Linear Feet |  | 8
3329-629 | SA23 - 24" Trenchless install (Not In soil) | Material | Linear Feet |  | 8
3329-630 | SA25 - Release of Claim | Material | Lump Sum |  | 8
3329-631 | Acceleration Median Traffic Shifts for NB&SB STA 590+00 | Material | Lump Sum |  | 8
3329-632 | MS#1 - Incentive I85 NB&SB Med Shift 484+40-590+00 8/31/18 | Material | Day |  | 8
3329-633 | 3804-Inter - SA20 BRIDGE SA CREDITS | Material | Lump Sum |  | 8
3329-634 | 3804-Inter - SA19 EMBANKMENT CREDIT | Material | Lump Sum |  | 8
3329-635 | 3804-Inter - SA 11 HYDRAULIC UPGRADES CREDIT | Material | Lump Sum |  | 8
3329-636 | 3804-Inter - NC152 INTERCHANGE LIGHTING CREDIT | Material | Lump Sum |  | 8
C00108424DB92.85018 | W.O-1 NS CLEAN EXIST STORM DRAIN PIPES | Material | Lump Sum |  | 8
3425 | 3425 - Cabot Yard | Nonlabor |  |  | 1
MB | Michael Baker | Labor |  |  | 1
Hamilton | Hamilton, NJ | Nonlabor |  |  | 1
I-10 OTH_Sub | I-10 Other Plans Submittal (12 Max) | Nonlabor |  |  | 1
I-10 O-STS | Other - Structure Type Selection (STS) Submittal (5 Max/week) | Nonlabor |  |  | 1
3425 - MBTA - Cabot Yard | Cabot Yard & Carhouse | Labor |  |  | 1
3425 - ABATE | Abatement Crew | Labor |  |  | 4
3425 - ELEV | Elevator Crew | Labor |  |  | 2
3425 - WHEEL | Wheel Truing Machine Crew | Labor |  |  | 2
3425 - LIFT | Truck Lift Crew | Labor |  |  | 2
3425 - WASH | Train Wash Crew | Labor |  |  | 2
3425 - CRANE | Crane Installation Crew | Labor |  |  | 3
3425 - MASON | Masonry Crew | Labor |  |  | 2
3425 - GLAZ | Glass & Glazer Crew | Labor |  |  | 2
3425 - WATER | Waterproofing Crew | Labor |  |  | 3
3425 - MECH | Mechanical Crew | Labor |  |  | 2
3425 - PLUMB | Plumbing Crew | Labor |  |  | 2
3425 - PAINT | Painting Crew | Labor |  |  | 2
3425 - TILE | Tile & Flooring Crew | Labor |  |  | 2
3425 - ROOF | Roofing Crew | Labor |  |  | 5
3425 - GYP | Gypsum/CFMF Crew | Labor |  |  | 2
3425 - PANEL | Metal Panel Crew | Labor |  |  | 2
3425 - DRILLER | Drilling Crew | Labor |  |  | 3
3425 - TEST | Test Pit Crew | Labor |  |  | 5
3425 - STEEL | Steel Crew | Labor |  |  | 5
3425 - MISC | Misc. Metals Crew | Labor |  |  | 3
3425 - ELEC | Electrician Crew | Labor |  |  | 3
3425 - CARP | Carpentry Crew | Labor |  |  | 3
3425 - RR-WE | Track Crew Weekend Outage | Labor |  |  | 12
3425 - RR-WD | Track Crew Weekday | Labor |  |  | 10
3425 - BOOTH | Paint Booth Crew | Labor |  |  | 2
3425 - CONC | Concrete Crew | Labor |  |  | 6
3425 - DEMO | Demolition Crew | Labor |  |  | 6
3425 - CEIL | Ceiling Crew | Labor |  |  | 2
3425 - DOOR | Door Crew | Labor |  |  | 2
3425 - FENCE | Fencing Crew | Labor |  |  | 3
3425 - SRAY | Spray Fire Proofing | Labor |  |  | 3
3425 - LAND | Landscaping Crew | Labor |  |  | 2
3425 - LINING | Conduit Cleaning & Lining Crew | Labor |  |  | 2
3425 - LABOR | General Laborer Crew | Labor |  |  | 3
3425 - SRVY | Survey Crew | Labor |  |  | 2
3425 - SITE | Sitework Crew | Labor |  |  | 3
3425 - SOE | Support of Excavation Crew | Labor |  |  | 7
3425 - EX-UTILIY | Utility Excavation & Installation Crew | Labor |  |  | 6
3425 - FLAT | Flatwork Crew | Labor |  |  | 6
3425 - MARK | Pavement Marking Crew | Labor |  |  | 2
3425 - PAVE | Paving Crew | Labor |  |  | 1
3425 - REBAR | Rebar Crew | Labor |  |  | 3
3425 - 0212170 | Remove Obsructions | Material | Cubic Yard |  | 8
3425 - 0130429 | Traffic Officers Services | Nonlabor |  |  | 0
3425 - 0213202 | Rodent Control | Nonlabor |  |  | 0
3425 - 0222027 | Material Removal | Nonlabor |  |  | 0
3425 - 0222087 | Pipeline Cleaning | Nonlabor |  |  | 0
3425 - 0222108 | Rock Excavation | Material | Cubic Yard |  | 8
3425 - 0222119 | Unsuitable Excavation | Material | Cubic Yard |  | 8
3425 - 0222442 | Test Pits | Material | Cubic Yard |  | 8
3425 - 0227007 | Filter Fabric | Material | Square Yard |  | 8
3425 - 0310049 | Concrete Cleaning & Restoration | Material | Square Feet |  | 8
3425 - 0354009 | Structural Crack Repair | Material | Linear Feet |  | 8
3425 - 6500000 | Risk Allowance | Nonlabor |  |  | 0
3425 - 0130174 | Maintenance Facility | Nonlabor |  |  | 0
3425 - 0275000 | Yard Improvements | Nonlabor |  |  | 0
3417-85018 | NS HRSD Reimbursement Fee | Material | Unit |  | 1
3417-85016 | NS Electricians | Material | Hour |  | 1
3417-27012 | Topsoil Class A-2" | Material |  |  | 1
3417-7000 | Demo Of Building - D732,D733,D734,D735 | Material |  |  | 1
3417-27112 | Hydraulic Erosion Control Product Type 3 | Material |  |  | 1
3417-27111 | Hydraulic Erosion Control Product Type 2 | Material |  |  | 1
3417-27110 | Hydraulic Erosion Control Product Type 1 | Material |  |  | 1
SUB-Subsurface Grout | Sub - Subsurface Grouting Crew | Labor |  |  | 1
3428 | 3428 Wekiva Parkway Section 8 | Nonlabor |  |  | 1
3428-001 | Mobilization | Material | Lump Sum |  | 8
3428-002 | Maintenance of Traffic | Material | Lump Sum |  | 8
3428-003 | Erosion Control | Material | Lump Sum |  | 8
3428-004 | Remove Existing Structures | Material | Lump Sum |  | 8
3428-005 | Clear & Grub | Material | Lump Sum |  | 8
3428-006 | Remove Existing Concrete | Material | Lump Sum |  | 8
3428-007 | Regular Excavation | Material | Cubic Yard |  | 8
3428-008 | Subsoil Excavation | Material | Cubic Yard |  | 8
3428-009 | Regular Embankment | Material | Cubic Yard |  | 8
3428-010 | Surcharge Embankment | Material | Cubic Yard |  | 8
3428-011 | Type B Stabilization | Material | Square Yard |  | 8
3428-012 | OBG 01 | Material | Square Yard |  | 8
3428-013 | OBG 02 | Material | Square Yard |  | 8
3428-014 | OBG 04 | Material | Square Yard |  | 8
3428-015 | OBG 09 | Material | Square Yard |  | 8
3428-016 | OBG 10 | Material | Square Yard |  | 8
3428-017 | OBG 11 | Material | Square Yard |  | 8
3428-018 | OBG 12 | Material | Square Yard |  | 8
3428-019 | OBG ALL (B12.5 ONLY) | Material | Square Yard |  | 8
3428-020 | Mill Exist Asphalt | Material | Square Yard |  | 8
3428-021 | Superpave Asphalt - TL B | Material |  |  | 8
3428-022 | Superpave Asphalt - TL C | Material |  |  | 8
3428-023 | Superpave Asphalt - TL D | Material |  |  | 8
3428-024 | Superpave Asphalt - TL D (Overbuild) | Material |  |  | 8
3428-025 | Superpave Asphalt - TL D (PG 76-22) | Material |  |  | 8
3428-026 | Friction Course, Inc Bit, FC-5 (PG 76-22) | Material |  |  | 8
3428-027 | Friction Course, TL-C, FC-12.5 (PG 76-22) | Material |  |  | 8
3428-028 | Friction Course, TL-D, FC-12.5 (PG 76-22) | Material |  |  | 8
3428-029 | Misc Asphalt | Material |  |  | 8
3428-030 | Conc Pavment - 10" | Material | Square Yard |  | 8
3428-031 | Bridge Aesthetics | Material | Lump Sum |  | 8
3428-032 | Conc Class II - Superstructure | Material | Cubic Yard |  | 8
3428-033 | Conc Class II - Approach Slabs | Material | Cubic Yard |  | 8
3428-034 | Conc Class IV - Ret Walls | Material | Cubic Yard |  | 8
3428-035 | Conc Class IV - Substructure | Material | Cubic Yard |  | 8
3428-036 | Bridge Deck Grooving | Material | Square Yard |  | 8
3428-037 | Class 5 Coating | Material | Square Feet |  | 8
3428-038 | Composite Neoprene Pads | Material | Cubic Feet |  | 8
3428-039 | Reinforcing Steel | Material | Lump Sum |  | 8
3428-040 | Prestressed Beam | Material | Linear Feet |  | 8
3428-041 | Test PC Pile 24" Sq | Material | Linear Feet |  | 8
3428-042 | Test Steel HP | Material | Linear Feet |  | 8
3428-043 | Production PC Pile 24" Sq | Material | Linear Feet |  | 8
3428-044 | Production Steel HP | Material | Linear Feet |  | 8
3428-045 | Deck Exp Joint | Material | Linear Feet |  | 8
3428-046 | Structural Steel | Material | Lump Sum |  | 8
3428-047 | Gravity Wall NS | Material | Cubic Yard |  | 8
3428-048 | CL I Endwalls | Material | Cubic Yard |  | 8
3428-049 | Drainage Structures | Material | Each |  | 8
3428-050 | 18" -30" Drainage Pipe | Material | Linear Feet |  | 8
3428-051 | 36" - 42" Drainage Pipe | Material | Linear Feet |  | 8
3428-052 | 48" - 54" Drainge Pipe | Material | Linear Feet |  | 8
3428-053 | EW / MES | Material | Each |  | 8
3428-054 | Utilitites | Material | Lump Sum |  | 8
3428-055 | Curb & Gutter | Material | Linear Feet |  | 8
3428-056 | Shoulder Gutter | Material | Linear Feet |  | 8
3428-057 | Traffic Separator | Material | Square Yard |  | 8
3428-058 | Slope Pavment | Material | Square Yard |  | 8
3428-059 | Median Barrier | Material | Linear Feet |  | 8
3428-060 | Bridge Rail | Material | Linear Feet |  | 8
3428-061 | Traffic Barrier w/Jct Slab | Material | Linear Feet |  | 8
3428-062 | Shoulder Barrier | Material | Linear Feet |  | 8
3428-063 | Sidewalk / Driveways | Material | Square Yard |  | 8
3428-064 | Rip Rap | Material |  |  | 8
3428-065 | Noise Wall | Material | Square Feet |  | 8
3428-066 | Guardrail | Material | Linear Feet |  | 8
3428-067 | Guardrail - Remove | Material | Linear Feet |  | 8
3428-068 | Guardrail - Reset | Material | Linear Feet |  | 8
3428-069 | Crash Cushion | Material | Each |  | 8
3428-070 | Rumble Strips | Material | Each |  | 8
3428-071 | MSE Wall | Material | Square Feet |  | 8
3428-072 | Fence Type B | Material | Linear Feet |  | 8
3428-073 | Fence Type B (Wall Mtd) | Material | Linear Feet |  | 8
3428-074 | Perf Turf | Material | Square Yard |  | 8
3428-075 | Signalization | Material | Lump Sum |  | 8
3428-076 | Lighting | Material | Lump Sum |  | 8
3428-077 | Signage | Material | Lump Sum |  | 8
3428-078 | Pavement Markings | Material | Lump Sum |  | 8
3428-079 | ITS | Material | Lump Sum |  | 8
3428-080 | Temp ITS | Material | Lump Sum |  | 8
3428-081 | Toll Gantry Complete | Material | Lump Sum |  | 8
3428-082 | FPL Distribution | Material | Lump Sum |  | 8
3428-083 | Preliminary Design Services | Material | Lump Sum |  | 8
3428-084 | Early Work Packages / Master Plans | Material | Lump Sum |  | 8
3428-085 | Geotech & Subsurface Investigation | Material | Lump Sum |  | 8
3428-086 | Survey / Permitting | Material | Lump Sum |  | 8
3428-087 | Roadway / MOT Plans (Phase 1) 90% | Material | Lump Sum |  | 8
3428-088 | Roadway / MOT Plans (Phase 2) 90% | Material | Lump Sum |  | 8
3428-089 | Drainage Plans (Phase 1) 90% | Material | Lump Sum |  | 8
3428-090 | Drainage Plans (Phase 2) 90% | Material | Lump Sum |  | 8
3428-091 | Bridge Plans / Wall / Aesthetic Plans 90% | Material | Lump Sum |  | 8
3428-092 | Signal, Signs, Lighting, ITS, Toll Gantry, Utility Plans 90% | Material | Lump Sum |  | 8
3428-093 | 100% Sign & Seal Plans | Material | Lump Sum |  | 8
3428-094 | Design Services During Construction | Material | Lump Sum |  | 8
3428-097 | Initial Contingeny | Material | Lump Sum |  | 8
3428-098 | DRB Meeting | Material | Lump Sum |  | 8
3428-099 | DRB Hearing | Material | Lump Sum |  | 8
3433 | 3433 - I440 | Nonlabor |  |  | 1
3433 - U2719 | 3433 - U2719 Revenue | Labor |  |  | 1
3433 - I4437 | 3433 - I4437 Revenue | Labor |  |  | 1
C00108424DB92.WO.02 | W.O-2 Scope Validation Item 08 Existing Cantilever Sign | Material | Lump Sum |  | 8
C00108424DB92.WO.03 | W.O-3 Scope Validation Item 05 Existing JB's and DI's | Material | Lump Sum |  | 8
I-10 O-ID | Other - Intermediate Design (ID) Submittal (3 Max/Week) | Nonlabor |  |  | 1
I-10 O-FD | Other- Final Design (FD) Submittal (2 Max /Week) | Nonlabor |  |  | 1
I-10 O-RFC | Other - Release for Construction (RFC) Submittal (2 Max/Week) | Nonlabor |  |  | 1
3417-3920 | Undercut Excavation | Material | Cubic Yard |  | 1
3433 - Revenue | 3433 - Revenue Resources | Labor |  |  | 1
9151 - 1 | Project Management Plan | Material |  |  | 8
9151 - 1a | Project Administration | Material | Unit |  | 8
9151 - 1b | Quality Manual Volume I (excluding the Construction Quality Management Plan) | Material | Unit |  | 8
9151 - 1c | Quality Manual Volume IV | Material | Unit |  | 8
3433 - Material | 3343 - Earthwork Material Resources | Nonlabor |  |  | 1
3433 - Exc | 3433 - Excavation | Material | Cubic Yard |  | 8
3433 - Emb | 3433 - Embankment | Material | Cubic Yard |  | 8
3420 - Revenue | 3420- SOV Items | Nonlabor |  |  | 1
3420-001 | P&P BOND and INSURANCE | Material | Lump Sum |  | 8
3420-002 | PRE-CONSTRUCTION OPERATING EXPENSES | Material |  |  | 8
3420-003 | CONSTRUCTION OPERATING EXPENSES | Material |  |  | 8
3420-004 | MOBILIZATION | Material |  |  | 8
3420-005 | EQUIPMENT PROCUREMENT | Material |  |  | 8
3420-006 | INFLUENT PUMPING STATION CONSTRUCTION | Material |  |  | 8
3420-007 | INFLUENT PUMPING STATION START-UP | Material |  |  | 8
3420-008 | BLOWER BUILDING CONSTRUCTION | Material |  |  | 8
3420-009 | BLOWER BUILDING START-UP | Material |  |  | 8
3420-010 | AERATION BASIN CONSTRUCTION | Material |  |  | 8
3420-011 | AERATION BASIN START-UP | Material |  |  | 8
3420-012 | DIGESTER AREA CONSTRUCTION | Material |  |  | 8
3420-013 | DIGESTER AREA START-UP | Material |  |  | 8
3420-014 | DEMOBILIZATION | Material |  |  | 8
I-10-COST | LUMP COST | Nonlabor |  |  | 0
9151 Revenue | 9151 - I-10 Revenue | Nonlabor |  |  | 1
9151 - 1d | Environmental Management Plan | Material | Unit |  | 8
9151 - 1e | Health, Safety, and Environmental Work Plan | Material | Unit |  | 8
9151 - 2 | Site Documentation | Material | Unit |  | 8
9151 - 3 | Segment Limits Map and Submittal Schedule | Material | Unit |  | 8
9151 - 4 | Transportation Management Plan (TMP) | Material | Unit |  | 8
9151 - 5 | Maintenance Work Plan | Material | Unit |  | 8
9151 - 6 | Crisis Communications Plan | Material | Unit |  | 8
9151 - 7 | ITS Inventory Assessment Report | Material | Unit |  | 8
9151 - 8 | Bat Habitat Management Plan | Material | Unit |  | 8
9151 - 9 | Nesting Bird Management Plan | Material | Unit |  | 8
9151 - 10 | Burrowing Owl Management Plan | Material | Unit |  | 8
9151 - 11 | Draft Geotechnical Execution Plan | Material | Unit |  | 8
9151 - 12 | NTP1 Mobilization | Material | Unit |  | 8
9151 - B | Professional Services | Material |  |  | 8
9151 - B1 | Community Outreach | Material | Unit |  | 8
9151 - B2 | Design Survey | Material | Unit |  | 8
9151 - B3 | Geotechnical Engineering/Site Condition Investigation | Material | Unit |  | 8
9151 - B4 | Design (Including TSP Coordination, Landscaping and Aesthetics, SHOPP Pavement Rehabilitation, and SHOPP Safety Lighting Design) | Material | Unit |  | 8
9151 - B5 | Environmental Permitting/Governmental Approval Activities | Material | Unit |  | 8
9151 - B6 | Utility Location, Survey, Design and Coordination | Material | Unit |  | 8
9151 - B7 | Project Vehicles | Material | Unit |  | 8
9151 - C | Construction | Material |  |  | 8
9151 - C1 | Construction Management | Material |  |  | 8
9151 - C1a | Construction Management | Material | Unit |  | 8
9151 - C1b | Co-Located Office | Material | Unit |  | 8
9151 - C2 | Mobilization | Material |  |  | 8
9151 - C2a | NTP2 Mobilization | Material | Unit |  | 8
9151 - C2b | NTP2 SHOPP Pavement Rehabilitation Work Mobilization | Material | Unit |  | 8
9151 - C3 | Bond Premiums | Material |  |  | 8
9151 - C3a | Bond Premium for NTP1 Work | Material | Unit |  | 8
9151 - C3b | Bond Premium for NTP2 Work | Material | Unit |  | 8
9151 - C4 | Insurance Premiums | Material |  |  | 8
9151 - C4a | Insurance Premiums for NTP1 Work | Material | Unit |  | 8
9151 - C4b | Insurance Premiums for NTP2 Work | Material | Unit |  | 8
9151 - C5 | Water Pollution Control (not including SWPPP BMP Maintenance) | Material | Unit |  | 8
9151 - C6 | SWPPP BMP Maintenance Allowance | Material | Unit |  | 8
9151 - C7 | Maintenance of Traffic | Material | Unit |  | 8
9151 - C8 | Earthwork | Material | Unit |  | 8
9151 - C9 | Roadway Structural Section | Material | Unit |  | 8
9151 - C10 | Pavements (not including Concrete Panel Replacement) | Material | Unit |  | 8
9151 - C11 | Concrete Panel Replacement and Repair | Material |  |  | 8
9151 - C11a | Concrete Panel Replacement (5,000 CY) | Material | Unit |  | 8
9151 - C11b | Spall Repair (700 EA) | Material | Unit |  | 8
9151 - C11c | Joint Repair (13,500 LF) | Material | Unit |  | 8
9151 - C12 | Structures | Material |  |  | 8
9151 - C12a | Bridges | Material | Unit |  | 8
9151 - C12b | Retaining Walls | Material | Unit |  | 8
9151 - C12c | Sound Walls | Material | Unit |  | 8
9151 - C13 | Drainage | Material | Unit |  | 8
9151 - C14 | ITS/Lighting/Electrical | Material | Unit |  | 8
9151 - C15 | Signing and Striping | Material | Unit |  | 8
9151 - C16 | Environmental Compliance | Material | Unit |  | 8
9151 - C17 | Utility Coordination, Protection, Adjustment, and Relocations | Material | Unit |  | 8
9151 - C18 | DB Civil TCS Infrastructure | Material | Unit |  | 8
9151 - C19 | Express Lane Closures | Material | Unit |  | 8
9151 - C20 | Plant Establishment (Section 14.3.8) | Material | Unit |  | 8
9151 - C21 | Aesthetics and Landscaping | Material | Unit |  | 8
9151 - C22 | Maintenance During Construction | Material | Unit |  | 8
9151 - C23 | As-Built Documents (shall equal 0.25% of Contract Price) | Material | Unit |  | 8
29479 | I-10 DB Project | Labor |  |  | 1
C00108424DB92.WO.04 | W.O-4 NS Signal Pole and Foundation | Material | Lump Sum |  | 8
3347 - Crew-1 | 3347 - Crew Resources | Nonlabor |  |  | 1
ST-WALL-FND | Wall Foundation Crew | Labor |  | Wall Crew | 1
3347-1 | MD 5 at Brandywine Road | Nonlabor |  |  | 1
3347-2 | MD 5 at Brandywine Road | Nonlabor |  |  | 1
3347-4 | MD 5 at Brandywine Road | Nonlabor |  |  | 1
9156 | I-540 JV | Nonlabor |  |  | 1
9161 | C-43 | Nonlabor |  |  | 1
9156 Revenue | 9156 Revenue | Labor |  |  | 1
3347-3 | MD 5 at Brandywine Road | Nonlabor |  |  | 1
3422 - CO | Change Order - Pay Items | Nonlabor |  |  | 1
3422 - 4028 | CO#2 - Geotechnical Engineer | Material | Day |  | 1
3422 - 4027 | CO#2 - Removal of Existing Wing Wall 2 Foundation | Material | Cubic Yard |  | 1
3422 - 4026 | CO#2 - Subfound Conc | Material | Cubic Yard |  | 1
I-10-SHOPP | SHOPP Cost | Material |  |  | 0
3417- | Trainee Hours | Material | Hour |  | 0
3418-01 | Mobilization | Material | Lump Sum |  | 1
3329-637 | MS#2-Incentive I-85 NB&SB Med Shift 484+40 - Existing I-2511BA | Material | Lump Sum |  | 8
3329-638 | MS#6-Incentive NC152 Traffic on Str#4&5, Temp Y21RPC w/LPD Left | Material | Lump Sum |  | 8
3329-639 | SA28 - Modified Valley Curb | Material | Lump Sum |  | 8
3329-640 | SA 29 - CMRB | Material | Lump Sum |  | 8
3329-641 | SA30 - Food Lion | Material | Lump Sum |  | 8
3329-642 | SA31 - OH Signs | Material | Lump Sum |  | 8
9156-01 | DESIGN | Material | Unit |  | 8
9156-02 | MOBILIZATION | Material | Lump Sum |  | 1
9156-03 | Liability Insurance | Material | Lump Sum |  | 1
9156-04 | Payment & Performance Bonds | Material | Lump Sum |  | 1
9156-06 | PROJECT MANAGEMENT (Design Phase) | Material | Month |  | 1
9156-07 | PROJECT MANAGEMENT (Construction Phase) | Material | Month |  | 1
9156-08 | RAILROAD REVIEW | Material | Lump Sum |  | 1
9156-09 | RAILROAD FLAGGING | Material | Day |  | 1
9156-10 | MAINTENANCE OF TRAFFIC | Material | Unit |  | 1
9156-11 | WORK ZONE SIGNS | Material | Square Feet |  | 1
9156-12 | MOT Devices | Material | Month |  | 1
9156-13 | TEMPORARY CRASH CUSHIONS | Material | Each |  | 1
9156-14 | RELOCATE CRASH CUSHIONS | Material | Each |  | 1
9156-15 | PORTABLE CONCRETE BARRIER | Material | Linear Feet |  | 1
9156-16 | RELOCATE PORTABLE CONCRETE BARRIER | Material | Linear Feet |  | 1
9156-17 | TEMP RAISED PAVEMENT MARKERS | Material | Each |  | 1
9156-18 | TEMPORARY PAVEMENT MARKINGS | Material | Linear Feet |  | 1
9156-19 | WORK ZONE TRAFFIC PATTERN MASKING | Material | Square Feet |  | 1
9156-20 | PAVEMENT MARKING TAPE | Material | Linear Feet |  | 1
9156-21 | REMOVAL OF PAVT MRKNG LINES | Material | Linear Feet |  | 1
9156-22 | Clearing and Grubbing | Material |  |  | 1
9156-23 | DEMO BUILDINGS | Material | Square Feet |  | 1
9156-24 | Removal of Bridges | Material | Each |  | 1
9156-25 | Asphalt Removal | Material | Square Yard |  | 1
9156-26 | Concrete Curb Removal | Material | Linear Feet |  | 1
9156-27 | EXIST CONC PAVMENT REMOVAL | Material | Cubic Yard |  | 1
9156-28 | EROSION CONTROL MAINTENANCE | Material | Unit |  | 1
9156-29 | CONSTRUCTION ENTRANCE | Material | Each |  | 1
9156-30 | SILT FENCE | Material | Linear Feet |  | 1
9156-31 | EROSION CONTROL STONE | Material |  |  | 1
9156-32 | EROSION CONTROL BASINS | Material | Cubic Yard |  | 1
9156-33 | HAZARDOUS SPILLS BASINS | Material | Each |  | 1
9156-34 | TEMPORARY SLOPE DRAINS | Material | Linear Feet |  | 1
9156-35 | SAFETY FENCE | Material | Linear Feet |  | 1
9156-36 | MATTING FOR EROSION CONTROL | Material | Square Yard |  | 1
9156-37 | COIR FIBER MAT | Material | Square Yard |  | 1
9156-38 | COIR FIBER WATTLE | Material | Linear Feet |  | 1
9156-39 | 1/4" HARDWARE CLOTH | Material | Linear Feet |  | 1
9156-40 | 12" WATTLE BARRIER | Material | Linear Feet |  | 1
9156-41 | POLYACRYLAMIDE (PAM) | Material | LB |  | 1
9156-42 | COIR FIBER BAFFLE | Material | Linear Feet |  | 1
9156-43 | DEMUCK PONDS | Material | Cubic Yard |  | 1
9156-44 | PERMANENT SEEDING AND MULCHING | Material |  |  | 1
9156-45 | REFORESTRATION | Material |  |  | 1
9156-46 | ENERGY DISSAPATORS | Material | Each |  | 1
9156-47 | Rip Rap | Material |  |  | 1
9156-48 | DRAINAGE STRUCTURE REMOVALS | Material | Each |  | 1
9156-49 | PIPE REMOVAL/FLOW FILL | Material | Linear Feet |  | 1
9156-50 | TIE IN PROP DRAINAGE TO EXISTING BOX | Material | Each |  | 1
9156-51 | TEMP PIPE | Material | Linear Feet |  | 1
9156-52 | 18" RC PIPE CULV | Material | Linear Feet |  | 1
9156-53 | 24" RCP Pipe Culv | Material | Linear Feet |  | 1
9156-54 | 30" RCP CULV | Material | Linear Feet |  | 1
9156-55 | 36" RCP CULV | Material | Linear Feet |  | 1
9156-56 | 42" RC PIPE CULV | Material | Linear Feet |  | 1
9156-57 | 48" RC PIPE CULV | Material | Linear Feet |  | 1
9156-58 | 54" RC PIPE CULV | Material | Linear Feet |  | 1
9156-59 | 60" RC PIPE CULV | Material | Linear Feet |  | 1
9156-60 | 15" RCP CULV | Material | Linear Feet |  | 1
9156-61 | 15" CS PIPE CULV | Material | Linear Feet |  | 1
9156-62 | 24" CS PIPE CULV | Material | Linear Feet |  | 1
9156-63 | 30" CS PIPE CULV | Material | Linear Feet |  | 1
9156-64 | JACK AND BORE | Material | Linear Feet |  | 1
9156-65 | ENDWALLS | Material | Each |  | 1
9156-66 | PIPE COLLARS | Material | Each |  | 1
9156-67 | MASONRY DRAINAGE STRUCTURES | Material | Each |  | 1
9156-68 | Frame & Grate | Material | Each |  | 1
9156-69 | Aprons | Material | Each |  | 1
9156-70 | SHOULDER DRAINS | Material | Linear Feet |  | 1
9156-71 | Underdrain | Material | Linear Feet |  | 1
9156-72 | DIVERSION FOR CULVERTS | Material | Each |  | 1
9156-73 | EXCAVATE FOR CULVERT FOOTER | Material | Cubic Yard |  | 1
9156-74 | FOUNDATION MATERIAL FOR CULVERT | Material |  |  | 1
9156-75 | POUR CULVERT | Material | Cubic Yard |  | 1
9156-76 | UNCLASS Excavation | Material | Cubic Yard |  | 1
9156-77 | EMBANKMENT | Material | Cubic Yard |  | 1
9156-78 | UNDERCUT EXCAVATION | Material | Cubic Yard |  | 1
9156-79 | Backup Shoulders | Material | Cubic Yard |  | 1
9156-80 | FINE GRADING | Material | Square Yard |  | 1
9156-81 | CEMENT STABILIZATION | Material | Square Yard |  | 1
9156-82 | ABC | Material |  |  | 1
9156-83 | DRIVEWAYS | Material | Square Yard |  | 1
9156-84 | ASPH INTERMEDIATE COURSE, TYPE I19.0C | Material |  |  | 1
9156-85 | ASPH SURFACE COURSE, TYPE S9.5B | Material |  |  | 1
9156-86 | ASPHALT CONC SURFACE COURSE, TYPE S9.5C | Material |  |  | 1
9156-87 | ASPHALT WEDGING | Material |  |  | 1
9156-88 | 9" RCC PAVING | Material | Square Yard |  | 1
9156-89 | CONCRETE PAVING - JOINTED 12" | Material | Cubic Yard |  | 1
9156-90 | SAW AND SEAL CONCRETE PAVING | Material | Square Yard |  | 1
9156-91 | Diamond Grind Concrete | Material | Square Yard |  | 1
9156-92 | FOUNDATION EXCAVATION ( INTERIOR BENTS ) | Material | Cubic Yard |  | 1
9156-93 | Trestle Installation | Material | Square Feet |  | 1
9156-94 | Trestle Removal | Material | Square Feet |  | 1
9156-95 | PIPE PILES | Material | Linear Feet |  | 1
9156-96 | HPILE F&I | Material | Linear Feet |  | 1
9156-97 | DRILLED SHAFTS | Material | Linear Feet |  | 1
9156-98 | SIP | Material | Square Feet |  | 1
9156-99 | Overhangs | Material | Linear Feet |  | 1
9156-100 | REINFORCING STEEL (BRIDGE) | Material | LB |  | 1
9156-101 | CLASS A CONCRETE (BRIDGE- SUB) | Material | Cubic Yard |  | 1
9156-102 | CLASS AA CONCRETE (Sidewalk and Median Concrete) | Material | Cubic Yard |  | 1
9156-103 | CLASS AA CONCRETE (RC DECK SLAB) | Material | Cubic Yard |  | 1
9156-104 | Approach Slabs | Material | Cubic Yard |  | 1
9156-105 | ELASTOMERIC BEARINGS | Material | Each |  | 1
9156-106 | PRESTRESSED CONC GIRDERS 36-45 | Material | Each |  | 1
9156-107 | PRESTRESSED CONC GIRDERS 54-63 | Material | Each |  | 1
9156-108 | PRESTRESSED CONC GIRDERS 72-78 | Material | Each |  | 1
9156-109 | STEEL DIAPHRAGMS | Material | Each |  | 1
9156-110 | Reinforced Approach Fill | Material |  |  | 1
9156-111 | EXPANSION JOINT SEALS | Material | Linear Feet |  | 1
9156-112 | GROOVING BRIDGE DECKS | Material | Square Feet |  | 1
9156-113 | GRAVITY RETAINING WALLS (COPING) | Material | Linear Feet |  | 1
9156-114 | GRAVITY RETAINING WALLS | Material | Square Feet |  | 1
9156-115 | Soundwall Posts | Material | Each |  | 1
9156-116 | SOUND WALLS - Panels | Material | Square Feet |  | 1
9156-117 | Sound Walls On Structures | Material | Square Feet |  | 1
9156-118 | Anti-Graffiti Coating | Material | Square Feet |  | 1
9156-119 | Structure / Barrier Painting | Material | Square Feet |  | 1
9156-120 | MSE WALLS | Material | Square Feet |  | 1
9156-121 | MSE Walls - Place Brick face | Material | Square Feet |  | 1
9156-122 | MSE Walls - Coping | Material | Linear Feet |  | 1
9156-123 | MSE MOMENT SLAB | Material | Linear Feet |  | 1
9156-124 | MSE BARRIER | Material | Linear Feet |  | 1
9156-125 | SINGLE FACED BARRIER (PRECAST) | Material | Linear Feet |  | 1
9156-126 | CONC PARAPETS | Material | Linear Feet |  | 1
9156-127 | CONCRETE CURB & GUTTER | Material | Linear Feet |  | 1
9156-128 | SHOULDER BERM GUTTER | Material | Linear Feet |  | 1
9156-129 | Paved Ditches | Material | Cubic Yard |  | 1
9156-130 | CONCRETE EXPRESSWAY GUTTER | Material | Linear Feet |  | 1
9156-131 | 4" CONCRETE SIDEWALK AND MULTI-USE PATHWAY | Material | Square Yard |  | 1
9156-132 | MONOLITHIC CONCRETE MEDIAN | Material | Square Yard |  | 1
9156-133 | THERMO SYMBOL/CHARACTER | Material | Each |  | 1
9156-134 | CLD APPL PVMT MARK | Material | Linear Feet |  | 1
9156-135 | POLYUREA | Material | Linear Feet |  | 1
9156-136 | THERMO PAVE MARK LINES | Material | Linear Feet |  | 1
9156-137 | BLACK EPOXY CONTRAST LINES | Material | Linear Feet |  | 1
9156-138 | SNOWPLOWABLE PAVEMENT MARKERS | Material | Each |  | 1
9156-139 | MILLED RUMBLE STRIPS | Material | Linear Feet |  | 1
9156-140 | Guardrail | Material | Linear Feet |  | 1
9156-141 | CABLE GUIDERAIL | Material | Linear Feet |  | 1
9156-142 | Temporary Guardrail | Material | Linear Feet |  | 1
9156-143 | TWO BAR METAL RAIL | Material | Linear Feet |  | 1
9156-144 | Woven Wire Fence | Material | Linear Feet |  | 1
9156-145 | BRIDGE FENCING | Material | Linear Feet |  | 1
9156-146 | OVERHEAD SIGN FOUNDATIONS | Material | Each |  | 1
9156-147 | CONCRETE COLUMN - OVERHEAD SIGNS | Material | Each |  | 1
9156-148 | PEDISTAL SIGN STRUCTURE | Material | Each |  | 1
9156-149 | CANTILEVER SIGNS STRUCTURE | Material | Each |  | 1
9156-150 | GANTRY SIGNS STRUCTURE | Material | Each |  | 1
9156-151 | OVERHEAD MOUNTED SIGNS | Material | Square Feet |  | 1
9156-152 | GROUND MOUNTED SIGNS | Material | Square Feet |  | 1
9156-153 | UNDERBRIDGE LIGHTING | Material | Each |  | 1
9156-154 | LIGHT POLE FOUNDATION 45' | Material | Each |  | 1
9156-155 | LIGHT POLE FOUNDATION 60' | Material | Each |  | 1
9156-156 | LIGHT POLE FOUNDATION 80' | Material | Each |  | 1
9156-157 | LIGHT POLE FOUNDATION 100' | Material | Each |  | 1
9156-158 | LIGHT POLE STRUCTURE & LUMINARES 45' | Material | Each |  | 1
9156-159 | LIGHT POLE STRUCTURE & LUMINARES 60' | Material | Each |  | 1
9156-160 | LIGHT POLE STRUCTURE & LUMINARES 80' | Material | Each |  | 1
9156-161 | LIGHT POLE STRUCTURE & LUMINARES 100' | Material | Each |  | 1
9156-162 | SIGNAL POLES | Material | Each |  | 1
9156-163 | CONDUIT FOR SIGNALS | Material | Linear Feet |  | 1
9156-164 | CABINETS FOR SIGNALS (HEADS/METERS/LOOPS/ECT...) | Material | Each |  | 1
9156-165 | ITS/AET - VEHICLE DETECTOR FOUNDATION | Material | Each |  | 1
9156-166 | ITS/AET - VEHICLE DETECTOR POLE AND EQUIPMENT | Material | Each |  | 1
9156-167 | ITS/AET - TRUNK LINE | Material | Linear Feet |  | 1
9156-168 | ITS/AET - TOLL VAULT & EQUIPMENT | Material | Each |  | 1
9156-169 | ITS/AET - CCTV FOUNDATION | Material | Each |  | 1
9156-170 | ITS/AET - CCTV POLE AND EQUIPMENT | Material | Each |  | 1
9156-171 | ITS/AET - TOLL VAULT BUILDING | Material | Each |  | 1
9156-172 | ITS/AET - TOLL AREA AESTETHICS SCREEN WALL | Material | Each |  | 1
9156-173 | ITS/AET - CONCRETE SLAB FOR TOLL VAULT AREA | Material | Square Feet |  | 1
9156-174 | ITS/AET - OVERHEAD TOLL GANTRY FOUNDATION | Material | Each |  | 1
9156-175 | ITS/AET - TOLL GANTRY COLUMN | Material | Each |  | 1
9156-176 | ITS/AET - TOLL GANTRY STRUCTURE (INCLUDES DMS AND EQUIPMENT) | Material | Each |  | 1
9156-177 | WATERLINE | Material | Linear Feet |  | 1
3434-1 | Mobilization | Material | Lump Sum |  | 8
3434-2 | Construction Surveying | Material | Lump Sum |  | 8
3434-3 | Field Office | Material | Lump Sum |  | 8
3434-4 | Design Fee | Material | Lump Sum |  | 8
9156-05 | Punch Work | Material | Unit |  | 1
EW-MASS | Mass Earthmoving Crew | Labor |  | Earthwork Crew | 1
EW-SML | Light Cut/Fill Earthwork Crew | Labor |  | Earthwork Crew | 1
EW-BUP | Pavement Backup Crew | Labor |  |  | 1
CP-RCC | Roller Compacted Concrete Crew | Labor |  |  | 1
SUB-RCC | Sub - Roller Compacted Concrete Crew | Labor |  |  | 1
3434 | 3434 - I-40 / I-77 Interchange - Statesville | Nonlabor |  |  | 1
3418 | 3418 - I-85 Widening SCDOT Cherokee Co | Nonlabor |  |  | 1
3434-5 | Bonds, Insurances, Success Fee, D/B Team Setup | Material | Lump Sum |  | 8
3434-6 | Generic Miscellaneous Item Video Existing Drainage Pipe | Material | Linear Feet |  | 8
3434-7 | Generic Miscellaneous Item Building Demolition | Material | Square Feet |  | 8
3434-8 | Clearing & Grubbing 49 Acres | Material | Lump Sum |  | 8
3434-9 | Unclassified Excavation | Material | Cubic Yard |  | 8
3434-10 | Type I Standard Approach Fill Station ********** | Material | Lump Sum |  | 8
3434-11 | Type III Reinforced Approach Fill, Station ******* | Material | Lump Sum |  | 8
3434-12 | Borrow Excavation | Material | Cubic Yard |  | 8
3434-13 | Embankment Settlement Gauges | Material | Each |  | 8
3434-14 | Drainage Ditch Excavation | Material | Cubic Yard |  | 8
3434-15 | Removal of Existing Asphalt Pavement | Material | Square Yard |  | 8
3434-16 | Removal of Existing Concrete Pavement | Material | Square Yard |  | 8
3434-17 | Removal of Existing Concrete Curb | Material | Square Yard |  | 8
3434-18 | Removal of Existing Sidewalk | Material | Square Yard |  | 8
3434-19 | Removal of Existing Shoulder Berm Gutter | Material | Square Yard |  | 8
3434-20 | Removal of Existing Barrier Wall | Material | Square Yard |  | 8
3434-21 | Proof Rolling | Material | Hour |  | 8
3434-22 | Temporary Shoring | Material | Square Feet |  | 8
3434-23 | Unclassified Excavation for Temporary Pavement | Material | Cubic Yard |  | 8
3434-24 | Foundation Conditioning Material, Minor Structures | Material |  |  | 8
3434-25 | Foundation Conditioning Geotextile | Material | Square Yard |  | 8
3434-26 | 15" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-27 | 18" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-28 | 24" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-29 | 30" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-30 | 36" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-31 | 48" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-32 | 54" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-33 | 60" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-34 | 66" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-35 | 72" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-36 | 15" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-37 | 18" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-38 | 24" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-39 | 30" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-40 | 36" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-41 | 42" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-42 | 48" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3434-43 | 15" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3434-44 | 18" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3434-45 | 24" CS Pipe Culverts, 0.064" Thick | Material | Linear Feet |  | 8
3434-46 | 30" CS Pipe Culverts, 0.079" Thick | Material | Linear Feet |  | 8
3434-47 | 36" CS Pipe Culverts, 0.079" Thick | Material | Linear Feet |  | 8
3434-48 | 42" CS Pipe Culverts, 0.079" Thick | Material | Linear Feet |  | 8
3434-49 | 48" CS Pipe Culverts, 0.079" Thick | Material | Linear Feet |  | 8
3434-50 | 18" Welded Steel Pipe, ****" Thick, Grade B in Soil | Material | Linear Feet |  | 8
3434-51 | 30" Welded Steel Pipe, ****" Thick, Grade B in Soil | Material | Linear Feet |  | 8
3434-52 | 42" Welded Steel Pipe, ****" Thick, Grade B in Soil | Material | Linear Feet |  | 8
3434-53 | 60" Welded Steel Pipe, ****" Thick, Grade B in Soil | Material | Linear Feet |  | 8
3434-54 | Pipe Removal | Material | Linear Feet |  | 8
3434-55 | Fine Grading | Material | Lump Sum |  | 8
3434-56 | Geotextile for Pavement Stabilization | Material | Square Yard |  | 8
3434-57 | Aggregate Base Course | Material |  |  | 8
3434-58 | 12" Type 1 Aggregate Subgrade | Material |  |  | 8
3434-59 | Aggregate Base Course for Temporary Pavement | Material |  |  | 8
3434-60 | Aggregate for Cement Treated Base Course | Material |  |  | 8
3434-61 | Portland Cement for Cement Treated Base Course | Material |  |  | 8
3434-62 | Incidental Stone Base | Material |  |  | 8
3434-63 | Milling for Temp Pavement 10" Depth | Material | Square Yard |  | 8
3434-64 | Milling for Temp Pavemet Removal 0 - 6" Depth | Material | Square Yard |  | 8
3434-65 | Asphalt Conc Base Course, Type B25.0C | Material |  |  | 8
3434-66 | Asphalt Conc Base Course, Type B25.0C, Temporary | Material |  |  | 8
3434-67 | Asphalt Conc Intermediate Course, Type I19.0C | Material |  |  | 8
3434-68 | Asphalt Conc Intermediate Course, Type I19.0C, Wedging | Material |  |  | 8
3434-69 | Asphalt Conc Intermediate Course, Type I19.0C, Temporary | Material |  |  | 8
3434-70 | Asphalt Conc Surface Course, Type S9.5B | Material |  |  | 8
3434-71 | Asphalt Conc Surface Course, Type S9.5B, Wedging | Material |  |  | 8
3434-72 | Asphalt Conc Surface Course, Type S9.5C, Temporary | Material |  |  | 8
3434-73 | Asphalt Conc Surface Course, Type S9.5D | Material |  |  | 8
3434-74 | Asphalt Conc Surface Course, Type S9.5D, Wedging | Material |  |  | 8
3434-75 | Asphalt Conc Surface Course, Type SF9.5B | Material |  |  | 8
3434-76 | Asphalt Conc Surface Course, Type SF9.5B, Driveways | Material |  |  | 8
3434-77 | Open-Graded Asphalt Friction Course, Type FC-1 Modified | Material |  |  | 8
3434-78 | Milled Rumble Strips - Asphalt | Material | Linear Feet |  | 8
3434-79 | 14" Port Cem Conc Pavement, through Lanes (with Dowels) | Material | Square Yard |  | 8
3434-80 | 11 1/2" Port Cem Conc Pavement, Ramps (with Dowels) | Material | Square Yard |  | 8
3434-81 | Diamond Grind Concrete Pavement with Slurry Disposal | Material | Square Yard |  | 8
3434-82 | Concrete Shoulders adjacent to 14" Pavement (w/o dowels) | Material | Square Yard |  | 8
3434-83 | Concrete Shoulders adjacent to 11 1/2" Pavement (w/o dowels) | Material | Square Yard |  | 8
3434-84 | Nonwoven Geotextile Interlayer | Material | Square Yard |  | 8
3434-85 | Field Laboratory Rental, Port Cem Conc Pavement | Material | Lump Sum |  | 8
3434-86 | Milled Rumble Strips - Concrete Shoulders | Material | Linear Feet |  | 8
3434-87 | Right-of-Way Markers | Material | Each |  | 8
3434-88 | Shoulder Drain | Material | Linear Feet |  | 8
3434-89 | 4" Shoulder Drain Pipe | Material | Linear Feet |  | 8
3434-90 | 4" Outlet Pipe for Shoulder Drains | Material | Linear Feet |  | 8
3434-91 | Concrete Pad for Shoulder Drain Pipe Outlet | Material | Each |  | 8
3434-92 | Endwalls (36" - 42") | Material | Cubic Yard |  | 8
3434-93 | Endwalls (48" - 54") | Material | Cubic Yard |  | 8
3434-94 | Endwalls (66" - 72") | Material | Cubic Yard |  | 8
3434-95 | Pipe Collars | Material | Cubic Yard |  | 8
3434-96 | Flowable Fill | Material | Cubic Yard |  | 8
3434-97 | Masonry Drainage Structures | Material | Each |  | 8
3434-98 | Masonry Drainage Structures - Traffic Bearing | Material | Each |  | 8
3434-99 | Frame with Two Grates, STD 840.04 | Material | Each |  | 8
3434-100 | Frame with Two Grates, STD 840.16 | Material | Each |  | 8
3434-101 | Frame with Two Grates, STD 840.20 | Material | Each |  | 8
3434-102 | Frame with Three Grates, STD 840.20 | Material | Each |  | 8
3434-103 | Frame with Grate & Hood, STD 840.03, Type E | Material | Each |  | 8
3434-104 | Frame with Grate & Hood, STD 840.03, Type F | Material | Each |  | 8
3434-105 | Frame with Grate & Hood, STD 840.03, Type G | Material | Each |  | 8
3434-106 | Frame with Cover, STD 840.54 | Material | Each |  | 8
3434-107 | **" Sluice Gate | Material | Each |  | 8
3434-108 | Generic Drainage Item - Open Throat Catch Basin Std 840.04 | Material | Each |  | 8
3434-109 | Generic Drainage Item - Tie in to Existing Box | Material | Each |  | 8
3434-110 | Generic Drainage Item - JB/MH Std 840.31 | Material | Each |  | 8
3434-111 | Generic Drainage Item - Spring Box | Material | Each |  | 8
3434-112 | Generic Drainage Item - Special Catch Basin | Material | Each |  | 8
3434-113 | Generic Drainage Item - Berm Ditch Outlets | Material | Each |  | 8
3434-114 | 2'-6" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3434-115 | Shoulder Berm Gutter | Material | Linear Feet |  | 8
3434-116 | Concrete Expressway Gutter | Material | Linear Feet |  | 8
3434-117 | 4" Concrete Sidewalk | Material | Square Feet |  | 8
3434-118 | Concrete Curb Ramps | Material | Each |  | 8
3434-119 | 5" Monolithic Concrete Islands (Keyed In) | Material | Square Feet |  | 8
3434-120 | Concrete Barrier, Type T | Material | Linear Feet |  | 8
3434-121 | Concrete Barrier, Type T1 | Material | Linear Feet |  | 8
3434-122 | Concrete Barrier, Type T2 | Material | Linear Feet |  | 8
3434-123 | Concrete Barrier Pier Protection | Material | Linear Feet |  | 8
3434-124 | Concrete Barrier Transition Section | Material | Each |  | 8
3434-125 | Precast Reinforced Concrete Barrier, Single Faced | Material | Linear Feet |  | 8
3434-126 | Reinforced Concrete Barrier, Single Faced | Material | Linear Feet |  | 8
3434-127 | Adjustment of Catch Basins Concrete Transition | Material | Each |  | 8
3434-128 | Adjustment of Drop Inlets | Material | Each |  | 8
3434-129 | Adjustment of Manholes | Material | Each |  | 8
3434-130 | Convert Existing Drop Inlet To Junction Box with Manhole | Material | Each |  | 8
3434-131 | Convert Existing Junction Box to Drop Inlet | Material | Each |  | 8
3434-132 | Impact Attenuator Units, Type TL-3 | Material | Each |  | 8
3434-133 | Steel Beam Guardrail | Material | Linear Feet |  | 8
3434-134 | Additional Guardrail Posts | Material | Each |  | 8
3434-135 | Guardrail End Units, Type CAT-1 | Material | Each |  | 8
3434-136 | Guardrail End Units, Type TL-3 | Material | Each |  | 8
3434-137 | Guardrail Anchor Units, Type B-77 | Material | Each |  | 8
3434-138 | Remove Existing Guardrail | Material | Linear Feet |  | 8
3434-139 | Remove Existing Guiderail | Material | Linear Feet |  | 8
3434-140 | Temporary Steel Beam Guardrail | Material | Linear Feet |  | 8
3434-141 | Reset Existing Guardrail | Material | Linear Feet |  | 8
3434-142 | Remove Temporary Guardrail | Material | Linear Feet |  | 8
3434-143 | Cable Guiderail | Material | Linear Feet |  | 8
3434-144 | Cable Guiderail Anchor Units | Material | Each |  | 8
3434-145 | Chain Link Fence, 48" Fabric | Material | Linear Feet |  | 8
3434-146 | Metal Line Posts for 48" Chainlink Fence | Material | Each |  | 8
3434-147 | Metal Terminal Posts for 48" Chain Link Fence | Material | Each |  | 8
3434-148 | Rip Rap, Class I | Material |  |  | 8
3434-149 | Rip Rap, Class II | Material |  |  | 8
3434-150 | Rip Rap, Class B | Material |  |  | 8
3434-151 | Geotextile for Drainage | Material | Square Yard |  | 8
3434-152 | Contractor Furnished, Type D Sign | Material | Square Feet |  | 8
3434-153 | Contractor Furnished, Type E Sign | Material | Square Feet |  | 8
3434-154 | Contractor Furnished, Type F Sign | Material | Square Feet |  | 8
3434-155 | Contractor Furnished, Type A Sign | Material | Square Feet |  | 8
3434-156 | Contractor Furnished, Type B Sign | Material | Square Feet |  | 8
3434-157 | Contractor Furnished, Milemarker Sign | Material | Square Feet |  | 8
3434-158 | Reinforced Concrete Sign Foundations | Material | Cubic Yard |  | 8
3434-159 | Overhead Footing | Material | Cubic Yard |  | 8
3434-160 | Supports, Breakaway Steel Beam | Material | LB |  | 8
3434-161 | Supports, Simple Steel Beam | Material | LB |  | 8
3434-162 | Supports, 3-LB Steel U-Channel | Material | Linear Feet |  | 8
3434-163 | Support, Barrier (Large) | Material | Each |  | 8
3434-164 | Supports, Overhead Sign Structure at Sta****** | Material | Lump Sum |  | 8
3434-165 | Sign Erection, Type D | Material | Each |  | 8
3434-166 | Sign Erection, Type E | Material | Each |  | 8
3434-167 | Sign Erection, Type F | Material | Each |  | 8
3434-168 | Sign Erection, Type A (Overhead) | Material | Each |  | 8
3434-169 | Sign Erection, Type B (Overhead) | Material | Each |  | 8
3434-170 | Sign Erection, Type A (Ground Mounted) | Material | Each |  | 8
3434-171 | Sign Erection, Type B (Ground Mounted) | Material | Each |  | 8
3434-172 | Sign Erection, Milemarkers | Material | Each |  | 8
3434-173 | Sign Erection, Relocate Type A (Ground Mounted) | Material | Each |  | 8
3434-174 | Sign Erection, Relocate Type B (Ground Mounted) | Material | Each |  | 8
3434-175 | Disposal of Support, Overhead Structure | Material | Each |  | 8
3434-176 | Disposal of Sign System, Overhead | Material | Each |  | 8
3434-177 | Disposal of Sign, A or B (Overhead) | Material | Each |  | 8
3434-178 | Stockpile Sign, A & B (Ground Mounted) | Material | Each |  | 8
3434-179 | Disposal of Sign, D, E or F | Material | Each |  | 8
3434-180 | Disposal of Sign, Milemarker | Material | Each |  | 8
3434-181 | Maintenance of Traffic During Construction | Material | Month |  | 8
3434-182 | Work Zone Signs (Stationary) | Material | Square Feet |  | 8
3434-183 | Work Zone Signs (Portable) | Material | Square Feet |  | 8
3434-184 | Flashing Arrow Board | Material | Each |  | 8
3434-185 | Portable Changeable Message Sign | Material | Each |  | 8
3434-186 | Work Zone Digital Speed Limit Signs | Material | Each |  | 8
3434-187 | Work Zone Presence Lighting | Material | Each |  | 8
3434-188 | Drums | Material | Each |  | 8
3434-189 | Sequential Flashing Warning Lights | Material | Each |  | 8
3434-190 | Barricades (Type III) | Material | Linear Feet |  | 8
3434-191 | Flagger | Material | Day |  | 8
3434-192 | Temporary Crash Cushions | Material | Each |  | 8
3434-193 | Remove & Reset Temporary Crash Cushion | Material | Each |  | 8
3434-194 | Truck Mounted Attenuator | Material | Each |  | 8
3434-195 | Portable Concrete Barrier | Material | Linear Feet |  | 8
3434-196 | Portable Concrete Barrier (Anchored) | Material | Linear Feet |  | 8
3434-197 | Reset Portable Concrete Barrier | Material | Linear Feet |  | 8
3434-198 | Relocated Portable Concrete Barrier | Material | Linear Feet |  | 8
3434-199 | Relocate Portable Concrete Barrier (Anchored) | Material | Linear Feet |  | 8
3434-200 | Law Enforecement | Material | Hour |  | 8
3434-201 | Skinny Drum | Material | Each |  | 8
3434-202 | Temporary Traffic Signals | Material | Each |  | 8
3434-203 | Relocate Existing OH Sign Panels | Material | Each |  | 8
3434-204 | Relocate Existing Post Mounted Signs | Material | Each |  | 8
3434-205 | Relocate Existing U Channel Signs | Material | Each |  | 8
3434-206 | Median Access Truck Warning Beacons | Material | Each |  | 8
3434-207 | Temporary GRAU-Type 3 | Material | Each |  | 8
3434-208 | Temporary B-77 | Material | Each |  | 8
3434-209 | Temporary CAT-1 | Material | Each |  | 8
3434-210 | On Call Towing | Material | Day |  | 8
3434-211 | Generic Traffic Control Item - Smart Zone System | Material | Month |  | 8
3434-212 | Temporary Raised Pavement Markers | Material | Each |  | 8
3434-213 | Thermoplastic Pavement Marking Lines (8", 90 Mils) | Material | Linear Feet |  | 8
3434-214 | Thermoplastic Pavement Marking Lines (8", 120 Mils) | Material | Linear Feet |  | 8
3434-215 | Thermoplastic Pavement Marking Lines (24", 120 Mils) | Material | Linear Feet |  | 8
3434-216 | Thermoplastic Pavement Marking Character (120 Mils) | Material | Each |  | 8
3434-217 | Thermoplastic Pavement Marking Symbol (90 Mils) | Material | Each |  | 8
3434-218 | Cold Applied Plastic Pavement Marking Lines, Type ** (6") - Temporary | Material | Linear Feet |  | 8
3434-219 | Paint Pavement Marking Lines (4") - Temporary | Material | Linear Feet |  | 8
3434-220 | Paint Pavement Marking Lines (8") - Temporary | Material | Linear Feet |  | 8
3434-221 | Paint Pavement Marking Lines (24") - Temporary | Material | Linear Feet |  | 8
3434-222 | Paint Pavement Marking Character - Temporary | Material | Each |  | 8
3434-223 | Paint Pavement Marking Symbol - Temporary | Material | Each |  | 8
3434-224 | Polyurea Pavement Marking Lines (4", 20 Mils) | Material | Linear Feet |  | 8
3434-225 | Polyurea Pavement Marking Lines (6", 20 Mils) | Material | Linear Feet |  | 8
3434-226 | Polyurea Pavement Marking Lines (8", 20 Mils) | Material | Linear Feet |  | 8
3434-227 | Polyurea Pavement Marking Lines (12", 20 Mils) | Material | Linear Feet |  | 8
3434-228 | Work Zone Performance Pavement Marking Lines, 6" | Material | Linear Feet |  | 8
3434-229 | Work Zone Performance Pavement Marking Lines, 12" | Material | Linear Feet |  | 8
3434-230 | Work Zone Performance Pavement Markings, Symbol | Material | Linear Feet |  | 8
3434-231 | Work Zone Performance Pavement Marking Lines, 6" Concrete Pvmt | Material | Linear Feet |  | 8
3434-232 | Work Zone Performance Pavement Marking Lines, 12" Concrete Pvmt | Material | Linear Feet |  | 8
3434-233 | Work Zone Traffic Pattern Masking | Material | Square Feet |  | 8
3434-234 | Removal of Pavement Marking Lines (4") | Material | Linear Feet |  | 8
3434-235 | Removal of Pavement Marking Lines (6") | Material | Linear Feet |  | 8
3434-236 | Removal of Pavement Marking Lines (8") | Material | Linear Feet |  | 8
3434-237 | Removal of Pavement Marking Lines (24") | Material | Linear Feet |  | 8
3434-238 | Removal of Pavement Marking Symbols & Characters | Material | Each |  | 8
3434-239 | Snowplowable Pavement Markers | Material | Each |  | 8
3434-240 | 60' High Mount Standard | Material | Each |  | 8
3434-241 | 80' High Mount Standard | Material | Each |  | 8
3434-242 | 100' High Mount Standard | Material | Each |  | 8
3434-243 | 120' High Mount Standard | Material | Each |  | 8
3434-244 | Portable Drive Unit | Material | Each |  | 8
3434-245 | High Mount Foundations | Material | Cubic Yard |  | 8
3434-246 | Light Standards, Type MTLT (45' SA, 15') | Material | Each |  | 8
3434-247 | Light Standards, Type MTLT (45' SA, 15' Twin) | Material | Each |  | 8
3434-248 | Standard Foundation Type R1 | Material | Each |  | 8
3434-249 | Standard Foundation Type M1 | Material | Each |  | 8
3434-250 | Light Standard Luminaires, Type RDW 185W HPS | Material | Each |  | 8
3434-251 | Light Standard Luminaires, Type RDW 285W HPS | Material | Each |  | 8
3434-252 | Electric Service Pole (30' Class 4) | Material | Each |  | 8
3434-253 | Electric Service Lateral (3 #1/0 Use) | Material | Linear Feet |  | 8
3434-254 | Electrical Duct, Type BD, Size (2") | Material | Linear Feet |  | 8
3434-255 | Electrical Duct, Type BD, Size (3") | Material | Linear Feet |  | 8
3434-256 | Electrical Duct, Type BD, Size (4") | Material | Linear Feet |  | 8
3434-257 | Electrical Duct, Type BD, Size (6") | Material | Linear Feet |  | 8
3434-258 | Electrical Duct, Type JA, Size (2") | Material | Linear Feet |  | 8
3434-259 | Electrical Duct, Type JA, Size (3") | Material | Linear Feet |  | 8
3434-260 | Electrical Duct, Type JA, Size (4") | Material | Linear Feet |  | 8
3434-261 | ** #8 W/G Feeder Circuit | Material | Linear Feet |  | 8
3434-262 | ** #6 W/G Feeder Circuit | Material | Linear Feet |  | 8
3434-263 | ** #4 W/G Feeder Circuit | Material | Linear Feet |  | 8
3434-264 | ** #4 W/G Feeder Circuit ITS | Material | Linear Feet |  | 8
3434-265 | ** #2 W/G Feeder Circuit | Material | Linear Feet |  | 8
3434-266 | ** #1 W/G Feeder Circuit | Material | Linear Feet |  | 8
3434-267 | ** #8 W/G Feeder Circuit in 1 1/2" Conduit | Material | Linear Feet |  | 8
3434-268 | ** #6 W/G Feeder Circuit in 1 1/2" Conduit | Material | Linear Feet |  | 8
3434-269 | ** #4 W/G Feeder Circuit in 1 1/2" Conduit | Material | Linear Feet |  | 8
3434-270 | ** #2 W/G Feeder Circuit in 1 1/2" Conduit | Material | Linear Feet |  | 8
3434-271 | ** #1 W/G Feeder Circuit in 1 1/2" Conduit | Material | Linear Feet |  | 8
3434-272 | Electrical Juntion Boxes (BRJB, 18" x 12") | Material | Each |  | 8
3434-273 | Electrical Juntion Boxes (CSJB, 36" x 24") | Material | Each |  | 8
3434-274 | Electrical Juntion Boxes (HMJB, 18" x 12") | Material | Each |  | 8
3434-275 | Electrical Juntion Boxes (HMJB, 30" x 17") | Material | Each |  | 8
3434-276 | Electrical Juntion Boxes (HMJB, 36" x 24") | Material | Each |  | 8
3434-277 | Electrical Juntion Boxes (IGJB, 18" x 12") | Material | Each |  | 8
3434-278 | Electrical Juntion Boxes (IGJB, 30" x 17") | Material | Each |  | 8
3434-279 | Electrical Juntion Boxes (IGJB, 36" x 24") | Material | Each |  | 8
3434-280 | Electrical Juntion Boxes (LSJB, 18" x 12") | Material | Each |  | 8
3434-281 | Underpass Luminaries 70W | Material | Each |  | 8
3434-282 | Underpass Luminaries 60W | Material | Each |  | 8
3434-283 | Underpass Circuitry | Material | Lump Sum |  | 8
3434-284 | Generic Lighting Item 60' High Mount Luminaire-320W LED | Material | Each |  | 8
3434-285 | Generic Lighting Item 80' High Mount Luminaire-320W LED | Material | Each |  | 8
3434-286 | Generic Lighting Item 100' High Mount Luminaire-320W LED | Material | Each |  | 8
3434-287 | Generic Lighting Item 120' High Mount Luminaire-320W LED | Material | Each |  | 8
3434-288 | 240/480V Lighting Controller | Material | Each |  | 8
3434-289 | Modify 240/480V Lighting Controller | Material | Each |  | 8
3434-290 | Lighting Communication Gateway | Material | Each |  | 8
3434-291 | Lighting Control Node | Material | Each |  | 8
3434-292 | 6" x 6" Wood Pedestal ITS | Material | Each |  | 8
3434-293 | Wet Utilities (further item detail provided upon final design) | Material | Lump Sum |  | 8
3434-294 | Temporary Silt Fence | Material | Linear Feet |  | 8
3434-295 | Stone For Erosion Control, Class A | Material |  |  | 8
3434-296 | Stone for Erosion Control, Class B | Material |  |  | 8
3434-297 | Sediment Control Stone | Material |  |  | 8
3434-298 | Temporary Mulching | Material |  |  | 8
3434-299 | Seed for Temporary Seeding | Material | LB |  | 8
3434-300 | Fertilizer for Temporary Seeding | Material |  |  | 8
3434-301 | Temporary Slope Drains | Material | Linear Feet |  | 8
3434-302 | Safety Fence | Material | Linear Feet |  | 8
3434-303 | Silt Excavation | Material | Cubic Yard |  | 8
3434-304 | Matting for Erosion Control | Material | Square Yard |  | 8
3434-305 | Coir Fiber Mat | Material | Square Yard |  | 8
3434-306 | Permanent Soil Reinforment Mat | Material | Square Yard |  | 8
3434-307 | High Velocity Matting | Material | Square Yard |  | 8
3434-308 | Coir Fiber Wattle | Material | Linear Feet |  | 8
3434-309 | Wattle Barrier | Material | Linear Feet |  | 8
3434-310 | Polyacrylamide (PAM) | Material | LB |  | 8
3434-311 | Coir Fiber Baffle | Material | Linear Feet |  | 8
3434-312 | 1 1/2" Skimmer | Material | Each |  | 8
3434-313 | 2" Skimmer | Material | Each |  | 8
3434-314 | 2 1/2" Skimmer | Material | Each |  | 8
3434-315 | 4" Skimmer | Material | Each |  | 8
3434-316 | Seeding & Mulching | Material |  |  | 8
3434-317 | Mowing | Material |  |  | 8
3434-318 | Seed for Repair Seeding | Material | LB |  | 8
3434-319 | Fertilizer for Repair Seeding | Material |  |  | 8
3434-320 | Seed for Supplemental Seeding | Material | LB |  | 8
3434-321 | Fertilizer Topdressing | Material |  |  | 8
3434-322 | Specialized Hand Mowing | Material | Hour |  | 8
3434-323 | Concrete Washout Structure | Material | Each |  | 8
3434-324 | Construction Entrance | Material | Each |  | 8
3434-325 | Erosion Control Maintenance | Material | Month |  | 8
3434-326 | Pedestrian Signal Head (16", 1 Section w/Countdown) | Material | Each |  | 8
3434-327 | Signal Cable | Material | Linear Feet |  | 8
3434-328 | Vehicle Signal Head (12", 3 Section) | Material | Each |  | 8
3434-329 | Vehicle Signal Head (12", 4 Section) | Material | Each |  | 8
3434-330 | Vehicle Signal Head (12", 5 Section) | Material | Each |  | 8
3434-331 | Messenger Cable (3/8") | Material | Linear Feet |  | 8
3434-332 | Tracer Wire ITS | Material | Linear Feet |  | 8
3434-333 | Unpaved Trenching (1 - 2") | Material | Linear Feet |  | 8
3434-334 | Unpaved Trenching (1 - 2") ITS | Material | Linear Feet |  | 8
3434-335 | Directional Drill (1 - 2") | Material | Linear Feet |  | 8
3434-336 | Junction Box (Standard Size) | Material | Each |  | 8
3434-337 | Junction Box (Standard Size) ITS | Material | Each |  | 8
3434-338 | Junction Box (Oversized, 30" x 15" x 24") | Material | Each |  | 8
3434-339 | Wood Pole for New Electrical Service | Material | Each |  | 8
3434-340 | CCTV Wood Pole | Material | Each |  | 8
3434-341 | 2" Riser with Weatherhead | Material | Each |  | 8
3434-342 | 2" Riser with Weatherhead ITS | Material | Each |  | 8
3434-343 | 2" Riser with Heat Shrink Tubing | Material | Each |  | 8
3434-344 | Inductive Loop Sawcut | Material | Linear Feet |  | 8
3434-345 | Lead-in Cable | Material | Linear Feet |  | 8
3434-346 | Microwave Vehicle Detector | Material | Each |  | 8
3434-347 | Communications Cable (96-Fiber) | Material | Linear Feet |  | 8
3434-348 | Drop Cable (12-Fiber) | Material | Linear Feet |  | 8
3434-349 | Splice Enclosure | Material | Each |  | 8
3434-350 | Interconnect Center | Material | Each |  | 8
3434-351 | Delineator Marker | Material | Each |  | 8
3434-352 | Delineator Marker ITS | Material | Each |  | 8
3434-353 | Furnish Fiber-Optic Transceiver | Material | Each |  | 8
3434-354 | Furnish Wireless Radio Modem | Material | Each |  | 8
3434-355 | Furnish Wireless Lighning Arrestor | Material | Each |  | 8
3434-356 | New Electrical Service | Material | Each |  | 8
3434-357 | New Electrical Service ITS | Material | Each |  | 8
3434-358 | Metal Strain Signal Pole | Material | Each |  | 8
3434-359 | Metal Pole with Single Mast Arm | Material | Each |  | 8
3434-360 | Soil Test | Material | Each |  | 8
3434-361 | Sign for Signals | Material | Each |  | 8
3434-362 | Type B Pedestal with Foundation | Material | Each |  | 8
3434-363 | Signal Cabinet Foundation | Material | Each |  | 8
3434-364 | Controllers with Cabinet (2070-E) | Material | Each |  | 8
3434-365 | Detector Card (2070-E) | Material | Each |  | 8
3434-366 | Controller with Cabinet (Type 2070L, Base Mounted) | Material | Each |  | 8
3434-367 | Detector Card (Type 2070L) | Material | Each |  | 8
3434-368 | Cabinet Base Extender | Material | Each |  | 8
3434-369 | Remove Existing Wireless System | Material | Each |  | 8
3434-370 | CCTV Cabinet (Type 336, Pole Mounted) | Material | Each |  | 8
3434-371 | CCTV Camera Assembly | Material | Each |  | 8
3434-372 | CCTV Cabinet Disconnect | Material | Each |  | 8
3434-373 | ITS Equipment Cabinet Disconnect | Material | Each |  | 8
3434-374 | Relocate Solar Power Assembly | Material | Each |  | 8
3434-375 | ITS Integration and Configuration | Material | Lump Sum |  | 8
3434-376 | 2" RGS Riser | Material | Linear Feet |  | 8
3434-377 | Removal of Existing Structure East Broad Street | Material | Lump Sum |  | 8
3434-378 | Removal of Existing Structure Davie Avenue | Material | Lump Sum |  | 8
3434-379 | Removal of Existing Structure Greenway NB | Material | Lump Sum |  | 8
3434-380 | Removal of Existing Structure Greenway SB | Material | Lump Sum |  | 8
3434-381 | Removal of Existing Structure I-77 NB | Material | Lump Sum |  | 8
3434-382 | Removal of Existing Structure I-77 SB | Material | Lump Sum |  | 8
3434-383 | Removal of Existing Structure I-40 WB | Material | Lump Sum |  | 8
3434-384 | Removal of Existing Structure I-40 EB | Material | Lump Sum |  | 8
3434-385 | Removal of Portion of Existing Structure I-40 over YRPDB and YRPCA | Material | Lump Sum |  | 8
3434-386 | Removal of Portion of Existing Structure on I-77 NB over YRPBD | Material | Lump Sum |  | 8
3434-387 | Removal of Existing Concrete Box Culvert under I-40 | Material | Lump Sum |  | 8
3434-388 | Asbestos Assessment | Material | Lump Sum |  | 8
3434-389 | Foundation Excavation (Bridge) | Material | Cubic Yard |  | 8
3434-390 | 3'-0" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3434-391 | 4'-0" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3434-392 | 4'-6" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3434-393 | 5'-6" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3434-394 | 3'-0" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3434-395 | 4'-0" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3434-396 | 4'-6" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3434-397 | 5'-6" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3434-398 | PDA Testing | Material | Each |  | 8
3434-399 | Reinforced Concrete Deck Slab | Material | Square Feet |  | 8
3434-400 | Grooving Bridge Floors | Material | Square Feet |  | 8
3434-401 | Class A Concrete (Bridge) | Material | Cubic Yard |  | 8
3434-402 | Bridge Approach Slabs, Station************ | Material | Lump Sum |  | 8
3434-403 | Reinforcing Steel (Bridge) | Material | LB |  | 8
3434-404 | Spiral Column Reinforcing Steel (Bridge) | Material | LB |  | 8
3434-405 | 45" Prestressed Concrete Girders | Material | Linear Feet |  | 8
3434-406 | 54" Prestressed Concrete Girders | Material | Linear Feet |  | 8
3434-407 | 63" Prestressed Concrete Girders | Material | Linear Feet |  | 8
3434-408 | 72" Prestressed Concrete Girders | Material | Linear Feet |  | 8
3434-409 | 78" Prestressed Concrete Girders | Material | Linear Feet |  | 8
3434-410 | Modified 72" Prestressed Concrete Girders | Material | Linear Feet |  | 8
3434-411 | Approx 2,616,070 LBS Structural Steel | Material | Lump Sum |  | 8
3434-412 | HP12X53 Steel Piles | Material | Linear Feet |  | 8
3434-413 | HP14X73 Steel Piles | Material | Linear Feet |  | 8
3434-414 | Two Bar Metal Rail | Material | Linear Feet |  | 8
3434-415 | Concrete Barrier Rail | Material | Linear Feet |  | 8
3434-416 | Concrete Barrier Rail with Moment Slab | Material | Linear Feet |  | 8
3434-417 | Rectangular Concrete Parapet | Material | Linear Feet |  | 8
3434-418 | 4" Slope Protection | Material | Square Yard |  | 8
3434-419 | Disc Bearings | Material | Lump Sum |  | 8
3434-420 | Elastomeric Bearings | Material | Lump Sum |  | 8
3434-421 | Expansion Joint Seals | Material | Lump Sum |  | 8
3434-422 | MSE Retaining Wall No **** | Material | Square Feet |  | 8
3434-423 | MSE Wall Concrete Ditch | Material | Square Yard |  | 8
3434-424 | Soil Nail Retaining Walls | Material | Square Feet |  | 8
3434-425 | Generic Structure Item Noisewalls | Material | Square Feet |  | 8
3418-02 | Bonds and Insurance | Material | Lump Sum |  | 1
3418-03 | ROW Acquisition | Material | Unit |  | 1
3418-04 | Design | Material | Unit |  | 1
3418-05 | Permitting / Mitigation | Material | Lump Sum |  | 1
3418-06 | Project Management (Design) | Material | Unit |  | 1
3418-08 | Quality Control | Material | Unit |  | 1
3418-09 | UTILITY RELOCATION COSTS | Material | Unit |  | 1
3418-10 | MOT Maintenance | Material | Unit |  | 1
3418-11 | Police | Material | Hour |  | 1
3418-12 | Milling | Material | Square Yard |  | 1
3418-13 | Fine Grade | Material | Square Yard |  | 1
3418-14 | CMRB | Material | Square Yard |  | 1
3418-15 | Milled Rumble strips | Material | Mile |  | 1
3418-16 | HMA Intermediate Course Type A | Material |  |  | 1
3418-17 | HMA Intermediate Course Type B | Material |  |  | 1
3418-18 | HMA SURFACE COURSE TYPE A | Material |  |  | 1
3418-19 | HMA Surface B | Material |  |  | 1
3418-20 | HMA Surface C | Material |  |  | 1
3418-21 | OGFC | Material |  |  | 1
3418-22 | HMA Base | Material |  |  | 1
3418-23 | Clear and Grub | Material |  |  | 1
3418-24 | Temp ROW Fence | Material | Linear Feet |  | 1
3418-25 | Demo Bldgs & Asbestos | Material | Each |  | 1
3418-26 | Remove Existing Pipe | Material | Linear Feet |  | 1
3418-27 | Flowable Fill Existing Pipe 16 Locations | Material | Cubic Yard |  | 1
3418-28 | Remove & Dispose Barb Wire w/ Post Fence | Material | Linear Feet |  | 1
3418-29 | Video Tape Existing Drainage System | Material | Linear Feet |  | 1
3418-30 | Remove drainage structures | Material | Each |  | 1
3418-31 | REMOVAL & DISPOSAL OF EXISTING CONCRETE | Material | Cubic Yard |  | 1
3418-32 | REMOVAL OF EXIST. MEDIAN CABLE RAIL | Material | Linear Feet |  | 1
3418-33 | REMOVAL & DISPOSAL OF EXISTING BRIDGE - S83 | Material | Each |  | 1
3418-34 | REMOVAL & DISPOSAL OF EXISTING BRIDGE - NSRR OVER | Material | Lump Sum |  | 1
3418-35 | Permanent Seed | Material |  |  | 1
3418-36 | Temporary Seed | Material |  |  | 1
3418-37 | Structural Excavation | Material | Cubic Yard |  | 1
3418-38 | Grade under structures | Material | Square Feet |  | 1
3418-39 | Rebar | Material | LB |  | 1
3418-40 | Fertilizer | Material | LB |  | 1
3418-41 | 18" RCP Temp Drainage 4' Ave Depth | Material | Linear Feet |  | 1
3418-42 | Remove Asphalt-Rip&Load | Material | Square Yard |  | 1
3418-43 | Temporary Earthwork | Material | Cubic Yard |  | 1
3418-44 | TEMP WIRE WALL | Material | Square Feet |  | 1
3418-45 | PERMANENT CONSTRUCTION SIGNS (GROUND MOUNTED) | Material | Square Feet |  | 1
3418-46 | C.Z.CHANGE.MESS.SGN(TRAIL.MTD) | Material | Each |  | 1
3418-47 | C.Z.ELEC.ARROW BRD.(TRAIL.MTD.) | Material | Each |  | 1
3418-48 | PORT.TERM.IMP.ATTEN-6BAY-2.0'W (TL-2) | Material | Each |  | 1
3418-49 | RESET TEMPORARY CRASH CUSHION (TL-2) | Material | Each |  | 1
3418-50 | PORTABLE PLASTIC DRUMs/cones | Material | Each |  | 1
3418-51 | BARRICADE - TYPE 2/3 | Material | Linear Feet |  | 1
3418-52 | TEMPORARY CONSTRUCTION SIGNS | Material | Square Feet |  | 1
3418-53 | TRUCK MOUNTED ATTENUATOR | Material | Each |  | 1
3418-54 | TEMP GUARDRAIL | Material | Linear Feet |  | 1
3418-55 | Unclasified Excavation | Material | Cubic Yard |  | 1
3418-56 | EXCAVATE FOR PERMANENT MEDIAN WIDENING | Material | Cubic Yard |  | 1
3418-57 | ROCK EXCAVATION | Material | Cubic Yard |  | 1
3418-58 | BORROW EXCAVATION | Material | Cubic Yard |  | 1
3418-59 | EMBANKMENT | Material | Cubic Yard |  | 1
3418-60 | Place Agg Bse-6" | Material |  |  | 1
3418-61 | SUBSTRUCTURE CLASS 4000 - S-83 | Material | Cubic Yard |  | 1
3418-62 | SUPERSTRUCTURE CLASS 4000 | Material | Cubic Yard |  | 1
3418-63 | Approach Slabs | Material | Cubic Yard |  | 1
3418-64 | Substructure NSRR | Material | Cubic Yard |  | 1
3418-65 | Superstructure Class 5000 NSRR | Material | Cubic Yard |  | 1
3418-66 | GROOVED SURFACE FINISH | Material | Square Yard |  | 1
3418-67 | PRESTRESSED CONC. BEAM (TYPE IV) | Material | Linear Feet |  | 1
3418-68 | CONCRETE BRIDGE BARRIER PARAPET | Material | Linear Feet |  | 1
3418-69 | STRUCTURAL STEEL | Material | LB |  | 1
3418-70 | STRUCTURE DRAINAGE SYSTEM | Material | Lump Sum |  | 1
3418-71 | ELASTOMERIC BEARING | Material | Each |  | 1
3418-72 | PRESTRESSED FLORIDA I-BEAM (36") | Material | Linear Feet |  | 1
3418-73 | PRESTRESSED FLORIDA I-BEAM (45") | Material | Each |  | 1
3418-74 | PRESTRESSED FLORIDA I-BEAM (54") | Material | Each |  | 1
3418-75 | (NS RR BRIDGE) Waterproof | Material | SYD |  | 1
3418-76 | Handrail and fence NSRR | Material | Linear Feet |  | 1
3418-77 | (NS RR BRIDGE) - SS SLIDING PLATE EXP JOINT ASSY | Material | Linear Feet |  | 1
3418-78 | Bearings NSRR Bridge | Material | Each |  | 1
3418-79 | (NS RR BRIDGE) - # 57 DRAINAGE STONE | Material | Cubic Yard |  | 1
3418-80 | (NS RR BRIDGE) - GRANULAR BACKFILL | Material | Cubic Yard |  | 1
3418-81 | AGGR UNDERDRAIN (AGG#789) W/ 4" PERF PIPE FOR STRS | Material | Cubic Yard |  | 1
3418-82 | (NS RR BRIDGE) - BALLAST | Material |  |  | 1
3418-83 | Bridge Construction access | Material | Lump Sum |  | 1
3418-84 | Pile Driving | Material | Linear Feet |  | 1
3418-85 | TEMP SHEET PILE | Material | Square Feet |  | 1
3418-86 | MECHANICALLY STABILIZED EARTH RETAINING WALL | Material | Square Feet |  | 1
3418-87 | Temp Soil Nail Wall | Material | Square Feet |  | 1
3418-88 | Coping For Retaining Wall | Material | Cubic Yard |  | 1
3418-89 | Precast Endwall | Material | Each |  | 1
3418-90 | J&B 66" casing/ 48" carrier | Material | Linear Feet |  | 1
3418-91 | 18" SMOOTH WALL PIPE | Material | Linear Feet |  | 1
3418-92 | 24" SMOOTH WALL PIPE | Material | Linear Feet |  | 1
3418-93 | 30" SMOOTH WALL PIPE | Material | Linear Feet |  | 1
3418-94 | 36" SMOOTH WALL PIPE | Material | Linear Feet |  | 1
3418-95 | 48" SMOOTH WALL PIPE | Material | Linear Feet |  | 1
3418-96 | 60" SMOOTH WALL PIPE | Material | Linear Feet |  | 1
3418-97 | LINE EXISTING 18" PIPE | Material | Linear Feet |  | 1
3418-98 | LINE EXISTING 24" PIPE | Material | Linear Feet |  | 1
3418-99 | LINE EXISTING 30" PIPE | Material | Linear Feet |  | 1
3418-100 | CLEANING EXISTING PIPE | Material | Linear Feet |  | 1
3418-101 | Catch Basin | Material | Each |  | 1
3418-102 | Drop inlet | Material | Each |  | 1
3418-103 | PRECAST CONCRETE RISER | Material | Linear Feet |  | 1
3418-104 | PRECAST CONCRETE DRAINAGE BASE | Material | Each |  | 1
3418-105 | PRECAST CONCRETE TRANSITION SECTION - FLAT SLAb | Material | Each |  | 1
3418-106 | EXTRA DEPTH OF BOX | Material | Linear Feet |  | 1
3418-107 | Convert drainage structure | Material | Each |  | 1
3418-108 | REPAIR BOX CULVERT | Material | Linear Feet |  | 1
3418-109 | 6'X4' P.C. BOX CULVERT FH=5' | Material | Cubic Yard |  | 1
3418-110 | 7'X7' P.C. BOX CULVERT FH=20' | Material | Cubic Yard |  | 1
3418-111 | 8'X8' P.C. BOX CULVERT FH=19 | Material | Cubic Yard |  | 1
3418-113 | CONCRETE CURB AND GUTTER(2'-0") VERT FACE | Material | Linear Feet |  | 1
3418-114 | SIDEWALK 6" | Material | Square Yard |  | 1
3418-115 | CONC DRIVEWAY 6" | Material | Square Yard |  | 1
3418-116 | 5" Island Cover - 1 location | Material | Square Yard |  | 1
3418-117 | 56ZOI VF BARRIER MEDIAN SYSTEM | Material | Linear Feet |  | 1
3418-118 | CONC MEDIAN BARR A 56" SLIP | Material | Linear Feet |  | 1
3418-119 | CONC MEDIAN BARR B 56" GRADE SEPARATION | Material | Linear Feet |  | 1
3418-120 | CONCRETE BARRIER SINGLE FACE | Material | Linear Feet |  | 1
3418-121 | RIP-RAP (CLASS A) | Material |  |  | 1
3418-122 | RIP-RAP (CLASS B) | Material |  |  | 1
3418-123 | RIP-RAP (CLASS C) | Material |  |  | 1
3418-124 | RIP-RAP (CLASS D) | Material |  |  | 1
3418-125 | SLOPE PROTECTION-4" CONCRETE(FIBER REINFORCED) | Material | Square Yard |  | 1
3418-126 | GEOTEXT FOR EC UNDER RIPRAP CLASS C | Material | Square Yard |  | 1
3418-127 | STEEL BEAM GUARDRAIL STEEL BEAM GR. | Material | Linear Feet |  | 1
3418-128 | REMOVAL OF EXISTING GUARDRAIL | Material | Linear Feet |  | 1
3418-129 | END ANCHOR-TYPE B | Material | Each |  | 1
3418-130 | END TERMINAL - TYPE T | Material | Each |  | 1
3418-134 | WOVEN WIRE FENCE - TYPE 5 WITH 3 STRANDS | Material | Linear Feet |  | 1
3418-135 | 72" SECURITY CHAIN LINK FENCE | Material | Linear Feet |  | 1
3418-136 | COMPOST | Material | Cubic Yard |  | 1
3418-137 | AGRICULTURAL GRANULAR LIME | Material | LB |  | 1
3418-138 | MOWING | Material |  |  | 1
3418-139 | MAINTAIN EROSION CONTROL | Material | Month |  | 1
3418-140 | TEMPORARY EROSION CONTROL BLANKET | Material | Square Yard |  | 1
3418-141 | TURF REINFORCEMENT MATTING (TRM) | Material | Square Yard |  | 1
3418-142 | INLET STRUCTURE FILTER - TYPE F (WEIGHTE | Material | Each |  | 1
3418-143 | SEDIMENT TUBES FOR DITCH CHECKS | Material | Linear Feet |  | 1
3418-144 | Silt Fence | Material | Linear Feet |  | 1
3418-145 | SILT BASINS | Material | Linear Feet |  | 1
3418-146 | DITCH CHECK | Material |  |  | 1
3418-147 | SEDIMENT DAM RIPRAP | Material |  |  | 1
3418-148 | AGGREGATE NO.5 OR 57 FOR EROSION CONTROL | Material |  |  | 1
3418-149 | STABILIZED CONSTRUCTION ENTRANCE | Material | Each |  | 1
3418-150 | TEMPORARY FLEXIBLE PIPE SLOPE DRAIN - 8" | Material | Linear Feet |  | 1
3418-151 | Permanent Pavement Markings | Material | Linear Feet |  | 1
3418-152 | Permanent Pavement Symbols | Material | Each |  | 1
3418-153 | Permanent Pavement Markers | Material | Each |  | 1
3418-154 | Temp Pavement Markings | Material | Linear Feet |  | 1
3418-155 | Permanen Sign Panels | Material | Square Feet |  | 1
3418-156 | U-SECTION POST FOR SIGN SUPPORTS | Material | Linear Feet |  | 1
3418-157 | BREAK-AWAY SIGN SUPPORTS | Material | LB |  | 1
3418-158 | OVERHEAD SIGN STRUCTURE NO.OH-01-16 | Material | Each |  | 1
3418-159 | ITS - 2" SCHEDULE 80 HDPE CONDUIT | Material | Linear Feet |  | 1
3418-160 | 144 SMFO LOOSE TUBE - BACKBONE | Material | Each |  | 1
3418-161 | Variable Message Signs | Material | Each |  | 1
3418-162 | Permanent Signals | Material | Each |  | 1
3418-163 | Temporary Signal | Material | Each |  | 1
3418-164 | Temporary Concrete Barrier | Material | Linear Feet |  | 1
3418-165 | TCB RELOCATE (WITH TRUCK) SUB | Material | Linear Feet |  | 1
3418-166 | TCB RESET (NO TRUCK) SUB | Material | Linear Feet |  | 1
R-2828 | R-2828 Triangle Expressway | Labor |  |  | 1
R2828.10 | Supplemental Survey | Labor |  |  | 1
R2828.20 | Right of Way Acquisition | Labor |  |  | 1
R2828.30 | Pavement Plans & PSP | Labor |  |  | 1
R2828.40 | MOT Plans & PSP | Labor |  |  | 1
R2828.50 | Deisgn Criteria & Structure Recs | Labor |  |  | 1
R2828.60 | Preliminary Roadway Plans | Labor |  |  | 1
R2828.70 | Revise/Resubmit Preliminary Roadway Plans | Labor |  |  | 1
R2828.80 | Temporary Pavement Design | Labor |  |  | 1
R2828.90 | Resubmit Temporary Pavement Design | Labor |  |  | 1
R2828.100 | Field Reconnaissance | Labor |  |  | 1
R2828.110 | Prepare 100% Hydraulic Design | Labor |  |  | 1
R2828.120 | Prepare Erosion Control Plans (Mainline Area 1) | Labor |  |  | 1
R2828.130 | Prepare Erosion Control Plans (Mainline Area 1) | Labor |  |  | 1
R2828.140 | Submit Preliminary Bridge/Culvert Survey Reports | Labor |  |  | 1
R2828.150 | Prepare Bridge/Culvert Survey REports | Labor |  |  | 1
R2828.160 | Geotech Field Investigation - Early Work Bridges | Labor |  |  | 1
R2828.170 | Prepare RR Agreement | Labor |  |  | 1
R2828.180 | Revise RR Agreement | Labor |  |  | 1
R2828.190 | Design Management | Labor |  |  | 1
R2828.200 | Utility Coordination | Labor |  |  | 1
R2828.210 | Discipline Coordination | Labor |  |  | 1
R2828.220 | Proposal Design Fee | Labor |  |  | 1
R2828.230 | Designer Project Spec Liab Insur | Labor |  |  | 1
R2828.240 | L/B Liability Insurance | Labor |  |  | 1
R2828.250 | L/B P&P Bonds | Labor |  |  | 1
R2828.260 | Mobilization (30% of 6%) | Labor |  |  | 1
R2828.280 | Remaining Costs | Labor |  |  | 1
9156 - Bid / Interm | 9156- Bid / Interm Resources | Nonlabor |  |  | 1
R2828 | R2828 Revenue | Material | Unit |  | 8
3417-85012-24 | NS External Leak Resistant Pipe Joint Wrap 24" | Material | Linear Feet |  | 8
3417-85012-36 | NS External Leak Resistant Pipe Joint Wrap 36" | Material | Linear Feet |  | 8
3417-85012-42 | NS External Leak Resistant Pipe Joint Wrap 42" | Material | Linear Feet |  | 8
3417-85012-48 | NS External Leak Resistant Pipe Joint Wrap 48" | Material | Linear Feet |  | 8
3417-85004 | NS Turbitity Curtain Type 2 | Material | Linear Feet |  | 8
3417-85012-MOB | NS Treatment System Mobilization | Material | Each |  | 8
3417-85014 | NS Contaminated Groundwater Treatment System | Material | Day |  | 8
MB Submittal | Submittal Count | Nonlabor |  |  | 1
MBTA - Cabot Yard | Cabot Yard & Carhouse | Labor |  |  | 1
CY.ABATE | Abatement Crew | Labor |  |  | 1
C43-LANE | C43 - Lane Crews | Labor |  |  | 1
C43-EW | C43 - Earthwork Crew | Labor |  |  | 1
C43-C&G | C43 - Clearing & Grubbing Crew | Labor |  |  | 1
C43-MASS | C43 - Mass Excavation / Embankment Crew | Labor |  |  | 1
C43-DAM FND | C43 - Dam Foundation Stripping & Prep Crew | Labor |  |  | 1
C43-TOE RD PREP | C43 - Toe Road Subgrade Prep & Ditches Crew | Labor |  |  | 1
C43-TOE RD EMB | C43 - Toe Road Embankment Crew | Labor |  |  | 1
C43-MAINT PREP | C43 - Maintenance Road Subgrade Prep Crew | Labor |  |  | 1
C43-TRENCH | C43 - Pre-Trenching Crew | Labor |  |  | 1
9151 - SHOPP | SHOPP Cost | Nonlabor |  |  | 0
SUB-ST-SOUND | Sub - Sound Wall Crews | Labor |  |  | 1
8A | ***ASPHALT PAVING*** | Nonlabor |  |  | 1
8AP0655 | CAT AP655 8' TRACK PAVER | Nonlabor |  |  | 1
8AP0800 | CAT AP800 8' R/T PAVER | Nonlabor |  |  | 1
8AP1000 | CAT AP1000 10' R/T PAVER | Nonlabor |  |  | 1
8AP1055 | CAT AP1055 10' TRACK PAVER | Nonlabor |  |  | 1
HCSS Equipment | EQUIPMENT RESOURCES | Material |  |  | 8
8APBAR | ABG/VOGELE TAMPER BAR PAVER | Nonlabor |  |  | 1
8APCS | CHIP SPREADER | Nonlabor |  |  | 1
8APMML | MAT'L TRANSFER MACH - SB2500 | Nonlabor |  |  | 1
8APMMS | MAT'L TRANSFER MACH - SB1500 | Nonlabor |  |  | 1
8APR51 | ROLLER -ASPH - 51" CAT CB 34 | Nonlabor |  |  | 1
8APR84 | ROLLER -ASPH - 84" CAT CB 64 | Nonlabor |  |  | 1
8APRW | ROAD WIDENER-RW195/WEILER730 | Nonlabor |  |  | 1
8APSB | WINDROW PICKUP MACHINE | Nonlabor |  |  | 1
8APTT | TACK/AC DISTRIBUTION TRUCK | Nonlabor |  |  | 1
8BH | ***BACKHOES/EXCAVATORS*** | Nonlabor |  |  | 1
8BH305 | CAT 305 MINI (<15K LBS) | Nonlabor |  |  | 1
8BH308 | CAT 308 (<25K LBS) | Nonlabor |  |  | 1
8BH316 | CAT 311-316 (25-40K LBS) | Nonlabor |  |  | 1
8BH318 | CAT M318 (44K LBS) | Nonlabor |  |  | 1
8BH325 | CAT 318-325 (41-64K LBS) | Nonlabor |  |  | 1
8BH336 | CAT 326-336 (65-89K LBS) | Nonlabor |  |  | 1
8BH349 | CAT 349/352 (90K-115K LBS) | Nonlabor |  |  | 1
8BH374 | CAT 374 (160K LBS) | Nonlabor |  |  | 1
8BH390 | CAT 390 (190K+ LBS) | Nonlabor |  |  | 1
8BH800 | EX1200 (250k LBS) | Nonlabor |  |  | 1
8BH900 | EX1900 (400k LBS) | Nonlabor |  |  | 1
8BHA | ***ATTACHMENTS*** | Nonlabor |  |  | 1
8BHAB | BARRIER CLAMP | Nonlabor |  |  | 1
8BHAC | COMPACTOR ATT | Nonlabor |  |  | 1
8BHAG | GRAPPLE ATT | Nonlabor |  |  | 1
8BHAP | PULVERIZER ATT | Nonlabor |  |  | 1
8BHAS | SHEAR ATT | Nonlabor |  |  | 1
8BR | ***BRIDGE/CONCRETE*** | Nonlabor |  |  | 1
8BRBW086 | BIDWELL MACHINE 3600 (86') | Nonlabor |  |  | 1
8BRBW116 | BIDWELL MACHINE 4800 (116') | Nonlabor |  |  | 1
8BRGB | GEORGIA BUGGY | Nonlabor |  |  | 1
8BRMM | MORTAR MIXER | Nonlabor |  |  | 1
8BRPC | CONCRETE PUMP 36M | Nonlabor |  |  | 1
8BRPG | CONC/GROUT LINE PUMP | Nonlabor |  |  | 1
8BRPP | CHEM GROUT PISTON PUMP | Nonlabor |  |  | 1
8BRSA | ALLEN ROLLER SCREED (6-26FT) | Nonlabor |  |  | 1
8BRST | TERAMITE SCREED | Nonlabor |  |  | 1
8CO | ***COMPRESSORS*** | Nonlabor |  |  | 1
8CO0185 | 185 CFM COMPRESSOR | Nonlabor |  |  | 1
8CO0375 | 375 CFM COMPRESSOR | Nonlabor |  |  | 1
8CO0500 | 500 CFM COMPRESSOR | Nonlabor |  |  | 1
8CO0750 | 750 CFM COMPRESSOR | Nonlabor |  |  | 1
8CO1200 | 1200 CFM COMPRESSOR | Nonlabor |  |  | 1
8CO1500 | 1500 CFM COMPRESSOR | Nonlabor |  |  | 1
8CP | ***CONCRETE PAVING*** | Nonlabor |  |  | 1
8CPBP | BELT PLACER (G&Z MP550) | Nonlabor |  |  | 1
8CPBWP | BARRIER WALL PAVER | Nonlabor |  |  | 1
8CPCM | CURB MACHINE (PC5700) | Nonlabor |  |  | 1
8CPCTM | CURE/TEXTURE MACHINE (TC600) | Nonlabor |  |  | 1
8CPMEPX | Epoxy Extruder | Nonlabor |  |  | 1
8CPS<24 | SLIP PAVER<24' (CMI/GOMACO) | Nonlabor |  |  | 1
8CPS>24 | SLIP PAVER>24' (GZ850) | Nonlabor |  |  | 1
8CPS>24D | SLIP PAVER>24' W/DBI (GZ850) | Nonlabor |  |  | 1
8CPTP | TRACK PLACER (GOMACO PS2600) | Nonlabor |  |  | 1
8CR | ***CRANES*** | Nonlabor |  |  | 1
8CRA040 | 40 TON RT CRANE | Nonlabor |  |  | 1
8CRA060 | 60 TON RT CRANE | Nonlabor |  |  | 1
8CRA080 | 80 TON RT CRANE | Nonlabor |  |  | 1
8CRA090 | 90 TON TRUCK CRANE | Nonlabor |  |  | 1
8CRA120 | 120 TON TRUCK CRANE | Nonlabor |  |  | 1
8CRC100 | 100 TON CRWLR CRANE | Nonlabor |  |  | 1
8CRC120 | 120 TON CRWLR CRANE(12000) | Nonlabor |  |  | 1
8CRC150 | 150 TON CRWLR CRANE(LS238) | Nonlabor |  |  | 1
8CRC200 | 200 TON CRWLR CRANE (777) | Nonlabor |  |  | 1
8CRC230 | 230 TON CRWLR CRANE (888) | Nonlabor |  |  | 1
8CRC250 | 250 TON CRWLR CRANE(LS298) | Nonlabor |  |  | 1
8CRC275 | 275 TON CRWLR CRANE (999) | Nonlabor |  |  | 1
8CRC300 | 300 TON CRWLR CRANE (2250) | Nonlabor |  |  | 1
8DH | ***DEMO HAMMERS / SAW*** | Nonlabor |  |  | 1
8DH01 | DEMO HAMMER <1KFTLB ATT | Nonlabor |  |  | 1
8DH02 | DEMO HAMMER 2.5KFTLB ATT | Nonlabor |  |  | 1
8DH05 | DEMO HAMMER 5KFTLB ATT | Nonlabor |  |  | 1
8DH10 | DEMO HAMMER 10KFTLB ATT | Nonlabor |  |  | 1
8DH12 | DEMO HAMMER 12KFTLB ATT | Nonlabor |  |  | 1
8DHS24 | DECK SAW 12"-24" | Nonlabor |  |  | 1
8DHS48 | WALK BEHIND SAW 36"-48" | Nonlabor |  |  | 1
8DR | ***DRILLS*** | Nonlabor |  |  | 1
8DR01 | LO-DRILL DH15-20 | Nonlabor |  |  | 1
8DR02 | LO-DRILL DH30-40 | Nonlabor |  |  | 1
8DR03 | DRILL RIG-AF300-350/BG38-40 | Nonlabor |  |  | 1
8DR04 | DRILL RIG-AF125-250/BG12-28 | Nonlabor |  |  | 1
8DR05 | KLEMM 803-806 TIE BACK RIG | Nonlabor |  |  | 1
8DR06 | HYD ROCK DRILL 0"-3.5" (TRACK) | Nonlabor |  |  | 1
8DR07 | HYD ROCK DRILL 3.5"-5" (Track) | Nonlabor |  |  | 1
8DR08 | CONCRETE CORE DRILL W/TRLR. | Nonlabor |  |  | 1
8DR09 | DOWEL DRILL MINNICH A-1 | Nonlabor |  |  | 1
8DR10 | EZ DRILL SA210 2 GANG | Nonlabor |  |  | 1
8DR11 | DOWEL DRILL MINNICH A-4 | Nonlabor |  |  | 1
8DR12 | EZ DRILL SA2105 5 GANG | Nonlabor |  |  | 1
8DR20 | Rev Drill 30" Auger | Nonlabor |  |  | 1
8DZ | ***DOZERS*** | Nonlabor |  |  | 1
8DZ04 | D4K DOZER (<95 HP) | Nonlabor |  |  | 1
8DZ04L | D4K LGP DOZER (<95 HP) | Nonlabor |  |  | 1
8DZ05 | D5K DOZER (96-115 HP) | Nonlabor |  |  | 1
8DZ06L | D6K LGP DOZER (130 HP) | Nonlabor |  |  | 1
8DZ06N | D6N DOZER (150HP) | Nonlabor |  |  | 1
8DZ06T | D6T DOZER (230 HP) | Nonlabor |  |  | 1
8DZ08 | D8 DOZER (350 HP) | Nonlabor |  |  | 1
8DZ09 | D9 DOZER (460 HP) | Nonlabor |  |  | 1
8DZ10 | D10 DOZER (600 HP) | Nonlabor |  |  | 1
8F | ***FORKS/TELEHANDLERS*** | Nonlabor |  |  | 1
8FL10 | MAST FORKLIFT 10T | Nonlabor |  |  | 1
8FL40 | MAST FORKLIFT 40T | Nonlabor |  |  | 1
8FT08 | TELEHANDLER (8K/40FT REACH) | Nonlabor |  |  | 1
8FT12 | TELEHANDLER (12K/55FT REACH) | Nonlabor |  |  | 1
8G | ***GRADERS*** | Nonlabor |  |  | 1
8G012 | GRADER (CAT 12) | Nonlabor |  |  | 1
8G014 | GRADER (CAT 14) | Nonlabor |  |  | 1
8G016 | GRADER (CAT 16) | Nonlabor |  |  | 1
8G018 | GRADER (CAT 18) | Nonlabor |  |  | 1
8G024 | GRADER (CAT 24) | Nonlabor |  |  | 1
8G140 | GRADER (CAT 140) | Nonlabor |  |  | 1
8GE | ***GENERATORS*** | Nonlabor |  |  | 1
8GE025 | 25KW GENERATOR | Nonlabor |  |  | 1
8GE050 | 50KW GENERATOR | Nonlabor |  |  | 1
8GE100 | 100 KW GENERATOR | Nonlabor |  |  | 1
8GE200 | 200 KW GENERATOR | Nonlabor |  |  | 1
8GE500 | 500 KW GENERATOR | Nonlabor |  |  | 1
8GE750 | 750 KW GENERATOR | Nonlabor |  |  | 1
8LD | ***LOADERS*** | Nonlabor |  |  | 1
8LD262 | SKIDSTEER (CAT 262) | Nonlabor |  |  | 1
8LD297 | SKIDSTEER, TRACK (CAT 297) | Nonlabor |  |  | 1
8LD430 | CAT 430, JD 410 LDR/BH (18K) | Nonlabor |  |  | 1
8LD450 | CAT 450, JD 710 LDR/BH (27K) | Nonlabor |  |  | 1
8LD938 | WHLDR 3-5CY(924-938,L60-L90) | Nonlabor |  |  | 1
8LD953 | TRACK LOADER 2CY (CAT 953 ) | Nonlabor |  |  | 1
8LD963 | TRACK LOADER 3CY (CAT 963) | Nonlabor |  |  | 1
8LD966 | WHLDR 4-5.5CY(950-966,L120) | Nonlabor |  |  | 1
8LD973 | TRACK LOADER 4CY (CAT 973) | Nonlabor |  |  | 1
8LD980 | WHLDR 6-8CY(972-980,L180) | Nonlabor |  |  | 1
8LD988 | WHLDR 9-10CY(CAT 988,L350) | Nonlabor |  |  | 1
8ME | ***MISC EQUIPMENT*** | Nonlabor |  |  | 1
8MEAB | ARROW BOARD | Nonlabor |  |  | 1
8MEAT | ATTENUATOR TRUCK | Nonlabor |  |  | 1
8MELP | LIGHT PLANT | Nonlabor |  |  | 1
8MEMB | MESSAGE BOARD | Nonlabor |  |  | 1
8MESW | BROOM/SWEEPER (SUPERIOR, BROCE) | Nonlabor |  |  | 1
8METC | TREE CHIPPER | Nonlabor |  |  | 1
8METG | TUB GRINDER | Nonlabor |  |  | 1
8ML | ***MANLIFTS*** | Nonlabor |  |  | 1
8ML040 | 40' MAN LIFT | Nonlabor |  |  | 1
8ML060 | 60' MAN LIFT | Nonlabor |  |  | 1
8ML080 | 80' MAN LIFT | Nonlabor |  |  | 1
8ML100 | 100' MAN LIFT | Nonlabor |  |  | 1
8ML120 | 120' MAN LIFT | Nonlabor |  |  | 1
8MLS20 | SCISSOR LIFT 20FT | Nonlabor |  |  | 1
8MLS40 | SCISSOR LIFT 40FT | Nonlabor |  |  | 1
8MM | ***MILLING MACHINES*** | Nonlabor |  |  | 1
8MMLG | MILLING MACHINE 80" (W210) | Nonlabor |  |  | 1
8MMMD | MILLING MACHINE 47" (W120) | Nonlabor |  |  | 1
8MMSM | MILLING MACHINE 20" (W50) | Nonlabor |  |  | 1
8MMXL | MILLING MACHINE 144" (W250) | Nonlabor |  |  | 1
8N | ***MARINE*** | Nonlabor |  |  | 1
8NBTC | BOAT - CREW | Nonlabor |  |  | 1
8NBTJ | BOAT - JACK BOAT | Nonlabor |  |  | 1
8NBTP | BOAT - PUSH BOAT | Nonlabor |  |  | 1
8NBTW | BOAT - WORKBOAT | Nonlabor |  |  | 1
8NDB0550 | DECK BARGE 90X35 (550 TN) | Nonlabor |  |  | 1
8NDB1575 | DECK BARGE 160X45 (1,575 TN) | Nonlabor |  |  | 1
8NDB4800 | DECK BARGE 240X60 (4,800 TN) | Nonlabor |  |  | 1
8NDSB075 | SPUD/CRANE BARGE w/75T | Nonlabor |  |  | 1
8NDSB150 | SPUD/CRANE BARGE w/150T | Nonlabor |  |  | 1
8NFF20 | FLEXI FLOAT 20X10X5 | Nonlabor |  |  | 1
8NFF40 | FLEXI FLOAT 40X10X5 | Nonlabor |  |  | 1
8NHB | HOPER BARGE 200X35 (1,600TN) | Nonlabor |  |  | 1
8NTGL | TUG - 1200 HP | Nonlabor |  |  | 1
8NTGS | TUG - 900 HP | Nonlabor |  |  | 1
8NZD12 | HYDRAULIC DREDGE 12" PUMP | Nonlabor |  |  | 1
8PD | ***PILE DRIVING*** | Nonlabor |  |  | 1
8PDE | DRIVE EXTRACTOR (ICE 28C) | Nonlabor |  |  | 1
8PDHL | LG DIESSEL HAM W/LEADS (D-100) | Nonlabor |  |  | 1
8PDHM | MD DIESSEL HAM W/LEADS (D-70) | Nonlabor |  |  | 1
8PDHS | SM DIESSEL HAM W/LEADS (D-30) | Nonlabor |  |  | 1
8PDMO | VIBRO BACKHOE HAMMER | Nonlabor |  |  | 1
8PDVL | LARGE VIBRO HAMMER ATTACH. (APE200) | Nonlabor |  |  | 1
8PDVS | SMALL VIBRO HAMMER ATTACH. (APE150) | Nonlabor |  |  | 1
8PL | ***FIXED PLANTS*** | Nonlabor |  |  | 1
8PL150 | CONCRETE BATCH PLNT 150CY/HR | Nonlabor |  |  | 1
8PL400 | CONCRETE BATCH PLNT 300CY/HR | Nonlabor |  |  | 1
8PLPM | PUGMILL 300T/HR | Nonlabor |  |  | 1
8PP | ***PORTABLE PLANTS*** | Nonlabor |  |  | 1
8PPCR | PORTABLE CRUSHER, < 400T/hr | Nonlabor |  |  | 1
8PPSC | PORTABLE SCREEN, < 400T/hr | Nonlabor |  |  | 1
8PPVR24 | CONVEYOR 24"X65' | Nonlabor |  |  | 1
8PPVR30 | CONVEYOR 30"X100' | Nonlabor |  |  | 1
8PU | ***PUMPS*** | Nonlabor |  |  | 1
8PU03E | 3" PUMP SUB ELEC | Nonlabor |  |  | 1
8PU03T | 3" PUMP TRASH | Nonlabor |  |  | 1
8PU04E | 4" PUMP SUB ELEC | Nonlabor |  |  | 1
8PU04T | 4" PUMP TRASH | Nonlabor |  |  | 1
8PU06E | 6" PUMP SUB ELEC | Nonlabor |  |  | 1
8PU06T | 6" PUMP TRASH | Nonlabor |  |  | 1
8PU12 | 12" BYPASS PUMP | Nonlabor |  |  | 1
8PU18 | 18" BYPASS PUMP | Nonlabor |  |  | 1
8RC | ***ROLLERS/COMPACTORS*** | Nonlabor |  |  | 1
8RC054 | ROLLER SOIL-54" | Nonlabor |  |  | 1
8RC084 | ROLLER SOIL 84" | Nonlabor |  |  | 1
8RC815 | COMPACTOR-SOIL CAT 815F2 | Nonlabor |  |  | 1
8RC825 | COMPACTOR-SOIL CAT 825H | Nonlabor |  |  | 1
8RCPC | PLATE COMPACTOR (12K DIESEL) | Nonlabor |  |  | 1
8RCPR | PNEUMATIC ROLLER (30 TN) | Nonlabor |  |  | 1
8RCWB | COMPACTOR - WALK BEHIND | Nonlabor |  |  | 1
8RR | ***RAILROAD/HI RAIL*** | Nonlabor |  |  | 1
8RRBC | BALLAST CAR | Nonlabor |  |  | 1
8RRBK | HI RAIL BUCKET TRUCK 50' | Nonlabor |  |  | 1
8RRBM | HI RAIL BOOM TRUCK | Nonlabor |  |  | 1
8RRBR | BALLAST REGULATOR | Nonlabor |  |  | 1
8RRCL | CLIPPER | Nonlabor |  |  | 1
8RREX | HI RAIL EXCAVATOR (CAT 318) | Nonlabor |  |  | 1
8RRFC | FLAT CAR 50' | Nonlabor |  |  | 1
8RRHR | RAIL HEATER | Nonlabor |  |  | 1
8RRLD | HI RAIL 950 LOADER | Nonlabor |  |  | 1
8RRPT | HI RAIL PLATFORM TRUCK | Nonlabor |  |  | 1
8RRPU | HI RAIL PICKUP TRUCK | Nonlabor |  |  | 1
8RRRG | RAIL GRINDER | Nonlabor |  |  | 1
8RRRT | RAIL THREADER | Nonlabor |  |  | 1
8RRSP | SPIKE PULLER | Nonlabor |  |  | 1
8RRSS | SPEED SWING | Nonlabor |  |  | 1
8RRTC | TRACK CRIBBER | Nonlabor |  |  | 1
8RRTJ | TIE JIG | Nonlabor |  |  | 1
8RRTM | TAMPER MARKIV | Nonlabor |  |  | 1
8RRTS | DYNAMIC TRACK STABALIZER | Nonlabor |  |  | 1
8RRVI | RAIL VIBRATOR | Nonlabor |  |  | 1
8SC | ***SCRAPERS/TRACTORS*** | Nonlabor |  |  | 1
8SC615 | SCRAPER PADDLE WHL CAT 615 | Nonlabor |  |  | 1
8SC621 | SCRAPER SNGL ENG CAT 621 | Nonlabor |  |  | 1
8SC623 | SCRAPER PADDLE WHL CAT 623 | Nonlabor |  |  | 1
8SC627 | SCRAPER TWIN ENG CAT 627 | Nonlabor |  |  | 1
8SC631 | SCRAPER SNGL ENG CAT 631 | Nonlabor |  |  | 1
8SC637 | SCRAPER TWIN ENG CAT 637 | Nonlabor |  |  | 1
8SC657 | SCRAPER TWIN ENG CAT 657 | Nonlabor |  |  | 1
8SCP18 | 18 CY PAN | Nonlabor |  |  | 1
8SCP21 | 21 CY PAN | Nonlabor |  |  | 1
8SCP24 | 24 CY PAN | Nonlabor |  |  | 1
8SCP33 | 33 CY PAN | Nonlabor |  |  | 1
8SCP42 | 42 CY PAN | Nonlabor |  |  | 1
8SCTRL | TRACTOR 550HP+ | Nonlabor |  |  | 1
8SCTRS | TRACTOR 200 HP | Nonlabor |  |  | 1
8SCZD | DISC ATTACHMENT | Nonlabor |  |  | 1
8ST | ***STABILIZATION/SUBBASE*** | Nonlabor |  |  | 1
8STM300 | MIXER, CAT RM300 | Nonlabor |  |  | 1
8STM500 | MIXER, CAT RM500 | Nonlabor |  |  | 1
8STSB | STONE BOX | Nonlabor |  |  | 1
8STTR | TRIMMER/PLACER | Nonlabor |  |  | 1
8T | ***OFF-HIGHWAY TRUCKS*** | Nonlabor |  |  | 1
8T730 | TRK - ARTIC 30 TON CAT 730 | Nonlabor |  |  | 1
8T735 | TRK - ARTIC 35 TON CAT 735 | Nonlabor |  |  | 1
8T740 | TRK - ARTIC 40 TON CAT 740 | Nonlabor |  |  | 1
8T745 | TRK - ARTIC 45 TON CAT 745 | Nonlabor |  |  | 1
8T770 | TRK - RIGID 45 TON CAT 770 | Nonlabor |  |  | 1
8T772 | TRK - RIGID 50 TON CAT 772 | Nonlabor |  |  | 1
8T773 | TRK - RIGID 60 TON CAT 773 | Nonlabor |  |  | 1
8T777 | TRK - RIGID 100 TON CAT 777 | Nonlabor |  |  | 1
8TH01 | DUMP TRUCK (TANDEM) | Nonlabor |  |  | 1
8TH02 | DUMP TRUCK (TRI-AXLE) | Nonlabor |  |  | 1
8TH03 | DUMP TRUCK (SEMI) | Nonlabor |  |  | 1
8TH04 | TRACTOR TRAILER (LOWBOY/FLATBED) | Nonlabor |  |  | 1
8TH05 | MECHANICS TRUCK | Nonlabor |  |  | 1
8TH06 | LUBE/FUEL TRUCK | Nonlabor |  |  | 1
8TH07 | SNOOPER TRUCK | Nonlabor |  |  | 1
8TH08 | VAC TRUCK | Nonlabor |  |  | 1
8TH09 | SWEEPER W/ VAC | Nonlabor |  |  | 1
8TH10 | BOOM TRUCK (27 TON) | Nonlabor |  |  | 1
8TH11 | CONCRETE MIXER/AGITATOR TRUCK | Nonlabor |  |  | 1
8TR | ***LIGHT TRUCKS*** | Nonlabor |  |  | 1
8TRA | ATV/QUAD/MULE | Nonlabor |  |  | 1
8TRFM | FLAT/MOT TRUCK (F750) | Nonlabor |  |  | 1
8TRPU | DIRECT PICKUP | Nonlabor |  |  | 1
8TRPUI | INDIRECT PICKUP / SUV | Nonlabor |  |  | 1
8TRTR | PICKUP TRAILER | Nonlabor |  |  | 1
8TRV | VAN / CREW BUS | Nonlabor |  |  | 1
8TX | ***TRENCHERS*** | Nonlabor |  |  | 1
8TX04 | SOIL TRENCHER 4" | Nonlabor |  |  | 1
8TX08 | ROCK TRENCHER 8" | Nonlabor |  |  | 1
8TX24 | ROCK TRENCHER 24" | Nonlabor |  |  | 1
8W | ***WELDERS*** | Nonlabor |  |  | 1
8W400 | 400 AMP WELDER | Nonlabor |  |  | 1
8W500 | 500 AMP WELDER | Nonlabor |  |  | 1
8WSW | STUD WELDER | Nonlabor |  |  | 1
8WT | ***WATER TRUCKS / WAGONS*** | Nonlabor |  |  | 1
8WT04 | WATER TRUCK 4 MG | Nonlabor |  |  | 1
8WT08 | WATER TRUCK 8MG | Nonlabor |  |  | 1
8WT10 | WATER TRUCK 10MG | Nonlabor |  |  | 1
8WTK | KLEIN WATER TANK 10MG | Nonlabor |  |  | 1
8Z | ***********Tunnel Equipment************ | Nonlabor |  |  | 1
8ZA | *** U/G VENT FANS *** | Nonlabor |  |  | 1
8ZA010 | VENT FAN - 10 HP | Nonlabor |  |  | 1
8ZA040 | VENT FAN - 40 HP | Nonlabor |  |  | 1
8ZA050 | VENT FAN - 50 HP | Nonlabor |  |  | 1
8ZA100 | VENT FAN - 100 HP | Nonlabor |  |  | 1
8ZA250 | JETAIR FAN - 250 HP | Nonlabor |  |  | 1
8ZA900 | BULKHEAD FAN | Nonlabor |  |  | 1
8ZA901 | AIR SCRUBBER W/ STACK | Nonlabor |  |  | 1
8ZB | *** U/G EXCAV BUCKETS *** | Nonlabor |  |  | 1
8ZB01 | CLAM BUCKET - 1 CY | Nonlabor |  |  | 1
8ZB02 | CLAM BUCKET - 2 CY | Nonlabor |  |  | 1
8ZB03 | CLAM BUCKET - 4 CY | Nonlabor |  |  | 1
8ZB04 | CLAM BUCKET - 8 CY | Nonlabor |  |  | 1
8ZB05 | MUCK BOX - 1 CY | Nonlabor |  |  | 1
8ZB06 | MUCK BOX - 2 CY | Nonlabor |  |  | 1
8ZB07 | MUCK BOX - 3 CY | Nonlabor |  |  | 1
8ZB08 | MUCK BOX - 4 CY | Nonlabor |  |  | 1
8ZB09 | MUCK BOX - 10 CY | Nonlabor |  |  | 1
8ZC | *** U/G CRANES *** | Nonlabor |  |  | 1
8ZCC150 | 150T (LIEBHERR 885) | Nonlabor |  |  | 1
8ZCC200 | 200T (LIEBHERR 895) | Nonlabor |  |  | 1
8ZCC500 | 500T CRAWLER (16000) | Nonlabor |  |  | 1
8ZCG050 | 50T GANTRY CRANE | Nonlabor |  |  | 1
8ZCG075 | 75T GANTRY CRANE | Nonlabor |  |  | 1
8ZCT025 | 25T TOWER CRAN (MD485) | Nonlabor |  |  | 1
8ZCT050 | 50T TOWER CRAN (MD650) | Nonlabor |  |  | 1
8ZCX001 | DRUM HOIST | Nonlabor |  |  | 1
8ZCX050 | STRADDLE CARRIER, 30T | Nonlabor |  |  | 1
8ZCZ001 | OSCILLATOR ATTACHMENT | Nonlabor |  |  | 1
8ZD | *** U/G DRILLS *** | Nonlabor |  |  | 1
8ZD01 | JACKLEG | Nonlabor |  |  | 1
8ZD02 | 2" HYD TRACK DRILL | Nonlabor |  |  | 1
8ZD03 | 4" HYD TRACK DRILL | Nonlabor |  |  | 1
8ZD04 | 4" AIR TRACK DRILL | Nonlabor |  |  | 1
8ZD05 | 4-8" ROTARY DRILL RIG | Nonlabor |  |  | 1
8ZD06 | 12-24" ROTARY DRILL RIG | Nonlabor |  |  | 1
8ZD07 | 36-48" ROTARY DRILL RIG | Nonlabor |  |  | 1
8ZD08 | 2 BOOM JUMBO | Nonlabor |  |  | 1
8ZD09 | 3 BOOM JUMBO | Nonlabor |  |  | 1
8ZD10 | 2 BOOM SHAFT JUMBO | Nonlabor |  |  | 1
8ZD11 | 3 BOOM SHAFT JUMBO | Nonlabor |  |  | 1
8ZD12 | CORE DRILL | Nonlabor |  |  | 1
8ZD13 | ROOF BOLTER | Nonlabor |  |  | 1
8ZE | *** U/G EXCAVATORS *** | Nonlabor |  |  | 1
8ZE138 | EXCV 0 SWING 30K# (PC138) | Nonlabor |  |  | 1
8ZE228 | EXCV 0 SWING 50K# (PC228) | Nonlabor |  |  | 1
8ZE800 | BROKK EXCV | Nonlabor |  |  | 1
8ZE924 | LIEBHERR 924 TUNNEL | Nonlabor |  |  | 1
8ZE944 | LIEBHERR 944 TUNNEL | Nonlabor |  |  | 1
8ZE950 | LIEBHERR 950 TUNNEL | Nonlabor |  |  | 1
8ZF | *** U/G FORKLIFTS *** | Nonlabor |  |  | 1
8ZF010 | MAST FORKLIFT 10T | Nonlabor |  |  | 1
8ZF020 | MAST FORKLIFT 20T | Nonlabor |  |  | 1
8ZF040 | MAST FORKLIFT 40T | Nonlabor |  |  | 1
8ZG | *** U/G COMP/GENERATORS *** | Nonlabor |  |  | 1
8ZG0750 | ELEC COMP 750 CFM | Nonlabor |  |  | 1
8ZG0800 | ELEC COMP 1300 CFM | Nonlabor |  |  | 1
8ZG1000 | GENERATOR 1000 KW | Nonlabor |  |  | 1
8ZG1500 | GENERATOR 1500 KW | Nonlabor |  |  | 1
8ZG2000 | GENERATOR 2000 KW | Nonlabor |  |  | 1
8ZH | *** U/G ROADHEADERS *** | Nonlabor |  |  | 1
8ZH025 | 25T ROADHEADER | Nonlabor |  |  | 1
8ZH050 | 50T ROADHEADER | Nonlabor |  |  | 1
8ZH100 | 100 T ROADHEADER | Nonlabor |  |  | 1
8ZH150 | 150 T ROADHEADER | Nonlabor |  |  | 1
8ZH900 | EXCV. ROADHEADER ATT. | Nonlabor |  |  | 1
8ZL | *** U/G LOCIS *** | Nonlabor |  |  | 1
8ZL08 | 8T DIESEL LOCOMOTIVE | Nonlabor |  |  | 1
8ZL15 | 15T DIESEL LOCOMOTIVE | Nonlabor |  |  | 1
8ZL20 | 20T DIESEL LOCOMOTIVE | Nonlabor |  |  | 1
8ZL35 | 35T DIESEL LOCOMOTIVE | Nonlabor |  |  | 1
8ZL50 | U/G MSV | Nonlabor |  |  | 1
8ZL80 | MANTRIP CAR | Nonlabor |  |  | 1
8ZL81 | FLAT CAR 5 TON | Nonlabor |  |  | 1
8ZL82 | FLAT CAR 10 TON | Nonlabor |  |  | 1
8ZL83 | MIXER CAR 5CY | Nonlabor |  |  | 1
8ZL84 | MIXER CAR 10CY | Nonlabor |  |  | 1
8ZL85 | MUCK CAR 3 CY | Nonlabor |  |  | 1
8ZL86 | MUCK CAR 5 CY | Nonlabor |  |  | 1
8ZL87 | MUCK CAR 8 CY | Nonlabor |  |  | 1
8ZM | *** U/G MUCKERS *** | Nonlabor |  |  | 1
8ZM03 | LHD LOADER 3.5CY | Nonlabor |  |  | 1
8ZM06 | LHD LOADER 6CY | Nonlabor |  |  | 1
8ZM08 | LHD LOADER 8CY | Nonlabor |  |  | 1
8ZM10 | LHD LOADER 10CY | Nonlabor |  |  | 1
8ZM15 | LOADER 15CY (CAT 992K) | Nonlabor |  |  | 1
8ZN | *** U/G PILE *** | Nonlabor |  |  | 1
8ZN01 | DELMAG 66K# HYD PILE HAMMR | Nonlabor |  |  | 1
8ZN02 | DELMAG 122K# HYD PILE HAMMR | Nonlabor |  |  | 1
8ZN03 | SWINGING LEADS | Nonlabor |  |  | 1
8ZN04 | SONIC SIDE GRIP SP100 HAMMER | Nonlabor |  |  | 1
8ZN05 | AMERICAN 50 VIBRO, 50T | Nonlabor |  |  | 1
8ZN06 | AMERICAN 150 VIBRO, 120T | Nonlabor |  |  | 1
8ZO | *** U/G PUMPS *** | Nonlabor |  |  | 1
8ZO01 | GODWIN 18" | Nonlabor |  |  | 1
8ZO02 | CAT 20" | Nonlabor |  |  | 1
8ZO03 | RAIN 4 RENT 24" | Nonlabor |  |  | 1
8ZO04 | 13 HP HEADING PUMP | Nonlabor |  |  | 1
8ZO05 | DEEPWELL PUMP | Nonlabor |  |  | 1
8ZO06 | SHAFT FLYGT PUMP, SM | Nonlabor |  |  | 1
8ZO07 | SHAFT FLYGT PUMP, LG | Nonlabor |  |  | 1
8ZP | *** U/G BATCH PLANTS *** | Nonlabor |  |  | 1
8ZP01 | LIEBHERR BATCH PLNT 50CY/HR | Nonlabor |  |  | 1
8ZP02 | CONCRETE BATCH PLNT 150CY/HR | Nonlabor |  |  | 1
8ZP03 | GROUT BATCH PLANT | Nonlabor |  |  | 1
8ZP04 | CEMENT SILO 84T | Nonlabor |  |  | 1
8ZQ | *** U/G CONCRETE *** | Nonlabor |  |  | 1
8ZQ01 | CONCRETE LINE PUMP | Nonlabor |  |  | 1
8ZQ02 | CONCRETE REMIXER | Nonlabor |  |  | 1
8ZQ03 | TUNNEL ARCH FORM TRAVELER | Nonlabor |  |  | 1
8ZQ04 | TRAVELER JUMBO | Nonlabor |  |  | 1
8ZQ05 | SHOTCRETE PUMP | Nonlabor |  |  | 1
8ZQ06 | SHOTCRETE ROBOT | Nonlabor |  |  | 1
8ZS | *** U/G SLURRY SYSTEM *** | Nonlabor |  |  | 1
8ZS01 | SLURRY SEP. PLANT, BUY | Nonlabor |  |  | 1
8ZS02 | FILTER PRESS, BUY | Nonlabor |  |  | 1
8ZS03 | CENTRIFUGE, BUY | Nonlabor |  |  | 1
8ZS04 | SLURRY PUMP, BUY | Nonlabor |  |  | 1
8ZT | *** U/G TBMS *** | Nonlabor |  |  | 1
8ZT01 | TUNNEL BORING MACHIN, BUY | Nonlabor |  |  | 1
8ZT03 | MICRO TBM, BUY | Nonlabor |  |  | 1
8ZT05 | XPASS TBM, BUY | Nonlabor |  |  | 1
8ZT07 | VERTICAL SHAFT MACH, BUY | Nonlabor |  |  | 1
8ZT09 | EVAPCO COOLING TOWER | Nonlabor |  |  | 1
8ZT10 | HYPERBARIC TUNNEL EQUIPMENT | Nonlabor |  |  | 1
8ZT11 | MANLOCK FOR HYPERBARIC | Nonlabor |  |  | 1
8ZV | *** U/G CONVEYORS *** | Nonlabor |  |  | 1
8ZV01 | CONTINUOUS CONVR, BUY | Nonlabor |  |  | 1
8ZV02 | VERTICAL CONVEY, BUY | Nonlabor |  |  | 1
8ZV03 | LAND CONVEYOR, BUY | Nonlabor |  |  | 1
8ZV04 | RADIAL STACKER, BUY | Nonlabor |  |  | 1
8ZW | *** U/G WATER TREATMENT *** | Nonlabor |  |  | 1
8ZW01 | WTREAT PLANT 250GPM, BUY | Nonlabor |  |  | 1
8ZW02 | WTREAT PLANT 500GPM, BUY | Nonlabor |  |  | 1
8ZW03 | WTREAT PLANT 1000GPM, BUY | Nonlabor |  |  | 1
8ZW07 | BAKER TANK | Nonlabor |  |  | 1
8ZW08 | SAND FILTERS | Nonlabor |  |  | 1
8ZW09 | CARBON FILTERS | Nonlabor |  |  | 1
8ZX | *** U/G SHAFTS *** | Nonlabor |  |  | 1
8ZX01 | ALIMAK SHAFT ELEVATOR | Nonlabor |  |  | 1
8ZX02 | SHAFT LIGHTING | Nonlabor |  |  | 1
8ZX03 | SHAFT STAIRTOWER | Nonlabor |  |  | 1
8ZX04 | SHAFT MAN CAGE | Nonlabor |  |  | 1
8ZX05 | SHAFT FAB'D LADDER | Nonlabor |  |  | 1
8ZX06 | SHAFT COVER | Nonlabor |  |  | 1
8ZX07 | SHAFT HANDRAIL | Nonlabor |  |  | 1
8DDICS | Disc / Harrows | Nonlabor |  |  | 1
3429 | 3429 - Kuwahee WWTP | Nonlabor |  |  | 1
3417-54240 | Temp Pave Markers 1 Way | Material | Each |  | 8
3418-112 | 12'X10' BOX CULVERT | Material | Each |  | 8
3418-131 | MTBBC3 (MASH) Thrie BeamBR Conn TL#3 | Material | Each |  | 8
3418-132 | MT3 Leading end treatment TL3 | Material | Each |  | 8
3418-133 | Impact Attenuator | Material | Each |  | 8
3418-07 | Project Managment (Construction | Material | Unit |  | 8
CY.ELEV | Elevator Crew | Labor |  |  | 1
CY.WHEEL | Wheel Truing Machine Crew | Labor |  |  | 1
CY.LIFT | Truck Lift Crew | Labor |  |  | 1
CY.WASH | Train Wash Crew | Labor |  |  | 1
CY.CRANE | Crane Installation Crew | Labor |  |  | 1
CY.MASON | Masonry Crew | Labor |  |  | 1
CY.GLAZ | Glass & Glazer Crew | Labor |  |  | 1
CY.WATER | Waterproofing Crew | Labor |  |  | 1
CY.MECH | Mechanical Crew | Labor |  |  | 1
CY.PLUMB | Plumbing Crew | Labor |  |  | 1
CY.PAINT | Painting Crew | Labor |  |  | 1
CY.TILE | Tile & Flooring Crew | Labor |  |  | 1
CY.ROOF | Roofing Crew | Labor |  |  | 1
CY.GYP | Gypsum/CFMF Crew | Labor |  |  | 1
CY.PANEL | Metal Panel Crew | Labor |  |  | 1
CY.DRILLER | Drilling Crew | Labor |  |  | 1
CY.TEST | Test Pit Crew | Labor |  |  | 1
CY.STEEL | Steel Crew | Labor |  |  | 1
CY.MISC | Misc. Metals Crew | Labor |  |  | 1
CY.ELEC-A | Electrician Crew | Labor |  |  | 1
CY.CARP | Carpentry Crew | Labor |  |  | 1
CY.RR-WE | Track Crew Weekend Outage | Labor |  |  | 1
CY.RR-WD | Track Crew Weekday | Labor |  |  | 1
CY.BOOTH | Paint Booth Crew | Labor |  |  | 1
CY.CONC | Concrete Crew | Labor |  |  | 1
CY.DEMO | Demolition Crew | Labor |  |  | 1
CY.CEIL | Ceiling Crew | Labor |  |  | 1
CY.DOOR | Door Crew | Labor |  |  | 1
CY.FENCE | Fencing Crew | Labor |  |  | 1
CY.SRAY | Spray Fire Proofing | Labor |  |  | 1
CY.LAND | Landscaping Crew | Labor |  |  | 1
CY.LINING | Conduit Cleaning & Lining Crew | Labor |  |  | 1
CY.LABOR | General Laborer Crew | Labor |  |  | 1
CY.SRVY | Survey Crew | Labor |  |  | 1
CY.SITE | Sitework Crew | Labor |  |  | 1
CY.SOE | Support of Excavation Crew | Labor |  |  | 1
CY.EX-UTILITY | Utility Excavation & Installation Crew | Labor |  |  | 1
CY.FLAT | Flatwork Crew | Labor |  |  | 1
CY.MARK | Pavement Marking Crew | Labor |  |  | 1
CY.PAVE | Paving Crew | Labor |  |  | 1
CY.REBAR | Rebar Crew | Labor |  |  | 1
CY.0212170 | Remove Obstructions | Material | Cubic Yard |  | 8
CY.0130429 | Traffic Officers Services | Nonlabor |  |  | 0
CY.0213202 | Rodent Control | Nonlabor |  |  | 0
CY.0222027 | Material Removal | Nonlabor |  |  | 0
CY.0222087 | Pipeline Cleaning | Nonlabor |  |  | 0
CY.0222108 | Rock Excavation | Material | Cubic Yard |  | 8
CY.0222119 | Unsuitable Excavation | Material | Cubic Yard |  | 8
CY.0222442 | Test Pits | Material | Cubic Yard |  | 8
CY.0227007 | Filter Fabric | Material | Square Yard |  | 8
CY.0310049 | Concrete Cleaning & Restoration | Material | Square Feet |  | 8
CY.0354009 | Structural Crack Repair | Material | Linear Feet |  | 8
CY.6500000 | Risk Allowance | Nonlabor |  |  | 0
CY.0130174 | Maintenance Facility | Nonlabor |  |  | 0
CY.0275000 | Yard Improvements | Nonlabor |  |  | 0
CY.ELEC-B | Electrician Crew | Labor |  |  | 1
ST-BRIDGE-SUB | Substructure Crew | Labor |  | Structures Crew | 1
ST-BRIDGE-SUP | Super-Structure Crew | Labor |  | Structures Crew | 1
ST-RUB | Rub & Patch Crew | Labor |  |  | 1
ST-WELD | Structural Welding Crew | Labor |  |  | 1
SUB-TRACK | Sub - Railroad Track Crew | Labor |  |  | 1
3418-167 | Subcontractor Mobilization | Material | Unit |  | 8
3418-168 | Pave Asphalt Under Guardrail | Material |  |  | 8
3434-432 | 13" Port Conc Pavement, Ramps (with Dowels) | Material | Square Yard |  | 8
3434-434 | 13" Port Conc Pavement, Shoulders (w/o Dowels) | Material | Square Yard |  | 8
3434-427 | 42" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3434-431 | 18" RC Pipe Culverts, Class V | Material | Linear Feet |  | 8
3434-426 | 15" RC Pipe Culverts, Class V | Material | Linear Feet |  | 8
3434-435 | Concrete Barrier, Type T3 | Material | Linear Feet |  | 8
3418-169 | REMOVAL & DISPOSAL OF EXISTING BRIDGE - SC5/198 | Material | Each |  | 8
3418-170 | REMOVAL & DISPOSAL OF EXISTING BRIDGE - S99 | Material | Each |  | 8
3418-171 | REMOVAL & DISPOSAL OF EXISTING BRIDGE - US29 | Material | Each |  | 8
3418-172 | SUBSTRUCTURE CLASS 4000 - SC-5 | Material | Cubic Yard |  | 8
3418-173 | SUBSTRUCTURE CLASS 4000 - S-99 | Material | Cubic Yard |  | 8
3418-174 | SUBSTRUCTURE CLASS 4000 - US-29 | Material | Cubic Yard |  | 8
8BH440 | CAT 420-450 | Nonlabor |  |  | 1
3434-430 | 5'" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3434-429 | 5'" Dia Drilled Piers in Soil | Material |  |  | 8
3434-428 | FRAME W/ 2 GRATES STD. 840.22 | Material |  |  | 8
3329-643 | SA 26 - Presence Lighting | Material | Lump Sum |  | 8
3329-644 | SA 33 - Pervious Concrete | Material | Lump Sum |  | 8
3329-645 | SA 35 - Roundabout Caps | Material | Lump Sum |  | 8
3329-646 | SA 36 - Select Tree Removal "Permit Site 4" | Material | Lump Sum |  | 8
C43-BP4-ROA-U0-11.1.1 | Preliminary Site Work | Material |  |  | 8
C43-BP4-ROA-U0-11.1.2 | General Conditions | Material |  |  | 8
C43-BP4-ROA-U0-11.1.3 | Submittal Prep, Review & Acceptance | Material |  |  | 8
C43-BP4-ROA-U0-11.1.4 | 90 Day Schedule (Bond Only) | Material |  |  | 8
C43-BP4-ROA-U0-11.1.5 | Procurement | Material |  |  | 8
C43-BP4-ROA-U0-11.1.6 | Perimeter Canal / Townsend Canal | Material |  |  | 8
C43-BP4-ROA-U0-11.1.7 | Roadways | Material |  |  | 8
C43-BP4-ROA-U0-11.1.8 | Proof Of Concept | Material |  |  | 8
C43-BP4-ROA-U0-11.1.9 | Intake Canals | Material |  |  | 8
C43-BP4-ROA-U0-11.1.10 | Work Arounds | Material |  |  | 8
C43-BP4-ROA-U0-11.1.11 | Gap Closures | Material |  |  | 8
C43-BP4-ROA-U0-11.1.12 | Demolition | Material |  |  | 8
C43-BP4-ROA-U0-11.1.13 | Structures | Material |  |  | 8
C43-BP4-ROA-U0-11.1.14 | Foundation Prep & Select Fill | Material |  |  | 8
C43-BP4-ROA-U0-11.1.15 | Soil-Bentonite Wall | Material |  |  | 8
C43-BP4-ROA-U0-11.1.16 | Dam Embankment +47 | Material |  |  | 8
C43-BP4-ROA-U0-11.1.17 | Dam Embankment Setlement Phase I | Material |  |  | 8
C43-BP4-ROA-U0-11.1.18 | Dam Embankment +53 | Material |  |  | 8
C43-BP4-ROA-U0-11.1.19 | Dam Embankment Setlement Phase II | Material |  |  | 8
C43-BP4-ROA-U0-11.1.20 | Sepage Collection Drain | Material |  |  | 8
C43-BP4-ROA-U0-11.1.21 | Toe Protection - Soil Cement Phase I | Material |  |  | 8
C43-BP4-ROA-U0-11.1.22 | Slope Protection - Soil Cement Phase II | Material |  |  | 8
C43-BP4-ROA-U0-11.1.23 | Crest Protection - Soil Cement Phase III | Material |  |  | 8
C43-BP4-ROA-U0-11.1.24 | Wave Walls | Material |  |  | 8
C43-BP4-ROA-U0-11.1.25 | Asphalt | Material |  |  | 8
C43-BP4-ROA-U0-11.XX | Finishing Work | Material |  |  | 8
C43-BP4-ROA-U0-11.XXX | Demobilization | Material |  |  | 8
C43-BP4-ROA-U0-11.X | Erosion Control | Material |  |  | 8
SUB-EW-SLURRY | Sub - Soil Bentonite Slurry Wall Crew | Labor |  |  | 1
3418-Bid | 3418 - Bid Revenue | Nonlabor |  |  | 1
3418-CO | 3418 - Change Orders | Nonlabor |  |  | 1
3418-0051 | 3418-0051 - Partnering Session # 1 | Material | Lump Sum |  | 8
3418-0052 | 3418-0052 - Mill Creek Design Exception | Material | Lump Sum |  | 8
3418-0053 | 3418-0053 - US 29 Left Turn Storage Design Exception | Material | Lump Sum |  | 8
3428-001.1 | SA 1 - IMR, Field Office, and Management Staff | Material | Lump Sum |  | 8
3428-SA | 3428 - Supplemental Agreements | Nonlabor |  |  | 1
3428-Rev | 3428 - Original Bid Revenue | Nonlabor |  |  | 1
2300126 | 2300126 - C13 VDOT | Nonlabor |  |  | 1
2300126-01 | Concrete Foundation CF-2 | Material | Each |  | 8
2300126-02 | 4 Conductor Cable | Material | Linear Feet |  | 8
2300126-03 | 6 Conductor Cable | Material | Linear Feet |  | 8
2300126-04 | 8 Conductor Cable | Material | Linear Feet |  | 8
2300126-05 | Concrete Foundation LF-1 Type A | Material | Each |  | 8
2300126-06 | Concrete Foundation High Mast Light Pole | Material | Cubic Yard |  | 8
2300126-07 | Lighting Pole LP-2 Type F | Material | Each |  | 8
2300126-08 | Lighting Pole LP-2 Type G | Material | Each |  | 8
2300126-09 | Lighting Pole LP-3 Type 4 | Material | Each |  | 8
2300126-10 | Electrical Service SE-8 Type A | Material | Each |  | 8
2300126-11 | Electrical Service SE-9 Type A | Material | Each |  | 8
2300126-12 | Control Center CCW-1 Type G | Material | Each |  | 8
2300126-13 | Control Center CCW-1 Type H | Material | Each |  | 8
2300126-14 | Junction Box JB-S1 | Material | Each |  | 8
2300126-15 | Junction Box JB-S3 | Material | Each |  | 8
2300126-16 | Electrical Service Grounding Electrode 10' | Material | Each |  | 8
2300126-17 | Bored Conduit 2" | Material | Linear Feet |  | 8
2300126-18 | 2" PVC Conduit | Material | Linear Feet |  | 8
2300126-19 | Trench Excavation ECI-1 | Material | Linear Feet |  | 8
2300126-20 | Test Bore | Material | Each |  | 8
2300126-21 | LIGHTING Conventional Luminaire (310 W-LED) | Material | Each |  | 8
2300126-22 | LIGHTING High Mast Luminaire (500 W-LED) | Material | Each |  | 8
2300126-23 | LIGHTING High Mast Ring Assembly (3-Luminaire LED) | Material | Each |  | 8
2300126-24 | LIGHTING Modify Existing Junction Box | Material | Each |  | 8
2300126-25 | LIGHTING Remove Existing Conductor Cable | Material | Linear Feet |  | 8
3422 - 4029 | CO#10 - Support Of Excavation | Material | Lump Sum |  | 8
3422 - 5031 | CO#10 - Thermoplastic Rumble Strips & Yield Sign | Material | Lump Sum |  | 8
SUB-ST-SOLDIER | Sub - Soldier Pile/Ground Anchor Crew | Labor |  |  | 1
9161-Cost | C-43 Cost Resources | Nonlabor |  |  | 1
3425 Labor | 3425 - Cabot Yard Labor Resources | Labor |  |  | 1
C43-MAINT EMB | C43 - Maintenance Road Embankment Crew | Labor |  |  | 1
C43-STRIP | C43 - Perimeter Canal Strip & Place Topsoil Crew | Labor |  |  | 1
C43-PLUG | C43 - Select Fill Plug Crew - foundation lift | Labor |  |  | 1
C43-SUB-CTA | C43 - Sub - Stabilized Subgrade Crew | Labor |  |  | 1
C43-STR EW | C43 - Mics Small Earthwork Crew / Structural | Labor |  |  | 1
C43-ABC | C43 - Agg Base Crew | Labor |  |  | 1
C43-PAD | C43 - Soil Bentonite Work Pad Crew | Labor |  |  | 1
C43-TOPSOIL | C43 - Perm Erosion Control Measures - Topsoil | Labor |  |  | 1
C43-RECOMPACT | C43 - Grade & Recompaction Crew | Labor |  |  | 1
C43-SLOPE RECOMPACT | C43 - Grade & Recompaction Slopes Crew | Labor |  |  | 1
C43-CREST RECOMPACT | C43 - Grade & Recompaction Crest Crew | Labor |  |  | 1
C43-RAMP RECOMPACT | C43 - Grade & Recompaction Ramps Crew | Labor |  |  | 1
C43-TOE TRENCH | C43 - Dam Toe Protection Prep Crew | Labor |  |  | 1
C43-SUB-SHELL ROCK | C43 - Sub - Shell Rock Base Crew | Labor |  |  | 1
C43-CHIMNEY | C43 - Chimney Drain Crew | Labor |  |  | 1
C43-BLANKET | C43 - Dam Blanket Drain & Protection Crew | Labor |  |  | 1
C43-SLOPE SAND | C43 - Dam Sand & Seepage Drain Crew | Labor |  |  | 1
C43-RIP RAP | C43 - Rip Rap Placement Crew | Labor |  |  | 1
C43-PRS EW | C43 - Earthwork & Drainage for Sand Column Crew | Labor |  |  | 1
C43-SEED | C43 - Seeding Crew | Labor |  |  | 1
C43-SOIL CEMENT | C43 - Dam Soil Cement Crew | Labor |  |  | 1
C43-DRAIN | C43 - Storm Drain / Cross Drain Crew | Labor |  |  | 1
C43-DEMO | C43 - Demolition Crew | Labor |  |  | 1
C43-E&S | C43 - Erosion Control Crew | Labor |  |  | 1
C43-DEWATER | C43 - Cofferdam Dewatering Crew | Labor |  |  | 1
C43-TRAFFIC | C43 - Traffic Control Crew | Labor |  |  | 1
C43-SURVEY | C43 - Survey Crew | Labor |  |  | 1
C43-WAVE WALL | C43 - Wave Wall Crew | Labor |  |  | 1
C43-WAVE ANCHOR | C43 - Wave Wall Anchor Crew | Labor |  |  | 1
C43-WAVE INSTAL | C43 - Wave Wall Placement Crew | Labor |  |  | 1
C43-SUB | C43 - Sub Contractor Crews | Labor |  |  | 1
C43-SUB-BENONITE | C43 - Sub - Soil Bentonite Crew | Labor |  |  | 1
C43-SUB-ASPHALT | C43 - Sub - Asphalt Paving Crew | Labor |  |  | 1
C43-SUB-STUCTURE | C43 - Sub - Structures Crew | Labor |  |  | 1
C43-SUB-BRIDGE | C43 - Sub - Bridge Crew | Labor |  |  | 1
C43-SUB-GROOVE | C43 - Sub - Bridge Grooving | Labor |  |  | 1
C43-SUB-SAND RELIEF | C43 - Sub - Sand Relief Column Crew | Labor |  |  | 1
C43-SUB-SHEET | C43 - Sub - Sheet Pile Crew | Labor |  |  | 1
C43-SUB-DAM STRUCTURE | C43 - Sub - Dam & Canal Structure Crew | Labor |  |  | 1
C43-SUB-ELEC | C43 - Sub - Electrical Installation Crew | Labor |  |  | 1
C43-SUB-MECH | C43 - Sub - Mechanical Equiment Crew | Labor |  |  | 1
C43-SUB-LANDSCAPE | C43 - Sub - Landscaping Crew | Labor |  |  | 1
C43-SUB-G-RAIL | C43 - Sub - Guardrail Crew | Labor |  |  | 1
C43-SUB-SIGN | C43 - Sub - Signing Crew | Labor |  |  | 1
C43-SUB-FENCE | C43 - Sub - Fencing Crew | Labor |  |  | 1
C43-SUB-MAINT BLD | C43 - Sub - Install Maintenance Buildings | Labor |  |  | 1
C43-SUB-FLATWORK | C43 - Sub - Concrete Flatwork Crew | Labor |  |  | 1
C43-SUB-MONITOR | C43 - Sub - Monitoring Crew | Labor |  |  | 1
C43-Crew | C43 - Crew Resources | Labor |  |  | 1
C43-SUB-STRIPE | C43 - Sub - Striping Crew | Labor |  |  | 1
9156-REV | 9156 - R-2828 Triangle Expressway REVENUE | Material |  |  | 8
9156-SA | Supplemental Aggrements | Material |  |  | 8
9156-SOV | Schedule Of Values | Material |  |  | 8
9156-SA04 | SA#04 - Phase 1 septic evaluation | Material | Lump Sum |  | 8
9156-SA03 | SA#03 - Escalation Cost due to delay receive unlimited NTP | Material | Lump Sum |  | 8
ST-SOUND | Sound Wall Crew | Labor |  | Wall Crew | 1
3448 | 3448 - West Ship Canal CSO | Nonlabor |  |  | 1
ST-COPING | Retaining Wall Coping / Railing Crew | Labor |  | Wall Crew | 1
9156-SM | Stored Materials | Material |  |  | 8
9156-SM-2 | H-Pile Stored Material | Material | Linear Feet |  | 8
9156-SM-1 | H-Pile Stored Material | Material | Linear Feet |  | 8
3417-621-Temp | B-621 | Material | Lump Sum |  | 8
9156-SA05 | SA#05 - Lighting Design Credit | Material | Lump Sum |  | 8
9156-SA06 | SA#06 - New Bethel Aesthetic Elimination | Material | Lump Sum |  | 8
9156-SA07 | SA#07 - Bridge 3&8 Fence Elimintatino | Material | Lump Sum |  | 8
9156-SA08 | SA#08 - Additional Aux Lane for Ramp FLYCC | Material |  |  | 8
9156-SA09 | SA#09 - Septic Field Evaluations | Material |  |  | 8
3425 - Lane Crews | 3425 - Lane Crews | Labor |  |  | 1
3425 - Sub Crews | 3425 - Sub Crews | Labor |  |  | 1
WO | 3404 - Work Orders | Nonlabor |  |  | 1
3404-WO-07 | WO #07 - Additional Redesign Efforts (Lighting, Easement, Custis Trail, W&OD Trail) | Material | Lump Sum |  | 8
3404-WO-06 | WO #06 - NS Signal Pole Mast Arm Extension (Design & Construction) | Material | Lump Sum |  | 8
3404 WO-05 | WO #05 - NS Asphalt Build Up (Design & Construction) | Material | Lump Sum |  | 8
EW-STR | Structural Earthwork Crew | Labor |  |  | 1
EW-STAB | Subgrade Stabilization Crew | Labor |  |  | 1
ST-ABUT | Abutment Crew | Labor |  | Structures Crew | 1
ST-FORM | Structure Form Crew | Labor |  |  | 1
ST-POUR | Structural Pour Crew | Labor |  |  | 1
ST-PAINT | Structural Painting Crew | Labor |  |  | 1
ST-SECANT | Secant Pile Crew | Labor |  | Wall Crew | 1
ST-SOLDIER | Soldier Pile Crew | Labor |  | Wall Crew | 1
ST-BLD-UGMECH | Underground Mechanical Crew | Labor |  |  | 1
RAILWAY | Railway Crews | Labor |  |  | 1
BALLAST | Railway Ballast Crew | Labor |  |  | 1
TRACK | Railway Track Crew | Labor |  |  | 1
UT-ELEC | Electrical Installation Crew | Labor |  |  | 1
TUNNEL | Tunneling Crews | Labor |  |  | 1
JET GROUT | Jet Grouting Crew | Labor |  |  | 1
TUNNEL CONC | Tunnel Concrete Crew | Labor |  |  | 1
SHAFT EXC | Shaft Excavation Crew | Labor |  |  | 1
D&B | Tunnel Drill & Blast Crew | Labor |  |  | 1
MTBM | MTBM Tunneling Crew | Labor |  |  | 1
TBM | TBM Tunneling Crew | Labor |  |  | 1
SUB-EW-DEWATER | Sub - Dewatering Crew | Labor |  |  | 1
SUB-ST-SECANT | Sub - Secant Wall Crew | Labor |  |  | 1
SUB-ST-FORM | Sub - Concrete Form Crew | Labor |  |  | 1
SUB-ST-POUR | Sub - Concrete Pour Crew | Labor |  |  | 1
SUB-ST-MICRO | Sub - Micro Pile Crew | Labor |  |  | 1
SUB-ST-SHOTCRETE | Sub - Shotcrete Crew | Labor |  |  | 1
SUB-BLD-ABATE | Sub - Abatement Crew | Labor |  |  | 1
SUB-BLD-CONC | Sub - Building Concrete Crew | Labor |  |  | 1
SUB-BLD-FRAME | Sub - Framing Crew | Labor |  |  | 1
SUB-BLD-INSUL | Sub - Insulation Crew | Labor |  |  | 1
SUB-BLD-SIDING | Sub - Siding Crew | Labor |  |  | 1
SUB-BLD-PLUMB | Sub - Plumbing Crew | Labor |  |  | 1
SUB-BLD-DOOR | Sub - Door Crew | Labor |  |  | 1
SUB-BLD-FINISH | Sub - Finishes Crew | Labor |  |  | 1
SUB-BLD-CEILING | Sub - Ceiling Crew | Labor |  |  | 1
SUB-BLD-ELEV | Sub - Elevator Crew | Labor |  |  | 1
SUB-BLD-FIREPF | Sub - Fireproofing Crew | Labor |  |  | 1
SUB-BLD-METALS | Sub - Misc. Metals Crew | Labor |  |  | 1
SUB-BLD-TILE | Sub - Tile Crew | Labor |  |  | 1
SUB-BLD-MILWORK | Sub - Milwork Crew | Labor |  |  | 1
SUB-BLD-WTPROOF | Sub - Waterproof Crew | Labor |  |  | 1
SUB-TRUING | Sub - Wheel Truing Crew | Labor |  |  | 1
SUB-BALLAST | Sub - Rail Ballast Crew | Labor |  |  | 1
SUB-WASH | Sub - Train Wash Crew | Labor |  |  | 1
SUB-CRANE | Sub - Crane Crew | Labor |  |  | 1
SUB-LIFT | Sub - Truck Lift Crew | Labor |  |  | 1
SUB-BOOTH | Sub - Paint Booth Crew | Labor |  |  | 1
SUB-RAILWAY | Sub - Railway Crews | Labor |  |  | 1
SUB-TUNNEL | Sub - Tunneling Crew | Labor |  |  | 1
9156-FA | 9156 - Fuel Adjustments | Material | Unit |  | 8
3433.I.100 | Mobilization - 10% | Material | Lump Sum |  | 8
3433.I.101 | Design Fee | Material | Lump Sum |  | 8
3433.I.102 | Bonds, Insurances, Success Fee, D/B Team Setup | Material | Lump Sum |  | 8
3433.I.103 | Construction Surveying | Material | Lump Sum |  | 8
3433.I.104 | Generic Miscellaneous Item Camera Existing Pipes | Material | Linear Feet |  | 8
3433.I.105 | HP12X53 Steel Piles | Material | Linear Feet |  | 8
3433.I.106 | 4'-0" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3433.I.107 | 4'-0" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3433.I.108 | Type I Standard Approach Fill Area 5 | Material | Cubic Yard |  | 8
3433.I.109 | Unclassified Structure Excavation Area 5 | Material | Cubic Yard |  | 8
3433.I.110 | Class A Concrete (Bridge) Substructure | Material | Cubic Yard |  | 8
3433.I.111 | Bridge Approach Slab, Station **** | Material | Square Feet |  | 8
3433.I.112 | Reinforced Concrete Deck Slab | Material | Square Feet |  | 8
3433.I.113 | 54" Prestressed Concrete Girders FIBS | Material | Linear Feet |  | 8
3433.I.114 | Generic Structure Item, Bridge Superstructure Slide | Material | Each |  | 8
3433.I.115 | Approx 859,104 LBS Structural Steel | Material | LB |  | 8
3433.I.116 | Pot Bearings | Material | Each |  | 8
3433.I.117 | Elastomeric Bearings | Material | Each |  | 8
3433.I.118 | Foam Joint Seals | Material | Linear Feet |  | 8
3433.I.119 | Expansion Joint Seals | Material | Linear Feet |  | 8
3433.I.120 | Grooving Bridge Floors | Material | Square Feet |  | 8
3433.I.121 | Waterproofing/Dampproofing | Material | Square Yard |  | 8
3433.I.122 | Concrete Barrier Rail 42" | Material | Linear Feet |  | 8
3433.I.123 | Reinforcing Steel (Bridge) | Material | LB |  | 8
3433.I.124 | Soldier Pile Retaining Walls | Material | Square Feet |  | 8
3433.I.125 | Generic Miscellaneous Item Building Demolition | Material | Square Feet |  | 8
3433.I.126 | Asphalt Conc Base Course, Type B25.0C Temporary | Material | Ton |  | 8
3433.I.127 | Asphalt Conc Surface Course, Type S9.5C Temporary | Material | Ton |  | 8
3433.I.128 | Generic Grading Item, Unclassified Excavation for Temp Pavement | Material | Cubic Yard |  | 8
3433.I.129 | Generic Pipe Item Temporary Drainage | Material | Linear Feet |  | 8
3433.I.130 | Generic Grading Item, Fine Grade for Temp Pavement | Material | Square Yard |  | 8
3433.I.131 | Generic Traffic Control Item Maintenance of Traffic during Construction | Material | Month |  | 8
3433.I.132 | Flagger | Material | Day |  | 8
3433.I.133 | Truck Mounted Attenuator (TMA) | Material | Each |  | 8
3433.I.134 | Water Filled Barrier | Material | Linear Feet |  | 8
3433.I.135 | Remove & Reset Water Filled Barrier | Material | Linear Feet |  | 8
3433.I.136 | Removal of Pavement Marking Lines (4") | Material | Linear Feet |  | 8
3433.I.137 | Removal of Pavement Marking Lines (8") | Material | Linear Feet |  | 8
3433.I.138 | Removal of Pavement Marking Lines (24") | Material | Linear Feet |  | 8
3433.I.139 | Paint Pavement Marking Character | Material | Each |  | 8
3433.I.140 | Paint Pavement Marking Symbol | Material | Each |  | 8
3433.I.141 | Generic Erosion Control Item E&S Maintenance (24 Mo's) | Material | Each |  | 8
3433.I.142 | Temporary Silt Fence | Material | Linear Feet |  | 8
3433.I.143 | Stone for Erosion Control, Class A | Material | Ton |  | 8
3433.I.144 | Stone for Erosion Control, Class B | Material | Ton |  | 8
3433.I.145 | Sediment Control Stone | Material | Ton |  | 8
3433.I.146 | Temporary Mulching | Material |  |  | 8
3433.I.147 | Seed for Temporary Seeding | Material | LB |  | 8
3433.I.148 | Fertilizer for Temporary Seeding | Material | Ton |  | 8
3433.I.149 | Temporary Slope Drains | Material | Linear Feet |  | 8
3433.I.150 | Safety Fence | Material | Linear Feet |  | 8
3433.I.151 | Silt Excavation | Material | Cubic Yard |  | 8
3433.I.152 | Matting for Erosion Control | Material | Square Yard |  | 8
3433.I.153 | Coir Fiber Mat | Material | Square Yard |  | 8
3433.I.154 | 1/4" Hardware Cloth | Material | Linear Feet |  | 8
3433.I.155 | Special Stilling Basins | Material | Each |  | 8
3433.I.156 | Coir Fiber Wattle | Material | Linear Feet |  | 8
3433.I.157 | Wattle Barrier | Material | Linear Feet |  | 8
3433.I.158 | Polyacrylamide (PAM) | Material | LB |  | 8
3433.I.159 | Coir Fiber Baffle | Material | Linear Feet |  | 8
3433.I.160 | Skimmer | Material | Each |  | 8
3433.I.161 | Seeding and Mulching | Material |  |  | 8
3433.I.162 | Mowing | Material |  |  | 8
3433.I.163 | Seed for Repair Seeding | Material | LB |  | 8
3433.I.164 | Fertilizer for Repair Seeding | Material | Ton |  | 8
3433.I.165 | Seed for Supplemental Seeding | Material | LB |  | 8
3433.I.166 | Fertilizer Topdressing | Material | Ton |  | 8
3433.I.167 | Specialized Hand Mowing | Material | Hour |  | 8
3433.I.168 | Concrete Washout Structure | Material | Each |  | 8
3433.I.169 | Geotextile for Drainage | Material | Square Yard |  | 8
3433.I.170 | Unclassified Excavation Area 5 | Material | Cubic Yard |  | 8
3433.I.171 | Borrow Excavation | Material | Cubic Yard |  | 8
3433.I.172 | Fine Grading Area 5 | Material | Square Yard |  | 8
3433.I.173 | Aggregate Base Course | Material | Ton |  | 8
3433.I.174 | 12" Type 1 Aggregate Subgrade | Material | Ton |  | 8
3433.I.175 | Milling Asphalt Pavement 3" Depth | Material | Square Yard |  | 8
3433.I.176 | Milling Asphalt Pavement 6" Depth | Material | Square Yard |  | 8
3433.I.177 | Asphalt Conc Base Course, Type B25.0C | Material | Ton |  | 8
3433.I.178 | Asphalt Conc Surface Course, Type S9.5B | Material | Ton |  | 8
3433.I.179 | Asphalt Conc Surface Course, Type S9.5C | Material | Ton |  | 8
3433.I.180 | 15" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.I.181 | 18" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.I.182 | 24" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.I.183 | 30" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.I.184 | 24" RC Pipe Culverts, Class V | Material | Linear Feet |  | 8
3433.I.185 | 30" CS Pipe Culverts, 0.079" Thick 10 Ga | Material | Linear Feet |  | 8
3433.I.186 | Pipe Removal/Abandon | Material | Linear Feet |  | 8
3433.I.187 | Masonry Drainage Structures | Material | Each |  | 8
3433.I.188 | Frame with Grate | Material | Each |  | 8
3433.I.189 | Generic Utility Item, Utility Relocation Package, Entire Project | Material | Lump Sum |  | 8
3433.I.190 | 4" Concrete Sidewalk | Material | Square Yard |  | 8
3433.I.191 | 1'-6" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3433.I.192 | 2'-6" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3433.I.193 | 5" Monolithic Concrete Islands (Keyed in) | Material | Square Yard |  | 8
3433.I.194 | 6" Concrete Driveway | Material | Square Yard |  | 8
3433.I.195 | Concrete Curb Ramps | Material | Each |  | 8
3433.I.196 | Steel Beam Guardrail | Material | Linear Feet |  | 8
3433.I.197 | Steel Beam Guardrail, Shop Curved | Material | Linear Feet |  | 8
3433.I.198 | Guardrail End Units, Type TL-3 | Material | Each |  | 8
3433.I.199 | Guardrail End Units, Type CAT-1 | Material | Each |  | 8
3433.I.200 | Guardrail Anchor Units, Type III | Material | Each |  | 8
3433.I.201 | Two Bar Metal Rail | Material | Linear Feet |  | 8
3433.I.202 | Thermoplastic Pavement Marking Lines (4", 90 Mils) | Material | Linear Feet |  | 8
3433.I.203 | Thermoplastic Pavement Marking Lines (6", 90 Mils) | Material | Linear Feet |  | 8
3433.I.204 | Cross Walk Bars | Material | Linear Feet |  | 8
3433.I.205 | Thermoplastic Pavement Markings Symbol (90 Mils) | Material | Each |  | 8
3433.I.206 | Contractor Furnished Signs Area 5 | Material | Each |  | 8
3433.I.207 | Railroad Work Area 5 | Material | Lump Sum |  | 8
3433.U.100 | U2719 - Mobilization - 10% | Material | Lump Sum |  | 8
3433.U.101 | U2719 - Design Fee | Material | Lump Sum |  | 8
3433.U.102 | U2719 - Bonds, Insurances, Success Fee, D/B Team Setup | Material | Lump Sum |  | 8
3433.U.103 | U2719 - Construction Surveying | Material | Lump Sum |  | 8
3433.U.104 | U2719 - Generic Miscellaneous Item Camera Existing Pipes | Material | Linear Feet |  | 8
3433.U.105 | U2719 - Field Office | Material | Lump Sum |  | 8
3433.U.106 | U2719 - Clearing & Grubbing (152 Acres) | Material |  |  | 8
3433.U.107 | U2719 - Removal of Existing Structure at Station (Jones Franklin) | Material | Each |  | 8
3433.U.108 | U2719 - Removal of Existing Structure at Station (Athens) | Material | Each |  | 8
3433.U.109 | U2719 - Removal of Existing Structure at Station (Melbourne) | Material | Each |  | 8
3433.U.110 | U2719 - Removal of Existing Structure at Station ( 440 EB over Western Blvd) | Material | Each |  | 8
3433.U.111 | U2719 - Removal of Existing Structure at Station ( 440 WB over Western Blvd) | Material | Each |  | 8
3433.U.112 | U2719 - Removal of Existing Structure at Station ( Western Flyover) | Material | Each |  | 8
3433.U.113 | U2719 - Removal of Existing Structure at Station ( 440 EB over Hillsborough) | Material | Each |  | 8
3433.U.114 | U2719 - Removal of Existing Structure at Station ( 440 WB over Hillsborough) | Material | Each |  | 8
3433.U.115 | U2719 - Removal of Existing Structure at Station ( 440 EB over Wade) | Material | Each |  | 8
3433.U.116 | U2719 - Removal of Existing Structure at Station ( 440 WB over Wade) | Material | Each |  | 8
3433.U.117 | U2719 - HP12X53 Steel Piles | Material | Linear Feet |  | 8
3433.U.118 | U2719 - 3'-6" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3433.U.119 | U2719 - 4'-6" Dia Drilled Piers in Soil | Material | Linear Feet |  | 8
3433.U.120 | U2719 - 4'-0" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3433.U.121 | U2719 - 4'-0" Dia Drilled Piers Not in Soil | Material | Linear Feet |  | 8
3433.U.122 | U2719 - Type I Standard Approach Fill Station *** (Jones Franklin) | Material | Cubic Yard |  | 8
3433.U.123 | U2719 - Type I Standard Approach Fill Station *** (Jones Franklin) | Material | Cubic Yard |  | 8
3433.U.124 | U2719 - Type I Standard Approach Fill Station *** (Athens) | Material | Cubic Yard |  | 8
3433.U.125 | U2719 - Type I Standard Approach Fill Station *** (Athens) | Material | Cubic Yard |  | 8
3433.U.126 | U2719 - Type I Standard Approach Fill Station *** (Melbourne) | Material | Cubic Yard |  | 8
3433.U.127 | U2719 - Type I Standard Approach Fill Station *** (Melbourne) | Material | Cubic Yard |  | 8
3433.U.128 | U2719 - Type I Standard Approach Fill Station *** (440 EB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.129 | U2719 - Type I Standard Approach Fill Station *** (440 EB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.130 | U2719 - Type I Standard Approach Fill Station *** (440 WB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.131 | U2719 - Type I Standard Approach Fill Station *** (440 WB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.132 | U2719 - Type I Standard Approach Fill Station *** (Ligon) | Material | Cubic Yard |  | 8
3433.U.133 | U2719 - Type I Standard Approach Fill Station *** (Ligon) | Material | Cubic Yard |  | 8
3433.U.134 | U2719 - Type I Standard Approach Fill Station *** (440 EB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.135 | U2719 - Type I Standard Approach Fill Station *** (440 EB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.136 | U2719 - Type I Standard Approach Fill Station *** (440 WB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.137 | U2719 - Type I Standard Approach Fill Station *** (440 WB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.138 | U2719 - Type I Standard Approach Fill Station *** (440 EB over Wade) | Material | Cubic Yard |  | 8
3433.U.139 | U2719 - Type I Standard Approach Fill Station *** (440 EB over Wade) | Material | Cubic Yard |  | 8
3433.U.140 | U2719 - Type I Standard Approach Fill Station *** (440 WB over Wade) | Material | Cubic Yard |  | 8
3433.U.141 | U2719 - Type I Standard Approach Fill Station *** (440 WB over Wade) | Material | Cubic Yard |  | 8
3433.U.142 | U2719 - Type I Standard Approach Fill Station *** (Wade over 440) | Material | Cubic Yard |  | 8
3433.U.143 | U2719 - Type I Standard Approach Fill Station *** (440 Ramp C over Wade/440) | Material | Cubic Yard |  | 8
3433.U.144 | U2719 - Type I Standard Approach Fill Station *** (Wade over 440) | Material | Cubic Yard |  | 8
3433.U.145 | U2719 - Type I Standard Approach Fill Station *** (440 Ramp B over Wade) | Material | Cubic Yard |  | 8
3433.U.146 | U2719 - Type I Standard Approach Fill Station *** (440 Ramp B over Wade) | Material | Cubic Yard |  | 8
3433.U.147 | U2719 - Unclassified Structure Excavation at Station **** (Jones Franklin) | Material | Cubic Yard |  | 8
3433.U.148 | U2719 - Unclassified Structure Excavation at Station **** (Jones Franklin) | Material | Cubic Yard |  | 8
3433.U.149 | U2719 - Unclassified Structure Excavation at Station **** (Athens) | Material | Cubic Yard |  | 8
3433.U.150 | U2719 - Unclassified Structure Excavation at Station **** (Athens) | Material | Cubic Yard |  | 8
3433.U.151 | U2719 - Unclassified Structure Excavation at Station **** (Melbourne) | Material | Cubic Yard |  | 8
3433.U.152 | U2719 - Unclassified Structure Excavation at Station **** (Melbourne) | Material | Cubic Yard |  | 8
3433.U.153 | U2719 - Unclassified Structure Excavation at Station **** (440 EB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.154 | U2719 - Unclassified Structure Excavation at Station **** (440 EB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.155 | U2719 - Unclassified Structure Excavation at Station **** (440 WB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.156 | U2719 - Unclassified Structure Excavation at Station **** (440 WB over Western Blvd) | Material | Cubic Yard |  | 8
3433.U.157 | U2719 - Unclassified Structure Excavation at Station **** (Ligon) | Material | Cubic Yard |  | 8
3433.U.158 | U2719 - Unclassified Structure Excavation at Station **** (Ligon) | Material | Cubic Yard |  | 8
3433.U.159 | U2719 - Unclassified Structure Excavation at Station **** (440 EB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.160 | U2719 - Unclassified Structure Excavation at Station **** (440 EB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.161 | U2719 - Unclassified Structure Excavation at Station **** (440 WB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.162 | U2719 - Unclassified Structure Excavation at Station **** (440 WB over Hillsborough) | Material | Cubic Yard |  | 8
3433.U.163 | U2719 - Unclassified Structure Excavation at Station **** (440 EB over Wade NB) | Material | Cubic Yard |  | 8
3433.U.164 | U2719 - Unclassified Structure Excavation at Station **** (440 EB over Wade NB) | Material | Cubic Yard |  | 8
3433.U.165 | U2719 - Unclassified Structure Excavation at Station **** (440 WB over Wade NB) | Material | Cubic Yard |  | 8
3433.U.166 | U2719 - Unclassified Structure Excavation at Station **** (440 WB over Wade NB) | Material | Cubic Yard |  | 8
3433.U.167 | U2719 - Unclassified Structure Excavation at Station **** (Wade over 440) | Material | Cubic Yard |  | 8
3433.U.168 | U2719 - Unclassified Structure Excavation at Station **** (440 Ramp C over Wade) | Material | Cubic Yard |  | 8
3433.U.169 | U2719 - Unclassified Structure Excavation at Station **** (Wade over 440) | Material | Cubic Yard |  | 8
3433.U.170 | U2719 - Unclassified Structure Excavation at Station **** (440 Ramp B over Wade) | Material | Cubic Yard |  | 8
3433.U.171 | U2719 - Unclassified Structure Excavation at Station **** (440 Ramp B over Wade) | Material | Cubic Yard |  | 8
3433.U.172 | U2719 - Class A Concrete (Bridge) Substructure | Material | Cubic Yard |  | 8
3433.U.173 | U2719 - Bridge Approach Slab, Station **** (Jones Franklin) | Material | Square Feet |  | 8
3433.U.174 | U2719 - Bridge Approach Slab, Station **** (Jones Franklin) | Material | Square Feet |  | 8
3433.U.175 | U2719 - Bridge Approach Slab, Station **** (Athens) | Material | Square Feet |  | 8
3433.U.176 | U2719 - Bridge Approach Slab, Station **** (Athens) | Material | Square Feet |  | 8
3433.U.177 | U2719 - Bridge Approach Slab, Station **** (Melbourne) | Material | Square Feet |  | 8
3433.U.178 | U2719 - Bridge Approach Slab, Station **** (Melbourne) | Material | Square Feet |  | 8
3433.U.179 | U2719 - Bridge Approach Slab, Station **** (440 EB over Western Blvd) | Material | Square Feet |  | 8
3433.U.180 | U2719 - Bridge Approach Slab, Station **** (440 EB over Western Blvd) | Material | Square Feet |  | 8
3433.U.181 | U2719 - Bridge Approach Slab, Station **** (440 WB over Western Blvd) | Material | Square Feet |  | 8
3433.U.182 | U2719 - Bridge Approach Slab, Station **** (440 WB over Western Blvd) | Material | Square Feet |  | 8
3433.U.183 | U2719 - Bridge Approach Slab, Station **** (Ligon) | Material | Square Feet |  | 8
3433.U.184 | U2719 - Bridge Approach Slab, Station **** (Ligon) | Material | Square Feet |  | 8
3433.U.185 | U2719 - Bridge Approach Slab, Station **** (440 EB over Hillsborough) | Material | Square Feet |  | 8
3433.U.186 | U2719 - Bridge Approach Slab, Station **** (440 EB over Hillsborough) | Material | Square Feet |  | 8
3433.U.187 | U2719 - Bridge Approach Slab, Station **** (440 WB over Hillsborough) | Material | Square Feet |  | 8
3433.U.188 | U2719 - Bridge Approach Slab, Station **** (440 WB over Hillsborough) | Material | Square Feet |  | 8
3433.U.189 | U2719 - Bridge Approach Slab, Station **** (440 EB over Wade NB) | Material | Square Feet |  | 8
3433.U.190 | U2719 - Bridge Approach Slab, Station **** (440 EB over Wade NB) | Material | Square Feet |  | 8
3433.U.191 | U2719 - Bridge Approach Slab, Station **** (440 WB over Wade NB) | Material | Square Feet |  | 8
3433.U.192 | U2719 - Bridge Approach Slab, Station **** (440 WB over Wade NB) | Material | Square Feet |  | 8
3433.U.193 | U2719 - Bridge Approach Slab, Station **** (Wade over 440) | Material | Square Feet |  | 8
3433.U.194 | U2719 - Bridge Approach Slab, Station **** (440 Ramp C over Wade) | Material | Square Feet |  | 8
3433.U.195 | U2719 - Bridge Approach Slab, Station **** (Wade over 440) | Material | Square Feet |  | 8
3433.U.196 | U2719 - Bridge Approach Slab, Station **** (440 Ramp B over Wade) | Material | Square Feet |  | 8
3433.U.197 | U2719 - Bridge Approach Slab, Station **** (440 Ramp B over Wade) | Material | Square Feet |  | 8
3433.U.198 | U2719 - Reinforced Concrete Deck Slab | Material | Square Feet |  | 8
3433.U.199 | U2719 - 36" Prestressed Concrete Girders FIBS | Material | Linear Feet |  | 8
3433.U.200 | U2719 - 45" Prestressed Concrete Girders FIBS | Material | Linear Feet |  | 8
3433.U.201 | U2719 - 54" Prestressed Concrete Girders FIBS | Material | Linear Feet |  | 8
3433.U.202 | U2719 - 63" Prestressed Concrete Girders FIBS | Material | Linear Feet |  | 8
3433.U.203 | U2719 - 72" Prestressed Concrete Girders FIBS | Material | Linear Feet |  | 8
3433.U.204 | U2719 - 56" MBT | Material | Linear Feet |  | 8
3433.U.205 | U2719 - Elastomeric Bearings | Material | Each |  | 8
3433.U.206 | U2719 - Foam Joint Seals | Material | Linear Feet |  | 8
3433.U.207 | U2719 - Expansion Joint Seals | Material | Linear Feet |  | 8
3433.U.208 | U2719 - Grooving Bridge Floors | Material | Square Feet |  | 8
3433.U.209 | U2719 - Concrete Barrier Rail 42" | Material | Linear Feet |  | 8
3433.U.210 | U2719 - Vertical Concrete Barrier Rail 42" | Material | Linear Feet |  | 8
3433.U.211 | U2719 - Concrete Median Barrier 32" | Material | Linear Feet |  | 8
3433.U.212 | U2719 - Concrete Parapet 30" | Material | Linear Feet |  | 8
3433.U.213 | U2719 - Reinforcing Steel (Bridge) | Material | LB |  | 8
3433.U.214 | U2719 - Epoxy Coated Reinforcing Steel (Bridge) | Material | LB |  | 8
3433.U.215 | U2719 - Spiral Column Reinforcing Steel (Bridge) | Material | LB |  | 8
3433.U.216 | U2719 - Reinforcing Steel (Culvert) | Material | LB |  | 8
3433.U.217 | U2719 - LEVELING PAD(LF) | Material | LB |  | 8
3433.U.218 | U2719 - Class A Concrete (Culvert) | Material | Cubic Yard |  | 8
3433.U.219 | U2719 - PRECAST COPING(CY) | Material | Cubic Yard |  | 8
3433.U.220 | U2719 - MSE Retaining Walls | Material | Square Feet |  | 8
3433.U.221 | U2719 - Cast In Place Coping | Material | Square Feet |  | 8
3433.U.222 | U2719 - Soil Nail Retaining Walls | Material | Square Feet |  | 8
3433.U.223 | U2719 - Segmental Gravity Retaining Walls | Material | Square Feet |  | 8
3433.U.224 | U2719 - Precast T-Wall Retaining Walls | Material | Square Feet |  | 8
3433.U.225 | U2719 - Generic Grading Item Remove Concrete Barrier Wall | Material | Linear Feet |  | 8
3433.U.226 | U2719 - Generic Grading Item Remove Concrete Curb and Gutter | Material | Linear Feet |  | 8
3433.U.227 | U2719 - Generic Grading Item Remove Paved Ditches, Sidewalk and Conc Islands | Material | Square Yard |  | 8
3433.U.228 | U2719 - Generic Miscellaneous Item Building Demolition | Material | Square Feet |  | 8
3433.U.229 | U2719 - Generic Miscellaneous Item Remove Billboard/Commerical Sign | Material | Each |  | 8
3433.U.230 | U2719 - Generic Miscellaneous Item Vibration Monitoring | Material | Lump Sum |  | 8
3433.U.231 | U2719 - Generic Traffic Control Item Maintenance of Traffic during Construction | Material | Month |  | 8
3433.U.232 | U2719 - Barricades (Type III) | Material | Each |  | 8
3433.U.233 | U2719 - Work Zone Signs (Stationary) | Material | Square Feet |  | 8
3433.U.234 | U2719 - Work Zone Signs (Portable) | Material | Square Feet |  | 8
3433.U.235 | U2719 - Flashing Arrow Board | Material | Each |  | 8
3433.U.236 | U2719 - Portable Changeable Message Sign | Material | Each |  | 8
3433.U.237 | U2719 - Work Zone Digital Speed Limit Signs | Material | Each |  | 8
3433.U.238 | U2719 - Work Zone Presence Lighting | Material | Each |  | 8
3433.U.239 | U2719 - Drums | Material | Each |  | 8
3433.U.240 | U2719 - Sequential Flashing Warning Lights | Material | Each |  | 8
3433.U.241 | U2719 - Trucks Entering Warning Signs/Lights | Material | Each |  | 8
3433.U.242 | U2719 - Flagger | Material | Day |  | 8
3433.U.243 | U2719 - Temporary Crash Cushion | Material | Each |  | 8
3433.U.244 | U2719 - Remove & Reset Temporary Crash Cushion | Material | Each |  | 8
3433.U.245 | U2719 - Truck Mounted Attenuator (TMA) | Material | Each |  | 8
3433.U.246 | U2719 - Portable Concrete Barrier | Material | Linear Feet |  | 8
3433.U.247 | U2719 - Portable Concrete Barrier (Anchored) | Material | Linear Feet |  | 8
3433.U.248 | U2719 - Reset Portable Concrete Barrier | Material | Linear Feet |  | 8
3433.U.249 | U2719 - Relocate Portable Concrete Barrier | Material | Linear Feet |  | 8
3433.U.250 | U2719 - Remove & Reset Portable Concrete Barrier (Stockpile & Return) | Material | Linear Feet |  | 8
3433.U.251 | U2719 - Remove & Reset Portable Concrete Barrier (Anchored) | Material | Linear Feet |  | 8
3433.U.252 | U2719 - Water Filled Barrier | Material | Linear Feet |  | 8
3433.U.253 | U2719 - Remove & Reset Water Filled Barrier | Material | Linear Feet |  | 8
3433.U.254 | U2719 - Law Enforcement | Material | Hour |  | 8
3433.U.255 | U2719 - Skinny Drum | Material | Each |  | 8
3433.U.256 | U2719 - Generic Traffic Control Item On Call Towing | Material | Day |  | 8
3433.U.257 | U2719 - Asphalt Conc Base Course, Type B25.0C Temporary | Material | Ton |  | 8
3433.U.258 | U2719 - Asphalt Conc Surface Course, Type S9.5C Temporary | Material | Ton |  | 8
3433.U.259 | U2719 - Asphalt Conc Surface Course, Type S9.5C Rumble Strip Fill | Material | Ton |  | 8
3433.U.260 | U2719 - Generic Grading Item, Unclassified Excavation for Temp Pavement | Material | Cubic Yard |  | 8
3433.U.261 | U2719 - Generic Pipe Item Temporary Drainage | Material | Linear Feet |  | 8
3433.U.262 | U2719 - Generic Grading Item, Fine Grade for Temp Pavement | Material | Square Yard |  | 8
3433.U.263 | U2719 - Temporary Raised Pavement Markers | Material | Each |  | 8
3433.U.264 | U2719 - Work Zone Performance Pavement Markings 4" | Material | Linear Feet |  | 8
3433.U.265 | U2719 - Work Zone Performance Pavement Markings 6" | Material | Linear Feet |  | 8
3433.U.266 | U2719 - Work Zone Performance Pavement Markings 8" | Material | Linear Feet |  | 8
3433.U.267 | U2719 - Work Zone Performance Pavement Markings 12" | Material | Linear Feet |  | 8
3433.U.268 | U2719 - Work Zone Performance Pavement Markings 24" | Material | Linear Feet |  | 8
3433.U.269 | U2719 - Work Zone Traffic Pattern Masking | Material | Square Feet |  | 8
3433.U.270 | U2719 - Paint Pavement Marking Lines (4") | Material | Linear Feet |  | 8
3433.U.271 | U2719 - Paint Pavement Marking Lines (8") | Material | Linear Feet |  | 8
3433.U.272 | U2719 - Paint Pavement Marking Lines (24") | Material | Linear Feet |  | 8
3433.U.273 | U2719 - Paint Pavement Marking Symbol | Material | Each |  | 8
3433.U.274 | U2719 - Removal of Pavement Marking Lines (4") | Material | Linear Feet |  | 8
3433.U.275 | U2719 - Removal of Pavement Marking Lines (6") | Material | Linear Feet |  | 8
3433.U.276 | U2719 - Removal of Pavement Marking Lines (8") | Material | Linear Feet |  | 8
3433.U.277 | U2719 - Removal of Pavement Marking Lines (12") | Material | Linear Feet |  | 8
3433.U.278 | U2719 - Removal of Pavement Marking Lines (24") | Material | Linear Feet |  | 8
3433.U.279 | U2719 - Generic Erosion Control Item E&S Maintenance (54 Mo's) | Material | Each |  | 8
3433.U.280 | U2719 - Temporary Silt Fence | Material | Linear Feet |  | 8
3433.U.281 | U2719 - Stone for Erosion Control, Class A | Material | Ton |  | 8
3433.U.282 | U2719 - Stone for Erosion Control, Class B | Material | Ton |  | 8
3433.U.283 | U2719 - Sediment Control Stone | Material | Ton |  | 8
3433.U.284 | U2719 - Temporary Mulching | Material |  |  | 8
3433.U.285 | U2719 - Seed for Temporary Seeding | Material | LB |  | 8
3433.U.286 | U2719 - Fertilizer for Temporary Seeding | Material | Ton |  | 8
3433.U.287 | U2719 - Temporary Slope Drains | Material | Linear Feet |  | 8
3433.U.288 | U2719 - Safety Fence | Material | Linear Feet |  | 8
3433.U.289 | U2719 - Silt Excavation | Material | Cubic Yard |  | 8
3433.U.290 | U2719 - Matting for Erosion Control | Material | Square Yard |  | 8
3433.U.291 | U2719 - Coir Fiber Mat | Material | Square Yard |  | 8
3433.U.292 | U2719 - 1/4" Hardware Cloth | Material | Linear Feet |  | 8
3433.U.293 | U2719 - Special Stilling Basins | Material | Each |  | 8
3433.U.294 | U2719 - Coir Fiber Wattle | Material | Linear Feet |  | 8
3433.U.295 | U2719 - Wattle Barrier | Material | Linear Feet |  | 8
3433.U.296 | U2719 - Polyacrylamide (PAM) | Material | LB |  | 8
3433.U.297 | U2719 - Coir Fiber Baffle | Material | Linear Feet |  | 8
3433.U.298 | U2719 - Skimmer | Material | Each |  | 8
3433.U.299 | U2719 - Seeding and Mulching | Material |  |  | 8
3433.U.300 | U2719 - Mowing | Material |  |  | 8
3433.U.301 | U2719 - Seed for Repair Seeding | Material | LB |  | 8
3433.U.302 | U2719 - Fertilizer for Repair Seeding | Material | Ton |  | 8
3433.U.303 | U2719 - Seed for Supplemental Seeding | Material | LB |  | 8
3433.U.304 | U2719 - Fertilizer Topdressing | Material | Ton |  | 8
3433.U.305 | U2719 - Specialized Hand Mowing | Material | Hour |  | 8
3433.U.306 | U2719 - Culvert Diversion Channel | Material | Cubic Yard |  | 8
3433.U.307 | U2719 - Reforestation | Material |  |  | 8
3433.U.308 | U2719 - Concrete Washout Structure | Material | Each |  | 8
3433.U.309 | U2719 - Geotextile for Drainage | Material | Square Yard |  | 8
3433.U.310 | U2719 - Generic Grading Item, Special Cut Ditch | Material | Linear Feet |  | 8
3433.U.311 | U2719 - Unclassified Excavation Areas 1 - 4 | Material | Cubic Yard |  | 8
3433.U.312 | U2719 - Borrow Excavation | Material | Cubic Yard |  | 8
3433.U.313 | U2719 - Fine Grading Areas 1-4 | Material | Square Yard |  | 8
3433.U.314 | U2719 - Proof Rolling | Material | Hour |  | 8
3433.U.315 | U2719 - Removal of Existing Concrete Pavement 9" | Material | Square Yard |  | 8
3433.U.316 | U2719 - Removal of Existing Concrete Pavement 12" | Material | Square Yard |  | 8
3433.U.317 | U2719 - Aggregate Base Course | Material | Ton |  | 8
3433.U.318 | U2719 - 12" Type 1 Aggregate Subgrade | Material | Ton |  | 8
3433.U.319 | U2719 - Non Woven Geotextile for Pvmt Stab | Material | Square Yard |  | 8
3433.U.320 | U2719 - Milling Concrete Pavement, 1.5" Depth | Material | Square Yard |  | 8
3433.U.321 | U2719 - Milling Asphalt Pavement 2" Depth | Material | Square Yard |  | 8
3433.U.322 | U2719 - Milling Asphalt Pavement 3" Depth | Material | Square Yard |  | 8
3433.U.323 | U2719 - Milling Asphalt Pavement 6" Depth | Material | Square Yard |  | 8
3433.U.324 | U2719 - Milling Asphalt Pavement 7" Depth | Material | Square Yard |  | 8
3433.U.325 | U2719 - Milling Asphalt Pavement, Shoulder Joint | Material | Square Yard |  | 8
3433.U.326 | U2719 - Asphalt Conc Base Course, Type B25.0C | Material | Ton |  | 8
3433.U.327 | U2719 - Asphalt Conc Base Course, Type B25.0C, Wedging | Material | Ton |  | 8
3433.U.328 | U2719 - Asphalt Conc Intermediate Course, Type I19.0C | Material | Ton |  | 8
3433.U.329 | U2719 - Asphalt Conc Intermediate Course, Type I19.0C, Wedging | Material | Ton |  | 8
3433.U.330 | U2719 - Asphalt Conc Surface Course, Type S9.5B | Material | Ton |  | 8
3433.U.331 | U2719 - Asphalt Conc Surface Course, Type S9.5B, Wedging | Material | Ton |  | 8
3433.U.332 | U2719 - Asphalt Conc Surface Course, Type S9.5C | Material | Ton |  | 8
3433.U.333 | U2719 - Asphalt Conc Surface Course, Type S9.5C, Wedging | Material | Ton |  | 8
3433.U.334 | U2719 - Asphalt Conc Surface Course, Type S9.5D | Material | Ton |  | 8
3433.U.335 | U2719 - Permeable Asphalt Drainage Course, Type P-78M | Material | Ton |  | 8
3433.U.336 | U2719 - Milled Rumble Strips (Asphalt) | Material | Linear Feet |  | 8
3433.U.337 | U2719 - Portland Cement Conc Pavement, Through Lanes 11" (with Dowels) | Material | Square Yard |  | 8
3433.U.338 | U2719 - Shoulder Drain | Material | Linear Feet |  | 8
3433.U.339 | U2719 - 4" Shoulder Drain Pipe | Material | Linear Feet |  | 8
3433.U.340 | U2719 - 4" Outlet Pipe for Shoulder Drains | Material | Linear Feet |  | 8
3433.U.341 | U2719 - Concrete Pad for Shoulder Drain Pipe Outlet | Material | Each |  | 8
3433.U.342 | U2719 - 15" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.343 | U2719 - 18" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.344 | U2719 - 24" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.345 | U2719 - 30" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.346 | U2719 - 36" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.347 | U2719 - 42" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.348 | U2719 - 48" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.349 | U2719 - 54" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.350 | U2719 - 60" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.351 | U2719 - 66" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.352 | U2719 - 96" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.353 | U2719 - 108" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.354 | U2719 - 120" RC Pipe Culverts, Class III | Material | Linear Feet |  | 8
3433.U.355 | U2719 - 15" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.356 | U2719 - 18" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.357 | U2719 - 24" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.358 | U2719 - 30" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.359 | U2719 - 36" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.360 | U2719 - 42" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.361 | U2719 - 48" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.362 | U2719 - 54" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.363 | U2719 - 66" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.364 | U2719 - 120" RC Pipe Culverts, Class IV | Material | Linear Feet |  | 8
3433.U.365 | U2719 - Generic Drainage Item, Pipe End Section | Material | Each |  | 8
3433.U.366 | U2719 - 15" CS Pipe Culverts, 0.064" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.367 | U2719 - 18" CS Pipe Culverts, 0.064" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.368 | U2719 - 24" CS Pipe Culverts, 0.064" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.369 | U2719 - 30" CS Pipe Culverts, 0.079" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.370 | U2719 - 36" CS Pipe Culverts, 0.079" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.371 | U2719 - 42" CS Pipe Culverts, 0.079" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.372 | U2719 - 54" CS Pipe Culverts, 0.079" Thick 10 Ga | Material | Linear Feet |  | 8
3433.U.373 | U2719 - Pipe Removal/Abandon | Material | Linear Feet |  | 8
3433.U.374 | U2719 - Masonry Drainage Structures | Material | Each |  | 8
3433.U.375 | U2719 - Masonry Drainage Structures, 108" - 120" (22'-33' Depth) | Material | Each |  | 8
3433.U.376 | U2719 - Masonry Drainage Structures, Traffic Bearing | Material | Each |  | 8
3433.U.377 | U2719 - Endwalls 15" - 36" | Material | Each |  | 8
3433.U.378 | U2719 - Endwalls 42" - 66" | Material | Each |  | 8
3433.U.379 | U2719 - Endwalls 72" - 120" | Material | Each |  | 8
3433.U.380 | U2719 - Temporary Steel Plate Covers for Masonry Drainage Structure | Material | Each |  | 8
3433.U.381 | U2719 - Frame with Grate | Material | Each |  | 8
3433.U.382 | U2719 - Generic Drainage Item, Drainage Structure Adjustments | Material | Each |  | 8
3433.U.383 | U2719 - Generic Drainage Item, Berm Ditch Outlet | Material | Each |  | 8
3433.U.384 | U2719 - Bore & Jack 18" Welded Steel Pipe ** Thick, Grade B in Soil | Material | Linear Feet |  | 8
3433.U.385 | U2719 - Bore & Jack 30" Welded Steel Pipe ** Thick, Grade B in Soil | Material | Linear Feet |  | 8
3433.U.386 | U2719 - Bore & Jack 36" Welded Steel Pipe ** Thick, Grade B in Soil | Material | Linear Feet |  | 8
3433.U.387 | U2719 - Bore & Jack 42" Welded Steel Pipe ** Thick, Grade B in Soil | Material | Linear Feet |  | 8
3433.U.388 | U2719 - Bore & Jack 60" Welded Steel Pipe ** Thick, Grade B in Soil | Material | Linear Feet |  | 8
3433.U.389 | U2719 - Bore & Jack 66" Welded Steel Pipe ** Thick, Grade B in Soil | Material | Linear Feet |  | 8
3433.U.390 | U2719 - Bore & Jack 72" Welded Steel Pipe ** Thick, Grade B | Material | Linear Feet |  | 8
3433.U.391 | U2719 - Bore & Jack 90" Welded Steel Pipe ** Thick, Grade B | Material | Linear Feet |  | 8
3433.U.392 | U2719 - Bore & Jack 108" Welded Steel Pipe ** Thick, Grade B | Material | Linear Feet |  | 8
3433.U.393 | U2719 - Bore & Jack 120" Welded Steel Pipe ** Thick, Grade B | Material | Linear Feet |  | 8
3433.U.394 | U2719 - Class A Concrete (Culvert) | Material | Cubic Yard |  | 8
3433.U.395 | U2719 - Culvert Excavation Sta **** | Material | Lump Sum |  | 8
3433.U.396 | U2719 - Generic Culvert Item, Remove/Abandon Existing Culverts | Material | Lump Sum |  | 8
3433.U.397 | U2719 - Generic Culvert Item, Clean/Desilt Existing Box Culverts | Material | Each |  | 8
3433.U.398 | U2719 - Generic Wall Item, Noise Barrier Wall | Material | Square Feet |  | 8
3433.U.399 | U2719 - Generic Utility Item, Utility Relocation Package, Entire Project | Material | Lump Sum |  | 8
3433.U.400 | U2719 - Rip Rap, Class I | Material | Ton |  | 8
3433.U.401 | U2719 - Rip Rap, Class II | Material | Ton |  | 8
3433.U.402 | U2719 - Rip Rap, Class B | Material | Ton |  | 8
3433.U.403 | U2719 - 4" Slope Protection | Material | Square Yard |  | 8
3433.U.404 | U2719 - 2'-9" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3433.U.405 | U2719 - 1'-6" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3433.U.406 | U2719 - 2'-6" Concrete Curb & Gutter | Material | Linear Feet |  | 8
3433.U.407 | U2719 - Shoulder Berm Gutter | Material | Linear Feet |  | 8
3433.U.408 | U2719 - Concrete Expressway Gutter | Material | Linear Feet |  | 8
3433.U.409 | U2719 - 4" Concrete Sidewalk | Material | Square Yard |  | 8
3433.U.410 | U2719 - Concrete Curb Ramps | Material | Each |  | 8
3433.U.411 | U2719 - 6" Concrete Driveway | Material | Square Yard |  | 8
3433.U.412 | U2719 - 5" Monolithic Concrete Islands (Keyed in) | Material | Square Yard |  | 8
3433.U.413 | U2719 - Concrete Barrier Type T | Material | Linear Feet |  | 8
3433.U.414 | U2719 - Concrete Barrier Single Faced | Material | Linear Feet |  | 8
3433.U.415 | U2719 - Concrete Barrier, Transition Section | Material | Each |  | 8
3433.U.416 | U2719 - Impact Attenuator Units, Type TL-3 | Material | Each |  | 8
3433.U.417 | U2719 - Steel Beam Guardrail | Material | Linear Feet |  | 8
3433.U.418 | U2719 - Steel Beam Guardrail, Shop Curved | Material | Linear Feet |  | 8
3433.U.419 | U2719 - Steel Beam Guardrail, Double Faced | Material | Linear Feet |  | 8
3433.U.420 | U2719 - Guardrail End Units, Type CAT-1 | Material | Each |  | 8
3433.U.421 | U2719 - Guardrail Anchor Units, Type III | Material | Each |  | 8
3433.U.422 | U2719 - Guardrail End Units, Type TL-3 | Material | Each |  | 8
3433.U.423 | U2719 - Guardrail End Units, Type TL-2 | Material | Each |  | 8
3433.U.424 | U2719 - Guardrail Anchor Units, Type B-77 | Material | Each |  | 8
3433.U.425 | U2719 - Remove Existing Guardrail | Material | Linear Feet |  | 8
3433.U.426 | U2719 - Remove Existing Cable Guiderail | Material | Linear Feet |  | 8
3433.U.427 | U2719 - Cable Guiderail | Material | Linear Feet |  | 8
3433.U.428 | U2719 - Cable Guiderail, Anchor Units | Material | Each |  | 8
3433.U.429 | U2719 - Woven Wire Fence, 47" Fabric, includes removal of existing | Material | Linear Feet |  | 8
3433.U.430 | U2719 - Generic Fencing Item - Black Ornamental Fence, Bridge 48" | Material | Linear Feet |  | 8
3433.U.431 | U2719 - Generic Fencing Item - Safety Fence Bridge, 60" | Material | Linear Feet |  | 8
3433.U.432 | U2719 - Generic Fencing Item - Temp Chain Link Fence | Material | Lump Sum |  | 8
3433.U.433 | U2719 - Generic Fencing Item - Black Ornamental Fence, 84" | Material | Each |  | 8
3433.U.434 | U2719 - Two Bar Metal Rail | Material | Linear Feet |  | 8
3433.U.435 | U2719 - Topsoil - Planter | Material | Each |  | 8
3433.U.436 | U2719 - Planter Landscaping | Material | Square Yard |  | 8
3433.U.437 | U2719 - Thermoplastic Pavement Marking Lines (4", 90 Mils) | Material | Linear Feet |  | 8
3433.U.438 | U2719 - Thermoplastic Pavement Marking Lines (6", 90 Mils) | Material | Linear Feet |  | 8
3433.U.439 | U2719 - Thermoplastic Pavement Marking Lines (12", 90 Mils) | Material | Linear Feet |  | 8
3433.U.440 | U2719 - Thermoplastic Pavement Marking Lines (36", 90 Mils) | Material | Linear Feet |  | 8
3433.U.441 | U2719 - Cross Walk Bars | Material | Linear Feet |  | 8
3433.U.442 | U2719 - Thermoplastic Pavement Markings Symbol (90 Mils) | Material | Each |  | 8
3433.U.443 | U2719 - Polyurea Pavement Marking Lines (4", 20 Mils) | Material | Linear Feet |  | 8
3433.U.444 | U2719 - Polyurea Pavement Marking Lines (6", 20 Mils) | Material | Linear Feet |  | 8
3433.U.445 | U2719 - Snowplowable Pavement Markers | Material | Each |  | 8
3433.U.446 | U2719 - Contractor Furnished, Type A Sign | Material | Square Feet |  | 8
3433.U.447 | U2719 - Contractor Furnished, Type B Sign | Material | Square Feet |  | 8
3433.U.448 | U2719 - Contractor Furnished, Type D Sign | Material | Square Feet |  | 8
3433.U.449 | U2719 - Contractor Furnished, Type E Sign | Material | Square Feet |  | 8
3433.U.450 | U2719 - Contractor Furnished, Type F Sign | Material | Square Feet |  | 8
3433.U.451 | U2719 - Contractor Furnished, Milemarkers | Material | Square Feet |  | 8
3433.U.452 | U2719 - Reinforced Concrete Sign Foundations | Material | Cubic Yard |  | 8
3433.U.453 | U2719 - Plain Concrete Sign Foundations | Material | Cubic Yard |  | 8
3433.U.454 | U2719 - Overhead Footing | Material | Cubic Yard |  | 8
3433.U.455 | U2719 - Supports, Breakaway Steel Beam | Material | LB |  | 8
3433.U.456 | U2719 - Supports, 3-Lb Steel U-Channel | Material | Linear Feet |  | 8
3433.U.457 | U2719 - Supports, Overhead Sign Structure at Sta ****** | Material | Each |  | 8
3433.U.458 | U2719 - Sign Erection, Type D | Material | Each |  | 8
3433.U.459 | U2719 - Sign Erection, Type E | Material | Each |  | 8
3433.U.460 | U2719 - Sign Erection, Type F | Material | Each |  | 8
3433.U.461 | U2719 - Sign Erection, Type A (Overhead) | Material | Each |  | 8
3433.U.462 | U2719 - Sign Erection, Type B (Overhead) | Material | Each |  | 8
3433.U.463 | U2719 - Sign Erection, Type A (Ground Mounted) | Material | Each |  | 8
3433.U.464 | U2719 - Sign Erection, Type B (Ground Mounted) | Material | Each |  | 8
3433.U.465 | U2719 - Sign Erection, Milemarkers | Material | Each |  | 8
3433.U.466 | U2719 - Disposal of Sign System, Overhead | Material | Each |  | 8
3433.U.467 | U2719 - Disposal of Sign System, Steelbeam | Material | Each |  | 8
3433.U.468 | U2719 - Disposal of Sign System, U-Channel | Material | Each |  | 8
3433.U.469 | U2719 - Stockpile Sign, A or B (Overhead) | Material | Each |  | 8
3433.U.470 | U2719 - 60' High Mount Standard | Material | Each |  | 8
3433.U.471 | U2719 - 80' High Mount Standard | Material | Each |  | 8
3433.U.472 | U2719 - 100' High Mount Standard | Material | Each |  | 8
3433.U.473 | U2719 - 120' High Mount Standard | Material | Each |  | 8
3433.U.474 | U2719 - Portable Drive Unit | Material | Each |  | 8
3433.U.475 | U2719 - High Mount Foundations | Material | Cubic Yard |  | 8
3433.U.476 | U2719 - Light Standards, Type MTLT (35' SA, 15' A) | Material | Each |  | 8
3433.U.477 | U2719 - Light Standards, Type MTLT (35' SA, 15' Twin A) | Material | Each |  | 8
3433.U.478 | U2719 - Light Standards, Type MTLT (45' SA, 15' A) | Material | Each |  | 8
3433.U.479 | U2719 - Generic Lighting Item - Relocate Twin Arm Light Standard | Material | Each |  | 8
3433.U.480 | U2719 - Standard Foundation (Type R1) | Material | Each |  | 8
3433.U.481 | U2719 - Standard Foundation (Type M1) | Material | Each |  | 8
3433.U.482 | U2719 - Electric Service Pole (30' Class 4) | Material | Each |  | 8
3433.U.483 | U2719 - Electric Service Lateral, 3#1/0 USE | Material | Linear Feet |  | 8
3433.U.484 | U2719 - Electrical Duct, Type BD, 1.5" | Material | Linear Feet |  | 8
3433.U.485 | U2719 - Eletrical Duct, Type BD, 2" | Material | Linear Feet |  | 8
3433.U.486 | U2719 - Electrical Duct, Type BD, 3" | Material | Linear Feet |  | 8
3433.U.487 | U2719 - Electrical Duct, Type JA, 3" | Material | Linear Feet |  | 8
3433.U.488 | U2719 - Electrical Duct, Type JA, 4" | Material | Linear Feet |  | 8
3433.U.489 | U2719 - Electrical Duct, Type JA, 6" | Material | Linear Feet |  | 8
3433.U.490 | U2719 - 2- #8 W/G Feeder Circuit | Material | Linear Feet |  | 8
3433.U.491 | U2719 - 2- #6 W/G Feeder Circuit | Material | Linear Feet |  | 8
3433.U.492 | U2719 - 2- #4 W/G Feeder Circuit | Material | Linear Feet |  | 8
3433.U.493 | U2719 - 2- #1 W/G Feeder Circuit | Material | Linear Feet |  | 8
3433.U.494 | U2719 - 2- #8 W/G Feeder Circuit in 1.5" Conduit | Material | Linear Feet |  | 8
3433.U.495 | U2719 - 2- #6 W/G Feeder Circuit in 1.5" Conduit | Material | Linear Feet |  | 8
3433.U.496 | U2719 - 2- #4 W/G Feeder Circuit in 1.5" Conduit | Material | Linear Feet |  | 8
3433.U.497 | U2719 - 2- #2 W/G Feeder Circuit in 1.5" Conduit | Material | Linear Feet |  | 8
3433.U.498 | U2719 - 2- #1 W/G Feeder Circuit in 2" Conduit | Material | Linear Feet |  | 8
3433.U.499 | U2719 - Generic Lighting Item - Remove Existing Conductor Cable | Material | Linear Feet |  | 8
3433.U.500 | U2719 - Underpass Circuitry at Jones Franklin | Material | Each |  | 8
3433.U.501 | U2719 - Underpass Circuitry at Western | Material | Each |  | 8
3433.U.502 | U2719 - Underpass Circuitry at Hillsborough | Material | Each |  | 8
3433.U.503 | U2719 - Underpass Circuitry at Wade | Material | Each |  | 8
3433.U.504 | U2719 - Electrical Junction Boxes BRJB, 18" x 12" | Material | Each |  | 8
3433.U.505 | U2719 - Electrical Junction Boses CSJB, 36" x 24" | Material | Each |  | 8
3433.U.506 | U2719 - Electrical Junction Boxes HMJB, 18" x 12" | Material | Each |  | 8
3433.U.507 | U2719 - Electrical Junction Boxes HMJB, 30" x 17" | Material | Each |  | 8
3433.U.508 | U2719 - Electrical Junction Boxes IGJB, 18" x 12" | Material | Each |  | 8
3433.U.509 | U2719 - Electrical Junction Boxes IGJB, 30" x 17" | Material | Each |  | 8
3433.U.510 | U2719 - Electrical Junction Boxes LSJB, 18" x 12" | Material | Each |  | 8
3433.U.511 | U2719 - Electrical Junction Boxes LSJB, 30" x 17" | Material | Each |  | 8
3433.U.512 | U2719 - Generic Lighting Item - Remove Existing Junction Box | Material | Each |  | 8
3433.U.513 | U2719 - Generic Lighting Item - 60' High Mount LED | Material | Each |  | 8
3433.U.514 | U2719 - Generic Lighting Item - 80' High Mount LED | Material | Each |  | 8
3433.U.515 | U2719 - Generic Lighting Item - 100' High Mount LED | Material | Each |  | 8
3433.U.516 | U2719 - Generic Lighting Item - 120' High Mount LED | Material | Each |  | 8
3433.U.517 | U2719 - Generic Lighting Item - Rdwy Light Std Lum (285 | Material | Each |  | 8
3433.U.518 | U2719 - Generic Lighting Item - 240/480V Light Control | Material | Each |  | 8
3433.U.519 | U2719 - Generic Lighting Item - Comm. Gateway | Material | Each |  | 8
3433.U.520 | U2719 - Generic Lighting Item - Control Node | Material | Each |  | 8
3433.U.521 | U2719 - Underpass Luminairies (Type PM, LED, 75W) | Material | Each |  | 8
3433.U.522 | U2719 - Pedestrian Signal Head (16", 1 Section w/Countdown) | Material | Each |  | 8
3433.U.523 | U2719 - Signal Cable | Material | Linear Feet |  | 8
3433.U.524 | U2719 - Vehicle Signal Head (12", 3 Section) | Material | Each |  | 8
3433.U.525 | U2719 - Vehicle Signal Head (12", 4 Section) | Material | Each |  | 8
3433.U.526 | U2719 - Vehicle Signal Head (12", 5 Section) | Material | Each |  | 8
3433.U.527 | U2719 - Messenger Cable (3/8") | Material | Linear Feet |  | 8
3433.U.528 | U2719 - Junction Box (Standard Size) | Material | Each |  | 8
3433.U.529 | U2719 - Wood Pole - Signal | Material | Each |  | 8
3433.U.530 | U2719 - Guy Assembly | Material | Each |  | 8
3433.U.531 | U2719 - 2" Riser with Weatherhead | Material | Each |  | 8
3433.U.532 | U2719 - Inductive Loop Sawcut | Material | Linear Feet |  | 8
3433.U.533 | U2719 - Lead-in Cable (************) | Material | Linear Feet |  | 8
3433.U.534 | U2719 - New Electrical Service | Material | Each |  | 8
3433.U.535 | U2719 - Metal Strain Signal Pole | Material | Each |  | 8
3433.U.536 | U2719 - Metal Pole with Single Mast Arm | Material | Each |  | 8
3433.U.537 | U2719 - Metal Pole with Dual Mast Arm | Material | Each |  | 8
3433.U.538 | U2719 - Soil Test | Material | Each |  | 8
3433.U.539 | U2719 - Drilled Pier Foundation | Material | Cubic Yard |  | 8
3433.U.540 | U2719 - Type II Pedestal with Foundation | Material | Each |  | 8
3433.U.541 | U2719 - Signal Cabinet Foundation | Material | Each |  | 8
3433.U.542 | U2719 - Controllers with Cabinet (Type 2070E, Base Mounted) | Material | Each |  | 8
3433.U.543 | U2719 - Detector Card (Type 2070L) | Material | Each |  | 8
3433.U.544 | U2719 - Cabinet Base Extender | Material | Each |  | 8
3433.U.545 | U2719 - Camera with Internal Loop Emulator Processing Unit | Material | Each |  | 8
3433.U.546 | U2719 - Unpaved Trenching (1 - 2") | Material | Linear Feet |  | 8
3433.U.547 | U2719 - Directional Drill (2 - 2") | Material | Linear Feet |  | 8
3433.U.548 | U2719 - Dynamic Message Sign System "DMS**" | Material | Each |  | 8
3433.U.549 | U2719 - Tracer Wire - DMS | Material | Linear Feet |  | 8
3433.U.550 | U2719 - Generic Signing Item - DMS Ladder | Material | Each |  | 8
3433.U.551 | U2719 - Generic Signing Item - DMS Pedestal | Material | Each |  | 8
3433.U.552 | U2719 - Generic Signing Item - Cabinet Foundation | Material | Each |  | 8
3433.U.553 | U2719 - Generic Signing Item - Cabinet Disconnect | Material | Each |  | 8
3433.U.554 | U2719 - Generic Signing Item - DMS Unpaved Trenching (2 - 2") | Material | Linear Feet |  | 8
3433.U.555 | U2719 - Generic Signing Item - DMS Directional Drill (2 - 2") | Material | Linear Feet |  | 8
3433.U.556 | U2719 - Communications Cable (144-Fiber) | Material | Linear Feet |  | 8
3433.U.557 | U2719 - Drop Cable (12-Fiber) | Material | Linear Feet |  | 8
3433.U.558 | U2719 - Splice Enclosure | Material | Each |  | 8
3433.U.559 | U2719 - Modify Splice Enclosure | Material | Each |  | 8
3433.U.560 | U2719 - Delineator Marker | Material | Each |  | 8
3433.U.561 | U2719 - New Electrical Service - ITS | Material | Each |  | 8
3433.U.562 | U2719 - Electrical Junction Boxes, JB Special Oversized, 36" x 24" x 24" | Material | Each |  | 8
3433.U.563 | U2719 - Electrical Junction Boxes, JB Standard Size for Electrical Service | Material | Each |  | 8
3433.U.564 | U2719 - Wood Pole - ITS | Material | Each |  | 8
3433.U.565 | U2719 - Guy Assembly - ITS | Material | Each |  | 8
3433.U.566 | U2719 - 2" Riser with Weatherhead - ITS | Material | Each |  | 8
3433.U.567 | U2719 - Generic Signing Item - Drilled Pir Foundation | Material | Cubic Yard |  | 8
3433.U.568 | U2719 - Generic Signing Item - Soil Test | Material |  |  | 8
3433.U.569 | U2719 - Generic Signal Item- CCTV Camera Assembly (Including Cabinet) | Material |  |  | 8
3433.U.570 | U2719 - Generic Signal Item - CCTV Wood Pole | Material |  |  | 8
3433.U.571 | U2719 - Generic Signal Item - CCTV Cabinet Disconnect | Material |  |  | 8
3433.U.572 | U2719 - Generic Signal Item - CCTV Equipment Cabinet Foundation | Material |  |  | 8
3433.U.573 | U2719 - Generic Signal Item - CCTV Equipment Cabinet Disconnect | Material |  |  | 8
3433.U.221.5 | U2719 - Concrete for Leveling Pad | Material |  |  | 8
9156-SA10 | SA#10 - Additional Turbine Bridge Design | Material | Lump Sum |  | 8
9156-SM-3 | Pipe Pile Stored Material | Material | Linear Feet |  | 8
3404-WO-08 | WO #08 - NS Barrier Modification (Design & Construction) | Material | Lump Sum |  | 8
3448 - COST | COST | Nonlabor |  |  | 1
3448 - MTLS | Materials | Material |  |  | 8
3448 - LS | LS | Material |  |  | 8
3448 - CY | CY | Material |  |  | 8
3448 - LF | LF | Material |  |  | 8
3448 - TN | TN | Material |  |  | 8
3448 - EA | EA | Material |  |  | 8
3448 - SF | SF | Material |  |  | 8
3448 - Ring Fab | Ring Fab | Material | Ring |  | 8
3448 - Ring Del | Ring Delivery | Material | Ring |  | 8
3448 - Ring Install | Ring Installation | Material | Ring |  | 8
3448 - VF | VF | Material | Vertical Footage |  | 8
UPC112815.25591 | Initial Geotechnical Investigations Field Investigations & Analysis 1 | Material | Lump Sum |  | 8
UPC112815.25591-3 | Initial Geotechnical Investigations Engineering Recommendations | Material | Lump Sum |  | 8
UPC112815.25591-10 | Early Grading Plan PWC/County Approval | Material | Lump Sum |  | 8
UPC112815.25591-11 | Public Hearing Advertise Public Hearing | Material | Lump Sum |  | 8
UPC112815.25591-1 | Supplemental Geotechnical Investigations Field Investigations & Analysis 1 | Material | Lump Sum |  | 8
UPC112815.25591-5 | Public Hearing Plans Perpare Plans | Material | Lump Sum |  | 8
UPC112815.25593 | Public Hearing Plans QA/QC | Material | Lump Sum |  | 8
UPC112815.25591-6 | Public Hearing Plans VDOT / County Review Approval | Material | Lump Sum |  | 8
3453 | 3453 - Balls Ford | Nonlabor |  |  | 1
9156 - DIRECT MTL | DIRECT COSTS MATERIALS | Material |  |  | 8
9156 - 20100 | MTL-TRAFFIC CONTROL | Material |  |  | 8
9156 - MAT1 | MTL-EROSION CONTROL | Material |  |  | 8
9156 - 202001 | Mtl-Eros Cntrl-Silt Fen | Material |  |  | 8
9156 - 202002 | Mtl-Eros Cntrl-Skimmers | Material |  |  | 8
9156 - 202003 | Mtl-Eros Cntrl-Snd Bag/ | Material |  |  | 8
9156 - 202004 | Mtl-Eros Cntrl-Matting | Material |  |  | 8
9156 - 202005 | Mtl-Eros Cntrl-Inlet Do | Material |  |  | 8
9156 - MAT2 | MTL-AGGREGATE-GENERAL | Material |  |  | 8
9156 - 203001 | Mtl-Cl A Stone-Temp | Material |  |  | 8
9156 - 203002 | Mtl-Cl B Stone-Temp | Material |  |  | 8
9156 - 203003 | Mtl-ABC Stone-Temp | Material |  |  | 8
9156 - 203004 | Mtl-#57 Stone-Temp | Material |  |  | 8
9156 - 203005 | Mtl-Cl 1 Stone-Permanen | Material |  |  | 8
9156 - 203006 | Mtl-Cl 2 Stone-Permanen | Material |  |  | 8
9156 - 203007 | Mtl-Cl B Stone-Permanen | Material |  |  | 8
9156 - 203008 | Mtl-#57 Stone Permanent | Material |  |  | 8
9156 - 203009 | Mtl-Pipe Bedding Stone | Material |  |  | 8
9156 - 203010 | Mtl-#4 Stn-Site Access/ | Material |  |  | 8
9156 - 203011 | Mtl-#78 Stone-MSE Backf | Material |  |  | 8
9156 - 203012 | Mtl-Sod | Material |  |  | 8
9156 - MAT3 | MTL-AGGREGATE-ROAD SECTION | Material |  |  | 8
9156 - 204001 | Mtl-ABC Stone-Permanent | Material |  |  | 8
9156 - 204002 | Mtl-#78 Stone-Bridge Ap | Material |  |  | 8
9156 - MAT4 | MTL-PLANT MATERIAL | Material |  |  | 8
9156 - 205001 | Plant Mtl-Concrete Sand | Material |  |  | 8
9156 - 205002 | Plant Mtl-#57/#78 Coars | Material |  |  | 8
9156 - MAT5 | MTL-CEMENT/FLYASH | Material |  |  | 8
9156 - 206001 | Plant Mtl-Cement | Material |  |  | 8
9156 - 206002 | Plant Mtl-Flyash | Material |  |  | 8
9156 - MAT6 | MTL-ASPHALT CONCRETE | Material |  |  | 8
9156 - 208001 | Mtl-HMA Intermediate | Material |  |  | 8
9156 - 208002 | Mtl-HMA Surface B | Material |  |  | 8
9156 - 208003 | Mtl-HMA Surface C | Material |  |  | 8
9156 - 208004 | Mtl-HMA Wedging | Material |  |  | 8
9156 - 208005 | Mtl-Tack | Material |  |  | 8
9156 - 208006 | Mtl-HMA Small Tools | Material |  |  | 8
9156 - MAT7 | MTL-GEOTEXTILE | Material |  |  | 8
9156 - 210001 | Mtl-Geotextile Ty 1/2/4 | Material |  |  | 8
9156 - 210002 | Mtl-Geotextile Ty 1/2/4 | Material |  |  | 8
9156 - 210003 | Mtl-Pvmt Overlay Fabric | Material |  |  | 8
9156 - 21100 | MTL-PIPE-CONCRETE | Material |  |  | 8
9156 - MAT8 | MTL-PIPE-METAL | Material |  |  | 8
9156 - 212001 | Mtl-CMP Pipe | Material |  |  | 8
9156 - 212002 | Mtl-DIP Pipe | Material |  |  | 8
9156 - 212003 | Mtl-Steel Casing | Material |  |  | 8
9156 - 212005 | Mtl-Pipe Pile | Material |  |  | 8
9156 - 21300 | MTL-PIPE-PLASTIC | Material |  |  | 8
9156 - 21400 | MTL-CONCRETE ADMIXTURE/W | Material |  |  | 8
9156 - MAT9 | MTL-PILING-STEEL H/W SECTION | Material |  |  | 8
9156 - 215001 | Mtl-H Pile | Material |  |  | 8
9156 - 215002 | Mtl-Pile Jacket | Material |  |  | 8
9156 - MAT10 | MTL-GENERAL BRIDGE ITEMS | Material |  |  | 8
9156 - 218001 | Mtl-Bearing Pads | Material |  |  | 8
9156 - 218002 | Mtl-Expansion Jnt | Material |  |  | 8
9156 - 218003 | *Bridge Structure Upgra | Material |  |  | 8
9156 - 218005 | Mtl-Sole Plate/Anchor A | Material |  |  | 8
9156 - MAT11 | MTL-SOUNDWALLS | Material |  |  | 8
9156 - 221001 | Mtl-Soundwall Sonotube | Material |  |  | 8
9156 - 221002 | Mtl-Sound Wall Coping | Material |  |  | 8
9156 - 221003 | Mtl-Sound Wall End Post | Material |  |  | 8
9156 - 221004 | Mtl-Sound Wall Footing | Material |  |  | 8
9156 - 221005 | Mtl-Sound Wall Posts | Material |  |  | 8
9156 - 221006 | Mtl-Struct Mtd SW Hardw | Material |  |  | 8
9156 - 221007 | Mtl-Struct Mtd SW Panel | Material |  |  | 8
9156 - 221008 | Mtl-Struct Mtd SW Posts | Material |  |  | 8
9156 - MAT12 | MTL-CONCRETE | Material |  |  | 8
9156 - 222001 | Mtl-Conc-SCAC | Material |  |  | 8
9156 - 222002 | Mtl-Point/Patch | Material |  |  | 8
9156 - 222003 | Mtl-Conc Paving-Spall R | Material |  |  | 8
9156 - 222005 | Mtl-Concrete -#3000-Cl | Material |  |  | 8
9156 - 222006 | Mtl-Concrete -#4500-Cl | Material |  |  | 8
9156 - 222007 | Mtl-PCCP Embeds | Material |  |  | 8
9156 - 222008 | Mtl-QC/MIT/Profilograph | Material |  |  | 8
9156 - 222009 | Mtl-Conc Pave Survey | Material |  |  | 8
9156 - 222010 | Mtl-Move Paver | Material |  |  | 8
9156 - 222011 | Mtl-Paving Crew Lodging | Material |  |  | 8
9156 - 222012 | Mtl-Paving Crew Per Die | Material |  |  | 8
9156 - MAT13 | MTL-PRECAST MATERIALS | Material |  |  | 8
9156 - 224001 | Mtl-Single Face Barrier | Material |  |  | 8
9156 - 224002 | Mtl-Precast Drain Struc | Material |  |  | 8
9156 - 224003 | Mtl-Precast Endwalls | Material |  |  | 8
9156 - 224004 | Mtl-Conc Washout | Material |  |  | 8
9156 - 224005 | Mtl-Conc Medallion | Material |  |  | 8
9156 - 22500 | MTL-PRECAST BEAMS | Material |  |  | 8
9156 - MAT14 | MTL-FORMWORK/CARPENTRY | Material |  |  | 8
9156 - 226001 | Mtl-False Deck | Material |  |  | 8
9156 - 226002 | Mtl-Form Liner | Material |  |  | 8
9156 - 226003 | Mtl-Clean/Adjust OH Bra | Material |  |  | 8
9156 - 226004 | Mtl-Crane Mats | Material |  |  | 8
9156 - 226005 | Mtl-PCCP Forms | Material |  |  | 8
9156 - 226006 | Mtl-SIP Forms | Material |  |  | 8
9156 - 226007 | Mtl-Sndwl Struct Mnt Fr | Material |  |  | 8
9156 - 226008 | Mtl-Substruct Formwork | Material |  |  | 8
9156 - 226009 | Mtl-Superstruct Formwor | Material |  |  | 8
9156 - 22700 | MTL-STRUCTURAL STEEL | Material |  |  | 8
9156 - MAT15 | MTL-MISCELLANEOUS METALS | Material |  |  | 8
9156 - 228001 | Mtl-Settlement Gages | Material |  |  | 8
9156 - 228002 | Mtl-Frames/Grates/Gates | Material |  |  | 8
9156 - 228003 | Mtl-Backwall MSE Straps | Material |  |  | 8
9156 - MAT16 | MTL-REINFORCING STEEL | Material |  |  | 8
9156 - 229001 | Mtl-Rebar-Black | Material |  |  | 8
9156 - 229002 | Mtl-Rebar-Epoxy | Material |  |  | 8
9156 - 229003 | Mtl-Rebar-Accessories | Material |  |  | 8
9156 - MAT17 | MTL-EMPLOYEE/PUBLIC PROTECTION | Material |  |  | 8
9156 - 232001 | Mtl-Fall Protection | Material |  |  | 8
9156 - 232002 | Mtl-Safety Fence | Material |  |  | 8
9156 - 232003 | Mtl-Trench Box | Material |  |  | 8
9156 - MAT18 | MTL-PLANT FACILITY | Material |  |  | 8
9156 - 233001 | Mtl-Plant-Setup | Material |  |  | 8
9156 - 233002 | Mtl-Plant-Teardown | Material |  |  | 8
9156 - 233003 | Mtl-Plant-Ops | Material |  |  | 8
9156 - 233004 | Mtl-Plant-Utilities | Material |  |  | 8
9156 - 23400 | MTL-TRESTLE | Material |  |  | 8
9156 - MAT19 | MTL-DIRECT MTL INCIDENTALS | Material |  |  | 8
9156 - 29001 | Mtl-Railroad Plan Revie | Material |  |  | 8
9156 - 29002 | Mtl-Slurry Disposal | Material |  |  | 8
9156 - 29003 | Mtl-All Salvage | Material |  |  | 8
9156 - 30010 | Design Sub | Material |  |  | 8
9156 - 30020 | MSE/Soundwall Sub | Material |  |  | 8
9156 - 30030 | Box Culvert Sub | Material |  |  | 8
9156 - 30040 | Bar Rail Sub | Material |  |  | 8
9156 - 30050 | Clear & Grub Sub | Material |  |  | 8
9156 - 30060 | Asbestos Removal Sub | Material |  |  | 8
9156 - 30080 | Bump Grind Sub | Material |  |  | 8
9156 - 30090 | Conc Deck Groove Sub | Material |  |  | 8
9156 - 30100 | Conc/ACP Sawing Sub | Material |  |  | 8
9156 - 30110 | Concrete Apron Sub | Material |  |  | 8
9156 - 30120 | Concrete Flatwork Sub | Material |  |  | 8
9156 - 30130 | Concrete Pump Sub | Material |  |  | 8
9156 - 30140 | Demolition Sub | Material |  |  | 8
9156 - 30150 | DRB Sub | Material |  |  | 8
9156 - 30170 | Fencing Sub | Material |  |  | 8
9156 - 30180 | Grinding Sub | Material |  |  | 8
9156 - 30190 | Guardrail Sub | Material |  |  | 8
9156 - 30210 | ITS Sub | Material |  |  | 8
9156 - 30220 | Jacking Sub | Material |  |  | 8
9156 - 30230 | Landscape/Eros Control S | Material |  |  | 8
9156 - 30240 | Lighting Sub | Material |  |  | 8
9156 - 30250 | Masonry Sub | Material |  |  | 8
9156 - 30260 | Metal Deck Sub | Material |  |  | 8
9156 - 30270 | Milling Sub | Material |  |  | 8
9156 - 30280 | Pavement Marking Sub | Material |  |  | 8
9156 - 30290 | PDA/CSL Test Sub | Material |  |  | 8
9156 - 30310 | Police Sub | Material |  |  | 8
9156 - 30320 | Protective Coat Sub | Material |  |  | 8
9156 - 30330 | RCC Sub | Material |  |  | 8
9156 - 30340 | Rebar Sub | Material |  |  | 8
9156 - 30350 | RR Flag Sub | Material |  |  | 8
9156 - 30360 | Rumble Strip Sub | Material |  |  | 8
9156 - 30370 | Saw/Seal Sub | Material |  |  | 8
9156 - 30380 | Sign Sub | Material |  |  | 8
9156 - 30390 | Signal Sub | Material |  |  | 8
9156 - 30400 | Slipform Sub | Material |  |  | 8
9156 - 30410 | Soil Nail Sub | Material |  |  | 8
9156 - 30430 | Stabilization Sub | Material |  |  | 8
9156 - 30440 | Street Sweeping Sub | Material |  |  | 8
9156 - 30450 | Toll Vault Sub | Material |  |  | 8
9156 - 30460 | Traffic Barrier Sub | Material |  |  | 8
9156 - 30470 | Underdrain Sub | Material |  |  | 8
9156 - 30480 | Welding Sub | Material |  |  | 8
9156 - 30490 | Well Sub | Material |  |  | 8
9156 - 30500 | MOT Sub | Material |  |  | 8
9156 - HAULING | HAULING | Material |  |  | 8
9156 - HAUL-TON | HAUL BY TON | Material |  |  | 8
9156 - 351001 | Haul By TN-HMA | Material |  |  | 8
9156 - 351002 | Haul By TN-#10 Bedding | Material |  |  | 8
9156 - 351003 | Haul By TN-Agg Base Crs | Material |  |  | 8
9156 - 351005 | Haul By TN-TY III-Bridg | Material |  |  | 8
9156 - 351006 | Haul By TN-MSE #78 Ston | Material |  |  | 8
9156 - 351007 | Haul By TN-#4/#57/#2S/S | Material |  |  | 8
9156 - 351008 | Haul By TN-Cl A/B/1/2/4 | Material |  |  | 8
9156 - 351009 | Haul By TN-Eros Control | Material |  |  | 8
9156 - HAUL-CY | HAUL BY CY | Material |  |  | 8
9156 - 352001 | Haul By CY-Wet Conc-Sem | Material |  |  | 8
9156 - HAUL-LOAD | HAUL BY LOAD | Material |  |  | 8
9156 - 353001 | Haul By LD-On/Offsite | Material |  |  | 8
9156 - 353002 | Haul By LD-Trestle/Mat/ | Material |  |  | 8
9156 - 353003 | Haul By LD-Spoil/Waste/ | Material |  |  | 8
9156 - HAUL5-HOUR | HAUL BY HOUR | Material |  |  | 8
9156 - 354001 | Haul By HR-Demo | Material |  |  | 8
9156 - 354002 | Haul By HR-Millings | Material |  |  | 8
9156 - 354003 | Haul By HR-Excavation | Material |  |  | 8
9156 - EQUIP | EQUIPMENT | Material |  |  | 8
9156 - 36010 | EQUIPMENT OWNERSHIP | Material |  |  | 8
9156 - 36020 | FUEL | Material |  |  | 8
9156 - 36030 | FOG | Material |  |  | 8
9156 - 36040 | EQUIP ABUSE/DAMAGE | Material |  |  | 8
9156 - ESCAL | MISC DIRECT | Material |  |  | 8
9156 - 39010 | DIRECT LABOR ESCALATION | Material |  |  | 8
9156 - TRAFFIC | TRAFFIC CONTROL | Material |  |  | 8
9156 - TRAFFIC1 | MAINTENANCE OF TRAFFIC | Material |  |  | 8
9156 - 405101 | Driveway Maintenance St | Material |  |  | 8
9156 - 405102 | Excavation-Road Flagger | Material |  |  | 8
9156 - 405103 | MOT Maint Crew | Material |  |  | 8
9156 - 405104 | MOT-Flagger | Material |  |  | 8
9156 - 405105 | Truck Mtd Attenuator | Material |  |  | 8
9156 - E&S | EROSION CONTROL | Material |  |  | 8
9156 - E&S1 | EROSION CONTROL-CREW | Material |  |  | 8
9156 - 410101 | Maint Erosion Control | Material |  |  | 8
9156 - 410102 | Rain Event Response | Material |  |  | 8
9156 - 410103 | Silt Excavation-Basins/ | Material |  |  | 8
9156 - E&S2 | EROSION CONTROL-DEVICES | Material |  |  | 8
9156 - 410201 | Plc Eros Cntrl Stone-Cl | Material |  |  | 8
9156 - 410202 | Plc Sediment Cntrl Ston | Material |  |  | 8
9156 - 410203 | Remove Silt Fence | Material |  |  | 8
9156 - 410204 | Skimmers/Conc Washout | Material |  |  | 8
9156 - 410205 | Temp Slope Drains | Material |  |  | 8
9156 - UTIL | UTILITY RELOCATION | Material |  |  | 8
9156 - 41510 | POTHOLING CREWS | Material |  |  | 8
9156 - DEMO-PVMT | DEMOLITION | Material |  |  | 8
9156 - 42010 | DEMO-AC PAVEMENT | Material |  |  | 8
9156 - 42020 | DEMO-CONC PAVEMENT | Material |  |  | 8
9156 - DEOM-BRG | DEMO-BRIDGE | Material |  |  | 8
9156 - 420401 | Demo Bridge-Rmv Deck Sl | Material |  |  | 8
9156 - 420402 | Demo Bridge-Rmv Rail/OH | Material |  |  | 8
9156 - 420403 | Demo Bridge-Rmv Steel B | Material |  |  | 8
9156 - 420404 | Demo Bridge-Shielding | Material |  |  | 8
9156 - 420405 | Demo Bridge-Substructur | Material |  |  | 8
9156 - 42060 | DEMO-DRAINAGE | Material |  |  | 8
9156 - SITE | SITE WORK | Material |  |  | 8
9156 - 42520 | TEMPORARY FENCING | Material |  |  | 8
9156 - 42570 | SIDEWALK/CURB PREP | Material |  |  | 8
9156 - EW | EARTHWORK | Material |  |  | 8
9156 - ACCESS | CONSTRUCTION ACCESS | Material |  |  | 8
9156 - 430201 | Assem Used Trstl Prior | Material |  |  | 8
9156 - 430202 | Cut Off Piles-Trestle | Material |  |  | 8
9156 - 430203 | Earthwork For Trestle C | Material |  |  | 8
9156 - 430204 | Fab Girder/Template-Tre | Material |  |  | 8
9156 - 430205 | Grade/Prep For Site Acc | Material |  |  | 8
9156 - 430206 | Instl Trestle/Trestle F | Material |  |  | 8
9156 - 430207 | Load Out Mtl To Trestle | Material |  |  | 8
9156 - 430208 | Load Out Trestle Mtrl-A | Material |  |  | 8
9156 - 430209 | Pioneering-Build Haul R | Material |  |  | 8
9156 - 430210 | Remove Trestle Spans | Material |  |  | 8
9156 - 430211 | Stream Crossings | Material |  |  | 8
9156 - 430212 | Unload/Store Trestle Mt | Material |  |  | 8
9156 - 430213 | Air Bridge Construction | Material |  |  | 8
9156 - COM EXC | COMMON EXCAVATION/FILL | Material |  |  | 8
9156 - 430401 | Cut To Fill Light Cuts/ | Material |  |  | 8
9156 - 4304010 | Temp Ditches | Material |  |  | 8
9156 - 4304011 | Dewater Lower Table | Material |  |  | 8
9156 - 430402 | Cut To Fill On Road Tru | Material |  |  | 8
9156 - 430403 | Cut To Fill W/ Off Road | Material |  |  | 8
9156 - 430404 | Cut To Fill With Truck | Material |  |  | 8
9156 - 430405 | Cut To Fill-Tractr Scra | Material |  |  | 8
9156 - 430407 | Excavate Spills Basins | Material |  |  | 8
9156 - 430408 | Haul Road Maintenance | Material |  |  | 8
9156 - 430409 | Proof Roll | Material |  |  | 8
9156 - RW EXC | ROADWAY EXCAVATION/FILL | Material |  |  | 8
9156 - 430601 | Ty III Reinf Bridge App | Material |  |  | 8
9156 - 43110 | TEMPORARY EARTHWORK-CUT/ | Material |  |  | 8
9156 - 43120 | TOPSOIL STRIPPING | Material |  |  | 8
9156 - UNSUIT | UNSUITABLE EXCAVATION/BACKFILL | Material |  |  | 8
9156 - 431601 | Dewater Ponds | Material |  |  | 8
9156 - 431602 | Excavate/Haul/Bkfl Unde | Material |  |  | 8
9156 - 431603 | Excavate/Haul/Spread Mu | Material |  |  | 8
9156 - FG-SG | FINEGRADE SUBGRADE | Material |  |  | 8
9156 - 432401 | Fine Grade Slopes | Material |  |  | 8
9156 - 432402 | Fine Grade Subgrade | Material |  |  | 8
9156 - SLOPE | SLOPE PROTECTION | Material |  |  | 8
9156 - 433201 | FG & Plc Conc Ditch | Material |  |  | 8
9156 - 433202 | Slope Protect-Rip Rap I | Material |  |  | 8
9156 - GEO | GEOFABRIC/GEOGRID | Material |  |  | 8
9156 - 433401 | Geotextile Soil Stabili | Material |  |  | 8
9156 - 433402 | Pavement Overlay Fabric | Material |  |  | 8
9156 - PAVE BASE | PAVEMENT BASE | Material |  |  | 8
9156 - 435101 | Fine Grade ABC @ 4.25" | Material |  |  | 8
9156 - 435102 | Fine Grade ABC @ 8" & 1 | Material |  |  | 8
9156 - ABC | AGGREGATE SUBBASE | Material |  |  | 8
9156 - 435201 | Plc/Cmpct ABC @ 4.25" | Material |  |  | 8
9156 - 435202 | Plc/Cmpct ABC @ 8" & 10 | Material |  |  | 8
9156 - 435203 | Temp ABC Stone-P&C/FG/R | Material |  |  | 8
9156 - 43560 | SHOULDER BACKUP | Material |  |  | 8
9156 - ASP | AC PAVING | Material |  |  | 8
9156 - ASP-MAIN | AC PAVE-MAINLINE | Material |  |  | 8
9156 - 440101 | I19.0C - Y Lines w/Ramp | Material |  |  | 8
9156 - 440102 | I19.0C-Turbine | Material |  |  | 8
9156 - 440103 | S9.5B-Mainline @ 1.25" | Material |  |  | 8
9156 - 440104 | S9.5-Y Line-New-Widen/O | Material |  |  | 8
9156 - 440105 | S9.5C-Turbine | Material |  |  | 8
9156 - 440106 | Y line Wedging/Driveway | Material |  |  | 8
9156 - 440107 | Access Point for Daylig | Material |  |  | 8
9156 - 440108 | Temp Asphalt S9.5C | Material |  |  | 8
9156 - 440109 | Temp Asphalt I19.0C | Material |  |  | 8
9156 - 440110 | Temp Asphalt B25.0C | Material |  |  | 8
9156 - CONC | CONCRETE PAVING | Material |  |  | 8
9156 - SLIP | CONCRETE PAVE-FULL LANE SLIP | Material |  |  | 8
9156 - 445101 | All Grind Slurry Dispos | Material |  |  | 8
9156 - 445102 | GPS Crew - Paving | Material |  |  | 8
9156 - 445103 | Hand Pours-Conc Pvmt | Material |  |  | 8
9156 - 445104 | Move/Erect/Prep Conc Pv | Material |  |  | 8
9156 - 445105 | Pump Dry Slurry Pond | Material |  |  | 8
9156 - 445106 | Sawcut/Rmv for Headr-Co | Material |  |  | 8
9156 - 445107 | Set/Rmv Forms-Conc Pvmt | Material |  |  | 8
9156 - 445108 | Slip Conc-Good 10-18' o | Material |  |  | 8
9156 - 445109 | Slip Conc-Good 24' w/DB | Material |  |  | 8
9156 - 445110 | Slip Conc-Slow 10-18' o | Material |  |  | 8
9156 - 445111 | Slip Conc-Slow 24' w/DB | Material |  |  | 8
9156 - 445112 | Trans/Long Jt-D&G-Dwl/T | Material |  |  | 8
9156 - 445113 | Transverse Jts/Tie Bar- | Material |  |  | 8
9156 - 445114 | U/H Embeds for Conc Pvm | Material |  |  | 8
9156 - 445115 | Width Changes-Conc Pvmt | Material |  |  | 8
9156 - 445116 | Winter Cure/Exp Jt | Material |  |  | 8
9156 - PIPE | PIPE AND DRAINAGE | Material |  |  | 8
9156 - 45510 | WATER LINE (6-12 INCH) | Material |  |  | 8
9156 - 45520 | WATER LINE (16-36 INCH) | Material |  |  | 8
9156 - SD-1 | STORM DRAIN PIPE (12-30 IN) | Material |  |  | 8
9156 - 455401 | 15" RCP Pipe | Material |  |  | 8
9156 - 455409 | 15" HDPE Pipe | Material |  |  | 8
9156 - 455402 | 15" to 36" Steel Pipe | Material |  |  | 8
9156 - 4554010 | 18" HDPE Pipe | Material |  |  | 8
9156 - 455403 | 18" RCP Pipe | Material |  |  | 8
9156 - 4554011 | 24" HDPE Pipe | Material |  |  | 8
9156 - 455404 | 24" RCP Pipe | Material |  |  | 8
9156 - 4554012 | 30" HDPE Pipe | Material |  |  | 8
9156 - 455405 | 30" RCP Pipe | Material |  |  | 8
9156 - 455406 | Desilt Proposed Pipe | Material |  |  | 8
9156 - 455407 | Install Pipe Collar | Material |  |  | 8
9156 - 455408 | Layout String Pipe/Supt | Material |  |  | 8
9156 - SD-2 | STORM DRAIN PIPE (36-60 IN) | Material |  |  | 8
9156 - 455501 | > 48" RCP Pipe | Material |  |  | 8
9156 - 455504 | 36" RCP Pipe | Material |  |  | 8
9156 - 455507 | 36" HDPE Pipe | Material |  |  | 8
9156 - 455505 | 42" RCP Pipe | Material |  |  | 8
9156 - 455508 | 42" HDPE Pipe | Material |  |  | 8
9156 - 455506 | 48" RCP Pipe | Material |  |  | 8
9156 - 455509 | 48" HDPE Pipe | Material |  |  | 8
9156 - SD-3 | STORM DRAIN INLET/CB/END | Material |  |  | 8
9156 - 455701 | Drn Struct-Tie in/Conve | Material |  |  | 8
9156 - 455702 | Instl Endwalls/Sluice G | Material |  |  | 8
9156 - 455703 | Install Frame & Grate | Material |  |  | 8
9156 - SD-4 | STORM DRAIN MH (48-72 IN) | Material |  |  | 8
9156 - 455802 | Install Drainage Str | Material |  |  | 8
9156 - 455803 | Install Drainage Str-In | Material |  |  | 8
9156 - 45660 | JACK AND BORE (24"-48") | Material |  |  | 8
9156 - 45680 | DRAINAGE RIP-RAP | Material |  |  | 8
9156 - UD | UNDERDRAIN | Material |  |  | 8
9156 - 457401 | Spill Basins | Material |  |  | 8
9156 - STR | STRUCTURE FOUNDATION | Material |  |  | 8
9156 - STR-EXC | STRUCTURE EXCAVATION | Material |  |  | 8
9156 - 470101 | Backfill Interior Bents | Material |  |  | 8
9156 - 470102 | Fnd Excav-Interior Bent | Material |  |  | 8
9156 - 47030 | FINEGRADE FOR FOUNDATION | Material |  |  | 8
9156 - PILE | DRIVEN PILE | Material |  |  | 8
9156 - 470601 | Abutment Restrikes | Material |  |  | 8
9156 - 470602 | Drive HP12/14 Steel Pil | Material |  |  | 8
9156 - 470603 | Fab/Instl/Rmv HP Templa | Material |  |  | 8
9156 - 470604 | Grade & CO HP12/14 Pile | Material |  |  | 8
9156 - 470605 | Install 12"/14" H-Pile | Material |  |  | 8
9156 - 470606 | Pile Redrives-HP12/14 P | Material |  |  | 8
9156 - 470607 | Setup Time Pile Driver/ | Material |  |  | 8
9156 - 470608 | Unld/Dray Pile Mtl | Material |  |  | 8
9156 - 470609 | Fab/Maint/Move Pipe Pil | Material |  |  | 8
9156 - 470610 | PDA Testing @ Pile Locs | Material |  |  | 8
9156 - 470611 | Install 30" D P-PIle Sp | Material |  |  | 8
9156 - 470612 | Pick/Pos/Drive 30" Pipe | Material |  |  | 8
9156 - BRINDGE | STRUCTURAL CONCRETE-BRIDGE | Material |  |  | 8
9156 - SUBSTRUCT | BRIDGE SUBSTRUCTURE-LAND | Material |  |  | 8
9156 - 475201 | F/S Substruct-Ftgs/Cols | Material |  |  | 8
9156 - 475202 | Frm Soffit-30" D PP She | Material |  |  | 8
9156 - 475203 | Patch/Finish Substr Con | Material |  |  | 8
9156 - 475204 | Place Class A Substr Co | Material |  |  | 8
9156 - 475205 | Prep/Apply Epoxy Cap Co | Material |  |  | 8
9156 - 475206 | Install & Prep Formline | Material |  |  | 8
9156 - 475207 | F/S Substruct Columns | Material |  |  | 8
9156 - 475208 | F/S Substruct Caps | Material |  |  | 8
9156 - 475209 | F/S Substruct End Bent | Material |  |  | 8
9156 - BEAM | BRIDGE BEAMS-SET PRECAST | Material |  |  | 8
9156 - 476001 | Instl Sole Plate/Weld S | Material |  |  | 8
9156 - 476002 | PSC Beam-Erect FIB's 36 | Material |  |  | 8
9156 - 476003 | PSC Beam-Erect FIB's 54 | Material |  |  | 8
9156 - 476004 | PSC Beam-Erect FIB's 72 | Material |  |  | 8
9156 - 476005 | PSC Beam-Instl Anchor B | Material |  |  | 8
9156 - 476006 | PSC Beam-Instl Crane Pa | Material |  |  | 8
9156 - 476007 | PSC Beam-Instl Diaph As | Material |  |  | 8
9156 - 476008 | PSC Beam-Rmv Temp X-Bra | Material |  |  | 8
9156 - DECK | BRIDGE DECK-ON GIRDER | Material |  |  | 8
9156 - 476401 | Clean/Adjust OH Bracket | Material |  |  | 8
9156 - 476402 | Cure Bridge Decks | Material |  |  | 8
9156 - 476403 | F/S Bridge Deck Overhan | Material |  |  | 8
9156 - 476404 | F/S Suprstruct (No OH)/ | Material |  |  | 8
9156 - 476405 | Form/Seal Bridge Deck S | Material |  |  | 8
9156 - 476406 | Patch/Finish Superstruc | Material |  |  | 8
9156 - 476407 | Plc Bridge Deck Slab Po | Material |  |  | 8
9156 - 476408 | Plc Sdwk/Median/End Pst | Material |  |  | 8
9156 - 476409 | Set Up/Brk Dwn Screed/D | Material |  |  | 8
9156 - MISC | BRIDGE-MISCALLANEOUS | Material |  |  | 8
9156 - 48300 | BRIDGE EXPANSION JOINTS | Material |  |  | 8
9156 - 48400 | BRIDGE SHIELDING | Material |  |  | 8
9156 - APPR | APPROACH SLAB | Material |  |  | 8
9156 - 484501 | F/S Approach Slabs | Material |  |  | 8
9156 - 484502 | FG Subgrade For App Sla | Material |  |  | 8
9156 - 484503 | Place App Slab | Material |  |  | 8
9156 - 484504 | Setup/Prep Screed App S | Material |  |  | 8
9156 - WALLS | STRUCTURAL CONCRETE-WALLS | Material |  |  | 8
9156 - MSE | RETAINING WALL-MSE | Material |  |  | 8
9156 - 517201 | MSE Wall-CIP Coping | Material |  |  | 8
9156 - 517202 | MSE Wall-Excav/FG | Material |  |  | 8
9156 - SOUND | SOUND WALL | Material |  |  | 8
9156 - 517401 | Sound Wall-Access | Material |  |  | 8
9156 - 517402 | Sound Wall-Backfill | Material |  |  | 8
9156 - 517403 | Sound Wall-Install Post | Material |  |  | 8
9156 - 517404 | Sound Wall-Instl Coping | Material |  |  | 8
9156 - 517405 | Sound Wall-Plc Concrete | Material |  |  | 8
9156 - 517406 | Sound Wall-Prep/Drill 3 | Material |  |  | 8
9156 - 517407 | Sound Wall-Set Conc Foo | Material |  |  | 8
9156 - 517408 | Sound Wall-Struct Mount | Material |  |  | 8
9156 - BARRIER | STRUCTURAL CONCRETE -BARRIER | Material |  |  | 8
9156 - BARRIER-PC | BARRIER WALL-PRECAST | Material |  |  | 8
9156 - 524001 | Grade/Bkfl 1 Face Barri | Material |  |  | 8
9156 - 524002 | Set 1 Face Barrier (Pre | Material |  |  | 8
9156 - GRIND | STRUCTURAL CONCRETE-SURFACE | Material |  |  | 8
9156 - 52520 | DECK GRINDING AND GROOVI | Material |  |  | 8
9156 - STAIN | CONCRETE SURFACE FINISHES | Material |  |  | 8
9156 - 525301 | Clean/Prep Brdg Surf Fo | Material |  |  | 8
9156 - 525302 | Support Concrete Stain | Material |  |  | 8
9156 - PLATFORM | STRUCTURAL-WORK PLATFORM | Material |  |  | 8
9156 - 532001 | Plc/Rmv Crane Mats | Material |  |  | 8
9156 - 532002 | Temp Access-Strip/Grd/P | Material |  |  | 8
9156 - REBAR | REINFORCING STEEL | Material |  |  | 8
9156 - 53530 | UNLOAD/HANDLE/ASSIST REB | Material |  |  | 8
9156 - BUILDING | BUILDING STRUCTURAL | Material |  |  | 8
9156 - COLUMN | BLDG CIP COLUMNS | Material |  |  | 8
9156 - 852001 | F/S ITS Columns/Fndtn | Material |  |  | 8
9156 - 852002 | Plc/Patch/Fin ITS Colum | Material |  |  | 8
9156 - 852003 | Signs-Aesthetic piers | Material |  |  | 8
9156 - CONC PLANT | CONCRETE BATCH PLANT | Material |  |  | 8
9156 - OPER | CNC PLANT-OPERATE PLANT | Material |  |  | 8
9156 - 931001 | Plant Ops-Conc Pl | Material |  |  | 8
9156 - 931002 | QC-Conc Pl | Material |  |  | 8
9156 - 931003 | Stock Agg/Agg To Plt-Co | Material |  |  | 8
9156 - SET UP | CNC PLANT-SET UP/TEAR DOWN | Material |  |  | 8
9156 - 932001 | Dismantle/Restore Site- | Material |  |  | 8
9156 - 932002 | Setup Plant-Conc Pl | Material |  |  | 8
9156 - 932003 | Site Prep-Conc Pl | Material |  |  | 8
9156 - SUBS | (New Resource) | Material |  |  | 8
9156 - FG - ABC | FINEGRADE AGGREGATE BASE | Material |  |  | 8
9156 - TEMP ACCESS | TEMPORARY ACCESS | Material |  |  | 8
9156 - JDE | 9156 - JDE Codes | Material |  |  | 8
9156-SM-4 | Anchor Bolt Stored Materials | Material |  |  | 8
9156-SM-5 | Cutting Shoes Stored Materials | Material |  |  | 8
9156-SA12 | SA#12 - Corridor Coordination - Additional Design Effort | Material | Lump Sum |  | 8
9156-SA13 | SA#13 - Change to Pavement Typical X-Sec | Material | Lump Sum |  | 8
9176 | 9176 - Van Wyck Expressway | Nonlabor |  |  | 1
9176-210000-210005 | DB - Construction Work Intersection Reco - Subbase Grading | Material | Square Feet |  | 8
9176-210000-210010 | DB - Construction Work Intersection Reco - Base Grading | Material | Square Feet |  | 8
9176-210000-210015 | DB - Construction Work Intersection Reco - Supply Subbase | Material | Ton |  | 8
9176-210000-660010 | DB - Construction Work Intersection Reco - Place Base Concrete | Material | Square Feet |  | 8
9176-210000-660033 | DB - Construction Work Intersection Reco - Set Forms | Material | Square Feet |  | 8
9176-210000-660034 | DB - Construction Work Intersection Reco - Supply Forms | Material | Square Feet |  | 8
9176-210000-660040 | DB - Construction Work Intersection Reco - Cure Concrete | Material | Square Feet |  | 8
9176-210000-660050 | DB - Construction Work Intersection Reco - Night Plant Openings | Material | Each |  | 8
9176-210000-660060 | DB - Construction Work Intersection Reco - Night Concrete Trucks | Material | Day |  | 8
9176-210000-660065 | DB - Construction Work Intersection Reco - Green Cut & Place Geotextile | Material | Linear Feet |  | 8
9176-210000-660070 | DB - Construction Work Intersection Reco - Furnish Concrete | Material | Cubic Yard |  | 8
9176-210000-661005 | DB - Construction Work Intersection Reco - Drill & Grout Dowels | Material | Each |  | 8
9176-210000-661010 | DB - Construction Work Intersection Reco - Supply Dowels | Material | Each |  | 8
9176-220000-220000.A | Traffic Enforcement Agents - Traffic Enforcement Agents | Material | Lump Sum |  | 8
9176-225000-290000.A | Design-Build - Force Account Work - Design-Build - Force Account Work | Material | Lump Sum |  | 8
9176-310000-310000.A | Design-Build - Design Services - Design-Build - Design Services | Material | Lump Sum |  | 8
9176-320000-320000.A | Design-Build - Construction Inspection Services - Design-Build - Construction Inspection Services | Material | Lump Sum |  | 8
9176-330000-330000.A | Design-Build - Quality Control Services - Design-Build - Quality Control Services | Material | Lump Sum |  | 8
9176-340010-230000.A | Con Edison Owner's Allowance - Design Build - Utility Related Work - Con Ed (Elec | Material | Lump Sum |  | 8
9176-340110-240000.A | National Grid Owner's Allowance - Design Build - Utility Related Work - National Gri | Material | Lump Sum |  | 8
9176-340210-250000.A | Verizon Owner's Allowance - Design Build - Utility Related Work - Verizon | Material | Lump Sum |  | 8
9176-340310-260000.A | Altice Owner's Allowance - Design Build - Utility Related Work - Altice (Cabl | Material | Lump Sum |  | 8
9176-340410-270000.A | Charter Spectrum Owner's Allowance - Design Build - Utility Related Work - Charter (Spe | Material | Lump Sum |  | 8
9176-340510-280000.A | Crown Castle Owner's Allowance - Design Build - Utility Related Work - Crown Castle | Material | Lump Sum |  | 8
9176-500011-904000 | MPT Materials - MPT Materials | Material | Lump Sum |  | 8
9176-500011-904010 | MPT Materials - Tow Truck Service for Cattle Shoot between Jamaica & Hillside | Material | Month |  | 8
9176-500011-904020 | MPT Materials - I/R/Reset Impact att and sand | Material | Each |  | 8
9176-500012-904100 | Temporary Barrier - Teporary Concrete Barrier | Material | Lump Sum |  | 8
9176-500012-904101 | Temporary Barrier - Set Barrier | Material | Linear Feet |  | 8
9176-500012-904102 | Temporary Barrier - Relocate Barrier | Material | Linear Feet |  | 8
9176-500012-904103 | Temporary Barrier - Remove From Site | Material | Linear Feet |  | 8
9176-500012-904104SALV | Temporary Barrier - salvage | Material | Linear Feet |  | 8
9176-500013-904125 | Temporary Striping - Install Temporary Striping | Material | Linear Feet |  | 8
9176-500013-904130 | Temporary Striping - Remove Temporary Striping | Material | Linear Feet |  | 8
9176-500014-904150 | Lane Closures Day - Lane Closures VWE Days | Material | Lump Sum |  | 8
9176-500015-9041065 | Lane Closures Night - Lane Closures VWE Nights | Material | Lump Sum |  | 8
9176-500022-904000 | MPT Materials - MPT Materials | Material | Lump Sum |  | 8
9176-500022-904020 | MPT Materials - I/R/Reset Impact att | Material | Each |  | 8
9176-500024-904100 | Temporary Concrete Barrier - Teporary Concrete Barrier | Material | Linear Feet |  | 8
9176-500024-904101 | Temporary Concrete Barrier - Set Barrier | Material | Linear Feet |  | 8
9176-500024-904102 | Temporary Concrete Barrier - Relocate Barrier | Material | Linear Feet |  | 8
9176-500024-904103 | Temporary Concrete Barrier - Remove From Site | Material | Linear Feet |  | 8
9176-500024-904104SALV | Temporary Concrete Barrier - salvage | Material | Linear Feet |  | 8
9176-500026-904125 | Tempoary Pavement Striping - Install Temporary Pavement Striping | Material | Linear Feet |  | 8
9176-500026-904130 | Tempoary Pavement Striping - Remove Temp Pavement Stripe | Material | Linear Feet |  | 8
9176-500028-904150 | Lane Closures Local Day - Lane Closures Local Days | Material | Day |  | 8
9176-500030-9041065 | Lane Closures Local Night - Lane Closures Local Nights | Material | Day |  | 8
9176-500032-904170 | Flaggers - Flaggers | Material | Day |  | 8
9176-500034-656010 | Temporary Asphalt - Asphalt Material | Material | Ton |  | 8
9176-500034-656015 | Temporary Asphalt - Install Asphalt Pavement Temporary | Material | Lump Sum |  | 8
9176-500034-656020 | Temporary Asphalt - Tack Coat | Material | Lump Sum |  | 8
9176-500034-656025 | Temporary Asphalt - Base Grade | Material | Square Feet |  | 8
9176-500034-656030 | Temporary Asphalt - Subbase Grade | Material | Square Feet |  | 8
9176-500034-656035 | Temporary Asphalt - Furnish RCA | Material | Ton |  | 8
9176-500036-902001 | Temporary Timber Curb W/ Fence - Timber Barracade | Material | Linear Feet |  | 8
9176-500036-902004 | Temporary Timber Curb W/ Fence - Install Timber Barracade | Material | Lump Sum |  | 8
9176-500038-520005 | Test Pits - Dig Test Pits | Material | Each |  | 8
9176-500038-520010 | Test Pits - Temp Aspalt | Material | Ton |  | 8
9176-500040-902110 | Temp Catwalk - Install Catwalk | Material | Linear Feet |  | 8
9176-500040-902115 | Temp Catwalk - Timbers | Material | Linear Feet |  | 8
9176-500040-902120 | Temp Catwalk - Relocate Catwalk | Material | Linear Feet |  | 8
9176-500040-902125 | Temp Catwalk - Remove Timbers | Material | Linear Feet |  | 8
9176-500042-201015 | Sawcut Sidewalk - Saw Cut Conc SW | Material | Linear Feet |  | 8
9176-500044-105100 | Bridge Deck Grinding - Grinding Bridge Deck | Material | Square Feet |  | 8
9176-500044-105110 | Bridge Deck Grinding - Support For Grinding Crew | Material | Square Feet |  | 8
9176-500060-360.310 | Demo exist Concrete Deck and Parapets - I&R Replacement Underdeck Protection | Material | Square Feet |  | 8
9176-500060-360.315 | Demo exist Concrete Deck and Parapets - Remove Retrofit Underdeck Protection | Material | Square Feet |  | 8
9176-500060-500060.A1 | Demo exist Concrete Deck and Parapets - Install Replacement Underdeck Protection | Material | Square Feet |  | 8
9176-500060-500060.A2 | Demo exist Concrete Deck and Parapets - Remove Retrofit Underdeck Protection | Material | Square Feet |  | 8
9176-500060-500060A4 | Demo exist Concrete Deck and Parapets - Removal for Planks for Demo | Material | Square Feet |  | 8
9176-500060-500060B | Demo exist Concrete Deck and Parapets - Sawcut of deck slab | Material | Linear Feet |  | 8
9176-500060-500060C.1 | Demo exist Concrete Deck and Parapets - Core drill Furnish and place anchers | Material | Each |  | 8
9176-500060-500060C.2 | Demo exist Concrete Deck and Parapets - Lift and Load deck panels | Material | Each |  | 8
9176-500060-500060C.2A | Demo exist Concrete Deck and Parapets - Cut rebar from deck panels | Material | Each |  | 8
9176-500060-500060C.2B | Demo exist Concrete Deck and Parapets - Remove studs | Material | Each |  | 8
9176-500060-500060C.2C | Demo exist Concrete Deck and Parapets - Haul and Dispose deck panels | Material | Ton |  | 8
9176-500060-500060C.2D | Demo exist Concrete Deck and Parapets - Remove concrete rubble from deck | Material | Each |  | 8
9176-500060-500060D.1A | Demo exist Concrete Deck and Parapets - Wiresaw parapet | Material | Linear Feet |  | 8
9176-500060-500060D.1B | Demo exist Concrete Deck and Parapets - Break at joints for parapet | Material | Linear Feet |  | 8
9176-500060-500060D.1C | Demo exist Concrete Deck and Parapets - Lift and Load Parapet | Material | Linear Feet |  | 8
9176-500060-500060D.2 | Demo exist Concrete Deck and Parapets - Demo of Sidewalk | Material | Cubic Yard |  | 8
9176-500060-500060D.3 | Demo exist Concrete Deck and Parapets - Clean up conc rubble from sidewalk | Material | Cubic Yard |  | 8
9176-500060-500060D.4 | Demo exist Concrete Deck and Parapets - Hand break conc top flange Retrofit | Material | Cubic Yard |  | 8
9176-500060-500060E | Demo exist Concrete Deck and Parapets - Haul and Dispose Concrete | Material | Ton |  | 8
9176-500060-500060F | Demo exist Concrete Deck and Parapets - Removal of Fence and Guiderail | Material | Linear Feet |  | 8
9176-500060-500060F.1 | Demo exist Concrete Deck and Parapets - Haul and Dispose Fence and Guiderail | Material | Linear Feet |  | 8
9176-500060-500589D.04 | Demo exist Concrete Deck and Parapets - Provide Paint Removal Util Cutlines | Material | Square Feet |  | 8
9176-500060-500589D.50 | Demo exist Concrete Deck and Parapets - Cut Underbridge Utility Pipe/Conduit | Material | Each |  | 8
9176-500060-500589D.55 | Demo exist Concrete Deck and Parapets - Remove Underbridge Utility Pipe/Conduit | Material | Linear Feet |  | 8
9176-500060-500589D.60 | Demo exist Concrete Deck and Parapets - Temp Support Bridge Utils | Material | Linear Feet |  | 8
9176-500070-589.02 | Demo exist Structural Steel and Bearings - Scrap Exisitng SS | Material | LB |  | 8
9176-500070-589.03 | Demo exist Structural Steel and Bearings - Provide SS Temp Matls | Material | Lump Sum |  | 8
9176-500070-589.043 | Demo exist Structural Steel and Bearings - Provide Lead/HazMat Abatement Sub | Material | Square Feet |  | 8
9176-500070-589.510 | Demo exist Structural Steel and Bearings - Remove Bearings- Retro | Material | Each |  | 8
9176-500070-589.512 | Demo exist Structural Steel and Bearings - Remove Bearings- Incidental | Material | Each |  | 8
9176-500070-589.520 | Demo exist Structural Steel and Bearings - Cut Retrofit Girder Ends | Material | Linear Feet |  | 8
9176-500070-589.525 | Demo exist Structural Steel and Bearings - Cut Diaphragms | Material | Each |  | 8
9176-500070-589.529 | Demo exist Structural Steel and Bearings - Prep Girders for Rigging | Material | Each |  | 8
9176-500070-589.530 | Demo exist Structural Steel and Bearings - Cut Girders | Material | Each |  | 8
9176-500070-589.552 | Demo exist Structural Steel and Bearings - Remove Girder Spans | Material | Each |  | 8
9176-500070-589.559 | Demo exist Structural Steel and Bearings - Tractor Night SS Demo Haul Offsite | Material | Each |  | 8
9176-500080-500080A | Demo Existing Substructure Piers, Abutments and - Break Demo Backwall and Abutment | Material | Cubic Yard |  | 8
9176-500080-500080A.1 | Demo Existing Substructure Piers, Abutments and - Lift, Load Haul and dispose debris for Backwall and Abutments | Material | Cubic Yard |  | 8
9176-500080-500080B | Demo Existing Substructure Piers, Abutments and - Break Demo Wingwalls | Material | Cubic Yard |  | 8
9176-500080-500080B.1 | Demo Existing Substructure Piers, Abutments and - Lift, Load Haul and dispose debris for Wingwalls | Material | Cubic Yard |  | 8
9176-500080-500080C.1 | Demo Existing Substructure Piers, Abutments and - Sawcut 4" footing | Material | Linear Feet |  | 8
9176-500080-500080C.2 | Demo Existing Substructure Piers, Abutments and - Break Demo Footings | Material | Cubic Yard |  | 8
9176-500080-500080C.3 | Demo Existing Substructure Piers, Abutments and - Lift, Load Haul and dispose debris for Footings | Material | Cubic Yard |  | 8
9176-500080-500080D | Demo Existing Substructure Piers, Abutments and - Break Demo Piers | Material | Cubic Yard |  | 8
9176-500080-500080D.1 | Demo Existing Substructure Piers, Abutments and - Lift, Load Haul and dispose debris for Piers | Material | Cubic Yard |  | 8
9176-500080-500080D.2 | Demo Existing Substructure Piers, Abutments and - Vertical Shield Protection | Material | Location |  | 8
9176-500080-500080E | Demo Existing Substructure Piers, Abutments and - Abatement of Hazardous materials | Material | Lump Sum |  | 8
9176-500080-500080SUPT.1 | Demo Existing Substructure Piers, Abutments and - Furnish Grilliage, Timber Mats and shoring towers | Material | Each |  | 8
9176-500080-500080SUPT.2 | Demo Existing Substructure Piers, Abutments and - Unload temp support mat | Material | Each |  | 8
9176-500080-500080SUPT.3 | Demo Existing Substructure Piers, Abutments and - set & Remove timber and steel grillage | Material | Each |  | 8
9176-500080-500080SUPT.4 | Demo Existing Substructure Piers, Abutments and - set & remove timber and steel grillage | Material | Each |  | 8
9176-500100-500100A | Demolition and Removal of Existing Approach Slabs - Sawcut Approach Slab | Material | Linear Feet |  | 8
9176-500100-500100B | Demolition and Removal of Existing Approach Slabs - Break up concrete approach slabs | Material | Cubic Yard |  | 8
9176-500100-500100C | Demolition and Removal of Existing Approach Slabs - Haul and Dispose of Concrete | Material | Ton |  | 8
9176-500160-500160.A0 | SOE and Decking Systems - Purchase Soldier Pile Materials | Material | LB |  | 8
9176-500160-500160.A1 | SOE and Decking Systems - Purchase Timber Lagging | Material | Board Foot |  | 8
9176-500160-500160.A2 | SOE and Decking Systems - Purchase Vertical Wood Sheeting for pretrench | Material | Board Foot |  | 8
9176-500160-500160.A4 | SOE and Decking Systems - Purchase Decking Steel Plates | Material | Each |  | 8
9176-500160-500160.A5 | SOE and Decking Systems - Purchase Decking Steel Materials | Material | LB |  | 8
9176-500160-500160.A6 | SOE and Decking Systems - Unload Materials at yard | Material | Load |  | 8
9176-500160-500160.B | SOE and Decking Systems - Sawcut pavement for excavation | Material | Linear Feet |  | 8
9176-500160-500160.C | SOE and Decking Systems - Excavate Sheeted pits for Tie Down @ 133rd Street | Material | Cubic Yard |  | 8
9176-500160-500160.D | SOE and Decking Systems - Install Footing Tie Downs - 60 TON @ 133rd Street | Material | Each |  | 8
9176-500160-500160.E | SOE and Decking Systems - Pretrench for soldier piles | Material | Cubic Yard |  | 8
9176-500160-500160.F | SOE and Decking Systems - Install Soldier Piles | Material | Each |  | 8
9176-500160-500160.G | SOE and Decking Systems - Extract 15 piles at West Liberty Abutment area | Material | Each |  | 8
9176-500160-500160.H | SOE and Decking Systems - Cutoff soldier piles initial | Material | Each |  | 8
9176-500160-500160.H1 | SOE and Decking Systems - Cutoff soldier piles during backfill | Material | Each |  | 8
9176-500160-500160.I | SOE and Decking Systems - Excavate trenches for decking Beams | Material | Cubic Yard |  | 8
9176-500160-500160.J | SOE and Decking Systems - demo opening in exist bridge backwall for deck beam seat | Material | Cubic Yard |  | 8
9176-500160-500160.K | SOE and Decking Systems - Set header beams | Material | Each |  | 8
9176-500160-500160.L | SOE and Decking Systems - Set decking beams | Material | Each |  | 8
9176-500160-500160.M | SOE and Decking Systems - Set diaphragms | Material | Each |  | 8
9176-500160-500160.M1 | SOE and Decking Systems - finish bolt diaphragms | Material | Each |  | 8
9176-500160-500160.N | SOE and Decking Systems - Set decking panels | Material | Each |  | 8
9176-500160-500160.O1 | SOE and Decking Systems - prep wales brackets in wales in yard | Material | Each |  | 8
9176-500160-500160.O2 | SOE and Decking Systems - install wales and struts | Material | Each |  | 8
9176-500160-500160.O3 | SOE and Decking Systems - Rebrace at Integral Abutments | Material | Each |  | 8
9176-500160-500160.P | SOE and Decking Systems - Remove SOE | Material | Each |  | 8
9176-500160-500160.Q | SOE and Decking Systems - Install Lagging | Material | Square Feet |  | 8
9176-500160-500160.Q1 | SOE and Decking Systems - Remove Lagging | Material | Square Feet |  | 8
9176-500160-500160.R | SOE and Decking Systems - Load and distribute Materials on-site | Material | Day |  | 8
9176-500160-500160.SALV | SOE and Decking Systems - Salvage SOE decking steel and Panels | Material | LB |  | 8
9176-500160-500160.VIBR | SOE and Decking Systems - Vibration Plan and Monitoring | Material | Day |  | 8
9176-500170-500170.A | Excavation & Backfill for Abutments & Piers Foun - Exc and backfill at West Abutments (133rd, Hillside, Jamaica) | Material | Cubic Yard |  | 8
9176-500170-500170.B1 | Excavation & Backfill for Abutments & Piers Foun - Excavate Decking Area (first 4 feet)- Night | Material | Cubic Yard |  | 8
9176-500170-500170.B2 | Excavation & Backfill for Abutments & Piers Foun - Excavate Decking Area | Material | Cubic Yard |  | 8
9176-500170-500170.B3 | Excavation & Backfill for Abutments & Piers Foun - Exc at New Piers (VWE) | Material | Cubic Yard |  | 8
9176-500170-500170.B4 | Excavation & Backfill for Abutments & Piers Foun - Backfill at New Piers (VWE) | Material | Cubic Yard |  | 8
9176-500170-500170.B5 | Excavation & Backfill for Abutments & Piers Foun - handle and dispose excess materials | Material | Cubic Yard |  | 8
9176-500170-500170.C | Excavation & Backfill for Abutments & Piers Foun - Fine Grade footing area | Material | Square Yard |  | 8
9176-500170-500170.D0 | Excavation & Backfill for Abutments & Piers Foun - lift and load at stockpile | Material | Cubic Yard |  | 8
9176-500170-500170.D1 | Excavation & Backfill for Abutments & Piers Foun - Backfill behind and adjacent to New Abutments | Material | Cubic Yard |  | 8
9176-500170-500170.D2 | Excavation & Backfill for Abutments & Piers Foun - Backfill behind and adjacent to New Abutments - NIGHT | Material | Cubic Yard |  | 8
9176-500180-365.02 | Construct Concrete Foundations - Procure Concrete PM | Material | Lump Sum |  | 8
9176-500180-365.03 | Construct Concrete Foundations - Procure Concrete Temp Matls | Material | Lump Sum |  | 8
9176-500180-365.041 | Construct Concrete Foundations - Provide Resteel Sub | Material | LB |  | 8
9176-500180-365.042 | Construct Concrete Foundations - Assist Resteel Sub | Material | LB |  | 8
9176-500180-365.56 | Construct Concrete Foundations - Drill and Grout Footing Dowels- Horiz | Material | Each |  | 8
9176-500180-367.60 | Construct Concrete Foundations - E&S Footing Forms | Material | Square Feet |  | 8
9176-500180-367.65 | Construct Concrete Foundations - Equip Support Forming | Material | Day |  | 8
9176-500180-367.70 | Construct Concrete Foundations - Place Footing Concrete | Material | Cubic Yard |  | 8
9176-500180-367.75 | Construct Concrete Foundations - Provide Winter Heating | Material | Each |  | 8
9176-500190-21320 | Install Driven Piles - Furnish Material - Driven Piles | Material | Linear Feet |  | 8
9176-500190-21330A.1 | Install Driven Piles - Install Piles - Driven Piles | Material | Each |  | 8
9176-500190-21330A.2 | Install Driven Piles - MOB Pile RIG Btw Str | Material | Day |  | 8
9176-500190-21330A.3 | Install Driven Piles - Install Pile Template | Material | Each |  | 8
9176-500190-21330C.1 | Install Driven Piles - PDA Testing - Driven Piles | Material | Each |  | 8
9176-500190-21330D | Install Driven Piles - Vibration Monitoring | Material | Day |  | 8
9176-500190-500160.H | Install Driven Piles - Cutoff soldier piles initial | Material | Each |  | 8
9176-500200-365.02 | Construct Abutments, Piers and Wing Walls - Procure Concrete PM | Material | Lump Sum |  | 8
9176-500200-365.03 | Construct Abutments, Piers and Wing Walls - Procure Concrete Temp Matls | Material | Lump Sum |  | 8
9176-500200-365.041 | Construct Abutments, Piers and Wing Walls - Provide Resteel Sub | Material | LB |  | 8
9176-500200-365.042 | Construct Abutments, Piers and Wing Walls - Assist Resteel Sub | Material | LB |  | 8
9176-500200-365.046 | Construct Abutments, Piers and Wing Walls - Apply Anti-Graffiti Coating | Material | Square Feet |  | 8
9176-500200-365.047 | Construct Abutments, Piers and Wing Walls - Provide Protective Sealer Sub | Material | Square Yard |  | 8
9176-500200-365.50 | Construct Abutments, Piers and Wing Walls - Install/Protect Anchor Bolts | Material | Each |  | 8
9176-500200-365.51 | Construct Abutments, Piers and Wing Walls - Install Anchor Bolt Sleeves in Pedestal | Material | Each |  | 8
9176-500200-365.52 | Construct Abutments, Piers and Wing Walls - Install & Grout Anchor Bolts in Pedestal | Material | Each |  | 8
9176-500200-365.54 | Construct Abutments, Piers and Wing Walls - Inst/Mod/Repair Arch Formliner | Material | Square Feet |  | 8
9176-500200-365.57 | Construct Abutments, Piers and Wing Walls - Drill and Grout Footing Dowels- Vertical | Material | Each |  | 8
9176-500200-365.61 | Construct Abutments, Piers and Wing Walls - E&S Abutment/Wingwall | Material | Square Feet |  | 8
9176-500200-365.62 | Construct Abutments, Piers and Wing Walls - E&S Pier | Material | Square Feet |  | 8
9176-500200-365.63 | Construct Abutments, Piers and Wing Walls - E&S Pedestal Forms | Material | Square Feet |  | 8
9176-500200-365.71 | Construct Abutments, Piers and Wing Walls - Place Abutment/Wingwall Concrete | Material | Cubic Yard |  | 8
9176-500200-365.72 | Construct Abutments, Piers and Wing Walls - Place Pier Concrete | Material | Cubic Yard |  | 8
9176-500200-365.73 | Construct Abutments, Piers and Wing Walls - Place Pedestal Concrete | Material | Cubic Yard |  | 8
9176-500200-365.79 | Construct Abutments, Piers and Wing Walls - Rub & Patch | Material | Square Feet |  | 8
9176-500200-365.81 | Construct Abutments, Piers and Wing Walls - Install Waterstop | Material | Linear Feet |  | 8
9176-500200-365.83 | Construct Abutments, Piers and Wing Walls - Install Drain Board | Material | Square Feet |  | 8
9176-500200-367.65 | Construct Abutments, Piers and Wing Walls - Equip Support Forming | Material | Day |  | 8
9176-500200-367.70 | Construct Abutments, Piers and Wing Walls - Provide Winter Heating | Material | Each |  | 8
9176-500310-350.02 | Bearings - New and Replacements - Procure SS PM | Material | Each |  | 8
9176-500310-350.03 | Bearings - New and Replacements - Provide SS Temp Matls | Material | Lump Sum |  | 8
9176-500310-350.043 | Bearings - New and Replacements - Provide Painting Sub- Touch Up | Material | Square Feet |  | 8
9176-500310-350.510 | Bearings - New and Replacements - I&R Jacking Temp Shoring | Material | Each |  | 8
9176-500310-350.512 | Bearings - New and Replacements - Dis/Reconnect Exist Diaphrams | Material | Each |  | 8
9176-500310-350.514 | Bearings - New and Replacements - Jack Existing SS to Grade | Material | Each |  | 8
9176-500310-350.541 | Bearings - New and Replacements - Install Retrofit Bridge Bearings | Material | Each |  | 8
9176-500310-350.542 | Bearings - New and Replacements - Install Replacement Bridge Bearings | Material | Each |  | 8
9176-500310-350.543 | Bearings - New and Replacements - Weld Bearings | Material | Linear Feet |  | 8
9176-500310-350.544 | Bearings - New and Replacements - Caulk Bearings | Material | Linear Feet |  | 8
9176-500320-350.02 | Retrofit Exisitng Steel to Remain - Procure SS PM | Material | LB |  | 8
9176-500320-350.03 | Retrofit Exisitng Steel to Remain - Provide SS Temp Matls | Material | Lump Sum |  | 8
9176-500320-350.041 | Retrofit Exisitng Steel to Remain - Provide Shear Stud Sub | Material | Lump Sum |  | 8
9176-500320-350.042 | Retrofit Exisitng Steel to Remain - Support Shear Stud Sub | Material | Each |  | 8
9176-500320-350.043 | Retrofit Exisitng Steel to Remain - Provide Painting Sub | Material | Square Feet |  | 8
9176-500320-350.501 | Retrofit Exisitng Steel to Remain - Prep Girders & Extensions | Material | Each |  | 8
9176-500320-350.503 | Retrofit Exisitng Steel to Remain - Tractor MOB SS to Crane | Material | Each |  | 8
9176-500320-350.540 | Retrofit Exisitng Steel to Remain - Field Drill Bolt Holes | Material | Each |  | 8
9176-500320-350.543 | Retrofit Exisitng Steel to Remain - Weld Semi-Int Abut Plates | Material | Linear Feet |  | 8
9176-500320-350.551 | Retrofit Exisitng Steel to Remain - Install Temp Girder Supports | Material | Each |  | 8
9176-500320-350.552 | Retrofit Exisitng Steel to Remain - Erect Girder Extensions | Material | Each |  | 8
9176-500320-350.553 | Retrofit Exisitng Steel to Remain - Make Up Splice Connections | Material | Each |  | 8
9176-500320-350.555 | Retrofit Exisitng Steel to Remain - Install Retrofit Stiffeners | Material | Each |  | 8
9176-500320-350.559 | Retrofit Exisitng Steel to Remain - Bolt Up | Material | Each |  | 8
9176-500320-350.560 | Retrofit Exisitng Steel to Remain - Install Diaphrams | Material | Each |  | 8
9176-500330-350.02 | Replacement Bridges - New Structural Steel - Procure SS PM | Material | LB |  | 8
9176-500330-350.03 | Replacement Bridges - New Structural Steel - Provide SS Temp Matls | Material | Lump Sum |  | 8
9176-500330-350.041 | Replacement Bridges - New Structural Steel - Provide Shear Stud Sub | Material | Lump Sum |  | 8
9176-500330-350.042 | Replacement Bridges - New Structural Steel - Support Shear Stud Sub | Material | Each |  | 8
9176-500330-350.043 | Replacement Bridges - New Structural Steel - Provide Painting Sub- Touch Up | Material | Square Feet |  | 8
9176-500330-350.501 | Replacement Bridges - New Structural Steel - Prep Girders | Material | Each |  | 8
9176-500330-350.503 | Replacement Bridges - New Structural Steel - Tractor Night MOB SS to Crane | Material | Each |  | 8
9176-500330-350.551 | Replacement Bridges - New Structural Steel - Install Temp Girder Supports | Material | Each |  | 8
9176-500330-350.552 | Replacement Bridges - New Structural Steel - Erect Girders | Material | Each |  | 8
9176-500330-350.553 | Replacement Bridges - New Structural Steel - Make Up Splice Connections | Material | Each |  | 8
9176-500330-350.559 | Replacement Bridges - New Structural Steel - Bolt Up Field Splices | Material | Each |  | 8
9176-500330-350.560 | Replacement Bridges - New Structural Steel - Install Diaphrams | Material | Each |  | 8
9176-500330-350.900 | Replacement Bridges - New Structural Steel - Non-Working Struct Steel Craft | Material | Month |  | 8
9176-500360-360.02 | Construct Bridge Decks - Procure Concrete PM | Material | Lump Sum |  | 8
9176-500360-360.03 | Construct Bridge Decks - Procure Concrete Temp Matls | Material | Lump Sum |  | 8
9176-500360-360.040 | Construct Bridge Decks - Provide Resteel Sub | Material | LB |  | 8
9176-500360-360.041 | Construct Bridge Decks - Assist Resteel Sub | Material | LB |  | 8
9176-500360-360.042 | Construct Bridge Decks - Provide SIP Deck Sub | Material | Square Feet |  | 8
9176-500360-360.046 | Construct Bridge Decks - Provide Grind & Groove Deck Sub | Material | Square Yard |  | 8
9176-500360-360.047 | Construct Bridge Decks - Provide Protective Sealer Sub | Material | Square Feet |  | 8
9176-500360-360.501 | Construct Bridge Decks - Weld OH Hangers & Screed Cups | Material | Each |  | 8
9176-500360-360.610 | Construct Bridge Decks - I&R Overhang Brackets | Material | Linear Feet |  | 8
9176-500360-360.615 | Construct Bridge Decks - E&S Integral Abutment Forms | Material | Square Feet |  | 8
9176-500360-360.617 | Construct Bridge Decks - E&S Integral Abutment Bulkheads | Material | Square Feet |  | 8
9176-500360-360.620 | Construct Bridge Decks - E&S Overhang Soffit | Material | Square Feet |  | 8
9176-500360-360.630 | Construct Bridge Decks - E&S Edge Forms | Material | Square Feet |  | 8
9176-500360-360.632 | Construct Bridge Decks - Install Deck Scuppers | Material | Each |  | 8
9176-500360-360.633 | Construct Bridge Decks - Install Light Pole Hardware | Material | Each |  | 8
9176-500360-360.635 | Construct Bridge Decks - E&S Bulkheads | Material | Square Feet |  | 8
9176-500360-360.637 | Construct Bridge Decks - E&S UHPC Closure Soffit | Material | Square Feet |  | 8
9176-500360-360.640 | Construct Bridge Decks - Install, Grade & Remove Screed Rail | Material | Linear Feet |  | 8
9176-500360-360.642 | Construct Bridge Decks - Setup/Breakdown Bidwell | Material | Each |  | 8
9176-500360-360.644 | Construct Bridge Decks - Dry-Run Bridge Deck | Material | Each |  | 8
9176-500360-360.650 | Construct Bridge Decks - Place Concrete Bridge Deck | Material | Cubic Yard |  | 8
9176-500360-360.651 | Construct Bridge Decks - Place Integral Abutment Concrete | Material | Cubic Yard |  | 8
9176-500360-360.652 | Construct Bridge Decks - Finish Concrete Bridge Deck | Material | Square Feet |  | 8
9176-500360-360.654 | Construct Bridge Decks - Wet Cure Bridge Deck | Material | Square Feet |  | 8
9176-500360-360.657 | Construct Bridge Decks - Place UHPC Closures | Material | Cubic Yard |  | 8
9176-500360-360.67 | Construct Bridge Decks - Rub & Patch | Material | Square Feet |  | 8
9176-500360-367.65 | Construct Bridge Decks - Equip Support Forming | Material | Day |  | 8
9176-500360-367.70 | Construct Bridge Decks - Provide Winter Heating | Material | Each |  | 8
9176-500370-340.02 | Construct Bridge Parapets - Procure Barrier Conc PM | Material | Cubic Yard |  | 8
9176-500370-340.03 | Construct Bridge Parapets - Procure Barrier Temp Matl | Material | Linear Feet |  | 8
9176-500370-340.041 | Construct Bridge Parapets - Provide Resteel Sub | Material | LB |  | 8
9176-500370-340.042 | Construct Bridge Parapets - Assist Resteel Sub | Material | LB |  | 8
9176-500370-340.62 | Construct Bridge Parapets - E&S Vert Parapet Form System | Material | Square Feet |  | 8
9176-500370-340.63 | Construct Bridge Parapets - E&S Parapet Bulkheads | Material | Square Feet |  | 8
9176-500370-340.65 | Construct Bridge Parapets - Place Barrier Concrete | Material | Cubic Yard |  | 8
9176-500370-340.67 | Construct Bridge Parapets - Rub & Patch | Material | Square Feet |  | 8
9176-500380-360.02 | Construct Bridge Sidewalks and Steel Face Curbs - Procure Conc PM | Material | Lump Sum |  | 8
9176-500380-360.03 | Construct Bridge Sidewalks and Steel Face Curbs - Procur Temp Matl | Material | Linear Feet |  | 8
9176-500380-360.040 | Construct Bridge Sidewalks and Steel Face Curbs - Provide Resteel Sub | Material | LB |  | 8
9176-500380-360.045A | Construct Bridge Sidewalks and Steel Face Curbs - Purchase Steel face curb on bridge | Material | Linear Feet |  | 8
9176-500380-360.045B | Construct Bridge Sidewalks and Steel Face Curbs - Set/form steel face curb | Material | Linear Feet |  | 8
9176-500380-360.637 | Construct Bridge Sidewalks and Steel Face Curbs - E&S Sidewalk Forms | Material | Square Feet |  | 8
9176-500380-360.651 | Construct Bridge Sidewalks and Steel Face Curbs - Place Concrete Sidewalk | Material | Cubic Yard |  | 8
9176-500380-360.653 | Construct Bridge Sidewalks and Steel Face Curbs - Finish Concrete Sidewalk | Material | Square Feet |  | 8
9176-500380-360.67 | Construct Bridge Sidewalks and Steel Face Curbs - Rub & Patch | Material | Square Feet |  | 8
9176-500410-360.02 | Construct Approach/Sleeper Slabs - Procure Conc PM | Material | Lump Sum |  | 8
9176-500410-360.03 | Construct Approach/Sleeper Slabs - Procur Temp Matl | Material | Lump Sum |  | 8
9176-500410-360.040 | Construct Approach/Sleeper Slabs - Provide Resteel Sub | Material | LB |  | 8
9176-500410-360.041 | Construct Approach/Sleeper Slabs - Assist Resteel Sub | Material | LB |  | 8
9176-500410-360.046 | Construct Approach/Sleeper Slabs - Provide Grind & Groove Deck Sub | Material | Square Yard |  | 8
9176-500410-360.601 | Construct Approach/Sleeper Slabs - Fabricate Modular Sleeper Form Sys | Material | Square Feet |  | 8
9176-500410-360.610 | Construct Approach/Sleeper Slabs - E&S Sleeper Slab Forms | Material | Square Feet |  | 8
9176-500410-360.630 | Construct Approach/Sleeper Slabs - E&S Appr Slab Forms | Material | Square Feet |  | 8
9176-500410-360.650 | Construct Approach/Sleeper Slabs - Place Concrete Sleeper Slabs | Material | Cubic Yard |  | 8
9176-500410-360.655 | Construct Approach/Sleeper Slabs - Place Concrete Appr Slabs | Material | Cubic Yard |  | 8
9176-500410-360.660 | Construct Approach/Sleeper Slabs - Finish Concrete Sleeper Slab | Material | Square Feet |  | 8
9176-500410-360.665 | Construct Approach/Sleeper Slabs - Finish Concrete Appr Slab | Material | Square Feet |  | 8
9176-500410-360.670 | Construct Approach/Sleeper Slabs - Cure Sleeper Slabs | Material | Square Feet |  | 8
9176-500430-370.02 | Construct Armorless Expansion Joint - Procure Joint PM | Material | Linear Feet |  | 8
9176-500430-370.03 | Construct Armorless Expansion Joint - Procure Joint Temp Matls | Material | Linear Feet |  | 8
9176-500430-370.61 | Construct Armorless Expansion Joint - Fab Joint Blockouts | Material | Linear Feet |  | 8
9176-500430-370.62 | Construct Armorless Expansion Joint - E&S Joint Blockout | Material | Linear Feet |  | 8
9176-500430-370.64 | Construct Armorless Expansion Joint - E&S Joint Bulkhead | Material | Linear Feet |  | 8
9176-500430-370.65 | Construct Armorless Expansion Joint - Place Elastomeric Conc | Material | Cubic Feet |  | 8
9176-500430-370.70 | Construct Armorless Expansion Joint - Install Joint Sealing System | Material | Linear Feet |  | 8
9176-500450-500450.A | Construct Drainage System - Bridge - Construct Drainage System - Bridge | Material | Lump Sum |  | 8
9176-500523-500523.A | Sanitary Piping - Permanent Pipe Materials | Material | Linear Feet |  | 8
9176-500523-500523.A1 | Sanitary Piping - Furnish Fill Materials | Material | Lump Sum |  | 8
9176-500523-500523.A2 | Sanitary Piping - Furnish Vertical Wood Materials | Material | Board Foot |  | 8
9176-500523-500523.A3 | Sanitary Piping - Unload Pipe Material | Material | LB |  | 8
9176-500523-500523.B0 | Sanitary Piping - Sawcut - Drainage Pipe | Material | Linear Feet |  | 8
9176-500523-500523.B1 | Sanitary Piping - Excavate and Vert.. Wood Sheet Trench | Material | Cubic Yard |  | 8
9176-500523-500523.B2 | Sanitary Piping - Excavate Shallow trench | Material | Cubic Yard |  | 8
9176-500523-500523.C | Sanitary Piping - Install and Backfill Pipe | Material | Linear Feet |  | 8
9176-500523-500523.D | Sanitary Piping - Pour Cradle/ Encasements | Material | Cubic Yard |  | 8
9176-500523-500523.E | Sanitary Piping - Haul and Dispose Excess Earth | Material | Cubic Yard |  | 8
9176-500523-500523.F | Sanitary Piping - Temp Asphalt Hand | Material | Ton |  | 8
9176-500524-500524.A | Sanitary Structures - Permanent Storm Structure Materials | Material | Each |  | 8
9176-500524-500524.A1 | Sanitary Structures - Furnish Fill Materials | Material | Lump Sum |  | 8
9176-500524-500524.A2 | Sanitary Structures - Unload Structures Material | Material | Load |  | 8
9176-500524-500524.B | Sanitary Structures - Excavate w/box | Material | Cubic Yard |  | 8
9176-500524-500524.C | Sanitary Structures - Install and Backfill Structures | Material | Each |  | 8
9176-500524-500524.C1 | Sanitary Structures - Haul and Dispose Excess Earth | Material | Cubic Yard |  | 8
9176-500524-500524.D | Sanitary Structures - Pour Inverts inside structures | Material | Cubic Yard |  | 8
9176-500524-500524.E | Sanitary Structures - patch pipe penetrations | Material | Each |  | 8
9176-500524-500524.F | Sanitary Structures - Form and Pour Dog House Bottoms | Material | Each |  | 8
9176-500524-500524.F1 | Sanitary Structures - Sawcut and demo pipe at doghouse structures | Material | Each |  | 8
9176-500524-500524.G | Sanitary Structures - Install Frame Cover | Material | Each |  | 8
9176-500524-500524.H | Sanitary Structures - core drill into existing | Material | Each |  | 8
9176-500524-500524.I | Sanitary Structures - Labor Crew for bypass/ Temp plug flow | Material | Day |  | 8
9176-500527-500527.A | Storm Pipe - Permanent Pipe Materials | Material | Linear Feet |  | 8
9176-500527-500527.A1 | Storm Pipe - Furnish Fill Materials | Material | Lump Sum |  | 8
9176-500527-500527.A2 | Storm Pipe - Furnish Vertical Wood Materials | Material | Board Foot |  | 8
9176-500527-500527.A3 | Storm Pipe - Unload Pipe Material | Material | Load |  | 8
9176-500527-500527.B0 | Storm Pipe - Sawcut - Drainage Pipe | Material | Linear Feet |  | 8
9176-500527-500527.B1 | Storm Pipe - Excavate and Vert.. Wood Sheet Trench | Material | Cubic Yard |  | 8
9176-500527-500527.B2 | Storm Pipe - Excavate Shallow trench | Material | Cubic Yard |  | 8
9176-500527-500527.C | Storm Pipe - Install and Backfill Pipe | Material | Linear Feet |  | 8
9176-500527-500527.D | Storm Pipe - Pour Cradle/ Encasements | Material | Cubic Yard |  | 8
9176-500527-500527.E | Storm Pipe - Haul and Dispose Excess Earth | Material | Cubic Yard |  | 8
9176-500527-500527.F | Storm Pipe - Temp Asphalt Hand | Material | Ton |  | 8
9176-500527-500527.G | Storm Pipe - Video Inspection - PreContruction | Material | Linear Feet |  | 8
9176-500527-500527.G1 | Storm Pipe - Video Inspection - Post Contruction | Material | Linear Feet |  | 8
9176-500527-500527.H1 | Storm Pipe - Drill & Grout Dowels | Material | Each |  | 8
9176-500527-500527.H2 | Storm Pipe - Place Base Concrete trench repair | Material | Cubic Yard |  | 8
9176-500527-500527.J | Storm Pipe - Remove Existing Structure | Material | Each |  | 8
9176-500527-500527.J1 | Storm Pipe - Remove Existing pipe | Material | Linear Feet |  | 8
9176-500527-500527.K | Storm Pipe - Fill and plug pipes | Material | Each |  | 8
9176-500528-500528.A | Strom Structures - Permanent Storm Structure Materials | Material | Each |  | 8
9176-500528-500528.A1 | Strom Structures - Furnish Fill Materials | Material | Lump Sum |  | 8
9176-500528-500528.A2 | Strom Structures - Unload Structures Material | Material | Load |  | 8
9176-500528-500528.B | Strom Structures - Excavate w/box | Material | Cubic Yard |  | 8
9176-500528-500528.C | Strom Structures - Install and Backfill Structures | Material | Each |  | 8
9176-500528-500528.C1 | Strom Structures - Haul and Dispose Excess Earth | Material | Cubic Yard |  | 8
9176-500528-500528.D | Strom Structures - Pour Inverts | Material | Cubic Yard |  | 8
9176-500528-500528.D1 | Strom Structures - Form and Pour Dog House Bottoms | Material | Each |  | 8
9176-500528-500528.E | Strom Structures - patch pipe penetrations | Material | Each |  | 8
9176-500528-500528.F | Strom Structures - Install Hoods and Hooks | Material | Each |  | 8
9176-500528-500528.G | Strom Structures - Install Frame & Grate/Cover | Material | Each |  | 8
9176-500528-500528.H | Strom Structures - core drill into existing | Material | Each |  | 8
9176-500531-102105 | Removal & Demolition Concrete Pavement - Break Concrete Pavement | Material | Square Feet |  | 8
9176-500531-102110 | Removal & Demolition Concrete Pavement - Excavate Pavement | Material | Square Feet |  | 8
9176-500531-102115 | Removal & Demolition Concrete Pavement - Haul Excavated Material | Material | Square Feet |  | 8
9176-500531-102120 | Removal & Demolition Concrete Pavement - Haul & Dispose Concrete | Material | Square Feet |  | 8
9176-500532-102205 | Removal & Demolition Of Curbs & Sidewalks - Excavate Concrete Curb | Material | Linear Feet |  | 8
9176-500532-102210 | Removal & Demolition Of Curbs & Sidewalks - Haul to Yard | Material | Linear Feet |  | 8
9176-500532-102215 | Removal & Demolition Of Curbs & Sidewalks - Haul & Dispose Concrete Curb | Material | Cubic Yard |  | 8
9176-500532-102305 | Removal & Demolition Of Curbs & Sidewalks - Excavate Concrete Sidewalk | Material | Square Feet |  | 8
9176-500532-102310 | Removal & Demolition Of Curbs & Sidewalks - Haul To Yard | Material | Square Feet |  | 8
9176-500532-102315 | Removal & Demolition Of Curbs & Sidewalks - Haul & Dispose Concrete SW | Material | Cubic Yard |  | 8
9176-500533-500533A | Removal/Demolition of Pilasters - Break up concrete pilasters | Material | Cubic Yard |  | 8
9176-500533-500533B | Removal/Demolition of Pilasters - Haul and Dispose of Concrete | Material | Ton |  | 8
9176-500534-500534A | Removal/Demolition of Light and Signal Posts - Break up concrete posts | Material | Cubic Yard |  | 8
9176-500534-500534B | Removal/Demolition of Light and Signal Posts - Haul and Dispose of Concrete | Material | Ton |  | 8
9176-500535-645005 | Mill Asphalt - Mill Asphalt | Material | Square Feet |  | 8
9176-500535-645010 | Mill Asphalt - Truck Milled Material | Material | Ton |  | 8
9176-500535-645015 | Mill Asphalt - Dispose Millings | Material | Ton |  | 8
9176-500535-645020 | Mill Asphalt - Support Milling Operation | Material | Square Feet |  | 8
9176-500537-656035 | Overlay Milled Asphalt - Asphalt Subcontractor | Material | Lump Sum |  | 8
9176-500539-656800 | Furnish & Install Composite Pavement - Asphalt Subcontractor | Material | Square Feet |  | 8
9176-500540-657010 | Furnish & Install Concrete Sidwalk - Furnish & Install Concrete Sidewalks | Material | Square Feet |  | 8
9176-500540-657010ADA | Furnish & Install Concrete Sidwalk - Furnish and Install ADA Ramps | Material | Each |  | 8
9176-500541-655075 | Furnish & Install Concrete Curbs - Concrete Curb Sub | Material | Linear Feet |  | 8
9176-500545-651005 | Furnish & Install Pavement Markings - Pavement Markings | Material | Lump Sum |  | 8
9176-500560-500560.A | Electrical - Traffic Signals, Lighting and ITS - Electrical - Traffic Signals, Lighting and ITS - BRIDGES | Material | Lump Sum |  | 8
9176-500560-500560.B | Electrical - Traffic Signals, Lighting and ITS - Remove Existing CCVT Poles | Material | Cubic Yard |  | 8
9176-500560-500560.B.1 | Electrical - Traffic Signals, Lighting and ITS - Haul and Dispose Concrete | Material | Cubic Yard |  | 8
9176-500560-500560C | Electrical - Traffic Signals, Lighting and ITS - Excavate for support of posts | Material | Cubic Yard |  | 8
9176-500560-500560D | Electrical - Traffic Signals, Lighting and ITS - Furnish and pour foundations | Material | Cubic Yard |  | 8
9176-500560-500560E | Electrical - Traffic Signals, Lighting and ITS - Haul and Dispose of Excess soil | Material | Cubic Yard |  | 8
9176-500570-500570.B | Signage - Regulatory Signs | Material | Square Feet |  | 8
9176-500600-500600A | Fabricate and Install Bridge Rail, Approach Guide - Install Protective Fence Sub - Ornamental Fence | Material | Linear Feet |  | 8
9176-500600-500600B | Fabricate and Install Bridge Rail, Approach Guide - Install Chain Link Fence ROW with 2 gates | Material | Linear Feet |  | 8
9176-500600-500600C | Fabricate and Install Bridge Rail, Approach Guide - Install Chain Link Fence ROW Gates | Material | Each |  | 8
9176-510105-102205 | Remove Existing Concrete curb - Excavate Concrete Curb | Material | Linear Feet |  | 8
9176-510105-102210 | Remove Existing Concrete curb - Haul To Yard | Material | Linear Feet |  | 8
9176-510105-102215 | Remove Existing Concrete curb - Haul & Dispose Concrete | Material | Ton |  | 8
9176-510110-102305 | Remove Concrete Sidewalk - Excavate Concrete Sidewalk | Material | Square Feet |  | 8
9176-510110-102310 | Remove Concrete Sidewalk - Haul Concrete to Yard | Material | Square Feet |  | 8
9176-510110-102315 | Remove Concrete Sidewalk - Haul & Dispose Concrete | Material | Ton |  | 8
9176-510112-904102 | Remove Existing Barrier - Break Barrier | Material | Linear Feet |  | 8
9176-510112-904103 | Remove Existing Barrier - Remove Barrier From Site | Material | Linear Feet |  | 8
9176-510112-904106 | Remove Existing Barrier - Haul Concrete to Yard | Material | Linear Feet |  | 8
9176-510112-904108 | Remove Existing Barrier - Haul & Dispose Concrete | Material | Ton |  | 8
9176-510114-106403.SUB | Remove Existing Fence & guardrail - Demolition/Removal - Fence and Guide Rail | Material | Linear Feet |  | 8
9176-510116-102105 | Remove Existing Pavement - Break Concrete Pavement | Material | Square Feet |  | 8
9176-510116-102110 | Remove Existing Pavement - Excavate Pavement | Material | Square Feet |  | 8
9176-510116-102115 | Remove Existing Pavement - Haul Material To Yard | Material | Square Feet |  | 8
9176-510116-102120 | Remove Existing Pavement - Haul & Dispose Material | Material | Ton |  | 8
9176-510118-720005 | Remove Existing Light Poles - support of electrican | Material | Each |  | 8
9176-510120-741000 | Remove Existing Cantilever Sign - Support of Sign Subcontractor | Material | Each |  | 8
9176-510122-730005 | Remove Existing Signs - Remove Signs | Material | Square Feet |  | 8
9176-510126-101105 | Remove Underdrain - Remove Underdrain | Material | Linear Feet |  | 8
9176-510126-101110 | Remove Underdrain - Disposal of Material | Material | Linear Feet |  | 8
9176-510200-510210A | Excavation and Grading - Clear and Grub | Material | Square Feet |  | 8
9176-510200-510210A.1 | Excavation and Grading - Strip top 6in for | Material | Cubic Yard |  | 8
9176-510200-510210A.2 | Excavation and Grading - Stock pile top soil | Material | Cubic Yard |  | 8
9176-510200-510210B | Excavation and Grading - Excavate | Material | Cubic Yard |  | 8
9176-510200-510210E | Excavation and Grading - Haul and Dispose excess soil | Material | Ton |  | 8
9176-510200-510250.A | Excavation and Grading - Furnish Silt Fence and Haybales | Material | Linear Feet |  | 8
9176-510200-510250.B | Excavation and Grading - Install/Remove/Maintain Silt fence | Material | Linear Feet |  | 8
9176-510200-510250.C | Excavation and Grading - Install/Remove/Maintain Haybale | Material | Each |  | 8
9176-510200-510250.D | Excavation and Grading - Install/Remove and maintain Entrances | Material | Each |  | 8
9176-510410-500527.A | Storm Piping - Permanent Pipe Materials | Material | Linear Feet |  | 8
9176-510410-500527.A1 | Storm Piping - Furnish Fill Materials | Material | Lump Sum |  | 8
9176-510410-500527.A2 | Storm Piping - Furnish Vertical Wood Materials | Material | Board Foot |  | 8
9176-510410-500527.A3 | Storm Piping - Unload Pipe Material | Material | Load |  | 8
9176-510410-500527.B0 | Storm Piping - Sawcut - Drainage Pipe | Material | Linear Feet |  | 8
9176-510410-500527.B1 | Storm Piping - Excavate and Vert.. Wood Sheet Trench | Material | Cubic Yard |  | 8
9176-510410-500527.B11 | Storm Piping - Excavate and Vert.. Wood Sheet Trench | Material | Cubic Yard |  | 8
9176-510410-500527.B2 | Storm Piping - Excavate Shallow trench | Material | Cubic Yard |  | 8
9176-510410-500527.C | Storm Piping - Install and Backfill Pipe | Material | Linear Feet |  | 8
9176-510410-500527.C1 | Storm Piping - Install and Backfill Pipe | Material | Linear Feet |  | 8
9176-510410-500527.D | Storm Piping - Pour Cradle/ Encasements | Material | Cubic Yard |  | 8
9176-510410-500527.E | Storm Piping - Haul and Dispose Excess Earth | Material | Cubic Yard |  | 8
9176-510410-500527.F | Storm Piping - Temp Asphalt Hand | Material | Ton |  | 8
9176-510420-500420.A | Storm Structures - Permanent Storm Structure Materials | Material | Each |  | 8
9176-510420-500420.A1 | Storm Structures - Furnish Fill Materials | Material | Lump Sum |  | 8
9176-510420-500420.A2 | Storm Structures - Unload Structures Material | Material | Load |  | 8
9176-510420-500420.B | Storm Structures - Excavate w/box | Material | Cubic Yard |  | 8
9176-510420-500420.B1 | Storm Structures - Excavate w/box - DAY | Material | Cubic Yard |  | 8
9176-510420-500420.C | Storm Structures - Install and Backfill Structures | Material | Each |  | 8
9176-510420-500420.C0 | Storm Structures - Install and Backfill Structures - Day | Material | Each |  | 8
9176-510420-500420.C1 | Storm Structures - Haul and Dispose Excess Earth | Material | Cubic Yard |  | 8
9176-510420-500420.D | Storm Structures - Pour Inverts | Material | Cubic Yard |  | 8
9176-510420-500420.D1 | Storm Structures - Form and Pour Dog House Bottoms | Material | Each |  | 8
9176-510420-500420.E | Storm Structures - patch pipe penetrations | Material | Each |  | 8
9176-510420-500420.F | Storm Structures - Install Hoods and Hooks | Material | Each |  | 8
9176-510420-500420.G | Storm Structures - Install Frame & Grate/Cover | Material | Each |  | 8
9176-510420-500420.H | Storm Structures - core drill into existing | Material | Each |  | 8
9176-510500-700009 | Cast-in-Place Concrete work - F & I Reinforcing Steel | Material | LB |  | 8
9176-510500-676010 | Cast-in-Place Concrete work - E&S Forms | Material | Square Feet |  | 8
9176-510500-676020 | Cast-in-Place Concrete work - Pour Barrier | Material | Cubic Yard |  | 8
9176-510500-676030 | Cast-in-Place Concrete work - Rub & Patch | Material | Lump Sum |  | 8
9176-510500-676040 | Cast-in-Place Concrete work - Eqip Assist | Material | Lump Sum |  | 8
9176-510605-420002 | Furnish & Install Underdrain - Furnish & Install Underdrain System | Material | Linear Feet |  | 8
9176-510607-103101 | Pavement Sawcutting - Saw Cutting Pavement | Material | Linear Feet |  | 8
9176-510610-655025 | Furnish & Install Concrete Curb - Concrete Subcontractor | Material | Linear Feet |  | 8
9176-510615-645005 | Mill Asphalt - Mill Asphalt | Material | Square Feet |  | 8
9176-510615-645010 | Mill Asphalt - Truck Milled Material | Material | Ton |  | 8
9176-510615-645015 | Mill Asphalt - Dispose Millings | Material | Ton |  | 8
9176-510615-645020 | Mill Asphalt - Support of Milling Subcotractor | Material | Square Feet |  | 8
9176-510620-6506030 | Overlay Milled Asphalt - Asphalt Subcontractor | Material | Ton |  | 8
9176-510625-210005 | Ground Stabilization - Subbase Grading | Material | Square Feet |  | 8
9176-510625-210010 | Ground Stabilization - Base Grading | Material | Square Feet |  | 8
9176-510625-210015 | Ground Stabilization - Supply RCA | Material | Cubic Yard |  | 8
9176-510625-656030 | Ground Stabilization - Asphalt Subcontractor | Material | Square Feet |  | 8
9176-510630-210005 | Temp HMA Pavement - Subbase Grading Machine | Material | Square Feet |  | 8
9176-510630-210007 | Temp HMA Pavement - Subbase Grading Hand | Material | Square Feet |  | 8
9176-510630-210010 | Temp HMA Pavement - Base Grading Machine | Material | Square Feet |  | 8
9176-510630-210012 | Temp HMA Pavement - Base Grading Hand | Material | Square Feet |  | 8
9176-510630-210015 | Temp HMA Pavement - Supply RCA | Material | Ton |  | 8
9176-510630-65680 | Temp HMA Pavement - Asphalt Subcontractor | Material | Ton |  | 8
9176-510635-210005 | F&I Funished Concrete Pavement - Subbase Grading Machine | Material | Square Feet |  | 8
9176-510635-210007 | F&I Funished Concrete Pavement - Subbase Grading Hand | Material | Square Feet |  | 8
9176-510635-210010 | F&I Funished Concrete Pavement - Base GradeMachine | Material | Square Feet |  | 8
9176-510635-210012 | F&I Funished Concrete Pavement - Base grade Hand | Material | Square Feet |  | 8
9176-510635-210015 | F&I Funished Concrete Pavement - Supply RCA | Material | Ton |  | 8
9176-510635-660010 | F&I Funished Concrete Pavement - Place Concrete Hand | Material | Square Feet |  | 8
9176-510635-660020 | F&I Funished Concrete Pavement - Place Concrete Machine | Material | Square Feet |  | 8
9176-510635-660025 | F&I Funished Concrete Pavement - Set Rails | Material | Square Feet |  | 8
9176-510635-660030 | F&I Funished Concrete Pavement - Set Machie & Test | Material | Square Feet |  | 8
9176-510635-660032 | F&I Funished Concrete Pavement - Supply Rails | Material | Square Feet |  | 8
9176-510635-660035 | F&I Funished Concrete Pavement - Finish Concrete | Material | Square Feet |  | 8
9176-510635-660040 | F&I Funished Concrete Pavement - Cure Concrete | Material | Square Feet |  | 8
9176-510635-660050 | F&I Funished Concrete Pavement - Night Plant Openings | Material | Each |  | 8
9176-510635-660060 | F&I Funished Concrete Pavement - Night Concrete Trucks | Material | Each |  | 8
9176-510635-660070 | F&I Funished Concrete Pavement - Furnish Concrete | Material | Cubic Yard |  | 8
9176-510635-661005 | F&I Funished Concrete Pavement - Drill & Grout Dowels | Material | Each |  | 8
9176-510635-661010 | F&I Funished Concrete Pavement - Supply dowels | Material | Each |  | 8
9176-510640-210005 | F&I Composite Pavement - Subbase Grading Machine | Material | Square Feet |  | 8
9176-510640-210007 | F&I Composite Pavement - Subbase Grading Hand | Material | Square Feet |  | 8
9176-510640-210010 | F&I Composite Pavement - Base Grading Machine | Material | Square Feet |  | 8
9176-510640-210012 | F&I Composite Pavement - Base Grading Hand | Material | Square Feet |  | 8
9176-510640-210015 | F&I Composite Pavement - Supply RCA | Material | Ton |  | 8
9176-510640-656800 | F&I Composite Pavement - Asphalt Subcontractor | Material | Square Feet |  | 8
9176-510640-660010 | F&I Composite Pavement - Place Concrete Trench | Material | Square Feet |  | 8
9176-510640-660020 | F&I Composite Pavement - Place Concrete Road Hand | Material | Square Feet |  | 8
9176-510640-660033 | F&I Composite Pavement - Set Forms | Material | Linear Feet |  | 8
9176-510640-660034 | F&I Composite Pavement - supply forms | Material | Linear Feet |  | 8
9176-510640-660040 | F&I Composite Pavement - Cure Concrete | Material | Square Feet |  | 8
9176-510640-660050 | F&I Composite Pavement - Night plant Openings | Material | Each |  | 8
9176-510640-660060 | F&I Composite Pavement - Night Concrete Truks | Material | Each |  | 8
9176-510640-660070 | F&I Composite Pavement - Furnish Concrete | Material | Cubic Yard |  | 8
9176-510640-661005 | F&I Composite Pavement - Drill & Grout Dowels | Material | Each |  | 8
9176-510640-661010 | F&I Composite Pavement - Supply Dowels | Material | Each |  | 8
9176-510645-280005 | Landscaping - landscapping | Material | Lump Sum |  | 8
9176-510700-510700.A | Guard Rails, Fence, Striping and Signs - Relocate Temp (Left in Place) Barrier | Material | Linear Feet |  | 8
9176-510700-510700.B | Guard Rails, Fence, Striping and Signs - Relocate Impact Attenuator | Material | Each |  | 8
9176-510700-510700.GUIDE | Guard Rails, Fence, Striping and Signs - Install Guide Rail | Material | Linear Feet |  | 8
9176-510700-510700.SIGNS | Guard Rails, Fence, Striping and Signs - VWEOverhead Signs - SIGNS | Material | Square Feet |  | 8
9176-510700-510700.STRIP | Guard Rails, Fence, Striping and Signs - RAMPS - STRIPING SUB | Material | Lump Sum |  | 8
9176-510800-510800.A | Lighting, Signal and ITS - Lighting, Signal and ITS - RAMPS & VWE Reilignments | Material | Lump Sum |  | 8
9176-901000-901010 | BONDS - CONTRACT BONDS | Material | Lump Sum |  | 8
9176-902000-902010 | INSURANCE - INSURANCE PREMIUMS, ITEMIZED | Material | Lump Sum |  | 8
9176-903000-903020 | STAFF LABOR - PROJECT MANAGEMENT | Material | Month |  | 8
9176-903000-903030 | STAFF LABOR - PROJECT ENGINEERING | Material | Month |  | 8
9176-903000-903040 | STAFF LABOR - DESIGN MANAGEMENT | Material | Month |  | 8
9176-903000-903050 | STAFF LABOR - HEALTH AND SAFETY | Material | Month |  | 8
9176-903000-903070 | STAFF LABOR - ADMIN/FINANCE/CONTROLS | Material | Month |  | 8
9176-903000-903080 | STAFF LABOR - FIELD SUPERVISION | Material | Month |  | 8
9176-903000-903090 | STAFF LABOR - SURVEY STAFF | Material | Month |  | 8
9176-903000-903100 | STAFF LABOR - QA / QC Management | Material | Month |  | 8
9176-903000-903120.LS | STAFF LABOR - NON-WORKING CRAFT - Labor Steward | Material | Month |  | 8
9176-903000-903120.MM | STAFF LABOR - NON-WORKING CRAFT - Master Mechanic | Material | Month |  | 8
9176-903000-903120.MMF | STAFF LABOR - NON-WORKING CRAFT - Maintenance Foreman | Material | Month |  | 8
9176-903000-903120.MMF.N | STAFF LABOR - NON-WORKING CRAFT - Maintenance Foreman - NIGHTS | Material | Month |  | 8
9176-903000-903120.TS | STAFF LABOR - NON-WORKING CRAFT - Teamster Steward | Material | Month |  | 8
9176-903000-903120.TSN | STAFF LABOR - NON-WORKING CRAFT - Teamster Steward - NIGHTS | Material | Month |  | 8
9176-904000-904010 | STAFF SUPPORT - OFFICE MEALS | Material | Month |  | 8
9176-904000-904020 | STAFF SUPPORT - TRAVEL | Material | Month |  | 8
9176-904000-904040 | STAFF SUPPORT - STAFF JOB MOVE / RELO | Material | Each |  | 8
9176-904000-904060 | STAFF SUPPORT - STAFF VEHICLES | Material | Month |  | 8
9176-904000-904080 | STAFF SUPPORT - RECRUITING | Material | Each |  | 8
9176-905000-905010 | PROFESSIONAL SERVICES - TEMPORARY DESIGN | Material | Lump Sum |  | 8
9176-905000-905020 | PROFESSIONAL SERVICES - PUBLIC AFFAIRS | Material | Month |  | 8
9176-905000-905050 | PROFESSIONAL SERVICES - AUDITS | Material | Each |  | 8
9176-905000-905060 | PROFESSIONAL SERVICES - OTHER CONSULTANTS - Environmental | Material | Lump Sum |  | 8
9176-906000-906010 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - PREP/RESTORE ALL OFFICE YARDS | Material | Lump Sum |  | 8
9176-906000-906020 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - JV OFFICE - FIXED COST (include space for designer & subs if needed) | Material | Lump Sum |  | 8
9176-906000-906030.EO1 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - ENGINEER'S OFFICE - TYPE III - MONTHLY | Material | Month |  | 8
9176-906000-906030.EO1FI | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - ENGINEER'S OFFICE - TYPE III - FIXED | Material | Month |  | 8
9176-906000-906030.EO1IT | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - ENGINEER'S OFFICE - TYPE III - IT | Material | Month |  | 8
9176-906000-906030.EO2 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - Engineering's Office - Setup | Material | Day |  | 8
9176-906000-906030.EO3 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - Engineer's Inspection Vehicles | Material | Each |  | 8
9176-906000-906030.EO4 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - Engineer's Inspection Vehicles - EOE | Material | Each |  | 8
9176-906000-906040 | PROJECT OFFICES, YARDS, SHOPS - FIXED COST - STORAGE/WORK YARDS AND SHOPS - FIXED COST | Material | Lump Sum |  | 8
9176-907000-907010 | PROJECT OFFICES, YARDS, SHOPS - RUNNING COST - JV OFFICE - MONTHLY (include designer & subs as needed) | Material | Month |  | 8
9176-907000-907010.LIRO | PROJECT OFFICES, YARDS, SHOPS - RUNNING COST - JV OFFICE - MONTHLY (LIRO) | Material | Month |  | 8
9176-908000-908010 | PROJECT OFFICES - IT - IT Spreadsheet | Material | Lump Sum |  | 8
9176-910000-910040 | CONSTRUCTION SURVEY - CONSTRUCT SURVEY - 3RD PRTY | Material | Month |  | 8
9176-910000-910050 | CONSTRUCTION SURVEY - Preconstruction Survey | Material | Lump Sum |  | 8
9176-910000-910055 | CONSTRUCTION SURVEY - Post Construction Building Survey | Material | Lump Sum |  | 8
9176-911000-911010 | JOB SERVICES / GC - Dumpsters | Material | Lump Sum |  | 8
9176-911000-911020 | JOB SERVICES / GC - Sanitary Facilities | Material | Lump Sum |  | 8
9176-911000-911030 | JOB SERVICES / GC - Jobsite Photos - Photo Consultant | Material | Lump Sum |  | 8
9176-911000-911040 | JOB SERVICES / GC - Dust Control & Construction Water | Material | Month |  | 8
9176-911000-911050 | JOB SERVICES / GC - Sweeping | Material | Month |  | 8
9176-911000-911090 | JOB SERVICES / GC - Project Signs | Material | Lump Sum |  | 8
9176-911000-911100 | JOB SERVICES / GC - Tolls | Material | Month |  | 8
9176-911000-911120 | JOB SERVICES / GC - Concrete Wash Outs | Material | Lump Sum |  | 8
9176-911000-911130.A | JOB SERVICES / GC - Yard Support Crew + Snow Removal | Material | Month |  | 8
9176-911000-911130.B | JOB SERVICES / GC - Project Boom Truck & Rack Truck | Material | Month |  | 8
9176-911000-911130.C | JOB SERVICES / GC - Yard Cherry Picker to Unload Misc at Yard | Material | Month |  | 8
9176-911000-911130.D | JOB SERVICES / GC - Furnish, Install and Remove Temp Stair Tower | Material | Lump Sum |  | 8
9176-911000-911160 | JOB SERVICES / GC - Project Clean-up | Material | Each |  | 8
9176-912000-912005 | EQUIPMENT SERVICING - FOREMAN PICKUPS | Material | Month |  | 8
9176-913000-913010 | SAFETY SUPPLIES AND RELATED - SAFETY SUPPLIES AND RELATED | Material | Month |  | 8
9176-914000-914010 | SMALL TOOLS AND CONSUMABLES - SMALL TOOLS AND CONSUMABLES | Material | Month |  | 8
9176-915000-915020 | EQUP. ADJ / MOBS / SMALL EQU - LOWBOY MOVES ON SITE | Material | Each |  | 8
9176-915000-915030 | EQUP. ADJ / MOBS / SMALL EQU - CRANE MOVES ON SITE | Material | Each |  | 8
9176-915000-915040 | EQUP. ADJ / MOBS / SMALL EQU - SMALL/OTHER EQUIPMENT (incl. Lighting) | Material | Month |  | 8
9176-916000-916010 | TAX / LICENSES / PERMITS - TAXES - Partnership Fee | Material | Lump Sum |  | 8
9176-916000-916020 | TAX / LICENSES / PERMITS - TAXES - EQUIPMENT EXCISE TAX | Material | Lump Sum |  | 8
9176-916000-916030 | TAX / LICENSES / PERMITS - PERMITS / THIRD PARTY REVIEW COSTS | Material | Lump Sum |  | 8
9176-919000-919020 | ESCALATION / ADD-ONS - Incidental Overtime / Lost Time | Material | Lump Sum |  | 8
9176-919000-919030 | ESCALATION / ADD-ONS - JV Management Fee - 0.5% of Project Bid | Material | Lump Sum |  | 8
9176-919000-919040 | ESCALATION / ADD-ONS - Pursuits Costs - Paid to HNTB | Material | Lump Sum |  | 8
9176-919000-919050 | ESCALATION / ADD-ONS - FINANCE COST | Material | Lump Sum |  | 8
9176-920000-920010 | RISK AND CONTINGENCY - Construction RISK | Material | Lump Sum |  | 8
9176-920000-920020 | RISK AND CONTINGENCY - Design RISK | Material | Lump Sum |  | 8
9176-920000-920030 | RISK AND CONTINGENCY - Inspection RISK | Material | Lump Sum |  | 8
9176-920000-920040 | RISK AND CONTINGENCY - Design Growth | Material | Lump Sum |  | 8
9176-50051201.010 | 133rd Avenue - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051201.015 | 133rd Avenue - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051201.020 | 133rd Avenue - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051201.025 | 133rd Avenue - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051201.030 | 133rd Avenue - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Linear Feet |  | 8
9176-50051201.040 | 133rd Avenue - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051201.050 | 133rd Avenue - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051201.060 | 133rd Avenue - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051201.070 | 133rd Avenue - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051201.080 | 133rd Avenue - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051201.100 | 133rd Avenue - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051201.110 | 133rd Avenue - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051201.150 | 133rd Avenue - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051201.200 | 133rd Avenue - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051202.010 | Rockaway Blvd - NYCDEP Watermain - 20" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051202.015 | Rockaway Blvd - NYCDEP Watermain - 20" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051202.020 | Rockaway Blvd - NYCDEP Watermain - 20" - Sawcut | Material | Linear Feet |  | 8
9176-50051202.025 | Rockaway Blvd - NYCDEP Watermain - 20" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051202.030 | Rockaway Blvd - NYCDEP Watermain - 20" - Exc in Intersection to Expose Existing Pipe | Material | Lump Sum |  | 8
9176-50051202.040 | Rockaway Blvd - NYCDEP Watermain - 20" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051202.050 | Rockaway Blvd - NYCDEP Watermain - 20" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051202.060 | Rockaway Blvd - NYCDEP Watermain - 20" - Set Expansion joint | Material | Each |  | 8
9176-50051202.070 | Rockaway Blvd - NYCDEP Watermain - 20" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051202.080 | Rockaway Blvd - NYCDEP Watermain - 20" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051202.100 | Rockaway Blvd - NYCDEP Watermain - 20" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051202.110 | Rockaway Blvd - NYCDEP Watermain - 20" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051202.150 | Rockaway Blvd - NYCDEP Watermain - 20" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051202.200 | Rockaway Blvd - NYCDEP Watermain - 20" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051203.010 | Foch Blvd - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051203.015 | Foch Blvd - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051203.020 | Foch Blvd - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051203.025 | Foch Blvd - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051203.030 | Foch Blvd - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Lump Sum |  | 8
9176-50051203.040 | Foch Blvd - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051203.050 | Foch Blvd - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051203.060 | Foch Blvd - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051203.070 | Foch Blvd - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051203.080 | Foch Blvd - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051203.090 | Foch Blvd - NYCDEP Watermain - 12" - Install Hydrants | Material | Each |  | 8
9176-50051203.100 | Foch Blvd - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051203.110 | Foch Blvd - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051203.150 | Foch Blvd - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051203.200 | Foch Blvd - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051204.010 | Linden Blvd - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051204.015 | Linden Blvd - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051204.020 | Linden Blvd - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051204.025 | Linden Blvd - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051204.030 | Linden Blvd - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Linear Feet |  | 8
9176-50051204.040 | Linden Blvd - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051204.050 | Linden Blvd - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051204.060 | Linden Blvd - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051204.070 | Linden Blvd - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051204.080 | Linden Blvd - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051204.100 | Linden Blvd - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051204.110 | Linden Blvd - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051204.150 | Linden Blvd - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051204.200 | Linden Blvd - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051205.010 | 109th Avenue - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051205.015 | 109th Avenue - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051205.020 | 109th Avenue - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051205.025 | 109th Avenue - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051205.030 | 109th Avenue - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Linear Feet |  | 8
9176-50051205.040 | 109th Avenue - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051205.050 | 109th Avenue - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051205.060 | 109th Avenue - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051205.070 | 109th Avenue - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051205.080 | 109th Avenue - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051205.090 | 109th Avenue - NYCDEP Watermain - 12" - Install Hydrants | Material | Each |  | 8
9176-50051205.100 | 109th Avenue - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051205.110 | 109th Avenue - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051205.150 | 109th Avenue - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051205.200 | 109th Avenue - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051206.010 | Liberty Avenue - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051206.015 | Liberty Avenue - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051206.020 | Liberty Avenue - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051206.025 | Liberty Avenue - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051206.030 | Liberty Avenue - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Each |  | 8
9176-50051206.040 | Liberty Avenue - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051206.050 | Liberty Avenue - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051206.060 | Liberty Avenue - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051206.070 | Liberty Avenue - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051206.080 | Liberty Avenue - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051206.100 | Liberty Avenue - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051206.110 | Liberty Avenue - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051206.150 | Liberty Avenue - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051206.200 | Liberty Avenue - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051207.010 | 101st Avenue - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051207.015 | 101st Avenue - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051207.020 | 101st Avenue - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051207.030 | 101st Avenue - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Each |  | 8
9176-50051207.040 | 101st Avenue - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051207.150 | 101st Avenue - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051208.010 | Jamaica Avenue - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051208.015 | Jamaica Avenue - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051208.020 | Jamaica Avenue - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051208.025 | Jamaica Avenue - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051208.030 | Jamaica Avenue - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Lump Sum |  | 8
9176-50051208.040 | Jamaica Avenue - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051208.050 | Jamaica Avenue - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051208.060 | Jamaica Avenue - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051208.070 | Jamaica Avenue - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051208.080 | Jamaica Avenue - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051208.100 | Jamaica Avenue - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051208.110 | Jamaica Avenue - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051208.150 | Jamaica Avenue - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051208.200 | Jamaica Avenue - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051209.010 | Hillside Avenue - NYCDEP Watermain - 12" - Permanent Materials | Material | Lump Sum |  | 8
9176-50051209.015 | Hillside Avenue - NYCDEP Watermain - 12" - Temporary Materials | Material | Lump Sum |  | 8
9176-50051209.020 | Hillside Avenue - NYCDEP Watermain - 12" - Sawcut | Material | Linear Feet |  | 8
9176-50051209.025 | Hillside Avenue - NYCDEP Watermain - 12" - Unload Steel Pipe | Material | Lump Sum |  | 8
9176-50051209.030 | Hillside Avenue - NYCDEP Watermain - 12" - Exc in Intersection to Expose Existing Pipe | Material | Lump Sum |  | 8
9176-50051209.040 | Hillside Avenue - NYCDEP Watermain - 12" - Cut Existing WM and Install New Connections | Material | Each |  | 8
9176-50051209.050 | Hillside Avenue - NYCDEP Watermain - 12" - Set Pipe on Bridge | Material | Linear Feet |  | 8
9176-50051209.060 | Hillside Avenue - NYCDEP Watermain - 12" - Set Expansion joint | Material | Each |  | 8
9176-50051209.070 | Hillside Avenue - NYCDEP Watermain - 12" - Close Pipe Joints on Bridge and Set Exp Jt | Material | Each |  | 8
9176-50051209.080 | Hillside Avenue - NYCDEP Watermain - 12" - Make Final Connections to Pipe on Bridge | Material | Each |  | 8
9176-50051209.090 | Hillside Avenue - NYCDEP Watermain - 12" - Install Hydrants | Material | Each |  | 8
9176-50051209.100 | Hillside Avenue - NYCDEP Watermain - 12" - F&S& Pour Exp Jt Chamber Slab | Material | Lump Sum |  | 8
9176-50051209.110 | Hillside Avenue - NYCDEP Watermain - 12" - F&S&Pour Walls | Material | Lump Sum |  | 8
9176-50051209.150 | Hillside Avenue - NYCDEP Watermain - 12" - Backfill & Temp Asphalt | Material | Lump Sum |  | 8
9176-50051209.200 | Hillside Avenue - NYCDEP Watermain - 12" - Weld Steel Main Joints | Material | Each |  | 8
9176-50051601.010 | 133rd Avenue - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051601.020 | 133rd Avenue - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051601.030 | 133rd Avenue - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051601.050 | 133rd Avenue - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051602.010 | Rockaway Blvd - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051602.020 | Rockaway Blvd - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051602.030 | Rockaway Blvd - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051602.050 | Rockaway Blvd - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051603.010 | Foch Blvd - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051603.020 | Foch Blvd - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051603.030 | Foch Blvd - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051603.050 | Foch Blvd - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051604.010 | Linden Blvd - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051604.020 | Linden Blvd - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051604.030 | Linden Blvd - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051604.050 | Linden Blvd - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051605.010 | 109th Avenue - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051605.020 | 109th Avenue - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051605.030 | 109th Avenue - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051605.050 | 109th Avenue - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051606.010 | Liberty Avenue - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051606.020 | Liberty Avenue - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051606.030 | Liberty Avenue - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051606.050 | Liberty Avenue - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051606.100 | Liberty Avenue - FDNY Communication System - Restore 800' of Trench beyond pavt limits | Material | Linear Feet |  | 8
9176-50051607.010 | 101st Avenue - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051607.020 | 101st Avenue - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051607.030 | 101st Avenue - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051607.050 | 101st Avenue - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051608.010 | Jamaica Avenue - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051608.020 | Jamaica Avenue - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051608.030 | Jamaica Avenue - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051608.050 | Jamaica Avenue - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051609.010 | Hillside Avenue - FDNY Communication System - Materials | Material | Lump Sum |  | 8
9176-50051609.020 | Hillside Avenue - FDNY Communication System - Sawcut | Material | Linear Feet |  | 8
9176-50051609.030 | Hillside Avenue - FDNY Communication System - Excavate & Sheet | Material | Cubic Yard |  | 8
9176-50051609.050 | Hillside Avenue - FDNY Communication System - Backfill and Temp Asphalt | Material | Lump Sum |  | 8
9176-50051610 | FDNY Communication System - FDNY - Electrical Sub | Material | Lump Sum |  | 8
3454-800.06000115 | Design Build Construction Work BIN 1055630 - Replacement - Rockaway Blvd | Material |  |  | 1
3417-27003 | NS Selective Clearing - CO 21 | Material | Lump Sum |  | 8
3417-54530 | NS Temp Pvmt Mrkg, Type E 14" - CO 20 | Material | Linear Feet |  | 8
3417-54532 | NS Temp Pvmt Mrkg, Type E 10" - CO 20 | Material | Linear Feet |  | 8
3417-54546 | Temp Pavement Marking Ty. D Tape 12" - CO 20 | Material | Linear Feet |  | 8
3417-54543 | Temp Pavement Marking Ty. D Tape 6" - CO 20 | Material | Linear Feet |  | 8
3417-54544 | Temp Pavement Marking Ty. D Tape 8" - CO 20 | Material | Linear Feet |  | 8
3417-27461-CO17 | Inlet Protection Ty B - CO 17 | Material | Each |  | 8
3417-13543 | NS Wall | Material | Lump Sum |  | 8
3428-076.1 | SA 3 - Additional SR 46 Lighting | Material | Lump Sum |  | 8
3428-001.2 | SA 2 - Hurricane Dorian | Material | Lump Sum |  | 8
9156-SM-6 | Loose Dowels Stored Materials | Material | Each |  | 8
9156-SM-7 | Dowel Baskets Stored Materials | Material | Linear Feet |  | 8
3418-0171 | 3418-0171 - Addition of Mash Guardrail - CO | Material | Lump Sum |  | 8
3454-800.06000115.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000115.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000115.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000115.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000115.05 | Construct Pier | Material |  |  | 1
3454-800.06000115.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000115.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000115.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000115.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000115.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000115.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000115.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000115.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000115.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000115.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000115.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000215 | Design Build Construction Work BIN 1055650 - Replacement - Linden Blvd | Material |  |  | 1
3454-800.06000215.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000215.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000215.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000215.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000215.05 | Construct Pier | Material |  |  | 1
3454-800.06000215.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000215.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000215.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000215.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000215.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000215.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000215.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000215.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000215.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000215.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000215.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000315 | Design Build - Construction Work BIN1055670 - Replacement - Liberty Ave | Material |  |  | 1
3454-800.06000315.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000315.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000315.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000315.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000315.05 | Construct Pier | Material |  |  | 1
3454-800.06000315.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000315.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000315.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000315.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000315.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000315.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000315.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000315.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000315.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000315.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000315.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000415 | Design Build - Construction Work BIN1055680 - Replacement - 101st Ave | Material |  |  | 1
3454-800.06000415.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000415.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000415.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000415.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000415.05 | Construct Pier | Material |  |  | 1
3454-800.06000415.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000415.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000415.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000415.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000415.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000415.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000415.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000415.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000415.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000415.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000415.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000515 | Design Build - Construction Work BIN 1055620 - Retrofit - 133rd Ave | Material |  |  | 1
3454-800.06000515.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000515.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000515.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000515.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000515.05 | Construct Pier | Material |  |  | 1
3454-800.06000515.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000515.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000515.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000515.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000515.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000515.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000515.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000515.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000515.14 | NB CD Road Realignment - Pavement, Utilities, Drainage, etc. | Material |  |  | 1
3454-800.06000515.15 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000515.16 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000515.17 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000615 | Design Build - Construction Work BIN 1055640 - Retrofit - Foch Blvd | Material |  |  | 1
3454-800.06000615.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000615.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000615.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000615.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000615.05 | Construct Pier | Material |  |  | 1
3454-800.06000615.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000615.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000615.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000615.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000615.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000615.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000615.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000615.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000615.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000615.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000615.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000715 | Design Build - Construction Work BIN 1055660 - Retrofit - 109th Ave | Material |  |  | 1
3454-800.06000715.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000715.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000715.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000715.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000715.05 | Construct Pier | Material |  |  | 1
3454-800.06000715.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000715.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000715.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000715.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000715.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000715.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000715.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000715.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000715.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000715.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000715.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000815 | Design Build - Construction Work BIN 1055700 - Retrofit - Jamaica Ave | Material |  |  | 1
3454-800.06000815.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000815.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000815.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000815.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000815.05 | Construct Pier | Material |  |  | 1
3454-800.06000815.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000815.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000815.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000815.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000815.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000815.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000815.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000815.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000815.14 | NB VWE Realignment (Jamaica Ave to Hillside Ave) | Material |  |  | 1
3454-800.06000815.15 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000815.16 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000815.17 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06000915 | Design Build - Construction Work BIN 1055710 - Retrofit - Hillside Ave | Material |  |  | 1
3454-800.06000915.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06000915.02 | Demolition and Removal of Existing Bridge Elements | Material |  |  | 1
3454-800.06000915.03 | Demolition and Removal of Existing Approach Slabs | Material |  |  | 1
3454-800.06000915.04 | Construct Pier and Abutment Foundations | Material |  |  | 1
3454-800.06000915.05 | Construct Pier | Material |  |  | 1
3454-800.06000915.06 | Construct Abutments and Wing Walls | Material |  |  | 1
3454-800.06000915.07 | Fabricate and Install Bearings and Superstructure | Material |  |  | 1
3454-800.06000915.08 | Construct Reinforced Concrete Bridge Deck Slab, Sidewalk and Curbs | Material |  |  | 1
3454-800.06000915.09 | Construct Reinforced Concrete Approach Slabs | Material |  |  | 1
3454-800.06000915.10 | NYCDEP (WATER & SEWER) and FDNY | Material |  |  | 1
3454-800.06000915.11 | Reconstruction of the bridge approaches (including curbs, drainage, and sidewalk) and adjacent service road intersections | Material |  |  | 1
3454-800.06000915.12 | Fabricate and Install Traffic Signals, Roadway Lighting, and Signage | Material |  |  | 1
3454-800.06000915.13 | Fabricate and Install Bridge Rail, Approach Guide Railing and Fencing | Material |  |  | 1
3454-800.06000915.14 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06000915.15 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06000915.16 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06001015 | Design Build - Construction Work NB VWE Exit Ramp to Linden Blvd. | Material |  |  | 1
3454-800.06001015.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06001015.02 | Ramp Construction and VWE Resurfacing Work, Including Drainage and Relocation/Protection of Utilities (NYCDEP, PANYNJ facilities) | Material |  |  | 1
3454-800.06001015.03 | Existing Ramp Removal | Material |  |  | 1
3454-800.06001015.04 | North Service Road Work | Material |  |  | 1
3454-800.06001015.05 | Removal and Installation of Lighting, Striping, Signage, and Signals | Material |  |  | 1
3454-800.06001015.06 | Punch List Work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06001015.07 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06001015.08 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06001115 | Design Build - Construction Work N. Conduit Ave Entrance Ramp to WB Belt Parkway | Material |  |  | 1
3454-800.06001115.01 | Work Zone Traffic Control | Material |  |  | 1
3454-800.06001115.02 | Ramp Construction and WB Belt Parkway Reconstruction Work, Including Drainage and Relocation of Utilities (NYCDEP) | Material |  |  | 1
3454-800.06001115.03 | Exit Ramp to N. Conduit Ave. Reconstruction | Material |  |  | 1
3454-800.06001115.04 | Existing Ramp Removal | Material |  |  | 1
3454-800.06001115.05 | Removal and Installation of Lighting, Striping, Signage, and Signals | Material |  |  | 1
3454-800.06001115.06 | Punch list work, Site Cleanup and Restoration | Material |  |  | 1
3454-800.06001115.07 | Final Acceptance (Per DB §109-09B) | Material |  |  | 1
3454-800.06001115.08 | Final Agreement (Per DB §109-09D) | Material |  |  | 1
3454-800.06001215 | Design Build - Construction Work Intersection Reconstruction PCC Base Course and Subbase Course (154,452 SF) | Material |  |  | 1
3454-619.22970011 | Traffic Enforcement Agents | Material |  |  | 1
3454-800.04000015 | Design Build - Force Account Work | Material |  |  | 1
3454-800.05000015 | Design Build - Site Mobilization (Maximum 4% of Subtotal A) | Material |  |  | 1
3454-800.01000015 | Design Build - Design Services | Material |  |  | 1
3454-800.02000015 | Design Build - Construction Inspection Services | Material |  |  | 1
3454-800.03000015 | Design Build - Quality Control Services | Material |  |  | 1
3454-800.10000115 | Design Build - Utility Related Work - Con Ed (Electric) (See Note 3) | Material |  |  | 1
3454-800.10000115.01 | Proposed Ramp from North Conduit Avenue to Belt Parkway | Material |  |  | 1
3454-800.10000115.02 | Rockaway Boulevard (BIN 1055630) | Material |  |  | 1
3454-800.10000115.03 | Van Wyck Expressway Mainline (I-678) between Foch Boulevard and Linden Boulevard | Material |  |  | 1
3454-800.10000115.04 | Linden Boulevard (BIN 1055650) | Material |  |  | 1
3454-800.10000115.05 | Liberty Avenue (BIN 1055670) | Material |  |  | 1
3454-800.10000115.06 | Northbound and Southbound Service Roads from Liberty Avenue to 101st Avenue | Material |  |  | 1
3454-800.10000115.07 | 101st Avenue (BIN 1055680) | Material |  |  | 1
3454-800.10000115.08 | Southbound Service Road from 101st Avenue to Atlantic Avenue | Material |  |  | 1
3454-800.10000115.09 | 133rd Avenue (BIN 1055620) | Material |  |  | 1
3454-800.10000115.10 | Foch Boulevard (BIN 1055640) | Material |  |  | 1
3454-800.10000115.11 | 109th Avenue (BIN 1055660) | Material |  |  | 1
3454-800.10000115.12 | Jamaica Avenue (BIN 1055700) | Material |  |  | 1
3454-800.10000115.13 | Hillside Avenue (BIN 1055710) | Material |  |  | 1
3454-800.10000215 | Design Build - Utility Related Work - National Grid (Gas) (See Note 3) | Material |  |  | 1
3454-800.10000215.01 | Rockaway Boulevard (BIN 1055630) | Material |  |  | 1
3454-800.10000215.02 | Linden Boulevard (BIN 1055650) | Material |  |  | 1
3454-800.10000215.03 | Liberty Avenue (BIN 1055670) | Material |  |  | 1
3454-800.10000215.04 | 101st Avenue (BIN 1055680) | Material |  |  | 1
3454-800.10000215.05 | 133rd Avenue (BIN 1055620) | Material |  |  | 1
3454-800.10000215.06 | Foch Boulevard (BIN 1055640) | Material |  |  | 1
3454-800.10000215.07 | 109th Avenue (BIN 1055660) | Material |  |  | 1
3454-800.10000215.08 | Jamaica Avenue (BIN 1055700) | Material |  |  | 1
3454-800.10000215.09 | Hillside Avenue (BIN 1055710) | Material |  |  | 1
3454-800.10000315 | Design Build - Utility Related Work - Verizon (See Note 3) | Material |  |  | 1
3454-800.10000315.01 | Rockaway Boulevard (BIN 1055630) | Material |  |  | 1
3454-800.10000315.02 | Linden Boulevard (BIN 1055650) | Material |  |  | 1
3454-800.10000315.03 | Liberty Avenue (BIN 1055670) | Material |  |  | 1
3454-800.10000315.04 | 101st Avenue (BIN 1055680) | Material |  |  | 1
3454-800.10000315.05 | 133rd Avenue (BIN 1055620) | Material |  |  | 1
3454-800.10000315.06 | Foch Boulevard (BIN 1055640) | Material |  |  | 1
3454-800.10000315.07 | 109th Avenue (BIN 1055660) | Material |  |  | 1
3454-800.10000315.08 | Jamaica Avenue (BIN 1055700) | Material |  |  | 1
3454-800.10000315.09 | Hillside Avenue (BIN 1055710) | Material |  |  | 1
3454-800.10000415 | Design Build - Utility Related Work Altice (Cablevision) | Material |  |  | 1
3454-800.10000415.01 | Rockaway Boulevard (BIN 1055630) | Material |  |  | 1
3454-800.10000515 | Design Build - Utility Related Work Charter (Spectrum) | Material |  |  | 1
3454-800.10000515.01 | Rockaway Boulevard (BIN 1055630) | Material |  |  | 1
3454-800.10000515.02 | Linden Boulevard (BIN 1055650) | Material |  |  | 1
3454-800.10000515.03 | Liberty Avenue (BIN 1055670) | Material |  |  | 1
3454-800.10000515.04 | 101st Avenue (BIN 1055680) | Material |  |  | 1
3454-800.10000515.05 | 133rd Avenue (BIN 1055620) | Material |  |  | 1
3454-800.10000515.06 | Foch Boulevard (BIN 1055640) | Material |  |  | 1
3454-800.10000515.07 | 109th Avenue (BIN 1055660) | Material |  |  | 1
3454-800.10000515.08 | Jamaica Avenue (BIN 1055700) | Material |  |  | 1
3454-800.10000515.09 | Hillside Avenue (BIN 1055710) | Material |  |  | 1
3454-800.10000615 | Design Build Utility Related Work Crown Castle | Material |  |  | 1
3458-100-6002 | PREPARING ROW | Material | Station |  | 8
3458-104-6001 | REMOVING CONC (PAV) | Material | Square Yard |  | 8
3458-104-6009 | REMOVING CONC (RIPRAP) | Material | Square Yard |  | 8
3458-104-6017 | REMOVING CONC (DRIVEWAYS) | Material | Square Yard |  | 8
3454 | 3454 - Van Wyck | Nonlabor |  |  | 1
9156-SA14 | SA#14 - DRB Payment | Material | Lump Sum |  | 8
3417-50974-CO23 | NS TRAFFIC - SE-9 TY. A MODIFICATIONS - CO23 | Material | Lump Sum |  | 8
3417-67260-CO29 | NS LIGHTING - BRIDGE CONDUIT SYSTEMAESTHETIC - B603 | Material | Lump Sum |  | 8
3417-85101-CO24 | FORCE ACCOUNT AUTH. #2 - REMOVAL OF OBSTRUCT - CO24 | Material | Lump Sum |  | 8
3417-50110-A-CO30 | Overlay Sign Panel - CO 30 | Material | Square Feet |  | 8
3417-50110-B-CO30 | Overlay Sign Panel_Material - CO30 | Material | Square Feet |  | 8
3450 | 3450 - I-405 Renton/Bellvue-Reimburse | Nonlabor |  |  | 1
UPC112815.70096 | ROW Plans Prepare ROW Plans 1 | Material | Lump Sum |  | 8
UPC112815.70096-1 | ROW Plans Prepare ROW Plans 2 | Material | Lump Sum |  | 8
UPC112815.70096-2 | ROW Plans Prepare ROW Plans 3 | Material | Lump Sum |  | 8
UPC112815.25591-7 | Early Grading Plan Prepare Early Grading Plans 1 | Material | Lump Sum |  | 8
UPC112815.25591-8 | Early Grading Plan Prepare Early Grading Plans 2 | Material | Lump Sum |  | 8
UPC112815.25593-3 | Early Grading Plan QA/QC | Material | Lump Sum |  | 8
UPC112815.25591-9 | Early Grading Plan Incorporate Review Comments | Material | Lump Sum |  | 8
UPC112815.25593-4 | Early Grading Plan QA/QC 2 | Material | Lump Sum |  | 8
UPC112815.25591-12 | Public Hearing Hold Public Hearing & Recieve Comments | Material | Lump Sum |  | 8
UPC112815.25591-13 | Public Hearing Prepare Transcript | Material | Lump Sum |  | 8
UPC112815.25591-14 | Bridge Design Balls Ford Over NSRC Prepare Preliminary Plans (Stage I) 1 | Material | Lump Sum |  | 8
UPC112815.25591-15 | Bridge Design Balls Ford Over NSRC Prepare Preliminary Plans (Stage I) 2 | Material | Lump Sum |  | 8
UPC112815.25591-16 | Bridge Design Balls Ford Over NSRC Incorporate VDOT / County Comments | Material | Lump Sum |  | 8
UPC112815.25591-17 | Bridge Design Balls Ford Rd Over PW Pkwy Prepare Preliminary Plans (Stage I) 1 | Material | Lump Sum |  | 8
UPC112815.25591-18 | Bridge Design Balls Ford Rd Over PW Pkwy Prepare Preliminary Plans (Stage I) 2 | Material | Lump Sum |  | 8
UPC112815.25591-27 | Environmental Environmental Studies 3 | Material | Lump Sum |  | 8
UPC112815.25591-19 | Bridge Design Balls Ford Rd Over PW Pkwy Incorporate VDOT/County Comments | Material | Lump Sum |  | 8
UPC112815.25591-20 | Environmental Perform Wetland Delineation | Material | Lump Sum |  | 8
UPC112815.25591-21 | Environmental Hazmat - Phase I ESA | Material | Lump Sum |  | 8
UPC112815.25591-22 | Environmental Environmental Studies 1 | Material | Lump Sum |  | 8
UPC112815.25591-23 | Environmental Obtain Jurisdictional Determination | Material | Lump Sum |  | 8
UPC112815.25591-24 | Environmental Environmental Studies 2 | Material | Lump Sum |  | 8
UPC112815.25591-25 | Environmental Obtain Water Quality Permits 1 | Material | Lump Sum |  | 8
UPC112815.25591-26 | Environmental Hazmat - Phase II ESA | Material | Lump Sum |  | 8
UPC112815.25591-28 | ROW Acquisition Prepare ROW Acquisition Plan | Material | Lump Sum |  | 8
UPC112815.40012-1 | Survey Utility Designation 2 | Material | Lump Sum |  | 8
UPC112815.25591-38 | Survey Base Mapping / Field Survey 3 | Material | Lump Sum |  | 8
UPC112815.25591-29 | Survey Base Mapping / Field Survey 1 | Material | Lump Sum |  | 8
UPC112815.40012 | Survey Utility Designation 1 | Material | Lump Sum |  | 8
UPC112815.25591-39 | Survey Base Mapping / Field Survey 2 | Material | Lump Sum |  | 8
UPC112815.40012-2 | Survey Utility Designation 3 | Material | Lump Sum |  | 8
UPC112815.40012-3 | Utility Coordination & Design Month 1 | Material | Lump Sum |  | 8
UPC112815.40012-4 | Utility Coordination & Desgn Month 2 | Material | Lump Sum |  | 8
UPC112815.40012-5 | Utility Coordinaiton & Deisgn Month 3 | Material | Lump Sum |  | 8
UPC112815.25591-4 | Initial Geotechnical Investigations Field Investigations & Analysis 2 | Material | Lump Sum |  | 8
UPC112815.25591-2 | Supplemental Geotechnical Investigations Field Investigations & Analysis 2 | Material | Lump Sum |  | 8
UPC112815.25591-30 | Scope Validation Month 1 | Material | Lump Sum |  | 8
UPC112815.25591-31 | Scope Validation Month 2 | Material | Lump Sum |  | 8
UPC112815.25591-32 | Scope Validation Month 3 | Material | Lump Sum |  | 8
UPC112815.25591-33 | Scope Validation Month 4 | Material | Lump Sum |  | 8
UPC112815.25591-34 | Railroad Coordination Month 1 | Material | Lump Sum |  | 8
UPC112815.25591-35 | Railroad Coordination Month 2 | Material | Lump Sum |  | 8
UPC112815.25591-36 | Railroad Coordination Month 3 | Material | Lump Sum |  | 8
UPC112815.25591-37 | Railroad Coordination Month 4 | Material | Lump Sum |  | 8
UPC112815.25591-40 | Project Start Up (Ins.) | Material | Lump Sum |  | 8
UPC112815.25591-41 | Pre-Bid Proposal & Design Costs | Material | Lump Sum |  | 8
UPC112815.25591-42 | Prepare/Submit Health Safety & Wellness Plan | Material | Lump Sum |  | 8
UPC112815.25565-2 | Prepare/Submit Preliminary Schedule & Narrative | Material | Lump Sum |  | 8
UPC112815.25565-1 | Prepare/Submit Baseline Schedule | Material | Lump Sum |  | 8
UPC112815.25591-43 | Approval Health Safety & Wellness Plan | Material | Lump Sum |  | 8
UPC112815.25565-3 | Approval Preliminary Schedule & Narrative | Material | Lump Sum |  | 8
UPC112815.25565-4 | Approval Baseline Schedule | Material | Lump Sum |  | 8
UPC112815.25591-44 | Construction Staff Management Month 1 | Material | Lump Sum |  | 8
UPC112815.25591-45 | Construction Staff Management Month 2 | Material | Lump Sum |  | 8
UPC112815.25591-46 | Construction Staff Management Month 3 | Material | Lump Sum |  | 8
UPC112815.25591-48 | Design Management Month 1 | Material | Lump Sum |  | 8
UPC112815.25591-49 | Design Management Month 2 | Material | Lump Sum |  | 8
UPC112815.25591-50 | Design Management Month 3 | Material | Lump Sum |  | 8
UPC112815.25591-52 | Develop QA/QC Plan Construction | Material | Lump Sum |  | 8
UPC112815.25591-53 | Approval of QA/QC Plan Construction | Material | Lump Sum |  | 8
UPC112815.25591-54 | Construction QA/QC Plan Month 1 | Material | Lump Sum |  | 8
UPC112815.25591-55 | Construction QA/QC Plan Month 2 | Material | Lump Sum |  | 8
UPC112815.25591-56 | Construction QA/QC Plan Month 3 | Material | Lump Sum |  | 8
UPC112815.40012-6 | Utility Coordination & Design Remaining | Material | Lump Sum |  | 8
UPC112815.25591-57 | Railroad Coordination Month 5 | Material | Lump Sum |  | 8
UPC112815.00100 | MOBILIZATION | Material | Lump Sum |  | 8
UPC112815.00101 | CONSTRUCTION SURVEYING | Material | Month |  | 8
UPC112815.25593-1 | QUALITY ASSURANCE | Material | Lump Sum |  | 8
UPC112815.25593-2 | QUALITY CONTROL | Material | Lump Sum |  | 8
UPC112815.00104-4 | PUBLIC RELATIONS | Material | Lump Sum |  | 8
UPC112815.49013 | UTILITY RELOCATION | Material | Lump Sum |  | 8
UPC112815.00108 | NS MONITORING INSTRUMENTATION AND MONITORING | Material | Lump Sum |  | 8
UPC112815.24330 | INCIDENT MANAGEMENT PLAN | Material | Lump Sum |  | 8
UPC112815.00109* | UTILITY LOCATING (TEST PITS) | Material | Each |  | 8
UPC112815.00111 | CLEARING AND GRUBBING | Material | Acres |  | 8
UPC112815.00120 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
UPC112815.00140 | BORROW EXCAVATION | Material | Cubic Yard |  | 8
UPC112815.00588 | UNDERDRAIN UD-4 | Material | Linear Feet |  | 8
UPC112815.00590 | CROSSDRAIN CD-1 | Material | Linear Feet |  | 8
UPC112815.00591 | CROSSDRAIN CD-2 | Material | Linear Feet |  | 8
UPC112815.00595 | OUTLET PIPE | Material | Linear Feet |  | 8
UPC112815.00596 | EW-12 | Material | Each |  | 8
UPC112815.00700* | POST INSTALLATION INSPECTION | Material | Linear Feet |  | 8
UPC112815.00525 | CONCRETE CLASS A3 MISC | Material | Cubic Yard |  | 8
UPC112815.01152 | 15" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01182 | 18" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01242 | 24" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01302 | 30" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01362 | 36" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01422 | 42" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01482 | 48" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.01542 | 54" CONC. PIPE | Material | Linear Feet |  | 8
UPC112815.06150 | 15" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06180 | 18" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06240 | 24" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06300 | 30" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06360 | 36" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06420 | 42" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06480 | 48" END SECTION, ES-1 OR 2 | Material | Each |  | 8
UPC112815.06745* | DROP INLET DI-2 | Material | Each |  | 8
UPC112815.06815* | DROP INLET DI-3 | Material | Each |  | 8
UPC112815.07106* | DROP INLET DI-4 | Material | Each |  | 8
UPC112815.07506 | DROP INLET DI-5 | Material | Each |  | 8
UPC112815.08185* | DROP INLET DI-10 | Material | Each |  | 8
UPC112815.09056 | MANHOLE MH-1 OR 2 | Material | Linear Feet |  | 8
UPC112815.09057 | FRAME & COVER MH-1 | Material | Each |  | 8
UPC112815.14411 | PIPE TIE IN | Material | Each |  | 8
UPC112815.01400-1 | REM EXIST PIPE END WALLS-ALL SIZES, TYPES | Material | Each |  | 8
UPC112815.01400-2 | REM EXIST DRAINAGE PIPE-ALL SIZES, TYPES | Material | Linear Feet |  | 8
UPC112815.01400-3 | CLEAN EXISTING & NEW STORM PIPES-ALL SIZES | Material | Linear Feet |  | 8
UPC112815.01400-4 | SALVAGE EXISTING STORM PIPES (CLEAN&INSPECT ONLY) | Material | Linear Feet |  | 8
UPC112815.09150 | EROS CTRL STONE CL I EC-1 | Material | Tons |  | 8
UPC112815.09185 | PAVED DITCH PG-2A | Material | Square Yard |  | 8
UPC112815.10103 | AGGR. MATL. NO. 25 OR 26 | Material | Tons |  | 8
UPC112815.00270 | SELECT MATL. TY. I MIN. CBR-30 | Material | Tons |  | 8
UPC112815.10017 | CEM STAB AGGR BASE MATL.TY.I NO. 21A | Material | Tons |  | 8
UPC112815.10062 | ASPH-STAB. OPEN-GRADED MATERIAL | Material | Tons |  | 8
UPC112815.10113 | AGGR. BASE MATL. TY.I NO. 21A OR 21B | Material | Tons |  | 8
UPC112815.10415 | PRIME COAT | Material | Gallon |  | 8
UPC112815.10603 | ASPHALT CONCRETE IM-19.0A | Material | Tons |  | 8
UPC112815.10628 | FLEXIBLE PAVE. PLANING 0" - 2" | Material | Square Yard |  | 8
UPC112815.10635 | ASPHALT CONCRETE SM-9.5A | Material | Tons |  | 8
UPC112815.10636 | ASPHALT CONCRETE SM-9.5D | Material | Tons |  | 8
UPC112815.10642 | ASPHALT CONCRETE BM-25.0A | Material | Tons |  | 8
UPC112815.11070 | NS SAW-CUT ASPH CONC | Material | Linear Feet |  | 8
UPC112815.12020 | STD. CURB CG-2 | Material | Linear Feet |  | 8
UPC112815.12030 | STD. CURB CG-3 | Material | Linear Feet |  | 8
UPC112815.12600 | STD. COMB. CURB & GUTTER CG-6 | Material | Linear Feet |  | 8
UPC112815.12940 | ENTRANCE GUTTER CG-9D | Material | Square Yard |  | 8
UPC112815.13108 | CG-12 DETECTABLE WARNING SURFACE | Material | Square Yard |  | 8
UPC112815.13212 | ROW MONUMENT, RM-2 | Material | Each |  | 8
UPC112815.13220 | HYDRAULIC CEMENT CONC. SIDEWALK 4" | Material | Square Yard |  | 8
UPC112815.13219* | CONC CURB RAMP | Material | Square Yard |  | 8
UPC112815.13280 | GUARDRAIL GR-MGS1 | Material | Linear Feet |  | 8
UPC112815.13286 | GUARDRAIL TERMINAL GR-MGS2 | Material | Each |  | 8
UPC112815.13287 | GUARDRAIL END ANCHORAGE GR-MGS3 | Material | Each |  | 8
UPC112815.13288 | GUARDRAIL HEIGHT TRANSITION GR-MGS4 | Material | Each |  | 8
UPC112815.13383 | FIXED OBJECT ATTACH. GR-FOA-1, TY I | Material | Each |  | 8
UPC112815.13384 | FIXED OBJECT ATTACH. GR-FOA-1, TY II | Material | Each |  | 8
UPC112815.13392 | FIXED OBJECT ATTACH. GR-FOA-2, TY I | Material | Each |  | 8
UPC112815.13393 | FIXED OBJECT ATTACH. GR-FOA-2, TY II | Material | Each |  | 8
UPC112815.13400 | NS MB-CPSR-2, 3 RAIL | Material | Linear Feet |  | 8
UPC112815.13462 | MB-7F | Material | Linear Feet |  | 8
UPC112815.65710 | PIER PROTECTION SYSTEM, 54" | Material | Linear Feet |  | 8
UPC112815.13604 | IMPACT ATTEN. SERVICE (MOT) | Material | Each |  | 8
UPC112815.13815 | RETAINING WALL (MSE) | Material | Square Feet |  | 8
UPC112815.21110 | MEDIAN STRIP MS-1A | Material | Square Yard |  | 8
UPC112815.21215 | MEDIAN STRIP MS-2 | Material | Linear Feet |  | 8
UPC112815.22501 | FENCE FE-W1 | Material | Linear Feet |  | 8
UPC112815.22541 | LINE BRACE UNIT FE-W1 | Material | Each |  | 8
UPC112815.22581 | CORNER BRACE UNIT FE-W1 | Material | Each |  | 8
UPC112815.22643 | FENCE FE-CL | Material | Linear Feet |  | 8
UPC112815.22653 | LINE BRACE UNIT FE-CL | Material | Each |  | 8
UPC112815.22663 | CORNER BRACE UNIT FE-CL | Material | Each |  | 8
UPC112815.22677 | GATE FE-CL L-14' | Material | Each |  | 8
UPC112815.24100 | ALLAYING DUST | Material | Month |  | 8
UPC112815.23560 | TEMP. SAFETY FENCE 4' | Material | Linear Feet |  | 8
UPC112815.24152 | TYPE III BARRICADE 8' | Material | Each |  | 8
UPC112815.24160 | TEMPORARY (CONSTRUCTION) SIGN | Material | Square Feet |  | 8
UPC112815.24290 | TRAFFIC BARRIER SERVICE CONC. MB-7D PC | Material | Linear Feet |  | 8
UPC112815.24278 | GROUP 2 CHANNELIZING DEVICES | Material | Each |  | 8
UPC112815.24279 | PORT.CHANGEABLE MESS. SIGN | Material | Each |  | 8
UPC112815.24355 | NS POLICE PATROL | Material | Hour |  | 8
UPC112815.24370* | MOT CREW | Material | Lump Sum |  | 8
UPC112815.24201*-1 | TEMP MOT PAVING | Material | Square Yard |  | 8
UPC112815.24201*-2 | TEMP MOT DRAINAGE | Material | Linear Feet |  | 8
UPC112815.24430 | DEMOLITION OF PAVEMENT (FLEXIBLE) | Material | Square Yard |  | 8
UPC112815.24400 | OBSCURING ROADWAY | Material | Unit |  | 8
UPC112815.24600 | REMOVE EXISTING GUARDRAIL | Material | Linear Feet |  | 8
UPC112815.25002 | HANDRAIL HR-1 | Material | Linear Feet |  | 8
UPC112815.25505 | FIELD OFFICE TY I | Material | Month |  | 8
UPC112815.27013 | TOPSOIL CLASS A | Material | Cubic Yard |  | 8
UPC112815.27102 | REGULAR SEED | Material | LB |  | 8
UPC112815.27103 | OVERSEEDING | Material | LB |  | 8
UPC112815.27215 | FERTILIZER (15-30-15) | Material | Tons |  | 8
UPC112815.27250 | LIME | Material | Tons |  | 8
UPC112815.27288 | EROSION CONTROL MULCH | Material | Acres |  | 8
UPC112815.27318 | PROTECTIVE COVERING EC-2 | Material | Square Yard |  | 8
UPC112815.27325 | SOIL STABILIZATION MAT EC-3 | Material | Square Yard |  | 8
UPC112815.27410 | CHECK DAM, ROCK TY. I | Material | Each |  | 8
UPC112815.09250 | SLOPE DRAIN | Material | Each |  | 8
UPC112815.27422 | DEWATERING BASIN | Material | Each |  | 8
UPC112815.27451 | INLET PROTECTION, TYPE A | Material | Each |  | 8
UPC112815.27461 | INLET PROTECTION, TYPE B | Material | Each |  | 8
UPC112815.27470* | E&S AND MISC LABOR CREW | Material | Month |  | 8
UPC112815.27471* | CONSTRUCTION ENTRANCE | Material | Each |  | 8
UPC112815.27472* | TEMPORARY SEEDING | Material | Acres |  | 8
UPC112815.27505 | TEMP. SILT FENCE TYPE A | Material | Linear Feet |  | 8
UPC112815.27504 | TEMP. SILT FENCE TYPE B | Material | Linear Feet |  | 8
UPC112815.27530* | TEMP SEDIMENT TRAP | Material | Each |  | 8
UPC112815.27531* | NS STREAM RELOCATION | Material | Linear Feet |  | 8
UPC112815.27543 | NS STORM WATER MGMT (BIOFILTER) | Material | Square Yard |  | 8
UPC112815.27560 | TEMPORARY RISER AND OUTLET | Material | Each |  | 8
UPC112815.27545 | STORM WATER MAN. BASIN EXCAV. | Material | Cubic Yard |  | 8
UPC112815.27550 | SMW-1 STRUCTURE | Material | Linear Feet |  | 8
UPC112815.38900 | NS PLANT OR TREE BIORETENTION 2-1 | Material | Each |  | 8
UPC112815.38950-1 | NS LANDSCAPE POND 1-1 AERATION | Material | Lump Sum |  | 8
UPC112815.38950-2 | NS LANDSCAPE AQUATIC BENCH SEEDING | Material | Square Yard |  | 8
UPC112815.38950-3 | NS LANDSCAPE WETLAND SEEDING | Material | Square Yard |  | 8
UPC112815.50108-1 | SIGN PANEL (OVERHEAD) | Material | Square Feet |  | 8
UPC112815.50108-2 | SIGN PANEL (GROUND MOUNT) | Material | Square Feet |  | 8
UPC112815.50414 | VIA SIGN POST, W14 X 22 | Material | Linear Feet |  | 8
UPC112815.50415 | VIA SIGN POST, W14 X 26 | Material | Linear Feet |  | 8
UPC112815.50417 | VIA SIGN POST, W16 X 31 | Material | Linear Feet |  | 8
UPC112815.50424 | VIA SIGN POST, W16 X 40 | Material | Linear Feet |  | 8
UPC112815.50418 | VIA SIGN POST, W18 X 35 | Material | Linear Feet |  | 8
UPC112815.50419 | VIA SIGN POST, W18 X 40 | Material | Linear Feet |  | 8
UPC112815.50421 | VIA SIGN POST, W21 X 44 | Material | Linear Feet |  | 8
UPC112815.50430 | SIGN POST STP-1, 2", 14 GAGE | Material | Linear Feet |  | 8
UPC112815.50434 | SIGN POST STP-1, 2.5", 10 GAGE | Material | Linear Feet |  | 8
UPC112815.50432 | SIGN POST STP-1, 2 3/16" | Material | Linear Feet |  | 8
UPC112815.50900 | NS TRAFFIC SIGN 4" SQ TUBE SIGN POST (STP-2) | Material | Linear Feet |  | 8
UPC112815.50485 | STP-1 CONCRETE FOUNDATION | Material | Each |  | 8
UPC112815.50491* | STP-2 CONCRETE FOUNDATION | Material | Each |  | 8
UPC112815.50528 | CONC.FOUND.SSP-VI A 3'0" DIA.X 7' DEPTH | Material | Each |  | 8
UPC112815.50544 | CONC.FOUND.SSP-VI A 3'6" DIA.X 9' DEPTH | Material | Each |  | 8
UPC112815.50548 | CONC.FOUND.SSP-VI A 3'6" DIA.X 10' DEPTH | Material | Each |  | 8
UPC112815.50320 | NS REMOVE AND DISPOSE OF GM SIGN STRUCTURE | Material | Each |  | 8
UPC112815.50310 | NS REMOVE EXISTING OH SIGN STRUCTURE AND LIGHTS | Material | Each |  | 8
UPC112815.50902-1 | NS OH SIGN STRUCTURE - 79' TRUSS | Material | Each |  | 8
UPC112815.50902-2 | NS OH SIGN STRUCTURE - 24' CANTILEVER | Material | Each |  | 8
UPC112815.50902-3 | NS OH SIGN STRUCTURE - 26' CANTILEVER | Material | Each |  | 8
UPC112815.50902-4 | NS OH SIGN STRUCTURE - 30' CANTILEVER | Material | Each |  | 8
UPC112815.50902-5 | NS OH SIGN STRUCTURE - 34' CANTILEVER | Material | Each |  | 8
UPC112815.50902-6 | NS OH SIGN STRUCTURE - 38' CANTILEVER | Material | Each |  | 8
UPC112815.50902-7 | NS OH SIGN STRUCTURE - 39' CANTILEVER | Material | Each |  | 8
UPC112815.50575 | CONC.FOUND.O/H SIGN STRUCTURE | Material | Cubic Yard |  | 8
UPC112815.56205-1 | TEST BORES O/H SIGNS | Material | Each |  | 8
UPC112815.54032 | TY. B CL. I PAVE. LINE MARK. 4" | Material | Linear Feet |  | 8
UPC112815.54034 | TY. B CL I PAVE LINE MARK 6" | Material | Linear Feet |  | 8
UPC112815.54037 | TY. B CL. I PAVE. LINE MARK. 8" | Material | Linear Feet |  | 8
UPC112815.54040 | TY. B CL. I PAVE. LINE MARK. 12" | Material | Linear Feet |  | 8
UPC112815.54041 | TY. B CL. I PAVE. LINE MARK. 24" | Material | Linear Feet |  | 8
UPC112815.54392 | TY. B CL. I PVMT SYMB MRKG "ONLY" | Material | Each |  | 8
UPC112815.54574 | TY. B CL. I PVMT SYMB MRKG (SGL TURN ARROW) | Material | Each |  | 8
UPC112815.54585 | PVMT SYMB MRKG (DBL TURN ARROW, LT/RT) TY B, CL I | Material | Each |  | 8
UPC112815.54217* | PLASTIC INLAID MARKERS (PIMS) ASPH ONE SIDED | Material | Each |  | 8
UPC112815.54240 | TEMP. PAVE. MARKER 1 WAY | Material | Each |  | 8
UPC112815.54105 | ERAD. OF EXIST.LINEAR PAVE.MARKING | Material | Linear Feet |  | 8
UPC112815.54543 | TYPE D, CLASS III TEMP. PVMT MRKG 6" | Material | Linear Feet |  | 8
UPC112815.51170 | ELECTRICAL SERVICE SE-5 | Material | Each |  | 8
UPC112815.51198 | PEDESTRIAN ACTUATION PA-2 | Material | Each |  | 8
UPC112815.51212 | PEDESTRIAN POLE PF-2 12' | Material | Each |  | 8
UPC112815.51238 | CONC. FOUNDATION SIGNAL POLE PF-8 | Material | Each |  | 8
UPC112815.51240 | CONC. FOUNDATION PF-2 | Material | Each |  | 8
UPC112815.51247 | CONC. FOUNDATION CF-3 | Material | Each |  | 8
UPC112815.51030 | CONTROLLER AND CABINET | Material | Each |  | 8
UPC112815.51540 | LOOP DETECTOR AMPLIFIER | Material | Each |  | 8
UPC112815.51484*-1 | SIGNAL MAST ARM POLE MP-1 20' ONE ARM 30' | Material | Each |  | 8
UPC112815.51484*-2 | SIGNAL MAST ARM POLE MP-1 20' ONE ARM 40' | Material | Each |  | 8
UPC112815.51484*-3 | SIGNAL MAST ARM POLE MP-1 20' ONE ARM 49' | Material | Each |  | 8
UPC112815.51484*-4 | SIGNAL MAST ARM POLE MP-1 20' ONE ARM 60' | Material | Each |  | 8
UPC112815.51484*-5 | SIGNAL MAST ARM POLE MP-3 ONE ARM 40' | Material | Each |  | 8
UPC112815.51484*-6 | SIGNAL MAST ARM POLE MP-3 ONE ARM 60' | Material | Each |  | 8
UPC112815.51484*-7 | SIGNAL MAST ARM POLE MP-3 ONE ARM 70' | Material | Each |  | 8
UPC112815.51484*-8 | SIGNAL MAST ARM POLE MP-3 ONE ARM 78' | Material | Each |  | 8
UPC112815.51484*-9 | SIGNAL MAST ARM POLE MP-3 TWO ARMS 49' & 60' | Material | Each |  | 8
UPC112815.55179* | 10' LUMINAIRE ARM (SIGNALS) | Material | Each |  | 8
UPC112815.51598 | 8/3 CONDUCTOR CABLE | Material | Linear Feet |  | 8
UPC112815.51615 | 14/1 ENCLOSED CONDUCTOR CABLE | Material | Linear Feet |  | 8
UPC112815.51600 | 14/2 CONDUCTOR CABLE | Material | Linear Feet |  | 8
UPC112815.51700 | 14/2 CONDUCTOR CABLE SHIELDED | Material | Linear Feet |  | 8
UPC112815.51702 | 14/4 CONDUCTOR CABLE | Material | Linear Feet |  | 8
UPC112815.51607 | 14/7 CONDUCTOR CABLE | Material | Linear Feet |  | 8
UPC112815.55125* | #6 AWG EGC | Material | Linear Feet |  | 8
UPC112815.52404 | PEDESTRIAN SIGNAL HEAD SP-9 | Material | Each |  | 8
UPC112815.51005 | MASTER CONTROLLER | Material | Each |  | 8
UPC112815.51513 | WIRELESS RADIO | Material | Each |  | 8
UPC112815.55586-1 | JUNCTION BOX JB-S1 - SIGNAL | Material | Each |  | 8
UPC112815.55587 | JUNCTION BOX JB-S2 | Material | Each |  | 8
UPC112815.55588 | JUNCTION BOX JB-S3 | Material | Each |  | 8
UPC112815.56014 | ELECT.SER.GRD.ELECTRODE 10' | Material | Each |  | 8
UPC112815.56021 | 1" PVC CONDUIT | Material | Linear Feet |  | 8
UPC112815.56026 | 1 1/4" METAL CONDUIT | Material | Linear Feet |  | 8
UPC112815.56053-1 | 2" PVC CONDUIT - SIGNAL | Material | Linear Feet |  | 8
UPC112815.56055-1 | 4" PVC CONDUIT - SIGNAL | Material | Linear Feet |  | 8
UPC112815.56050 | BORED CONDUIT 2" | Material | Linear Feet |  | 8
UPC112815.56052-1 | BORED CONDUIT 4" - SIGNAL | Material | Linear Feet |  | 8
UPC112815.56200-1 | TRENCH EXCAVATION ECI-1 - SIGNAL | Material | Linear Feet |  | 8
UPC112815.56205-2 | TEST BORE SIGNALS | Material | Each |  | 8
UPC112815.51530*-1 | EMERG. PREEMPT. CABLE | Material | Linear Feet |  | 8
UPC112815.51992* | UNINTERRUPTABLE POWER SUPPLY | Material | Each |  | 8
UPC112815.51912 | LOOP SAW CUT 3/8" | Material | Linear Feet |  | 8
UPC112815.51913 | LOOP SAW CUT 5/8" | Material | Linear Feet |  | 8
UPC112815.51000 | TEMP SIGNAL - PW PKWY/BFR | Material | Lump Sum |  | 8
UPC112815.51530*-2 | EMERGENCY PRE-EMPTION 3 WAY | Material | Each |  | 8
UPC112815.51530*-3 | EMERGENCY PRE-EMPTION 4 WAY | Material | Each |  | 8
UPC112815.51184/51830 | SIGNAL HEAD, LED 12" 3-SECTION, BACKPLATE AND SM-3 | Material | Each |  | 8
UPC112815.51951 | SIGN PANEL (SIGNALS) | Material | Square Feet |  | 8
UPC112815.51963 | REMOVAL AND SALVAGE OF EXISTING TRAFFIC SIGNAL (PE | Material | Each |  | 8
UPC112815.51968-1 | ELECTRICAL UTILITY SERVICE CONNECTION FEE | Material | Each |  | 8
UPC112815.51968-2 | COMM UTILITY SERVICE CONNECTION FEE | Material | Each |  | 8
UPC112815.52002 | MAINTENANCE OF EXISTING SIGNALS (PER INTERSECTION) | Material | Each |  | 8
UPC112815.55140 | CONCRETE FOUNDATION LF-1 TY. A | Material | Each |  | 8
UPC112815.24502 | NS REMOVE EXIST LIGHT POLE & FOUND | Material | Each |  | 8
UPC112815.55200*-1 | 45' LIGHT POLE W/ 5' ARM | Material | Each |  | 8
UPC112815.55200*-2 | 45' LIGHT POLE W/ 7' ARM | Material | Each |  | 8
UPC112815.55200*-3 | 45' LIGHT POLE W/ 10' ARM | Material | Each |  | 8
UPC112815.55200*-4 | 45' LIGHT POLE W/ TWIN 5' ARMS | Material | Each |  | 8
UPC112815.55505*-1 | 280 WATT LUMINAIRE | Material | Each |  | 8
UPC112815.55505*-2 | 280 WATT LUMINAIRE (UNDER BRIDGE) | Material | Each |  | 8
UPC112815.55020 | 2 CONDUCTOR CABLE (WITH SPLICE KITS) | Material | Linear Feet |  | 8
UPC112815.55040 | 4 CONDUCTOR CABLE (W/ SPLICE KITS) | Material | Linear Feet |  | 8
UPC112815.55060 | 6 CONDUCTOR CABLE (W/SPLICE KITS) | Material | Linear Feet |  | 8
UPC112815.55080 | 8 CONDUCTOR CABLE (W/SPLICE KITS) | Material | Linear Feet |  | 8
UPC112815.55100 | 10 CONDUCTOR CABLE (W/ SPLICE KITS) | Material | Linear Feet |  | 8
UPC112815.55346 | ELECT. SERVICE SE-8 TYPE A | Material | Each |  | 8
UPC112815.55353 | CONTROL CENTER CCW-1 TYPE D | Material | Each |  | 8
UPC112815.55580 | JUNCTION BOX JB-R1 (ON BRIDGE) | Material | Each |  | 8
UPC112815.56022 | 1" METAL CONDUIT | Material | Linear Feet |  | 8
UPC112815.55586-2 | JUNCTION BOX JB-S1 - LIGHTING | Material | Each |  | 8
UPC112815.56052-2 | BORED CONDUIT 4" - LIGHTING | Material | Linear Feet |  | 8
UPC112815.56053-2 | 2" PVC CONDUIT - LIGHTING | Material | Linear Feet |  | 8
UPC112815.56054 | 3" PVC CONDUIT | Material | Linear Feet |  | 8
UPC112815.56055-2 | 4" PVC CONDUIT - LIGHTING | Material | Linear Feet |  | 8
UPC112815.56200-2 | TRENCH EXCAVATION ECI-1 - LIGHTING | Material | Linear Feet |  | 8
UPC112815.59003 | NS LIGHTING - ELEC UTILITY SERVICE CONNECTION FEES | Material | Each |  | 8
UPC112815.60420 - PW | CONCRETE CLASS A4 (LOW PERMEABILITY) - PW PKWY | Material | Cubic Yard |  | 8
UPC112815.60450 - PW | CONC. CL. A4 BRIDGE APPR. SLAB - PW PKWY | Material | Cubic Yard |  | 8
UPC112815.60452 - PW | REINF. STEEL BRIDGE APPR. SLAB - PW PKWY | Material | LB |  | 8
UPC112815.60490 - PW | BRIDGE DECK GROOVING - PW PKWY | Material | Square Yard |  | 8
UPC112815.61812 - PW | STR.STEEL PLATE GIRDER ASTM A709 GRADE 50W - PW PKWY | Material | LB |  | 8
UPC112815.62036* - PW | RAILING, CPSR 1, 2 RAIL - PW PKWY | Material | Linear Feet |  | 8
UPC112815.62034 - PW | RAILING, CPSR 2, 3 RAIL - PW PKWY | Material | Linear Feet |  | 8
UPC112815.64011 - PW | STRUCTURE EXCAVATION - PW PKWY | Material | Cubic Yard |  | 8
UPC112815.64015 - PW | SELECT BACKFILL ABUTMENT ZONE - PW PKWY | Material | Tons |  | 8
UPC112815.64036 - PW | PIPE UNDERDRAIN 6" - PW PKWY | Material | Linear Feet |  | 8
UPC112815.64112 - PW | STEEL PILES 12" - PW PKWY | Material | Linear Feet |  | 8
UPC112815.65013 - PW | CONCRETE CLASS A3 - PW PKWY | Material | Cubic Yard |  | 8
UPC112815.65200 - PW | REINF. STEEL - PW PKWY | Material | LB |  | 8
UPC112815.65211 - PW | CORROSION RESISTANT REINF.STEEL CL. I - PW PKWY | Material | LB |  | 8
UPC112815.65213 - PW | CORROSION RESISTANT REINF.STEEL CL. III - PW PKWY | Material | LB |  | 8
UPC112815.62004 - PW | ARCHITECTURAL TREATMENT - PW PKWY | Material | Square Yard |  | 8
UPC112815.67910 - PW | NS NBIS ACCESS, UNDER BRIDGE - PW PKWY | Material | Day |  | 8
UPC112815.60495 - PW | COVER DEPTH SURVEY - PW PKWY | Material | Square Yard |  | 8
UPC112815.60420 - NSRR | CONCRETE CLASS A4 (LOW PERMEABILITY) - NSRR | Material | Cubic Yard |  | 8
UPC112815.60450 - NSRR | CONC. CL. A4 BRIDGE APPR. SLAB - NSRR | Material | Cubic Yard |  | 8
UPC112815.60452 - NSRR | REINF. STEEL BRIDGE APPR. SLAB - NSRR | Material | LB |  | 8
UPC112815.60490 - NSRR | BRIDGE DECK GROOVING - NSRR | Material | Square Yard |  | 8
UPC112815.61812 - NSRR | STR.STEEL PLATE GIRDER ASTM A709 GRADE 50W - NSRR | Material | LB |  | 8
UPC112815.62036* - NSRR | RAILING, CPSR 1, 2 RAIL - NSRR | Material | Linear Feet |  | 8
UPC112815.62034 - NSRR | RAILING, CPSR 2, 3 RAIL - NSRR | Material | Linear Feet |  | 8
UPC112815.64011 - NSRR | STRUCTURE EXCAVATION - NSRR | Material | Cubic Yard |  | 8
UPC112815.64015 - NSRR | SELECT BACKFILL ABUTMENT ZONE - NSRR | Material | Tons |  | 8
UPC112815.64036 - NSRR | PIPE UNDERDRAIN 6" - NSRR | Material | Linear Feet |  | 8
UPC112815.64112 - NSRR | STEEL PILES 12" - NSRR | Material | Linear Feet |  | 8
UPC112815.65013 - NSRR | CONCRETE CLASS A3 - NSRR | Material | Cubic Yard |  | 8
UPC112815.65211 - NSRR | CORROSION RESISTANT REINF.STEEL CL. I - NSRR | Material | LB |  | 8
UPC112815.65213 - NSRR | CORROSION RESISTANT REINF.STEEL CL. III - NSRR | Material | LB |  | 8
UPC112815.67090 - NSRR | NS PEDESTRIAN FENCE 9' - NSRR | Material | Linear Feet |  | 8
UPC112815.62004 - NSRR | ARCHITECTURAL TREATMENT - NSRR | Material | Square Yard |  | 8
UPC112815.67910 - NSRR | NS NBIS ACCESS, UNDER BRIDGE - NSRR | Material | Day |  | 8
UPC112815.60495 - NSRR | COVER DEPTH SURVEY - NSRR | Material | Square Yard |  | 8
UPC112815.70201 - NSRR | NS CLEARING PARCEL 49/59 (D-601) | Material | Lump Sum |  | 8
UPC112815.70510 - NSRR | CONTAMINATED MATERIALS (SOIL) | Material | Cubic Yard |  | 8
UPC112815.25591-58 | Construction Staff Management Month 3-33 | Material | Lump Sum |  | 8
UPC112815.25591-59 | Environmental Permitting | Material | Lump Sum |  | 8
UPC112815.25591-60 | Design Management Remaining | Material | Lump Sum |  | 8
UPC112815.25591-61 | Supplemental Geotechnical Investigations Field Investigations & Analysis 3 | Material | Lump Sum |  | 8
UPC112815.25591-62 | Supplemental Geotechnical Investigations Field Investigations & Analysis 4 | Material | Lump Sum |  | 8
UPC112815.25591-63 | Prepare Final Plans 1 Roadway | Material | Lump Sum |  | 8
UPC112815.25591-64 | Prepare Final Plans 2 Roadway | Material | Lump Sum |  | 8
UPC112815.25591-65 | Prepare Final Plans 3 Roadway | Material | Lump Sum |  | 8
UPC112815.25591-66 | Prepare Final Plans QA/QC Roadway | Material | Lump Sum |  | 8
UPC112815.25591-67 | Prepare Final Plans Address Comments Roadway | Material | Lump Sum |  | 8
UPC112815.25591-68 | Prepare Final Plans Address Comments QA/QC Roadway | Material | Lump Sum |  | 8
UPC112815.25591-69 | Final Plans Approval Roadway | Material | Lump Sum |  | 8
UPC112815.25591-70 | Obtain PWC Design Approval | Material | Lump Sum |  | 8
UPC112815.25591-71 | Obtain VDOT Design Approval | Material | Lump Sum |  | 8
UPC112815.25591-72 | Railroad Coordination Month 6 | Material | Lump Sum |  | 8
UPC112815.25591-73 | Railroad Coordination Month 7 | Material | Lump Sum |  | 8
UPC112815.25591-74 | Submit AWP | Material | Lump Sum |  | 8
UPC112815.25591-75 | Review Comments AWP | Material | Lump Sum |  | 8
UPC112815.25591-76 | QA/QC AWP | Material | Lump Sum |  | 8
UPC112815.25591-77 | Approval of AWP | Material | Lump Sum |  | 8
UPC112815.70096-3 | Prepare ROW Acquisistion Plats West of PW | Material | Lump Sum |  | 8
UPC112815.70096-4 | Title Report Prep West of PW | Material | Lump Sum |  | 8
UPC112815.70096-5 | Appraisals & Appraisal Reviews 1 West of PW | Material | Lump Sum |  | 8
UPC112815.70096-6 | Appraisals & Appraisal Reviews 2 West of PW | Material | Lump Sum |  | 8
UPC112815.70096-7 | Prepare and Submit Offers West of PW | Material | Lump Sum |  | 8
UPC112815.70096-8 | Negotiations 1 West of PW | Material | Lump Sum |  | 8
UPC112815.70096-9 | Negotiations 2 West of PW | Material | Lump Sum |  | 8
UPC112815.70096-10 | Settlement/File COT West of PW | Material | Lump Sum |  | 8
UPC112815.70096-11 | Prepare ROW Acquisistion Plats East of PW | Material | Lump Sum |  | 8
UPC112815.70096-12 | Title Report Prep East of PW | Material | Lump Sum |  | 8
UPC112815.70096-13 | Appraisals & Appraisal Reviews 1 East of PW | Material | Lump Sum |  | 8
UPC112815.70096-14 | Appraisals & Appraisal Reviews 2 East of PW | Material | Lump Sum |  | 8
UPC112815.70096-15 | Prepare and Submit Offers East of PW | Material | Lump Sum |  | 8
UPC112815.70096-16 | Negotiations 1 East of PW | Material | Lump Sum |  | 8
UPC112815.70096-17 | Negotiations 2 East of PW | Material | Lump Sum |  | 8
UPC112815.70096-18 | Settlement/File COT East of PW | Material | Lump Sum |  | 8
UPC11815.25505 | Set Up Field Office | Material | Lump Sum |  | 8
UPC112815 Exc | Excavator | Nonlabor |  |  | 1
UPC112815 Load | Loader | Nonlabor |  |  | 1
UPC112815 Doz | Dozer | Nonlabor |  |  | 1
UPC112815 Roll | Roller | Nonlabor |  |  | 1
UPC112815 Crane | Crane | Nonlabor |  |  | 1
UPC112815 Bidwell | Bidwell | Nonlabor |  |  | 1
UPC112815 MG | Motorgrader | Nonlabor |  |  | 1
UPC112815 | Balls Ford Rd. REVENUE | Material | Lump Sum |  | 8
SUB-CONT Crews | Subcontractor Crews | Labor |  |  | 1
external resources | External Resources | Labor |  |  | 1
UPC112815.25567-1 | PROGRESS SCHEDULE UPDATES | Material | Each |  | 1
UPC112815.70096-19 | QA/QC ROW Plans | Material | Lump Sum |  | 8
UPC112815.70096-20 | VDOT/County Review/Approval ROW Plans | Material | Lump Sum |  | 8
3448 - COST-L | COST | Labor |  |  | 1
C43-SUB-UNSUIT | C43 - Sub - Unsuitable Foundation Prep Crew | Labor |  |  | 1
9156-ASP | 9156 - Asphalt Adjustment | Material | Unit |  | 8
9156-SA15 | SA#15 - Additional Fiber Construction | Material | Lump Sum |  | 8
9156-SA16 | SA#16 - Global Settlement | Material | Lump Sum |  | 8
3404-WO-10 | WO #10 - Install Handheld Signs | Material | Lump Sum |  | 8
3417-Rev-Adjust | 3417 - Revenue Adjustment for Over-runs & Under-Runs | Material | Unit |  | 8
3404-WO-09 | WO #09 - Removal of Pavement Markers | Material | Lump Sum |  | 8
3404-WO-11 | WO #11 - Plastic Inlaid Pavment Marker Asphalt | Material | Lump Sum |  | 8
3418-0132 | 3418-0132 - DMS Sign Upgrade | Material | Lump Sum |  | 8
3433.I.177.1 | Asphalt Conc Surface Course, Type I19.0C | Material | Tons |  | 8
3433.U.270.1 | U2719 - Paint Pavement Marking Lines (6") | Material | Linear Feet |  | 8
3433.U.271.1 | U2719 - Paint Pavement Marking Lines (12") | Material | Linear Feet |  | 8
3433.U.431.1 | U2719 - Generic Fencing Item - Safety Fence Bridge, 72" | Material | Linear Feet |  | 8
9156-SA18 | SA#18 - Additional Septic Field Investigation | Material | Lump Sum |  | 8
9156-SA19 | SA#19 - Single Controller Upgrade | Material | Lump Sum |  | 8
9156-SA20 | SA#20 - Colonial Pipeline Construction of Basin | Material | Lump Sum |  | 8
3448 - Man Power | 3448 - Man Power Resources | Labor |  |  | 1
R-7 | 3448 - Sub | Labor |  |  | 1
3448 - Mechanic | 3448 - Mechanic | Labor |  |  | 1
3448 - Master Mechanic | 3448 - Master Mechanic | Labor |  |  | 1
3448 - Miner | 3448 - Miner | Labor |  |  | 1
3448 - Operator | 3448 - Operator | Labor |  |  | 1
3448 - Shifter | 3448 - Shifter | Labor |  |  | 1
3448 - Walker | 3448 - Walker | Labor |  |  | 1
3448 - Super | 3448 - Superintendent | Labor |  |  | 1
3433.U.336.1 | U3719 - ACSC Type S4.75A | Material | Tons |  | 8
3433.U.337.3 | U2719 - Form and Strip Portland Cement Concrete | Material | Linear Feet |  | 8
3433.U.337.2 | U2719 - Saw and Seal | Material | Linear Feet |  | 8
3433.U.337.1 | U2719 - Set Baskets | Material | Linear Feet |  | 8
3433.U.337.4 | U2719 - Drill and Epoxy Tie Bars | Material | Each |  | 8
3433.U.475.1 | U2719 - Light Standards, Type MTLT (30' SA, 15' A) | Material |  |  | 8
3433.U.475.2 | U2719 - Light Standards, Type MTLT (30' Twin Arm , 15' A) | Material |  |  | 8
3433.U.475.3 | U2719 - Light Standards, Bridge Mount Type MTLT (45' SA, 15' A) | Material |  |  | 8
3433.U.475.4 | U2719 - Light Standards, Type MTLT (45' TA, 15' A) | Material |  |  | 8
3433.U.556.1 | U2719 - Communications Cable (96-Fiber) | Material | Linear Feet |  | 8
3433.U.556.2 | U2719 - Communication Cable (48 - Fiber) | Material | Linear Feet |  | 8
3433.U.311.1 | U2719 - Embankment | Material | Cubic Yard |  | 8
3433.U.407.1 | U2719 - MSE V Ditch | Material | Linear Feet |  | 8
UPC112815.70096-21 | QA/QC ROW Plans Resubmission | Material | Lump Sum |  | 8
UPC112815.70096-22 | VDOT/County Review/Approval ROW Plans QA/QC | Material | Lump Sum |  | 8
UPC112815.25591-78 | Prepare Final Bridge Plan Balls Ford Over NSRC | Material | Lump Sum |  | 8
UPC112815.25591-79 | Prepare Final Bridge Plan 2 Balls Ford Over NSRC | Material | Lump Sum |  | 8
UPC112815.25591-80 | Incoporate VDOT Comments Balls Ford Over NSRC | Material | Lump Sum |  | 8
UPC112815.25591-81 | VDOT Approval Stage II Bridge Plans Balls Ford Over NSRC | Material | Lump Sum |  | 8
UPC112815.25591-82 | Prepare Final Bridge Plan 1 BF Over PWP | Material | Lump Sum |  | 8
UPC112815.25591-83 | Prepare Final Bridge Plan 2 BF Over PWP | Material | Lump Sum |  | 8
UPC112815.25591-84 | Incorporate VDOT Comments BF Over PWP | Material | Lump Sum |  | 8
UPC112815.25591-85 | VDOT Final Approval BF Over PWP | Material | Lump Sum |  | 8
UPC112815.25591-86 | Design Utility Area 1 West of PWP | Material | Lump Sum |  | 8
UPC112815.25591-87 | Mobilization Utility Area 1 West of PWP | Material | Lump Sum |  | 8
UPC112815.25591-88 | Relocation Utility Area 1 West of PWP | Material | Lump Sum |  | 8
UPC112815.25591-89 | Design Utility Area 2 East of PWP | Material | Lump Sum |  | 8
UPC112815.25591-90 | Mobilization Utility Area 2 East of PWP | Material | Lump Sum |  | 8
UPC112815.25591-91 | Relocation Utility Area 2 East of PWP | Material | Lump Sum |  | 8
UPC112815.40012-7 | UTILITY TEST PITS 1 | Material | Lump Sum |  | 8
UPC112815.40012-8 | UTILITY TEST PITS 2 | Material | Lump Sum |  | 8
C000056899B03 | I81/Rte 232 | Material |  |  | 8
D-2-5 | SOUND WALL LANDSCAPING | Material | Lump Sum |  | 8
3433.U.220.1 | U2719 - MSE Moment Slab | Material | Square Feet |  | 8
3448 - Laborer VI | 3448 - Laborer VI | Labor |  |  | 1
3448 - Laborer | 3448 - Laborer | Labor |  |  | 1
3448 - Operator IV | 3448 - Operator IV | Labor |  |  | 1
3448 - Operator III | 3448 - Operator III | Labor |  |  | 1
3448 - Operator II | 3448 - Operator II | Labor |  |  | 1
3448 - Operator I | 3448 - Operator I | Labor |  |  | 1
3448 - Operator IAAA | 3448 - Operator IAAA | Labor |  |  | 1
3448 - Operator IAA | 3448 - Operator IAA | Labor |  |  | 1
3448 - Operator IA | 3448 - Operator IA | Labor |  |  | 1
3448 - Laborer V | 3448 - Laborer V | Labor |  |  | 1
3448 - Laborer IV | 3448 - Laborer IV | Labor |  |  | 1
3448 - Laborer III | 3448 - Laborer III | Labor |  |  | 1
3448 - Laborer IIC | 3448 - Laborer IIC | Labor |  |  | 1
3448 - Laborer IIB | 3448 - Laborer IIB | Labor |  |  | 1
3448 - Laborer IIA | 3448 - Laborer IIA | Labor |  |  | 1
3448 - Laborer I | 3448 - Laborer I | Labor |  |  | 1
3434-433 | 13" Port Conc Pavement, Shoulders (with Dowels) | Material |  |  | 8
3434-436 | 54" Welded Steel Pipe, Grad B in Soil | Material | Linear Feet |  | 8
3434-437 | Smart Work Zone-Mobilization | Material | Lump Sum |  | 8
3434-900 | 30" Class V | Material | Linear Feet |  | 8
3434-901 | 36" Trenchless | Material | Linear Feet |  | 8
3434-902 | 48" Trenchless | Material | Linear Feet |  | 8
3434-903 | STEEL FRAME WITH TWO GRATES STD. 840.37 | Material | Each |  | 8
3434-904 | Single Arm Found | Material | Each |  | 8
3434-905 | Twin Arm Found | Material | Each |  | 8
3434-906 | Luminare 560W LED | Material | Each |  | 8
3434-907 | Type I Pushbutton Post With Foundation | Material | Each |  | 8
3434-908 | Type II Signal Pedestal With Foundation | Material | Each |  | 8
3434-909 | Signal Cabinet Foundation | Material | Each |  | 8
3434-910 | 8.5 DB Yagi Antenna | Material | Each |  | 8
3434-911 | 6 DB Omni Antenna | Material | Each |  | 8
3434-912 | 900 MHZ Ethernet Radio | Material | Each |  | 8
3434-913 | Messenger Cable (1/4") | Material | Each |  | 8
3434-914 | 3.5' DS Soil | Material | Linear Feet |  | 8
3434-915 | 3.5' DS Not Soil | Material | Linear Feet |  | 8
3434-916 | 3.5' Perm Steel Casing | Material | Linear Feet |  | 8
3434-917 | 4' Perm Steel Casing | Material | Linear Feet |  | 8
3434-918 | 5' Perm Steel Casing | Material | Linear Feet |  | 8
3434-919 | Piles HP 14 X 89 | Material | Linear Feet |  | 8
3434-920 | Class AA Concrete (Bridge) | Material | Cubic Yard |  | 8
3458 | 3458 - SH 183A Austin TX | Nonlabor |  |  | 1
3458-104-6024 | REMOVING CONC (RETAINING WALLS) | Material | Square Yard |  | 8
3458-104-6029 | REMOVING CONC (CURB OR CURB & GUTTER) | Material | Linear Feet |  | 8
3458-104-6036 | REMOVING CONC (SIDEWALK OR RAMP) | Material | Square Yard |  | 8
3458-104-6037 | REMOVE CONC (RAIL) | Material | Linear Feet |  | 8
3458-104-6054 | REMOVING CONCRETE (MOW STRIP) | Material | Linear Feet |  | 8
3458-110-6001 | EXCAVATION | Material | Cubic Yard |  | 8
3458-110-6002 | EXCAVATION (CHANNEL) | Material | Cubic Yard |  | 8
3458-110-6003 | EXCAVATION (SPECIAL) | Material | Cubic Yard |  | 8
3458-132-6001 | EMBANKMENT (FINAL)(ORD COMP)(TY A) | Material | Cubic Yard |  | 8
3458-132-6003 | EMBANKMENT (FINAL)(ORD COMP)(TY B) | Material | Cubic Yard |  | 8
3458-132-6005 | EMBANKMENT (FINAL)(ORD COMP)(TY C) | Material | Cubic Yard |  | 8
3458-132-6025 | EMBANKMENT (FINAL)(DENS CONT)(TY C1) | Material | Cubic Yard |  | 8
3458-161-6017 | COMPOST MANUF TOPSOIL (4") | Material | Square Yard |  | 8
3458-161-6030 | COMPOST MANUF TOPSOIL (6") | Material | Square Yard |  | 8
3458-162-6002 | BLOCK SODDING | Material | Square Yard |  | 8
3458-164-6003 | BROADCAST SEED (PERM) (RURAL) (CLAY) | Material | Square Yard |  | 8
3458-164-6009 | BROADCAST SEED (TEMP) (WARM) | Material | Square Yard |  | 8
3458-164-6011 | BROADCAST SEED (TEMP) COOL) | Material | Square Yard |  | 8
3458-164-6023 | CELL FBR MLCH SEED (PERM)(RURAL)(CLAY) | Material | Square Yard |  | 8
3458-164-6029 | CELL FBR MLCH SEED (TEMP)(WARM) | Material | Square Yard |  | 8
3458-164-6031 | CELL FBR MLCH SEED (TEMP)(COOL) | Material | Square Yard |  | 8
3458-168-6001 | VEGETATIVE WATERING | Material | Gallon |  | 8
3458-169-6001 | SOIL RETENTION BLANKETS (CL 1) (TY A) | Material | Square Yard |  | 8
3458-169-6005 | SOIL RETENTION BLANKETS (CL 2) (TY E) | Material | Square Yard |  | 8
3458-169-6007 | SOIL RETENTION BLANKETS (CL 2) (TY G) | Material | Square Yard |  | 8
3458-192-6004 | PLANT MATERIAL (5-GAL) | Material | Each |  | 8
3458-192-6015 | LANDSCAPE EDGE | Material | Linear Feet |  | 8
3458-192-6071 | PLANT MATERIAL (10 GAL) | Material | Each |  | 8
3458-192-6072 | PLANT MATERIAL (7-GAL) | Material | Each |  | 8
3458-192-6074 | PLANT MATERIAL (25 GAL) (TREE) | Material | Each |  | 8
3458-192-6076 | PLANT MATERIAL (36IN BOX) (MIN 4IN CAL) | Material | Each |  | 8
3458-192-6101 | LANDSCAPE EDGE GROUTED RIVER ROCK | Material | Linear Feet |  | 8
3458-192-9001 | CONC LANDSCAPE EDGE (CONC BAND 18") | Material | Linear Feet |  | 8
3458-216-6001 | PROOF ROLLING | Material | Hour |  | 8
3458-247-6366 | FL BS (CMP IN PLC)(TY A GR 5)(FNAL POS) | Material | Cubic Yard |  | 8
3458-247-6381 | FL BS (CMP IN PLC)(TY A GR 5)(4") | Material | Square Yard |  | 8
3458-276-6302 | CEM TRT (PLNT MX)(CL N)(TY A)(GR 5)(6") | Material | Square Yard |  | 8
3458-276-9001 | CEM TRT (PLNT MX)(CL N)(TY A)(GR 5)(8") | Material | Square Yard |  | 8
3458-305-6033 | SALV, HAUL & STKPL RCL APH PV (0 TO 8") | Material | Square Yard |  | 8
3458-310-6001 | PRIME COAT (MULTI OPTION) | Material | Gallon |  | 8
3458-340-6246 | D-GR HMA (SQ) TY-D PG64-22 (LEVEL-UP) | Material | Ton |  | 8
3458-347-6001 | TOM (ASPHALT) PG 76-22 | Material | Ton |  | 8
3458-347-6002 | TOM - C (AGGREGATE) SAC - A | Material | Ton |  | 8
3458-347-6008 | TACK COAT | Material | Gallon |  | 8
3458-351-6008 | FLEXIBLE PAVEMENT STRUCTURE REPAIR (12") | Material | Square Yard |  | 8
3458-354-6020 | PLANE ASPH CONC PAV (0" TO 1") | Material | Square Yard |  | 8
3458-360-6013 | CONC PVMT (CONT REINF - CRCP)(10.5") | Material | Square Yard |  | 8
3458-360-6086 | CONC PAV (JOINT REINF) (11") | Material | Square Yard |  | 8
3458-400-6005 | CEM STABIL BKFL | Material | Cubic Yard |  | 8
3458-400-6008 | CUT & RESTORE ASPH PAVING | Material | Square Yard |  | 8
3458-402-6001 | TRENCH EXCAVATION PROTECTION | Material | Linear Feet |  | 8
3458-403-6001 | TEMPORARY SPL SHORING | Material | Square Feet |  | 8
3458-403-6002 | TEMPORARY SPL SHORING (SOIL NAIL) | Material | Square Feet |  | 8
3458-410-6001 | SOIL NAIL ANCHORS | Material | Linear Feet |  | 8
3458-416-6001 | DRILL SHAFT (18 IN) | Material | Linear Feet |  | 8
3458-416-6002 | DRILL SHAFT (24 IN) | Material | Linear Feet |  | 8
3458-416-6004 | DRILL SHAFT (36 IN) | Material | Linear Feet |  | 8
3458-416-6005 | DRILL SHAFT (42 IN) | Material | Linear Feet |  | 8
3458-416-6006 | DRILL SHAFT (48 IN) | Material | Linear Feet |  | 8
3458-416-6008 | DRILL SHAFT (60 IN) | Material | Linear Feet |  | 8
3458-416-6015 | DRILL SHAFT (NON - REINFORCED) (12 IN) | Material | Linear Feet |  | 8
3458-416-6018 | DRILL SHAFT (SIGN MTS) (24 IN) | Material | Linear Feet |  | 8
3458-416-6022 | DRILL SHAFT (SIGN MTS) (48 IN) | Material | Linear Feet |  | 8
3458-416-6023 | DRILL SHAFT (SIGN MTS) (54 IN) | Material | Linear Feet |  | 8
3458-416-6029 | DRILL SHAFT (RDWY ILL POLE) (30 IN) | Material | Linear Feet |  | 8
3458-416-6031 | DRILL SHAFT (TRF SIG POLE) (30 IN) | Material | Linear Feet |  | 8
3458-416-6032 | DRILL SHAFT (TRF SIG POLE) (36 IN) | Material | Linear Feet |  | 8
3458-416-6034 | DRILL SHAFT (TRF SIG POLE) (48 IN) | Material | Linear Feet |  | 8
3458-416-6068 | DRILL SHAFT (SIGN MTS) (60 IN) | Material | Linear Feet |  | 8
3458-420-6009 | CL A CONC (COLLAR) | Material | Each |  | 8
3458-420-6012 | CL B CONC (MISC) | Material | Cubic Yard |  | 8
3458-420-6013 | CL C CONC (ABUT) | Material | Cubic Yard |  | 8
3458-420-6019 | CL C CONC (ABUT)(EXTEND) | Material | Cubic Yard |  | 8
3458-420-6029 | CL C CONC (CAP) | Material | Cubic Yard |  | 8
3458-420-6033 | CL C CONC (CAP)(EXTEND) | Material | Cubic Yard |  | 8
3458-420-6037 | CL C CONC (COLUMN) | Material | Cubic Yard |  | 8
3458-420-6043 | CL C CONC (FOOTING) | Material | Cubic Yard |  | 8
3458-420-6066 | CL C CONC (RAIL FOUNDATION) | Material | Cubic Yard |  | 8
3458-420-6068 | CL C CONC (SIGN COLUMN) | Material | Cubic Yard |  | 8
3458-420-6074 | CL C CONC (MISC) | Material | Cubic Yard |  | 8
3458-420-6156 | CL C CONC (WEBWALL) | Material | Cubic Yard |  | 8
3458-420-9001 | CL S CONC (MISC) | Material | Cubic Yard |  | 8
3458-420-9002 | CL H CONC (COPING & PILASTER CAP) | Material | Linear Feet |  | 8
3458-422-6001 | REINF CONC SLAB | Material | Square Feet |  | 8
3458-422-6003 | REINF CONC SLAB (EXTEND SLAB) | Material | Square Feet |  | 8
3458-422-6015 | APPROACH SLAB | Material | Cubic Yard |  | 8
3458-422-6035 | APPROACH SLAB (EXTEND) | Material | Cubic Yard |  | 8
3458-423-6001 | RETAINING WALL (MSE) | Material | Square Feet |  | 8
3458-423-6004 | RETAINING WALL (CONC BLOCK) | Material | Square Feet |  | 8
3458-423-6005 | RETAINING WALL (SPREAD FOOTING) | Material | Square Feet |  | 8
3458-423-6006 | RETAINING WALL (STONE) | Material | Square Feet |  | 8
3458-423-6022 | RETAINING WALL (SOIL NAIL)(FACIA) | Material | Square Feet |  | 8
3458-425-6037 | PRESTR CONC GIRDER (TX40) | Material | Linear Feet |  | 8
3458-425-6039 | PRESTR CONC GIRDER (TX54) | Material | Linear Feet |  | 8
3458-432-6001 | RIPRAP (CONC)(4 IN) | Material | Cubic Yard |  | 8
3458-432-6002 | RIPRAP (CONC)(5 IN) | Material | Cubic Yard |  | 8
3458-432-6033 | RIPRAP (STONE PROTECTION)(18 IN) | Material | Cubic Yard |  | 8
3458-432-6035 | RIPRAP (STONE PROTECTION)(24 IN) | Material | Cubic Yard |  | 8
3458-432-6045 | RIPRAP (MOW STRIP)(4 IN) | Material | Cubic Yard |  | 8
3458-438-6005 | CLEANING AND SEALING JOINTS | Material | Linear Feet |  | 8
3458-438-6009 | CLEANING EXISTING JOINTS | Material | Linear Feet |  | 8
3458-442-6007 | STR STEEL (MISC NON - BRIDGE) | Material | LB |  | 8
3458-450-6023 | RAIL (TY SSTR) | Material | Linear Feet |  | 8
3458-450-6066 | RAIL (TY C411)(MOD) | Material | Linear Feet |  | 8
3458-450-6113 | RAIL (TY PR11)(MOD) | Material | Linear Feet |  | 8
3458-450-9001 | RAIL (TY C402)(MOD) | Material | Linear Feet |  | 8
3458-450-9002 | RAIL (HANDRAIL)(TY F)(MOD) | Material | Linear Feet |  | 8
3458-450-9003 | RAIL (TY C221)(MOD) | Material | Linear Feet |  | 8
3458-450-9004 | RAIL (HANDRAIL)(TY B)(MOD) | Material | Linear Feet |  | 8
3458-454-6004 | ARMOR JOINT (SEALED) | Material | Linear Feet |  | 8
3458-454-6018 | SEALED EXPANSION JOINT (4 IN) (SEJ - M) | Material | Linear Feet |  | 8
3458-460-6002 | CMP (GAL STL 18 IN) | Material | Linear Feet |  | 8
3458-462-6001 | CONC BOX CULV (3 FT X 2 FT) | Material | Linear Feet |  | 8
3458-462-6002 | CONC BOX CULV (3 FT X 3 FT) | Material | Linear Feet |  | 8
3458-462-6003 | CONC BOX CULV (4 FT X 2 FT) | Material | Linear Feet |  | 8
3458-462-6004 | CONC BOX CULV (4 FT X 3 FT) | Material | Linear Feet |  | 8
3458-462-6005 | CONC BOX CULV (4 FT X 4 FT) | Material | Linear Feet |  | 8
3458-462-6007 | CONC BOX CULV (5 FT X 3 FT) | Material | Linear Feet |  | 8
3458-462-6008 | CONC BOX CULV (5 FT X 4 FT) | Material | Linear Feet |  | 8
3458-462-6010 | CONC BOX CULV (6 FT X 3 FT) | Material | Linear Feet |  | 8
3458-462-6011 | CONC BOX CULV (6 FT X 4 FT) | Material | Linear Feet |  | 8
3458-462-6014 | CONC BOX CULV (7 FT X 3 FT) | Material | Linear Feet |  | 8
3458-462-6015 | CONC BOX CULV (7 FT X 4 FT) | Material | Linear Feet |  | 8
3458-462-6019 | CONC BOX CULV (8 FT X 4 FT) | Material | Linear Feet |  | 8
3458-462-6029 | CONC BOX CULV (10 FT X 5 FT) | Material | Linear Feet |  | 8
3458-462-6052 | CONC BOX CULV (5 FT X 4 FT)(EXTEND) | Material | Linear Feet |  | 8
3458-462-6073 | CONC BOX CULV (10 FT X 5 FT)(EXTEND) | Material | Linear Feet |  | 8
3458-464-6001 | RC PIPE (CL III)(12 IN) | Material | Linear Feet |  | 8
3458-464-6003 | RC PIPE (CL III)(18 IN) | Material | Linear Feet |  | 8
3458-464-6005 | RC PIPE (CL III)(24 IN) | Material | Linear Feet |  | 8
3458-464-6007 | RC PIPE (CL III)(30 IN) | Material | Linear Feet |  | 8
3458-464-6008 | RC PIPE (CL III)(36 IN) | Material | Linear Feet |  | 8
3458-464-6009 | RC PIPE (CL III)(42 IN) | Material | Linear Feet |  | 8
3458-464-6010 | RC PIPE (CL III)(48 IN) | Material | Linear Feet |  | 8
3458-464-6011 | RC PIPE (CL III)(54 IN) | Material | Linear Feet |  | 8
3458-464-6017 | RC PIPE (CL IV)(18 IN) | Material | Linear Feet |  | 8
3458-464-6018 | RC PIPE (CL IV)(24 IN) | Material | Linear Feet |  | 8
3458-464-6019 | RC PIPE (CL IV)(30 IN) | Material | Linear Feet |  | 8
3458-464-6051 | RC PIPE (CL IV)(54 IN) | Material | Linear Feet |  | 8
3458-465-6002 | MANH (COMPL)(PRM)(48 IN) | Material | Each |  | 8
3458-465-6003 | MANH (COMPL)(PRM)(60 IN) | Material | Each |  | 8
3458-465-6004 | MANH (COMPL)(PRM)(72 IN) | Material | Each |  | 8
3458-465-6005 | JCTBOX (COMPL)(PJB)(3FTX3FT) | Material | Each |  | 8
3458-465-6006 | JCTBOX (COMPL)(PJB)(4FTX4FT) | Material | Each |  | 8
3458-465-6010 | JCTBOX (COMPL)(PJB)(5FTX6FT) | Material | Each |  | 8
3458-465-6014 | INLET (COMPL)(PCO)(3FT)(LEFT) | Material | Each |  | 8
3458-465-6015 | INLET (COMPL)(PCO)(3FT)(RIGHT) | Material | Each |  | 8
3458-465-6016 | INLET (COMPL)(PCO)(3FT)(BOTH) | Material | Each |  | 8
3458-465-6018 | INLET (COMPL)(PCO)(4FT)(LEFT) | Material | Each |  | 8
3458-465-6019 | INLET (COMPL)(PCO)(4FT)(RIGHT) | Material | Each |  | 8
3458-465-6030 | INLET (COMPL)(PCU)(3FT)(LEFT) | Material | Each |  | 8
3458-465-6031 | INLET (COMPL)(PCU)(3FT)(RIGHT) | Material | Each |  | 8
3458-465-6032 | INLET (COMPL)(PCU)(3FT)(BOTH) | Material | Each |  | 8
3458-465-6034 | INLET (COMPL)(PCU)(4FT)(LEFT) | Material | Each |  | 8
3458-465-6048 | INLET (COMPL)(POD)(FG)(3FTX3FT) | Material | Each |  | 8
3458-465-6049 | INLET (COMPL)(POD)(FG)(4FTX4FT) | Material | Each |  | 8
3458-465-6051 | INLET (COMPL)(POD)(SFG)(3FTX3FT) | Material | Each |  | 8
3458-465-6052 | INLET (COMPL)(POD)(SFG)(4FTX4FT) | Material | Each |  | 8
3458-465-6071 | INLET (COMPL)(PSL)(RC)(4FTX4FT) | Material | Each |  | 8
3458-465-6074 | INLET (COMPL)(PSL)(RC)(5FTX5FT) | Material | Each |  | 8
3458-465-6075 | INLET (COMPL)(PSL)(RC)(5FTX6FT) | Material | Each |  | 8
3458-465-6076 | INLET (COMPL)(PSL)(RC)(6FTX6FT) | Material | Each |  | 8
3458-465-6126 | INLET (COMPL)(PSL)(FG)(3FTX3FT-3FTX3FT) | Material | Each |  | 8
3458-465-6128 | INLET (COMPL)(PSL)(FG)(4FTX4FT-4FTX4FT) | Material | Each |  | 8
3458-465-6132 | INLET (COMPL)(PSL)(FG)(4FTX5FT-4FTX4FT) | Material | Each |  | 8
3458-465-6138 | INLET (COMPL)(PSL)(FG)(5FTX6FT-4FTX4FT) | Material | Each |  | 8
3458-465-6146 | INLET (COMPL)(PSL)(SFG)(3FTX3FT-3FTX3FT) | Material | Each |  | 8
3458-465-6147 | INLET (COMPL)(PSL)(SFG)(4FTX4FT-4FTX4FT) | Material | Each |  | 8
3458-465-6178 | INLET (COMPL)(TY MSE1) | Material | Each |  | 8
3458-465-6179 | INLET (COMPL)(TY MSE2) | Material | Each |  | 8
3458-465-9001 | WQ RISER STRUCTURE | Material | Each |  | 8
3458-465-9002 | INLET (COMPL)(GRATE) NEENAH R-3924 | Material | Each |  | 8
3458-466-6095 | HEADWALL (CH - PW - 0) (DIA= 18 IN) | Material | Each |  | 8
3458-466-6099 | HEADWALL (CH - PW - 0) (DIA= 30 IN) | Material | Each |  | 8
3458-466-6171 | WINGWALL (PW - 1) (HW=10 FT) | Material | Each |  | 8
3458-466-6172 | WINGWALL (PW - 1) (HW=11 FT) | Material | Each |  | 8
3458-466-6180 | WINGWALL (PW - 1) (HW=5 FT) | Material | Each |  | 8
3458-466-6182 | WINGWALL (PW - 1) (HW=7 FT) | Material | Each |  | 8
3458-466-6184 | WINGWALL (PW - 1) (HW=9 FT) | Material | Each |  | 8
3458-467-6001 | SET (PIPE RUNNER ASSEMBLY) | Material | Each |  | 8
3458-467-6109 | SET (TY I) (S= 3 FT) (HW= 3 FT) (6:1) (C) | Material | Each |  | 8
3458-467-6139 | SET (TY I) (S= 4 FT) (HW= 3 FT) (4:1) (C) | Material | Each |  | 8
3458-467-6141 | SET (TY I) (S= 4 FT) (HW= 3 FT) (6:1) (C) | Material | Each |  | 8
3458-467-6143 | SET (TY I) (S= 4 FT) (HW= 4 FT) (3:1) (C) | Material | Each |  | 8
3458-467-6144 | SET (TY I) (S= 4 FT) (HW= 4 FT) (4:1) (C) | Material | Each |  | 8
3458-467-6158 | SET (TY I) (S= 4 FT) (HW= 7 FT) (4:1) (C) | Material | Each |  | 8
3458-467-6179 | SET (TY I) (S= 5 FT) (HW= 4 FT) (6:1) (C) | Material | Each |  | 8
3458-467-6212 | SET (TY I) (S= 6 FT) (HW= 4 FT) (4:1) (C) | Material | Each |  | 8
3458-467-6214 | SET (TY I) (S= 6 FT) (HW= 4 FT) (6:1) (C) | Material | Each |  | 8
3458-467-6247 | SET (TY I) (S= 7 FT) (HW= 4 FT) (6:1) (P) | Material | Each |  | 8
3458-467-6248 | SET (TY I) (S= 7 FT) (HW= 5 FT) (3:1) (C) | Material | Each |  | 8
3458-467-6323 | SET (TY II) (12 IN) (RCP) (4: 1) (C) | Material | Each |  | 8
3458-467-6354 | SET (TY II) (18 IN) (RCP) (2: 1) (C) | Material | Each |  | 8
3458-467-6358 | SET (TY II) (18 IN) (RCP) (4: 1) (C) | Material | Each |  | 8
3458-467-6363 | SET (TY II) (18 IN) (RCP) (6: 1) (P) | Material | Each |  | 8
3458-467-6390 | SET (TY II) (24 IN) (RCP) (4: 1) (C) | Material | Each |  | 8
3458-467-6395 | SET (TY II) (24 IN) (RCP) (6: 1) (P) | Material | Each |  | 8
3458-467-6423 | SET (TY II) (30 IN) (RCP) (6: 1) (P) | Material | Each |  | 8
3458-467-6451 | SET (TY II) (36 IN) (RCP) (4: 1) (P) | Material | Each |  | 8
3458-467-6454 | SET (TY II) (36 IN) (RCP) (6: 1) (P) | Material | Each |  | 8
3458-467-6475 | SET (TY II) (48 IN) (RCP) (3: 1) (P) | Material | Each |  | 8
3458-467-6477 | SET (TY II) (48 IN) (RCP) (4: 1) (C) | Material | Each |  | 8
3458-471-6007 | GRATE AND FRAME (BRIDGE DRAIN) | Material | Each |  | 8
3458-476-6008 | JACK BOR OR TUN PIPE (18 IN)(RC)(CL V) | Material | Linear Feet |  | 8
3458-476-6021 | JACK BOR OR TUN PIPE (30 IN)(RC)(CL V) | Material | Linear Feet |  | 8
3458-476-6036 | JACK BOR OR TUN PIPE (48 IN)(RC)(CL V) | Material | Linear Feet |  | 8
3458-476-6041 | JACK BOR OR TUN PIPE (54 IN)(RC)(CL V) | Material | Linear Feet |  | 8
3458-479-6004 | ADJUSTING MANHOLES (SANITARY) | Material | Each |  | 8
3458-479-6005 | ADJUSTING MANHOLES (WATER VALVE BOX) | Material | Each |  | 8
3458-479-6006 | ADJUSTING INLET (CAP) | Material | Each |  | 8
3458-481-6013 | PIPE (PVC) (SCH 40) (6 IN) | Material | Linear Feet |  | 8
3458-481-6014 | PIPE (PVC) (SCH 40) (8 IN) | Material | Linear Feet |  | 8
3458-481-6015 | PIPE (PVC) (SCH 40) (10 IN) | Material | Linear Feet |  | 8
3458-481-6023 | PIPE (PVC) (SCH 80) (6 IN) | Material | Linear Feet |  | 8
3458-496-6002 | REMOV STR (INLET) | Material | Each |  | 8
3458-496-6004 | REMOV STR (SET) | Material | Each |  | 8
3458-496-6005 | REMOV STR (WINGWALL) | Material | Each |  | 8
3458-496-6007 | REMOV STR (PIPE) | Material | Linear Feet |  | 8
3458-496-6008 | REMOV STR (BOX CULVERT) | Material | Linear Feet |  | 8
3458-496-6072 | REMOVING ROCK RIPRAP | Material | Linear Feet |  | 8
3458-500-6001 | MOBILIZATION | Material | Lump Sum |  | 8
3458-502-6001 | BARRICADES, SIGNS & TRAFFIC HANDLING | Material | Month |  | 8
3458-506-6001 | ROCK FILTER DAMS (INSTALL) (TY 1) | Material | Linear Feet |  | 8
3458-506-6002 | ROCK FILTER DAMS (INSTALL) (TY 2) | Material | Linear Feet |  | 8
3458-506-6003 | ROCK FILTER DAMS (INSTALL) (TY 3) | Material | Linear Feet |  | 8
3458-506-6005 | ROCK FILTER DAMS (INSTALL) (TY 5) | Material | Linear Feet |  | 8
3458-506-6011 | ROCK FILTER DAMS (REMOVE) | Material | Linear Feet |  | 8
3458-506-6020 | CONSTRUCTION EXITS (INSTALL) (TY 1) | Material | Square Yard |  | 8
3458-506-6024 | CONSTRUCTION EXITS (REMOVE) | Material | Square Yard |  | 8
3458-506-6032 | BLADING WORK (EROSION & SEDMT CONT) | Material | Hour |  | 8
3458-506-6035 | SANDBAGS FOR EROSION CONTROL | Material | Each |  | 8
3458-506-6038 | TEMP SEDMT CONT FENCE (INSTALL) | Material | Linear Feet |  | 8
3458-506-6039 | TEMP SEDMT CONT FENCE (REMOVE) | Material | Linear Feet |  | 8
3458-506-6040 | BIODEG EROSN CONT LOGS (INSTL) (8") | Material | Linear Feet |  | 8
3458-506-6042 | BIODEG EROSN CONT LOGS (INSTL) (18") | Material | Linear Feet |  | 8
3458-506-6043 | BIODEG EROSN CONT LOGS REMOVE) | Material | Linear Feet |  | 8
3458-508-6001 | CONSTRUCTING DETOURS | Material | Square Yard |  | 8
3458-512-6005 | PORT CTB (FUR & INST)(F-SHAPE)(TY 1) | Material | Linear Feet |  | 8
3458-512-6009 | PORT CTB (FUR & INST)(LOW PROF)(TY 1) | Material | Linear Feet |  | 8
3458-512-6010 | PORT CTB (FUR & INST)(LOW PROF)(TY 2) | Material | Linear Feet |  | 8
3458-512-6029 | PORT CTB (MOVE)(F-SHAPE)(TY 1) | Material | Linear Feet |  | 8
3458-512-6033 | PORT CTB (MOVE)(LOW PROF)(TY 1) | Material | Linear Feet |  | 8
3458-512-6034 | PORT CTB (MOVE)(LOW PROF)(TY 2) | Material | Linear Feet |  | 8
3458-512-6053 | PORT CTB (REMOVE)(F-SHAPE)(TY 1) | Material | Linear Feet |  | 8
3458-512-6057 | PORT CTB (REMOVE)(LOW PROF)(TY 1) | Material | Linear Feet |  | 8
3458-512-6058 | PORT CTB (REMOVE)(LOW PROF)(TY 2) | Material | Linear Feet |  | 8
3458-528-6001 | COLORED TEXTURED CONCRETE (4") | Material | Square Yard |  | 8
3458-529-6004 | CONC CURB (MONO) (TY I) | Material | Linear Feet |  | 8
3458-529-6007 | CONC CURB & GUTTER (TY I) | Material | Linear Feet |  | 8
3458-529-6008 | CONC CURB & GUTTER (TY II) | Material | Linear Feet |  | 8
3458-530-6004 | DRIVEWAYS (CONC) | Material | Square Yard |  | 8
3458-530-6005 | DRIVEWAYS (ACP) | Material | Square Yard |  | 8
3458-530-6013 | DRIVEWAYS AND TURNOUTS (CONC) | Material | Square Yard |  | 8
3458-531-6002 | CONC SIDEWALKS (5") | Material | Square Yard |  | 8
3458-531-6004 | CURB RAMPS (TY 1) | Material | Each |  | 8
3458-531-6008 | CURB RAMPS (TY 5) | Material | Each |  | 8
3458-531-6037 | CURB RAMPS (TY 1)(MOD) | Material | Each |  | 8
3458-531-6054 | CURB RAMPS (TY 21) (MOD) | Material | Each |  | 8
3458-540-6001 | MTL W-BEAM GD FEN (TIM POST) | Material | Linear Feet |  | 8
3458-540-6006 | MTL BEAM GD FEN TRANS (THRIE-BEAM) | Material | Each |  | 8
3458-540-6016 | DOWNSTREAM ANCHOR TERMINAL SECTION | Material | Each |  | 8
3458-540-6033 | MTL BM GD FEN (LONG SPAN SYSTEM) | Material | Each |  | 8
3458-542-6001 | REMOVING METAL BEAM GUARD FENCE | Material | Linear Feet |  | 8
3458-542-6002 | REMOVE TERMINAL ANCHOR SECTION | Material | Each |  | 8
3458-542-6003 | REMOVE DOWNSTREAM ANCHOR TERMINAL | Material | Each |  | 8
3458-544-6001 | GUARDRAIL END TREATMENT (INSTALL) | Material | Each |  | 8
3458-544-6003 | GUARDRAIL END TREATMENT (REMOVE) | Material | Each |  | 8
3458-545-6003 | CRASH CUSH ATTEN (MOVE & RESET) | Material | Each |  | 8
3458-545-6005 | CRASH CUSH ATTEN (REMOVE) | Material | Each |  | 8
3458-545-6007 | CRASH CUSH ATTEN (INSTL)(L)(N)(TL3) | Material | Each |  | 8
3458-545-6010 | CRASH CUSH ATTEN (INSTL)(L)(W)(TL3) | Material | Each |  | 8
3458-545-6019 | CRASH CUSH ATTEN (INSTL)(S)(N)(TL3) | Material | Each |  | 8
3458-550-6003 | CHAIN LINK FENCE (REMOVE) | Material | Linear Feet |  | 8
3458-550-6006 | GATE (REMOVE) | Material | Each |  | 8
3458-550-9001 | CHAIN LINK FENCE (INSTALL)(PVC COATED)(6') | Material | Linear Feet |  | 8
3458-550-9002 | CHAIN LINK FENCE GATE (INSTALL)(PVC COATED)(6’ X 5’) | Material | Each |  | 8
3458-550-9003 | CHAIN LINK FENCE GATE (INSTALL)(PVC COATED)(6’ X 12’) | Material | Each |  | 8
3458-550-9004 | CHAIN LINK FENCE (W/T-POSTS)(5 FT) | Material | Linear Feet |  | 8
3458-550-9005 | CHAIN LINK FENCE GATE (INSTALL)(PVC COATED)(6’ X 8’) | Material | Each |  | 8
3458-556-6006 | PIPE UNDERDRAINS (TY 6)(6") | Material | Linear Feet |  | 8
3458-560-6001 | MAILBOX INSTALL-S (TWG-POST) TY 1 | Material | Each |  | 8
3458-560-6003 | MAILBOX INSTALL-M (TWG-POST) TY 1 | Material | Each |  | 8
3458-610-6009 | REMOVE RD IL ASM (TRANS-BASE) | Material | Each |  | 8
3458-610-6104 | IN RD IL (U/P) (TY 1) (150W EQ) LED | Material | Each |  | 8
3458-610-9001 | IN RD IL (TY DA) 40B-8 (250W EQ) LED | Material | Each |  | 8
3458-610-9002 | IN RD IL (TY DA) 40T-8 (250W EQ) LED | Material | Each |  | 8
3458-610-9003 | IN RD IL (TY DA) 16S-4 (150W EQ) LED | Material | Each |  | 8
3458-618-6023 | CONDT (PVC) (SCH 40) (2") | Material | Linear Feet |  | 8
3458-618-6024 | CONDT (PVC) (SCH 40) (2") (BORE) | Material | Linear Feet |  | 8
3458-618-6029 | CONDT (PVC) (SCH 40) (3") | Material | Linear Feet |  | 8
3458-618-6031 | CONDT (PVC) (SCH 40) (3") (CONC ENCSE) | Material | Linear Feet |  | 8
3458-618-6033 | CONDT (PVC) (SCH 40) (4") | Material | Linear Feet |  | 8
3458-618-6042 | CONDT (PVC) (SCH 80) (1 1/4") | Material | Linear Feet |  | 8
3458-618-6047 | CONDT (PVC) (SCH 80) (2") (BORE) | Material | Linear Feet |  | 8
3458-618-6053 | CONDT (PVC) (SCH 80) (3") | Material | Linear Feet |  | 8
3458-618-6054 | CONDT (PVC) (SCH 80) (3") (BORE) | Material | Linear Feet |  | 8
3458-618-6059 | CONDT (PVC) (SCH 80) (4") (BORE) | Material | Linear Feet |  | 8
3458-618-6062 | CONDT (RM) (3/4") | Material | Linear Feet |  | 8
3458-618-6066 | CONDT (RM) (1 1/4") | Material | Linear Feet |  | 8
3458-618-6074 | CONDT (RM) (3") | Material | Linear Feet |  | 8
3458-620-6003 | ELEC CONDR (NO.12) BARE | Material | Linear Feet |  | 8
3458-620-6004 | ELEC CONDR (NO.12) INSULATED | Material | Linear Feet |  | 8
3458-620-6007 | ELEC CONDR (NO.8) BARE | Material | Linear Feet |  | 8
3458-620-6008 | ELEC CONDR (NO.8) INSULATED | Material | Linear Feet |  | 8
3458-620-6009 | ELEC CONDR (NO.6) BARE | Material | Linear Feet |  | 8
3458-620-6010 | ELEC CONDR (NO.6) INSULATED | Material | Linear Feet |  | 8
3458-620-6011 | ELEC CONDR (NO.4) BARE | Material | Linear Feet |  | 8
3458-620-6012 | ELEC CONDR (NO.4) INSULATED | Material | Linear Feet |  | 8
3458-620-6015 | ELEC CONDR (NO.2) BARE | Material | Linear Feet |  | 8
3458-620-6016 | ELEC CONDR (NO.2) INSULATED | Material | Linear Feet |  | 8
3458-624-6001 | GROUND BOX TY A (122311) | Material | Each |  | 8
3458-624-6002 | GROUND BOX TY A (122311) W/APRON | Material | Each |  | 8
3458-624-6009 | GROUND BOX TY D (162922) | Material | Each |  | 8
3458-624-6010 | GROUND BOX TY D (162922) W/APRON | Material | Each |  | 8
3458-624-6028 | REMOVE GROUND BOX | Material | Each |  | 8
3458-628-6002 | REMOVE ELECTRICAL SERVICES | Material | Each |  | 8
3458-628-6045 | ELC SRV TY A 240/480 060 (NS) SS (E) SP (O) | Material | Each |  | 8
3458-628-6152 | ELC SRV TY D 120/240 060 (NS) SS (N) SP (O) | Material | Each |  | 8
3458-628-6165 | ELC SRV TY D 120/240 070 (NS) AL (E) SP (O) | Material | Each |  | 8
3458-628-9001 | ELC SRV TY D 120/240 060 (NS) SS (N) EX (O) | Material | Each |  | 8
3458-628-9002 | ELC SRV TY D 120/240 200 (NS) SS (N) SP (O) | Material | Each |  | 8
3458-636-6001 | ALUMINUM SIGNS (TY A) | Material | Square Feet |  | 8
3458-636-6002 | ALUMINUM SIGNS (TY G) | Material | Square Feet |  | 8
3458-636-6003 | ALUMINUM SIGNS (TY O) | Material | Square Feet |  | 8
3458-644-6001 | IN SM RD SN SUP&AM TY10BWG (1) SA (P) | Material | Each |  | 8
3458-644-6002 | IN SM RD SN SUP&AM TY10BWG (1) SA (P-BM) | Material | Each |  | 8
3458-644-6004 | IN SM RD SN SUP&AM TY10BWG (1) SA (T) | Material | Each |  | 8
3458-644-6005 | IN SM RD SN SUP&AM TY10BWG (1) SA (T-2EXT) | Material | Each |  | 8
3458-644-6007 | IN SM RD SN SUP&AM TY10BWG (1) SA (U) | Material | Each |  | 8
3458-644-6027 | IN SM RD SN SUP&AM TYS80 (1) SA (P) | Material | Each |  | 8
3458-644-6028 | IN SM RD SN SUP&AM TYS80 (1) SA (P-BM) | Material | Each |  | 8
3458-644-6030 | IN SM RD SN SUP&AM TYS80 (1) SA (T) | Material | Each |  | 8
3458-644-6031 | IN SM RD SN SUP&AM TYS80 (1) SA (T-2EXT) | Material | Each |  | 8
3458-644-6033 | IN SM RD SN SUP&AM TYS80 (1) SA (U) | Material | Each |  | 8
3458-644-6034 | IN SM RD SN SUP&AM TYS80 (1) SA (U-1EXT) | Material | Each |  | 8
3458-644-6036 | IN SM RD SN SUP&AM TYS80 (1) SA (U-BM) | Material | Each |  | 8
3458-644-6052 | IN SM RD SN SUP&AM TYS80 (2) SA (T-2EXT) | Material | Each |  | 8
3458-644-6064 | IN BRIDGE MNT CLEARANCE SGN ASSM (TY N) | Material | Each |  | 8
3458-644-6065 | IN BRIDGE MNT CLEARANCE SGN ASSM (TY S) | Material | Each |  | 8
3458-644-6066 | IN SM RD SN SUP&AM (RAIL MOUNT) | Material | Each |  | 8
3458-644-6076 | REMOVE SM RD SN SUP&AM | Material | Each |  | 8
3458-644-6092 | IN SM RD SN SUP & AM TYTWT (1) WA (P) (3FT) | Material | Each |  | 8
3458-644-9001 | IN SM RD SN SUP&AM (BARRIER MOUNT) | Material | Each |  | 8
3458-647-6001 | INSTALL LRSS (STRUCT STEEL) | Material | LB |  | 8
3458-647-6003 | REMOVE LRSA | Material | Each |  | 8
3458-650-6024 | INS OH SN SUP(25 FT BAL TEE)(SPAN ONLY) | Material | Each |  | 8
3458-650-6034 | INS OH SN SUP(30 FT CANT)(SPAN ONLY) | Material | Each |  | 8
3458-650-6041 | INS OH SN SUP (35 FT CANT)(SPAN ONLY) | Material | Each |  | 8
3458-650-6048 | INS OH SN SUP(40 FT CANT)(SPAN ONLY) | Material | Each |  | 8
3458-650-6091 | INS OH SN SUP (80 FT BRDG)(SPAN ONLY) | Material | Each |  | 8
3458-650-6096 | INS OH SN SUP (85 FT BRDG)(SPAN ONLY) | Material | Each |  | 8
3458-650-6106 | INS OH SN SUP (95 FT BRDG)(SPAN ONLY) | Material | Each |  | 8
3458-650-6204 | REMOVE OVERHD SIGN SUP | Material | Each |  | 8
3458-658-6001 | INSTL DEL ASSM (D-SW) SZ 1 (FLX) GND | Material | Each |  | 8
3458-658-6013 | INSTL DEL ASSM (D-SW) SZ (BRF) CTB | Material | Each |  | 8
3458-658-6014 | INSTL DEL ASSM (D-SW) SZ (BRF) CTB (BI) | Material | Each |  | 8
3458-658-6018 | INSTL DEL ASSM (D-SY) SZ 1 (FLX) GND | Material | Each |  | 8
3458-658-6026 | INSTL DEL ASSM (D-SY) SZ (BRF) CTB | Material | Each |  | 8
3458-658-6036 | INSTL DEL ASSM (D-DW) SZ 1 (FLX) GND | Material | Each |  | 8
3458-658-6041 | INSTL DEL ASSM (D-DY) SZ 1 (FLX) GND | Material | Each |  | 8
3458-658-6048 | INSTL OM ASSM (OM-2Z) (FLX) GND | Material | Each |  | 8
3458-658-6061 | INSTL DEL ASSM (D-SW) SZ 1 (BRF) GF2 | Material | Each |  | 8
3458-658-6064 | INSTL DEL ASSM (D-SY) SZ 1 (BRF) GF2 | Material | Each |  | 8
3458-662-6001 | WK ZN PAV MRK NON-REMOV (W) 4" (BRK) | Material | Linear Feet |  | 8
3458-662-6004 | WK ZN PAV MRK NON-REMOV (W) 4" (SLD) | Material | Linear Feet |  | 8
3458-662-6010 | WK ZN PAV MRK NON-REMOV (W) 8" (DOT) | Material | Linear Feet |  | 8
3458-662-6012 | WK ZN PAV MRK NON-REMOV (W) 8" (SLD) | Material | Linear Feet |  | 8
3458-662-6016 | WK ZN PAV MRK NON-REMOV (W) 24" (SLD) | Material | Linear Feet |  | 8
3458-662-6017 | WK ZN PAV MRK NON-REMOV (W)(ARROW) | Material | Each |  | 8
3458-662-6026 | WK ZN PAV MRK NON-REMOV (W)(UTURN ARW) | Material | Each |  | 8
3458-662-6029 | WK ZN PAV MRK NON-REMOV(W)(WORD) | Material | Each |  | 8
3458-662-6031 | WK ZN PAV MRK NON-REMOV (W) 36" (YLD TRI) | Material | Each |  | 8
3458-662-6032 | WK ZN PAV MRK NON-REMOV (Y) 4" (BRK) | Material | Linear Feet |  | 8
3458-662-6034 | WK ZN PAV MRK NON-REMOV (Y) 4" (SLD) | Material | Linear Feet |  | 8
3458-662-6060 | WK ZN PAV MRK REMOV (W) 4" (BRK) | Material | Linear Feet |  | 8
3458-662-6061 | WK ZN PAV MRK REMOV (W) 4" (DOT) | Material | Linear Feet |  | 8
3458-662-6063 | WK ZN PAV MRK REMOV (W) 4" (SLD) | Material | Linear Feet |  | 8
3458-662-6071 | WK ZN PAV MRK REMOV (W) 8" (SLD) | Material | Linear Feet |  | 8
3458-662-6075 | WK ZN PAV MRK REMOV (W) 24" (SLD) | Material | Linear Feet |  | 8
3458-662-6092 | WK ZN PAV MRK REMOV (W) 36" (YLD TRI) | Material | Each |  | 8
3458-662-6093 | WK ZN PAV MRK REMOV (Y) 4" (BRK) | Material | Linear Feet |  | 8
3458-662-6095 | WK ZN PAV MRK REMOV (Y) 4" (SLD) | Material | Linear Feet |  | 8
3458-666-6005 | REFL PAV MRK TY I (W) 4" (DOT)(090MIL) | Material | Linear Feet |  | 8
3458-666-6029 | REFL PAV MRK TY I (W) 8" (DOT)(090MIL) | Material | Linear Feet |  | 8
3458-666-6035 | REFL PAV MRK TY I (W) 8" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6038 | REFL PAV MRK TY I (W) 12" (LNDP)(090MIL) | Material | Linear Feet |  | 8
3458-666-6041 | REFL PAV MRK TY I (W) 12" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6047 | REFL PAV MRK TY I (W) 24" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6053 | REFL PAV MRK TY I (W)(ARROW)(090MIL) | Material | Each |  | 8
3458-666-6056 | REFL PAV MRK TY I (W)(DBL ARROW)(090MIL) | Material | Each |  | 8
3458-666-6062 | REFL PAV MRK TY I (W)(UTURN ARW)(090MIL) | Material | Each |  | 8
3458-666-6071 | REFL PAV MRK TY I (W)(LNDP ARW)(090MIL) | Material | Each |  | 8
3458-666-6077 | REFL PAV MRK TY I (W)(WORD)(090MIL) | Material | Each |  | 8
3458-666-6098 | REFL PAV MRK TY I (W) 18" (YLD TRI)(090MIL) | Material | Each |  | 8
3458-666-6140 | REFL PAV MRK TY I (Y) 12" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6167 | REFL PAV MRK TY II (W) 4" (BRK) | Material | Linear Feet |  | 8
3458-666-6168 | REFL PAV MRK TY II (W) 4" (DOT) | Material | Linear Feet |  | 8
3458-666-6170 | REFL PAV MRK TY II (W) 4" (SLD) | Material | Linear Feet |  | 8
3458-666-6171 | REFL PAV MRK TY II (W) 6" (BRK) | Material | Linear Feet |  | 8
3458-666-6174 | REFL PAV MRK TY II (W) 6" (SLD) | Material | Linear Feet |  | 8
3458-666-6176 | REFL PAV MRK TY II (W) 8" (DOT) | Material | Linear Feet |  | 8
3458-666-6178 | REFL PAV MRK TY II (W) 8" (SLD) | Material | Linear Feet |  | 8
3458-666-6179 | REFL PAV MRK TY II (W) 12" (LNDP) | Material | Linear Feet |  | 8
3458-666-6180 | REFL PAV MRK TY II (W) 12" (SLD) | Material | Linear Feet |  | 8
3458-666-6182 | REFL PAV MRK TY II (W) 24" (SLD) | Material | Linear Feet |  | 8
3458-666-6184 | REFL PAV MRK TY II (W) (ARROW) | Material | Each |  | 8
3458-666-6185 | REFL PAV MRK TY II (W) (DBL ARROW) | Material | Each |  | 8
3458-666-6187 | REFL PAV MRK TY II (W) (UTURN ARROW) | Material | Each |  | 8
3458-666-6190 | REFL PAV MRK TY II (W) (LNDP ARW) | Material | Each |  | 8
3458-666-6192 | REFL PAV MRK TY II (W) (WORD) | Material | Each |  | 8
3458-666-6198 | REFL PAV MRK TY II (W) 18" (YLD TRI) | Material | Each |  | 8
3458-666-6205 | REFL PAV MRK TY II (Y) 4" (BRK) | Material | Linear Feet |  | 8
3458-666-6207 | REFL PAV MRK TY II (Y) 4" (SLD) | Material | Linear Feet |  | 8
3458-666-6210 | REFL PAV MRK TY II (Y) 6" (SLD) | Material | Linear Feet |  | 8
3458-666-6212 | REFL PAV MRK TY II (Y) 12" (SLD) | Material | Linear Feet |  | 8
3458-666-6285 | REF PROF PAV MRK TY I (W) 6" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6289 | REF PROF PAV MRK TY I (Y) 6" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6299 | RE PM W/RET REQ TY I (W) 4" (BRK)(090MIL) | Material | Linear Feet |  | 8
3458-666-6302 | RE PM W/RET REQ TY I (W) 4" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-666-6311 | RE PM W/RET REQ TY I (Y) 4" (BRK)(090MIL) | Material | Linear Feet |  | 8
3458-666-6314 | RE PM W/RET REQ TY I (Y) 4" (SLD)(090MIL) | Material | Linear Feet |  | 8
3458-668-6010 | PREFAB PAV MRK TY B (W)(6")(BRK)CNTST | Material | Linear Feet |  | 8
3458-672-6006 | REFL PAV MRKR TY I-A | Material | Each |  | 8
3458-672-6007 | REFL PAV MRKR TY I-C | Material | Each |  | 8
3458-672-6008 | REFL PAV MRKR TY I-R | Material | Each |  | 8
3458-672-6009 | REFL PAV MRKR TY II-A-A | Material | Each |  | 8
3458-672-6010 | REFL PAV MRKR TY II-C-R | Material | Each |  | 8
3458-677-6001 | ELIM EXT PAV MRK & MRKS (4") | Material | Linear Feet |  | 8
3458-677-6003 | ELIM EXT PAV MRK & MRKS (8") | Material | Linear Feet |  | 8
3458-677-6007 | ELIM EXT PAV MRK & MRKS (24") | Material | Linear Feet |  | 8
3458-677-6008 | ELIM EXT PAV MRK & MRKS (ARROW) | Material | Each |  | 8
3458-677-6012 | ELIM EXT PAV MRK & MRKS (WORD) | Material | Each |  | 8
3458-677-6036 | ELIM EXT PAV MRK & MRKS (UTURN ARROW) | Material | Each |  | 8
3458-678-6001 | PAV SURF PREP FOR MRK (4") | Material | Linear Feet |  | 8
3458-678-6002 | PAV SURF PREP FOR MRK (6") | Material | Linear Feet |  | 8
3458-678-6004 | PAV SURF PREP FOR MRK (8") | Material | Linear Feet |  | 8
3458-678-6005 | PAV SURF PREP FOR MRK (10") | Material | Linear Feet |  | 8
3458-678-6006 | PAV SURF PREP FOR MRK (12") | Material | Linear Feet |  | 8
3458-678-6008 | PAV SURF PREP FOR MRK (24") | Material | Linear Feet |  | 8
3458-678-6009 | PAV SURF PREP FOR MRK (ARROW) | Material | Each |  | 8
3458-678-6016 | PAV SURF PREP FOR MRK (WORD) | Material | Each |  | 8
3458-680-6002 | INSTALL HWY TRF SIG (ISOLATED) | Material | Each |  | 8
3458-680-6004 | REMOVING TRAFFIC SIGNALS | Material | Each |  | 8
3458-681-6001 | TEMP TRAF SIGNALS | Material | Each |  | 8
3458-682-6001 | VEH SIG SEC (12") LED (GRN) | Material | Each |  | 8
3458-682-6002 | VEH SIG SEC (12") LED (GRN ARW) | Material | Each |  | 8
3458-682-6003 | VEH SIG SEC (12") LED (YEL) | Material | Each |  | 8
3458-682-6004 | VEH SIG SEC (12") LED (YEL ARW) | Material | Each |  | 8
3458-682-6005 | VEH SIG SEC (12") LED (RED) | Material | Each |  | 8
3458-682-6006 | VEH SIG SEC (12") LED (RED ARW) | Material | Each |  | 8
3458-682-6018 | PED SIG SEC (LED)(COUNTDOWN) | Material | Each |  | 8
3458-682-6023 | BACK PLATE (12")(3 SEC) | Material | Each |  | 8
3458-682-6024 | BACK PLATE (12")(4 SEC) | Material | Each |  | 8
3458-682-6025 | BACK PLATE (12")(5 SEC) | Material | Each |  | 8
3458-684-6031 | TRF SIG CBL (TY A)(14 AWG)(5 CONDR) | Material | Linear Feet |  | 8
3458-684-6033 | TRF SIG CBL (TY A)(14 AWG)(7 CONDR) | Material | Linear Feet |  | 8
3458-684-6042 | TRF SIG CBL (TY A)(14 AWG)(16 CONDR) | Material | Linear Feet |  | 8
3458-684-6079 | TRF SIG CBL (TY C)(12 AWG)(2 CONDR) | Material | Linear Feet |  | 8
3458-686-6028 | INS TRF SIG PL AM (S) 1 ARM (24') LUM & ILSN | Material | Each |  | 8
3458-686-6032 | INS TRF SIG PL AM (S) 1 ARM (28') LUM & ILSN | Material | Each |  | 8
3458-686-6036 | INS TRF SIG PL AM (S) 1 ARM (32') LUM & ILSN | Material | Each |  | 8
3458-686-6040 | INS TRF SIG PL AM (S) 1 ARM (36') LUM & ILSN | Material | Each |  | 8
3458-686-6044 | INS TRF SIG PL AM (S) 1 ARM (40') LUM & ILSN | Material | Each |  | 8
3458-686-6060 | INS TRF SIG PL AM (S) 1 ARM (55') LUM & ILSN | Material | Each |  | 8
3458-686-6104 | INS TRF SIG PL AM (S) 2 ARM (32-28') LUM & ILSN | Material | Each |  | 8
3458-686-6212 | INS TRF SIG PL AM (S) 2 ARM (55-32') LUM & ILSN | Material | Each |  | 8
3458-686-6216 | INS TRF SIG PL AM (S) 2 ARM (55-36') LUM & ILSN | Material | Each |  | 8
3458-686-6282 | RELOC TRF SG PL AM(S)SNGL MST ARM POLE | Material | Each |  | 8
3458-687-6001 | PED POLE ASSEMBLY | Material | Each |  | 8
3458-688-6001 | PED DETECT PUSH BUTTON (APS) | Material | Each |  | 8
3458-688-6003 | PED DETECTOR CONTROLLER UNIT | Material | Each |  | 8
3458-730-6106 | STRIP MOWING | Material |  |  | 8
3458-730-6107 | FULL - WIDTH MOWING | Material |  |  | 8
3458-734-6002 | LITTER REMOVAL | Material |  |  | 8
3458-738-6005 | CLEANING / SWEEPING (FRONTAGE ROAD) | Material |  |  | 8
3458-752-6022 | TREE TRIMMING AND BRUSH REMOVAL | Material | Linear Feet |  | 8
3458-1002-6022 | LANDSCAPE AMENITY (INTERPRETIVE SIGN) | Material | Each |  | 8
3458-1002-6023 | LANDSCAPE AMENITY (TRAILHEAD SIGN) | Material | Each |  | 8
3458-1002-6025 | LANDSCAPE AMENITY (TRASH/RECYCLE BIN) | Material | Each |  | 8
3458-1002-6026 | LANDSCAPE AMENITY (BENCH) | Material | Each |  | 8
3458-1002-6029 | LANDSCAPE AMENITY (BOULDER) | Material | Each |  | 8
3458-1002-9001 | LANDSCAPE AMENITY (BICYCLE RACK) | Material | Each |  | 8
3458-1005-6001 | LOOSE AGGR FOR GROUNDCOVER (TYPE 1) | Material | Cubic Yard |  | 8
3458-1005-6002 | LOOSE AGGR FOR GROUNDCOVER (TYPE 2) | Material | Cubic Yard |  | 8
3458-2000-6001 | DECOMPOSED GRANITE | Material | Square Yard |  | 8
3458-3076-6001 | D-GR HMA TY-B PG64-22 | Material | Ton |  | 8
3458-3076-6035 | D-GR HMA TY-D PG64-22 | Material | Ton |  | 8
3458-3076-6048 | D-GR HMA TY-D PG76-22 | Material | Ton |  | 8
3458-3076-6066 | TACK COAT | Material | Gallon |  | 8
3458-3085-6001 | UNDERSEAL COURSE | Material | Gallon |  | 8
3458-6001-6002 | PORTABLE CHANGEABLE MESSAGE SIGN | Material | Each |  | 8
3458-6016-6008 | ITS MULTI-DUCT CND (PVC-40)(CONC ENCSE) | Material | Linear Feet |  | 8
3458-6016-6011 | ITS MULTI-DUCT CND (PVC-80)(BORE) | Material | Linear Feet |  | 8
3458-6016-6013 | ITS MULTI-DUCT CND (RMC) | Material | Linear Feet |  | 8
3458-6016-6015 | FIBER OPTIC CABLE ROAD MARKER | Material | Each |  | 8
3458-6027-6008 | GROUND BOX (PREPARE) | Material | Each |  | 8
3458-6049-6001 | LONG CHANNEL MOUNT CURB SYS (INSTALL) | Material | Linear Feet |  | 8
3458-6058-6001 | BBU SYSTEM (EXTERNAL BATT CABINET) | Material | Each |  | 8
3458-6064-6010 | ITS POLE (30 FT)(90 MPH) | Material | Each |  | 8
3458-6064-6019 | ITS POLE (40 FT)(90 MPH) | Material | Each |  | 8
3458-6185-6002 | TMA (STATIONARY) | Material | Day |  | 8
3458-6185-6003 | TMA (MOBILE OPERATION) | Material | Hour |  | 8
3458-6186-6001 | ITS GND BOX (PCAST) TY 1 (243636) | Material | Each |  | 8
3458-6186-6002 | ITS GND BOX (PCAST) TY 1 (243636)W/APRN | Material | Each |  | 8
3458-6186-6007 | ITS GND BOX (PCAST) TY 2 (366036) | Material | Each |  | 8
3458-6186-6008 | ITS GND BOX (PCAST) TY 2 (366036)W/APRN | Material | Each |  | 8
3458-6186-6025 | REMOVE ITS GROUND BOX | Material | Each |  | 8
3458-6292-6001 | RVDS (PRESENCE DETECTION ONLY) | Material | Each |  | 8
3458-6292-6002 | RVDS (ADVANCE DETECTION ONLY) | Material | Each |  | 8
3458-RMA-1-9001 | TERMINAL ANCHORAGE SYSTEM | Material | Cubic Yard |  | 8
3458-RMA-2-9001 | DETENTION POND CONTROL SYSTEM | Material | Each |  | 8
3458-RMA-3-9001 | PREFAB STEEL TRUSS (110 FT) | Material | Each |  | 8
3458-RMA-3-9002 | PREFAB STEEL TRUSS (115 FT) | Material | Each |  | 8
3458-RMA-3-9003 | PREFAB STEEL TRUSS (115 FT) (SPECIAL) | Material | Each |  | 8
3458-RMA-4-9001 | ILSN (LED)(4S) | Material | Each |  | 8
3458-RMA-4-9002 | ILSN (LED)(6S) | Material | Each |  | 8
3458-RMA-4-9003 | ILSN (LED)(10S) | Material | Each |  | 8
3458-RMA-6-9001 | LIGHTNING PROTECTION SYSTEM | Material | Each |  | 8
3458-RMA-7-9001 | PIPE (8") PVC C900 (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9002 | PIPE (8") DIP CL350 (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9003 | PIPE (12") DIP CL350 (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9004 | PIPE (18") DIP CL250 (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9005 | PIPE (8") PVC C900 RESTRAINED JOINT (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9006 | PIPE (8") DIP CL350 RESTRAINED JOINT (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9007 | PIPE (12") DIP CL350 RESTRAINED JOINT (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9008 | PIPE (18") DIP CL250 RESTRAINED JOINT (ALL DEPTHS) | Material | Linear Feet |  | 8
3458-RMA-7-9009 | PIPE (8") DIP CL350 RESTR JOINT (IN ENCASEMENT) | Material | Linear Feet |  | 8
3458-RMA-7-9010 | PIPE (12") DIP CL350 RESTR JOINT (IN ENCASEMENT) | Material | Linear Feet |  | 8
3458-RMA-7-9011 | PIPE (18") DIP CL250 RESTR JOINT (IN ENCASEMENT) | Material | Linear Feet |  | 8
3458-RMA-7-9012 | BORE OR JACK PIPE (STEEL) 18" | Material | Linear Feet |  | 8
3458-RMA-7-9013 | BORE OR JACK PIPE (STEEL) 24" | Material | Linear Feet |  | 8
3458-RMA-7-9014 | BORE OR JACK PIPE (STEEL) 30" | Material | Linear Feet |  | 8
3458-RMA-7-9015 | VALVE (GATE) (8") | Material | Each |  | 8
3458-RMA-7-9016 | VALVE (GATE) (12") | Material | Each |  | 8
3458-RMA-7-9017 | VALVE (GATE) (18") | Material | Each |  | 8
3458-RMA-7-9018 | DRAIN VALVE | Material | Each |  | 8
3458-RMA-7-9019 | BLOW-OFF VALVE | Material | Each |  | 8
3458-RMA-7-9020 | 3" COMBINATION AIR VALVE | Material | Each |  | 8
3458-RMA-7-9021 | 8" PRESSURE REDUCING VALVE VAULT | Material | Each |  | 8
3458-RMA-7-9022 | WET CONNECTION 8" DIA X 8" DIA | Material | Each |  | 8
3458-RMA-7-9023 | WET CONNECTION 8" DIA X 18" DIA | Material | Each |  | 8
3458-RMA-7-9024 | WET CONNECTION 12" DIA X 12" DIA | Material | Each |  | 8
3458-RMA-7-9025 | WET CONNECTION 18" DIA X 18" DIA | Material | Each |  | 8
3458-RMA-7-9026 | PRESSURE TAP 8" DIA X 18" DIA | Material | Each |  | 8
3458-RMA-7-9027 | PRESSURE TAP 12" DIA X 18" DIA | Material | Each |  | 8
3458-RMA-7-9028 | CUT AND PLUG WATER MAIN (8" DIA) | Material | Each |  | 8
3458-RMA-7-9029 | CUT AND PLUG WATER MAIN (12" DIA) | Material | Each |  | 8
3458-RMA-7-9030 | CUT AND PLUG WATER MAIN (18" DIA) | Material | Each |  | 8
3458-RMA-7-9031 | DUCTILE IRON FITTINGS | Material | Ton |  | 8
3458-RMA-8-9001 | CONCRETE MASONRY UNIT | Material | Square Feet |  | 8
3458-CONT | CONTINGENCY ALLOWANCE | Material | Lump Sum |  | 8
3458-FA | FORCE ACCOUNT | Material | Lump Sum |  | 8
3458-RIDE | RIDE QUALITY BONUS | Material | Lump Sum |  | 8
3457 | 3457 - CFX-Poinciana Parkway Ph2 | Nonlabor |  |  | 1
9156-SA27 | SA#27 - TRAFFIC ANALYSIS AND DETOUR DESIGN - FANNY BROWN ROAD (-Y16-) | Material | Lump Sum |  | 8
9156-SA-1.1 | SA#1.1 - HOLLAND CHURCH ROAD - EC DESIGN OUT OF SEQUENCE WORK | Material | Lump Sum |  | 8
9156-SA21 | SA#21 - S9.5D SURFACE MIX | Material | Tons |  | 8
9156-SA22 | SA#22 - ADDITIONAL DESIGN AND CONSTRUCTION @ BENSON DRIVE | Material | Lump Sum |  | 8
9156-SA23 | SA#23 - DRIVEWAY ACCESS - LOWE PROPERTY | Material | Lump Sum |  | 8
9156-SA24 | SA#24 - I-40 RAMPS AND LANES | Material | Lump Sum |  | 8
9156-SA25 | SA#25 - BUFFER CLEARING IMPACT CREDIT | Material | Lump Sum |  | 8
9156-SA26 | SA#26 - HOLLAND CHURCH ROAD - OUT OF SEQUENCE CONSTRUCTION | Material | Lump Sum |  | 8
C43- Labor Types | C-43 Labor Types | Nonlabor |  |  | 1
C-43 - Labor Gen | Labor Gen | Labor |  |  | 10
MBO | Michael Oboyle | Labor |  |  | 1
SUB-FLAGGER | Sub - Railway Flagger Crew | Labor |  |  | 1
OWNER-FLAGGER | Owner - Railway Flagger | Labor |  |  | 1
SUB-EW-MASS | Sub - Mass Earthwork Crew | Labor |  |  | 1
3458-132-6005-57 | EMBANKMENT (FINAL)(ORD COMP)(TY C) (57 MSE) | Material | Cubic Yard |  | 8
3418-0331 | 3418-0331 - Town of Blacksburg Wet Utility Relocation - CO | Material | Lump Sum |  | 8
3418-0011 | 3418-0011 - Reimbursement For ROW Premiums - CO | Material | Lump Sum |  | 8
3418-0111 | 3418-0111 - 200 Lb/SY Interm. Type B & PG64-22 Binder - CO | Material | Lump Sum |  | 8
SUB-ST-SLURRY | Sub - Slurry Wall Crew | Labor |  |  | 1
Tunnel-Mech | Tunneling Mechanical Crew | Labor |  |  | 1
SUB-MTBM | Sub - MTBM Tunneling Crew | Labor |  |  | 1
SUB-TUNNEL-CONCRETE | Sub - Tunnel Concrete Crew | Labor |  |  | 1
SUB-TBM | Sub - TBM Tunneling Crew | Labor |  |  | 1
SUB-JET GROUT | Sub - Jet Grout Crew | Labor |  |  | 1
SUB-TUNNEL-MECH | Sub - Tunnel Mechanical Crew | Labor |  |  | 1
SUB-TUNNEL-ELEC | Sub - Tunnel Electrical Crew | Labor |  |  | 1
C43-PRS Earthwotk | C43 - PRS Earthwork Crew | Labor |  |  | 1
9156-SA28 | SA#28 - Addl Supp Temp Seeding | Material | Acre |  | 8
9156-SA30 | SA#30 - Y-18 Holland Church Road | Material | Lump Sum |  | 8
9156-SA32 | SA#32 - Lighting Construction | Material | Lump Sum |  | 8
9156-SA31 | SA#31 - Borrow Area #06 Stockpiling | Material | Cubic Yard |  | 8
UPC112815.CO001 | CO#01 - Merrifield Garden Change Order | Material | Unit |  | 8
UPC112815.CO002 | CO#02 - GOT Property Clean Up | Material | Unit |  | 8
DM-WALL | Demo Wall Crew | Labor |  |  | 1
3404-WO-13 | WO #13 - NS Tub Girder Repair G6 | Material | Lump Sum |  | 8
2300135 | 2300135 - SCM JV - Nice Middleton Bridge | Nonlabor |  |  | 1
2300135-DES | Design Services | Material |  |  | 8
2300135-LGT-NAV-CO1 | Navigation lighting - CO1 | Material |  |  | 8
2300135-MOB | Mobilization | Material |  |  | 8
2300135-LGT-REP | Light Repairs | Material |  |  | 8
2300135-LGT-NAV | Furnish and Install Navigational Lighting | Material |  |  | 8
2300135-PB | Furnish a Payment and Performance Bond | Material |  |  | 8
2300135-TEMP | Project Wide Temporary Electric | Material |  |  | 8
2300135-DEMO | Project Wide Electrical Demolition | Material |  |  | 8
2300135-LGT-F | Lighting Fixtures (Furnish and install) | Material |  |  | 8
2300135-LGT-P | Install Light Pole Foundations | Material |  |  | 8
2300135-SS | Furnish and install Substations | Material |  |  | 8
2300135-ATS | Furnish and install Gensets and Associated Automatic Transfer Switch, ATS | Material |  |  | 8
2300135-LGTN-PT | Furnish and Install Lightning Protection System | Material |  |  | 8
2300135-LGT-CON-B | Furnish and Install Conduits and Conductors on Bridge | Material |  |  | 8
2300135-LGT-CON-MD | Furnish and Install Conduits and Conductors on MD Approach | Material |  |  | 8
2300135-LGT-CON-VA | Furnish and Install Conduits and Conductors on VA Approach | Material |  |  | 8
2300135-ITS-FND | ITS Sign Foundations | Material |  |  | 8
2300135-ITS-MICS | Miscellaneous Sign Foundations | Material |  |  | 8
2300135-ITS-CON-B | Furnish and Install Conduits on Bridge | Material |  |  | 8
2300135-ITS-CON-MD | Furnish and Install Conduits on MD Approach | Material |  |  | 8
2300135-ITS-CON-VA | Furnish and Install Conduits on VA Approach | Material |  |  | 8
2300135-ITS-CCTV | Furnish and install CCTV Cameras | Material |  |  | 8
2300135-ITS | Other ITS Items | Material |  |  | 8
2300135-SGN | Signage | Material |  |  | 8
FACILITY | Facility Set-Up Crews | Labor |  |  | 1
9156-SA33 | SA#33 - Rail Road Flagging Reimbursement | Material | Lump Sum |  | 8
C-43-SUB EW | C43 - Sub Earthwork Crews | Labor |  |  | 1
C-43-SUB-FOUND PREP | C43 - Sub - Foundation Prep Crew | Labor |  |  | 1
C-43-SUB-SPOIL RMV | C43 - Sub - Spoil Mound Removal Crew | Labor |  |  | 1
C43-SUB-MASS | C43 - Sub - Mass Embankment Crew | Labor |  |  | 1
C43-SUB-DEMO | C43 - Sub - Demo Crew | Labor |  |  | 1
4028 | CO#2 - Geotechnical Engineer | Material | Day |  | 1
4027 | CO#2 - Removal of Existing Wing Wall 2 Foundation | Material | Cubic Yard |  | 1
4026 | CO#2 - Subfound Conc | Material | Cubic Yard |  | 1
3433 - SA | 3433 - Supplemental Agreements | Labor |  |  | 1
3434-SA1A | SA1 - VEP #1 - Replace 3" B25.0C with NDI on Loops/Ramps | Material | Lump Sum |  | 8
3434-SA1B | SA1 - VEP #1 - Contractor's Share of Cost Savings | Material | Lump Sum |  | 8
3434-SA2 | SA2 - Add Shoulder Drains under Concrete Loops/Ramps | Material | Lump Sum |  | 8
3434-SA3A | SA3 - Mobilization | Material | Lump Sum |  | 8
3434-SA3B | SA3 - Pipe Cleanout / Spoil Disposal - per Hour | Material | Hour |  | 8
3434-SA3C | SA3 - Single Lane Closure w/ TC Super - per Each | Material | Each |  | 8
3434-SA4A | SA4 - Emergency Response For Non-Functional Guardrail / Guiderail (48HR) | Material | Each |  | 8
3434-SA4B | SA4 - Routine Repair Response For Functional Guardrail / Guiderail (7Day) | Material | Each |  | 8
3434-SA4C | SA4 - Additional Guardrail Post | Material | Each |  | 8
3434-SA4D | SA4 - Cable Guiderail | Material | Linear Feet |  | 8
3434-SA4E | SA4 - Cable Spring Assembly Repair | Material | Each |  | 8
3434-SA4F | SA4 - Cable Anchor Post Repair | Material | Each |  | 8
3434-SA4G | SA4 - Cable Retension (Per Cable) | Material | Each |  | 8
3434-SA4H | SA4 - Steel Beam Guardrail Replacement (Remove, Repair, and Disposal) | Material | Linear Feet |  | 8
3434-SA4I | SA4 - Steel Beam GR- Shop Curved Replacement (Remove, Repair, And Disposal) | Material | Linear Feet |  | 8
3434-SA4J | SA4 - GRAU Type III Replacement | Material | Each |  | 8
3434-SA4K | SA4 - GRAU Type B-77 Replacement | Material | Each |  | 8
3434-SA4L | SA4 - GRAU Type CAT-1 Replacement | Material | Each |  | 8
3434-SA4M | SA4 - GREU Type TL-3 (GRAU-350/GRAU M-350) Replacement | Material | Each |  | 8
3434-SA4N | SA4 - GREU Type TL-3 (GRAU-350/GRAU M-350) Replacement MEDIAN | Material | Each |  | 8
3434-SA4O | SA4 - Single Lane Closure w/ TC Super | Material | Each |  | 8
3434-SA5 | SA5 - 12' Concrete Paved Shoulders on I-40 C-D Lanes | Material | Lump Sum |  | 8
3434-SA6 | SA6 - Design Change for I-77 NB Lane Drop | Material | Lump Sum |  | 8
3434-SA7 | SA7 - Video Existing Drainge - I-77 North Extended Lane Drop | Material | Lump Sum |  | 8
3434-SA8 | SA8 - City of Statesville Sidewalk Betterments | Material | Lump Sum |  | 8
3434-SA9 | SA9 - Roadway Changes to RFC Plan Sheet 16 and 17 | Material | Lump Sum |  | 8
3434-SA10 | SA 10 - I-77 Southern Crossover | Material | Lump Sum |  | 8
3434-SA11 | SA 11 - Signal Upgrades | Material | Lump Sum |  | 8
3434-SA12 | SA 12 - Design of Structurally Deficient Pipes (Group A) | Material | Lump Sum |  | 8
3434-SA13 | SA 13 - Circuit 334 Access Road and AUE Clearing | Material | Lump Sum |  | 8
3434-SA14 | SA 14 - Right-of-Way Acquisition for Parcel 100 | Material | Lump Sum |  | 8
3434-SA15 | SA 15 - Design of Structurally Deficient Pipes(Group B) | Material | Lump Sum |  | 8
3434-SA16 | SA 16 - City of Statesville Sewer Betterments | Material | Lump Sum |  | 8
3434-SA17 | SA 17 - Design of I-40 Temporary Bridge at Old Mocksville Road | Material | Lump Sum |  | 8
3434-SA18A | SA18 - VEP #2 - Replace 3" B25.0C with NDI where New meets Exist | Material | Lump Sum |  | 8
3434-SA18B | SA18 - Contractor's Share of Cost Savings | Material | Lump Sum |  | 8
3434-SA19 | SA 19 - US 64 (Davie Ave) Right-of-Way Revision | Material | Lump Sum |  | 8
3434-SA20 | SA 20 - NB Lane Drop Extension | Material | Lump Sum |  | 8
3434-SA21 | SA 21 - Backflow Preventers | Material | Lump Sum |  | 8
3434-SA22 | SA 22 - Additional Type 1 Aggregate Subgrade | Material | Cubic Yard |  | 8
3434-SA23 | SA 23 - Noise Wall Maintenance Access | Material | Lump Sum |  | 8
3434-SA24 | SA 24 - Additional Width for Temporary Loops | Material | Lump Sum |  | 8
3434-SA25 | SA 25 - Bore & Jack 48" "Not in Soil" | Material | Lump Sum |  | 8
3434-SA26A | SA 26 - VEP#3 - Eliminate Full Depth Reconstruction | Material | Lump Sum |  | 8
3434-SA26B | SA 26 - VEP#3 - Contractor's Share of Cost Savings | Material | Lump Sum |  | 8
3434-SA27A | SA 27 - Construction of Structurally Deficient Pipes, Goup A | Material | Linear Feet |  | 8
3434-SA27B | SA 27 - 15" Wld Stl Pipe Grade B Not in Soil | Material | Linear Feet |  | 8
3434-SA27C | SA 27 - 18" Wld Stl Pipe Grade B Not in Soil | Material | Linear Feet |  | 8
3434-SA27D | SA 27 - 30" Wld Stl Pipe Grade B Not in Soil | Material | Linear Feet |  | 8
3434-SA27E | SA 27 - 36" Wld Stl Pipe Grade B Not in Soil | Material | Linear Feet |  | 8
3434-SA28 | SA 28 - Asbestos Abatement | Material | Lump Sum |  | 8
3434-SA | 3434 - Suplemental Agreements | Material |  |  | 8
3418-0332 | 3418-0332 - Bonds for Wet Utility Work - CO | Material | Lump Sum |  | 8
3418-0341 | 3418-0341 - Mobilization for work on henson road (S-11-362) - CO | Material | Lump Sum |  | 8
3418-0343 | 3418-0343 - Traffic Control for Henson Rd (S-11-362) - CO | Material | Day |  | 8
3418-0344 | 3418-0344 - 10" cmrb wet cured on S-11-362 - recycled pc conc.base cr.-6"un | Material | Square Yard |  | 8
3418-0345 | 3418-0345 - Portland Cement for S-11-362 - cem.mod.rec.base | Material | Ton |  | 8
3418-0346 | 3418-0346 - Liquid Binder for S-11-362 - pg64-22 | Material | Ton |  | 8
3418-0347 | 3418-0347 - Interm. Type B for S-11-362 | Material | Ton |  | 8
3418-0348 | 3418-0348 - Surf. B for S-11-362 | Material | Ton |  | 8
3418-0349 | 3418-0349 - Surf. C 400 Lb/SY for Driveways on S-11-362 | Material | Ton |  | 8
3418-0350 | 3418-0350 - Surf. C 400 Lb/SY for Intersections on S-11-362 | Material | Ton |  | 8
3418-0351 | 3418-0351 - Unclassified Excavation on S-11-362 | Material | Cubic Yard |  | 8
3418-0352 | 3418-0352 - Borrow Excavation on S-11-362 | Material | Cubic Yard |  | 8
3418-0353 | 3418-0353 - 4"wh.brkn.line-gap ex-f.d.pnt. for S-11-362 | Material | Linear Feet |  | 8
3418-0354 | 3418-0354 - 4"wh.sld.line-pvt.edge-f.d.pnt for S-11-362 | Material | Linear Feet |  | 8
3418-0355 | 3418-0355 - 24"wh.sld.lne-stop/dia-f.d.pnt for S-11-362 | Material | Linear Feet |  | 8
3418-0356 | 3418-0356 - 4"yel.sld.lne-pvt edge-f.d.pnt for S-11-362 | Material | Linear Feet |  | 8
3418-0357 | 3418-0357 - 4"wh.brknline thermo-90 mil. for S-11-362 | Material | Linear Feet |  | 8
3418-0358 | 3418-0358 - 4" wh sld lne pvt el th-90 ml for S-11-362 | Material | Linear Feet |  | 8
3418-0359 | 3418-0359 - 24"wh sldlnes thermo-125 mil. for S-11-362 | Material | Linear Feet |  | 8
3418-0360 | 3418-0360 - 4"yel.sld.lnes.-thermo. 90mil for S-11-362 | Material | Linear Feet |  | 8
3418-0361 | 3418-0361 - perm.yel.pav.mark bi-dir 4"x4" for S-11-362 | Material | Each |  | 8
3418-0362 | 3418-0362 - trm for S-11-362 - CO | Material | Square Yard |  | 8
3418-0363 | 3418-0363 - Permanent cover for road S-11-362 | Material | Acre |  | 8
3418-0112 | 3418-0112 - Add'l Priester Road pavement structure - CO #11 | Material | Lump Sum |  | 8
3418-0161 | 3418-0161 - 4000 PSI Barrier Price Reduction | Material | Lump Sum |  | 8
3457-SOV | 3457-SOV | Nonlabor |  |  | 1
3457-SOV-01 | 3457 - Design | Material |  |  | 8
3457-SOV-02 | 3457 - Mobilization | Material |  |  | 8
3457-SOV-04 | 3457 - Clear & Grub | Material |  |  | 8
3457-SOV-03 | 3457 - Erosion Control | Material |  |  | 8
3457-SOV-05 | 3457 - Excavation & Embankment | Material |  |  | 8
3457-SOV-06 | 3457 - Stabilization & Road Base | Material |  |  | 8
3457-SOV-07 | 3457 - Asphalt Paving | Material |  |  | 8
3457-SOV-08 | 3457 - Bridge Rebar & Concrete | Material |  |  | 8
3457-SOV-09 | 3457 - Drainage | Material |  |  | 8
3457-SOV-10 | 3457 - Bridge Beams | Material |  |  | 8
3457-SOV-11 | 3457 - Bridge Piles | Material |  |  | 8
3457-SOV-12 | 3457 - Concrete Gutters & Barrier Wall | Material |  |  | 8
3457-SOV-13 | 3457 - Soundwall | Material |  |  | 8
3457-SOV-14 | 3457 - Guardrail | Material |  |  | 8
3457-SOV-15 | 3457 - MSE Walls | Material |  |  | 8
3457-SOV-16 | 3457 - Sod | Material |  |  | 8
3457-SOV-17 | 3457 - Conduit & Manholes | Material |  |  | 8
3457-SOV-18 | 3457 - Wire / Fiber | Material |  |  | 8
3457-SOV-19 | 3457 - ITS Equip | Material |  |  | 8
3457-SOV-20 | 3457 - Signs | Material |  |  | 8
3457-SOV-21 | 3457 - Markers / Pavement Markings | Material |  |  | 8
3457-SOV-22 | Lighting | Material |  |  | 8
3457-SOV-23 | Cypress Signal | Material |  |  | 8
3457-SOV-25 | Utility Construction | Material |  |  | 8
3457-SOV-24 | Construction Tolling Sites | Material |  |  | 8
3457-COST | 3457-COST | Nonlabor |  |  | 1
3404-WO-12 | WO #12 - NS Replace Bearings | Material | Lump Sum |  | 8
3404-WO-14 | WO#14 - NS Tub Girder Repair G4 | Material | Lump Sum |  | 8
3404-WO-15 | WO#15 - Remove and Dispose of Asbestos Pipe | Material | Lump Sum |  | 8
UPC112815.CO004 | CO#04 – Drainfield Locations | Material | Unit |  | 8
UPC112815.CO005 | CO#05 – Randolph Ridge Design | Material | Unit |  | 8
3338 | 3338 - Port Access | Nonlabor |  |  | 1
C43 - Labor | Labor | Labor |  |  | 10
I405-1 | I405 Project Resource | Nonlabor |  |  | 1
I405 Revenue | I405 Revenue | Nonlabor |  |  | 1
9161 - 20100 | MTL-TRAFFIC CONTROL | Material | Month |  | 1
9161 - 20200 | MTL-EROSION CONTROL/DEWATERING | Material | Month |  | 1
9161 - 203001 | MTL-Filter Sand-Slopes & Toe | Material | Ton |  | 1
9161 - 203002 | MTL-Filter Sand-Chimney Drain | Material | Ton |  | 1
9161 - 203003 | MTL-Filter Sand-Blanket Drain | Material | Ton |  | 1
9161 - 203004 | MTL-Filter Snd-Pressure Relief | Material | Ton |  | 1
9161 - 203005 | MTL-Aggregate-Pipe Bed/BF | Material | Ton |  | 1
9161 - 203006 | MTL-Aggregate-Shell/Lime Rock | Material | Ton |  | 1
9161 - 203007 | MTL-Aggregate-Rip Rap Bedding | Material | Ton |  | 1
9161 - 203009 | MTL-Aggregate-Rip Rap/Lime | Material | Ton |  | 1
9161 - 203010 | MTL-Aggregate-Rip Rap/Granite | Material | Ton |  | 1
9161 - 203089 | MTL-Aggregate-Temporary | Material | Ton |  | 1
9161 - 203099 | MTL-Aggregate-General | Material | Ton |  | 1
9161 - 205001 | MTL-Portland Cement | Material | Ton |  | 1
9161 - 21000 | MTL-GEOTEXTILE | Material | Square Yard |  | 1
9161 - 21100 | MTL-PIPE-CONCRETE | Material | Linear Feet |  | 1
9161 - 21200 | MTL-PIPE-METAL | Material | Linear Feet |  | 1
9161 - 21300 | MTL-PIPE-PLASTIC | Material | Linear Feet |  | 1
9161 - 21600 | MTL-PILING-SHEET PILE | Material | Ton |  | 1
9161 - 21700 | MTL-PILING-CONCRETE PILE | Material | Linear Feet |  | 1
9161 - 22000 | MTL-ARTICULATING BLOCK WALL | Material | Square Feet |  | 1
9161 - 22200 | MTL-CONCRETE | Material | Cubic Yard |  | 1
9161 - 22300 | MTL-WATERPROOFING | Material | Lump Sum |  | 1
9161 - 22400 | MTL-PRECAST MATERIALS | Material | Lump Sum |  | 1
9161 - 22500 | MTL-PRECAST BEAMS | Material | Linear Feet |  | 1
9161 - 22510 | MTL-PRECAST BARRIER WALL | Material | Linear Feet |  | 1
9161 - 22600 | MTL-FORMWORK/CARPENTRY | Material | Square Feet |  | 1
9161 - 22800 | MTL-MISCELLANEOUS METALS | Material | Lump Sum |  | 1
9161 - 22900 | MTL-REINFORCING STEEL | Material | Ton |  | 1
9161 - 23200 | MTL-SAFETY & WORK AREA PROTECT | Material | Lump Sum |  | 1
9161 - 23300 | MTL-PLANT FACILITY | Material | Cubic Yard |  | 1
9161 - 23400 | MTL-DIRECT MTL INCIDENTALS | Material | Lump Sum |  | 1
9161 - 23500 | MTL-WATERWAY MECHANICAL | Material | Each |  | 1
9161 - 23600 | MTL-LANDSCAPING | Material | Lump Sum |  | 1
9161 - 23900 | MTL-ELECTRICAL | Material | Lump Sum |  | 1
9161 - 30010 | Asphalt Sub | Material | Ton |  | 1
9161 - 30020 | Bridge Deck Grooving Sub | Material | Square Yard |  | 1
9161 - 30030 | Building Sub | Material | Each |  | 1
9161 - 30050 | Concrete Pump Sub | Material | Cubic Yard |  | 1
9161 - 30070 | Concrete Flatwork | Material | Lump Sum |  | 1
9161 - 30080 | Desilt/Video/Laser Pipe Sub | Material | Linear Feet |  | 1
9161 - 30090 | Monitoring Wells | Material | Lump Sum |  | 1
9161 - 30100 | Dewatering Engineer Sub | Material | Lump Sum |  | 1
9161 - 30120 | Elec/Light Sub | Material | Lump Sum |  | 1
9161 - 30130 | Construction Engineering | Material | Lump Sum |  | 1
9161 - 30140 | Tuffboom Debris Skirt Sub | Material | Linear Feet |  | 1
9161 - 30160 | Fence Sub | Material | Lump Sum |  | 1
9161 - 30170 | Geotechnical Investigations | Material | Lump Sum |  | 1
9161 - 30180 | Seeding/Sod Sub | Material | Acre |  | 1
9161 - 30190 | Guardrail Sub | Material | Linear Feet |  | 1
9161 - 30200 | Handrail Sub | Material | Linear Feet |  | 1
9161 - 30210 | Instrumentation Sub | Material | Month |  | 1
9161 - 30220 | Landscaping Sub | Material | Lump Sum |  | 1
9161 - 30230 | Liner Sub | Material | Square Feet |  | 1
9161 - 30250 | Mechanical Sub | Material | Lump Sum |  | 1
9161 - 30270 | Mowing Sub | Material | Acre |  | 1
9161 - 30280 | Needle Beam Sub | Material | Lump Sum |  | 1
9161 - 30310 | Quality Control Sub | Material | Lump Sum |  | 1
9161 - 30320 | Rebar Sub | Material | LB |  | 1
9161 - 30330 | Drilled Shaft - Pressure Rel. | Material | Linear Feet |  | 1
9161 - 30340 | Sand Screening Sub | Material | Month |  | 1
9161 - 30370 | Security Sub | Material | Hour |  | 1
9161 - 30380 | Sew Filter Fabric | Material | Square Yard |  | 1
9161 - 30390 | Signage | Material | Each |  | 1
9161 - 30410 | Soil Bentonite Wall Sub | Material | Square Feet |  | 1
9161 - 30430 | Stilling Well Sub | Material | Each |  | 1
9161 - 30440 | Street Sweep Sub | Material | Hour |  | 1
9161 - 30450 | Striping Sub | Material | Lump Sum |  | 1
9161 - 30460 | Survey Sub | Material | Lump Sum |  | 1
9161 - 30470 | Water Well Sub | Material | Each |  | 1
9161 - 30480 | Waterproofing Sub | Material | Lump Sum |  | 1
9161 - 30490 | Dumpsetr for Demo | Material | Month |  | 1
9161 - 30500 | Sanitary Sewer Sub | Material | Lump Sum |  | 1
9161 - 30510 | MDC Sub - Electric/Mech | Material | Lump Sum |  | 1
9161 - 30520 | MDC Sub - Roadway | Material | Month |  | 1
9161 - 30530 | MDC Sub - Landscape | Material | Lump Sum |  | 1
9161 - 30540 | Erosion Control Sub | Material | Lump Sum |  | 1
9161 - 30580 | Sheet Pile Install Sub | Material | Square Yard |  | 1
9161 - 30570 | Compound Site Prep Sub | Material | Lump Sum |  | 1
9161 - 30585 | Concrete works | Material | Cubic Yard |  | 1
9161 - 30590 | TEMP SLOPE INTERUPTION DEVICES (WATTLES) | Material | Linear Feet |  | 1
9161 - 30595 | TEMP SEED & MULCH | Material | Square Yard |  | 1
9161 - 30600 | Concrete piles sub | Material | Linear Feet |  | 1
9161 - 30550 | Survey Sub | Material | Lump Sum |  | 1
9161 - 30560 | S&I Sheet Piling | Material | Lump Sum |  | 1
9161 - 30605 | Unsuitable Fndn Area Sub | Material | Lump Sum |  | 1
9161 - 30610 | Townsend Canal Fndn Prep Sub | Material | Lump Sum |  | 1
9161 - 30615 | Segment M Dam Turnkey Sub | Material | Lump Sum |  | 1
9161 - 30620 | Townsend Clear and Grub Sub | Material | Acre |  | 1
9161 - 30630 | Hydro Gates Installation Sub | Material | Lump Sum |  | 1
9161 - 30635 | LPDD 1 Demo Sub | Material | Lump Sum |  | 1
9161 - 351001 | Haul By Ton - Sand | Material | Ton |  | 1
9161 - 351002 | Haul By Ton - Pipe Bed/BF | Material | Ton |  | 1
9161 - 351003 | Haul By Ton - Shell/Limerock | Material | Ton |  | 1
9161 - 351004 | Haul By Ton - Rip Rap Bedding | Material | Ton |  | 1
9161 - 351005 | Haul By Ton - Rip Rap, Limestn | Material | Ton |  | 1
9161 - 351006 | Haul By Ton - Rip Rap, Granite | Material | Ton |  | 1
9161 - 351007 | Haul By Ton - Temporary | Material | Ton |  | 1
9161 - 351008 | Haul By Ton - General | Material | Ton |  | 1
9161 - 351009 | Haul By Ton - Portland Cement | Material | Ton |  | 1
9161 - 352001 | Haul By CY (Compost) | Material | Cubic Yard |  | 1
9161 - 353001 | Haul By Load (Debris) | Material | Load |  | 1
9161 - 40500 | TRAFFIC CONTROL | Material | Month |  | 1
9161 - 41010 | EROSION CONTROL-CREW | Material | Month |  | 1
9161 - 41060 | EROSION CONTROL-TEMP DRAIN | Material | Linear Feet |  | 1
9161 - 41070 | EROSION CONTROL-DUST | Material | Month |  | 1
9161 - 41080 | EROSION CONTROL-REPAIRS | Material | Month |  | 1
9161 - 41510 | POTHOLING CREWS | Material | Month |  | 1
9161 - 42010 | DEMO-AC PAVEMENT | Material | Cubic Yard |  | 1
9161 - 42030 | DEMO-BUILDINGS | Material | Square Feet |  | 1
9161 - 42040 | DEMO-BRIDGE | Material | Cubic Yard |  | 1
9161 - 42060 | DEMO-DRAINAGE | Material | Linear Feet |  | 1
9161 - 42080 | DEMO-APPURTANCES | Material | Lump Sum |  | 1
9161 - 425051 | Work/Hazard Zone Delineation | Material | Linear Feet |  | 1
9161 - 425052 | Debris Removal | Material | Load |  | 1
9161 - 42510 | CLEAR AND GRUB | Material | Acre |  | 1
9161 - 425551 | Miscallaneous Flatwork | Material | Square Feet |  | 1
9161 - 425552 | Low Water Crossings | Material | Each |  | 1
9161 - 428101 | Install 6, 8, and 18" PVC | Material | Linear Feet |  | 1
9161 - 428102 | Place Townsend Sand Blanket | Material | Ton |  | 1
9161 - 428103 | Place Townsend Stone | Material | Ton |  | 1
9161 - 428104 | Instl Fltr Fab-Prsr Relief Sys | Material | Square Yard |  | 1
9161 - 428105 | Plc Tremi Plug-Prsr Relief Sys | Material | Cubic Yard |  | 1
9161 - 428106 | Dewater Can & Place Sand | Material | Each |  | 1
9161 - 430201 | Construct/Maintain Haul Roads | Material | Square Yard |  | 1
9161 - 430202 | Maintain Haul Roads | Material | Month |  | 1
9161 - 430203 | Maint Land Owner Access Rd | Material | Month |  | 1
9161 - 430205 | Construct Temporary Brdg Cross | Material | Each |  | 1
9161 - 430408 | Common Ex to Fill | Material | Cubic Yard |  | 1
9161 - 430411 | Common Ex to Waste | Material | Cubic Yard |  | 1
9161 - 430412 | Place and Compact Common Fill | Material | Cubic Yard |  | 1
9161 - 430413 | Common Ex to Stockpile | Material | Cubic Yard |  | 1
9161 - 4304135 | Common Ex to Stockpile-Sub | Material | Cubic Yard |  | 1
9161 - 430415 | Load and Haul Stock to Embank | Material | Cubic Yard |  | 1
9161 - 4304155 | Load & Haul Stock to Emb-Sub | Material | Cubic Yard |  | 1
9161 - 43080 | Rip / Break Rock | Material | Cubic Yard |  | 1
9161 - 431201 | Topsoil Stripping | Material | Cubic Yard |  | 1
9161 - 431202 | Foundation Preparation | Material | Cubic Yard |  | 1
9161 - 431406 | Topsoil-Haul To Waste | Material | Cubic Yard |  | 1
9161 - 431601 | Muck/Grade N. Canal/Boat Rmp | Material | Cubic Yard |  | 1
9161 - 431602 | Surface Wtr Mngt-Agg Ditching | Material | Cubic Yard |  | 1
9161 - 431206 | Dozer Push Strip Borrow | Material | Cubic Yard |  | 1
9161 - 431407 | Topsoil-Push To Wst in Borrow | Material | Cubic Yard |  | 1
9161 - 432013 | Borrow Ex | Material | Cubic Yard |  | 1
9161 - 30636 | Borrow Ex-Sub | Material | Cubic Yard |  | 1
9161 - 432017 | Place and Compact Borrow | Material | Cubic Yard |  | 1
9161 - 432037 | Place and Compact Dam Emb | Material | Cubic Yard |  | 1
9161 - 4320375 | Place and Compact Dam Emb-Sub | Material | Cubic Yard |  | 1
9161 - 433203 | Borrow Ex To Soil Cement Stkpl | Material | Cubic Yard |  | 1
9161 - 432201 | 18" Blanket Drain Filter Sand | Material | Cubic Yard |  | 1
9161 - 30637 | 18" Blanket Drain FS- Sub | Material | Cubic Yard |  | 1
9161 - 432202 | 25' Wide Chimney Drain Sand | Material | Cubic Yard |  | 1
9161 - 432203 | Wtr Side Filter Sand on Slope | Material | Cubic Yard |  | 1
9161 - 432204 | Place Soil Bentonite Cap | Material | Cubic Yard |  | 1
9161 - 432206 | Screen Excav Mtl-Cln Snd Spec | Material | Cubic Yard |  | 1
9161 - 550305 | Place and compact select fill | Material | Cubic Yard |  | 1
9161 - 550306 | Load and Haul from Stock pile to place | Material | Cubic Yard |  | 1
9161 - 432401 | FG Slopes, Road, and Landscape | Material | Square Yard |  | 1
9161 - 432402 | Fine Grade Misc Areas | Material | Square Yard |  | 1
9161 - 432404 | Finegrade Haul Roads | Material | Square Yard |  | 1
9161 - 433201 | Soil Cement Toe - Ex to Waste | Material | Cubic Yard |  | 1
9161 - 433202 | Place and Cure Soil Cmnt | Material | Cubic Yard |  | 1
9161 - 433401 | Filter Fabric For Rip Rap | Material | Square Yard |  | 1
9161 - 433402 | Filter Fabric - Misc. | Material | Square Yard |  | 1
9161 - 433403 | Filter Fabric For Soil Cement | Material | Square Yard |  | 1
9161 - 433404 | Marine Mattress | Material | Square Yard |  | 1
9161 - 435101 | Finegrade Aggregate Base | Material | Square Yard |  | 1
9161 - 435301 | P&C Shell Rock | Material | Ton |  | 1
9161 - 435302 | P&C Limerock | Material | Ton |  | 1
9161 - 435303 | Stockpile Shell Rock Lime Rock | Material | Ton |  | 1
9161 - 435401 | Place & Finish Soil Cem (15") | Material | Cubic Yard |  | 1
9161 - 435402 | Place & Finish Soil Cem (24") | Material | Cubic Yard |  | 1
9161 - 435701 | Stabilize Subgrade (Lbr40) | Material | Square Yard |  | 1
9161 - 435702 | Finish Type B Stabilization | Material | Square Yard |  | 1
9161 - 455401 | ELB Temp. Drainage | Material | Linear Feet |  | 1
9161 - 455402 | ELB Storm Drain 12-30" | Material | Linear Feet |  | 1
9161 - 455404 | ELB Storm Drainge 6-12" | Material | Linear Feet |  | 1
9161 - 455406 | Hydrostatic Prsr Test 12-30" | Material | Linear Feet |  | 1
9161 - 455407 | Pipe BF 84" Pipe (#89 Stone) | Material | Ton |  | 1
9161 - 455502 | ELB Storm Drain 36-60" | Material | Linear Feet |  | 1
9161 - 45570 | STORM DRAIN INLET/CB/END | Material | Each |  | 1
9161 - 456801 | Rip Rap Type A | Material | Ton |  | 1
9161 - 456802 | Rip Rap Type B | Material | Ton |  | 1
9161 - 456803 | Rip Rap Type C | Material | Ton |  | 1
9161 - 457001 | E&S End Wall/Outfall/Stilling | Material | Square Feet |  | 1
9161 - 457003 | Plc End Wall/Outfall/Stilling | Material | Cubic Yard |  | 1
9161 - 457005 | CIP End Wall | Material | Each |  | 1
9161 - 457701 | E&S SOG Culvert | Material | Square Feet |  | 1
9161 - 457702 | E&S Walls Culvert | Material | Square Feet |  | 1
9161 - 457703 | E&S SS Culvert | Material | Square Feet |  | 1
9161 - 457704 | Place & Finish Box Culvert CNC | Material | Cubic Yard |  | 1
9161 - 460101 | Dewater Ditch/Sumps EX/BF | Material | Month |  | 1
9161 - 460102 | Dewater Water Cntrl Structures | Material | Month |  | 1
9161 - 460103 | Dewater Pressure Relief System | Material | Month |  | 1
9161 - 460104 | Set Up Pumps and Discharge | Material | Month |  | 1
9161 - 465501 | Prep for Drive Piles | Material |  |  | 1
9161 - 465505 | Drive Sheet Piles | Material |  |  | 1
9161 - 465509 | Pull Sheet Piles | Material |  |  | 1
9161 - 465701 | Cofferdam-Mob for Sheet Pile | Material |  |  | 1
9161 - 465705 | Cofferdam-Drive Sheet Pile | Material |  |  | 1
9161 - 465706 | Cofferdam-Cut off Sheet Pile Structure Bypass | Material | Each |  | 1
9161 - 465708 | Cofferdam-Install Tie Rod | Material |  |  | 1
9161 - 47010 | STRUCTURE EXCAVATION | Material | Cubic Yard |  | 1
9161 - 470201 | Struct Bkfll S-470/All Struct | Material | Cubic Yard |  | 1
9161 - 47030 | FINEGRADE FOR FOUNDATION | Material | Square Feet |  | 1
9161 - 470601 | Mobe Pile Equip/Handle Pile | Material |  |  | 1
9161 - 470603 | Fab/Setup/Move Pile Template | Material |  |  | 1
9161 - 470604 | Drive 12" Conc. Piles | Material |  |  | 1
9161 - 470605 | Drive 18" Conc Pile w/Cushion | Material |  |  | 1
9161 - 470606 | Drive 24" Conc. Piles | Material |  |  | 1
9161 - 470607 | Cut off Conc.pile | Material |  |  | 1
9161 - 475201 | E&S Substructure | Material | Square Feet |  | 1
9161 - 475203 | Place Concrete Substructure | Material | Cubic Yard |  | 1
9161 - 47600 | BRIDGE BEAMS-SET PRECAST | Material | Linear Feet |  | 1
9161 - 476402 | E&S Deck Overhang | Material | Square Feet |  | 1
9161 - 476403 | E&S Bridge Deck | Material | Square Feet |  | 1
9161 - 476405 | Place Concrete Superstructure | Material | Cubic Yard |  | 1
9161 - 48300 | BRIDGE EXPANSION JOINTS | Material | Linear Feet |  | 1
9161 - 484501 | Finegrade Appraoch Slab | Material | Square Feet |  | 1
9161 - 484502 | E&S Approach Slab | Material | Square Feet |  | 1
9161 - 484503 | Place Conc. Approach Slab | Material | Cubic Yard |  | 1
9161 - 521001 | E&S Bridge Traffic Rail | Material | Square Feet |  | 1
9161 - 521002 | Plc Conc Brdg Traffic Rail | Material | Cubic Yard |  | 1
9161 - 524001 | F/P/S Leveling Pad Wave Wall | Material | Linear Feet |  | 1
9161 - 524002 | Unload & Set Wave Wall | Material | Linear Feet |  | 1
9161 - 524003 | Anchor/Pin Wave Wall | Material | Each |  | 1
9161 - 53530 | UNLOAD/HANDLE/ASSIST REBAR | Material | Ton |  | 1
9161 - 53540 | REINFORCING STEEL-MESH | Material | Square Yard |  | 1
9161 - 550301 | Bentonite Mixing Area | Material | Each |  | 1
9161 - 550302 | Handle Soil Bentonite Slurry | Material | Cubic Yard |  | 1
9161 - 550303 | Load and Haul to SBW Sub | Material | Cubic Yard |  | 1
9161 - 550307 | Load and Haul to SBW Sub Soil bentonite wall clay phase II | Material | Cubic Yard |  | 1
9161 - 550304 | Provide Water to SBW Sub | Material | Cubic Yard |  | 1
9161 - 851001 | F/P/S Mud Mat | Material | Cubic Yard |  | 1
9161 - 851002 | E&S Intake/Disharge Foundation | Material | Square Feet |  | 1
9161 - 851003 | E&S Cont/Gen Foundation/Apron | Material | Square Feet |  | 1
9161 - 851005 | Place Conc Intake/Disch Found | Material | Cubic Yard |  | 1
9161 - 851006 | Plc Conc Cont/Gen Found/Apron | Material | Cubic Yard |  | 1
9161 - 851008 | Set Anchor Bolts | Material | Each |  | 1
9161 - 852002 | F/P/S Pipe Craddles/Deadmen | Material | Cubic Yard |  | 1
9161 - 853001 | Wtr Control Str Precast Beams | Material | Each |  | 1
9161 - 853003 | Wtr Control Str Needle Beams | Material | Cubic Yard |  | 1
9161 - 855001 | F/P/S Conc. Stairs | Material | Cubic Yard |  | 1
9161 - 856001 | E&S Intake/Dischg Fndtn Wall | Material | Square Feet |  | 1
9161 - 856002 | Plc Conc Intake/Disch Fnd Wall | Material | Cubic Yard |  | 1
9161 - 856003 | Patch/Grout Intake/Disch Wall | Material | Square Feet |  | 1
9161 - 85900 | BLDG MISC METALS | Material | Lump Sum |  | 1
9161 - 86100 | BUILDING MECHANICAL | Material | Lump Sum |  | 1
9161 - 89900 | ELECTRIC INSTALL STRUCTURE | Material | Lump Sum |  | 1
9161 - 901001 | Pugmill Incidentals (LS) | Material | Cubic Yard |  | 1
9161 - 901002 | Pugmill Operation (CY) | Material | Cubic Yard |  | 1
9161 - 901003 | Pugmill Power | Material | Cubic Yard |  | 1
9161 - 901004 | Pugmill Ownership Cost | Material | Cubic Yard |  | 1
9161 - 901005 | Haul Mix to Soil Cem (15 IN) | Material | Cubic Yard |  | 1
9161 - 901006 | Haul Mix to Soil Cem (24 IN) | Material | Cubic Yard |  | 1
9161 - 901007 | Haul Mix to Soil Cem (Toe) | Material | Cubic Yard |  | 1
9161 - 901008 | Haul Mix to Soil Cem (Slope) | Material | Cubic Yard |  | 1
9161 - 95900 | PUNCHLIST | Material | Lump Sum |  | 1
9161 - 96001 | Eagle Lakes 1 thru 6 | Material | Lump Sum |  | 1
9161 - 96002 | Eagle Lakes 8 thru 20 | Material | Lump Sum |  | 1
9161 - 96003 | Eagle Lakes 21 thru 25 | Material | Lump Sum |  | 1
9161 - 96020 | Temporary VO to be Assigned | Material | Lump Sum |  | 1
UPC112815.Internal - 3453.007 | 4" High Contrast | Material | Linear Feet |  | 8
UPC112815.Internal - 3453.008 | 8" High Contrast | Material | Linear Feet |  | 8
UPC112815.Internal - 3453.005 | FOA-5 | Material | Each |  | 8
UPC112815.Internal - 3453.003 | TEMP SEDIMENT TRAP | Material | Cubic Yard |  | 8
UPC112815.Internal - 3453.004 | NS STREAM RELOCATION | Material | Cubic Yard |  | 8
UPC112815.Internal - 3453.001 | Endwall Sections/Junction Boxes | Material | Each |  | 8
UPC112815.Internal - 3453.002 | Adjust existing manhole/DI | Material | Each |  | 8
UPC112815.Internal - 3453.006 | MB-7F | Material | Each |  | 8
UPC112815.Internal - 3453.009 | SIGNAL MAST ARM POLE MP-3 ONE ARM 65' | Material | Each |  | 8
UPC112815.Internal - 3453.010 | SIGNAL MAST ARM POLE MP-3 ONE ARM 75' | Material | Each |  | 8
UPC112815.Internal - 3453.011 | 1 CONDUCTOR CABLE (WITH SPLICE KITS) | Material | Linear Feet |  | 8
3404-WO-16 | NS Luminaire Shields | Material | Lump Sum |  | 8
3404-WO-17 | NS Mill, Overlay, Markings, Inlaid Markers | Material | Lump Sum |  | 8
9156-SA29 | SA#29 - Turbine Increased Depth of Base | Material | Lump Sum |  | 8
9156-SA35 | SA#35 - Colonial Inspecting Allowance Credit | Material | Lump Sum |  | 8
SUB-GROUND IMPROV | Sub - Ground Improvement Crew | Labor |  |  | 1
SUB-ST-SIP | Sub - Bridge SIP Sub Crew | Labor |  |  | 1
9156-SA38 | SA#38 - Reinforced Approach Fill Upgrades | Material | Lump Sum |  | 8
ST-PARAPET | Parapet Crew | Labor |  | Structures Crew | 1
ST-DIAPHRAM | Diaphram Crew | Labor |  | Structures Crew | 1
ST-DECK DRAIN | Deck Drain Crew | Labor |  | Structures Crew | 1
3418-0013 | 3418-0013 - R/W Premiums for tracts 13, 54, & 172 - CO | Material | Lump Sum |  | 8
3418-0071 | 3418-0071 - Asbestos abatement tracts 3, 66, & 150/underground tank rem. - CO | Material | Lump Sum |  | 8
3418-0073 | 3418-0073 - Abandon 17 monitoring wells - CO | Material | Lump Sum |  | 8
3418-0333 | 3418-0333 - Wet utility relocations - town of grover - CO | Material | Lump Sum |  | 8
3460 | 3460 - KS Levee | Nonlabor |  |  | 1
3461 | 3461 - 495 NEXT | Nonlabor |  |  | 1
3461-001 | EARLY WORKS | Material |  |  | 1
3461-002 | DESIGN SERVICES | Material |  |  | 1
3461-003 | MOBILIZATION (Maximum of 2% of Total) | Material |  |  | 1
3461-004 | CONSTRUCTION MANAGEMENT & QA/QC | Material |  |  | 1
3461-005 | DEMOLITION & SITE PREPARATION | Material |  |  | 1
3461-006 | EROSION & SEDIMENT CONTROL | Material |  |  | 1
3461-007 | EARTHWORK | Material |  |  | 1
3461-008 | PAVEMENT | Material |  |  | 1
3461-009 | PERMANENT BARRIERS, GUARDRAIL & FENCING | Material |  |  | 1
3461-010 | SIGNING & PAVEMENT MARKINGS | Material |  |  | 1
3461-011 | LIGHTING | Material |  |  | 1
3461-012 | DRAINAGE & STORMWATER MANAGEMENT | Material |  |  | 1
3461-013 | BRIDGES | Material |  |  | 1
3461-014 | RETAINING WALLS | Material |  |  | 1
3461-015 | UTILITIES | Material |  |  | 1
3461-016 | ITS & TMS EQUIPMENT | Material |  |  | 1
3461-017 | TMS SUBCONTRACTOR | Material |  |  | 1
3461-018 | NOISE BARRIERS - GROUND MOUNTED | Material |  |  | 1
3461-019 | NOISE BARRIERS - RETAINING WALL MOUNTED | Material |  |  | 1
3461-020 | NOISE BARRIERS - BRIDGE MOUNTED | Material |  |  | 1
3461-021 | ENVIRONMENTAL MITIGATION | Material |  |  | 1
3461-022 | MAINTENANCE OF TRAFFIC | Material |  |  | 1
3461-023 | RIGHT-OF-WAY | Material |  |  | 1
3461-024 | ALTERNATIVE MARYLAND EXPRESS LANES INTERFACE ADJUSTMENT | Material |  |  | 1
3404-WO-19-1 | WO #19 - NS Nutrient Credit Purchase | Material | Lump Sum |  | 8
3404-WO-19-2 | WO #19 - NS Asphalt Rideability Adjustment | Material | Lump Sum |  | 8
3404-WO-20 | WO #20 - Replace 5 bearings | Material | Lump Sum |  | 8
3404-WO-21 | WO #21 - Signal Interconnect | Material | Lump Sum |  | 8
9156-SA37 | SA#37 - Construction of Structures 23 & 24 | Material | Lump Sum |  | 8
9156-SA39 | SA#39 - Town of Garner Utility Construction Addition | Material | Lump Sum |  | 8
9156-SA40 | SA#40 - Additional ITS Work | Material | Lump Sum |  | 8
3460 - COST | KC Levee CostResource | Labor |  |  | 0
9151 - Formliners | I-10 - Formliners | Material |  |  | 1
9151 - Flutted Fin | I-10 - Fluted Fin Pattern Formliner | Material | Each |  | 1
9151 - Flow Pattern | I-10 - Flow Patternf Formliner | Material | Each |  | 1
9151 - Lemon Motif | I-10 - Lemon Motif Formliner | Material | Each |  | 1
9151 - Grape Motif | I-10 - Grape Motif Formliner | Material | Each |  | 1
9151 - Orange Motif | I-10 - Orange Motif Formliner | Material | Each |  | 1
9151 - Lemon Trans Motif | I-10 - Lemon Transition Motif | Material |  |  | 8
9151 - Orang Trans Motif | I-10 - Orange Transition Motif | Material |  |  | 8
SUB-GEO | Sub - Geotechnical Monitoring & Instruments | Labor |  |  | 1
UPC112815.CO010 | CO#10 – Merrifield Stockpile Removal Piles E and F | Material | Unit |  | 8
UPC112815.CO006 | CO#06 - DDI Signal & ITS Preferences | Material | Unit |  | 8
UPC112815.CO007 | CO#07 - Mill & Overlay Limits on PWC Parkway | Material | Unit |  | 8
UPC112815.CO008 | CO#08 - Custom Rock Form Liner | Material | Unit |  | 8
UPC112815.CO009A | CO#09A - Jennell Extension | Material | Unit |  | 8
9156-SETTLEMENT | Settlement & Release Agreement | Material | Unit |  | 8
9156-SA41 | SA#41 - ADDL CLEARING – PARCEL 662/1774 | Material | Lump Sum |  | 8
9156-SA42 | SA#42 - Elimination of Painting and Staining | Material | Lump Sum |  | 8
3418-0365 | 3418-0365 - Extra MOB for Gosalia | Material | Each |  | 8
3418-0366 | 3418-0366 - 7/1/22 Escalation for Gosalia | Material | Lump Sum |  | 8
3418-0367 | 3418-0367 - Southend added barrier | Material | Lump Sum |  | 8
3434-SA29 | SA 29 - Additional Construction Lighting | Material | Lump Sum |  | 8
3434-SA30 | SA 30 - Design of Signs on Old Mocksville Road | Material | Lump Sum |  | 8
3434-SA31 | SA 31 - Construction of Structurally Deficient Pipes Group B | Material | Lump Sum |  | 8
3434-SA32 | SA 32 - Davie Avenue Water Meters & BFP | Material | Lump Sum |  | 8
3434-SA33 | SA 33 - Geotextile for Bridge Approach Fills | Material | Lump Sum |  | 8
3434-SA34 | SA 34 - Anchored Sheet Pile RW 1 – Design & Construction | Material | Lump Sum |  | 8
3434-SA35 | SA 35 - Y9 Retaining Walls & 8” x 18” Curb | Material | Lump Sum |  | 8
3434-C5 | Claim 5 - RW Delays, Permit, Prior Rights | Material | Lump Sum |  | 8
9151 - Malcom | 9151 - Malcom Drilling Resources | Nonlabor |  |  | 1
9151 - GA Rig #1 | Horizontal Soil Nail and GA Rig #1 | Nonlabor |  |  | 1
9151 - GA Rig #2 | Horizontal Soil Nail and GA Rig #2 | Nonlabor |  |  | 1
9151 - GA Rig #3 | Horizontal Soil Nail and GA Rig #3 | Nonlabor |  |  | 1
9151 - GA Rig #4 | Horizontal Soil Nail and GA Rig #4 | Nonlabor |  |  | 1
9151 - Rig #1 | Vertical Pile Driving Rig #1 | Nonlabor |  |  | 1
9151 - Rig #2 | Vertical Pile Driving Rig #2 | Nonlabor |  |  | 1
DESIGN-SOV | DESIGN - SOV | Labor |  |  | 0
PM | DESIGN PROJECT MGMT | Labor |  |  | 1
RDWY | RDWY DESIGN | Labor |  |  | 1
STR | STRUCTURE DESIGN | Labor |  |  | 1
STR.BR | BRIDGE DESIGN | Labor |  |  | 1
STR.RW | RETAINING WALL DESIGN | Labor |  |  | 1
STR.NW | NOISE WALL DESIGN | Labor |  |  | 1
STR.MISC | MISC STRUCTURE DESIGN (CULVERTS ETC) | Labor |  |  | 1
HYD | HYDRAULIC DESIGN (DRAINAGE) | Labor |  |  | 1
HYD.CD | CLOSED DRAINAGE DESIGN (PIPE ETC) | Labor |  |  | 1
HYD.OD | OPEN DRAINAGE DESIGN (DITCHES ETC) | Labor |  |  | 1
MOT | MAINTENANCE OF TRAFFIC DESIGN | Labor |  |  | 1
EROS | EROSION CONTROL DESIGN | Labor |  |  | 1
TRAF | TRAFFIC ANALYSIS | Labor |  |  | 1
SIG | SIGNAL DESIGN | Labor |  |  | 1
SIGN | SIGNAGE DESIGN | Labor |  |  | 1
RR | RAILROADS | Labor |  |  | 1
RR.DGN | RAILROAD DESIGN | Labor |  |  | 1
RR.CORD | RAILROAD COORDINATION | Labor |  |  | 1
PMT ENV | PERMITTING AND ENVIROMENTAL DESIGN | Labor |  |  | 1
UTIL | UTILITIES | Labor |  |  | 1
UTIL.DGN | UTILITY DESIGN | Labor |  |  | 1
UTIL.COORD | UTILITY COORDINATION | Labor |  |  | 1
NOISEW | NOISEWALL ANALYSIS | Labor |  |  | 1
GEOTECH | GEOTECHNICAL DESIGN | Labor |  |  | 1
GEOTECH.RDWY | ROADWAY GEOTECHNICAL DESIGN | Labor |  |  | 1
GEOTECH.BR | BRIDGE GEOTECHNICAL DESIGN | Labor |  |  | 1
GEOTECH.RW | RETAINING WALL GEOTECHNICAL DESIGN | Labor |  |  | 1
GEOTECH.NW | NOISEWALL GEOTECHNICAL DESIGN | Labor |  |  | 1
GEOTECH.MISC | MISCELLANEOUS GEOTECHNICAL DESIGN | Labor |  |  | 1
ITS | INFORMATION TECHNOLOGY SYSTEMS DESIGN | Labor |  |  | 1
TOLL | TOLLING DESIGN | Labor |  |  | 1
LGHT | LIGHTING DESIGN | Labor |  |  | 1
LDSC/AR | LANDSCAPING / ARCHITECT DESIGN | Labor |  |  | 1
SURV/SU | SURVEY / SUE | Labor |  |  | 1
QLTY | DESIGN QUALITY CONTROL/QUALITY ASSURANCE | Labor |  |  | 1
PR | PUBLIC RELATIONS | Labor |  |  | 1
SUB-OCS Pole | Sub - OCS Pole Crew | Labor |  |  | 1
SUB-OCS FND | Sub - OCS FND Crew | Labor |  |  | 1
C43-Sub-Mass-Moina | C-43 - Sub - Mass EW - Moina | Labor |  |  | 1
C43-Sub-Mass-Eagle | C-43 - Sub - Mass EW - Eagle | Labor |  |  | 1
C-43 Bentonite Support | C43 - Soil Bentonite Support Crew | Labor |  |  | 1
3404-WO-22 | WO #22 - NS Remove electrical junction boxes (B680) | Material | Lump Sum |  | 8
3404-WO-23 | WO #23 - NS Conductor Cable and Luminaires | Material | Lump Sum |  | 8
3404-WO-24 | WO #24 - NS Concrete Box Beam Demolition (B678) | Material | Lump Sum |  | 8
C43-Plug47 | C43 - Select Fill Plug Crew - 47 lift | Labor |  |  | 1
3453-203001 | Sand | Material | Ton |  | 8
3453-203002 | Agg #21B | Material | Ton |  | 8
3453-203003 | Agg #57/#68 | Material | Ton |  | 8
3453-203004 | Rip Rap | Material | Ton |  | 8
3453-203005 | Agg #21A Cement Treated | Material | Ton |  | 8
3453-203006 | 3000 PSI Pea Gravel | Material | Ton |  | 8
3453-211001 | 15" to 24" Concrete Pipe | Material | Linear Feet |  | 8
3453-211002 | 30" to 42" Concrete Pipe | Material | Linear Feet |  | 8
3453-211003 | 48" to 54" Concrete Pipe | Material | Linear Feet |  | 8
3453-211004 | Concrete Pipe End Sections | Material | Each |  | 8
3453-212001 | Water Main Pipe/Components | Material | Lump Sum |  | 8
3453-212002 | Sanitary Sewer Pipe/Components | Material | Lump Sum |  | 8
3453-212003 | Corrugated Metal Pipe | Material | Lump Sum |  | 8
3453-222001 | 3000/4000 PSI Conc-Drainage | Material | Cubic Yard |  | 8
3453-222002 | A3 Structural Concrete | Material | Cubic Yard |  | 8
3453-222003 | A4 Structural Concrete | Material | Cubic Yard |  | 8
3453-222004 | Concrete All Class/Misc | Material | Lump Sum |  | 8
3453-224001 | Precast - DI Structure | Material | Each |  | 8
3453-224002 | Precast - EW Structure | Material | Each |  | 8
3453-224003 | Precast - SWM | Material | Each |  | 8
3453-224004 | Precast - MH | Material | Each |  | 8
3453-229001 | Rebar-Black/Incidentals | Material | LB |  | 8
3453-229002 | Rebar-MMFX | Material | LB |  | 8
3453-229003 | Rebar-Stainless | Material | LB |  | 8
3453-229004 | Rebar-Couplers | Material | Each |  | 8
3453-290001 | SS/WL Conflict-Dump Fee | Material | Lump Sum |  | 8
3453-290002 | Miscellanous | Material | Lump Sum |  | 8
3453-290003 | EPS 18" Thk | Material | Lump Sum |  | 8
3453-345008 | Haul By HR-Offsite/Waste | Material | Cubic Yard |  | 8
3453-345009 | Haul By HR-Lowboy/Trailer | Material | Hour |  | 8
3453-351001 | Haul By TN-Stone/Sand | Material | Ton |  | 8
3453-351002 | Haul By TN-Rip Rap | Material | Ton |  | 8
3453-354001 | Haul By HR-SS/WL Conflicts | Material | Cubic Yard |  | 8
3453-354002 | Haul By HR-Unsuitable/Undercut | Material | Cubic Yard |  | 8
3453-354004 | Haul By HR-Backup Shldr Fill | Material | Cubic Yard |  | 8
3453-354005 | Haul By HR-Demo/Boxout/Excav | Material | Cubic Yard |  | 8
3453-354006 | Haul By HR-Topsoil To Fill | Material | Cubic Yard |  | 8
3453-354007 | Haul By HR-Onsite Clay | Material | Cubic Yard |  | 8
3453-405101 | Install/Remove Attenuator | Material | Each |  | 8
3453-405102 | Install Sign / TY III | Material | Each |  | 8
3453-405201 | Set MB-7D Barrier | Material | Linear Feet |  | 8
3453-405202 | Remove MB-7D Barrier To Stock | Material | Linear Feet |  | 8
3453-405203 | Load MB-7D Onto Buyers Truck | Material | Linear Feet |  | 8
3453-410102 | Install Silt Fence | Material | Linear Feet |  | 8
3453-410103 | Dewatering/Storm Maint | Material | Lump Sum |  | 8
3453-410104 | Install Inlet Protection | Material | Each |  | 8
3453-410105 | Install Check Dam | Material | Each |  | 8
3453-410201 | Temp Sediment Trap/Stream Relo | Material | Cubic Yard |  | 8
3453-410202 | Instl/Muckout Temp Risr/Outlet | Material | Cubic Yard |  | 8
3453-415501 | SS Conflict | Material | Each |  | 8
3453-415502 | W/L Conflict | Material | Each |  | 8
3453-415503 | Test Pits | Material | Each |  | 8
3453-425201 | Temp Safety Fence | Material | Linear Feet |  | 8
3453-430201 | Const Entrance/Temp Drain | Material | Each |  | 8
3453-4304001 | Load Earth Excav | Material | Cubic Yard |  | 8
3453-4304002 | Self-Perform MOT | Material | Month |  | 8
3453-4304004 | Lane Haul Earth to Fill -1/2 M | Material | Cubic Yard |  | 8
3453-4304005 | Load Undercut | Material | Cubic Yard |  | 8
3453-4304009 | Place Earth Rdwy Emb | Material | Cubic Yard |  | 8
3453-4304013 | Load/Install Clay Liner | Material | Cubic Yard |  | 8
3453-4304016 | Dozer Exc Topsoil to Stock | Material | Cubic Yard |  | 8
3453-430801 | Hoe Ram Trench Near Utilities | Material | Cubic Yard |  | 8
3453-431601 | Excav/Fill Unsuit Blw SD Invrt | Material | Cubic Yard |  | 8
3453-431602 | Undercut Backfill | Material | Ton |  | 8
3453-432201 | Backup Shoulders Fill | Material | Linear Feet |  | 8
3453-432202 | FG SG Under Pavement | Material | Square Yard |  | 8
3453-432203 | FG Shldr/Sdwlk/Trail | Material | Square Yard |  | 8
3453-432204 | Haul Road Maint | Material | Hour |  | 8
3453-435301 | Spread/Compact CBR-30 | Material | Ton |  | 8
3453-435302 | F&I 4" Stone-Sdwlk/Curb | Material | Ton |  | 8
3453-435303 | Spread/Compact 21B Rdwy/Pond | Material | Ton |  | 8
3453-435401 | Cement Stabilized Base | Material | Ton |  | 8
3453-455401 | < 42" RCP-Bed/Plc/BF | Material | Linear Feet |  | 8
3453-455402 | Pipe Tie In | Material | Each |  | 8
3453-455404 | Flowfill/Pipe Abnd | Material | Linear Feet |  | 8
3453-455501 | => 42"RCP-Bed/Plc/BF | Material | Linear Feet |  | 8
3453-455701 | Drop Inlet/Invert | Material | Each |  | 8
3453-455702 | Drop Inlet-Excav/Instl DI/BF | Material | Each |  | 8
3453-455703 | Drop Inlet-Install Top | Material | Each |  | 8
3453-455704 | Excav/Install SMW-1 | Material | Each |  | 8
3453-455705 | Install End Section | Material | Each |  | 8
3453-455706 | Cl A3-Pour Endwall/Cradle | Material | Cubic Yard |  | 8
3453-455801 | Install MH/Frame/Cover | Material | Each |  | 8
3453-457401 | Install UD | Material | Linear Feet |  | 8
3453-457402 | Install CD | Material | Linear Feet |  | 8
3453-457501 | Cross Trench HMA Repair | Material | Ton |  | 8
3453-470601 | Bridges-Set Pile/Plc Concrete | Material | Each |  | 8
3453-4752021 | NSRR-Frm/Strp/Pour/Rub Abut | Material | Cubic Yard |  | 8
3453-4752022 | NSRR-Form/Strip Integral Abut | Material | Square Feet |  | 8
3453-4752023 | NSRR-Place Integral Abutment | Material | Cubic Yard |  | 8
3453-4752031 | Pkwy-Frm/Strp/Pour/Rub Abut | Material | Cubic Yard |  | 8
3453-4752032 | Pkwy-Form/Strip Integral Abut | Material | Square Feet |  | 8
3453-4752033 | Pkwy-Place Integral Abutment | Material | Cubic Yard |  | 8
3453-476401 | Inspect Bridges | Material | Day |  | 8
3453-4764020 | NSRR-Deck & SIP Crane Support | Material | Day |  | 8
3453-4764021 | NSRR-Form/Strip Deck Bulkheads | Material | Square Feet |  | 8
3453-4764022 | NSRR-Form/Strip Deck Edge | Material | Square Feet |  | 8
3453-4764023 | NSRR-Form/Strip Deck OH | Material | Square Feet |  | 8
3453-4764025 | NSRR-Temp Deck Shielding | Material | Square Feet |  | 8
3453-4764027 | NSRR-Set Rail & Dry Run | Material | Hour |  | 8
3453-4764028 | NSRR-Pour Deck/Sidewalk | Material | Cubic Yard |  | 8
3453-4764029 | NSRR-Cure/Rub Deck | Material | Square Feet |  | 8
3453-4764030 | Pkwy-Deck & SIP Crane Support | Material | Day |  | 8
3453-4764031 | Pkwy-Form/Strip Deck Bulkheads | Material | Square Feet |  | 8
3453-4764032 | Pkwy-Form/Strip Deck Edge | Material | Square Feet |  | 8
3453-4764033 | Pkwy-Form/Strip Deck OH | Material | Square Feet |  | 8
3453-4764035 | Pkwy-Temp Deck Shielding | Material | Square Feet |  | 8
3453-4764037 | Pkwy-Set Rail & Dry Run | Material | Hour |  | 8
3453-4764038 | Pkwy-Pour Deck | Material | Cubic Yard |  | 8
3453-4764039 | Pkwy-Cure/Rub Deck | Material | Square Feet |  | 8
3453-484501 | App Slab-Stone Base | Material | Ton |  | 8
3453-4845021 | NSRR-Form/Strip App/Sleep Slab | Material | Square Feet |  | 8
3453-4845022 | NSRR-Place App/Sleep Slab | Material | Cubic Yard |  | 8
3453-4845031 | Pkwy-Form/Strip App/Sleep Slab | Material | Square Feet |  | 8
3453-4845032 | Pkwy-Place App/Sleep Slab | Material | Cubic Yard |  | 8
3453-5172021 | NSRR-Excav MSE Level Pad | Material | Linear Feet |  | 8
3453-5172022 | NSRR-F/P/S MSE Top/Coping | Material | Linear Feet |  | 8
3453-5172023 | NSRR-Form/Pour MSE Level Pad | Material | Cubic Yard |  | 8
3453-5172024 | NSRR-Install MSE Panel | Material | Square Feet |  | 8
3453-5172025 | NSRR-Place Backfill | Material | Ton |  | 8
3453-5172031 | Pkwy-Excav MSE Level Pad | Material | Linear Feet |  | 8
3453-5172032 | Pkwy-F/P/S MSE Top/Coping | Material | Linear Feet |  | 8
3453-5172033 | Pkwy-Form/Pour MSE Level Pad | Material | Cubic Yard |  | 8
3453-5172034 | Pkwy-Install MSE Panel | Material | Square Feet |  | 8
3453-5172035 | Pkwy-Place Backfill | Material | Ton |  | 8
3453-5210011 | MB CPSR-Form/Strip | Material | Square Feet |  | 8
3453-5210012 | MB CPSR-Install Steel Rail | Material | Linear Feet |  | 8
3453-5210013 | MB CPSR-Place Concrete | Material | Cubic Yard |  | 8
3453-5210014 | Prep Barrier Subgrade | Material | Linear Feet |  | 8
3453-5210021 | NSRR-CPSR-Form/Strip | Material | Square Feet |  | 8
3453-5210022 | NSRR-CPSR-Install Steel Rail | Material | Linear Feet |  | 8
3453-5210023 | NSRR-CPSR-Place Concrete | Material | Cubic Yard |  | 8
3453-5210031 | Pkwy-CPSR-Form/Strip | Material | Square Feet |  | 8
3453-5210032 | Pkwy-CPSR-Install Steel Rail | Material | Linear Feet |  | 8
3453-5210033 | Pkwy-CPSR-Place Concrete | Material | Cubic Yard |  | 8
3453-525201 | Slurry Sub Support | Material | Each |  | 8
3453-541002 | NSRR-Erect Beams | Material | Each |  | 8
3453-541003 | Pkwy-Erect Beams | Material | Each |  | 8
3453 - Cost | 3453 - Cost Resources | Nonlabor |  |  | 1
UPC112815.CO009 | CO#09 - Betterment | Material | Unit |  | 8
UPC112815.CO011 | CO#11 - VA Eagle & Devlin Spur | Material | Unit |  | 8
UPC112815.COTBD | CO#TBD - To be assigned | Material | Unit |  | 8
9156-SA43 | SA#43 - Reduction in required soil stabilization classification testing | Material | Lump Sum |  | 8
9156-SA44 | SA#44 - Additional Septic Field Investigation | Material | Lump Sum |  | 8
3460 - LCost | KC Levee LANE Cost Resource | Nonlabor |  |  | 1
3460-302538 | CID EW - 77+43/ 105+00 Kis | Material |  |  | 1
3462 | 3462 - I-275 | Nonlabor |  |  | 1
3462 Revenue | 3462 - I-275 Revenue | Nonlabor |  |  | 1
3462-0101 1 | MOBILIZATION 43182125201 | Material | Lump Sum |  | 8
3462-0102 1 | MAINTENANCE OF TRAFFIC 43182125201 | Material | Lump Sum |  | 8
3462-0102 2200 | SPECIAL DETOUR- TEMP PAVEMENT 431821 | Material | Lump Sum |  | 8
3462-0102 2300 | SPECIAL DETOUR- TEMP EARTHWORK/BASE 431821 | Material | Lump Sum |  | 8
3462-0102 14 | TRAFFIC CONTROL OFFICER | Material | Hour |  | 8
3462-0102 30 23 | TEMPORARY HIGHWAY LIGHTING, PROJECT 4318 | Material | Lump Sum |  | 8
3462-0102 60 | WORK ZONE SIGN | Material | Lump Sum |  | 8
3462-0102 71 13 | TEMPORARY BARRIER, F&I, LOW PROFILE, CON | Material | Linear Feet |  | 8
3462-0102 71 15 | TEMPORARY BARRIER, F&I, ANCHORED | Material | Linear Feet |  | 8
3462-0102 71 16 | TEMPORARY BARRIER, F&I, FREE STANDING | Material | Linear Feet |  | 8
3462-0102 71 25 | TEMPORARY BARRIER, RELOCATE, ANCHORED | Material | Linear Feet |  | 8
3462-0102 71 26 | TEMPORARY BARRIER, RELOCATE, FREE STANDI | Material | Linear Feet |  | 8
3462-0102 74 1 | CHANNELIZING DEVICE- TYPES I, II, DI, VP | Material | Lump Sum |  | 8
3462-0102 74 8 | CHANNELIZING DEVICE- PEDESTRIAN LCD (LON | Material | Lump Sum |  | 8
3462-0102 76 | ARROW BOARD / ADVANCE WARNING ARROW PANE | Material | Lump Sum |  | 8
3462-0102 78 | TEMPORARY RAISED/RETROREFLECTIVE PAVEMEN | Material | Each |  | 8
3462-0102 89 1 | TEMPORARY CRASH CUSHION, REDIRECTIVE OPT | Material | Lump Sum |  | 8
3462-0102 99 | PORTABLE CHANGEABLE MESSAGE SIGN, TEMPOR | Material | Lump Sum |  | 8
3462-0102104 | TEMPORARY SIGNALIZATION AND MAINTENANCE, | Material | Lump Sum |  | 8
3462-0102107 1 | TEMPORARY TRAFFIC DETECTION AND MAINTENA | Material | Lump Sum |  | 8
3462-0102115 | TYPE III BARRICADE | Material | Lump Sum |  | 8
3462-0102150 1 | PORTABLE REGULATORY, SIGN | Material | Lump Sum |  | 8
3462-0102150 2 | RADAR SPEED DISPLAY UNIT | Material | Lump Sum |  | 8
3462-0104 10 3 | SEDIMENT BARRIER | Material | Linear Feet |  | 8
3462-0104 15 | SOIL TRACKING PREVENTION DEVICE | Material | Each |  | 8
3462-0104 18 | INLET PROTECTION SYSTEM | Material | Each |  | 8
3462-0107 1 | LITTER REMOVAL | Material | Acre |  | 8
3462-0107 2 | MOWING | Material | Acre |  | 8
3462-0108 1 | MONITOR EXISTING STRUCTURES- INSPECTION | Material | Lump Sum |  | 8
3462-0108 2 | MONITOR EXISTING STRUCTURES- VIBRATION | Material | Lump Sum |  | 8
3462-0110 1 1 | CLEARING & GRUBBING 43182125201 | Material | Lump Sum |  | 8
3462-0110 3 | REMOVAL OF EXISTING STRUCTURES/BRIDGES | Material | Lump Sum |  | 8
3462-0110 4 10 | REMOVAL OF EXISTING CONCRETE | Material | Square Yard |  | 8
3462-0110 21 | TREE PROTECTION BARRIER | Material | Linear Feet |  | 8
3462-0110 22 | TREE ROOT AND BRANCH PRUNING | Material | Each |  | 8
3462-0120 1 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3462-0120 6 | EMBANKMENT | Material | Cubic Yard |  | 8
3462-0160 4 | TYPE B STABILIZATION | Material | Square Yard |  | 8
3462-0285701 | OPTIONAL BASE, BASE GROUP 01 | Material | Square Yard |  | 8
3462-0285702 | OPTIONAL BASE, BASE GROUP 02 | Material | Square Yard |  | 8
3462-0285706 | OPTIONAL BASE, BASE GROUP 06 | Material | Square Yard |  | 8
3462-0285709 | OPTIONAL BASE, BASE GROUP 09 | Material | Square Yard |  | 8
3462-0327 70 6 | MILLING EXISTING ASPHALT PAVEMENT, 1 1/2 | Material | Square Yard |  | 8
3462-0334 1 12 | SUPERPAVE ASPHALTIC CONC, TRAFFIC B | Material | Ton |  | 8
3462-0337 7 83 | ASPHALT CONCRETE FRICTION COURSE,TRAFFIC | Material | Ton |  | 8
3462-0339 1 | MISCELLANEOUS ASPHALT PAVEMENT | Material | Ton |  | 8
3462-0350 3 7 | PLAIN CEMENT CONCRETE PAVEMENT, 9" | Material | Square Yard |  | 8
3462-0350 3 17 | PLAIN CEMENT CONCRETE PAVEMENT, 14" | Material | Square Yard |  | 8
3462-0350 5 | CLEANING & SEALING JOINTS- CONCRETE PAVE | Material | Linear Feet |  | 8
3462-0352 70 | GRINDING CONCRETE PAVEMENT | Material | Square Yard |  | 8
3462-0353 70 | CONCRETE PAVEMENT SLAB REPLACEMENT | Material | Cubic Yard |  | 8
3462-0400 0 11 | CONCRETE CLASS NS, GRAVITY WALL INDEX 40 | Material | Cubic Yard |  | 8
3462-0400 2 4 | CONC CLASS II, BRIDGE SUPERSTRUCTURE | Material | Cubic Yard |  | 8
3462-0400 2 10 | CONCRETE CLASS II, APPROACH SLABS | Material | Cubic Yard |  | 8
3462-0400 4 1 | CONCRETE CLASS IV CULVERTS | Material | Cubic Yard |  | 8
3462-0400 4 5 | CONCRETE CLASS IV, BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 8
3462-0400 4 11 | CONC CLASS IV, RETAINING WALLS | Material | Cubic Yard |  | 8
3462-0400 7 1 | BRIDGE DECK GROOVING | Material | Square Yard |  | 8
3462-0400 4 1 | CONCRETE CLASS IV CULVERTS | Material | Cubic Yard |  | 8
3462-0400143 | CLEANING & COATING CONCRETE SURFACE, CLA | Material | Square Feet |  | 8
3462-0400147 | COMPOSITE NEOPRENE PADS | Material | Cubic Feet |  | 8
3462-0415 1 1 | REINFORCING STEEL- ROADWAY | Material | LB |  | 8
3462-0415 1 3 | REINFORCING STEEL- RETAINING WALL | Material | LB |  | 8
3462-0415 1 4 | REINFORCING STEEL - BRIDGE SUPERSTRUCTUR | Material | LB |  | 8
3462-0415 1 5 | REINFORCING STEEL- BRIDGE SUBSTRUCTURE | Material | LB |  | 8
3462-0415 1 9 | REINFORCING STEEL- APPROACH SLABS | Material | LB |  | 8
3462-0425 1351 | INLETS, CURB, TYPE P-5, <10' | Material | Each |  | 8
3462-0425 1361 | INLETS, CURB, TYPE P-6, <10' | Material | Each |  | 8
3462-0425 1452 | INLETS, CURB, TYPE J-5, >10' | Material | Each |  | 8
3462-0425 1471 | INLETS, CURB, TYPE 7, <10' | Material | Each |  | 8
3462-0425 1521 | INLETS, DT BOT, TYPE C,<10' | Material | Each |  | 8
3462-0425 1529 | INLETS, DT BOT, TYPE C, MODIFY | Material | Each |  | 8
3462-0425 1541 | INLETS, DT BOT, TYPE D, <10' | Material | Each |  | 8
3462-0425 1543 | INLETS, DITCH BOTTOM, TYPE D, J BOT, <10 | Material | Each |  | 8
3462-0425 1701 | INLETS, GUTTER, TYPE S, <10' | Material | Each |  | 8
3462-0425 1781 | INLETS, MEDIAN BARRIER, TYPE 1, <=10' | Material | Each |  | 8
3462-0425 1783 | INLETS, MEDIAN BARRIER, TYPE 1, J BOT, < | Material | Each |  | 8
3462-0425 1790 | INLETS, MEDIAN BARRIER, TYPE 2, < =10' | Material | Each |  | 8
3462-0425 1792 | INLETS, MEDIAN BARRIER, TYPE 2, >10' | Material | Each |  | 8
3462-0425 1793 | INLETS, MEDIAN BARRIER, TYPE 2, J BOT, < | Material | Each |  | 8
3462-0425 1921 | INLETS, ADJACENT BARRIER, <=10' | Material | Each |  | 8
3462-0425 1922 | INLETS, ADJACENT BARRIER, >10' | Material | Each |  | 8
3462-0425 1923 | INLETS, ADJACENT BARRIER, J BOTTOM, < 10 | Material | Each |  | 8
3462-0425 1924 | INLETS, ADJACENT BARRIER, J BOTTOM, >10' | Material | Each |  | 8
3462-0425 2 61 | MANHOLES, P-8, <10' | Material | Each |  | 8
3462-0425 2 62 | MANHOLES, P-8, >10' | Material | Each |  | 8
3462-0425 2 63 | MANHOLES, P-8, PARTIAL | Material | Each |  | 8
3462-0425 2 91 | MANHOLES, J-8, <10' | Material | Each |  | 8
3462-0425 2 92 | MANHOLES, J-8, >10' | Material | Each |  | 8
3462-0430174124 | PIPE CULVERT, OPT MATERIAL, RND, 24" SD | Material | Linear Feet |  | 8
3462-0430174130 | PIPE CULVERT, OPT MATERIAL, RND, 30" SD | Material | Linear Feet |  | 8
3462-0430175112 | PIPE CULVERT, OPT MAT, RND, 12" S/CD | Material | Linear Feet |  | 8
3462-0430175115 | PIPE CULVERT, OPT MAT, RND, 15" S/CD | Material | Linear Feet |  | 8
3462-0430175118 | PIPE CULVERT, OPT MAT, RND, 18" S/CD | Material | Linear Feet |  | 8
3462-0430175124 | PIPE CULVERT, OPT MAT, RND, 24" S/CD | Material | Linear Feet |  | 8
3462-0430175130 | PIPE CULVERT, OPT MAT, RND, 30" S/CD | Material | Linear Feet |  | 8
3462-0430175136 | PIPE CULVERT, OPT MAT, RND, 36" S/CD | Material | Linear Feet |  | 8
3462-0430175142 | PIPE CULVERT, OPT MAT, RND, 42" S/CD | Material | Linear Feet |  | 8
3462-0430175148 | PIPE CULVERT, OPT MAT, RND, 48" S/CD | Material | Linear Feet |  | 8
3462-0430175218 | PIPE CULVERT,OPT MAT, OTHER-ELIP, 18" (14X23) | Material | Linear Feet |  | 8
3462-0430175236 | PIPE CULVERT, OPT MAT, OTHER-ELIPT, 36" (29X45) | Material | Linear Feet |  | 8
3462-0430185124 | PIPE CULVERT,OPT MAT, RND, 24" J&B | Material | Linear Feet |  | 8
3462-0430518102 | STRAIGHT CONCRETE ENDWALLS, 18", SINGLE, | Material | Each |  | 8
3462-0430524100 | STRAIGHT CONCRETE ENDWALLS, 24", SINGLE, | Material | Each |  | 8
3462-0430548100 | STRAIGHT CONCRETE ENDWALLS, 48", SINGLE, | Material | Each |  | 8
3462-0430611125 | U-ENDWALL WITH BAFFLES, INDEX 261/430-01 | Material | Each |  | 8
3462-0430611129 | U-ENDWALL WITH BAFFLES, INDEX 261/430-01 | Material | Each |  | 8
3462-0430611325 | U-ENDWALL WITH BAFFLES, INDEX 261/430-01 | Material | Each |  | 8
3462-0430830 | PIPE FILLING AND PLUGGING- PLACE OUT OF | Material | Cubic Yard |  | 8
3462-0430982125 | MITERED END SECTION, OPTIONAL ROUND, 18" | Material | Each |  | 8
3462-0430982133 | MITERED END SECTION, OPTIONAL ROUND, 30" | Material | Each |  | 8
3462-0430982625 | MITERED END SECTION, OPTIONAL - ELLIPTIC | Material | Each |  | 8
3462-0430982638 | MITERED END SECTION, OPTIONAL - ELLIPTIC | Material | Each |  | 8
3462-0430984129 | MITERED END SECTION, OPTIONAL ROUND, 24" | Material | Each |  | 8
3462-0430984133 | MITERED END SECTION , OPTIONAL ROUND, 30 | Material | Each |  | 8
3462-0440 1 50 | UNDERDRAIN, TYPE V | Material | Linear Feet |  | 8
3462-0440 70 | UNDERDRAIN INSPECTION BOX | Material | Each |  | 8
3462-0440 73 2 | UNDERDRAIN OUTLET PIPE, 6" | Material | Linear Feet |  | 8
3462-0446 1 1 | EDGEDRAIN DRAINCRETE, STANDARD | Material | Linear Feet |  | 8
3462-0446 71 1 | EDGEDRAIN OUTLET PIPE, 4" | Material | Linear Feet |  | 8
3462-0450 1 1 | PRESTRESSED BEAMS, TYPE II | Material | Linear Feet |  | 8
3462-0450 2 36 | PREST BEAMS: FLORIDA-I BEAM 36" | Material | Linear Feet |  | 8
3462-0451 70 | PREST SOIL ANCHORS | Material | Each |  | 8
3462-0451 70 1 | PRESTRESSED SOIL ANCHOR, PERFORMANCE TES | Material | Each |  | 8
3462-0451 70 2 | PRESTRESSED SOIL ANCHOR, CREEP TEST | Material | Each |  | 8
3462-0455 35 6 | STEEL PILING, HP 14 X 89 | Material | Linear Feet |  | 8
3462-0455 35113 | STEEL PILING, HP 14 X 89 WITH 100% DYNAM | Material | Linear Feet |  | 8
3462-0455 88 5 | DRILLED SHAFT, 48" DIA | Material | Linear Feet |  | 8
3462-0455107 5 | DRILLED SHAFT CASING, 48" DIAMETER | Material | Linear Feet |  | 8
3462-0455111 | CORE-PILOT HOLE, DRILLED SHAFT EXCAVATIO | Material | Linear Feet |  | 8
3462-0455122 5 | EXCAVATION UNCLASSIFIED SHAFT, 48" DIA | Material | Linear Feet |  | 8
3462-0455133 2 | SHEET PILING STEEL, TEMPORARY-CRITICAL | Material | Square Feet |  | 8
3462-0455147 1 | THERMAL INTEGRITY TESTING, UP TO 4' SHAF | Material | Each |  | 8
3462-0458 1 11 | BRIDGE DECK EXPANSION JOINT, NEW CONSTRU | Material | Linear Feet |  | 8
3462-0520 1 7 | CONCRETE CURB & GUTTER, TYPE E | Material | Linear Feet |  | 8
3462-0520 1 10 | CONCRETE CURB & GUTTER, TYPE F | Material | Linear Feet |  | 8
3462-0520 2 4 | CONCRETE CURB, TYPE D | Material | Linear Feet |  | 8
3462-0520 6 | SHOULDER GUTTER- CONCRETE | Material | Linear Feet |  | 8
3462-0520 7 1 | GRANITE CURB, FURNISH & INSTALL | Material | Linear Feet |  | 8
3462-0520 7 2 | GRANITE CURB, RESET | Material | Linear Feet |  | 8
3462-0520 70 | CONCRETE TRAFFIC SEPARATOR, SPECIAL- VAR | Material | Square Yard |  | 8
3462-0521 1 11 | MEDIAN CONCRETE BARRIER, 38" HEIGHT | Material | Linear Feet |  | 8
3462-0521 1 13 | MEDIAN CONCRETE BARRIER, TALL GRADE-SEPA | Material | Linear Feet |  | 8
3462-0521 1 14 | MEDIAN CONCRETE BARRIER, VARIABLE SECTIO | Material | Linear Feet |  | 8
3462-0521 5 13 | CONCRETE TRAFFIC RAILING- BRIDGE, 36" SI | Material | Linear Feet |  | 8
3462-0521 5 22 | CONCRETE TRAFFIC RAILING- BRIDGE, 8'-0" | Material | Linear Feet |  | 8
3462-0521 8 11 | CONCRETE BARRIER, WITH JUNCTION SLAB, 8' | Material | Linear Feet |  | 8
3462-0521 72 24 | SHOULDER CONCRETE BARRIER WALL, 8' NOISE | Material | Linear Feet |  | 8
3462-0521 72 27 | SHOULDER CONCRETE BARRIER WALL, 14' NOIS | Material | Linear Feet |  | 8
3462-0521 72 40 | SHOULDER CONCRETE BARRIER, 38" OR 44" HE | Material | Linear Feet |  | 8
3462-0521 72 43 | SHOULDER CONCRETE BARRIER, CURB AND GUTT | Material | Linear Feet |  | 8
3462-0522 1 | CONCRETE SIDEWALK AND DRIVEWAYS, 4" THIC | Material | Square Yard |  | 8
3462-0522 2 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THIC | Material | Square Yard |  | 8
3462-0524 1 2 | CONCRETE DITCH PAVEMENT, NON REINFORCED, | Material | Square Yard |  | 8
3462-0524 2 2 | CONCRETE SLOPE PAVEMENT,NON REINFORCED, | Material | Square Yard |  | 8
3462-0526 1 1 | PAVERS, ARCHITECTURAL, ROADWAY | Material | Square Yard |  | 8
3462-0527 2 | DETECTABLE WARNINGS | Material | Square Feet |  | 8
3462-0530 3 4 | RIPRAP, RUBBLE, F&I, DITCH LINING | Material | Ton |  | 8
3462-0536 1 1 | GUARDRAIL -ROADWAY, GENERAL TL-3 | Material | Linear Feet |  | 8
3462-0536 73 | GUARDRAIL REMOVAL | Material | Linear Feet |  | 8
3462-0536 85 20 | GUARDRAIL END TREATMENT- TRAILING ANCHOR | Material | Each |  | 8
3462-0536 85 24 | GUARDRAIL END TREATMENT- PARALLEL APPROA | Material | Each |  | 8
3462-0538 1 | GUARDRAIL RESET | Material | Linear Feet |  | 8
3462-0544 3 1 | CRASH CUSHION, TL-3, NARROW | Material | Each |  | 8
3462-0546 72 1 | GROUND-IN RUMBLE STRIPS, 16" | Material | Mile |  | 8
3462-0548 12 | RETAINING WALL SYSTEM, PERMANENT, EXCLUD | Material | Square Feet |  | 8
3462-0548 13 | RETAINING WALL SYSTEM,TEMPORARY, EXCLUDI | Material | Square Feet |  | 8
3462-0548 14 | RETAINING WALL SYS PERM-WIDEN ATTACH TO EXIST | Material | Square Feet |  | 8
3462-0550 10220 | FENCING, TYPE B, 5.1-6.0', STANDARD | Material | Linear Feet |  | 8
3462-0550 10222 | FENCING, TYPE B, 5.1-6.0, W/ VINYL COATI | Material | Linear Feet |  | 8
3462-0550 10236 | FENCING, TYPE B, 6.1-7.0', WITH VINYL CO | Material | Linear Feet |  | 8
3462-0550 10810 | FENCING, MESH WITH COATING, 4' ON GRAVIT | Material | Linear Feet |  | 8
3462-0550 10811 | FENCING, MESH WITH COATING, 6', PROJECT | Material | Linear Feet |  | 8
3462-0550 10813 | FENCING, MESH WITH COATING, 8', PROJECT | Material | Linear Feet |  | 8
3462-0550 60212 | FENCE GATE, TYPE B, SINGLE, 6.1 - 12.0' | Material | Each |  | 8
3462-0550 60612 | FENCE GATE, TYPE B VINYL, SINGLE, 6.1 - | Material | Each |  | 8
3462-0550 60622 | FENCE GATE, TYPE B WITH VINYL COATING, D | Material | Each |  | 8
3462-0550 60623 | FENCE GATE, TYPE B VINYL, DOUBLE, 12.1-1 | Material | Each |  | 8
3462-0550 60806 | FENCE GATE, 4' HEIGHT ON GRAVITY WALL, S | Material | Each |  | 8
3462-0550 60807 | FENCE GATE, 6' HEIGHT, DOUBLE, 9' OPENIN | Material | Each |  | 8
3462-0563 4 | ANTI-GRAFFITI COATING, NON-SACRIFICIAL | Material | Square Feet |  | 8
3462-0570 1 1 | PERFORMANCE TURF | Material | Square Yard |  | 8
3462-0571 1 11 | PLASTIC EROSION MAT, TURF REINFORCED MAT | Material | Square Yard |  | 8
3462-0630 2 11 | CONDUIT, FURNISH & INSTALL, OPEN TRENCH | Material | Linear Feet |  | 8
3462-0630 2 12 | CONDUIT, FURNISH & INSTALL, DIRECTIONAL | Material | Linear Feet |  | 8
3462-0630 2 14 | CONDUIT, FURNISH & INSTALL, ABOVEGROUND | Material | Linear Feet |  | 8
3462-0630 2 15 | CONDUIT, FURNISH & INSTALL, BRIDGE MOUNT | Material | Linear Feet |  | 8
3462-0630 2 16 | CONDUIT, FURNISH & INSTALL, EMBEDDED CON | Material | Linear Feet |  | 8
3462-0630 2 65 | CONDUIT, REMOVE, BRIDGE MOUNT | Material | Linear Feet |  | 8
3462-0633 1121 | FIBER OPTIC CABLE, F&I, UGROUND,2-12 | Material | Linear Feet |  | 8
3462-0633 1124 | FIBER OPTIC CABLE, F&I, UGROUND, 97-144 | Material | Linear Feet |  | 8
3462-0633 1320 | FIBER OPTIC CABLE, INSTALL, UNDERGROUND | Material | Linear Feet |  | 8
3462-0633 1620 | FIBER OPTIC CABLE, REMOVE, UNDERGROUND | Material | Linear Feet |  | 8
3462-0633 2 31 | FIBER OPTIC CONNECTION, INSTALL, SPLICE | Material | Each |  | 8
3462-0633 3 11 | FIBER OPTIC CONNECTION HDW SPLICE ENCLOS | Material | Each |  | 8
3462-0633 3 12 | FIBER OPTIC CONNECTION HDW SPLICE TRAY | Material | Each |  | 8
3462-0633 3 15 | FIBER OPTIC CONNECTION HDW PREDETERM | Material | Each |  | 8
3462-0633 8 1 | MULTI-CONDUCTOR COMMUNICATION CABLE, FUR | Material | Linear Feet |  | 8
3462-0635 2 11 | PULL & SPLICE BOX, F&I, 13" X 24" COVER | Material | Each |  | 8
3462-0635 2 12 | PULL & SPLICE BOX, F&I, 24" X 36" COVER | Material | Each |  | 8
3462-0635 2 13 | PULL & SPLICE BOX, F&I, 30" X 60" RECTAN | Material | Each |  | 8
3462-0635 3 11 | JUNCTION BOX, FURNISH & INSTALL, AERIAL | Material | Each |  | 8
3462-0635 3 13 | JUNCTION BOX, FURNISH & INSTALL, EMBEDDE | Material | Each |  | 8
3462-0639 1122 | ELECTRICAL POWER SERVICE, F&I, UNDERGROU | Material | Each |  | 8
3462-0639 1610 | ELECTRICAL POWER SERVICE, REMOVE OVERHEA | Material | Each |  | 8
3462-0639 2 1 | ELECTRICAL SERVICE WIRE, FURNISH & INSTA | Material | Linear Feet |  | 8
3462-0639 2 6 | ELECTRICAL SERVICE WIRE, REMOVE | Material | Linear Feet |  | 8
3462-0639 3 11 | ELECTRICAL SERVICE DISCONNECT, F&I, POLE | Material | Each |  | 8
3462-0639 5 25 | EMERGENCY GENERATOR- PERMANENT UP TO 25 | Material | Each |  | 8
3462-0639 6 1 | ELECTRICAL POWER SERVICE- TRANSFORMER FU | Material | Each |  | 8
3462-0641 2 12 | PRESTRESSED CONCRETE POLE, TYPE P-I SERVICE | Material | Each |  | 8
3462-0641 2 13 | PRESTRESSED CONCRETE POLE, TYPE P-III | Material | Each |  | 8
3462-0641 2 60 | PRESTRESSED CONC POLE, COMPLETE REMOVAL | Material | Each |  | 8
3462-0641 3175 | CONCRETE CCTV POLE, LOWERING 75' | Material | Each |  | 8
3462-0641 3186 | CONCRETE CCTV POLE, LOWERING 86' | Material | Each |  | 8
3462-0649 2605 | STEEL CCTV POLE, REMOVE POLE- COMPLETE/D | Material | Each |  | 8
3462-0660 3 11 | VEHICLE DETECTION SYSTEM- MICROWAVE, CABINET EQP | Material | Each |  | 8
3462-0660 3 12 | VEHICLE DETECTION SYSTEM- MICROWAVE, ABOVE GRD | Material | Each |  | 8
3462-0660 3 60 | VEHICLE DETECTION SYSTEM - MICROWAVE, REMOVE | Material | Each |  | 8
3462-0660 7 11 | VEHICLE DETECTION SYSTEM- WRONG WAY FOR | Material | Each |  | 8
3462-0676 2122 | ITS CABINET, FURNISH & INSTALL, POLE W SHIELD | Material | Each |  | 8
3462-0676 2143 | ITS CABINET, FURNISH & INSTALL, BASE MOUNT | Material | Each |  | 8
3462-0676 2600 | ITS CABINET- REMOVE | Material | Each |  | 8
3462-0682 1113 | ITS CCTV CAMERA, F&I, DOME PTZ ENCLOSUR | Material | Each |  | 8
3462-0684 1 1 | MANAGED FIELD ETHERNET SWITCH, FURNISH & | Material | Each |  | 8
3462-0684 2 1 | DEVICE SERVER, FURNISH & INSTALL | Material | Each |  | 8
3462-0684 6 40 | WIRELESS COMMUNICATION DEVICE, RELOCATE | Material | Each |  | 8
3462-0685 1 11 | UNINTERRUPTIBLE POWER SUPPLY, LINE INTERACTIVE | Material | Each |  | 8
3462-0685 2 1 | REMOTE POWER MANAGEMENT UNIT- RPMU, FURN | Material | Each |  | 8
3462-0695 1 1 | TRAFFIC MONITORING SITE VEHICLE SENSOR-N | Material | Each |  | 8
3462-0695 6 12 | TRAFFIC MONITORING SITE INDUCTIVE LOOP A | Material | Each |  | 8
3462-0695 7162 | TRAFFIC MONITORING SITE CABINET, F&I, TY | Material | Each |  | 8
3462-0695 7600 | TRAFFIC MONITORING SITE CABINET, REMOVE | Material | Each |  | 8
3462-0700 1 11 | SINGLE POST SIGN, F&I GROUND MOUNT, UP T | Material | Each |  | 8
3462-0700 1 12 | SINGLE POST SIGN, F&I GROUND MOUNT, 12-2 | Material | Each |  | 8
3462-0700 1 14 | SINGLE POST SIGN, F&I GROUND MOUNT, 31+ | Material | Each |  | 8
3462-0700 1 22 | SINGLE POST SIGN, F&I BARRIER MT 12-20 SF | Material | Each |  | 8
3462-0700 1 31 | SINGLE POST SIGN, F&I BRIDGE MT UP TO 12 SF | Material | Each |  | 8
3462-0700 1 32 | SINGLE POST SIGN, F&I BRIDGE MT 12-20 SF | Material | Each |  | 8
3462-0700 1 60 | SINGLE POST SIGN, REMOVE | Material | Each |  | 8
3462-0700 1 74 | SINGLE POST SIGN, F&I CUSTOM, 31+ SF | Material | Each |  | 8
3462-0700 2 14 | MULTI- POST SIGN, F&I GROUND MT 31-50 | Material | Each |  | 8
3462-0700 2 18 | MULTI- POST SIGN, F&I GROUND MT 301-400 | Material | Each |  | 8
3462-0700 2 50 | MULTI- POST SIGN, GROUND MOUNT, RELOCAT | Material | Each |  | 8
3462-0700 2 60 | MULTI- POST SIGN, REMOVE | Material | Each |  | 8
3462-0700 3201 | SIGN PANEL, OH MTD UP TO 12 | Material | Each |  | 8
3462-0700 3203 | SIGN PANEL, OH MTD 21-31 SF | Material | Each |  | 8
3462-0700 3205 | SIGN PANEL, OH MTD 51-100 SF | Material | Each |  | 8
3462-0700 3206 | SIGN PANEL, OH MTD 101-200 SF | Material | Each |  | 8
3462-0700 3207 | SIGN PANEL, OH MTD 201-300 SF | Material | Each |  | 8
3462-0700 3208 | SIGN PANEL, OH MTD 301-400 SF | Material | Each |  | 8
3462-0700 3302 | SIGN PANEL, SINGLE POST BRIDGE MTD | Material | Each |  | 8
3462-0700 3601 | SIGN PANEL, REMOVE, UP TO 12 SF | Material | Each |  | 8
3462-0700 3602 | SIGN PANEL, REMOVE, 12-20 SF | Material | Each |  | 8
3462-0700 3603 | SIGN PANEL, REMOVE, 21-30 SF | Material | Each |  | 8
3462-0700 3604 | SIGN PANEL, REMOVE, 31-50 SF | Material | Each |  | 8
3462-0700 3605 | SIGN PANEL, REMOVE, 51-100 SF | Material | Each |  | 8
3462-0700 3606 | SIGN PANEL, REMOVE, 101-200 SF | Material | Each |  | 8
3462-0700 3607 | SIGN PANEL, REMOVE, 201-300 SF | Material | Each |  | 8
3462-0700 4131 | OVERHEAD STATIC SIGN STRUCTURE, UP TO 20 SF | Material | Each |  | 8
3462-0700 4133 | OVERHEAD STATIC SIGN STRUCTURE, 31-40 SF | Material | Each |  | 8
3462-0700 4134 | OVERHEAD STATIC SIGN STRUCTURE, 41-50 SF | Material | Each |  | 8
3462-0700 4135 | OVERHEAD STATIC SIGN STRUCTURE, 51-100 SF | Material | Each |  | 8
3462-0700 4136 | OVERHEAD STATIC SIGN STRUCTURE, 101-150 SF | Material | Each |  | 8
3462-0700 4137 | OVERHEAD STATIC SIGN STRUCTURE, 151-200 SF | Material | Each |  | 8
3462-0700 4140 | OVERHEAD STATIC SIGN STRUCTURE, BRIDGE MTD | Material | Each |  | 8
3462-0700 4630 | OVERHEAD STATIC SIGN, REMOVE MONOTUBE | Material | Each |  | 8
3462-0700 4640 | OVERHEAD STATIC SIGN, REMOVE BRIDGE MTD | Material | Each |  | 8
3462-0700 6 11 | HIGHLIGHTED SIGN, F&I GROUND MOUNT- AC P | Material | Each |  | 8
3462-0700 9137 | WALK-IN DYNAMIC MESSAGE SIGN, UPS COLOR 201-300 SF | Material | Each |  | 8
3462-0700 9600 | WALK-IN DYNAMIC MESSAGE SIGN, REMOVE | Material | Each |  | 8
3462-0700 13 12 | RETROREFLECTIVE SIGN STRIP- FURNISH AND | Material | Each |  | 8
3462-0701 17101 | PROFILED THERMOPLASTIC, CONC WH 6" SOLID | Material | Mile |  | 8
3462-0701 17201 | PROFILED THERMOPLASTIC,CONC YL 6" SOLID | Material | Mile |  | 8
3462-0705 10 3 | OBJECT MARKER, TYPE 3 | Material | Each |  | 8
3462-0710 11101 | PAINTED PAVEMENT MARKINGS, WH SOLID 6" | Material | Mile |  | 8
3462-0710 11102 | PAINTED PAVEMENT MARKINGS, WH 8" | Material | Mile |  | 8
3462-0710 11103 | PAINTED PAVEMENT MARKINGS, WH 12" | Material | Mile |  | 8
3462-0710 11124 | PAINTED PAVEMENT MARKINGS, WH 18" | Material | Linear Feet |  | 8
3462-0710 11125 | PAINTED PAVEMENT MARKINGS, WH 24" | Material | Linear Feet |  | 8
3462-0710 11131 | PAINTED PAVEMENT MARKINGS, WH SKIP | Material | Mile |  | 8
3462-0710 11133 | PAINTED PAVEMENT MARKING, WH 12' PLAZA | Material | Mile |  | 8
3462-0710 11160 | PAINTED PAVEMENT MARKINGS, WH MESSAGE | Material | Each |  | 8
3462-0710 11170 | PAINTED PAVEMENT MARKINGS, WH ARROWS | Material | Each |  | 8
3462-0710 11201 | PAINTED PAVEMENT MARKINGS, YL SOLID 6" | Material | Mile |  | 8
3462-0710 11202 | PAINTED PAVEMENT MARKINGS, YL 8" | Material | Mile |  | 8
3462-0710 11224 | PAINTED PAVEMENT MARKINGS, YL 18" | Material | Linear Feet |  | 8
3462-0710 11331 | PAINTED PAVEMENT MARKINGS, BLK 6" | Material | Mile |  | 8
3462-0710 11333 | PAINTED PAVEMENT MARKING, BLK 12" PLAZA | Material | Mile |  | 8
3462-0710 90 | PAINTED PAVEMENT MARKINGS, FINAL SURFACE | Material | Lump Sum |  | 8
3462-0711 11102 | THERMOPLASTIC, STANDARD, WH, SOLID, 8" | Material | Mile |  | 8
3462-0711 11103 | THERMOPLASTIC, STANDARD, WH, SOLID, 12" INTER | Material | Mile |  | 8
3462-0711 11123 | THERMOPLASTIC, STANDARD, WH SOLID 12" CROSS | Material | Linear Feet |  | 8
3462-0711 11124 | THERMOPLASTIC, STANDARD, WH, 18" DIAG | Material | Linear Feet |  | 8
3462-0711 11125 | THERMOPLASTIC, STANDARD, WH, SOLID, 24" | Material | Linear Feet |  | 8
3462-0711 11170 | THERMOPLASTIC, STANDARD, WHITE, ARROW | Material | Each |  | 8
3462-0711 11224 | THERMOPLASTIC, STANDARD, YL SOLID 18" | Material | Linear Feet |  | 8
3462-0711 14125 | THERMOPLASTIC, PREFORMED, WH 24" | Material | Linear Feet |  | 8
3462-0711 14560 | THERMOPLASTIC, PREFORMED, WHITE WITH BLA | Material | Each |  | 8
3462-0711 14570 | THERMOPLASTIC, PREFORMED, WHITE WITH BLA | Material | Each |  | 8
3462-0711 16101 | THERMOPLASTIC, STANDARD-OTHER WH 6" SOLID | Material | Mile |  | 8
3462-0711 16102 | THERMOPLASTIC, STANDARD-OTHER WH 8" SOLID | Material | Mile |  | 8
3462-0711 16131 | THERMOPLASTIC, STANDARD-OTHER WH SKIP | Material | Mile |  | 8
3462-0711 16201 | THERMOPLASTIC, STANDARD-OTHER YL 6" SOLID | Material | Mile |  | 8
3462-0713103101 | PERMANENT TAPE, WHITE, SOLID, 6" FOR BRIDGE | Material | Mile |  | 8
3462-0713103103 | PERMANENT TAPE, WHITE, SOLID DROP 12" | Material | Mile |  | 8
3462-0713103131 | PERMANENT TAPE, WHITE, SKIP/DOTTED, 6" F | Material | Mile |  | 8
3462-0713103133 | PERMANENT TAPE, WHITE, SKIP, 12" WIDE 3' | Material | Mile |  | 8
3462-0713103201 | PERMANENT TAPE, YELLOW, SOLID, 6" FOR CO | Material | Mile |  | 8
3462-0713103331 | PERMANENT TAPE, BLACK, SKIP/DOTTED, 6" F | Material | Mile |  | 8
3462-0713103333 | PERMANENT TAPE, BLACK, 3'-9' DROP LANE, | Material | Mile |  | 8
3462-0715 1 11 | LIGHTING CONDUCTORSINSULATED, NO. 10 | Material | Linear Feet |  | 8
3462-0715 1 12 | LIGHTING CONDUCTORS, INSULATED, NO.8-6 | Material | Linear Feet |  | 8
3462-0715 1 13 | LIGHTING CONDUCTORS, INSULATED, NO4-2 | Material | Linear Feet |  | 8
3462-0715 1 60 | LIGHTING CONDUCTORS, REMOVE & DISPOSE, C | Material | Linear Feet |  | 8
3462-0715 4 15 | LIGHT POLE COMPLETE, 50' HEIGHT | Material | Each |  | 8
3462-0715 4 25 | LIGHT POLE COMPLETE, SPECIAL 50' | Material | Each |  | 8
3462-0715 4 70 | LIGHT POLE COMPLETE, REMOVE POLE AND FOU | Material | Each |  | 8
3462-0715 5 51 | LUMINAIRE & BRACKET ARM, REMOVE LUMINAIR | Material | Each |  | 8
3462-0715 7 11 | LOAD CENTER, F&I, SECONDARY VOLTAGE | Material | Each |  | 8
3462-0715 11125 | LUMINAIRE, F&I, UNDER DECK, WALL MOUNT | Material | Each |  | 8
3462-0715 11213 | LUMINAIRE, F&I- REPLACE EXISTING LUMINAI | Material | Each |  | 8
3462-0715 11500 | LUMINAIRE, REMOVE | Material | Each |  | 8
3462-0715500 1 | POLE CABLE DISTRIBUTION SYSTEM, CONVENT | Material | Each |  | 8
3462-0715500 3 | POLE CABLE DISTRIBUTION SYSTEM, WALL MOU | Material | Each |  | 8
3462-0715516150 | LIGHT POLE COMPLETE- SPECIAL DESIGN, 50' TOP | Material | Each |  | 8
3418-0368 | 3418-0368 - Deletion of MSE Wall/Regrading & Paving on Gibbons Road | Material | Lump Sum |  | 8
3453-115101 | Foreman Bonus Pay | Material | Hour |  | 8
3453-115102 | Holiday Pay | Material | Day |  | 8
3453-354003 | Haul By HR-Undercut | Material | Cubic Yard |  | 8
3453-410101 | Erosion Control Maintenance | Material | Month |  | 8
3453-4304003 | Demo-Hoe Ram Concrete | Material | Cubic Yard |  | 8
3453-4304007 | Load Rock Exc | Material | Cubic Yard |  | 8
3453-4304008 | Lane Haul Rock to Fill-1/2 M | Material | Cubic Yard |  | 8
3453-4304010 | Plc Ucut/Unsuit In Waste Area | Material | Cubic Yard |  | 8
3453-4304011 | Place Rock Rdwy Emb | Material | Cubic Yard |  | 8
3453-4304012 | Excavate for Biofilter | Material | Cubic Yard |  | 8
3453-4304014 | Wlngtn to Wlngfrd-Ld/Haul Earth | Material | Cubic Yard |  | 8
3453-4304015 | Wlngtn to Wlngfrd-Ld/Haul Rock | Material | Cubic Yard |  | 8
3453-432205 | Place Earth Rdwy Emb | Material | Cubic Yard |  | 8
3453-432206 | RG Slopes/Green Areas | Material | Square Yard |  | 8
3453-455403 | Move Pipes/Structures | Material | Month |  | 8
3453-455405 | Repair Exist. Pipe | Material | Each |  | 8
3453-5210026 | B666 Fence Post Install | Material | Each |  | 8
EW-RIPRAP | Stone Rip Rap Crew | Labor |  |  | 1
SUB-ST-SHTPILE | Sub - Sheet Pile Crew | Labor |  |  | 1
ST-SHTPILE | Sheet Pile Crew | Labor |  |  | 1
9161 - Materials | C-43 - Materials | Nonlabor |  |  | 1
9161 - FDOT SAND | FDOT SAND | Material | Ton |  | 8
9161 - SHELL ROCK | SHELL ROCK | Material | Ton |  | 8
9161 - #89 | #89 Stone | Material | Ton |  | 8
9161 - #57 | #57 Stone | Material | Ton |  | 8
9161 - RR-B Lime | Rip Rap B - Limestone | Material | Ton |  | 8
9161 - #3 Lime | Bedding Stone - #3 Limestone | Material | Ton |  | 8
9161 - RR Granite | Rip Rap B& C Granite | Material | Ton |  | 8
9161 - #3 Granite | Bedding Stone - #3 Granite | Material | Ton |  | 8
9161 - Geotextile | Geotextile Material | Material |  |  | 8
9161 - 24" RCP | 24" RCP | Material | Linear Feet |  | 8
9161 - 12" PVC | 12" PVC | Material | Linear Feet |  | 8
9161 - 6" PVC | 6" PVC | Material | Linear Feet |  | 8
9161 - 18" slotted | 18" Slotted PVC | Material | Linear Feet |  | 8
3460 - Conc | 3460 Concrete Material | Material |  |  | 1
3460 Mat'l | 3460 Material Resources | Material |  |  | 8
3418-0015 | 3418-0015 - Off-Duty Law Enforcement Officers - CO #16 | Material | Hour |  | 8
3418-0335 | 3418-0335 - Wet Util Relocation for Town of Blacksburg MOA 2 - CO #17 | Material | Lump Sum |  | 8
3460 - COST - | KC Levee Cost Resource | Labor |  |  | 1
3460 - REV | KC Levee Revenue | Material |  |  | 1
UPC112815.CO012 | CO#12 - Merrifield Garden Additions | Material | Unit |  | 8
3418-0369 | 3418-0369 - Traffic Control for Emergency Median Wall Repair on I-77 - CO | Material | Lump Sum |  | 8
3418-0371 | 3418-0371 - Mobilization for Emergency Median Wall Repair on I-77 - CO | Material | Lump Sum |  | 8
3418-0373 | 3418-0373 - Maint Repair of Jersey TY 2 w/ glare median wall on I-77 - CO | Material | Linear Feet |  | 8
3460-0001 | 01-ARG-Site Prep/Demo/Restore | Material | Lump Sum |  | 8
3460-4251011 | ARG-Clearing & Grubbing | Material | Acre |  | 8
3460-4251012 | ARG-Mulching / Mowing | Material | Acre |  | 8
3460-4568011 | ARG-Rmv/Stkpl Exist Rip Rap | Material | Cubic Yard |  | 8
3460-45680111 | ARG-Load Existing Rip Rap | Material | Cubic Yard |  | 8
3460-45680112 | ARG-Haul Exist Rip Rap to Scrn | Material | Cubic Yard |  | 8
3460-4312011 | ARG-Strip Topsoil | Material | Cubic Yard |  | 8
3460-43120111 | ARG-Strip/Haul Topsl 1500' | Material | Cubic Yard |  | 8
3460-43120112 | ARG-Dozer Exc Topsoil to Stock | Material | Cubic Yard |  | 8
3460-4306011 | ARG-Remove Aggregate Surfacing | Material | Cubic Yard |  | 8
3460-43060111 | ARG-Haul Agg Surf to Stockpile | Material | Cubic Yard |  | 8
3460-43060112 | ARG-Remove Aggregate Surfacing | Material | Cubic Yard |  | 8
3460-4306012 | ARG-Demo Gravel Parking Lot | Material | Square Yard |  | 8
3460-4202011 | ARG-Demo Concrete Parking Lot | Material | Square Yard |  | 8
3460-4205011 | ARG-Remove Grouted Riprap | Material | Cubic Yard |  | 8
3460-4205012 | ARG-Demo Strong Ave Pump Stn | Material | Lump Sum |  | 8
3460-4203011 | ARG-Demo Existing Buildings | Material | Each |  | 8
3460-4205013 | ARG-Demo Concrete Wall | Material | Cubic Yard |  | 8
3460-4205014 | ARG-Demo Stackbl Conc Blk Wall | Material | Square Feet |  | 8
3460-4208011 | ARG-Remove Existing Fence | Material | Linear Feet |  | 8
3460-4208012 | ARG-Rmv/Rplc Clearance Sgn/Pst | Material | Each |  | 8
3460-4208013 | ARG-Rmv Exist Freeboard Gauge | Material | Each |  | 8
3460-4209011 | ARG-Remove Existing Pipe | Material | Linear Feet |  | 8
3460-4206011 | ARG-Rmv Drainage/Culv/Sewer | Material | Linear Feet |  | 8
3460-42090112 | ARG-Rmv Gas/Com/Pwr/CATV | Material | Linear Feet |  | 8
3460-4205015 | ARG-Demo Misc Utility Struct | Material | Each |  | 8
3460-4100011 | ARG-E&S Controls | Material | Lump Sum |  | 8
3460-4101011 | ARG-Remove Silt Fence | Material | Linear Feet |  | 8
3460-4102011 | ARG-Plc E&S-Silt/Mat/Inlet/Dam | Material | Linear Feet |  | 8
3460-4103011 | ARG-Temp Seeding | Material | Square Yard |  | 8
3460-4314011 | ARG-Place 6" Topsoil | Material | Square Yard |  | 8
3460-43140111 | ARG-Purchase Topsoil | Material | Cubic Yard |  | 8
3460-43140112 | ARG-Load Topsoil | Material | Cubic Yard |  | 8
3460-43140113 | ARG-Haul Topsoil 1500 Ft | Material | Cubic Yard |  | 8
3460-43140114 | ARG-Plc/Finish Topsoil | Material | Square Yard |  | 8
3460-4253011 | ARG-6' Chain Link Fence | Material | Linear Feet |  | 8
3460-4253012 | ARG-Gate | Material | Each |  | 8
3460-8940011 | ARG-Temporary Signal | Material | Month |  | 8
3460-4258011 | ARG-Seeding | Material | Square Yard |  | 8
3460-0002 | 02-ARG-Levee Improve | Material | Lump Sum |  | 8
3460-4324011 | ARG-Prep Fill Area | Material | Square Yard |  | 8
3460-43240111 | ARG-Prep Embankment Area | Material | Square Yard |  | 8
3460-43240112 | ARG-Haul Fill | Material | Cubic Yard |  | 8
3460-4304011 | ARG-On Site Cut & Fill | Material | Cubic Yard |  | 8
3460-43040111 | ARG-On Site Cuts | Material | Cubic Yard |  | 8
3460-43040112 | ARG-On Site Cut-40 Tn Trk Haul | Material | Cubic Yard |  | 8
3460-43040113 | ARG-Place Fill | Material | Cubic Yard |  | 8
3460-4322011 | ARG-Pervious Fill | Material | Cubic Yard |  | 8
3460-4322012 | ARG-Plc Pervious Fill Material | Material | Cubic Yard |  | 8
3460-4320011 | ARG-Levee Random Fill | Material | Cubic Yard |  | 8
3460-43200111 | ARG-Place Random/UBF | Material | Cubic Yard |  | 8
3460-43200112 | ARG-Haul Random/UBF | Material | Cubic Yard |  | 8
3460-4322013 | ARG-Impervious Fill | Material | Cubic Yard |  | 8
3460-43220131 | ARG-Place Impervious Fill | Material | Cubic Yard |  | 8
3460-43220132 | ARG-Haul Impervious Fill | Material | Cubic Yard |  | 8
3460-4306013 | ARG-Agg Surfacing-Complete | Material | Square Yard |  | 8
3460-4334011 | ARG-Furnish & Install Geotext | Material | Square Yard |  | 8
3460-6020011 | ARG-6" Conc Overtopping w/FG | Material | Square Yard |  | 8
3460-4054011 | ARG-F&I Freeboard Gage | Material | Each |  | 8
3460-0003 | 03-ARG-Floodwall Improve | Material | Lump Sum |  | 8
3460-4701011 | ARG-Fldwl-Exc/Truck to Stkpl | Material | Cubic Yard |  | 8
3460-4702011 | ARG-Fldwl-Backfill | Material | Cubic Yard |  | 8
3460-47020111 | ARG-Fldwl-Place/Compact Bkfl | Material | Cubic Yard |  | 8
3460-47020112 | ARG-Fldwl-Load/Truck Bkfl | Material | Cubic Yard |  | 8
3460-4656011 | ARG-Fldwl-SOE-Trench Box | Material | Linear Feet |  | 8
3460-4655011 | ARG-Fldwl-Sht Pile Cap | Material | Cubic Yard |  | 8
3460-46550111 | ARG-Fldwl-Sht Pile Cap-F/S | Material | Square Feet |  | 8
3460-46550112 | ARG-Fldwl-Sht Pile Cap-Pour | Material | Cubic Yard |  | 8
3460-5151011 | ARG-Fldwl-Footng Concrete | Material | Cubic Yard |  | 8
3460-51510111 | ARG-Fldwl-Footng Mtl | Material | Square Feet |  | 8
3460-4703011 | ARG-Fldwl-Footng-FG & F/S CLSM | Material | Square Feet |  | 8
3460-51510112 | ARG-Fldwl-Footng Pour CLSM | Material | Cubic Yard |  | 8
3460-51510113 | ARG-Fldwl-Footng F/S Base/Heel | Material | Square Feet |  | 8
3460-51510114 | ARG-Fldwl-Footng-Pour Concrete | Material | Cubic Yard |  | 8
3460-5151012 | ARG-Fldwl-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510121 | ARG-Fldwl-Wall Mtl | Material | Square Feet |  | 8
3460-51510122 | ARG-Fldwl-F/S Stem w/Crane | Material | Square Feet |  | 8
3460-51510123 | ARG-Fldwl-Pour/Cure Stem Conc | Material | Cubic Yard |  | 8
3460-51510124 | ARG-Fldwl-F/S I-Wall w/Shr Std | Material | Square Feet |  | 8
3460-51510125 | ARG-Fldwl-Pour I-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510126 | ARG-Fldwl-Patch / Point Stems | Material | Square Feet |  | 8
3460-5351011 | ARG-Reinforcing Steel | Material | LB |  | 8
3460-53510111 | ARG-Fldwl-Rebar Mtl | Material | LB |  | 8
3460-53510112 | ARG-Fldwl-F&I Rebar ARG0003 | Material | LB |  | 8
3460-5353011 | ARG-Fldwl-Rebar-Crane Support | Material | LB |  | 8
3460-4706011 | ARG-H-Piles | Material | Linear Feet |  | 8
3460-47060111 | ARG-Buy Stl H-Piles | Material | Linear Feet |  | 8
3460-47060112 | ARG-Plc H-Pile-Complete w/Sub | Material | Linear Feet |  | 8
3460-4655012 | ARG-Sheetpiles | Material | Square Feet |  | 8
3460-46550121 | ARG-Buy Stl SSP | Material | Square Feet |  | 8
3460-46550122 | ARG-Instl SSP Complete | Material | Square Feet |  | 8
3460-4655013 | ARG-Sheetpiles-Low Headroom | Material | Square Feet |  | 8
3460-46550131 | ARG-Buy Stl SSP-Low Headroom | Material | Square Feet |  | 8
3460-46550132 | ARG-Instl SSP-Low Hdrm-Complet | Material | Square Feet |  | 8
3460-4205016 | ARG-Demo Existing Floodwall | Material | Cubic Yard |  | 8
3460-0004 | 04-ARG-Relief Well Improve | Material | Lump Sum |  | 8
3460-4554011 | ARG-Relief Well-12" Dia. RCP | Material | Linear Feet |  | 8
3460-45540111 | ARG-Relief Well-RCP Materials | Material | Linear Feet |  | 8
3460-45540112 | ARG-Relief Well-ELB 12" RCP | Material | Linear Feet |  | 8
3460-45540113 | ARG-Relief Well-ELB 18" 5-10' | Material | Linear Feet |  | 8
3460-45540114 | ARG-Relief Well-ELB 18" 10-15' | Material | Linear Feet |  | 8
3460-4565011 | ARG-Relief Well-Manholes | Material | Each |  | 8
3460-4561011 | ARG-Relief Well-C.I.P. Boxes | Material | Each |  | 8
3460-45610111 | ARG-Relief Well-6' x 6 Jct Box | Material | Each |  | 8
3460-6030011 | ARG-Relief Well-12-24" Gate | Material | Each |  | 8
3460-4554012 | ARG-Relief Well-Sub | Material | Each |  | 8
3460-0005 | 05-ARG-Gatewell/Pump Stn Imprv | Material | Lump Sum |  | 8
3460-5110011 | ARG-Gatewell Extension Conc | Material | Each |  | 8
3460-8990011 | ARG-Electrical | Material | Lump Sum |  | 8
3460-0006 | 06-ARG-Santa Fe Ditch Drn-SFDD | Material | Lump Sum |  | 8
3460-4601011 | ARG-SFDD-Dewater | Material | Linear Feet |  | 8
3460-46010111 | ARG-Rmv/Rplc 48" ADS Pipe | Material | Linear Feet |  | 8
3460-46010112 | ARG-Rmv/Rplc Cut Off Dams | Material | Each |  | 8
3460-4701012 | ARG-SFDD-RCB Box Exc & Bed | Material | Cubic Yard |  | 8
3460-4701013 | ARG-SFDD-Backfill | Material | Cubic Yard |  | 8
3460-4702012 | ARG-SFDD-Load Backfill | Material | Cubic Yard |  | 8
3460-4702013 | ARG-SFDD-Haul Backfill | Material | Cubic Yard |  | 8
3460-4702014 | ARG-SFDD-Plc Struct Bkfl > 4' | Material | Cubic Yard |  | 8
3460-4702015 | ARG-SFDD-Plc Wall Emb withn 4' | Material | Cubic Yard |  | 8
3460-4561012 | ARG-SFDD-CIP Box/Outlet Struct | Material | Cubic Yard |  | 8
3460-5351012 | ARG-SFDD-F&I Rebar-Outlet | Material | LB |  | 8
3460-45610121 | ARG-SFDD-FS Box Culvert | Material | Square Feet |  | 8
3460-45610122 | ARG-SFDD-Pour Box Culvert | Material | Cubic Yard |  | 8
3460-4568012 | ARG-SFDD-F&I Rip Rap | Material | Cubic Yard |  | 8
3460-6030012 | ARG-SFDD-Flap Gate/Slide Gate | Material | Each |  | 8
3460-60300121 | ARG-SFDD-Flap Gate Mtl | Material | Each |  | 8
3460-60300122 | ARG-SFDD-Flap Gate Install | Material | Each |  | 8
3460-0007 | 07-ARG-Riprap and Bedding | Material | Lump Sum |  | 8
3460-4332011 | ARG-Bedding | Material | Cubic Yard |  | 8
3460-43320111 | ARG-F&I Bedding | Material | Cubic Yard |  | 8
3460-43320112 | ARG-Haul Bedding From Stkpl | Material | Cubic Yard |  | 8
3460-4568013 | ARG-Riprap | Material | Cubic Yard |  | 8
3460-45680131 | ARG-Haul RIP RAP From Stkpl | Material | Cubic Yard |  | 8
3460-45680132 | ARG-F&I Rip Rap | Material | Cubic Yard |  | 8
3460-4332012 | ARG-Toe Revetment | Material | Cubic Yard |  | 8
3460-43320121 | ARG-Toe-Exc Trench | Material | Cubic Yard |  | 8
3460-43320122 | ARG-Toe-Haul Rip Rap | Material | Ton |  | 8
3460-43320123 | ARG-Toe-Plc Bedng frm Crushr | Material | Cubic Yard |  | 8
3460-43320124 | ARG-Toe-Plc Rip Rap frm Crushr | Material | Cubic Yard |  | 8
3460-43320125 | ARG-Toe-Embank OX | Material | Cubic Yard |  | 8
3460-0008 | 08-ARG-Utility Relocations | Material | Lump Sum |  | 8
3460-4152011 | ARG-Support Elec Utility | Material | Lump Sum |  | 8
3460-4576011 | ARG-Utility-Line 24" Pipe | Material | Linear Feet |  | 8
3460-4557011 | ARG-Utility-Drainage-Scope Adj | Material | Lump Sum |  | 8
3460-0009 | 09-ARG-Rmv/Dispose Contam Mtls | Material | Ton |  | 8
3460-4316013 | ARG-Load Contam Mtls | Material | Cubic Yard |  | 8
3460-4316014 | ARG-Haul Contam Mtls | Material | Cubic Yard |  | 8
3460-4316011 | ARG-Haul Unsuit Replcmnt Mtl | Material | Cubic Yard |  | 8
3460-4316012 | ARG-Embank Replcmnt Mtl | Material | Cubic Yard |  | 8
3460-0010 | 10-ARG-Rmv of Existing Riprap | Material | Cubic Yard |  | 8
3460-45680141 | ARG-Haul Exst Rip Rap to Stkpl | Material | Cubic Yard |  | 8
3460-45680142 | ARG-Remove Existing Riprap | Material | Cubic Yard |  | 8
3460-0011 | 11-ARM-Site Prep/Demo/Restore | Material | Lump Sum |  | 8
3460-4251021 | ARM-Clearing & Grubbing | Material | Acre |  | 8
3460-4251022 | ARM-Mulching/Mowing | Material | Acre |  | 8
3460-4312021 | ARM-Strip Topsoil | Material | Cubic Yard |  | 8
3460-43120211 | ARM-Strip/Haul Topsl 1500' | Material | Cubic Yard |  | 8
3460-43120212 | ARM-Dozer Exc Topsoil to Stock | Material | Cubic Yard |  | 8
3460-4306021 | ARM-Remove Aggregate Surfacing | Material | Cubic Yard |  | 8
3460-4201021 | ARM-Remove Existing Pavement | Material | Square Yard |  | 8
3460-4202021 | ARM-Demo Concrete Pavement | Material | Square Yard |  | 8
3460-4207021 | ARM-Sawcut | Material | Linear Feet |  | 8
3460-4203021 | ARM-Demo Silo | Material | Each |  | 8
3460-4204021 | ARM-Demo Access Bridge | Material | Each |  | 8
3460-4205023 | ARM-Demo Concrete Wall | Material | Cubic Yard |  | 8
3460-4208022 | ARM-Demo Curb & Gutter | Material | Linear Feet |  | 8
3460-4205024 | ARM-Remove Concrete Foundation | Material | Lump Sum |  | 8
3460-4208023 | ARM-Rmv Exist RR Track/Tie | Material | Linear Feet |  | 8
3460-4208021 | ARM-Rmv Exist Fence | Material | Linear Feet |  | 8
3460-4208024 | ARM-Rmv Exist Signs | Material | Each |  | 8
3460-4209021 | ARM-Rmv Exist Pipe | Material | Linear Feet |  | 8
3460-42090213 | ARM-Abandon & Fill Pipe CLSM | Material | Linear Feet |  | 8
3460-42090214 | ARM-Rmv Wtr/Drn/Swr/RW Pipe | Material | Linear Feet |  | 8
3460-42090212 | ARM-Rmv Pwr/Com/CATV | Material | Linear Feet |  | 8
3460-4209025 | ARM-Demo Misc Utility Struct | Material | Each |  | 8
3460-4100021 | ARM-E&S Controls | Material | Lump Sum |  | 8
3460-4101021 | ARM-Remove Silt Fence | Material | Linear Feet |  | 8
3460-4102021 | ARM-Plc E&S-Silt/Mat/Inlet/Dam | Material | Linear Feet |  | 8
3460-4103021 | ARM-Temp.Seeding | Material | Square Yard |  | 8
3460-4255021 | ARM-Curb & Gutter | Material | Linear Feet |  | 8
3460-4253021 | ARM-6' Chain Link Fence | Material | Linear Feet |  | 8
3460-4314021 | ARM-Place Topsoil | Material | Square Yard |  | 8
3460-43140214 | ARM-Load/Plc/Finish Topsoil | Material | Square Yard |  | 8
3460-43140213 | ARM-Haul Topsoil 1500' | Material | Cubic Yard |  | 8
3460-4258021 | ARM-Seeding | Material | Square Yard |  | 8
3460-5171021 | ARM-Retain Wall (Modular)-Sub | Material | Square Feet |  | 8
3460-0012 | 12-ARM-Levee Improve | Material | Lump Sum |  | 8
3460-4324021 | ARM-Prep Fill Area | Material | Square Yard |  | 8
3460-43240211 | ARM-Prep Embankment Area | Material | Square Yard |  | 8
3460-43240212 | ARM-Haul Fill | Material | Cubic Yard |  | 8
3460-4304021 | ARM-On Site Cut | Material | Cubic Yard |  | 8
3460-43040211 | ARM-On Site Cut | Material | Cubic Yard |  | 8
3460-43040212 | ARM-On Site Cut-40 Tn Trk Haul | Material | Cubic Yard |  | 8
3460-43040213 | ARM-Place Fill | Material | Cubic Yard |  | 8
3460-4322021 | ARM-Pervious Fill | Material | Cubic Yard |  | 8
3460-4322022 | ARM-Plc Pervious Fill Material | Material | Cubic Yard |  | 8
3460-4320021 | ARM-Levee Random Fill | Material | Cubic Yard |  | 8
3460-43200211 | ARM-Place Random/UBF | Material | Cubic Yard |  | 8
3460-43200212 | ARM-Haul Random/UBF | Material | Cubic Yard |  | 8
3460-4322023 | ARM-Impervious Fill | Material | Cubic Yard |  | 8
3460-43220231 | ARM-Place Impervious Fill | Material | Cubic Yard |  | 8
3460-43220232 | ARM-Haul Impervious Fill | Material | Cubic Yard |  | 8
3460-4306023 | ARM-Agg Surfacing-Complete | Material | Square Yard |  | 8
3460-4604021 | ARM-Rmv/Rplc Piezometers | Material | Each |  | 8
3460-4054021 | ARM-F&I Freeboard Gage | Material | Each |  | 8
3460-4334021 | ARM-Furnish & Install Geotex | Material | Square Yard |  | 8
3460-6020021 | ARM-6" Conc Overtopping w/FG | Material | Square Yard |  | 8
3460-0013 | 13-ARM-Floodwall Improve | Material | Lump Sum |  | 8
3460-4701021 | ARM-Fldwl-Exc/Truck to Stkpl | Material | Cubic Yard |  | 8
3460-4702021 | ARM-Fldwl-Backfill | Material | Cubic Yard |  | 8
3460-47020211 | ARM-Fldwl-Place/Compact Bkfl | Material | Cubic Yard |  | 8
3460-47020212 | ARM-Fldwl-Load/Truck Bkfl | Material | Cubic Yard |  | 8
3460-4690021 | ARM-Fldwl-SOE | Material | Square Feet |  | 8
3460-4656021 | ARM-Fldwl-SOE-Trench Box | Material | Linear Feet |  | 8
3460-46900211 | ARM-Fldwl-F/I One-Sided SOE | Material | Square Feet |  | 8
3460-4655021 | ARM-Fldwl-Sheet Pile Cap Conc | Material | Cubic Yard |  | 8
3460-46550211 | ARM-Fldwl-Sht Pile Cap-F/S | Material | Square Feet |  | 8
3460-46550212 | ARM-Fldwl-Sht Pile Cap-Pour | Material | Cubic Yard |  | 8
3460-5151021 | ARM-Fldwl-Footing Concrete | Material | Cubic Yard |  | 8
3460-51510211 | ARM-Fldwl-Footng Mtl | Material | Square Feet |  | 8
3460-4703021 | ARM-Fldwl-Footng-FG & F/S CLSM | Material | Square Feet |  | 8
3460-51510212 | ARM-Fldwl-Footng Pour CLSM | Material | Cubic Yard |  | 8
3460-51510213 | ARM-Fldwl-Footng F/S Base/Heel | Material | Square Feet |  | 8
3460-51510214 | ARM-Fldwl-Footng-Pour Concrete | Material | Cubic Yard |  | 8
3460-5151022 | ARM-Fldwl-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510227 | ARM-Fldwl-Wall-Permanent Mtl | Material | Cubic Yard |  | 8
3460-51510221 | ARM-Fldwl-Wall-Constructn Mtl | Material | Square Feet |  | 8
3460-51510222 | ARM-Fldwl-F/S Stem w/Crane | Material | Square Feet |  | 8
3460-51510223 | ARM-Fldwl-Pour/Cure Stem Conc | Material | Cubic Yard |  | 8
3460-51510224 | ARM-Fldwl-F/S I-Wall w/Shr Std | Material | Square Feet |  | 8
3460-51510225 | ARM-Fldwl-Pour I-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510226 | ARM-Fldwl-Patch / Point Stems | Material | Square Feet |  | 8
3460-5151023 | ARM-Fldwl-Buttress Ftng Conc | Material | Cubic Yard |  | 8
3460-51510231 | ARM-Fldwl-Buttress Ftg-F/S | Material | Square Feet |  | 8
3460-51510232 | ARM-Fldwl-Buttress Ftg-Pour | Material | Cubic Yard |  | 8
3460-5151024 | ARM-Fldwl-Butrs Wall Conc | Material | Cubic Yard |  | 8
3460-51510241 | ARM-Fldwl-Butrs Wall-Const Mtl | Material | Square Feet |  | 8
3460-51510242 | ARM-Fldwl-F/S Stem/Butrs Extsn | Material | Square Feet |  | 8
3460-51510243 | ARM-Fldwl-Pour/Cure Stem/Butrs | Material | Cubic Yard |  | 8
3460-51510245 | ARM-Fldwl-Butrs Wall-Patch/Pnt | Material | Square Feet |  | 8
3460-5351021 | ARM-Fldwl-Reinforcing Steel | Material | LB |  | 8
3460-53510211 | ARM-Fldwl-Rebar Mtl | Material | LB |  | 8
3460-53510212 | ARM-Fldwl-F&I Rebar ARM0013 | Material | LB |  | 8
3460-5353021 | ARM-Fldwl-Crane Support | Material | LB |  | 8
3460-5352021 | ARM-Fldwl-Instl Dowel/Coupler | Material | Each |  | 8
3460-53510213 | ARM-Fldwl-Drill for Rebar | Material | Linear Feet |  | 8
3460-53510214 | ARM-Fldwl-Core Drill for Stem | Material | Linear Feet |  | 8
3460-4706021 | ARM-Fldwl-H-Piles | Material | Linear Feet |  | 8
3460-47060211 | ARM-Fldwl-Buy Stl H Pile | Material | Linear Feet |  | 8
3460-47060212 | ARM-Fldwl-Instl H-Pile w/Sub | Material | Linear Feet |  | 8
3460-47060213 | ARM-Fldwl-Unld/Hndl H Pile | Material | Each |  | 8
3460-4655022 | ARM-Fldwl-Sheetpiles | Material | Square Feet |  | 8
3460-46550221 | ARM-Fldwl-Buy Stl SSP | Material | Square Feet |  | 8
3460-46550222 | ARM-Fldwl-Install SSP-Complete | Material | Square Feet |  | 8
3460-4655023 | ARM-Fldwl-Sheetpile-Low Headrm | Material | Square Feet |  | 8
3460-46550231 | ARM-Buy Stl SSP-Low Headroom | Material | Square Feet |  | 8
3460-46550232 | ARM-Instl SSP-Low Hdrm-Complet | Material | Square Feet |  | 8
3460-4705021 | ARM-Fldwl-30" Dia Drill Shaft | Material | Linear Feet |  | 8
3460-4205026 | ARM-Fldwl-Demo Exist Floodwall | Material | Cubic Yard |  | 8
3460-42050261 | ARM-Fldwl-Haul Conc to Crusher | Material | Cubic Yard |  | 8
3460-42050262 | ARM-Fldwl-Break/Ld Conc Stem | Material | Cubic Yard |  | 8
3460-42050263 | ARM-Fldwl-Break/Ld Conc Base | Material | Cubic Yard |  | 8
3460-4205027 | ARM-Fldwl-Rmv 12" Conc Sht Ple | Material | Linear Feet |  | 8
3460-0014 | 14-ARM-Relief Well Improve | Material | Lump Sum |  | 8
3460-4554021 | ARM-Relief Well-15" Dia Rcp | Material | Linear Feet |  | 8
3460-45540211 | ARM-Relief Well-RCP Materials | Material | Linear Feet |  | 8
3460-45540212 | ARM-Relief Well-ELB 15" RCP | Material | Linear Feet |  | 8
3460-4566021 | ARM-Relief Well-J&B 36" Pipe | Material | Linear Feet |  | 8
3460-4565021 | ARM-Relief Well-Manholes | Material | Each |  | 8
3460-45650211 | ARM-Relief Well-MH Materials | Material | Each |  | 8
3460-45650212 | ARM-Relief Well-48" Sewer MH | Material | Each |  | 8
3460-4554022 | ARM-Relief Well-Complete | Material | Each |  | 8
3460-45540221 | ARM-Relief Well-Weld Pipes | Material | Each |  | 8
3460-45540222 | ARM-Relief Well-Abandon-Sub | Material | Each |  | 8
3460-0015 | 15-ARM-Relief Well Pilot Hole | Material | Lump Sum |  | 8
3460-4554023 | ARM-Relief Well Pilot Hole | Material | Each |  | 8
3460-0016 | 16-ARM-Relief Well Screen | Material | Linear Feet |  | 8
3460-4554024 | ARM-Relief Well Screen Sub | Material | Linear Feet |  | 8
3460-0017 | 17-ARM-Relief Well Blank Riser | Material | Linear Feet |  | 8
3460-4554025 | ARM-Relief Well-Blank Risr Sub | Material | Linear Feet |  | 8
3460-0018 | 18-ARM-Relief Well Filter Pack | Material | Cubic Yard |  | 8
3460-4554026 | ARM-Relief Well Filter Pack | Material | Cubic Yard |  | 8
3460-0019 | 19-ARM-Gatewell/Pump Stn Imprv | Material | Lump Sum |  | 8
3460-51100211 | ARM-Modify Exist Structure | Material | Each |  | 8
3460-51100212 | ARM-FPS Gatewell Top Extension | Material | Each |  | 8
3460-8990021 | ARM-Electrical | Material | Lump Sum |  | 8
3460-6030021 | ARM-Install Flap Gates | Material | Each |  | 8
3460-0020 | 20-ARM-Riprap and Bedding | Material | Lump Sum |  | 8
3460-4332021 | ARM-Bedding | Material | Cubic Yard |  | 8
3460-43320211 | ARM-F&I Bedding | Material | Cubic Yard |  | 8
3460-43320212 | ARM-Haul Bedding From Stkpl | Material | Cubic Yard |  | 8
3460-4568023 | ARM-Riprap | Material | Cubic Yard |  | 8
3460-45680231 | ARM-Haul RIP RAP From Stkpl | Material | Cubic Yard |  | 8
3460-45680232 | ARM-F&I Rip Rap | Material | Cubic Yard |  | 8
3460-4332022 | ARM-Toe Revetment | Material | Cubic Yard |  | 8
3460-0021 | 21-ARM-Utility Relocations | Material | Lump Sum |  | 8
3460-4155021 | ARM-36" San Force-OPTION | Material | Linear Feet |  | 8
3460-4153021 | ARM-Electrical-Sub | Material | Linear Feet |  | 8
3460-4576021 | ARM-Line Pipe | Material | Linear Feet |  | 8
3460-4557021 | ARM-Structure Raise | Material | Each |  | 8
3460-4155022 | ARM-Wall Penetrations | Material | Each |  | 8
3460-0022 | 22-ARM-Rmv/Dispose Contam Mtls | Material | Ton |  | 8
3460-4316023 | ARM-Load Contam Mtls | Material | Cubic Yard |  | 8
3460-4316024 | ARM-Haul Contam Mtls | Material | Cubic Yard |  | 8
3460-4316021 | ARM-Haul Unsuit Replcmnt Mtl | Material | Cubic Yard |  | 8
3460-4316022 | ARM-Embank Replcmnt Mtl | Material | Cubic Yard |  | 8
3460-0023 | 23-ARM-Rmv of Existing Riprap | Material | Cubic Yard |  | 8
3460-45680241 | ARM-Haul Exst Rip Rap to Stkpl | Material | Cubic Yard |  | 8
3460-45680242 | ARM-Remove Existing Riprap | Material | Cubic Yard |  | 8
3460-0041 | 41-ARM-Stoplog Struct-STA 233+ | Material | Lump Sum |  | 8
3460-4304022 | ARM-Stoplog-Excav/Stkpl | Material | Cubic Yard |  | 8
3460-4304023 | ARM-Stoplog-Backfill | Material | Cubic Yard |  | 8
3460-4655024 | ARM-Stoplog-SOE/SSP | Material | Square Feet |  | 8
3460-5151025 | ARM-Stoplog-Footing Concrete | Material | Cubic Yard |  | 8
3460-51510251 | ARM-Stoplog-Footing-F/S | Material | Square Feet |  | 8
3460-51510252 | ARM-Stoplog-Footing-Pour Conc | Material | Cubic Yard |  | 8
3460-5151026 | ARM-Stoplog-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510261 | ARM-Stoplog-Wall-F/S | Material | Square Feet |  | 8
3460-51510262 | ARM-Stoplog-Wall-Pour Conc | Material | Cubic Yard |  | 8
3460-51510263 | ARM-Stoplog-Wall-Patch/Point | Material | Square Feet |  | 8
3460-5173021 | ARM-Stoplog-Post/Panel | Material | Each |  | 8
3460-51730211 | ARM-Stoplog-Post/Panel-Mtl | Material | Each |  | 8
3460-4051021 | ARM-Stoplog-Post/Panel-Install | Material | Each |  | 8
3460-8590021 | ARM-Stoplog-Storage Bldg | Material | Lump Sum |  | 8
3460-85900211 | ARM-Stoplog-Bldg-Perm Mtl | Material | Lump Sum |  | 8
3460-8510021 | ARM-Stoplog-Bldg-Exc/Ftg/Slab | Material | Cubic Yard |  | 8
3460-85900212 | ARM-Stoplog-Bldg-Install | Material | Each |  | 8
3460-85900213 | ARM-Stoplog-Bldg-Install Crane | Material | Each |  | 8
3460-5351022 | ARM-Stoplog-Reinforcing Steel | Material | LB |  | 8
3460-53510221 | ARM-Stoplog-Rebar Mtl | Material | LB |  | 8
3460-53510222 | ARM-Stoplog-F&I Rebar ARM0041 | Material | LB |  | 8
3460-4706022 | ARM-Stoplog-H-Piles | Material | Linear Feet |  | 8
3460-47060221 | ARM-Stoplog-Buy Stl H Pile | Material | Linear Feet |  | 8
3460-47060222 | ARM-Stoplog-Instl H-Pile w/Sub | Material | Linear Feet |  | 8
3460-47060223 | ARM-Stoplog-Unld/Hndl H Pile | Material | Linear Feet |  | 8
3460-4655025 | ARM-Stoplog-Sheetpiles | Material | Square Feet |  | 8
3460-46550251 | ARM-Stoplog-Buy Stl SSP | Material | Square Feet |  | 8
3460-46550252 | ARM-Stoplog-Install SSP-Complt | Material | Square Feet |  | 8
3460-0024 | 24-CID-Site Prep/Demo/Restore | Material | Lump Sum |  | 8
3460-4251031 | CID-Clearing & Grubbing | Material | Acre |  | 8
3460-4251032 | CID-Mulching/Mowing | Material | Acre |  | 8
3460-4312031 | CID-Strip/Haul/Stkpl Topsoil | Material | Cubic Yard |  | 8
3460-4306031 | CID-Rmv Aggregate Surfacing | Material | Cubic Yard |  | 8
3460-4201031 | CID-Rmv Asphalt Pavement | Material | Square Yard |  | 8
3460-4205033 | CID-Rmv Concrete Fndtn/Wall | Material | Cubic Yard |  | 8
3460-4205034 | CID-Rmv Box Culvert | Material | Cubic Yard |  | 8
3460-4208033 | CID-Rmv Exist RR Tracks/Ties | Material | Linear Feet |  | 8
3460-4208034 | CID-Rmv Guardrail/Sign | Material | Lump Sum |  | 8
3460-4208031 | CID-Rmv Existing Fence | Material | Linear Feet |  | 8
3460-4208032 | CID-Demo Curb & Gutter | Material | Linear Feet |  | 8
3460-4209031 | CID-Remove Existing Pipe | Material | Linear Feet |  | 8
3460-42090313 | CID-Abandon & Fill Pipe CLSM | Material | Linear Feet |  | 8
3460-4206031 | CID-Remove Drainage | Material | Linear Feet |  | 8
3460-4205035 | CID-Demo Misc Utility Struct | Material | Each |  | 8
3460-4100031 | CID-E&S Controls | Material | Lump Sum |  | 8
3460-4101031 | CID-Remove Silt Fence | Material | Linear Feet |  | 8
3460-4102031 | CID-Plc E&S-Silt/Mat/Inlet/Dam | Material | Linear Feet |  | 8
3460-4253031 | CID-6' Chain Link Fence | Material | Linear Feet |  | 8
3460-4314031 | CID-Place 6" Topsoil | Material | Square Yard |  | 8
3460-43140313 | CID-Load/Haul Topsoil | Material | Cubic Yard |  | 8
3460-43140314 | CID-Place/Finish Topsoil | Material | Square Yard |  | 8
3460-4258031 | CID-Seeding | Material | Square Yard |  | 8
3460-0025 | 25-CID-Levee Improve | Material | Lump Sum |  | 8
3460-4324031 | CID-Prep Fill Area | Material | Square Yard |  | 8
3460-43240311 | CID-Prep Embankment Area | Material | Square Yard |  | 8
3460-43240312 | CID-Haul Fill | Material | Cubic Yard |  | 8
3460-4304031 | CID-On Site Cut | Material | Cubic Yard |  | 8
3460-43040311 | CID-On Site Cut | Material | Cubic Yard |  | 8
3460-43040312 | CID-Place Random Mtrl | Material | Cubic Yard |  | 8
3460-43040313 | CID-On Site Cut-40 Tn Trk Haul | Material | Cubic Yard |  | 8
3460-4322031 | CID-Pervious Fill | Material | Cubic Yard |  | 8
3460-4322032 | CID-Plc Pervious Fill Material | Material | Cubic Yard |  | 8
3460-4320031 | CID-Levee Random Fill | Material | Cubic Yard |  | 8
3460-43200311 | CID-Place Random/UBF | Material | Cubic Yard |  | 8
3460-43200312 | CID-Haul Random/UBF | Material | Cubic Yard |  | 8
3460-4322033 | CID-Impervious Fill | Material | Cubic Yard |  | 8
3460-43220331 | CID-Place Impervious Fill | Material | Cubic Yard |  | 8
3460-43220332 | CID-Haul Impervious Fill | Material | Cubic Yard |  | 8
3460-4306033 | CID-Agg Surfacing-Complete | Material | Square Yard |  | 8
3460-4334031 | CID-Furnish & Install Geotex | Material | Square Yard |  | 8
3460-4604031 | CID-Piezometer | Material | Each |  | 8
3460-4054031 | CID-F&I Freeboard Gage | Material | Each |  | 8
3460-0026 | 26-CID-Floodwall Improve | Material | Lump Sum |  | 8
3460-4701031 | CID-Fldwl-Exc/Truck to Stkpl | Material | Cubic Yard |  | 8
3460-4702031 | CID-Fldwl-Backfill | Material | Cubic Yard |  | 8
3460-4690031 | CID-Fldwl-SOE | Material | Linear Feet |  | 8
3460-5151031 | CID-Fldwl-Footing Concrete | Material | Cubic Yard |  | 8
3460-51510315 | CID-Fldwl-Footng-Permanent Mtl | Material | Cubic Yard |  | 8
3460-51510311 | CID-Fldwl-Footng-Constrctn Mtl | Material | Square Feet |  | 8
3460-4703031 | CID-Fldwl-Footng-FG & F/S CLSM | Material | Square Feet |  | 8
3460-51510312 | CID-Fldwl-Footng Pour CLSM | Material | Cubic Yard |  | 8
3460-51510313 | CID-Fldwl-Footng F/S Base/Heel | Material | Square Feet |  | 8
3460-51510314 | CID-Fldwl-Footng-Pour Concrete | Material | Cubic Yard |  | 8
3460-5151032 | CID-Fldwl-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510327 | CID-Fldwl-Wall-Permanent Mtl | Material | Cubic Yard |  | 8
3460-51510321 | CID-Fldwl-Wall-Constructn Mtl | Material | Square Feet |  | 8
3460-51510322 | CID-Fldwl-F/S Stem | Material | Square Feet |  | 8
3460-51510323 | CID-Fldwl-Pour/Cure Stem Conc | Material | Cubic Yard |  | 8
3460-51510325 | CID-Fldwl-F/S/Pour I-Wall | Material | Cubic Yard |  | 8
3460-51510326 | CID-Fldwl-Patch/Point Stem | Material | Square Feet |  | 8
3460-5351031 | CID-Fldwl-Reinforcing Steel | Material | LB |  | 8
3460-53510311 | CID-Fldwl-Rebar Mtrl | Material | LB |  | 8
3460-53510312 | CID-Fldwl-F&I Rebar CID0026 | Material | LB |  | 8
3460-4706031 | CID-Fldwl-H-Piles | Material | Linear Feet |  | 8
3460-47060311 | CID-Fldwl-Buy Stl H Pile | Material | Linear Feet |  | 8
3460-47060312 | CID-Fldwl-Instl H-Pile w/Sub | Material | Linear Feet |  | 8
3460-4655032 | CID-Fldwl-Sheetpiles | Material | Square Feet |  | 8
3460-46550321 | CID-Fldwl-Buy Stl SSP | Material | Square Feet |  | 8
3460-46550322 | CID-Fldwl-Install SSP-Complete | Material | Square Feet |  | 8
3460-4205036 | CID-Fldwl-Demo Exist Floodwall | Material | Cubic Yard |  | 8
3460-4205037 | CID-Fldwl-HydroBlst-Exist Toe | Material | Cubic Yard |  | 8
3460-4206032 | CID-Fldwl-Rmv Toe Drain Pipe | Material | Linear Feet |  | 8
3460-0027 | 27-CID-Relief Well Improve | Material | Lump Sum |  | 8
3460-4206033 | CID-Relief Well-Drilling | Material | Each |  | 8
3460-42060331 | CID-Relief Well-Weld Pipe | Material | Each |  | 8
3460-42060332 | CID-Relief Well-Abandon-Sub | Material | Each |  | 8
3460-42060333 | CID-Relief Well-Fill Pipe CLSM | Material | Linear Feet |  | 8
3460-4557031 | CID-Relief Well-Drng-Scope Adj | Material | Lump Sum |  | 8
3460-4554031 | CID-Relief Well-12" Dia Pipe | Material | Linear Feet |  | 8
3460-45540311 | CID-Relief Well-RCP Materials | Material | Linear Feet |  | 8
3460-45540312 | CID-Relief Well-ELB 12" RCP | Material | Linear Feet |  | 8
3460-4557032 | CID-Relief Well-MH/Inlet/J-Box | Material | Each |  | 8
3460-4557033 | CID-Relief Well-Struct Raise | Material | Each |  | 8
3460-0031 | 31-CID-Gatewell/Pump Stn Imprv | Material | Lump Sum |  | 8
3460-5110031 | CID-Gatewell Extnsn-Complete | Material | Each |  | 8
3460-8990031 | CID-Electrical | Material | Lump Sum |  | 8
3460-6030031 | CID-Install Flap Gates | Material | Each |  | 8
3460-0032 | 32-CID-Riprap and Bedding | Material | Lump Sum |  | 8
3460-4332031 | CID-F&I Bedding | Material | Cubic Yard |  | 8
3460-4568033 | CID-Riprap | Material | Cubic Yard |  | 8
3460-45680331 | CID-Haul RIP RAP From Stkpl | Material | Cubic Yard |  | 8
3460-45680332 | CID-F&I Rip Rap | Material | Cubic Yard |  | 8
3460-0033 | 33-CID-Utility Relocations | Material | Lump Sum |  | 8
3460-4576031 | CID-Line Pipe | Material | Linear Feet |  | 8
3460-4153031 | CID-Reroute Electric | Material | Lump Sum |  | 8
3460-0034 | 34-CID-Rmv/Dispose Contam Mtls | Material | Ton |  | 8
3460-4316033 | CID-Load Contam Mtls | Material | Cubic Yard |  | 8
3460-4316034 | CID-Haul Contam Mtls | Material | Cubic Yard |  | 8
3460-4316031 | CID-Haul Unsuit Replcmnt Mtl | Material | Cubic Yard |  | 8
3460-4316032 | CID-Embank Replcmnt Mtl | Material | Cubic Yard |  | 8
3460-0035 | 35-CID-Rmv of Existing Riprap | Material | Cubic Yard |  | 8
3460-4568034 | CID-Rmv Exist Riprap-Complete | Material | Cubic Yard |  | 8
3460-0045 | 45-CID-Stoplog Struct-STA 134+ | Material | Lump Sum |  | 8
3460-4304032 | CID-Stoplog-Excav/Stkpl | Material | Cubic Yard |  | 8
3460-4304033 | CID-Stoplog-Backfill | Material | Cubic Yard |  | 8
3460-4655034 | CID-Stoplog-SOE/SSP | Material | Square Feet |  | 8
3460-5151035 | CID-Stoplog-Footing Concrete | Material | Cubic Yard |  | 8
3460-51510351 | CID-Stoplog-Footing-F/S | Material | Square Feet |  | 8
3460-51510352 | CID-Stoplog-Footing-Pour Conc | Material | Cubic Yard |  | 8
3460-5151036 | CID-Stoplog-Wall Concrete | Material | Cubic Yard |  | 8
3460-51510361 | CID-Stoplog-Wall-F/S | Material | Square Feet |  | 8
3460-51510362 | CID-Stoplog-Wall-Pour Conc | Material | Cubic Yard |  | 8
3460-51510363 | CID-Stoplog-Wall-Patch/Point | Material | Square Feet |  | 8
3460-5173031 | CID-Stoplog-Post/Panel | Material | Each |  | 8
3460-51730311 | CID-Stoplog-Post/Panel-Mtl | Material | Each |  | 8
3460-4051031 | CID-Stoplog-Post/Panel-Install | Material | Each |  | 8
3460-5351032 | CID-Stoplog-Reinforcing Steel | Material | LB |  | 8
3460-53510321 | CID-Stoplog-Rebar Mtl | Material | LB |  | 8
3460-53510322 | CID-Stoplog-F&I Rebar CID0045 | Material | LB |  | 8
3460-4706032 | CID-Stoplog-H-Piles | Material | Linear Feet |  | 8
3460-47060321 | CID-Stoplog-Buy Stl H Pile | Material | Linear Feet |  | 8
3460-47060322 | CID-Stoplog-Instl H-Pile w/Sub | Material | Linear Feet |  | 8
3460-4655035 | CID-Stoplog-Sheetpiles | Material | Square Feet |  | 8
3460-46550351 | CID-Stoplog-Buy Stl SSP | Material | Square Feet |  | 8
3460-46550352 | CID-Stoplog-Install SSP-Complt | Material | Square Feet |  | 8
3460-4203031 | CID-Stoplog-Demo Storage Bldg | Material | Square Feet |  | 8
3460-4306034 | CID-Stoplog-Agg Surfacing | Material | Square Yard |  | 8
3460-0036 | 36-Borrow Pit-Site Prep | Material | Lump Sum |  | 8
3460-4251041 | Borrow Pit-Clearing & Grub | Material | Acre |  | 8
3460-4251042 | Borrow Pit-Mulching/Mowing | Material | Acre |  | 8
3460-4312041 | Borrow Pit-Strip Topsoil | Material | Cubic Yard |  | 8
3460-43120411 | Borrow Pit-Strip/Haul Topsoil | Material | Cubic Yard |  | 8
3460-43120412 | Borrow Pit-Dzr Exc Tpsl to Stk | Material | Cubic Yard |  | 8
3460-4100041 | Borrow Pit-E&S Controls | Material | Lump Sum |  | 8
3460-4101041 | Borrow Pit-Remove Silt Fence | Material | Linear Feet |  | 8
3460-4102041 | Borrow Pit-Silt/Mat/Inlet/Dam | Material | Linear Feet |  | 8
3460-4103041 | Borrow Pit-Temp Seeding | Material | Square Yard |  | 8
3460-4304041 | Borrow Pit-Embank Berm Borrow | Material | Cubic Yard |  | 8
3460-43040411 | Borrow Pit-On Site Cut & Fill | Material | Cubic Yard |  | 8
3460-43040412 | Borrow Pit-Plc All Random Mtl | Material | Cubic Yard |  | 8
3460-4304042 | Borrow Pit-Finish Slopes | Material | Square Yard |  | 8
3460-4314041 | Borrow Pit-Place 6" Topsoil | Material | Square Yard |  | 8
3460-43140412 | Borrow Pit-Load Topsoil | Material | Cubic Yard |  | 8
3460-43140413 | Borrow Pit-Haul Topsoil to Plc | Material | Cubic Yard |  | 8
3460-43140414 | Borrow Pit-Place Topsoil | Material | Square Yard |  | 8
3460-4352041 | Borrow Pit-6" Agg Surf-Complt | Material | Cubic Yard |  | 8
3460-4253041 | Borrow Pit-Rmv/Replace Fence | Material | Linear Feet |  | 8
3460-4101042 | Borrow Pit-Rmv/Rplc Silt Fence | Material | Linear Feet |  | 8
3460-4258041 | Borrow Pit-Seeding | Material | Square Yard |  | 8
3460-5320041 | Borrow Pit-Pit Enterance-57 St | Material | Square Yard |  | 8
3460-4304043 | Borrow Pit-Excav/Load | Material | Cubic Yard |  | 8
3460-4322041 | Borrow Pit-Load/Haul Pervious Fill | Material | Cubic Yard |  | 8
3460-0037 | 37-Replacement Inland Drive | Material | Lump Sum |  | 8
3460-4306051 | Inland Dr-Replacement | Material | Each |  | 8
3460-43060511 | Inland Dr-Haul to Crusher | Material | Cubic Yard |  | 8
3460-4051051 | Inland Dr-MOT | Material | Lump Sum |  | 8
3460-4053051 | Inland Dr-Wht/Yellow Edge Line | Material | Linear Feet |  | 8
3460-4201051 | Inland Dr-Remove Asphalt Pvmt | Material | Square Yard |  | 8
3460-4324051 | Inland Dr-Scarify/Cmpct Subgrd | Material | Square Yard |  | 8
3460-4356051 | Inland Dr-Surf Exist Agg Shldr | Material | Square Yard |  | 8
3460-4401051 | Inland Dr-Ty 1 HMA Base-9" | Material | Ton |  | 8
3460-4401052 | Inland Dr-Ty 3 HMA Surface-2" | Material | Ton |  | 8
3460-4558051 | Inland Dr-Adjust to Manhole | Material | Each |  | 8
3460-91500 | Crusher | Material | Lump Sum |  | 8
3460-917001 | Crusher-Mobe/Setup | Material | Lump Sum |  | 8
3460-917002 | Crusher-De Mobe | Material | Month |  | 8
3460-91600 | Crusher-Operations | Material | Ton |  | 8
3460-39010 | Direct Labor Escalation | Material | Lump Sum |  | 8
3460-390101 | Direct Labor Escalation | Material | Lump Sum |  | 8
3460-390102 | Incidental Overtime/Lost Time | Material | Lump Sum |  | 8
3460-39020 | PROJECTWIDE SERVICES | Material | Month |  | 8
3460-4107061 | Prj Wide-Dust Cntrl/Const Wtr | Material | Month |  | 8
3460-4604061 | Prj Wide-Dewatr for Rain Event | Material | Month |  | 8
3460-4102061 | Prj Wide-Flood Protection Mtrl | Material | Lump Sum |  | 8
3460-4102062 | Prj Wide-Concrete Wash Outs | Material | Lump Sum |  | 8
3460-4104061 | Prj Wide-Sweeping | Material | Month |  | 8
3460-4102063 | Prj Wide-Winter Protection | Material | Lump Sum |  | 8
3460-4101061 | Prj Wide-SWPPP Crew | Material | Month |  | 8
3460-4155061 | Prj Wide-Utility Location | Material | Lump Sum |  | 8
3460-4251061 | Prj Wide-Discing | Material | Month |  | 8
3460-4250561 | Prj Wide-Exist Roadway Maint | Material | Month |  | 8
3460-4101062 | Prj Wide-E&S Crew | Material | Lump Sum |  | 8
3460-4250562 | Prj Wide-Bull Gang Crew | Material | Month |  | 8
3460-1262061 | Prj Wide-Onsite Water Develpmt | Material | Gallon |  | 8
3460-12620611 | Prj Wide-Setup H2O Sys/Buy H2O | Material | Gallon |  | 8
3460-12620612 | Prj Wide-Water Storage Tanks | Material | Month |  | 8
3460-4302061 | Prj Wide-Access Roads | Material | Square Yard |  | 8
3460-43020611 | Prj Wide-Instl New Access Road | Material | Square Yard |  | 8
3460-43020612 | Prj Wide-Rmv Access Roads | Material | Ton |  | 8
3460-43020613 | Prj Wide-Maintain Access Roads | Material | Square Yard |  | 8
3460-4302062 | Prj Wide-Constructn Entrances | Material | Each |  | 8
3460-4501061 | Prj Wide-Railroad Crossings | Material | Each |  | 8
3460-45010611 | Prj Wide-Instl/Rmv RR Crossing | Material | Each |  | 8
3460-45010612 | Prj Wide-Mod Eqp/Rubber Tracks | Material | Each |  | 8
3460-4252061 | Prj Wide-Temp Safety Fence | Material | Linear Feet |  | 8
3460-4554061 | Prj Wide-15" Dia Rcp | Material | Linear Feet |  | 8
3460-45540611 | Prj Wide-15" RCP Mtl | Material | Linear Feet |  | 8
3460-45540612 | Prj Wide-ELB 15" RCP | Material | Linear Feet |  | 8
3460-4557061 | Prj Wide-MH/Inlets/J-Boxes | Material | Each |  | 8
3460-45570611 | Prj Wide-MH/Inlets/J-Boxes-Mtl | Material | Each |  | 8
3460-45570612 | Prj Wide-Instl MH/Inlets/J-Box | Material | Each |  | 8
3460-4554062 | Prj Wide-30" Dia. RCP | Material | Linear Feet |  | 8
3460-45540621 | Prj Wide-30" RCP-Line Pipe | Material | Linear Feet |  | 8
3460-4557062 | Prj Wide-Structure Raise | Material | Each |  | 8
3460-10000 | INDIRECT | Material | Month |  | 8
3460-10620 | TEMPORARY DESIGN | Material | Lump Sum |  | 8
3460-10670 | CONSULTING SERVICES | Material | Lump Sum |  | 8
3460-10850 | QC - 3RD PARTY | Material | Lump Sum |  | 8
3460-10210 | INSURANCE PREMIUMS | Material | Lump Sum |  | 8
3460-10410 | PAYMENT/PERFORMANCE BOND | Material | Lump Sum |  | 8
3460-10830 | QUALITY CONTROL-FIXED COST | Material | Lump Sum |  | 8
3460-11010 | SURVEY STAFF | Material | Month |  | 8
3460-11020 | SURVEY EQUIPMENT & SUPPLY | Material | Month |  | 8
3460-11030 | CONSTRUCT SURVEY MODELING | Material | Month |  | 8
3460-11210 | CONSTRUCTION PERMITS | Material | Lump Sum |  | 8
3460-11420 | PROJECT MANAGEMENT | Material | Month |  | 8
3460-11430 | PROJECT CONTROLS | Material | Month |  | 8
3460-11440 | DESIGN MANAGEMENT | Material | Month |  | 8
3460-11450 | HEALTH AND SAFETY | Material | Month |  | 8
3460-11460 | ENVIRONMENTAL | Material | Month |  | 8
3460-11470 | PROJECT ADMIN | Material | Month |  | 8
3460-11480 | FIELD SUPERVISION | Material | Month |  | 8
3460-11490 | PROJECT ENGINEERING | Material | Month |  | 8
3460-11520 | QA/QC STAFF | Material | Month |  | 8
3460-11540 | PLANT AND EQUIPMENT STAFF | Material | Month |  | 8
3460-11560 | INTERNS | Material | Month |  | 8
3460-11610 | MEALS | Material | Month |  | 8
3460-11710 | STAFF JOB MOVE / RELO | Material | Lump Sum |  | 8
3460-11720 | FIELD STAFF HOUSING | Material | Month |  | 8
3460-11730 | STAFF VEHICLES | Material | Month |  | 8
3460-11750 | RECRUITING | Material | Lump Sum |  | 8
3460-11810 | CONTRACTOR OFFICE-FIXED COST | Material | Lump Sum |  | 8
3460-11820 | CONTRACTOR OFFICE-MONTHLY | Material | Month |  | 8
3460-118201 | Lane Office-Monthly | Material | Month |  | 8
3460-118202 | Dumpsters | Material | Month |  | 8
3460-118203 | Jobsite Photos | Material | Lump Sum |  | 8
3460-12010 | CLIENT OFFICE-FIXED COST (RR) | Material | Lump Sum |  | 8
3460-12020 | Client Office-Monthly (RR) | Material | Month |  | 8
3460-12210 | YARD AND SHOPS-FIXED COST | Material | Lump Sum |  | 8
3460-122101 | ARG-Yards and Shops | Material | Each |  | 8
3460-122102 | ARM-Yards and Shops | Material | Each |  | 8
3460-122103 | CID-Yards and Shops | Material | Each |  | 8
3460-12410 | TECHNOLOGY ALLOCATION | Material | Month |  | 8
3460-12420 | COMPUTER SOFTWARE | Material | Month |  | 8
3460-12430 | COMPUTER HARDWARE | Material | Month |  | 8
3460-12440 | CELL PHONE | Material | Month |  | 8
3460-12450 | INTERNET/PHONE NETWORK | Material | Month |  | 8
3460-12470 | COPIERS | Material | Month |  | 8
3460-12510 | SAFETY SUPPLIES | Material | Month |  | 8
3460-12810 | ONSITE MOVES | Material | Month |  | 8
3460-13210 | SMALL TOOLS | Material | Hour |  | 8
3460-132101 | Small/Other Equip (incl lighting) | Material | Lump Sum |  | 8
3460-132102 | Small Tools | Material | Hour |  | 8
3460-13220 | PORTA JOHN | Material | Month |  | 8
3460-13480 | LICENSES | Material | Lump Sum |  | 8
3460-13610 | LEGAL EXPENSE/FEE | Material | Lump Sum |  | 8
3460-13680 | PARTNERING | Material | Lump Sum |  | 8
3460-14040 | LABOR ESCALATION (INDIRECT) | Material | Lump Sum |  | 8
3460-15010 | CONSTRUCTION RISK CONTINGENCY | Material | Lump Sum |  | 8
3460-15030 | FINANCE CONTINGENCY | Material | Lump Sum |  | 8
3460-15040 | K FACTOR | Material | Lump Sum |  | 8
3418-0191 | 3418-0191 - Addition of Glare Screen to Median Barrier Wall - CO #18 | Material | Lump Sum |  | 8
3418-0337 | 3418-0337 - Gibbons Road Drainage Adjustments to Address Duke Energy - CO #18 | Material | Lump Sum |  | 8
ST-BRIDGE-MECH | Bridge Mechanical Crew | Labor |  |  | 1
9156-CREDIT | Asphalt Compaction Credit | Material | Lump Sum |  | 8
3462-10000 | INDIRECT | Material | Month |  | 8
3462-10410 | PAYMENT/PERFORMANCE BOND | Material | Lump Sum |  | 8
3462-405101 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
3462-440201 | SPECIAL DETOUR-TEMP PAVEMENT | Material | Square Yard |  | 8
3462-431101 | SPCL DETOUR-TEMP ERTHWRK/BASE | Material | Square Yard |  | 8
3462-4051020 | TRAFFIC CONTROL OFFICER | Material | Hour |  | 8
3462-8910020 | TEMP HIGHWY LIGHT-PROJECT 4318 | Material | Lump Sum |  | 8
3462-4054010 | WORK ZONE SIGN | Material | Each |  | 8
3462-4052010 | TEMP BARR-F&I-LOW PROFILE-CON | Material | Linear Feet |  | 8
3462-4052020 | TEMP BARRIER-F&I-ANCHORED | Material | Linear Feet |  | 8
3462-4052030 | TEMP BARRIER-F&I-FREE STANDING | Material | Linear Feet |  | 8
3462-4052040 | TEMP BARRIER-REL-ANCHORED | Material | Linear Feet |  | 8
3462-4052050 | TEMP BARRIER-REL-FREE STAND | Material | Linear Feet |  | 8
3462-4054020 | CHANLIZNG DEVICE-TY I-II-DI-VP | Material | Each |  | 8
3462-4054030 | CHANLIZNG DEVICE-PEDESTRN LCD | Material | Each |  | 8
3462-4054040 | ARROW BRD/ADVANCE WARNG ARROW | Material | Each |  | 8
3462-4054050 | TEMP RAISED/RETROREFLECTV PVMT | Material | Each |  | 8
3462-4057010 | TEMP CRSH CUSH-REDIRECTIVE OPT | Material | Each |  | 8
3462-4054060 | PORTABLE CHANGE MSG SIGN-TEMP | Material | Each |  | 8
3462-8980010 | TEMP SIGNALIZATION/MAINT | Material | Each |  | 8
3462-8980020 | TEMP TRAFFIC DETECT AND MAINT | Material | Each |  | 8
3462-4054070 | TY III BARRICADE | Material | Each |  | 8
3462-4054080 | PORTABLE REGULATORY, SIGN | Material | Each |  | 8
3462-4054090 | RADAR SPEED DISPLAY UNIT | Material | Each |  | 8
3462-4252010 | SEDIMENT BARRIER | Material | Linear Feet |  | 8
3462-410201 | SOIL TRACKING PREVENTN DEVICE | Material | Each |  | 8
3462-4102020 | INLET PROTECTION SYS | Material | Each |  | 8
3462-4251010 | LITTER REMOVAL | Material | Acre |  | 8
3462-4258010 | MOWING | Material | Acre |  | 8
3462-410101 | MONITOR EXIST STRUCT-INSPECT | Material | Lump Sum |  | 8
3462-410103 | MONITOR EXIST STRUCT-VIBRATE | Material | Lump Sum |  | 8
3462-4251021 | Sub-Clear & Grub | Material | Acre |  | 8
3462-4251022 | C&G-Maintain Erosion Control | Material | Month |  | 8
3462-4251023 | Sub-Dumpster | Material | Lump Sum |  | 8
3462-4251024 | Sub-Asphalt Milling | Material | Lump Sum |  | 8
3462-4251025 | Remove Flatwork,Chain&Discing | Material | Hour |  | 8
3462-4251026 | Remove Asphalt Pave & Soulders | Material | Hour |  | 8
3462-4251027 | Remove Drain Struct & Ditch | Material | Hour |  | 8
3462-4251028 | Remove Headwall,SoundW,RW | Material | Hour |  | 8
3462-425109 | Sub-Haul | Material | Hour |  | 8
3462-420501 | RMV EXIST STRUCT/BRIDGE | Material | Each |  | 8
3462-420201 | REMOVAL OF EXISTING CONCRETE | Material | Square Yard |  | 8
3462-4252020 | TREE PROTECTION BARRIER | Material | Linear Feet |  | 8
3462-425802 | TREE ROOT/BRANCH PRUNE | Material | Each |  | 8
3462-430601 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3462-430602 | EMBANKMENT | Material | Cubic Yard |  | 8
3462-435701 | TYPE B STABILIZATION | Material | Square Yard |  | 8
3462-435101 | OPTIONAL BASE GROUP 01 | Material | Square Yard |  | 8
3462-435102 | OPTIONAL BASE GROUP 02 | Material | Square Yard |  | 8
3462-435103 | OPTIONAL BASE GROUP 06 | Material | Square Yard |  | 8
3462-435104 | OPTIONAL BASE GROUP 09 | Material | Square Yard |  | 8
3462-4401010 | MILL EXIST ASPHALT PVMT-1 1/2 | Material | Square Yard |  | 8
3462-4401020 | SUPERPAVE ASPHALT CONC-TRAFF B | Material | Ton |  | 8
3462-4401030 | ASPHALT CONC FRICTION CRS-TRFC | Material | Ton |  | 8
3462-440203 | MISC ASPHALT PAVEMENT | Material | Ton |  | 8
3462-445301 | PLAIN CEMENT CONC PVMT-9" | Material | Square Yard |  | 8
3462-445302 | PLAIN CEMENT CONC PVMT-14" | Material | Square Yard |  | 8
3462-525101 | CLEAN/SEAL JNT-CONC PAVE | Material | Linear Feet |  | 8
3462-5252020 | GRINDING CONC PAVEMENT | Material | Square Yard |  | 8
3462-476402 | CONC PVMT SLAB REPLACE | Material | Cubic Yard |  | 8
3462-517101 | CONC CL NS-GRAVITY WALL | Material | Cubic Yard |  | 8
3462-476401 | CONC CL II-BRIDGE SUPERSTRUCT | Material | Cubic Yard |  | 8
3462-484501 | CONC CL II-APP SLABS | Material | Cubic Yard |  | 8
3462-457806 | CONCRETE CLASS IV CULVERT | Material | Cubic Yard |  | 8
3462-475201 | CONC CL IV-BRIDGE SUBSTRUCT | Material | Cubic Yard |  | 8
3462-517102 | CONC CL IV-RETAINING WALL | Material | Cubic Yard |  | 8
3462-525201 | BRIDGE DECK GROOVING | Material | Square Yard |  | 8
3462-5253010 | CLEAN/COAT CONC SURFACE | Material | Square Feet |  | 8
3462-4825010 | COMPOSITE NEOPRENE PADS | Material | Each |  | 8
3462-535104 | REINF STEEL-ROADWAY | Material | LB |  | 8
3462-535105 | REINF STEEL- RETAIN WALL | Material | LB |  | 8
3462-535101 | REINF STEEL-BRIDGE SUPERSTRUCT | Material | LB |  | 8
3462-535102 | REINF STEEL- BRIDGE SUBSTRUCT | Material | LB |  | 8
3462-535103 | REINF STEEL-APP SLABS | Material | LB |  | 8
3462-457301 | INLETS-CURB-TY P-5<10' | Material | Each |  | 8
3462-457302 | INLETS-CURB-TY P-6<10' | Material | Each |  | 8
3462-457303 | INLETS-CURB-TY J-5>10' | Material | Each |  | 8
3462-457304 | INLETS-CURB-TYPE 7-<10' | Material | Each |  | 8
3462-457305 | INLETS-DT BOT-TYPE C,<10' | Material | Each |  | 8
3462-457306 | INLETS-DT BOT-TYPE C-MODIFY | Material | Each |  | 8
3462-457307 | INLETS-DT BOT-TYPE D-<10' | Material | Each |  | 8
3462-457308 | INLETS-DITCH BTM-TY D-J BOT<10 | Material | Each |  | 8
3462-457309 | INLETS-GUTTER-TYPE S-<10' | Material | Each |  | 8
3462-457201 | INLETS-MEDN BARR-TY 1<=10' | Material | Each |  | 8
3462-457202 | INLETS-MEDN BARR-TY 1-J BOT-< | Material | Each |  | 8
3462-457203 | INLETS-MEDN BARR-TY 2-< =10' | Material | Each |  | 8
3462-457204 | INLETS-MEDN BARR-TY 2->10' | Material | Each |  | 8
3462-457205 | INLETS-MEDN BARR-TY 2-J BOT-< | Material | Each |  | 8
3462-457206 | INLETS-ADJACENT BARR-<=10' | Material | Each |  | 8
3462-457207 | INLETS-ADJACENT BARR->10' | Material | Each |  | 8
3462-457208 | INLET-ADJACENT BARR-J BTM-< 10 | Material | Each |  | 8
3462-457209 | INLET-ADJACENT BARR-J BTM->10' | Material | Each |  | 8
3462-455801 | MANHOLES, P-8, <10' | Material | Each |  | 8
3462-455802 | MANHOLES, P-8, >10' | Material | Each |  | 8
3462-455803 | MANHOLES, P-8, PARTIAL | Material | Each |  | 8
3462-455804 | MANHOLES, J-8, <10' | Material | Each |  | 8
3462-455805 | MANHOLES, J-8, >10' | Material | Each |  | 8
3462-455401 | PIPE CULV-OPT MAT-RND-24" SD | Material | Linear Feet |  | 8
3462-455402 | PIPE CULV-OPT MAT-RND-30" SD | Material | Linear Feet |  | 8
3462-455403 | PIPE CULV-OPT MAT-RND-12" S/CD | Material | Linear Feet |  | 8
3462-455404 | PIPE CULV-OPT MAT-RND-15" S/CD | Material | Linear Feet |  | 8
3462-455405 | PIPE CULV-OPT MAT-RND-18" S/CD | Material | Linear Feet |  | 8
3462-455406 | PIPE CULV-OPT MAT-RND-24" S/CD | Material | Linear Feet |  | 8
3462-455407 | PIPE CULV-OPT MAT-RND-30" S/CD | Material | Linear Feet |  | 8
3462-455501 | PIPE CULV-OPT MAT-RND-36" S/CD | Material | Linear Feet |  | 8
3462-455502 | PIPE CULV-OPT MAT-RND-42" S/CD | Material | Linear Feet |  | 8
3462-455503 | PIPE CULV-OPT MAT-RND-48" S/CD | Material | Linear Feet |  | 8
3462-455408 | CULV-OPT MAT-OTHER-ELIP-18" | Material | Linear Feet |  | 8
3462-455409 | CULV-OPT MAT-OTHER-ELIP-36" | Material | Linear Feet |  | 8
3462-455400 | PIPE CULV-OPT MAT-RND-24"-J&B | Material | Linear Feet |  | 8
3462-4573010 | STRAIGHT CONC ENDWL-18"-SNGL | Material | Each |  | 8
3462-4573011 | STRAIGHT CONC ENDWL-24"-SNGL | Material | Each |  | 8
3462-4573012 | STRAIGHT CONC ENDWL-48"-SNGL | Material | Each |  | 8
3462-4573013 | U-ENDWL W/ BFL-INDX 261/430-01 | Material | Each |  | 8
3462-457601 | PIPE FILL/PLUG-PLACE OUT | Material | Cubic Yard |  | 8
3462-457801 | MES-OPTIONAL ROUND-18" | Material | Each |  | 8
3462-457802 | MES-OPTIONAL ROUND-30" | Material | Each |  | 8
3462-457803 | MES-OPTIONAL-ELLIP | Material | Each |  | 8
3462-457805 | MES-OPTIONAL ROUND-24" | Material | Each |  | 8
3462-457807 | MES+OPTIONAL ROUND-30" | Material | Each |  | 8
3462-457401 | UNDERDRAIN-TY V | Material | Linear Feet |  | 8
3462-457402 | UNDERDRAIN INSPECTION BOX | Material | Each |  | 8
3462-4574030 | UNDERDRAIN OUTLET PIPE-6" | Material | Linear Feet |  | 8
3462-4573016 | EDGEDRAIN DRAINCRETE-STNDRD | Material | Linear Feet |  | 8
3462-4573017 | EDGEDRAIN OUTLET PIPE-4" | Material | Linear Feet |  | 8
3462-476001 | PRESTRESSED BEAMS-TY II | Material | Linear Feet |  | 8
3462-476002 | PREST BEAMS-FLORIDA-I BEAM 36" | Material | Linear Feet |  | 8
3462-410203 | PREST SOIL ANCHORS | Material | Each |  | 8
3462-4102040 | PRESTRS SOIL ANCHR-PERFMC TEST | Material | Each |  | 8
3462-4102050 | PRESTRS SOIL ANCHOR-CREEP TEST | Material | Each |  | 8
3462-470602 | HP 14 X 89 NO OH RESTRICTION | Material | Linear Feet |  | 8
3462-470603 | HP LOW OVERHEAD 14 X 89 | Material | Linear Feet |  | 8
3462-470601 | STEEL PILE-HP 14 X 89 | Material | Linear Feet |  | 8
3462-470501 | DRILLED SHAFT- 48" DIA | Material | Linear Feet |  | 8
3462-4705030 | DS CASING-48" DIAMETER | Material | Linear Feet |  | 8
3462-4705040 | CORE-PILOT HOLE-DS EXCAVATIO | Material | Linear Feet |  | 8
3462-470101 | EXCAV UNCLASSFD SHAFT-48" DIA | Material | Linear Feet |  | 8
3462-465501 | WALL TW-1 SHT PILE TEMP CRITCL | Material | Square Feet |  | 8
3462-466401 | PDH HP LAG ALT LEAVE IN PLC | Material | Square Feet |  | 8
3462-466101 | PDH SOIL ANCHR TEMP CRITIL WAL | Material | Each |  | 8
3462-4705050 | THERMAL INTEGRTY TEST-UP TO 4' | Material | Each |  | 8
3462-4830010 | BRIDG DCK EXPNSN JNT-NEW CONST | Material | Linear Feet |  | 8
3462-425501 | CONCR CURB & GUTTER-TY E | Material | Linear Feet |  | 8
3462-425502 | CONCRETE CURB & GUTTER-TY F | Material | Linear Feet |  | 8
3462-425503 | CONCRETE CURB-TY D | Material | Linear Feet |  | 8
3462-425504 | SHOULDER GUTTER-CONCRETE | Material | Linear Feet |  | 8
3462-4255050 | GRANITE CURB-FURNISH/INSTL | Material | Linear Feet |  | 8
3462-4255060 | GRANITE CURB, RESET | Material | Linear Feet |  | 8
3462-521003 | CONC TRFC SEPRTR-SPECIAL-VAR | Material | Square Yard |  | 8
3462-521004 | MEDN CONC BAR-38" HEIGHT | Material | Linear Feet |  | 8
3462-521005 | MEDN CONC BARR-TALL GRADE-SEPA | Material | Linear Feet |  | 8
3462-521006 | MEDN CONC BARR-VARBL SECT | Material | Linear Feet |  | 8
3462-521001 | CONC TRFC RAIL-BRIDGE-36" | Material | Linear Feet |  | 8
3462-521002 | CONC TRAFF RAIL-BRIDGE-8 | Material | Linear Feet |  | 8
3462-521007 | CONC BARR W/ JUNCTN SLAB-8' | Material | Linear Feet |  | 8
3462-521008 | SHLDR CONC BARR WALL-8' NOISE | Material | Linear Feet |  | 8
3462-521009 | SHLDR CONC BARR WALL-14' NOISE | Material | Linear Feet |  | 8
3462-5210010 | SHLDR CONC BARR-38 OR 44" | Material | Linear Feet |  | 8
3462-5210011 | SHLDR CONC BARR-CURB/GUTR | Material | Linear Feet |  | 8
3462-425402 | CONC SDWK/DRVWY-4" THICK | Material | Square Yard |  | 8
3462-425403 | CONC SDWK/DRVWY-6" THICK | Material | Square Yard |  | 8
3462-425404 | CONC DITCH PVMT-NON REINFRCD | Material | Square Yard |  | 8
3462-425405 | PAVERS-ARCHITECTURAL-RDWY | Material | Square Yard |  | 8
3462-4254060 | DETECTABLE WARNINGS | Material | Square Feet |  | 8
3462-4568010 | RIPRAP-RUBBLE-F&I-DITCH LINING | Material | Ton |  | 8
3462-4259010 | GUARDRAIL-ROADWAY-GENERAL TL-3 | Material | Linear Feet |  | 8
3462-4259020 | GUARDRAIL REMOVAL | Material | Linear Feet |  | 8
3462-4259030 | GRDRL END TREAT-TRAILING ANCHR | Material | Each |  | 8
3462-4259040 | GRDRL END TREAT-PARALLEL APP | Material | Each |  | 8
3462-4259050 | GUARDRAIL RESET | Material | Linear Feet |  | 8
3462-4057020 | CRASH CUSHION, TL-3, NARROW | Material | Each |  | 8
3462-405703 | GROUND-IN RUMBLE STRIPS, 16" | Material | Gross Mile |  | 8
3462-517201 | MSE WALL | Material | Square Feet |  | 8
3462-517202 | MSE WALL CIP COPING | Material | Linear Feet |  | 8
3462-5173010 | RETAIN WALL SYS,TEMP-EXCLUDI | Material | Square Feet |  | 8
3462-517204 | RETAIN WALL SYS PERM-WIDEN | Material | Square Feet |  | 8
3462-4253010 | FENCE-TY B-5.1-6.0'-STAND | Material | Linear Feet |  | 8
3462-4253020 | FENCE-TY B-5.1-6.0-W/VINYL CT | Material | Linear Feet |  | 8
3462-42530110 | FENCE-TY B-6.1-7.0'-W/VINYL CT | Material | Linear Feet |  | 8
3462-4253030 | FENCE-MESH W/COAT-4' ON GRAVIT | Material | Linear Feet |  | 8
3462-4253040 | FENCE-MESH W/COATING-6'-PROJ | Material | Linear Feet |  | 8
3462-4253050 | FENCE-MESH W/COATING-8'-PROJ | Material | Linear Feet |  | 8
3462-4253060 | GATE-TY B-SNGL-6.1-12.0' | Material | Each |  | 8
3462-4253070 | GATE-TY B VINYL-SNGL-6.1- | Material | Each |  | 8
3462-42530120 | GATE-TY B W/VINYL COATING-D | Material | Each |  | 8
3462-4253080 | GATE-TY B VINYL-DOUBLE-12.1-1 | Material | Each |  | 8
3462-4253090 | GATE-4' H ON GRAVITY WALL-S | Material | Each |  | 8
3462-42530100 | GATE-6' H-DOUBLE-9' OPENIN | Material | Each |  | 8
3462-525302 | ANTI-GRAFFITI COAT-NON-SCRFCL | Material | Square Feet |  | 8
3462-4258030 | PERFORMANCE TURF | Material | Square Yard |  | 8
3462-410206 | PLASTIC ERO MAT-TURF REINF MAT | Material | Square Yard |  | 8
3462-891003 | CONDUIT-FURN/INSTL-OPEN TRNCH | Material | Linear Feet |  | 8
3462-891004 | CONDUIT-FURN/INSTL-DIRECTNL | Material | Linear Feet |  | 8
3462-891005 | CONDUIT-FURN/INSTL-ABOVE GRND | Material | Linear Feet |  | 8
3462-8910060 | CONDUIT-FURN/INSTL-BRIDGE MNT | Material | Linear Feet |  | 8
3462-891001 | CONDUIT-FURN/INSTL-EMBED | Material | Linear Feet |  | 8
3462-8910070 | CONDUIT, RMV, BRIDGE MOUNT | Material | Linear Feet |  | 8
3462-89800140 | FIBR OPTC CBL-F&I-UGRND,2-12 | Material | Linear Feet |  | 8
3462-89800150 | FIBR OPTC CBL-F&I-UGRND-97-144 | Material | Linear Feet |  | 8
3462-89800160 | FIBR OPTC CABLE-INSTL-UNDRGRND | Material | Linear Feet |  | 8
3462-89800170 | FIBR OPTC CABLE-RMV-UNDRGRND | Material | Linear Feet |  | 8
3462-89800180 | FIBR OPTC CNCT-INSTL-SPLICE | Material | Each |  | 8
3462-89800190 | FIBR OPTC CNCT HDW SPLCE ENCLS | Material | Each |  | 8
3462-89800200 | FIBR OPTC CNCT HDW SPLICE TRAY | Material | Each |  | 8
3462-89800210 | FIBR OPTC CNCT HDW PREDETERM | Material | Each |  | 8
3462-89800220 | MULTI-CONDUCTOR COMM CABLE-FUR | Material | Linear Feet |  | 8
3462-891008 | PULL/SPLICE BOX-F&I-13X 4" CVR | Material | Each |  | 8
3462-89800240 | PULL/SPLICE BOX-F&I-24X36" CVR | Material | Each |  | 8
3462-89800250 | PULL/SPLCE BOX-F&I-30X60" RECT | Material | Each |  | 8
3462-8910090 | JUNCTION BOX-F&I-AERIAL | Material | Each |  | 8
3462-89100100 | JUNCTION BOX-F&I-EMBEDDE | Material | Each |  | 8
3462-89100110 | ELEC POWER SERVC-F&I-UNDRGRND | Material | Each |  | 8
3462-89800260 | ELEC POWER SERVICE-RMV OVERHEA | Material | Each |  | 8
3462-89800280 | ELEC SERVICE WIRE-RMV | Material | Linear Feet |  | 8
3462-89800290 | ELEC SERVC DISCONNECT-F&I-POLE | Material | Each |  | 8
3462-89800300 | EMERGENCY GENRTR-PERM UP TO 25 | Material | Each |  | 8
3462-89800310 | ELEC PWR SERVICE-TRANSFORMR FU | Material | Each |  | 8
3462-89800320 | PRESTRES CONC POLE-TY P-I SRVC | Material | Each |  | 8
3462-89800330 | PRESTRESSED CONC POLE-TY P-III | Material | Each |  | 8
3462-89800340 | PRESTRESS CONC POLE-COMP RMV | Material | Each |  | 8
3462-89800350 | CONC CCTV POLE-LOWERING 75' | Material | Each |  | 8
3462-89800360 | CONC CCTV POLE-LOWERING 86' | Material | Each |  | 8
3462-89800370 | STEEL CCTV POLE-RMV POLE-COMP | Material | Each |  | 8
3462-89800380 | VDS-MICROWAVE-CABINET EQP | Material | Each |  | 8
3462-89800390 | VDS-MICROWAVE-ABOVE GRD | Material | Each |  | 8
3462-89800400 | VDS-MICROWAVE-RMV | Material | Each |  | 8
3462-89800410 | VDS-WRONG WAY FOR | Material | Each |  | 8
3462-89800420 | ITS CABINET-F&I-POLE W SHIELD | Material | Each |  | 8
3462-89800430 | ITS CABINET-F&I-BASE MOUNT | Material | Each |  | 8
3462-89800440 | ITS CABINET-RMV | Material | Each |  | 8
3462-89800450 | ITS CCTV CAMERA-DOME PTZ ENCLS | Material | Each |  | 8
3462-89800460 | MNG FIELD ETHERNET SWITCH | Material | Each |  | 8
3462-89800470 | DEVICE SERVER-FURNISH/INSTL | Material | Each |  | 8
3462-89800480 | WIRELESS COMM DEVICE-REL | Material | Each |  | 8
3462-89800490 | UNINTRUPT PWR SUP-LINE INTRACT | Material | Each |  | 8
3462-89800500 | REMOTE PWR MNGT UNIT-RPMU-FURN | Material | Each |  | 8
3462-8980070 | TRAFF MONITR SITE VEHICL SENSR | Material | Each |  | 8
3462-8980080 | TRAFF MONITOR SITE INDCTV LOOP | Material | Each |  | 8
3462-8980090 | TRAFF MONITOR SITE CAB-F&I-TY | Material | Each |  | 8
3462-89800100 | TRAFF MONITOR SITE CABINET-RMV | Material | Each |  | 8
3462-4055010 | SNGL PST SIGN-GRND MNT-UP T | Material | Each |  | 8
3462-4055020 | SNGL PST SIGN-GRND MNT-12-2 | Material | Each |  | 8
3462-4055030 | SNGL PST SIGN-F&I GRND MNT-31+ | Material | Each |  | 8
3462-4055040 | SNGL PST SIGN-BARR MT 12-20 SF | Material | Each |  | 8
3462-4055050 | SNGL PST SIGN-BRDG MT <12 SF | Material | Each |  | 8
3462-4055060 | SNGL PST SIGN-BRDG MT 12-20 SF | Material | Each |  | 8
3462-4055070 | SNGL PST SIGN, RMV | Material | Each |  | 8
3462-4055080 | SNGL PST SIGN-F&I CUST-31+ SF | Material | Each |  | 8
3462-4055090 | MULTI-PST SIGN-GRND MT 31-50 | Material | Each |  | 8
3462-40550100 | MULTI-PST SIGN-GRD MT 301-400 | Material | Each |  | 8
3462-40550110 | MULTI-PST SIGN-GRND MNT-RELO | Material | Each |  | 8
3462-40550120 | MULTI-PST SIGN, RMV | Material | Each |  | 8
3462-40550130 | SIGN PANEL, OH MTD UP TO 12 | Material | Each |  | 8
3462-40550140 | SIGN PANEL, OH MTD 21-31 SF | Material | Each |  | 8
3462-40550150 | SIGN PANEL, OH MTD 51-100 SF | Material | Each |  | 8
3462-40550160 | SIGN PANEL, OH MTD 101-200 SF | Material | Each |  | 8
3462-40550170 | SIGN PANEL, OH MTD 201-300 SF | Material | Each |  | 8
3462-40550180 | SIGN PANEL, OH MTD 301-400 SF | Material | Each |  | 8
3462-40550190 | SIGN PNL-SNGL PST BRIDG MTD | Material | Each |  | 8
3462-40550200 | SIGN PANEL-RMV-UP TO 12 SF | Material | Each |  | 8
3462-40550210 | SIGN PANEL, RMV, 12-20 SF | Material | Each |  | 8
3462-40550220 | SIGN PANEL, RMV, 21-30 SF | Material | Each |  | 8
3462-40550230 | SIGN PANEL, RMV, 31-50 SF | Material | Each |  | 8
3462-40550240 | SIGN PANEL, RMV, 51-100 SF | Material | Each |  | 8
3462-40550250 | SIGN PANEL, RMV, 101-200 SF | Material | Each |  | 8
3462-40550260 | SIGN PANEL, RMV, 201-300 SF | Material | Each |  | 8
3462-40550270 | OH SIGN STRUCT-UP TO 20 SF | Material | Each |  | 8
3462-40550280 | OH SIGN STRUCT-31-40 SF | Material | Each |  | 8
3462-40550290 | OH SIGN STRUCT-41-50 SF | Material | Each |  | 8
3462-40550300 | OH SIGN STRUCT-51-100 SF | Material | Each |  | 8
3462-40550310 | OH SIGN STRUCT-101-150 SF | Material | Each |  | 8
3462-40550320 | OH SIGN STRUCT-151-200 SF | Material | Each |  | 8
3462-40550330 | OH SIGN STRUCT-BRIDGE MTD | Material | Each |  | 8
3462-40550340 | OH SIGN-RMV MONOTUBE | Material | Each |  | 8
3462-40550350 | OH SIGN-RMV BRIDGE MTD | Material | Each |  | 8
3462-89800510 | HIGHLHT SIGN-F&I GRND MNT-AC P | Material | Each |  | 8
3462-89800520 | WALK-IN DYNMC MSG SIGN-UPS CLR | Material | Each |  | 8
3462-89800530 | WALK-IN DYNMC MESSAGE SIGN-RMV | Material | Each |  | 8
3462-40550360 | RETROREFLECT SIGN STRIP-FURN | Material | Each |  | 8
3462-40530150 | PROFLE THMPLSTC-CONC WH 6" SOL | Material | Gross Mile |  | 8
3462-40530160 | PROFLE THMPLSTC,CONC YL 6" SOL | Material | Gross Mile |  | 8
3462-40530170 | OBJECT MARKER, TY 3 | Material | Each |  | 8
3462-4053010 | PAINT PVMT MRK-WH SOLID 6" | Material | Gross Mile |  | 8
3462-4053020 | PAINT PVMT MRK-WH 8" | Material | Gross Mile |  | 8
3462-4053030 | PAINT PVMT MRK-WH 12" | Material | Gross Mile |  | 8
3462-4053040 | PAINT PVMT MRK-WH 18" | Material | Linear Feet |  | 8
3462-4053050 | PAINT PVMT MRK-WH 24" | Material | Linear Feet |  | 8
3462-4053060 | PAINT PVMT MRK-WH SKIP | Material | Gross Mile |  | 8
3462-4053070 | PAINT PVMT MRK-WH 12' PLAZA | Material | Gross Mile |  | 8
3462-4053080 | PAINT PVMT MRK-WH MESSAGE | Material | Each |  | 8
3462-4053090 | PAINT PVMT MRK-WH ARROWS | Material | Each |  | 8
3462-40530100 | PAINT PVMT MRK-YL SOLID 6" | Material | Gross Mile |  | 8
3462-40530110 | PAINT PVMT MRK-YL 8" | Material | Gross Mile |  | 8
3462-40530120 | PAINT PVMT MRK-YL 18" | Material | Linear Feet |  | 8
3462-40530130 | PAINT PVMT MRK-BLK 6" | Material | Gross Mile |  | 8
3462-40530140 | PAINT PVMT MRK-BLK 12" PLAZA | Material | Gross Mile |  | 8
3462-4053018 | PAINT PVMT MARK,FNL SURF | Material | Lump Sum |  | 8
3462-40530200 | THRMPLSTC-STAND-WH-SOLID-8" | Material | Gross Mile |  | 8
3462-40530210 | THRMPLSTC-STAND-WH-SOL-12" INT | Material | Gross Mile |  | 8
3462-40530220 | THRMPLSTC-STAND-WH SOL 12" CRS | Material | Linear Feet |  | 8
3462-40530230 | THRMPLSTC-STAND-WH-18" DIAG | Material | Linear Feet |  | 8
3462-40530240 | THRMPLSTC-STAND-WH-SOLID-24" | Material | Linear Feet |  | 8
3462-40530250 | THRMPLSTC-STAND-WHITE-ARROW | Material | Each |  | 8
3462-40530260 | THRMPLSTC-STAND-YL SOLID 18" | Material | Linear Feet |  | 8
3462-40530270 | THRMPLSTC-PREFORMED-WH 24" | Material | Linear Feet |  | 8
3462-40530280 | THMPLSTC-PREFORMED-WHITE W/BLA | Material | Each |  | 8
3462-40530290 | THMPLSTC-PREFORMED-WHITE W/BLA | Material | Each |  | 8
3462-40530300 | THMPLSTC-STAND-OTHER WH 6" SOL | Material | Gross Mile |  | 8
3462-40530310 | THMPLSTC-STAND-OTHER WH 8" SOL | Material | Gross Mile |  | 8
3462-40530320 | THMPLSTC-STAND-OTHER WH SKIP | Material | Gross Mile |  | 8
3462-40530330 | THMPLSTC-STAND-OTHER YL 6" SOL | Material | Gross Mile |  | 8
3462-40530340 | PERM TAPE-WHITE-SOLID-6"-BRIDG | Material | Gross Mile |  | 8
3462-40530350 | PERM TAPE-WHITE-SOLID DROP 12" | Material | Gross Mile |  | 8
3462-40530360 | PERM TAPE-WHITE-SKIP/DOT-6" F | Material | Gross Mile |  | 8
3462-40530370 | PERM TAPE-WHITE-SKIP-12" WIDE | Material | Gross Mile |  | 8
3462-40530380 | PERM TAPE-YELW-SOLID-6" FOR CO | Material | Gross Mile |  | 8
3462-40530390 | PERM TAPE-BLACK-SKIP/DOT-6" F | Material | Gross Mile |  | 8
3462-40530400 | PERM TAPE-BLCK-3'-9' DROP LANE | Material | Gross Mile |  | 8
3462-89100130 | LIGHT CONDUCTORSINSUL-NO. 10 | Material | Linear Feet |  | 8
3462-89100140 | LIGHT CONDUCTORS-INSUL-NO.8-6 | Material | Linear Feet |  | 8
3462-89100150 | LIGHT CONDUCTORS-INSUL-NO4-2 | Material | Linear Feet |  | 8
3462-89100160 | LIGHT CONDUCTORS-RMV/DISPOSE-C | Material | Linear Feet |  | 8
3462-89100170 | LIGHT POLE COMPLETE-50' HEIGHT | Material | Each |  | 8
3462-89100180 | LIGHT POLE COMP-SPECIAL 50' | Material | Each |  | 8
3462-89100190 | LIGHT POLE COMP-RMVEPOLE/FNDTN | Material | Each |  | 8
3462-89100200 | LUMIN/BRACKET ARM-RMV LUMIN | Material | Each |  | 8
3462-89100210 | LOAD CENTER-F&I-SECONDARY VOLT | Material | Each |  | 8
3462-89100220 | LUMIN-F&I-UNDER DECK-WALL MNT | Material | Each |  | 8
3462-89100230 | LUMIN-F&I-REPLACE EXIST LUMIN | Material | Each |  | 8
3462-89100240 | LUMINAIRE, RMV | Material | Each |  | 8
3462-89100250 | POLE CABLE DIST SYS-CONVENT | Material | Each |  | 8
3462-89100260 | POLE CABLE DIST SYS-WALL MOU | Material | Each |  | 8
3462-89100270 | LIGHT POLE COMP-DESIGN-50' TOP | Material | Each |  | 8
3462-95900 | PUNCHLIST | Material | Day |  | 8
3462-Cost | 3462 - Cost | Nonlabor |  |  | 1
3462-8910011 | ELEC SRVC WIRE, FURN/INSTL | Material | Linear Feet |  | 8
3461-Revenue | 3461 - SOV | Nonlabor |  |  | 1
3461-CBE-WO | Capital Beltway Express Work Orders | Material |  |  | 1
9156-Jordan Rd Work | Jordan Rd Work | Material | Unit |  | 8
3463 - 10102296_Cost | Cost | Nonlabor |  |  | 2
3463 - 10102296_LMH | Direct Labor Manhours | Labor |  |  | 2
3463 | 3463 - I-3306A | Nonlabor |  |  | 1
9156-Additional Noise Wall Settlement | Additional Noise Wall Settlement | Material | Unit |  | 8
9156-Material Cost Escalation | Material Cost Escalation | Material | Lump Sum |  | 8
3465 | 3465 - Tyndall | Nonlabor |  |  | 1
3465 - Project Revenue | Project Revenue | Material |  |  | 8
3418-0055 | 3418-0055 - Price Escalation Program - CO #21 | Material | Dollar |  | 8
9156-SA45 | SA#45 - I-42 SIGNAGE – DESIGN AND CONSTRUCTION | Material | Lump Sum |  | 8
3462-4752013 | Formwork-BridgeSubS | Material | Square Feet |  | 8
3462-4764012 | Clean&Adjust Overhang Brackets | Material | Each |  | 8
3462-4764014 | Formwork-SIP-BridgeSuperS | Material | Square Feet |  | 8
3462-5171018 | Slope Pavement-Gravity Wall | Material | Square Yard |  | 8
3462-5253020 | ANTI-GRAFFITI COAT-NON-SCRFCL-BRIDGE | Material | Square Feet |  | 8
3462-456801 | RIPRAP-RUBBLE | Material | Ton |  | 8
3462-5253030 | ANTI-GRAFFITI COAT-NON-SCRFCL - WALLS | Material | Square Feet |  | 8
3462-4306023 | Fine Grade | Material | Square Yard |  | 8
3462-5253040 | ANTI-GRAFFITI COATING, NON-SACRIFICIAL - SIGNS | Material | Square Feet |  | 8
3461-Cost | 3461 - Cost | Nonlabor |  |  | 1
3461-302500 | GENERALCONTRACTING | Material |  |  | 8
3461-302501 | DESIGN SERVICE | Material |  |  | 8
3461-302502 | Shirley Direct Cost Area 1/2 | Material |  |  | 8
3461-302503 | Shirley Direct Cost Area 4 | Material |  |  | 8
3461-302504 | Shirley Indirect Cost | Material |  |  | 8
3461-40501 | O&M DURING CONSTRUCTION | Material |  |  | 8
3461-30012 | O&M GUARDRAIL | Material |  |  | 8
3461-425051 | POTHOLE REPAIR | Material |  |  | 8
3461-30021 | PUBLIC COMM & OUTREACH | Material |  |  | 8
3461-13300 | MAINTENANCE DURING CONSTRUCTION | Material |  |  | 8
3461-42000 | DEMOLITION & SITE PREPARATION | Material |  |  | 8
3461-30031 | CLEARING & GRUBBING | Material |  |  | 8
3461-42060 | DEMO-DRAINAGE | Material |  |  | 8
3461-42010 | DEMO-AC PAVEMENT | Material |  |  | 8
3461-42020 | DEMO-CONC PAVEMENT | Material |  |  | 8
3461-30041 | SAW CUT, FULL DEPTH | Material |  |  | 8
3461-30051 | FLEXIBLE PAVEMENT (MILLING) | Material |  |  | 8
3461-42050 | DEMO-WALL/BARRIER/MISC STRUCT | Material |  |  | 8
3461-4204001 | DEMO EXIST STRUCTURE (BRIDGE) | Material |  |  | 8
3461-30013 | GUARDRAIL REMOVAL | Material |  |  | 8
3461-41000 | EROSION CONTROL | Material |  |  | 8
3461-43140 | TOPSOIL | Material |  |  | 8
3461-30071 | SEEDING & FERTILIZER | Material |  |  | 8
3461-30081 | EROSION CONTROL | Material |  |  | 8
3461-43020 | CONSTRUCTION ACCESS | Material |  |  | 8
3461-41020 | EROSION CONTROL-DEVICES | Material |  |  | 8
3461-41010 | EROSION CONTROL-CREW | Material |  |  | 8
3461-30091 | LANDSCAPING | Material |  |  | 8
3461-43000 | EARTHWORK | Material |  |  | 8
3461-43060 | ROADWAY EXCAVATION/FILL | Material |  |  | 8
3461-43160 | UNSUITABLE EXCAVATION/BACKFILL | Material |  |  | 8
3461-43340 | SG STAB GEOTEXTILE | Material |  |  | 8
3461-43500 | PAVEMENT BASE | Material |  |  | 8
3461-43540 | CEMENT TREATED BASE/SUBGRADE | Material |  |  | 8
3461-43530 | AGGREGATE BASE COURSE | Material |  |  | 8
3461-30101 | ASPHALT | Material |  |  | 8
3461-30111 | CURB & GUTTER | Material |  |  | 8
3461-42570 | SIDEWALK | Material |  |  | 8
3461-30124 | SAWCUTTING & SEALING | Material |  |  | 8
3461-30102 | PAVEMENT JOINT REPAIRS TYPE 3 | Material |  |  | 8
3461-30103 | PAVEMENT JOINT REPAIRS TYPE 4 | Material |  |  | 8
3461-30113 | FULL DEPTH PCC PAVE PATCHING | Material |  |  | 8
3461-435001 | LANE SUB ASSIST | Material |  |  | 8
3461-52000 | ROADWAY BARRIER | Material |  |  | 8
3461-30011 | GUARDRAIL | Material |  |  | 8
3461-30115 | MEDIAN BARRIER MB | Material |  |  | 8
3461-30141 | NS MEDIAN BARRIER GLARE SCREEN | Material |  |  | 8
3461-30151 | FENCE | Material |  |  | 8
3461-30152 | HANDRAIL HR-1 | Material |  |  | 8
3461-30160 | SIGNING & PAVEMENT MARKING | Material |  |  | 8
3461-30161 | PAVEMENT MARKING | Material |  |  | 8
3461-30180 | LIGHTING & SIGNALIZATION | Material |  |  | 8
3461-30181 | LIGHTHING | Material |  |  | 8
3461-30190 | SIGNAL | Material |  |  | 8
3461-30171 | OVERHEAD & GROUND MOUNTED SIGNAGE | Material |  |  | 8
3461-45500 | DRAINAGE & STORM STRUCTURES | Material |  |  | 8
3461-45572 | ENDWALL JUNCTION BOX | Material |  |  | 8
3461-30210 | UNDERDRAIN | Material |  |  | 8
3461-30212 | OUTLET PIPE | Material |  |  | 8
3461-45761 | MOD ADJ EXIST STRUCTURES | Material |  |  | 8
3461-45540 | STORM DRAIN PIPE (12-30 IN) | Material |  |  | 8
3461-45550 | STORM DRAIN PIPE (36-54 IN) | Material |  |  | 8
3461-45560 | STORM DRAIN PIPE (60 IN+) | Material |  |  | 8
3461-45660 | JACK AND BORE | Material |  |  | 8
3461-30251 | NS PIPE REPAIR/PIPELINER | Material |  |  | 8
3461-45573 | END SECTION | Material |  |  | 8
3461-45571 | DROP INLETS | Material |  |  | 8
3461-45581 | MH-1 or 2 | Material |  |  | 8
3461-45582 | INSTALL MH F&C | Material |  |  | 8
3461-45680 | RIP-RAP | Material |  |  | 8
3461-30261 | STREAM RESTORATION | Material |  |  | 8
3461-30262 | PAVED DITCH PG-2A -6' WIDE | Material |  |  | 8
3461-30252 | CIPP LINER | Material |  |  | 8
3461-47500 | BRIDGES | Material |  |  | 8
3461-41021 | BRIDGE DECK GROOVING - AREA 3 | Material |  |  | 8
3461-30281 | PREPARE AND SPOT COAT EXISTING STRUCTURE - AREA 3 | Material |  |  | 8
3461-30282 | NS DISPOSAL OF MATERIAL-AREA 3 | Material |  |  | 8
3461-30283 | NS ENV. PROT. & HEALTH SAFETY-AREA 3 | Material |  |  | 8
3461-30291 | EMBEDDED GALVANIC ANODES-AREA 3 | Material |  |  | 8
3461-30292 | PATCHING TYPE B-AREA 3 | Material |  |  | 8
3461-30293 | PATCHING TYPE B-AREA 4 | Material |  |  | 8
3461-30294 | PATCHING TYPE C-AREA 3 | Material |  |  | 8
3461-30295 | PATCHING TYPE C-AREA 4 | Material |  |  | 8
3461-30296 | DECK JOINT ELIMINATION-AREA 3 | Material |  |  | 8
3461-30297 | JACKING AND BLOCKING BEAM-AREA 4 | Material |  |  | 8
3461-30298 | CONCRETE SUPERSTRUCTURE SURFACE REPAIR-AREA 3 | Material |  |  | 8
3461-30299 | REPLACE ANCHOR BOLT-AREA 3 | Material |  |  | 8
3461-30300 | ADHESIVE BASED JOINT SEALER CLASS I, 1"-AREA 4 | Material |  |  | 8
3461-30301 | CLEAN AND RESEAL EXPANSION JOINT-AREA 4 | Material |  |  | 8
3461-30053 | REMOVE ASPHALT CONCRETE OVERLAY-AREA 3 | Material |  |  | 8
3461-30302 | TYPE A MILLING 1"-AREA 3 | Material |  |  | 8
3461-30303 | FURNISH VES LATEX MOD CONC (1 1/2" - 2")-AREA 3 | Material |  |  | 8
3461-30304 | PLACE VES LATEX MODIFIED CONCRETE-AREA 3 | Material |  |  | 8
3461-30305 | TYPE A HYDRO-DEMOLITION 1/2"-AREA 3 | Material |  |  | 8
3461-30306 | EPOXY OVERLAY-AREA 4 | Material |  |  | 8
3461-30307 | BEAM END REPAIR-AREA 4 | Material |  |  | 8
3461-30308 | CLEAN AND PAINT BEARINGS-AREA 3 | Material |  |  | 8
3461-30309 | EMBEDDED GALVANIC ANODES-AREA 3 | Material |  |  | 8
3461-30310 | CONCRETE SUBSTRUCTURE SURFACE REPAIR-AREA 3 | Material |  |  | 8
3461-30311 | CONCRETE SUBSTRUCTURE SURFACE REPAIR-AREA 4 | Material |  |  | 8
3461-30312 | CRACK REPAIR TYPE B-AREA 3 | Material |  |  | 8
3461-30313 | RAILING REPAIR (ALUMINUM)-AREA 4 | Material |  |  | 8
3461-30314 | TEMPORARY SHIELD FOR REPAIR-AREA 4 | Material |  |  | 8
3461-30315 | NBIS ACCESS, UNDER BRIDGE-AREA 3 | Material |  |  | 8
3461-30316 | NBIS ACCESS, UNDER BRIDGE-AREA 4 | Material |  |  | 8
3461-30317 | CLEAN AND WASH ABUTMENTS AND PIERS-AREA 3 | Material |  |  | 8
3461-30318 | REMOVE VEGETATION-AREA 4 | Material |  |  | 8
3461-30319 | UNCLOG DECK DRAINS-AREA 4 | Material |  |  | 8
3461-47640 | CONC CLASS A4 SUPERSTRUCTURE | Material |  |  | 8
3461-48450 | CONC CL A4 BRIDGE APPR. SLAB | Material |  |  | 8
3461-30133 | APP SLAB F&I REBAR | Material |  |  | 8
3461-52521 | SLAB BRIDGE DECK GROOVING | Material |  |  | 8
3461-30331 | COVER DEPTH SURVEY | Material |  |  | 8
3461-47600 | STR.STEEL PLATE GIRDER | Material |  |  | 8
3461-5254001 | ARCHITECTURAL TREATMENT | Material |  |  | 8
3461-5210001 | RAILING, CPSR 1 RAIL | Material |  |  | 8
3461-5210002 | RAILING, CPSR 2 RAIL | Material |  |  | 8
3461-5210003 | CONCRETE PARAPET 32" | Material |  |  | 8
3461-5210004 | CONCRETE PARAPET 42" | Material |  |  | 8
3461-4701001 | STRUCTURE EXCAVATION/BFILL | Material |  |  | 8
3461-4702001 | SELECT BACKFILL ABUTMENT ZONE | Material |  |  | 8
3461-4571001 | BRIDGE WALL DRAIN / UNDERDRAIN | Material |  |  | 8
3461-46550 | TEMP SUPPORT OF EXCAVATION | Material |  |  | 8
3461-4706001 | 12" STEEL PILE | Material |  |  | 8
3461-4706007 | 14" STEEL PILE | Material |  |  | 8
3461-4752001 | CONCRETE CLASS A3-SUBSTRUCTURE | Material |  |  | 8
3461-5351001 | SUBSTRUCTURE REINFORCING STEEL | Material |  |  | 8
3461-5351002 | SUBSTRUCTUR PROTECTION CORR | Material |  |  | 8
3461-4109001 | ARTICULATED CONC BLOCK | Material |  |  | 8
3461-5210005 | PEDESTRIAN FENCE | Material |  |  | 8
3461-4850001 | BRIDGE DECK DRAIN / CONDUIT | Material |  |  | 8
3461-4815001 | NBIS ACCESS, UNDER BRIDGE (VDOT Inspection) | Material |  |  | 8
3461-51700 | RETAINING WALLS | Material |  |  | 8
3461-5151004 | RETAINING WALL RW-3 | Material |  |  | 8
3461-5173001 | COMBO WALL (RETAINED PORTION) | Material |  |  | 8
3461-5173007 | POST & PANEL | Material |  |  | 8
3461-5172001 | MSE WALLS | Material |  |  | 8
3461-5253001 | CONC. SURF. COLOR COATING | Material |  |  | 8
3461-4655002 | TEMP SOE RET WALLS | Material |  |  | 8
3461-4701002 | RETAINING WALL EXCAVATION | Material |  |  | 8
3461-4153000 | UTILITIES | Material |  |  | 8
3461-30061 | UTILITY LOCATING SERVICE | Material |  |  | 8
3461-4153001 | DRY UTILITY RELOCATION | Material |  |  | 8
3461-4155001 | WET UTILITY RELOCATIONS | Material |  |  | 8
3461-30440 | ITS & TMS EQ | Material |  |  | 8
3461-30441 | ITS & TMS EQ | Material |  |  | 8
3461-30450 | TMS SUBCONTR | Material |  |  | 8
3461-30451 | TMS SUBCONTR | Material |  |  | 8
3461-5253000 | NOISE-GM | Material |  |  | 8
3461-5253002 | SOUND WALL COATING, GND MNT | Material |  |  | 8
3461-5174001 | NOISE BARRIERS - GND MNT | Material |  |  | 8
3461-5253003 | NOISE-RWM | Material |  |  | 8
3461-5253004 | SOUND WALL COATING, RW MNT | Material |  |  | 8
3461-5174004 | NOISE BARRIERS - RW MNT | Material |  |  | 8
3461-5174007 | NOISE-BM | Material |  |  | 8
3461-5174010 | NOISE-BM MNT | Material |  |  | 8
3461-23900 | ENVIRONMENTAL CREDITS | Material |  |  | 8
3461-23901 | ENVIRONMENTAL CREDITS | Material |  |  | 8
3461-410000 | TRAFFIC CONTROL | Material |  |  | 8
3461-4659001 | TEMPORARY WOTKS (MOT) | Material |  |  | 8
3461-4056001 | IMPACT ATTEN. SER. | Material |  |  | 8
3461-4252002 | TEMP. SAFETY FENCE & BARRICADE | Material |  |  | 8
3461-4054001 | TEMPORARY CONSTRUCTION SIGNS | Material |  |  | 8
3461-4054002 | PORTABLE CHANGEABLE MESSAGE SIGN | Material |  |  | 8
3461-4054003 | TRAFFIC BARREL | Material |  |  | 8
3461-4051001 | MOT CREW | Material |  |  | 8
3461-4059001 | POLICE PATROL | Material |  |  | 8
3461-4052001 | TRAFFIC BARRIER SER. CONC.MB-7D PC | Material |  |  | 8
3461-4052006 | MB-10A SET & LOAD TRAF. BARR. SER. CONC. | Material |  |  | 8
3461-4053001 | TEMP. PVMT MRKG | Material |  |  | 8
3461-20400 | 21B BASE MATERIAL | Material |  |  | 8
3461-21101 | STORM DRAIN PIPE (12-30 IN) PIPE | Material |  |  | 8
3461-21102 | STORM DRAIN PIPE (36-54 IN) PIPE | Material |  |  | 8
3461-21103 | STORM DRAIN PIPE (60 IN+) PIPE | Material |  |  | 8
3461-21104 | JACK AND BORE PIPE | Material |  |  | 8
3461-21501 | STEEL PILE 12" - MAT | Material |  |  | 8
3461-21502 | STEEL PILE 14" - MAT | Material |  |  | 8
3461-2160001 | SHEET PILE MATERIAL (EXCAVATION) | Material |  |  | 8
3461-21603 | SHEET PILE MATERIAL SOE RET | Material |  |  | 8
3461-21801 | BEARING MATERIAL | Material |  |  | 8
3461-21910 | MSE WALL PANEL MAT | Material |  |  | 8
3461-21911 | PRECAST COPING & SLAB MAT | Material |  |  | 8
3461-21912 | CIP MOMENT SLAB & COPING MAT | Material |  |  | 8
3461-22010 | CONCRETE PANELS MAT | Material |  |  | 8
3461-22011 | CONCRETE POST MAT | Material |  |  | 8
3461-22101 | CONCRETE POST - MAT | Material |  |  | 8
3461-22102 | CONCRETE PANEL & DOORS | Material |  |  | 8
3461-22103 | NOISE RWM ANCHOR BOLT I&R | Material |  |  | 8
3461-22104 | NOISE BARRIERS - RW MNT - MAT | Material |  |  | 8
3461-22105 | NOISE BM ANCHOR BOLT I&R | Material |  |  | 8
3461-22601 | SIP FORMS | Material |  |  | 8
3461-22700 | STRUCTURAL STEEL | Material |  |  | 8
3461-22901 | MB - REBAR MATERIAL | Material |  |  | 8
3461-22902 | REBAR APP SLAB | Material |  |  | 8
3461-22903 | RAILING, CPSR 1 RAIL - REBAR | Material |  |  | 8
3461-22904 | RAILING, CPSR 2 RAIL -REBAR | Material |  |  | 8
3461-22905 | CONCRETE PARAPET 32" -REBAR | Material |  |  | 8
3461-22906 | CONCRETE PARAPET 42" - REBAR | Material |  |  | 8
3461-22907 | SUBSTRUCTURE REINFORCING STEEL - MAT | Material |  |  | 8
3461-30052 | MILLING & LOAD | Material |  |  | 8
3461-30116 | MB- INSTALL | Material |  |  | 8
3461-30120 | CIP MEDIAN BARRIER ON TOP OF DI-10 | Material |  |  | 8
3461-30134 | REBAR APP SLAB INST | Material |  |  | 8
3461-30211 | UNDERDRAIN | Material |  |  | 8
3461-30220 | VIDEO INSPECTION - UD | Material |  |  | 8
3461-30320 | SIP INSTALL | Material |  |  | 8
3461-30340 | F&I SHEAR STUDS | Material |  |  | 8
3461-30350 | ERECT STRUCTURAL STEEL | Material |  |  | 8
3461-35101 | HAUL CONSTRUCTION ACCESS | Material |  |  | 8
3461-35102 | HAUL EROSION CONTROL | Material |  |  | 8
3461-35103 | EROSION CONTROL-CREW HAUL | Material |  |  | 8
3461-35104 | HAUL BY TN | Material |  |  | 8
3461-35105 | HAUL BASE | Material |  |  | 8
3461-35106 | SIDEWALK HAUL | Material |  |  | 8
3461-35107 | MB- HAULING | Material |  |  | 8
3461-35110 | HAUL ENDWALL JUNCTION BOX | Material |  |  | 8
3461-35111 | STORM DRAIN PIPE (12-30 IN) HAUL | Material |  |  | 8
3461-35112 | STORM DRAIN PIPE (36-54 IN) HAUL | Material |  |  | 8
3461-35113 | STORM DRAIN PIPE (60 IN+) HAUL | Material |  |  | 8
3461-35114 | JACK AND BORE HAUL | Material |  |  | 8
3461-35115 | HAUL DROP INLETS | Material |  |  | 8
3461-35116 | HAUL RIP-RAP | Material |  |  | 8
3461-35117 | HAUL BASE MATERIAL | Material |  |  | 8
3461-35118 | SELECT BACKFILL ABUTMENT ZONE - HAUL | Material |  |  | 8
3461-35120 | ARTICULATED CONC BLOCK - HAUL | Material |  |  | 8
3461-35122 | COMBO HAUL - FILL | Material |  |  | 8
3461-35123 | POST & PANEL HAUL - FILL | Material |  |  | 8
3461-35124 | MSE WALL PANEL HAUL | Material |  |  | 8
3461-35125 | MAT HAULING | Material |  |  | 8
3461-35401 | HAUL EXIST PIPE/STRUCT | Material |  |  | 8
3461-35402 | HAUL ASPHALT | Material |  |  | 8
3461-35403 | HAUL CONCRET PAVMENT | Material |  |  | 8
3461-35404 | HAULING MILLING | Material |  |  | 8
3461-35405 | HAUL CONC BARRIER | Material |  |  | 8
3461-35406 | HAUL TOPSOIL | Material |  |  | 8
3461-35407 | HAUL EXCAVATION | Material |  |  | 8
3461-35408 | HAUL UNSUITABLE | Material |  |  | 8
3461-35411 | STRUCTURE EXCAVATION/BFILL HAUL | Material |  |  | 8
3461-35413 | HAULING | Material |  |  | 8
3461-4052003 | MB - 7D RESET TEMP BARRIER | Material |  |  | 8
3461-4052004 | MB-7D REMOVE BARRIER TO STOCKPILE | Material |  |  | 8
3461-4052005 | MB- 7D SET & LOAD OUT TEMP BARRIER | Material |  |  | 8
3461-4052007 | MB-10A SET & LOAD OUT TEMP BARRIER | Material |  |  | 8
3461-4052008 | MB-10A RESET TEMP BARRIER | Material |  |  | 8
3461-4052009 | MB-10A REMOVE BARRIER TO STOCKPILE | Material |  |  | 8
3461-4056002 | I&R TEMP ATTENUATOR | Material |  |  | 8
3461-4056003 | RESET TEMP ATTENUATOR | Material |  |  | 8
3461-4056004 | REP/REPL DAMAGES ATTENUATOR | Material |  |  | 8
3461-41011 | EROSION CONTROL-CREW MAINTENANCE | Material |  |  | 8
3461-41022 | EROSION CONTROL -DEVICES | Material |  |  | 8
3461-4109002 | ARTICULATED CONC BLOCK - INST | Material |  |  | 8
3461-4151001 | RW-3 - UTILITIES | Material |  |  | 8
3461-4151003 | UTILITY LOCATES- COMBO WALL | Material |  |  | 8
3461-4151004 | UTILITY LOCATES | Material |  |  | 8
3461-4151005 | UTILITY LOCATE | Material |  |  | 8
3461-4153002 | DRY UTILITY RELOC - ELECTR. DOMINION &Fee | Material |  |  | 8
3461-4153003 | DRY UTILITY RELOC - ELECTRICITY PEPCO Fee | Material |  |  | 8
3461-4153004 | UTY-POWER DISTRIBUTION | Material |  |  | 8
3461-4153005 | UTY-TRANSMISSION POWER | Material |  |  | 8
3461-4154001 | DRY UTILITY RELOC - GAS & Fee | Material |  |  | 8
3461-4155002 | WATER UTILITY RELOC | Material |  |  | 8
3461-4155003 | SEWER UTILITY RELOC | Material |  |  | 8
3461-42011 | HOREAM ASPHALT | Material |  |  | 8
3461-42012 | LOAD ASPHALT | Material |  |  | 8
3461-42021 | HOREAM CONCRETE PAVMENT | Material |  |  | 8
3461-42022 | LOAD CONCRETE PAVMENT | Material |  |  | 8
3461-42051 | HOE RAM CONC BARRIER | Material |  |  | 8
3461-42052 | LOAD CONC BARRIER | Material |  |  | 8
3461-42053 | REMOVE NOISE BARRIER GND | Material |  |  | 8
3461-42054 | REMOVE NOISE BARRIER STR | Material |  |  | 8
3461-42061 | FLOWFILL EXIST PIPE | Material |  |  | 8
3461-42062 | DEMO EXIST PIPE/STRUCT | Material |  |  | 8
3461-42571 | SIDEWALK PLACE | Material |  |  | 8
3461-4302001 | NOISE RWM ACCESS BENCHING FOR GMSW | Material |  |  | 8
3461-4302002 | NOISE RWM FINISH GRADING TO GMSW | Material |  |  | 8
3461-4302003 | COMBO ACCESS BENCHING FOR GMSW | Material |  |  | 8
3461-4302004 | POST & PANEL ACCESS BENCHING FOR GMSW | Material |  |  | 8
3461-4302005 | COMBO FINISH GRADING TO GMSW | Material |  |  | 8
3461-4302006 | POST & PANEL FINISH GRADING TO GMSW | Material |  |  | 8
3461-43021 | CONSTRUCTION ACCESS | Material |  |  | 8
3461-43061 | ROADWAY EXCAVATION | Material |  |  | 8
3461-43062 | ROADWAY FILL | Material |  |  | 8
3461-43063 | GRADE SLOPE | Material |  |  | 8
3461-43064 | TOPSOIL EXCAVATION | Material |  |  | 8
3461-43141 | TOPSOIL PLACEMENT | Material |  |  | 8
3461-43161 | UNDERCUT UNSUITABLE | Material |  |  | 8
3461-43162 | REPLACE UNDERCUT | Material |  |  | 8
3461-43241 | FINEGRADE SUBGRADE | Material |  |  | 8
3461-43242 | FG SG SIDEWALK/TRAIL | Material |  |  | 8
3461-43531 | P&C 21B BASE ROADWAY | Material |  |  | 8
3461-43532 | P&C 21B BASE - SUP | Material |  |  | 8
3461-43533 | F&I APP SLAB BASE | Material |  |  | 8
3461-43541 | CEMENT TREATED BASE/SUBGRADE | Material |  |  | 8
3461-43560 | SHOULDER BACKUP | Material |  |  | 8
3461-45541 | STORM DRAIN PIPE (12-30 IN) INST | Material |  |  | 8
3461-45551 | STORM DRAIN PIPE (36-54 IN) INST | Material |  |  | 8
3461-45561 | STORM DRAIN PIPE (60 IN+) INST | Material |  |  | 8
3461-45574 | DI-2 THROUGH DI-5 | Material |  |  | 8
3461-45575 | DI-10 THROUGH DI-13 | Material |  |  | 8
3461-45576 | ENDWALL JUNCTION BOX INST | Material |  |  | 8
3461-45661 | JACK AND BORE INST | Material |  |  | 8
3461-45681 | RIP-RAP | Material |  |  | 8
3461-4655001 | I&R SHEET PILE | Material |  |  | 8
3461-4655003 | I&R SHEETS WALERS TIEBACKS | Material |  |  | 8
3461-4659002 | TEMPORARY WOTKS (MOT) | Material |  |  | 8
3461-4663001 | I&R WALES / TIEBACKS | Material |  |  | 8
3461-4701003 | STRUCTURE EXCAVATION/BFILL | Material |  |  | 8
3461-4702002 | SELECT BACKFILL ABUTMENT ZONE - INST | Material |  |  | 8
3461-4706002 | DRIVE 12" STEEL PILE | Material |  |  | 8
3461-4706003 | 12" PILE MSE CANS & SAND | Material |  |  | 8
3461-4706004 | PILE POINT FOR 12" STEEL PILE | Material |  |  | 8
3461-4706005 | TEST PILE FOR 12" | Material |  |  | 8
3461-4706008 | DRIVE 14" STEEL PILE | Material |  |  | 8
3461-4706009 | PILE POINT FOR 14" STEEL PILE | Material |  |  | 8
3461-4706010 | TEST PILE FOR 14" | Material |  |  | 8
3461-4706011 | PREBORING PILE 14" STEEL PILE | Material |  |  | 8
3461-4752002 | F&S FOOTING & ABUT | Material |  |  | 8
3461-4752003 | F&S COLUMNS | Material |  |  | 8
3461-4752004 | F&S WALL PIER | Material |  |  | 8
3461-4752005 | F&S CAP | Material |  |  | 8
3461-4752006 | PLACE SUBSTRUCTURE CONCRETE | Material |  |  | 8
3461-4752007 | RUB SUBSTRUCTURE CONCRETE | Material |  |  | 8
3461-47641 | F&S OVERHANG & EDGE | Material |  |  | 8
3461-47642 | F&S BULKHEADS | Material |  |  | 8
3461-47643 | SET RAIL, DRY RUN AND BIDWELL | Material |  |  | 8
3461-47644 | PLC DECK AND INTG BWALL | Material |  |  | 8
3461-47645 | FPS MEDIAN/SIDEWALK/CURB | Material |  |  | 8
3461-47646 | RUB DECK | Material |  |  | 8
3461-48201 | I&R FALL PROTECTION | Material |  |  | 8
3461-48401 | TEMP DECK SHIELD | Material |  |  | 8
3461-48451 | FORM/STRIP APPR SLAB | Material |  |  | 8
3461-48452 | PLC SLEEPER & APP SLAB & SW | Material |  |  | 8
3461-5151001 | RW-3 - FORMWORKS | Material |  |  | 8
3461-5151002 | RW-3 - CONCRETE PLC | Material |  |  | 8
3461-5151003 | RW-3 - FINISHES | Material |  |  | 8
3461-5172002 | MSE WALL PANEL INSTALL | Material |  |  | 8
3461-5172003 | WIREWALL INST | Material |  |  | 8
3461-5172004 | CIP MOMENT SLAB & COPING INST | Material |  |  | 8
3461-5172005 | PRECAST COPING & SLAB INST | Material |  |  | 8
3461-5172006 | MSE WALL PRECAST COPING SUB | Material |  |  | 8
3461-5173002 | COMBO LAGGING INSTALLATION | Material |  |  | 8
3461-5173003 | COMBO CONCRETE POST INSTALL | Material |  |  | 8
3461-5173004 | COMBO TIEBACK INSTALLATION | Material |  |  | 8
3461-5173005 | COMBO PLACE CONCRETE PANELS | Material |  |  | 8
3461-5173006 | COMBO DRAINAGE COMPOSITE | Material |  |  | 8
3461-5173008 | POST & PANEL CONCRETE POST INSTALL | Material |  |  | 8
3461-5173009 | POST & PANEL TIEBACK INSTALLATION | Material |  |  | 8
3461-5173010 | POST & PANEL DRAINAGE COMPOSITE | Material |  |  | 8
3461-5173011 | POST & PANEL LAGGING INSTALLATION | Material |  |  | 8
3461-5173012 | POST & PANEL PLACE CONCRETE PANELS | Material |  |  | 8
3461-5174002 | CONCRETE POST INST | Material |  |  | 8
3461-5174003 | PL CONCRETE PANEL & DOORS | Material |  |  | 8
3461-5174005 | NOISE RWM CONCRETE POSTS INST | Material |  |  | 8
3461-5174006 | NOISE RWM CONCRETE PANELS INST | Material |  |  | 8
3461-5174008 | NOISE BM CONCRETE POSTS INST | Material |  |  | 8
3461-5174009 | NOISE BM CONCRETE PANELS INST | Material |  |  | 8
3461-5210007 | RAILING, CPSR 2 RAIL -INST | Material |  |  | 8
3461-5210008 | CONCRETE PARAPET 32" - INST | Material |  |  | 8
3461-5210009 | CONCRETE PARAPET 42" -INST | Material |  |  | 8
3461-521006 | RAILING, CPSR 1 RAIL - INST | Material |  |  | 8
3461-5351003 | SUBSTRUCTURE REINFORCING STEEL -INST | Material |  |  | 8
3463-40500 | TRAFFIC CONTROL | Material | Month |  | 8
3463-40510 | MAINTENANCE OF TRAFFIC | Material | Month |  | 8
3463-405101 | Traffic Control | Material | Month |  | 8
3463-405102 | Traffic Control Subcontract | Material | Month |  | 8
3463-405103 | Traffic Control Devices | Material | Month |  | 8
3463-405104 | Dynamic Traveler Info System | Material | Lump Sum |  | 8
3463-405105 | Off Duty Patrol Support | Material | Hour |  | 8
3463-405106 | Temp Pavement - Materials | Material | Square Yard |  | 8
3463-405107 | Temp Pavment Earthwork | Material | Square Yard |  | 8
3463-405108 | Temp Pavment Drainage | Material | Linear Feet |  | 8
3463-405109 | Temp Pavment Removal/Clean Up | Material | Square Yard |  | 8
3463-405110 | Temp Pavement Haul | Material | Cubic Yard |  | 8
3463-405111 | Temp Pavement Milling | Material | Square Yard |  | 8
3463-405112 | Temp Pavement - Asphalt | Material | Ton |  | 8
3463-405113 | Remove Rumble Strips | Material | Square Yard |  | 8
3463-405114 | Fill Rumble Strips | Material | Ton |  | 8
3463-40520 | TEMPORARY CTB | Material | Linear Feet |  | 8
3463-4052001 | PCB - Material Roadway | Material | Linear Feet |  | 8
3463-4052003 | PCB - Material Anchored | Material | Linear Feet |  | 8
3463-4052004 | PCB Intial Set | Material | Linear Feet |  | 8
3463-4052005 | Reset PCB Without Truck | Material | Linear Feet |  | 8
3463-4052006 | Reset PCB With Truck | Material | Linear Feet |  | 8
3463-4052007 | Anchored PCB | Material | Linear Feet |  | 8
3463-4052008 | PCB Hauling | Material | Linear Feet |  | 8
3463-4052009 | Temp Crash Cushion - Material | Material | Each |  | 8
3463-4052010 | Temp Crash Cushion Set | Material | Each |  | 8
3463-4052011 | Reset Temp Crash Cushions | Material | Each |  | 8
3463-40530 | PAVEMENT MARKING | Material | Lump Sum |  | 8
3463-4053011 | Permanent Pavmt Mark | Material | Linear Feet |  | 8
3463-4053021 | Permanent Pavmt Mark Symbols | Material | Each |  | 8
3463-4053031 | Snowplowable Pavement Markers | Material | Each |  | 8
3463-4053041 | Permanent Pavmt Mark Removal | Material | Linear Feet |  | 8
3463-4053051 | Temporary Pavement Markings | Material | Linear Feet |  | 8
3463-4053061 | Temporary Pavement Symbols | Material | Each |  | 8
3463-4053071 | Temporary RPMs | Material | Each |  | 8
3463-4053081 | Pavement Marking Removal | Material | Linear Feet |  | 8
3463-4053091 | Pavement Marking Removal Symb. | Material | Each |  | 8
3463-40540 | ROADWAY SIGNAGE/WAYFINDING | Material | Square Feet |  | 8
3463-4054011 | Mobilization | Material | Lump Sum |  | 8
3463-4054021 | Material Signs | Material | Square Feet |  | 8
3463-4054031 | Ground Mounted Supports | Material | LB |  | 8
3463-4054041 | Sign Erection | Material | Each |  | 8
3463-4054051 | Sign Disposal | Material | Each |  | 8
3463-40550 | OVERHEAD SIGNAGE | Material | Square Feet |  | 8
3463-405501 | Overhead Sign Structures | Material | Lump Sum |  | 8
3463-405502 | Sign Erection | Material | Each |  | 8
3463-405503 | Foundations | Material | Cubic Yard |  | 8
3463-405504 | Foundation Borings | Material | Each |  | 8
3463-41000 | EROSION CONTROL | Material | Month |  | 8
3463-41010 | EROSION CONTROL-CREW | Material | Month |  | 8
3463-410101 | Erosion Control Maintenance | Material | Month |  | 8
3463-410102 | TEMPORARY SILT FENCE | Material | Linear Feet |  | 8
3463-410103 | SAFETY FENCE | Material | Linear Feet |  | 8
3463-410104 | Erosion Control Matting | Material | Square Yard |  | 8
3463-410105 | 1/4" HARDWARE CLOTH | Material | Linear Feet |  | 8
3463-410106 | Erosion Control Wattles | Material | Linear Feet |  | 8
3463-410107 | COIR FIBER BAFFLE | Material | Linear Feet |  | 8
3463-410108 | POLYACRYLAMIDE (PAM) | Material | LB |  | 8
3463-41020 | EROSION CONTROL-DEVICES | Material | Month |  | 8
3463-410201 | Temp Silt Fence Install/Remove | Material | Linear Feet |  | 8
3463-410202 | Safety Fence Install/Remove | Material | Linear Feet |  | 8
3463-410203 | Matting for Erosion Control | Material | Square Yard |  | 8
3463-410204 | Coir Fiber Mat | Material | Square Yard |  | 8
3463-410205 | 1/4" Harware Cloth | Material | Linear Feet |  | 8
3463-410206 | Coir Fiber Wattle | Material | Linear Feet |  | 8
3463-410207 | Wattles | Material | Linear Feet |  | 8
3463-410208 | PAM | Material | LB |  | 8
3463-410209 | Coir Fiber Baffle | Material | Linear Feet |  | 8
3463-410210 | GEOTEXT FOR SOIL STABILIZATION | Material | Square Yard |  | 8
3463-410211 | Geotext for Soil Stabiliation | Material | Square Yard |  | 8
3463-410212 | GEOTEXTILE FOR DRAINAGE | Material | Square Yard |  | 8
3463-410213 | Geotextile for Drainage | Material | Square Yard |  | 8
3463-410214 | Concrete Washouts | Material | Each |  | 8
3463-410215 | Silt Excavation | Material | Cubic Yard |  | 8
3463-410216 | Stilling Basins | Material | Cubic Yard |  | 8
3463-410217 | Special Stilling Basins | Material | Each |  | 8
3463-410218 | Special Stilling Basins | Material | Each |  | 8
3463-410219 | Skimmer - Material | Material | Each |  | 8
3463-410220 | Skimmer - Install | Material | Each |  | 8
3463-410221 | Impervious Dike - Material | Material | Linear Feet |  | 8
3463-410222 | Impervious Dike - Install | Material | Linear Feet |  | 8
3463-41030 | EROSION CONTROL-TEMP SEED | Material | Acre |  | 8
3463-410301 | Temporary Seeding | Material | Acre |  | 8
3463-410302 | Temp Mulching | Material | Acre |  | 8
3463-410303 | Mowing | Material | Acre |  | 8
3463-41050 | EROSION CONTROL-STONE | Material | Ton |  | 8
3463-410501 | SEDIMENT CNTRL STONE - Matl | Material | Ton |  | 8
3463-410502 | SEDIMENT CONTROL STONE - Haul | Material | Ton |  | 8
3463-410503 | SEDIMENT CONTROL STONE - Inst. | Material | Ton |  | 8
3463-410504 | Construction Entrances | Material | Each |  | 8
3463-410505 | EROSION CNTRL CLASS A Material | Material | Ton |  | 8
3463-410506 | EROSION CNTRL CLASS A Install | Material | Ton |  | 8
3463-410507 | EROSION CNTRL CLASS A Haul | Material | Ton |  | 8
3463-410508 | EROSION CNTRL CLASS B Material | Material | Ton |  | 8
3463-410509 | EROSION CNTRL CLASS B Haul | Material | Ton |  | 8
3463-410510 | EROSION CNTRL CLASS B Install | Material | Ton |  | 8
3463-41060 | EROSION CONTROL-TEMP DRAIN | Material | Linear Feet |  | 8
3463-410601 | Temp Slope Drains - Materials | Material | Linear Feet |  | 8
3463-410602 | Temp Slope Drains - Install | Material | Linear Feet |  | 8
3463-410603 | 36" Temporary Pipe | Material | Linear Feet |  | 8
3463-410604 | 36" Temporary Pipe - Install | Material | Linear Feet |  | 8
3463-42000 | DEMOLITION | Material | Lump Sum |  | 8
3463-42010 | MILL ASPHALT PAVEMENT | Material | Cubic Yard |  | 8
3463-42040 | DEMO-BRIDGE | Material | Cubic Yard |  | 8
3463-420401 | Demo - Materials | Material | Square Feet |  | 8
3463-420402 | Demo Old NC 86 - Sheilding | Material | Square Feet |  | 8
3463-420403 | Demo Old NC 86 | Material | Square Feet |  | 8
3463-420404 | Demo I-40 Millhouse/NSRR Sawct | Material | Linear Feet |  | 8
3463-420405 | Demo I-40 Over Millhouse/NSRR | Material | Lump Sum |  | 8
3463-420406 | Demo I-40 Millhouse/NSRR Haul | Material | Load |  | 8
3463-42050 | DEMO-WALL/BARRIER/MISC STRUCT | Material | Cubic Yard |  | 8
3463-420501 | Demo Existing Asphalt Pavement | Material | Square Yard |  | 8
3463-420502 | Demo Existing Flatwork | Material | Square Yard |  | 8
3463-420503 | Asphalt Pavement Demo/Haul | Material | Square Yard |  | 8
3463-42060 | DEMO-DRAINAGE | Material | Linear Feet |  | 8
3463-420601 | Pipe Removal | Material | Linear Feet |  | 8
3463-420602 | Drainage Structure Removal | Material | Each |  | 8
3463-420603 | Flowable Fill Materal | Material | Cubic Yard |  | 8
3463-420604 | Flowable Fill Labor | Material | Cubic Yard |  | 8
3463-420605 | Flowable Fill Concrete Pumping | Material | Cubic Yard |  | 8
3463-42500 | SITE WORK | Material | Month |  | 8
3463-42510 | CLEAR AND GRUB | Material | Acre |  | 8
3463-42530 | PERMANENT FENCING | Material | Linear Feet |  | 8
3463-425301 | Fencing | Material | Linear Feet |  | 8
3463-425302 | Remove Existing Fencing | Material | Linear Feet |  | 8
3463-425303 | Curb and Gutter | Material | Linear Feet |  | 8
3463-425304 | 5" Monolith Conc. Island Surf. | Material | Square Yard |  | 8
3463-425305 | 5" Monolith Conc. Island Keyed | Material | Square Yard |  | 8
3463-425306 | Shoulder Berm | Material | Linear Feet |  | 8
3463-425307 | Expressway Gutter | Material | Linear Feet |  | 8
3463-42580 | LANDSCAPE | Material | Square Yard |  | 8
3463-425801 | Permenant Seeding | Material | Acre |  | 8
3463-425802 | Sod and Wetland Plants | Material | Acre |  | 8
3463-42590 | GUARDRAIL | Material | Linear Feet |  | 8
3463-425901 | ROW Markers | Material | Each |  | 8
3463-425902 | Guardrail | Material | Linear Feet |  | 8
3463-425903 | Attentuator | Material | Each |  | 8
3463-425904 | Guardrail End - Cat1 | Material | Each |  | 8
3463-425905 | Guardrail End Unit - TL3 | Material | Each |  | 8
3463-425906 | Guardrail End Units - B77 | Material | Each |  | 8
3463-425907 | Guardrail Removal | Material | Linear Feet |  | 8
3463-42600 | NOISE WALL | Material | Square Feet |  | 8
3463-426001 | Noise Wall - Materials | Material | Square Feet |  | 8
3463-426002 | Noise Wall - Install | Material | Square Feet |  | 8
3463-426003 | Noise Wall Access & Backfill | Material | Square Feet |  | 8
3463-43000 | EARTHWORK | Material | Cubic Yard |  | 8
3463-43020 | CONSTRUCTION ACCESS | Material | Square Yard |  | 8
3463-43120 | TOPSOIL STRIPPING | Material | Cubic Yard |  | 8
3463-431201 | Strip/Load/Maintian Topsoil | Material | Cubic Yard |  | 8
3463-43040 | COMMON EXCAVATION/FILL | Material | Cubic Yard |  | 8
3463-430401 | Excavation Large Areas | Material | Cubic Yard |  | 8
3463-430402 | Excavation Small Areas | Material | Cubic Yard |  | 8
3463-430403 | Ditch/Basin Excavation | Material | Cubic Yard |  | 8
3463-430404 | Excavation With Mill | Material | Cubic Yard |  | 8
3463-430405 | Excavation/Backfill Undercut | Material | Cubic Yard |  | 8
3463-430406 | Haul to Stockpile | Material | Cubic Yard |  | 8
3463-430407 | Haul to Embankment | Material | Cubic Yard |  | 8
3463-430408 | Place and Compact | Material | Cubic Yard |  | 8
3463-430410 | Disking | Material | Month |  | 8
3463-430411 | Maintain Haul Roads | Material | Month |  | 8
3463-430412 | Proof Rolling | Material | Hour |  | 8
3463-43240 | FINEGRADE SUBGRADE | Material | Square Yard |  | 8
3463-432401 | Fine Grade Subgrade | Material | Square Yard |  | 8
3463-43280 | Haul to Excavation to Waste | Material | Cubic Yard |  | 8
3463-43500 | PAVEMENT BASE | Material | Square Yard |  | 8
3463-43510 | FINEGRADE AGGREGATE BASE | Material | Square Yard |  | 8
3463-435101 | Class IV Aggergate - Place | Material | Square Yard |  | 8
3463-43530 | AGGREGATE BASE COURSE | Material | Ton |  | 8
3463-435301 | Class IV Aggergate-Material | Material | Ton |  | 8
3463-435302 | Haul Class IV Aggergate - Haul | Material | Ton |  | 8
3463-435303 | Class IV Aggergate - Place | Material | Ton |  | 8
3463-435304 | Concrete Shoulder Break | Material | Square Yard |  | 8
3463-435305 | Concrete Shoulder Demo Load | Material | Square Yard |  | 8
3463-435306 | Concrete Shoulder Demo Haul | Material | Square Yard |  | 8
3463-435307 | Stock Pile Demo Conc. Shoulder | Material | Cubic Yard |  | 8
3463-435308 | Crush Concrete Rubble | Material | Cubic Yard |  | 8
3463-435309 | Haul Proc'd Conc. Matl to Site | Material | Ton |  | 8
3463-43560 | SHOULDER BACKUP | Material | Linear Feet |  | 8
3463-435601 | Shoulder Backup | Material | Cubic Yard |  | 8
3463-435602 | Shouldr Bckup/Surf. Drain Haul | Material | Cubic Yard |  | 8
3463-43570 | AGGREGATE STABILIZATION - Geotextile | Material | Square Yard |  | 8
3463-44000 | AC PAVING | Material | Ton |  | 8
3463-44010 | AC PAVE-MAINLINE | Material | Ton |  | 8
3463-4401011 | HMA Base B25.0C | Material | Ton |  | 8
3463-4401021 | HMA Intermediate I9.0C | Material | Ton |  | 8
3463-4401031 | HMA Surface S9.0B | Material | Ton |  | 8
3463-4401041 | HMA Surface S9.5C | Material | Ton |  | 8
3463-4401051 | HMA Surface S9.5S | Material | Ton |  | 8
3463-4401061 | HMA Wedging | Material | Ton |  | 8
3463-4401071 | Ultra-Thin Bond Wearing Course | Material | Ton |  | 8
3463-4401081 | Liquid AC, 64-22 | Material | Ton |  | 8
3463-4401091 | Liquid AC, 76-22 | Material | Ton |  | 8
3463-4401101 | Rumble Strips (Asp/Conc) | Material | Linear Feet |  | 8
3463-44500 | CONCRETE PAVING | Material | Cubic Yard |  | 8
3463-44510 | CONCRETE PAVE-FULL LANE SLIP | Material | Cubic Yard |  | 8
3463-44520 | CONCRETE PAVE-SHOULDER SLIP | Material | Cubic Yard |  | 8
3463-44530 | CONCRETE PAVE-HAND POUR | Material | Cubic Yard |  | 8
3463-44540 | PCCP Crew | Material | Month |  | 8
3463-44550 | PCCP Incidentals | Material | Cubic Yard |  | 8
3463-445001 | Unload/Handle Embeds | Material | Each |  | 8
3463-445002 | PCCP Cure - Material | Material | Square Yard |  | 8
3463-445003 | PCCP Forms | Material | Linear Feet |  | 8
3463-445004 | Form Headers | Material | Each |  | 8
3463-445005 | Remove Headers | Material | Each |  | 8
3463-445006 | Drainage Box Out Materials | Material | Each |  | 8
3463-445007 | Paving Spall/Patching - Matls | Material | Square Yard |  | 8
3463-445008 | SawCut | Material | Linear Feet |  | 8
3463-445009 | Widen and Seal | Material | Linear Feet |  | 8
3463-445010 | Concrete Cores | Material | Day |  | 8
3463-445011 | Erect Move Paver | Material | Each |  | 8
3463-445012 | ModifY Paver | Material | Each |  | 8
3463-445013 | Move Paver | Material | Each |  | 8
3463-445014 | Joint/Spall Repair | Material | Each |  | 8
3463-445015 | Diamond Grind Concrete | Material | Square Yard |  | 8
3463-445016 | Slurry Pond - Materials | Material | Cubic Yard |  | 8
3463-445017 | Slurry Pond - Install | Material | Each |  | 8
3463-445018 | Slurry Pond - Maintain | Material | Cubic Yard |  | 8
3463-445019 | Slurry Pond Backfill | Material | Cubic Yard |  | 8
3463-45500 | PIPE AND DRAINAGE | Material | Month |  | 8
3463-45990 | Video Pipe Inspection | Material | Linear Feet |  | 8
3463-45900 | Jack and Bore Access/Support | Material | Each |  | 8
3463-45660 | JACK AND BORE (24"-48") | Material | Linear Feet |  | 8
3463-456601 | 15" Trenchless | Material | Linear Feet |  | 8
3463-456602 | 15" WSP Open Cut | Material | Linear Feet |  | 8
3463-456603 | 18" Trenchless | Material | Linear Feet |  | 8
3463-456604 | 15" WSP Open Cut | Material | Linear Feet |  | 8
3463-456605 | 24" Trenchless | Material | Linear Feet |  | 8
3463-456606 | 24" WSP Open Cut | Material | Linear Feet |  | 8
3463-456607 | 30 Trenchless | Material | Linear Feet |  | 8
3463-456608 | 30 WSP Open Cut | Material | Linear Feet |  | 8
3463-456609 | 36" Trenchless | Material | Linear Feet |  | 8
3463-456610 | 36" WSP Open Cut | Material | Linear Feet |  | 8
3463-456611 | 42" Trenchless | Material | Linear Feet |  | 8
3463-456612 | 48" Trenchless | Material | Linear Feet |  | 8
3463-45670 | JACK AND BORE (48"+) | Material | Linear Feet |  | 8
3463-456701 | 60" Trenchless | Material | Linear Feet |  | 8
3463-456702 | 66" Trenchless | Material | Linear Feet |  | 8
3463-456703 | 72" Trenchless | Material | Linear Feet |  | 8
3463-456704 | 78" Trenchless | Material | Linear Feet |  | 8
3463-456705 | 84" Trenchless | Material | Linear Feet |  | 8
3463-456706 | 108" Trenchless | Material | Linear Feet |  | 8
3463-45980 | Bedding Materials | Material | Ton |  | 8
3463-45540 | STORM DRAIN PIPE (12-30 IN) | Material | Linear Feet |  | 8
3463-455401 | 15" CMP - Material | Material | Linear Feet |  | 8
3463-455402 | 15" CMP - Install | Material | Linear Feet |  | 8
3463-455403 | 18" CMP - Material | Material | Linear Feet |  | 8
3463-455404 | 18" CMP - Install | Material | Linear Feet |  | 8
3463-455405 | 24" CMP - Material | Material | Linear Feet |  | 8
3463-455406 | 24" CMP - Install | Material | Linear Feet |  | 8
3463-455407 | 30" CMP - Material | Material | Linear Feet |  | 8
3463-455408 | 30" CMP - Install | Material | Linear Feet |  | 8
3463-455409 | 15" RCP - Material | Material | Linear Feet |  | 8
3463-455410 | 15" RCP - Install | Material | Linear Feet |  | 8
3463-455411 | 18" RCP - Material | Material | Linear Feet |  | 8
3463-455412 | 18" RCP - Install | Material | Linear Feet |  | 8
3463-455413 | 24" RCP - Material | Material | Linear Feet |  | 8
3463-455414 | 24" RCP - Install | Material | Linear Feet |  | 8
3463-455415 | 30" RCP - Material | Material | Linear Feet |  | 8
3463-455416 | 30" RCP - Install | Material | Linear Feet |  | 8
3463-45550 | STORM DRAIN PIPE (36-60 IN) | Material | Linear Feet |  | 8
3463-455501 | 36" CMP - Material | Material | Linear Feet |  | 8
3463-455502 | 36" CMP - Install | Material | Linear Feet |  | 8
3463-455503 | 36" RCP - Material | Material | Linear Feet |  | 8
3463-455504 | 36" RCP - Install | Material | Linear Feet |  | 8
3463-455505 | 42" RCP - Material | Material | Linear Feet |  | 8
3463-455506 | 42" RCP - Install | Material | Linear Feet |  | 8
3463-455507 | 48" RCP - Material | Material | Linear Feet |  | 8
3463-455508 | 48" RCP - Install | Material | Linear Feet |  | 8
3463-45560 | STORM DRAIN PIPE (66 IN+) | Material | Linear Feet |  | 8
3463-455601 | 66" RCP - Material | Material | Linear Feet |  | 8
3463-455602 | 66" RCP - Install | Material | Linear Feet |  | 8
3463-455603 | 72" RCP - Material | Material | Linear Feet |  | 8
3463-455604 | 72" RCP - Install | Material | Linear Feet |  | 8
3463-455605 | 78" RCP - Material | Material | Linear Feet |  | 8
3463-455606 | 78" RCP - Install | Material | Linear Feet |  | 8
3463-455607 | 84" RCP - Material | Material | Linear Feet |  | 8
3463-455608 | 84" RCP - Install | Material | Linear Feet |  | 8
3463-455609 | 108" RCP - Material | Material | Linear Feet |  | 8
3463-455610 | 108" RCP - Install | Material | Linear Feet |  | 8
3463-45970 | Sawcut/Remove Pavement | Material | Linear Feet |  | 8
3463-459701 | Drainage Sawcut/Select BKFL | Material | Linear Feet |  | 8
3463-457010 | Pipe Collars | Material | Square Feet |  | 8
3463-457020 | ENDWALLS | Material | Each |  | 8
3463-4570201 | Unreinforced Endwall Material | Material | Each |  | 8
3463-4570202 | Unreinforced Endwall - Install | Material | Each |  | 8
3463-4570203 | Reinforced Endwall - Material | Material | Each |  | 8
3463-4570204 | Reinforced Endwall - Install | Material | Each |  | 8
3463-45570 | STORM DRAIN INLET/CB/END | Material | Each |  | 8
3463-45600 | STORM DRAIN-PRECAST BOX | Material | Cubic Yard |  | 8
3463-456001 | Junction Box - Material | Material | Each |  | 8
3463-456002 | Junction Box - Install | Material | Each |  | 8
3463-45580 | STORM DRAIN MH (48-72 IN) | Material | Each |  | 8
3463-455801 | Manhole - Material | Material | Each |  | 8
3463-455802 | Manhole - Install | Material | Each |  | 8
3463-457030 | Set/Adjust/Grate and Inverts | Material | Each |  | 8
3463-457040 | Berm Ditch Outlet | Material | Each |  | 8
3463-457050 | Structure Flatwork | Material | Each |  | 8
3463-4570501 | Drain Structure Concrete Apron | Material | Each |  | 8
3463-4570502 | Drainage Struct Curb & Gutter | Material | Each |  | 8
3463-4570503 | Utility Test Pits | Material | Each |  | 8
3463-457060 | Detention Basin Outlet | Material | Each |  | 8
3463-4570601 | Detention Basin Outlet - Matls | Material | Each |  | 8
3463-4570602 | Detention Basin Outlet Install | Material | Each |  | 8
3463-457070 | End Treatment - Rip Rap & Geo | Material | Ton |  | 8
3463-45740 | UNDERDRAIN | Material | Linear Feet |  | 8
3463-457401 | 4" Shoulder Drain Pipe | Material | Linear Feet |  | 8
3463-457402 | 4" Shldr Drain Pipe Convey Trk | Material | Linear Feet |  | 8
3463-457403 | 4" Shoulder Drain Pipe Outlet | Material | Linear Feet |  | 8
3463-457404 | Concrete Pad for Shld Drain | Material | Each |  | 8
3463-46500 | SUPPORT OF EXCAVATION | Material | Square Feet |  | 8
3463-46590 | TEMP WIRE WALL | Material | Square Feet |  | 8
3463-46550 | SHEETPILE WALL | Material | Square Feet |  | 8
3463-47000 | STRUCTURE FOUNDATION | Material | Month |  | 8
3463-47005 | STRUCTURE SITE ACCESS | Material | Each |  | 8
3463-47010 | STRUCTURE EXCAVATION | Material | Cubic Yard |  | 8
3463-47020 | STRUCTURE BACKFILL | Material | Cubic Yard |  | 8
3463-47050 | DRILLED SHAFTS | Material | Cubic Yard |  | 8
3463-47060 | DRIVEN PILE | Material | Linear Feet |  | 8
3463-47520 | BRIDGE SUBSTRUCTURE-LAND | Material | Cubic Yard |  | 8
3463-475200 | BRIDGE SUBSTRUCTURE | Material | Cubic Yard |  | 8
3463-47600 | BRIDGE BEAMS-SET PRECAST | Material | Linear Feet |  | 8
3463-47640 | BRIDGE DECK-ON GIRDER | Material | Cubic Yard |  | 8
3463-476401 | Conc. Deck Class AA Concrete | Material | Cubic Yard |  | 8
3463-476402 | Conc. Deck Frmwrk and Incdntls | Material | Cubic Yard |  | 8
3463-476403 | SIP Purchase | Material | Square Feet |  | 8
3463-476404 | SIP - Install | Material | Square Feet |  | 8
3463-476405 | Unload/Handle/Fabricate Frmwrk | Material | Square Feet |  | 8
3463-476406 | Form/Strip Diaphragms | Material | Square Feet |  | 8
3463-476407 | Form/Strip Deck O/H | Material | Linear Feet |  | 8
3463-476408 | Frm/Strp Deck Edge Beam Sffits | Material | Square Feet |  | 8
3463-476409 | Form/Strip Bulk Head | Material | Square Feet |  | 8
3463-476410 | Form/Strip Closure Bay | Material | Square Feet |  | 8
3463-476411 | Erect/Dismntle/Dry Run Bidwell | Material | Each |  | 8
3463-476412 | Pour/Cure/P&P Deck | Material | Cubic Yard |  | 8
3463-476413 | Grooving Grinding | Material | Square Feet |  | 8
3463-476414 | Structures MOT Asphalt Overlay | Material | Square Yard |  | 8
3463-476415 | Install Sheilding | Material | Square Feet |  | 8
3463-476416 | Struct Reinforcing Steel Matl | Material | LB |  | 8
3463-476417 | Struct Reinforcing Steel Inst | Material | LB |  | 8
3463-476418 | Unld/Hndle Rnfrcng Steel/SIP | Material | LB |  | 8
3463-476419 | Structure Point & Patch | Material | Square Feet |  | 8
3463-476420 | Structure Concrete Pumping | Material | Cubic Yard |  | 8
3463-48000 | BRIDGE-MISCALLANEOUS | Material | Lump Sum |  | 8
3463-48250 | BRIDGE BEARINGS | Material | Each |  | 8
3463-48300 | BRIDGE EXPANSION JOINTS | Material | Linear Feet |  | 8
3463-48350 | 42" BRIDGE RAILING | Material | Linear Feet |  | 8
3463-48400 | BRIDGE SHIELDING | Material | Square Feet |  | 8
3463-48450 | APPROACH SLAB | Material | Cubic Yard |  | 8
3463-48500 | Bridge Rehab | Material | Square Yard |  | 8
3463-485001 | PPC/EPC Deck Overlay | Material | Square Yard |  | 8
3463-485002 | PPC/EPC Deck Groove | Material | Square Feet |  | 8
3463-485003 | PPC/EPC Deck Overlay Sweeping | Material | Square Feet |  | 8
3463-485004 | Replace Joint - Material | Material | Linear Feet |  | 8
3463-485005 | Replace Joint - Sawcut | Material | Linear Feet |  | 8
3463-485006 | Replace Joint - Replace | Material | Linear Feet |  | 8
3463-485007 | Replace Approach lab | Material | Square Yard |  | 8
3463-485008 | Paint Repr on Steel Brdg Beams | Material | Linear Feet |  | 8
3463-485009 | Straighten Steel beam | Material | Each |  | 8
3463-51700 | STRUCTURAL CONCRETE-WALLS | Material | Square Feet |  | 8
3463-51720 | RETAINING WALL-MSE | Material | Square Feet |  | 8
3463-517201 | Soil Nail Wall Subcontract | Material | Square Feet |  | 8
3463-517202 | MSE Wall Subcontractor | Material | Square Feet |  | 8
3463-517203 | Soil Nail Wall Finishes | Material | Square Feet |  | 8
3463-517204 | Wire Baskets & Drainage Matls | Material | Square Feet |  | 8
3463-517205 | Excavate for Soil Nail | Material | Cubic Yard |  | 8
3463-517206 | Wire Baskets & Drainage - Inst | Material | Square Feet |  | 8
3463-517207 | CIP Coping/V Ditch - Material | Material | Square Feet |  | 8
3463-517208 | CIP Coping - Install | Material | Square Feet |  | 8
3463-517209 | CIP V Ditch - Install | Material | Square Feet |  | 8
3463-51760 | REINFORCED SOIL SLOPE WALLS | Material | Square Feet |  | 8
3463-517601 | Reforced Soil Slope Walls Matl | Material | Square Feet |  | 8
3463-517602 | Reforced Soil Slope Walls Haul | Material | Cubic Yard |  | 8
3463-517603 | Reforced Soil Slope Walls Exc | Material | Cubic Yard |  | 8
3463-517604 | Reforced Soil Slope Walls Inst | Material | Square Feet |  | 8
3463-52000 | STRUCTURAL CONCRETE -BARRIER | Material | Cubic Yard |  | 8
3463-52100 | BARRIER WALL-CIP | Material | Cubic Yard |  | 8
3463-52200 | BARRIER WALL-SLIP FORM | Material | Cubic Yard |  | 8
3463-522001 | Median Barrier Permenant Matls | Material | Linear Feet |  | 8
3463-522002 | Median Barrier Grading/Backfil | Material | Linear Feet |  | 8
3463-522003 | Median Barrier Type T | Material | Linear Feet |  | 8
3463-522004 | Median Barrier Type T1 | Material | Linear Feet |  | 8
3463-522005 | Median Barrier Type T2 | Material | Linear Feet |  | 8
3463-522006 | SLIP SINGLE FACE BARRIER | Material | Linear Feet |  | 8
3463-52400 | BARRIER WALL-PRECAST Single Face | Material | Cubic Yard |  | 8
3463-524001 | Precst Sngl Face Barrier Matl | Material | Linear Feet |  | 8
3463-524002 | Precst 1 Face Barr. Bckfl Matl | Material | Ton |  | 8
3463-524003 | Precst 1 Face Barr. Bckfl Haul | Material | Ton |  | 8
3463-524004 | Install Precast Face Barrier | Material | Linear Feet |  | 8
3463-524005 | Backfill Single Face Barrier | Material | Square Yard |  | 8
3463-524006 | Impact Attenuator | Material | Each |  | 8
3463-89000 | ELECTRICAL/COMM/ITS | Material | Lump Sum |  | 8
3463-93000 | CONCRETE BATCH PLANT | Material | Cubic Yard |  | 8
3463-93050 | Plant Material | Material | Ton |  | 8
3463-93100 | CNC PLANT-OPERATE PLANT | Material | Cubic Yard |  | 8
3463-93200 | CNC PLANT-SET UP/TEAR DOWN | Material | Cubic Yard |  | 8
3463-93300 | CNC PLANT-TRUCK TO PLACE | Material | Cubic Yard |  | 8
3463-89000-2 | Mobilization | Material |  |  | 8
3463-89000-3 | Bond | Material |  |  | 8
3463-89000-4 | Signal Cable (4c) | Material |  |  | 8
3463-89000-5 | Signal Cable (7c) | Material |  |  | 8
3463-89000-6 | Vehicle Signal Head (12", 3 section) | Material |  |  | 8
3463-89000-7 | Vehicle Signal Head (12", 4 section) | Material |  |  | 8
3463-89000-8 | Vehicle Signal Head (12", 5 section) | Material |  |  | 8
3463-89000-9 | Messenger Cable (3/8") | Material |  |  | 8
3463-89000-10 | Unpaved Trenching (1-2" Conduit) | Material |  |  | 8
3463-89000-11 | Unpaved Trenching (2-2" Conduit) | Material |  |  | 8
3463-89000-12 | Junction Box (Standar Size) | Material |  |  | 8
3463-89000-13 | Junction Box (Over-sized, Heavy Duty) | Material |  |  | 8
3463-89000-14 | Inductive Loop Sawcut | Material |  |  | 8
3463-89000-15 | Lead-In Cable (14-2) | Material |  |  | 8
3463-89000-16 | Site Survey | Material |  |  | 8
3463-89000-17 | Fiber-Optic Training | Material |  |  | 8
3463-89000-18 | Metal Strain Signal Pole | Material |  |  | 8
3463-89000-19 | Soil Test | Material |  |  | 8
3463-89000-20 | Drilled Pier Foundation | Material |  |  | 8
3463-89000-21 | Metal Strain Pole Design | Material |  |  | 8
3463-89000-22 | Sign for Signals | Material |  |  | 8
3463-89000-23 | Signal cabinet Foundation | Material |  |  | 8
3463-89000-24 | Controller with Cabinet ( Ty. 2070L, Base Mounted) | Material |  |  | 8
3463-89000-25 | Detector Card (Ty. 2070L)(2 Channel) | Material |  |  | 8
3463-89000-26 | Cabinet Base Extender | Material |  |  | 8
3463-89000-27 | Traffic Sign Removal | Material |  |  | 8
3463-89000-28 | Metal Pole Foundation Removal | Material |  |  | 8
3463-89000-29 | Metal Pole Removal | Material |  |  | 8
3463-89000-30 | Splice Cabinet | Material |  |  | 8
3463-89000-31 | 24 SMFO Cable | Material |  |  | 8
3463-89000-32 | Ethernet Edge Switch | Material |  |  | 8
3463-89000-33 | Splice Enclosures | Material |  |  | 8
3463-89000-34 | Ped Signal Head | Material |  |  | 8
3463-89000-35 | Electric Service | Material |  |  | 8
3463-89000-36 | Mobilization - Temporary | Material |  |  | 8
3463-89000-37 | Signal Cable (4c) - Temporary | Material |  |  | 8
3463-89000-38 | Signal Cable (7c) - Temporary | Material |  |  | 8
3463-89000-39 | Vehicle Signal Head (12", 3 section) - Temporary | Material |  |  | 8
3463-89000-40 | Vehicle Signal Head (12", 4 section) | Material |  |  | 8
3463-89000-41 | Vehicle Signal Head (12", 5 section) - Temporary | Material |  |  | 8
3463-89000-42 | Messenger Cable (3/8") - Temporary | Material |  |  | 8
3463-89000-43 | Wood Pole - Temporary | Material |  |  | 8
3463-89000-44 | Guy Assembly - Temporary | Material |  |  | 8
3463-89000-45 | 2" Riser with Weatherhead - Temporary | Material |  |  | 8
3463-89000-46 | Camera w/ Internal Loop Emulator Processing Unit - Temporary | Material |  |  | 8
3463-89000-47 | Sign for Signals - Temporary | Material |  |  | 8
3463-89000-48 | Controller with Cabinet ( Ty. 2070L, Pole Mounted) - Temporary | Material |  |  | 8
3463-89000-49 | Bond - ITS | Material |  |  | 8
3463-89000-50 | Dynamic Message Sign (Walk-in, 20mm Pixel Pitch, Color, Full Matrix) | Material |  |  | 8
3463-89000-51 | Dynamic Message Sign Structure (Pedestal) | Material |  |  | 8
3463-89000-52 | Dynamic Message Sign Foundation | Material |  |  | 8
3463-89000-53 | DMS Controller Cabinet Assembly (Ty. 334 Str. Mounted) | Material |  |  | 8
3463-89000-54 | Dynamic UPS | Material |  |  | 8
3463-89000-55 | DMS System Integration | Material |  |  | 8
3463-89000-56 | DMS Maintenance Training | Material |  |  | 8
3463-89000-57 | DMS System Operational Field Testing | Material |  |  | 8
3463-89000-58 | CCTV Cabinet (Ty 336S, Pole Mounted) | Material |  |  | 8
3463-89000-59 | CCTV Camera Assembly | Material |  |  | 8
3463-89000-60 | CCTV Metal Pole, 50' | Material |  |  | 8
3463-89000-61 | CCTV Pole Foundation | Material |  |  | 8
3463-89000-62 | CCTV Integration | Material |  |  | 8
3463-89000-63 | CCTV Testing | Material |  |  | 8
3463-89000-64 | Air Terminal Lightning Protection System | Material |  |  | 8
3463-89000-65 | New Electrical Service - ITS | Material |  |  | 8
3463-89000-66 | 3-#X W/G Feeder Circuit | Material |  |  | 8
3463-89000-67 | Electrical Junction Boxes/Pull Boxes (16"x10"x10") - ITS | Material |  |  | 8
3463-89000-68 | Electrical Circuit Markers | Material |  |  | 8
3463-89000-69 | Unpaved Trenching (1-2" Electrical Conduit) - ITS | Material |  |  | 8
3463-89000-70 | Wood Pole - ITS | Material |  |  | 8
3463-89000-71 | 1" Riser with Weatherhead - ITS | Material |  |  | 8
3463-89000-72 | Directional Drill (1-2" Electrical Conduit) - ITS | Material |  |  | 8
3463-89000-73 | Ethernet Edge Switch - ITS | Material |  |  | 8
3463-89000-74 | 48 Port Hub Switch (NCDOT Provided) | Material |  |  | 8
3463-89000-75 | Communications Cable (Twisted-Pair) | Material |  |  | 8
3463-89000-76 | Junction Box (Oversized, Heavy duty)(36"x24"x24") | Material |  |  | 8
3463-89000-77 | 2" Conduit - Unpaved Trenching - ITS | Material |  |  | 8
3463-89000-78 | 2" Conduit - Bored - ITS | Material |  |  | 8
3463-89000-79 | 4" Conduit with 4 innerducts, Bridge Attachment | Material |  |  | 8
3463-89000-80 | 144 Count SMFO | Material |  |  | 8
3463-89000-81 | 12 Count SMFO | Material |  |  | 8
3463-89000-82 | Fiber Optic Splices | Material |  |  | 8
3463-89000-83 | Fiber Optic Splice Enclosures | Material |  |  | 8
3463-89000-84 | SFP Modules | Material |  |  | 8
3463-89000-85 | Hub Cabinet and Foundation | Material |  |  | 8
3463-89000-86 | Maintain and Repair during Construction - ITS | Material |  |  | 8
3463-89000-87 | Remove and Salvage Existing CCTV & Pole | Material |  |  | 8
3463-89000-88 | Remove and Salvage Existing Electrical Service Panel | Material |  |  | 8
UPC112815.CO013 | CO#13 – Additional Betterment Material | Material | Unit |  | 8
UPC112815.CO015 | CO#15 – Additional Signal Preferences | Material | Unit |  | 8
UPC112815.CO016 | CO#16 – Extension to Jennell | Material | Unit |  | 8
UPC112815.CO017 | CO#17 – Additional Betterment Design | Material | Unit |  | 8
3460-51510228 | ARM- Fldwl 48+74 SUB | Material |  |  | 8
3460-6030013 | ARG - Sluice Gates | Material |  |  | 8
C43-Concrete | C43 - Structural Concrete | Labor |  |  | 1
C43-Grates | C43 - Structural Grates | Labor |  |  | 1
C43-Sub-Pile | C43 - Sub - Concrete Pile | Labor |  |  | 1
C43-Sub-WAVE | C43 - Sub - Wave Wall Crew | Labor |  |  | 1
C43-Sub-DEWATER | C43 - Sub Dewatering Crew | Labor |  |  | 1
9156-SA46 | SA#46 - US70 Off-site Detour | Material | Lump Sum |  | 8
C43-SUB-WELD | C43 - Sub - Pipe Welding | Labor |  |  | 1
3468 | 3468 - DTI I-275 | Nonlabor |  |  | 1
3468-01 | 01 Asphalt | Material |  |  | 8
3468-01-Labor | 01 Asphalt-Labor | Material |  |  | 8
3468-01-Equip | 01 Asphalt-Equip | Material |  |  | 8
3468-01-Mat | 01 Asphalt-Mat | Material |  |  | 8
3468-01-Sub | 01 Asphalt-Sub | Material |  |  | 8
3468-01-Trkg | 01 Asphalt-Trkg | Material |  |  | 8
3468-02 | 02 Clear & Grub | Material |  |  | 8
3468-02-Labor | 02 Clear & Grub-Labor | Material |  |  | 8
3468-02-Equip | 02 Clear & Grub-Equip | Material |  |  | 8
3468-02-Mat | 02 Clear & Grub-Mat | Material |  |  | 8
3468-02-Sub | 02 Clear & Grub-Sub | Material |  |  | 8
3468-02-Trkg | 02 Clear & Grub-Trkg | Material |  |  | 8
3468-03 | 03 Design | Material |  |  | 8
3468-03-Labor | 03 Design-Labor | Material |  |  | 8
3468-03-Equip | 03 Design-Equip | Material |  |  | 8
3468-03-Mat | 03 Design-Mat | Material |  |  | 8
3468-03-Sub | 03 Design-Sub | Material |  |  | 8
3468-03-Trkg | 03 Design-Trkg | Material |  |  | 8
3468-04 | 04 Drainage | Material |  |  | 8
3468-04-Labor | 04 Drainage-Labor | Material |  |  | 8
3468-04-Equip | 04 Drainage-Equip | Material |  |  | 8
3468-04-Mat | 04 Drainage-Mat | Material |  |  | 8
3468-04-Sub | 04 Drainage-Sub | Material |  |  | 8
3468-04-Trkg | 04 Drainage-Trkg | Material |  |  | 8
3468-05 | 05 Erosion Control | Material |  |  | 8
3468-05-Labor | 05 Erosion Control-Labor | Material |  |  | 8
3468-05-Equip | 05 Erosion Control-Equip | Material |  |  | 8
3468-05-Mat | 05 Erosion Control-Mat | Material |  |  | 8
3468-05-Sub | 05 Erosion Control-Sub | Material |  |  | 8
3468-05-Trkg | 05 Erosion Control-Trkg | Material |  |  | 8
3468-06 | 06 Flatwork | Material |  |  | 8
3468-06-Labor | 06 Flatwork-Labor | Material |  |  | 8
3468-06-Equip | 06 Flatwork-Equip | Material |  |  | 8
3468-06-Mat | 06 Flatwork-Mat | Material |  |  | 8
3468-06-Sub | 06 Flatwork-Sub | Material |  |  | 8
3468-06-Trkg | 06 Flatwork-Trkg | Material |  |  | 8
3468-07 | 07 Grassing | Material |  |  | 8
3468-07-Labor | 07 Grassing-Labor | Material |  |  | 8
3468-07-Equip | 07 Grassing-Equip | Material |  |  | 8
3468-07-Mat | 07 Grassing-Mat | Material |  |  | 8
3468-07-Sub | 07 Grassing-Sub | Material |  |  | 8
3468-07-Trkg | 07 Grassing-Trkg | Material |  |  | 8
3468-08 | 08 Indirects | Material |  |  | 8
3468-08-Labor | 08 Indirects-Labor | Material |  |  | 8
3468-08-Equip | 08 Indirects-Equip | Material |  |  | 8
3468-08-Mat | 08 Indirects-Mat | Material |  |  | 8
3468-08-Sub | 08 Indirects-Sub | Material |  |  | 8
3468-08-Trkg | 08 Indirects-Trkg | Material |  |  | 8
3468-09 | 09 ITS | Material |  |  | 8
3468-09-Labor | 09 ITS-Labor | Material |  |  | 8
3468-09-Equip | 09 ITS-Equip | Material |  |  | 8
3468-09-Mat | 09 ITS-Mat | Material |  |  | 8
3468-09-Sub | 09 ITS-Sub | Material |  |  | 8
3468-09-Trkg | 09 ITS-Trkg | Material |  |  | 8
3468-10 | 10 Landscape | Material |  |  | 8
3468-10-Labor | 10 Landscape-Labor | Material |  |  | 8
3468-10-Equip | 10 Landscape-Equip | Material |  |  | 8
3468-10-Mat | 10 Landscape-Mat | Material |  |  | 8
3468-10-Sub | 10 Landscape-Sub | Material |  |  | 8
3468-10-Trkg | 10 Landscape-Trkg | Material |  |  | 8
3468-11 | 11 Lighting | Material |  |  | 8
3468-11-Labor | 11 Lighting-Labor | Material |  |  | 8
3468-11-Equip | 11 Lighting-Equip | Material |  |  | 8
3468-11-Mat | 11 Lighting-Mat | Material |  |  | 8
3468-11-Sub | 11 Lighting-Sub | Material |  |  | 8
3468-11-Trkg | 11 Lighting-Trkg | Material |  |  | 8
3468-12 | 12 MOB | Material |  |  | 8
3468-12-Labor | 12 MOB-Labor | Material |  |  | 8
3468-12-Equip | 12 MOB-Equip | Material |  |  | 8
3468-12-Mat | 12 MOB-Mat | Material |  |  | 8
3468-12-Sub | 12 MOB-Sub | Material |  |  | 8
3468-12-Trkg | 12 MOB-Trkg | Material |  |  | 8
3468-13 | 13 MOT | Material |  |  | 8
3468-13-Labor | 13 MOT-Labor | Material |  |  | 8
3468-13-Equip | 13 MOT-Equip | Material |  |  | 8
3468-13-Mat | 13 MOT-Mat | Material |  |  | 8
3468-13-Sub | 13 MOT-Sub | Material |  |  | 8
3468-13-Trkg | 13 MOT-Trkg | Material |  |  | 8
3468-14 | 14 Owner Pay IT | Material |  |  | 8
3468-14-Labor | 14 Owner Pay IT-Labor | Material |  |  | 8
3468-14-Equip | 14 Owner Pay IT-Equip | Material |  |  | 8
3468-14-Mat | 14 Owner Pay IT-Mat | Material |  |  | 8
3468-14-Sub | 14 Owner Pay IT-Sub | Material |  |  | 8
3468-14-Trkg | 14 Owner Pay IT-Trkg | Material |  |  | 8
3468-15 | 15 Pavement Marking | Material |  |  | 8
3468-15-Labor | 15 Pavement Marking-Labor | Material |  |  | 8
3468-15-Equip | 15 Pavement Marking-Equip | Material |  |  | 8
3468-15-Mat | 15 Pavement Marking-Mat | Material |  |  | 8
3468-15-Sub | 15 Pavement Marking-Sub | Material |  |  | 8
3468-15-Trkg | 15 Pavement Marking-Trkg | Material |  |  | 8
3468-16 | 16 Rail/Barr | Material |  |  | 8
3468-16-Labor | 16 Rail/Barr-Labor | Material |  |  | 8
3468-16-Equip | 16 Rail/Barr-Equip | Material |  |  | 8
3468-16-Mat | 16 Rail/Barr-Mat | Material |  |  | 8
3468-16-Sub | 16 Rail/Barr-Sub | Material |  |  | 8
3468-16-Trkg | 16 Rail/Barr-Trkg | Material |  |  | 8
3468-17 | 17 Roadway | Material |  |  | 8
3468-17-Labor | 17 Roadway-Labor | Material |  |  | 8
3468-17-Equip | 17 Roadway-Equip | Material |  |  | 8
3468-17-Mat | 17 Roadway-Mat | Material |  |  | 8
3468-17-Sub | 17 Roadway-Sub | Material |  |  | 8
3468-17-Trkg | 17 Roadway-Trkg | Material |  |  | 8
3468-18 | 18 Signals | Material |  |  | 8
3468-18-Labor | 18 Signals-Labor | Material |  |  | 8
3468-18-Equip | 18 Signals-Equip | Material |  |  | 8
3468-18-Mat | 18 Signals-Mat | Material |  |  | 8
3468-18-Sub | 18 Signals-Sub | Material |  |  | 8
3468-18-Trkg | 18 Signals-Trkg | Material |  |  | 8
3468-19 | 19 Signs | Material |  |  | 8
3468-19-Labor | 19 Signs-Labor | Material |  |  | 8
3468-19-Equip | 19 Signs-Equip | Material |  |  | 8
3468-19-Mat | 19 Signs-Mat | Material |  |  | 8
3468-19-Sub | 19 Signs-Sub | Material |  |  | 8
3468-19-Trkg | 19 Signs-Trkg | Material |  |  | 8
3468-20 | 20 SmartWorkZ | Material |  |  | 8
3468-20-Labor | 20 SmartWorkZ-Labor | Material |  |  | 8
3468-20-Equip | 20 SmartWorkZ-Equip | Material |  |  | 8
3468-20-Mat | 20 SmartWorkZ-Mat | Material |  |  | 8
3468-20-Sub | 20 SmartWorkZ-Sub | Material |  |  | 8
3468-20-Trkg | 20 SmartWorkZ-Trkg | Material |  |  | 8
3468-21 | 21 Structures | Material |  |  | 8
3468-21-Labor | 21 Structures-Labor | Material |  |  | 8
3468-21-Equip | 21 Structures-Equip | Material |  |  | 8
3468-21-Mat | 21 Structures-Mat | Material |  |  | 8
3468-21-Sub | 21 Structures-Sub | Material |  |  | 8
3468-21-Trkg | 21 Structures-Trkg | Material |  |  | 8
3468-22 | 22 Utility Relocation | Material |  |  | 8
3468-22-Labor | 22 Utility Relocation-Labor | Material |  |  | 8
3468-22-Equip | 22 Utility Relocation-Equip | Material |  |  | 8
3468-22-Mat | 22 Utility Relocation-Mat | Material |  |  | 8
3468-22-Sub | 22 Utility Relocation-Sub | Material |  |  | 8
3468-22-Trkg | 22 Utility Relocation-Trkg | Material |  |  | 8
3468-23 | 23 Walls | Material |  |  | 8
3468-23-Labor | 23 Walls-Labor | Material |  |  | 8
3468-23-Equip | 23 Walls-Equip | Material |  |  | 8
3468-23-Mat | 23 Walls-Mat | Material |  |  | 8
3468-23-Sub | 23 Walls-Sub | Material |  |  | 8
3468-23-Trkg | 23 Walls-Trkg | Material |  |  | 8
3468-24 | 24 Bonds & Insurance | Material |  |  | 8
3468-24-Labor | 24 Bonds & Insurance-Labor | Material |  |  | 8
3468-24-Equip | 24 Bonds & Insurance-Equip | Material |  |  | 8
3468-24-Mat | 24 Bonds & Insurance-Mat | Material |  |  | 8
3468-24-Sub | 24 Bonds & Insurance-Sub | Material |  |  | 8
3468-24-Trkg | 24 Bonds & Insurance-Trkg | Material |  |  | 8
3395 | 3395 - NEBT | Nonlabor |  |  | 1
NL | Non-Labor Resources | Nonlabor |  |  | 0
MTL | Material Quantities | Material |  |  | 1
MH | Man hours | Labor |  |  | 1
CY | Cubic Yards | Material | Cubic Yard |  | 1
Day | Days | Material | Day |  | 1
EA | Each | Material | Each |  | 1
LBS | Pounds | Material | Per Pound |  | 1
LF | Linear Foot | Material | Linear Feet |  | 1
LS | Lump Sum | Material | Lump Sum |  | 1
MBF | Thousand Board-Feet | Material | Thousand Board-feet |  | 1
MMO | Man Months | Material | Man Months |  | 1
S | Shifts | Material | Shifts |  | 1
SF | Square Foot | Material | Square Feet |  | 1
SY | Square Yards | Material | Square Yard |  | 1
TON | Tons | Material | Tons |  | 1
HR | Hours | Material | Hour |  | 8
VF | Vertical Feet | Material | Vertical Footage |  | 1
RING | Ring | Material | Ring |  | 1
3457-A | 3457-A | Material |  |  | 8
3457-0101-001-000 | MOBILIZATION | Material | Lump Sum |  | 8
3457-0102-001-000 | MAINTENANCE OF TRAFFIC | Material | Lump Sum |  | 8
3457-0122-99C-000 | PORTABLE CHANGEABLE MESSAGE SIGN, TEMPORARY (CONTINGENCY) | Material | Each |  | 8
3457-0104-020-000 | EROSION CONTROL MEASURES | Material | Lump Sum |  | 8
3457-0107-002-000 | MOWING | Material | Lump Sum |  | 8
3457-0110-001-001 | CLEARING & GRUBBING | Material | Lump Sum |  | 8
3457-0120-001-000 | REGULAR EXCAVATION | Material | Cubic Yard |  | 8
3457-0120-006-000 | EMBANKMENT | Material | Cubic Yard |  | 8
3457-0425-001-589 | INLETS, DITCH BOTTOM, TYPE H, MODIFY | Material | Each |  | 8
3457-0430-175-124 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 24" S/CD | Material | Linear Feet |  | 8
3457-0430-175-130 | PIPE CULVERT, OPTIONAL MATERIAL, ROUND, 30" S/CD | Material | Linear Feet |  | 8
3457-0430-982-129 | MITERED END SECTION, OPTIONAL ROUND, 24" CD | Material | Linear Feet |  | 8
3457-0430-982-133 | MITERED END SECTION, OPTIONAL ROUND, 30" CD | Material | Linear Feet |  | 8
3457-0550-010-220 | FENCING, TYPE B, 5.1'-6.0', STANDARD | Material | Linear Feet |  | 8
3457-0550-060-224 | FENCE GATE, TYPE B, DOUBLE, 20' OPENING | Material | Each |  | 8
3457-0570-001-002 | PERFORMANCE TURF, SOD | Material | Square Yard |  | 8
3457-0999-001-000 | ALLOWANCE FOR DISPUTES REVIEW BOARD | Material | Lump Sum |  | 8
3457-0999-002-000 | WORK ORDER ALLOWANCE | Material | Lump Sum |  | 8
NEBT-LANE CREWS | Lane Crew Resource 1 unit / shift | Labor |  |  | 1
Lane-TUNNEL | Tunnel Crew | Labor |  |  | 1
LANE-TUNNEL.Cleanup | Tunnel Clean-up Crew | Labor |  |  | 1
LANE-Shaft Crews | Lane Shaft Crews | Labor |  |  | 1
SUB-SOE | Support of Excavation Crews | Labor |  |  | 1
SUB-SOE.Secant Pile | Secant Pile Crew | Labor |  |  | 1
SUB-NSS CONCRETE | NSS Concrete Works Crew | Labor |  |  | 1
SUB-SHOTCRETE | Adit Shotcrete Crew | Labor |  |  | 1
SUB-DEWATERING | Dewatering Crew | Labor |  |  | 1
SUB-FREEZING | Ground Freezing Crew | Labor |  |  | 1
SUB-LANDSCAPE | Landscape Crew | Labor |  |  | 1
SUB-UTILITIES WORKS | Utilities Work Crew | Labor |  |  | 1
SUB-Vent. Control | Ventilation Control System Crew | Labor |  |  | 1
SUB-INSTRUMENT | Geotechnical Instrumentation Installation, Monitoring and Decommissioning Crew | Labor |  |  | 1
LANE-TUNNEL.EXCAV | Tunnel Excavation Crew | Labor |  |  | 1
LANE-Shaft-NSS | Near Surface Structures, Restoration Crews | Labor |  |  | 1
LANE-Shaft.Concrete | Shaft Liner, Adit Liner, Internal Hydraulic Structure Crews | Labor |  |  | 1
LANE-Shaft.Exc-Demo | Shaft Excavation, NSS Excavation, Demo, Clean-up Crews | Labor |  |  | 1
SUB-SOE.Soldier Pile | Soldier Piles Crew | Labor |  |  | 1
SUB-UTILITIES.Liner | Reinforce Utility Liner Crew | Labor |  |  | 1
SUB-UTILITIES.Sewer | Sewer Company Crew | Labor |  |  | 1
SUB-UTILITIES.Water | Water Company Crew | Labor |  |  | 1
SUB-UTILITIES.Electr | Electric Company Crew | Labor |  |  | 1
SUB-UTILITIES.Leak | Leak Detection Crew | Labor |  |  | 1
SUB-Mechanical | Mechanical Crew VV | Labor |  |  | 1
SUB-Electrical | Electrical Crew VV | Labor |  |  | 1
LANE-TUNNEL.MOR Tunn | MOR Tunnel Excavation Crew | Labor |  |  | 2
9156-SM-8 | Guardrail Stored Materials | Material | Lump Sum |  | 8
9156-SM-9 | ITS Stored Materials | Material | Lump Sum |  | 8
UPC112815.CO018 | CO#18 – Mill and Pave PWCP South of B665 | Material | Unit |  | 8
3417-85400-01 | NS Pile Cutoff 12" Pile | Material | Linear Feet |  | 8
3417-10250-01 | NS Aggr Material Lightweight Fill | Material | Ton |  | 8
3417-85011-01 | NS - 12" Pile B601 Abut B Batter Delay | Material | Lump Sum |  | 8
3417-85011-02 | NS - Sound Wall One (Wall R) | Material | Lump Sum |  | 8
3417-85011-03 | NS - Sound Wall One (Wall R) - Anchor Bolt Plates | Material | Lump Sum |  | 8
3417-85011-04 | NS HRSD 24" Sanitary Bypass (6400 GPM) | Material | Lump Sum |  | 8
3417-85400-02 | NS Pile Cutoff 24" Pile | Material | Linear Feet |  | 8
3417-85102-01 | B603 Pier 3 Modifications - Force Acct Auth #3 | Material | Dollar |  | 8
3417-85102-02 | Test Pit Excavation Locate - Force Acct Auth #3 | Material | Dollar |  | 8
3417-85075-01 | Value Engineering | Material | Dollar |  | 8
3417-85075-02 | Value Engineering | Material | Dollar |  | 8
3417-70000-7530 | NS Demo of Building, Parcel 11, D732 | Material | Lump Sum |  | 8
3417-70000-7540 | NS Demo of Building, Parcel 11, D733 | Material | Lump Sum |  | 8
3417-70000-7550 | NS Demo of Building, Parcel 11, D734 | Material | Lump Sum |  | 8
3417-70000-7560 | NS Demo of Building, Parcel 11, D735 | Material | Lump Sum |  | 8
3417-27003-01 | NS Selective Clearing | Material | Lump Sum |  | 8
3417-13543-01 | NS Wall Relocate Sound Wall | Material | Square Feet |  | 8
3417-50974-01 | NS Traffic | Material | Lump Sum |  | 8
3417-85014-01 | 4" Temp Pump at Storm Drain Str 5C-18 | Material | Day |  | 8
3417-85014-02 | Temp Pump at Storm Drain Str 5C-18 | Material | Day |  | 8
3417-38953-01 | NS-Additional Planting at B603 Pier 2 | Material | Lump Sum |  | 8
3417-06800-01 | Drop Inlet DI-2F, L=8' | Material | Each |  | 8
3417-06785-01 | Drop Inlet DI-2E, L=10' | Material | Each |  | 8
3417-02090-01 | Transition Pipe Inversion Liner 60" to 66" | Material | Linear Feet |  | 8
3417-51484-01 | Newtown Road Cuit for Conflict Adjustment | Material | Each |  | 8
3417-51965-01 | Virginia Beach Welcome Sign | Material | Lump Sum |  | 8
3417-54530-01 | NS Temp Pvmt Marking, Type E, 14" | Material | Linear Feet |  | 8
3417-54532-01 | NS Temp Pvmt Marking, Type E, 10" | Material | Linear Feet |  | 8
3417-54543-01 | Type D, Cl III Temp Pvmt Marking, 6" | Material | Linear Feet |  | 8
3417-54544-01 | Type D, Cl III Temp Pvmt Marking, 8" | Material | Linear Feet |  | 8
3417-54546-01 | Type D, Cl III Temp Pvmt Marking, 12" | Material | Linear Feet |  | 8
3417-51246-01 | Concrete Found CF-2 | Material | Each |  | 8
3417-59003-01 | NS Lighting High Mast Temporary Power | Material | Lump Sum |  | 8
3417-50901-01 | NS Traffic Sign - Overlay Sign Panel | Material | Square Feet |  | 8
3417-59000-01 | NS COVB Lighting Electrical Service Cabinet | Material | Each |  | 8
3417-51247-01 | Concrete Found CF-3 | Material | Each |  | 8
3417-85103-01 | Force Account Auth #4 | Material | Dollar |  | 8
3417-51961-01 | NS Adjust Existing Junction Box | Material | Each |  | 8
3417-54080-01 | Ty B CL VI Contrast Pvmt Mrkg, 6" | Material | Linear Feet |  | 8
3417-85100-01 | Force Account Auth #1 | Material | Dollar |  | 8
3417-85101-01 | Force Account Auth #2, Removal of Obstructions | Material | Dollar |  | 8
3417-85100-02 | Force Account Auth #1 - Payment 10/21/19 - 1/19/20 | Material | Dollar |  | 8
3417-85100-03 | Force Acct Auth #1 - GWTT Standby Rate 12.08.19 - 5.31.2020 | Material | Dollar |  | 8
3417-85100-04 | Force Acct Auth #1 - Prime Markup on 2nd Tier Sub. | Material | Dollar |  | 8
3417-85104-01 | Force Acct Auth #5 - 24" HRSD Wooden Shoring Excav | Material | Dollar |  | 8
3417-42064-01 | 6" Sanitary Service Lateral Connection | Material | Linear Feet |  | 8
3417-85100-05 | Force Account Auth #1 - GWTT Standby Rate | Material | Dollar |  | 8
3417-85100-06 | Force Account Auth #1 - GWTT Standby | Material | Dollar |  | 8
3417-49005-01 | NS Sewer Utility- Vicom Additional 4" SSL | Material | Lump Sum |  | 8
NEBT-SUB CREWS | Sub Crew Resource 1 unit / shift | Labor |  |  | 1
9156-SA49 | SA#49 - Additional Clearing – Parcel 142 | Material | Lump Sum |  | 8

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | comments | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(d) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Comments | Delete This Row
D1370 | U1860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install 6" PE GM (N Mitchell Ave) - TPG | 0 |  |  | H
D1370 | U1850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install 6" PE GM (E Columbus Dr) - TPG | 0 |  |  | H
D1370 | U1840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | 0 |  |  | H
U1540 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | Start Construction - R1 | 0 |  |  | H
U1540 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | Start Construction - R2 | 0 |  |  | H
U1540 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | Start Construction - R3 | 0 |  |  | H
U1530 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | Start Construction - R1 | 0 |  |  | H
U1530 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | Start Construction - R2 | 0 |  |  | H
U1530 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | Start Construction - R3 | 0 |  |  | H
U1410 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1410 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1410 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1400 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1400 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1400 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1390 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1390 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1390 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1380 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1380 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1380 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1370 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1370 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1370 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1360 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1360 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1360 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1350 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1350 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1350 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1340 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1340 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1340 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1330 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1330 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1330 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1320 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1320 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1320 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1310 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1310 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1310 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1300 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | Start Construction - R1 | 0 |  |  | H
U1300 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | Start Construction - R2 | 0 |  |  | H
U1300 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | Start Construction - R3 | 0 |  |  | H
U1290 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1290 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1290 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1280 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1280 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1280 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1270 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | Start Construction - R1 | 0 |  |  | H
U1270 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | Start Construction - R2 | 0 |  |  | H
U1270 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | Start Construction - R3 | 0 |  |  | H
U1250 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 6" CS GM (Ramp NE) - TPG | Start Construction - R1 | 0 |  |  | H
U1250 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 6" CS GM (Ramp NE) - TPG | Start Construction - R2 | 0 |  |  | H
U1250 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 6" CS GM (Ramp NE) - TPG | Start Construction - R3 | 0 |  |  | H
U1240 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | Start Construction - R1 | 0 |  |  | H
U1240 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | Start Construction - R2 | 0 |  |  | H
U1240 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | Start Construction - R3 | 0 |  |  | H
U1230 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1230 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1230 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1220 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1220 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1220 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1210 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 8" PE GM (E Columbus Dr) - TPG | Start Construction - R1 | 0 |  |  | H
U1210 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 8" PE GM (E Columbus Dr) - TPG | Start Construction - R2 | 0 |  |  | H
U1210 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 8" PE GM (E Columbus Dr) - TPG | Start Construction - R3 | 0 |  |  | H
U1200 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1200 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1200 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1190 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 2" BS GM (E Oak Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1190 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 2" BS GM (E Oak Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1190 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 2" BS GM (E Oak Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1180 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1180 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1180 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1170 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 6" PE GM (SMF 3A) - TPG | Start Construction - R1 | 0 |  |  | H
U1170 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 6" PE GM (SMF 3A) - TPG | Start Construction - R2 | 0 |  |  | H
U1170 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 6" PE GM (SMF 3A) - TPG | Start Construction - R3 | 0 |  |  | H
U1160 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Existing 3" WI GM (E 7th Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1160 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Existing 3" WI GM (E 7th Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1160 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Existing 3" WI GM (E 7th Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1150 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1150 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1150 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1140 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | Start Construction - R1 | 0 |  |  | H
U1140 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | Start Construction - R2 | 0 |  |  | H
U1140 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | Start Construction - R3 | 0 |  |  | H
U1130 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | Start Construction - R1 | 0 |  |  | H
U1130 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | Start Construction - R2 | 0 |  |  | H
U1130 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | Start Construction - R3 | 0 |  |  | H
U1120 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | Start Construction - R1 | 0 |  |  | H
U1120 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | Start Construction - R2 | 0 |  |  | H
U1120 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | Start Construction - R3 | 0 |  |  | H
U1110 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | Start Construction - R1 | 0 |  |  | H
U1110 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | Start Construction - R2 | 0 |  |  | H
U1110 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | Start Construction - R3 | 0 |  |  | H
U1100 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | Start Construction - R1 | 0 |  |  | H
U1100 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | Start Construction - R2 | 0 |  |  | H
U1100 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | Start Construction - R3 | 0 |  |  | H
U1090 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | Start Construction - R1 | 0 |  |  | H
U1090 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | Start Construction - R2 | 0 |  |  | H
U1090 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | Start Construction - R3 | 0 |  |  | H
U1080 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | Start Construction - R1 | 0 |  |  | H
U1080 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | Start Construction - R2 | 0 |  |  | H
U1080 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | Start Construction - R3 | 0 |  |  | H
U1070 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | Start Construction - R1 | 0 |  |  | H
U1070 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | Start Construction - R2 | 0 |  |  | H
U1070 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | Start Construction - R3 | 0 |  |  | H
U1060 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | Start Construction - R1 | 0 |  |  | H
U1060 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | Start Construction - R2 | 0 |  |  | H
U1060 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | Start Construction - R3 | 0 |  |  | H
U1050 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | Start Construction - R1 | 0 |  |  | H
U1050 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | Start Construction - R2 | 0 |  |  | H
U1050 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | Start Construction - R3 | 0 |  |  | H
U1040 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | Start Construction - R1 | 0 |  |  | H
U1040 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | Start Construction - R2 | 0 |  |  | H
U1040 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | Start Construction - R3 | 0 |  |  | H
U1030 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | Start Construction - R1 | 0 |  |  | H
U1030 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | Start Construction - R2 | 0 |  |  | H
U1030 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | Start Construction - R3 | 0 |  |  | H
U1020 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | Start Construction - R1 | 0 |  |  | H
U1020 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | Start Construction - R2 | 0 |  |  | H
U1020 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | Start Construction - R3 | 0 |  |  | H
U1010 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | Start Construction - R1 | 0 |  |  | H
U1010 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | Start Construction - R2 | 0 |  |  | H
U1010 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | Start Construction - R3 | 0 |  |  | H
U1000 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | Start Construction - R1 | 0 |  |  | H
U1000 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | Start Construction - R2 | 0 |  |  | H
U1000 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | Start Construction - R3 | 0 |  |  | H
U1720 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Fiber Distrib HUB - 207+04, 100 L - FTR | Start Construction - R1 | 0 |  |  | H
U1720 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Fiber Distrib HUB - 207+04, 100 L - FTR | Start Construction - R2 | 0 |  |  | H
U1720 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Fiber Distrib HUB - 207+04, 100 L - FTR | Start Construction - R3 | 0 |  |  | H
U1860 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 6" PE GM (N Mitchell Ave) - TPG | Start Construction - R1 | 0 |  |  | H
U1860 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 6" PE GM (N Mitchell Ave) - TPG | Start Construction - R2 | 0 |  |  | H
U1860 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 6" PE GM (N Mitchell Ave) - TPG | Start Construction - R3 | 0 |  |  | H
U1850 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 6" PE GM (E Columbus Dr) - TPG | Start Construction - R1 | 0 |  |  | H
U1850 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 6" PE GM (E Columbus Dr) - TPG | Start Construction - R2 | 0 |  |  | H
U1850 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 6" PE GM (E Columbus Dr) - TPG | Start Construction - R3 | 0 |  |  | H
U1840 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | Start Construction - R1 | 0 |  |  | H
U1840 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | Start Construction - R2 | 0 |  |  | H
U1840 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | Start Construction - R3 | 0 |  |  | H
U1430 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | Start Construction - R1 | 0 |  |  | H
U1430 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | Start Construction - R2 | 0 |  |  | H
U1430 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | Start Construction - R3 | 0 |  |  | H
U1660 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | Start Construction - R1 | 0 |  |  | H
U1660 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | Start Construction - R2 | 0 |  |  | H
U1660 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | Start Construction - R3 | 0 |  |  | H
U1650 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | Start Construction - R1 | 0 |  |  | H
U1650 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | Start Construction - R2 | 0 |  |  | H
U1650 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | Start Construction - R3 | 0 |  |  | H
U1640 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 1806+90, 85 R - TECO | Start Construction - R1 | 0 |  |  | H
U1640 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 1806+90, 85 R - TECO | Start Construction - R2 | 0 |  |  | H
U1640 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 1806+90, 85 R - TECO | Start Construction - R3 | 0 |  |  | H
U1630 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 1805+55, 130 R - TECO | Start Construction - R1 | 0 |  |  | H
U1630 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 1805+55, 130 R - TECO | Start Construction - R2 | 0 |  |  | H
U1630 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 1805+55, 130 R - TECO | Start Construction - R3 | 0 |  |  | H
U1620 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 1802+90, 10 L - TECO | Start Construction - R1 | 0 |  |  | H
U1620 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 1802+90, 10 L - TECO | Start Construction - R2 | 0 |  |  | H
U1620 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 1802+90, 10 L - TECO | Start Construction - R3 | 0 |  |  | H
U1610 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | Start Construction - R1 | 0 |  |  | H
U1610 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | Start Construction - R2 | 0 |  |  | H
U1610 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | Start Construction - R3 | 0 |  |  | H
U1600 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | Start Construction - R1 | 0 |  |  | H
U1600 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | Start Construction - R2 | 0 |  |  | H
U1600 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | Start Construction - R3 | 0 |  |  | H
U1590 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole - sta. 1806+90, 20 R - TECO | Start Construction - R1 | 0 |  |  | H
U1590 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole - sta. 1806+90, 20 R - TECO | Start Construction - R2 | 0 |  |  | H
U1590 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole - sta. 1806+90, 20 R - TECO | Start Construction - R3 | 0 |  |  | H
U1580 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole - sta. 1806+15, 10 R - TECO | Start Construction - R1 | 0 |  |  | H
U1580 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole - sta. 1806+15, 10 R - TECO | Start Construction - R2 | 0 |  |  | H
U1580 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole - sta. 1806+15, 10 R - TECO | Start Construction - R3 | 0 |  |  | H
U1570 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole - sta. 1805+30, 25 R - TECO | Start Construction - R1 | 0 |  |  | H
U1570 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole - sta. 1805+30, 25 R - TECO | Start Construction - R2 | 0 |  |  | H
U1570 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole - sta. 1805+30, 25 R - TECO | Start Construction - R3 | 0 |  |  | H
U1560 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole - sta. 1803+90, 10 R - TECO | Start Construction - R1 | 0 |  |  | H
U1560 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole - sta. 1803+90, 10 R - TECO | Start Construction - R2 | 0 |  |  | H
U1560 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole - sta. 1803+90, 10 R - TECO | Start Construction - R3 | 0 |  |  | H
U1550 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole - sta. 1802+90, 10 R - TECO | Start Construction - R1 | 0 |  |  | H
U1550 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole - sta. 1802+90, 10 R - TECO | Start Construction - R2 | 0 |  |  | H
U1550 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole - sta. 1802+90, 10 R - TECO | Start Construction - R3 | 0 |  |  | H
U1520 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 96+40, 65 L - TECO | Start Construction - R1 | 0 |  |  | H
U1520 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 96+40, 65 L - TECO | Start Construction - R2 | 0 |  |  | H
U1520 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 96+40, 65 L - TECO | Start Construction - R3 | 0 |  |  | H
U1510 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 95+95, 60 L - TECO | Start Construction - R1 | 0 |  |  | H
U1510 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 95+95, 60 L - TECO | Start Construction - R2 | 0 |  |  | H
U1510 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 95+95, 60 L - TECO | Start Construction - R3 | 0 |  |  | H
U1500 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 95+15, 60 L - TECO | Start Construction - R1 | 0 |  |  | H
U1500 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 95+15, 60 L - TECO | Start Construction - R2 | 0 |  |  | H
U1500 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 95+15, 60 L - TECO | Start Construction - R3 | 0 |  |  | H
U1490 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 94+40, 60 L - TECO | Start Construction - R1 | 0 |  |  | H
U1490 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 94+40, 60 L - TECO | Start Construction - R2 | 0 |  |  | H
U1490 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 94+40, 60 L - TECO | Start Construction - R3 | 0 |  |  | H
U1480 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 93+80, 60 L - TECO | Start Construction - R1 | 0 |  |  | H
U1480 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 93+80, 60 L - TECO | Start Construction - R2 | 0 |  |  | H
U1480 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 93+80, 60 L - TECO | Start Construction - R3 | 0 |  |  | H
U1470 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 93+35, 50 L - TECO | Start Construction - R1 | 0 |  |  | H
U1470 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 93+35, 50 L - TECO | Start Construction - R2 | 0 |  |  | H
U1470 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 93+35, 50 L - TECO | Start Construction - R3 | 0 |  |  | H
U1460 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 92+45, 50 L - TECO | Start Construction - R1 | 0 |  |  | H
U1460 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 92+45, 50 L - TECO | Start Construction - R2 | 0 |  |  | H
U1460 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 92+45, 50 L - TECO | Start Construction - R3 | 0 |  |  | H
U1450 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 91+25, 40 L - TECO | Start Construction - R1 | 0 |  |  | H
U1450 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 91+25, 40 L - TECO | Start Construction - R2 | 0 |  |  | H
U1450 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 91+25, 40 L - TECO | Start Construction - R3 | 0 |  |  | H
U1440 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Pole - sta. 317+70, 73 L - TECO | Start Construction - R1 | 0 |  |  | H
U1440 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Pole - sta. 317+70, 73 L - TECO | Start Construction - R2 | 0 |  |  | H
U1440 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Pole - sta. 317+70, 73 L - TECO | Start Construction - R3 | 0 |  |  | H
U1420 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Start Construction - R1 | 0 |  |  | H
U1420 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Start Construction - R2 | 0 |  |  | H
U1420 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Start Construction - R3 | 0 |  |  | H
U1710 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | Start Construction - R1 | 0 |  |  | H
U1710 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | Start Construction - R2 | 0 |  |  | H
U1710 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | Start Construction - R3 | 0 |  |  | H
U1700 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R1 | 0 |  |  | H
U1700 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R2 | 0 |  |  | H
U1700 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R3 | 0 |  |  | H
U1690 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R1 | 0 |  |  | H
U1690 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R2 | 0 |  |  | H
U1690 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R3 | 0 |  |  | H
U1680 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | Start Construction - R1 | 0 |  |  | H
U1680 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | Start Construction - R2 | 0 |  |  | H
U1680 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | Start Construction - R3 | 0 |  |  | H
U1670 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | Start Construction - R1 | 0 |  |  | H
U1670 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | Start Construction - R2 | 0 |  |  | H
U1670 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | Start Construction - R3 | 0 |  |  | H
U1830 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Splice/Cutover new facilities within project limits - FTR | Start Construction - R1 | 0 |  |  | H
U1830 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Splice/Cutover new facilities within project limits - FTR | Start Construction - R2 | 0 |  |  | H
U1830 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Splice/Cutover new facilities within project limits - FTR | Start Construction - R3 | 0 |  |  | H
U1820 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install all Copper/Fiber Cables within project limits - FTR | Start Construction - R1 | 0 |  |  | H
U1820 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install all Copper/Fiber Cables within project limits - FTR | Start Construction - R2 | 0 |  |  | H
U1820 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install all Copper/Fiber Cables within project limits - FTR | Start Construction - R3 | 0 |  |  | H
U1810 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | Start Construction - R1 | 0 |  |  | H
U1810 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | Start Construction - R2 | 0 |  |  | H
U1810 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | Start Construction - R3 | 0 |  |  | H
U1800 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | Start Construction - R1 | 0 |  |  | H
U1800 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | Start Construction - R2 | 0 |  |  | H
U1800 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | Start Construction - R3 | 0 |  |  | H
U1790 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | Start Construction - R1 | 0 |  |  | H
U1790 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | Start Construction - R2 | 0 |  |  | H
U1790 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | Start Construction - R3 | 0 |  |  | H
U1780 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | Start Construction - R1 | 0 |  |  | H
U1780 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | Start Construction - R2 | 0 |  |  | H
U1780 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | Start Construction - R3 | 0 |  |  | H
U1770 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Fiber XBOX - 207+00, 5 L - FTR | Start Construction - R1 | 0 |  |  | H
U1770 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Fiber XBOX - 207+00, 5 L - FTR | Start Construction - R2 | 0 |  |  | H
U1770 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Fiber XBOX - 207+00, 5 L - FTR | Start Construction - R3 | 0 |  |  | H
U1760 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | Start Construction - R1 | 0 |  |  | H
U1760 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | Start Construction - R2 | 0 |  |  | H
U1760 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | Start Construction - R3 | 0 |  |  | H
U1750 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | Start Construction - R1 | 0 |  |  | H
U1750 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | Start Construction - R2 | 0 |  |  | H
U1750 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | Start Construction - R3 | 0 |  |  | H
U1740 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | Start Construction - R1 | 0 |  |  | H
U1740 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | Start Construction - R2 | 0 |  |  | H
U1740 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | Start Construction - R3 | 0 |  |  | H
U1730 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Fiber XBOX - 207+04, 110 L - FTR | Start Construction - R1 | 0 |  |  | H
U1730 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Fiber XBOX - 207+04, 110 L - FTR | Start Construction - R2 | 0 |  |  | H
U1730 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Fiber XBOX - 207+04, 110 L - FTR | Start Construction - R3 | 0 |  |  | H
D1370 | U1830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Splice/Cutover new facilities within project limits - FTR | 0 |  |  | H
D1370 | U1820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install all Copper/Fiber Cables within project limits - FTR | 0 |  |  | H
D1370 | U1810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | 0 |  |  | H
D1370 | U1800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | 0 |  |  | H
D1370 | U1790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | 0 |  |  | H
D1370 | U1780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | 0 |  |  | H
D1370 | U1770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Fiber XBOX - 207+00, 5 L - FTR | 0 |  |  | H
D1370 | U1760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | 0 |  |  | H
D1370 | U1750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | 0 |  |  | H
D1370 | U1740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | 0 |  |  | H
D1370 | U1730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Fiber XBOX - 207+04, 110 L - FTR | 0 |  |  | H
A36060 | A36530 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Excav for 60" Str - OUT-1 - R3 | Const 60" Storm Drainage - OUT-2 to OUT-1 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
D1370 | U1720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Fiber Distrib HUB - 207+04, 100 L - FTR | 0 |  |  | H
P1030 | A1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Review and Approve - Construction Quality Control Plan | Mobilization | 0 |  |  | H
D1140 | A1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Review and Approve - SWPPP & NOI | Install Erosion Control Devices | 0 |  | SUB-EROSION | H
D2790 | A26990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Issue - RFC Roadway Plans - R3 | Install DRG CS-3A to S-117A / S-120 - Pond SMF 3A - R3 - P0 | 0 |  | PIPE | H
D1370 | U1660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | 0 |  |  | H
D1370 | U1650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | 0 |  |  | H
D1370 | U1640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 1806+90, 85 R - TECO | 0 |  |  | H
D1370 | U1630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 1805+55, 130 R - TECO | 0 |  |  | H
D1370 | U1620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 1802+90, 10 L - TECO | 0 |  |  | H
D1370 | U1610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | 0 |  |  | H
D1370 | U1600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | 0 |  |  | H
D1370 | U1590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole - sta. 1806+90, 20 R - TECO | 0 |  |  | H
D1370 | U1580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole - sta. 1806+15, 10 R - TECO | 0 |  |  | H
D1370 | U1570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole - sta. 1805+30, 25 R - TECO | 0 |  |  | H
D1370 | U1560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole - sta. 1803+90, 10 R - TECO | 0 |  |  | H
D1370 | U1550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole - sta. 1802+90, 10 R - TECO | 0 |  |  | H
Admin-1100 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Design Completion | Substantial Completion (Sept. 4th, 2026) | 0 |  |  | H
D1370 | U1520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 96+40, 65 L - TECO | 0 |  |  | H
D1370 | U1510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 95+95, 60 L - TECO | 0 |  |  | H
D1370 | U1500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 95+15, 60 L - TECO | 0 |  |  | H
D1370 | U1490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 94+40, 60 L - TECO | 0 |  |  | H
D1370 | U1480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 93+80, 60 L - TECO | 0 |  |  | H
D1370 | U1470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 93+35, 50 L - TECO | 0 |  |  | H
D1370 | U1460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 92+45, 50 L - TECO | 0 |  |  | H
D1370 | U1450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 91+25, 40 L - TECO | 0 |  |  | H
D1370 | U1440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole - sta. 317+70, 73 L - TECO | 0 |  |  | H
D1370 | U1430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | 0 |  |  | H
D1370 | U1420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Dry Utility Relocation Plans | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | 0 |  |  | H
U1420 | U1430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - IBL(all) - B1.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | 0 |  |  | H
D3250 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Issue - RFC - 60" Drainage System - R3 | Start Construction - R3 | 0 |  |  | H
D1590 | A1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Issue - RFC TTCP Plans - R1 Phase 1 | Mobilization | 0 |  |  | H
A1070 | A1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Install Advanced Warning signs | Install Erosion Control Devices | 0 | TC-Maint. | SUB-EROSION | H
A15140 | A15050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | ST-PILE | EW- ALL EW | H
A1630 | A15050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | EW- ALL EW | EW- ALL EW | H
A1630 | A14700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | EW- ALL EW | EW-STR | H
Admin-1045 | D2740 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Begin Design | Develop and Submit - 90% Roadway Plans - R3 | 0 |  |  | H
Admin-1045 | D2680 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Begin Design | Develop and Submit - 90% Roadway Plans - R2 | 0 |  |  | H
D5170 | A1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Issue - RFC Early Pkg Eros - R1 | Install Erosion Control Devices | 0 |  | SUB-EROSION | H
D1260 | D1250 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | Develop and Submit - 90% TTCP Plans - R1 Phase 2 | 20 |  |  | H
D1370 | U1260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.3.2 Uniti Fiber/Southern Light - During Construction | Issue - RFC Dry Utility Relocation Plans | Adj HH to grade 24x36x36- (256+20, 105' RT) - Uniti | 0 |  |  | H
D1370 | U1250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 6" CS GM (Ramp NE) - TPG | 0 |  |  | H
D1370 | U1240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | 0 |  |  | H
D1370 | U1230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | 0 |  |  | H
D1370 | U1220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | 0 |  |  | H
D1370 | U1210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 8" PE GM (E Columbus Dr) - TPG | 0 |  |  | H
D1370 | U1200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | 0 |  |  | H
D1370 | U1190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 2" BS GM (E Oak Ave) - TPG | 0 |  |  | H
D1370 | U1180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | 0 |  |  | H
D1370 | U1170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 6" PE GM (SMF 3A) - TPG | 0 |  |  | H
D1370 | U1160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Remove Existing 3" WI GM (E 7th Ave) - TPG | 0 |  |  | H
D1370 | U1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Dry Utility Relocation Plans | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | 0 |  |  | H
D1370 | U1140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | 0 |  |  | H
D1370 | U1130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | 0 |  |  | H
D1370 | U1120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | 0 |  |  | H
D1370 | U1110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | 0 |  |  | H
D1370 | U1100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | 0 |  |  | H
D1370 | U1090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | 0 |  |  | H
D1370 | U1080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | 0 |  |  | H
D1370 | U1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | 0 |  |  | H
D1370 | U1060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | 0 |  |  | H
D1370 | U1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | 0 |  |  | H
D1370 | U1040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | 0 |  |  | H
D1370 | U1030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | 0 |  |  | H
D1370 | U1020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | 0 |  |  | H
D1370 | U1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | 0 |  |  | H
D1370 | U1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Dry Utility Relocation Plans | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | 0 |  |  | H
A22010 | A22000 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | ST-CIP | SUB-BR-SLIP | H
A21150 | A22210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | Place Wall Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Install Perm. Signs - R1 - P3 | 0 | SUB-BR-SLIP | SUB-SIGN | H
P1640 | A36360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | Procure Pile - Bridge 12 | Drive Pile - Brg 100143 - Pier 2 - R3 - P3 | 0 |  | ST-PILE | H
P1640 | A36340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | Procure Pile - Bridge 12 | Drive Pile - Brg 100143 - Pier 1 - R3 - P3 | 0 |  | ST-PILE | H
P1640 | A36330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Procure Pile - Bridge 12 | Drive Pile - Brg 100143 - End Bent 2 - R3 - P3 | 0 |  | ST-PILE | H
P1640 | A36320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Procure Pile - Bridge 12 | Drive Pile - Brg 100143 - End Bent 1 - R3 - P3 | 0 |  | ST-PILE | H
P1630 | A32630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - Pier 2 - R3 - P3 | 0 |  | ST-PILE | H
P1630 | A30330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1630 | A30990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - Pier 1 - R3 - P3 | 0 |  | ST-PILE | H
P1630 | A28580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1630 | A31510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P3 | 0 |  | ST-PILE | H
P1630 | A29110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1630 | A31440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P3 | 0 |  | ST-PILE | H
P1630 | A29040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Procure Pile - Bridge 11 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1620 | A29630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1620 | A29550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1620 | A29390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1620 | A30900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P3 | 0 |  | ST-PILE | H
P1620 | A28440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1620 | A30830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P3 | 0 |  | ST-PILE | H
P1620 | A28370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Procure Pile - Bridge 10 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 |  | ST-PILE | H
P1610 | A32990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Procure Pile - Bridge 09 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P3 | 0 |  | ST-PILE | H
P1610 | A25570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Procure Pile - Bridge 09 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 |  | ST-PILE | H
P1610 | A32680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Procure Pile - Bridge 09 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P3 | 0 |  | ST-PILE | H
P1610 | A25250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Procure Pile - Bridge 09 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 |  | ST-PILE | H
P1430 | A26420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Procure Pile - Bridge 08 | Drive Pile - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 |  | ST-PILE | H
P1430 | A24880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Procure Pile - Bridge 08 | Drive Pile - Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 |  | ST-PILE | H
D3610 | P1640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 12 Plans - R3 | Procure Pile - Bridge 12 | 0 |  |  | H
D3670 | P1630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 11 Plans - R3 | Procure Pile - Bridge 11 | 0 |  |  | H
D2370 | P1620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat2 Brg 10 Plans - R3 | Procure Pile - Bridge 10 | 0 |  |  | H
D3550 | P1610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 09 Plans - R3 | Procure Pile - Bridge 09 | 0 |  |  | H
A1020 | A1080 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | Clear and Grub | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | 0 | SUB-EW-C&G | EW-SML | H
D5170 | A1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Issue - RFC Early Pkg Eros - R1 | Mobilization | 0 |  |  | H
Admin-1045 | D5120 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | Begin Design | Develop and Submit - 90% Early Pkg Eros - R1 | 0 |  |  | H
D5150 | D5160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | Review and Approve - Final Early Pkg Eros - R1 | Develop and Submit - Sign & Seal Early Pkg Eros - R1 | 0 |  |  | H
D5130 | D5140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | Review and Approve - 90% Early Pkg Eros - R1 | Develop and Submit - Final Early Pkg Eros - R1 | 0 |  |  | H
D5120 | D5130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | Develop and Submit - 90% Early Pkg Eros - R1 | Review and Approve - 90% Early Pkg Eros - R1 | 0 |  |  | H
D5140 | D5150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | Develop and Submit - Final Early Pkg Eros - R1 | Review and Approve - Final Early Pkg Eros - R1 | 0 |  |  | H
D5160 | D5170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | I-275 - I-4 - IBL(all) - B1.3.11.2 R1 Early Package Design | Develop and Submit - Sign & Seal Early Pkg Eros - R1 | Issue - RFC Early Pkg Eros - R1 | 0 |  |  | H
D1590 | A1030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.2.2.1.1 R1 - Ph0 - MOT | Issue - RFC TTCP Plans - R1 Phase 1 | Install MOT - I-4 Exit Ramp - R1 - P0 | 0 |  | TC-Maint. | H
A1070 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Advanced Warning signs | Start Construction - R1 | 0 | TC-Maint. |  | H
D1590 | A1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Issue - RFC TTCP Plans - R1 Phase 1 | Install Advanced Warning signs | 0 |  | TC-Maint. | H
P1280 | A23000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Procure Pile - Bridge 6 - R2 | Drive Pile - Brg 100650 - Pier 2 - R2 - P1 | 0 |  | ST-PILE | H
P1280 | A22620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Procure Pile - Bridge 6 - R2 | Drive Pile - Brg 100650 - Pier 1 - R2 - P1 | 0 |  | ST-PILE | H
P1280 | A22930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Procure Pile - Bridge 6 - R2 | Drive Pile - Brg 100650 - End Bent 2 - R2 - P1 | 0 |  | ST-PILE | H
P1280 | A22540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Procure Pile - Bridge 6 - R2 | Drive Pile - Brg 100650 - End Bent 1 - R2 - P1 | 0 |  | ST-PILE | H
P1600 | A23710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Procure Pile - Bridge 7 - R2 | Drive Pile - Brg 100652 - Pier 2 - R2 - P1 | 0 |  | ST-PILE | H
P1600 | A23400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Procure Pile - Bridge 7 - R2 | Drive Pile - Brg 100652 - Pier 1 - R2 - P1 | 0 |  | ST-PILE | H
P1600 | A23640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Procure Pile - Bridge 7 - R2 | Drive Pile - Brg 100652 - End Bent 2 - R2 - P1 | 0 |  | ST-PILE | H
P1600 | A23320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Procure Pile - Bridge 7 - R2 | Drive Pile - Brg 100652 - End Bent 1 - R2 - P1 | 0 |  | ST-PILE | H
P1490 | A23000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Procure Girders - Bridge 6 | Drive Pile - Brg 100650 - Pier 2 - R2 - P1 | 0 |  | ST-PILE | H
P1490 | A22620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Procure Girders - Bridge 6 | Drive Pile - Brg 100650 - Pier 1 - R2 - P1 | 0 |  | ST-PILE | H
P1490 | A22930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Procure Girders - Bridge 6 | Drive Pile - Brg 100650 - End Bent 2 - R2 - P1 | 0 |  | ST-PILE | H
P1490 | A22540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Procure Girders - Bridge 6 | Drive Pile - Brg 100650 - End Bent 1 - R2 - P1 | 0 |  | ST-PILE | H
D3490 | P1600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 07 Plans - R2 | Procure Pile - Bridge 7 - R2 | 0 |  |  | H
P1580 | A17910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Procure Pile - Bridge 4 - R1 | Drive Pile - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1580 | A17520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Procure Pile - Bridge 4 - R1 | Drive Pile - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1580 | A18060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Procure Pile - Bridge 4 - R1 | Drive Pile - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1580 | A17980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Procure Pile - Bridge 4 - R1 | Drive Pile - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1570 | A17200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Procure Pile - Bridge 3 - R1 | Drive Pile - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1570 | A16690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Procure Pile - Bridge 3 - R1 | Drive Pile - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1570 | A17360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Procure Pile - Bridge 3 - R1 | Drive Pile - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1570 | A17270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Procure Pile - Bridge 3 - R1 | Drive Pile - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 |  | ST-PILE | H
P1560 | A35250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Procure Pile - Bridge 2 - R1 | Drive Pile - Brg 2 - Pier 3 - R1 - P2.S1 | 0 |  | ST-PILE | H
P1560 | A34980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Procure Pile - Bridge 2 - R1 | Drive Pile - Brg 2 - Pier 2 - R1 - P2.S1 | 0 |  | ST-PILE | H
P1560 | A34740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Procure Pile - Bridge 2 - R1 | Drive Pile - Brg 2 - Pier 1 - R1 - P2.S1 | 0 |  | ST-PILE | H
P1560 | A35520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Procure Pile - Bridge 2 - R1 | Drive Pile - Brg 2 - End Bent 2 - R1 - P2.S1 | 0 |  | ST-PILE | H
P1560 | A35450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Procure Pile - Bridge 2 - R1 | Drive Pile - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 |  | ST-PILE | H
P1590 | A15140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | ST-PILE | H
P1590 | A14720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | ST-PILE | H
P1590 | A15070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 |  | ST-PILE | H
P1590 | A1650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 |  | ST-PILE | H
D3430 | P1590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 05 Plans - R1 | Procure Pile - Bridge 5 - R1 | 0 |  |  | H
D3370 | P1580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 04 Plans - R1 | Procure Pile - Bridge 4 - R1 | 0 |  |  | H
D2850 | P1570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 03 Plans - R1 | Procure Pile - Bridge 3 - R1 | 0 |  |  | H
D2930 | P1560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat2 Brg 02 Plans - R1 | Procure Pile - Bridge 2 - R1 | 0 |  |  | H
D2080 | P1430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 08 Plans - R3 | Procure Pile - Bridge 08 | 0 |  |  | H
D3090 | P1280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.5.3 R2 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 06 Plans - R2 | Procure Pile - Bridge 6 - R2 | 0 |  |  | H
D3310 | P1200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 01 Plans - R1 | Procure Pile - Bridge 1 - R1 | 0 |  |  | H
P1550 | A33740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Procure Girders - Bridge 12 | Erect Girders - Brg 100143 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
P1550 | A33650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Procure Girders - Bridge 12 | Erect Girders - Brg 100143 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
P1550 | A33500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Procure Girders - Bridge 12 | Erect Girders - Brg 100143 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A32340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 6 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A30040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1530 | A32250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 5 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A29950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 5 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1530 | A32160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 4 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A29860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 4 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1530 | A30720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A28200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 3 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1530 | A30630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A28110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 2 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1530 | A30480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
P1530 | A27960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Procure Girders - Bridge 10 | Erect Girders - Brg 100139 - Span 1 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1540 | A31280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Procure Girders - Bridge 11 | Erect Girders - Brg 100141 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
P1540 | A28870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Procure Girders - Bridge 11 | Erect Girders - Brg 100141 - Span 3 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1540 | A31190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Procure Girders - Bridge 11 | Erect Girders - Brg 100141 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
P1540 | A28780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Procure Girders - Bridge 11 | Erect Girders - Brg 100141 - Span 2 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1540 | A31040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Procure Girders - Bridge 11 | Erect Girders - Brg 100141 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
P1540 | A28630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Procure Girders - Bridge 11 | Erect Girders - Brg 100141 - Span 1 - R3 - P2.S2 | 0 |  | ST-BEAM | H
P1520 | A32820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Procure Girders - Bridge 9 | Erect Girders - Brg 100869 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
P1520 | A25400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Procure Girders - Bridge 9 | Erect Girders - Brg 100869 - Span 1 - R3 - P1.S2 | 0 |  | ST-BEAM | H
P1510 | A25110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Procure Girders - Bridge 8 | Erect Girders - Brg 100868 - Span 4 - R3 - P1.S2 | 0 |  | ST-BEAM | H
P1510 | A26490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Procure Girders - Bridge 8 | Erect Girders - Brg 100868 - Span 3 - R3 - P1.S2 | 0 |  | ST-BEAM | H
P1510 | A25020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Procure Girders - Bridge 8 | Erect Girders - Brg 100868 - Span 2 - R3 - P1.S2 | 0 |  | ST-BEAM | H
P1510 | A24640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Procure Girders - Bridge 8 | Erect Girders - Brg 100868 - Span 1 - R3 - P1.S2 | 0 |  | ST-BEAM | H
D3610 | P1550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 12 Plans - R3 | Procure Girders - Bridge 12 | 0 |  |  | H
D3670 | P1540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 11 Plans - R3 | Procure Girders - Bridge 11 | 0 |  |  | H
D2370 | P1530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat2 Brg 10 Plans - R3 | Procure Girders - Bridge 10 | 0 |  |  | H
D3550 | P1520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 09 Plans - R3 | Procure Girders - Bridge 9 | 0 |  |  | H
D2080 | P1510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 08 Plans - R3 | Procure Girders - Bridge 8 | 0 |  |  | H
P1500 | A23870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Procure Girders - Bridge 7 | Erect Girders - Brg 100652 - Span 3 - R2 - P1 | 0 |  | ST-BEAM | H
P1500 | A23780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Procure Girders - Bridge 7 | Erect Girders - Brg 100652 - Span 2 - R2 - P1 | 0 |  | ST-BEAM | H
P1500 | A23470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Procure Girders - Bridge 7 | Erect Girders - Brg 100652 - Span 1 - R2 - P1 | 0 |  | ST-BEAM | H
P1490 | A23160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Procure Girders - Bridge 6 | Erect Girders - Brg 100650 - Span 3 - R2 - P1 | 0 |  | ST-BEAM | H
P1490 | A23070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Procure Girders - Bridge 6 | Erect Girders - Brg 100650 - Span 2 - R2 - P1 | 0 |  | ST-BEAM | H
P1490 | A22690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Procure Girders - Bridge 6 | Erect Girders - Brg 100650 - Span 1 - R2 - P1 | 0 |  | ST-BEAM | H
D3490 | P1500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 07 Plans - R2 | Procure Girders - Bridge 7 | 0 |  |  | H
D3090 | P1490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.5.1 R2 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 06 Plans - R2 | Procure Girders - Bridge 6 | 0 |  |  | H
P1460 | A17810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Procure Girders - Bridge 4 | Erect Girders - Brg 100657 - Span 3 - R1 - P1.S2 | 0 |  | ST-BEAM | H
P1460 | A17720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Procure Girders - Bridge 4 | Erect Girders - Brg 100657 - Span 2 - R1 - P1.S2 | 0 |  | ST-BEAM | H
P1460 | A17570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Procure Girders - Bridge 4 | Erect Girders - Brg 100657 - Span 1 - R1 - P1.S2 | 0 |  | ST-BEAM | H
P1470 | A17100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Procure Girders - Bridge 3 | Erect Girders - Brg 100656 - Span 3 - R1 - P1.S2 | 0 |  | ST-BEAM | H
P1470 | A17010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Procure Girders - Bridge 3 | Erect Girders - Brg 100656 - Span 2 - R1 - P1.S2 | 0 |  | ST-BEAM | H
P1470 | A16770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Procure Girders - Bridge 3 | Erect Girders - Brg 100656 - Span 1 - R1 - P1.S2 | 0 |  | ST-BEAM | H
P1480 | A20580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Procure Girders - Bridge 1 | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S3 | 0 |  | ST-BEAM | H
P1480 | A21570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Procure Girders - Bridge 1 | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S2 | 0 |  | ST-BEAM | H
D3370 | P1460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 04 Plans - R1 | Procure Girders - Bridge 4 | 0 |  |  | H
D2850 | P1470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 03 Plans - R1 | Procure Girders - Bridge 3 | 0 |  |  | H
D3310 | P1480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 01 Plans - R1 | Procure Girders - Bridge 1 | 0 |  |  | H
P1450 | A15300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Procure Girders - Bridge 5 | Erect Girders - Brg 100865 - Span 3 - R1 - P1.S1 | 0 |  | ST-BEAM | H
P1450 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Procure Girders - Bridge 5 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | ST-BEAM | H
P1450 | A14790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Procure Girders - Bridge 5 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | ST-BEAM | H
D3430 | P1450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 05 Plans - R1 | Procure Girders - Bridge 5 | 0 |  |  | H
P1440 | A36580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6 R3 Procurement | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Procure 60" Drainage Structures | Install Str for 60" Drainage - OUT-9 - R3 | 0 |  | SUB-TUNNEL | H
A36670 | A26580 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.4 R3 - Ph0 - 60" Drainage - Abandonment | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Flow Fill existing 60" Drainage System | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | 0 | DRAIN |  | H
A36640 | A36670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.4 R3 - Ph0 - 60" Drainage - Abandonment | Install Str for 60" Drainage - OUT-1 - R3 | Flow Fill existing 60" Drainage System | 0 | SUB-TUNNEL | DRAIN | H
A36530 | A36640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-2 to OUT-1 - R3 | Install Str for 60" Drainage - OUT-1 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36530 | A36630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-2 to OUT-1 - R3 | Install Str for 60" Drainage - OUT-2 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36510 | A36620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-3 to OUT-2 - R3 | Install Str for 60" Drainage - OUT-3 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36500 | A36610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-4 to OUT-3 - R3 | Install Str for 60" Drainage - OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36480 | A36600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | Install Str for 60" Drainage - OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36450 | A36590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | Install Str for 60" Drainage - OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36540 | A36660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | Install Str for 60" Drainage - OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36550 | A36650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | Install Str for 60" Drainage - OUT-8 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36440 | A36580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | Install Str for 60" Drainage - OUT-9 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36660 | A36590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-7 - R3 | Install Str for 60" Drainage - OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36650 | A36660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-8 - R3 | Install Str for 60" Drainage - OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36580 | A36650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-9 - R3 | Install Str for 60" Drainage - OUT-8 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36510 | A36060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-3 to OUT-2 - R3 | Excav for 60" Str - OUT-1 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36500 | A36050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-4 to OUT-3 - R3 | Excav for 60" Str - OUT-2 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36480 | A36040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | Excav for 60" Str - OUT-3 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36450 | A36030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | Excav for 60" Str - OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36540 | A36020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | Excav for 60" Str - OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36550 | A36010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | Excav for 60" Str - OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
D3250 | A36000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Issue - RFC - 60" Drainage System - R3 | Excav for 60" Str - OUT-9 - R3 | 0 |  | SUB-TUNNEL | H
A36440 | A36570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | Excav for 60" Str - OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36000 | A36440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Excav for 60" Str - OUT-9 - R3 | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36570 | A36010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-7 - R3 | Excav for 60" Str - OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36560 | A36570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-8 - R3 | Excav for 60" Str - OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36000 | A36560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-9 - R3 | Excav for 60" Str - OUT-8 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36510 | A36530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-3 to OUT-2 - R3 | Const 60" Storm Drainage - OUT-2 to OUT-1 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36500 | A36510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-4 to OUT-3 - R3 | Const 60" Storm Drainage - OUT-3 to OUT-2 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36480 | A36500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | Const 60" Storm Drainage - OUT-4 to OUT-3 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36450 | A36480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36540 | A36450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36550 | A36540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36440 | A36550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - IBL(all) - B1.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
SD2390 | P1440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - IBL(all) - B1.4.3.6 R3 Procurement | FDOT - Review & Comment Shp Drwgs - 60" Drainage Str | Procure 60" Drainage Structures | 0 |  |  | H
D3250 | SD2350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Issue - RFC - 60" Drainage System - R3 | Develop & Submit Shp Drwgs - 60" Drainage Str | 0 |  |  | H
SD2380 | SD2390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Design 2nd Review & Comnt Shp Drwgs - 60" Drainage Str | FDOT - Review & Comment Shp Drwgs - 60" Drainage Str | 0 |  |  | H
SD2370 | SD2380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Revise & Resubmit Shp Drwgs - 60" Drainage Str | Design 2nd Review & Comnt Shp Drwgs - 60" Drainage Str | 0 |  |  | H
SD2360 | SD2370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Designer Review & Comnt Shp Drwgs - 60" Drainage Str | Revise & Resubmit Shp Drwgs - 60" Drainage Str | 0 |  |  | H
SD2350 | SD2360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - IBL(all) - B1.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Develop & Submit Shp Drwgs - 60" Drainage Str | Designer Review & Comnt Shp Drwgs - 60" Drainage Str | 0 |  |  | H
Admin-1045 | D3180 | SS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Begin Design | Develop and Submit - 60% - 60" Drainage System - R3 | 0 |  |  | H
D4870 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | Design Completion | 0 |  |  | H
D4810 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | Design Completion | 0 |  |  | H
D4750 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 9 | Design Completion | 0 |  |  | H
D4690 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | Design Completion | 0 |  |  | H
D4630 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | Design Completion | 0 |  |  | H
D4570 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 7-2 Ramp EN / Br 7 | Design Completion | 0 |  |  | H
D4510 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 7-1 Ramp EN / Br 7 | Design Completion | 0 |  |  | H
D4450 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 6-1 Ramp EN / Br 6 | Design Completion | 0 |  |  | H
D4390 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | Design Completion | 0 |  |  | H
D4330 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | Design Completion | 0 |  |  | H
D4270 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 4-2 Br 4 | Design Completion | 0 |  |  | H
D4210 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 4-1 Br 4 | Design Completion | 0 |  |  | H
D4150 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 3-2 Br 3 | Design Completion | 0 |  |  | H
D4090 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 3-1 Br 3 | Design Completion | 0 |  |  | H
D4030 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 2-4 Br 2 | Design Completion | 0 |  |  | H
D3910 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Design Completion | 0 |  |  | H
D3850 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Design Completion | 0 |  |  | H
D3790 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 2-1 - Br 2 | Design Completion | 0 |  |  | H
D5110 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 104 Ramp EN | Design Completion | 0 |  |  | H
D5050 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 103 Ramp EN | Design Completion | 0 |  |  | H
D4990 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 102 Ramp C | Design Completion | 0 |  |  | H
D4930 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | Design Completion | 0 |  |  | H
D3730 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | Design Completion | 0 |  |  | H
D2310 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MSE Wall RW 1-1 | Design Completion | 0 |  |  | H
D2370 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat2 Brg 10 Plans - R3 | Design Completion | 0 |  |  | H
D3610 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 12 Plans - R3 | Design Completion | 0 |  |  | H
D3670 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 11 Plans - R3 | Design Completion | 0 |  |  | H
D3550 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 09 Plans - R3 | Design Completion | 0 |  |  | H
D2080 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 08 Plans - R3 | Design Completion | 0 |  |  | H
D3490 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 07 Plans - R2 | Design Completion | 0 |  |  | H
D3090 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 06 Plans - R2 | Design Completion | 0 |  |  | H
D3430 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 05 Plans - R1 | Design Completion | 0 |  |  | H
D3370 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 04 Plans - R1 | Design Completion | 0 |  |  | H
D2850 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 03 Plans - R1 | Design Completion | 0 |  |  | H
D3310 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat1 Brg 01 Plans - R1 | Design Completion | 0 |  |  | H
D5000 | D5060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | 0 |  |  | H
D4570 | D5000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Issue - RFC MSE Wall RW 7-2 Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | 0 |  |  | H
D4460 | D4520 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4400 | D4460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4930 | D4400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D2850 | D3320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Issue - RFC Cat1 Brg 03 Plans - R1 | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D3430 | D2800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Issue - RFC Cat1 Brg 05 Plans - R1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2800 | D4040 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4040 | D4100 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4160 | D4220 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D3320 | D4160 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D3670 | D3560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Issue - RFC Cat1 Brg 11 Plans - R3 | Develop and Submit - 90% Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3550 | D3620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Issue - RFC Cat1 Brg 09 Plans - R3 | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3370 | D3040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Issue - RFC Cat1 Brg 04 Plans - R1 | Develop and Submit - 90% Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3550 | D1220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Issue - RFC Cat1 Brg 09 Plans - R3 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D3370 | D3440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Issue - RFC Cat1 Brg 04 Plans - R1 | Develop and Submit - 90% Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D1230 | D2930 | FF | In Progress | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | Issue - RFC Cat2 Brg 02 Plans - R1 | 0 |  |  | H
A30570 | A31610 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | FRPS Approach Slab 1 - Brg 100139 - R3 - P3 | Cut/Fill to Grade - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A36430 | A31990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | FRP Footing - Brg 100139 - Pier 5 - R3 - P3 | Cure/Strip Footing - Brg 100139 - Pier 5 - R3 - P3 | 0 | ST-FOOT |  | H
A31930 | A36430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | Install Drilled Shaft - Brg 100139 - Pier 5 - R3 - P3 | FRP Footing - Brg 100139 - Pier 5 - R3 - P3 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A36420 | A31860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | Cure/Strip Footing - Brg 100139 - Pier 4 - R3 - P3 | FRP Column - Brg 100139 - Pier 4 - R3 - P3 | 0 |  | ST-COL | H
A36410 | A36420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | FRP Footing - Brg 100139 - Pier 4 - R3 - P3 | Cure/Strip Footing - Brg 100139 - Pier 4 - R3 - P3 | 0 | ST-FOOT |  | H
A31850 | A36410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | Install Drilled Shaft - Brg 100139 - Pier 4 - R3 - P3 | FRP Footing - Brg 100139 - Pier 4 - R3 - P3 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A36400 | A31830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | FRP Footing - Brg 100139 - Pier 3 - R3 - P3 | Cure/Strip Footing - Brg 100139 - Pier 3 - R3 - P3 | 0 | ST-FOOT |  | H
A31770 | A36400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P3 | FRP Footing - Brg 100139 - Pier 3 - R3 - P3 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A36390 | A31750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | FRP Footing - Brg 100139 - Pier 2 - R3 - P3 | Cure/Strip Footing - Brg 100139 - Pier 2 - R3 - P3 | 0 | ST-FOOT |  | H
A31690 | A36390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | Install Drilled Shaft - Brg 100139 - Pier 2 - R3 - P3 | FRP Footing - Brg 100139 - Pier 2 - R3 - P3 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A36380 | A31670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | FRP Footing - Brg 100139 - Pier 1 - R3 - P3 | Cure/Strip Footing - Brg 100139 - Pier 1 - R3 - P3 | 0 | ST-FOOT |  | H
A30430 | A36380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P3 | FRP Footing - Brg 100139 - Pier 1 - R3 - P3 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A36370 | A34090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | FRP Footing - Brg 100143 - Pier 2 - R3 - P3 | Cure/Strip Footing - Brg 100143 - Pier 2 - R3 - P3 | 0 | ST-FOOT |  | H
A33830 | A36360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | Grading - Brg 100143 - Pier 2 - R3 - P3 | Drive Pile - Brg 100143 - Pier 2 - R3 - P3 | 0 | EW- ALL EW | ST-PILE | H
A36360 | A36370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | Drive Pile - Brg 100143 - Pier 2 - R3 - P3 | FRP Footing - Brg 100143 - Pier 2 - R3 - P3 | 0 | ST-PILE | ST-FOOT | H
A33440 | A36340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | Grading - Brg 100143 - Pier 1 - R3 - P3 | Drive Pile - Brg 100143 - Pier 1 - R3 - P3 | 0 | EW- ALL EW | ST-PILE | H
A36350 | A34060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | FRP Footing - Brg 100143 - Pier 1 - R3 - P3 | Cure/Strip Footing - Brg 100143 - Pier 1 - R3 - P3 | 0 | ST-FOOT |  | H
A36340 | A36350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | Drive Pile - Brg 100143 - Pier 1 - R3 - P3 | FRP Footing - Brg 100143 - Pier 1 - R3 - P3 | 0 | ST-PILE | ST-FOOT | H
A36330 | A33980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Drive Pile - Brg 100143 - End Bent 2 - R3 - P3 | FRP Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | 0 | ST-PILE | ST-ABUT | H
A34040 | A36330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Demo Abut - Brg 100143 - End Bent 2 - R3 - P3 | Drive Pile - Brg 100143 - End Bent 2 - R3 - P3 | 0 | DM-BRIDGE | ST-PILE | H
A36320 | A33910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Drive Pile - Brg 100143 - End Bent 1 - R3 - P3 | FRP Abt Cap - Brg 100143 - End Bent 1 - R3 - P3 | 0 | ST-PILE | ST-ABUT | H
A34030 | A36320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Demo Abut - Brg 100143 - End Bent 1 - R3 - P3 | Drive Pile - Brg 100143 - End Bent 1 - R3 - P3 | 0 | DM-BRIDGE | ST-PILE | H
A36310 | A30320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | FRP Footing - Brg 100141 - Pier 1 - R3 - P2.S2 | Cure/Strip Footing - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A28580 | A36310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Drive Pile - Brg 100141 - Pier 1 - R3 - P2.S2 | FRP Footing - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | ST-PILE | ST-FOOT | H
A36300 | A29530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | FRP Footing - Brg 100139 - Pier 3 - R3 - P2.S2 | Cure/Strip Footing - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A29470 | A36300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A36290 | A29370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | FRP Footing - Brg 100139 - Pier 1 - R3 - P2.S2 | Cure/Strip Footing - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A27910 | A36290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A25230 | A26058 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Grading - Brg 100869 - End Bent 1 - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | 0 | EW- ALL EW | EW-SML | H
A26380 | A27030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | Install DRG S-156 to S-160 - Ramp B Sta 624 to 629 - R3 - P0 | 0 | SUB-TC-PCB | PIPE | H
A26380 | A27010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | Install DRG S-136C to S-133 to S-132 - Pond SMF 3A /Ramp B - R3 - P0 | 0 | SUB-TC-PCB | PIPE | H
A26380 | A27000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | Install DRG S-123 to S-122/ S-139 to S-137 - Pond SMF 3A - R3 - P0 | 0 | SUB-TC-PCB | PIPE | H
A26380 | A26990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | Install DRG CS-3A to S-117A / S-120 - Pond SMF 3A - R3 - P0 | 0 | SUB-TC-PCB | PIPE | H
A24230 | A27020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.5 R3 - Ph1, Stg1, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Open Traffic to Temp Ramp F Close Exist Ramp F - R3 - P1.S1 | Install DRG OUT-3 to S-149 to S-153 - Ramp F Sta 504 to 508 - R3 - P0 | 0 | TC-Maint. | PIPE | H
A24230 | A26990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.5 R3 - Ph1, Stg1, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | Open Traffic to Temp Ramp F Close Exist Ramp F - R3 - P1.S1 | Install DRG CS-3A to S-117A / S-120 - Pond SMF 3A - R3 - P0 | 0 | TC-Maint. | PIPE | H
A22845 | A22880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 2 | Place Stabilization - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-MSE | EW-STAB | H
A22845 | A23980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 2 | Place 3-Pour Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-MSE | SUB-BR-SLIP | H
A22870 | A22845 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 2 | 0 | EW-SML | ST-MSE | H
A22270 | A16380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-101 to S-105 - I-4 Sta 310 to 314 - R2 - P1 | 0 | TC-Maint. | PIPE | H
A22270 | A16430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-104 to S-113/S-112 - Ramp EN Sta 97 to 103 - R2 - P1 | 0 | TC-Maint. | PIPE | H
A22270 | A16440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-113 to O-101 - Ramp EN Sta 90 to 99 - R2 - P1 | 0 | TC-Maint. | PIPE | H
A22270 | A16450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-118 to S-123 - Pond SMF 4A - R2 - P1 | 0 | TC-Maint. | PIPE | H
A22270 | A16460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-126 to S-134 - Pond SMF 4A to Taliaferro Sta 21 - R2 - P1 | 0 | TC-Maint. | PIPE | H
A22270 | A16470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-136 to S-146 - Taliaferro Ave - R2 - P1 | 0 | TC-Maint. | PIPE | H
A22270 | A16480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Install DRG S-147 to S-151 - I-275 Sta 715 to 717 - R2 - P1 | 0 | TC-Maint. | PIPE | H
A1130 | A15440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
A1130 | A15420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
A1130 | A15010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
A1150 | A15430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp NE - R1 - P1.S1 | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
D1500 | D1380 | FF | In Progress | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.2 Right of Way | I-275 - I-4 - IBL(all) - B1.3.2 Right of Way | Owner Right of Way Acquisition | Owner Right Of Way Acquisition Complete / Clear Date (7/1/24) | 0 |  |  | H
Admin-1080 | D1500 | FS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.2 Right of Way | Anticipated Contract Execution Date | Owner Right of Way Acquisition | 0 |  |  | H
P1320 | P1380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | Review and Approve - Girder Shop Drawings - Brg 2 - Cat 2 | Procure Girders - Brg 2 - Cat 2 - Steel | 0 |  |  | H
PC1110 | A21450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.3 R1 Procurement - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Fab & Deliver - RW 1-1 - Ramp NE / Br 1 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 |  | ST-MSE | H
PC1070 | A18010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.10 R1 Procurement - Retaining Wall RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Fab & Deliver - RW 4-1 Br 4 | Const MSE Wall & Bkfill - RW 4-1 / Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 |  | ST-MSE | H
PC1080 | A18090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.11 R1 Procurement - Retaining Wall RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Fab & Deliver - RW 4-2 Br 4 | Const MSE Wall & Bkfill - RW 4-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 |  | ST-MSE | H
PC1180 | A25600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.3 R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 |  | ST-MSE | H
PC1180 | A26240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.3 R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 1 | 0 |  | ST-MSE | H
PC1190 | A26133 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.5 R3 Procurement - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Fab & Deliver - RW 9-3 - Ramp B/F / Br 9 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 2 | 0 |  | ST-MSE | H
PC1210 | A34270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.7 R3 Procurement - Retaining Wall RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Fab & Deliver - RW 102 Ramp C | Const MSE Wall & Bkfill - RW 102 - Ramp C Sta 708 to 715 - R3 - P3 | 0 |  | ST-MSE | H
PC1220 | A16530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.8 R2 Procurement - Retaining Wall RW 103 Ramp EN | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Fab & Deliver - RW 103 Ramp EN | Const MSE Wall & Bkfill - RW 103 - I-4 Sta 311 to 320 - R2 - P1 | 0 |  | ST-MSE | H
PC1230 | A36270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.9 R2 Procurement - Retaining Wall RW 104 Ramp EN | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Fab & Deliver - RW 104 Ramp EN | Const MSE Wall & Bkfill - RW 104 - Ramp EN Sta 68 to 72 - R2 - P1 | 0 |  | ST-MSE | H
PC1010 | A35480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.2 R1 Procurement - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Fab & Deliver - RW 2-1 - Br 2 | Const MSE Wall & Bkfill - RW 2-1 / Brg 2 - End Bent 1 - R1 - P2.S1 | 0 |  | ST-MSE | H
PC1200 | A15970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.6 R1 Procurement - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Fab & Deliver - RW 100 I-4 EB (Br 3 & Br 4) | Const MSE Wall & Bkfill - RW-100 - Left 13th Ave Sta 13 to 16 - R1 - P1.S1 | 0 |  | ST-MSE | H
PC1090 | A14950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.12 R1 Procurement - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Fab & Deliver - RW 5-1 Ramp WE-B / Br 5 | Const MSE Wall & Bkfill - RW 5-1 - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 |  | ST-MSE | H
PC1100 | A15080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.13 R1 Procurement - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Fab & Deliver - RW 5-2 Ramp WE-B / Br 5 | Const MSE Wall & Bkfill - RW 5-2 / Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 |  | ST-MSE | H
D2930 | A35490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Issue - RFC Cat2 Brg 02 Plans - R1 | Temp Wall or SOE - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 |  | EW-STR | H
PC1140 | A22960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.3 R2 Procurement - Retaining Wall RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Fab & Deliver - RW 6-1 Ramp EN / Br 6 | Const MSE Wall & Bkfill - RW 6-1 / Brg 6 100650 - End Bent 2- R2 - P1 | 0 |  | ST-MSE | H
PC1120 | A23670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.1 R2 Procurement - Retaining Wall RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Fab & Deliver - RW 7-1 Ramp EN / Br 7 | Const MSE Wall & Bkfill - RW 7-1 / Brg 100652 - End Bent 2 - R2 - P1 | 0 |  | ST-MSE | H
PC1130 | A23350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.2 R2 Procurement - Retaining Wall RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Fab & Deliver - RW 7-2 Ramp EN / Br 7 | Const MSE Wall & Bkfill - RW 7-2 / Brg 100652 - End Bent 1 - R2 - P1 | 0 |  | ST-MSE | H
PC1150 | A24520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.4 R3 Procurement - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Fab & Deliver - RW 8-1 - Ramp B / Br 8 | Const MSE Wall & Bkfill - RW 8-1 / Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 |  | ST-MSE | H
PC1160 | A24910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.1 R3 Procurement - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Fab & Deliver - RW 8-2 - Ramp B / Br 8 | Const MSE Wall & Bkfill - RW 8-2 / Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 |  | ST-MSE | H
PC1170 | A25280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.2 R3 Procurement - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Fab & Deliver - RW 9-1 - Ramp B/F / Br 8 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 |  | ST-MSE | H
PC1020 | A21015 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.4 R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 1 | 0 |  | ST-MSE | H
PC1020 | A21018 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.4 R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 2 | 0 |  | ST-MSE | H
PC1030 | A21995 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.5 R1 Procurement - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Fab & Deliver - RW 2-3 - Ramp NE 125 to 130 RT | Const MSE Wall & Bkfill - RW 2-3 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 |  | ST-MSE | H
PC1040 | A35550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.7 R1 Procurement - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Fab & Deliver - RW 2-4 Br 2 | Const MSE Wall & Bkfill - RW 2-4 / Brg 2 - End Bent 2 - R1 - P2.S1 | 0 |  | ST-MSE | H
PC1050 | A17300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.8 R1 Procurement - Retaining Wall RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Fab & Deliver - RW 3-1 Br 3 | Const MSE Wall & Bkfill - RW 3-1 / Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 |  | ST-MSE | H
PC1060 | A17390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.9 R1 Procurement - Retaining Wall RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Fab & Deliver - RW 3-2 Br 3 | Const MSE Wall & Bkfill - RW 3-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 |  | ST-MSE | H
D3670 | A29160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.4.12.7 R3 - Ph2, Stg2 - Bridge 100141 - Demo | Issue - RFC Cat1 Brg 11 Plans - R3 | Demo Barrier - Brg 100141 - R3 - P2.S2 | 0 |  | DM-BRIDGE | H
D2370 | A28410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Issue - RFC Cat2 Brg 10 Plans - R3 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 |  | EW-STR | H
D3550 | A25290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Issue - RFC Cat1 Brg 09 Plans - R3 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 |  | EW-STR | H
D2080 | A24530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Issue - RFC Cat1 Brg 08 Plans - R3 | Temp Wall or SOE - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 |  | EW-STR | H
D3490 | A23360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Issue - RFC Cat1 Brg 07 Plans - R2 | Temp Wall or SOE - Brg 100652 - End Bent 1 - R2 - P1 | 0 |  | EW-STR | H
D3490 | A26710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.7 R2 - Ph1 - Bridge 100652 Ramp EN - Demo | Issue - RFC Cat1 Brg 07 Plans - R2 | Demo Barrier - Brg 100652 - R2 - P1 | 0 |  | DM-BRIDGE | H
D3090 | A22980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Issue - RFC Cat1 Brg 06 Plans - R2 | Excavate - Brg 100650 - Pier 2 - R2 - P1 | 0 |  | EW-STR | H
D3430 | A15120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Issue - RFC Cat1 Brg 05 Plans - R1 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | EW-STR | H
D3430 | A14700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Issue - RFC Cat1 Brg 05 Plans - R1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | EW-STR | H
D3370 | A17510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Issue - RFC Cat1 Brg 04 Plans - R1 | Excavate - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 |  | EW-STR | H
D2850 | A16680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Issue - RFC Cat1 Brg 03 Plans - R1 | Excavate - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 |  | EW-STR | H
SD2290 | PC1230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.3.5.2.9 R2 Procurement - Retaining Wall RW 104 Ramp EN | FDOT - Review & Comment Shp Drwgs - RW 104 Ramp EN | Fab & Deliver - RW 104 Ramp EN | 0 |  |  | H
SD2240 | PC1220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.3.5.2.8 R2 Procurement - Retaining Wall RW 103 Ramp EN | FDOT - Review & Comment Shp Drwgs - RW 103 Ramp EN | Fab & Deliver - RW 103 Ramp EN | 0 |  |  | H
SD2340 | PC1210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.4.3.6.3.7 R3 Procurement - Retaining Wall RW 102 Ramp C | FDOT - Review & Comment Shp Drwgs - RW 102 Ramp C | Fab & Deliver - RW 102 Ramp C | 0 |  |  | H
SD2040 | PC1200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.4.3.4.1.6 R1 Procurement - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | FDOT - Review & Comment Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Fab & Deliver - RW 100 I-4 EB (Br 3 & Br 4) | 0 |  |  | H
SD1990 | PC1190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.5 R3 Procurement - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-3 - Ramp B/F / Br 9 | 0 |  |  | H
SD1940 | PC1180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.3 R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | 0 |  |  | H
SD1890 | PC1170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.2 R3 Procurement - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Fab & Deliver - RW 9-1 - Ramp B/F / Br 8 | 0 |  |  | H
SD1840 | PC1160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.1 R3 Procurement - Retaining Wall RW 8-2 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Fab & Deliver - RW 8-2 - Ramp B / Br 8 | 0 |  |  | H
SD1790 | PC1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.3.6.3.4 R3 Procurement - Retaining Wall RW 8-1 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Fab & Deliver - RW 8-1 - Ramp B / Br 8 | 0 |  |  | H
D5110 | SD2250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Issue - RFC MSE Wall RW 104 Ramp EN | Develop & Submit Shp Drwgs - RW 104 Ramp EN | 0 |  |  | H
D5050 | SD2200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Issue - RFC MSE Wall RW 103 Ramp EN | Develop & Submit Shp Drwgs - RW 103 Ramp EN | 0 |  |  | H
D4990 | SD2300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Issue - RFC MSE Wall RW 102 Ramp C | Develop & Submit Shp Drwgs - RW 102 Ramp C | 0 |  |  | H
D4930 | SD2000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop & Submit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0 |  |  | H
D4870 | SD1950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0 |  |  | H
D4810 | SD1900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0 |  |  | H
D4750 | SD1850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0 |  |  | H
D4690 | SD1800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0 |  |  | H
D4630 | SD1750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0 |  |  | H
D4570 | SD1700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Issue - RFC MSE Wall RW 7-2 Ramp EN / Br 7 | Develop & Submit Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4510 | SD1650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Issue - RFC MSE Wall RW 7-1 Ramp EN / Br 7 | Develop & Submit Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4450 | SD1600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Issue - RFC MSE Wall RW 6-1 Ramp EN / Br 6 | Develop & Submit Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
SD1640 | PC1140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.3 R2 Procurement - Retaining Wall RW 6-1 - Ramp EN / Br 6 | FDOT - Review & Comment Shp Drwgs - RW 6-1 Ramp EN / Br 6 | Fab & Deliver - RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
SD1690 | PC1120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.1 R2 Procurement - Retaining Wall RW 7-1 - Ramp EN / Br 7 | FDOT - Review & Comment Shp Drwgs - RW 7-1 Ramp EN / Br 7 | Fab & Deliver - RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
SD1740 | PC1130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.3.5.2.2 R2 Procurement - Retaining Wall RW 7-2 - Ramp EN / Br 7 | FDOT - Review & Comment Shp Drwgs - RW 7-2 Ramp EN / Br 7 | Fab & Deliver - RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
SD2330 | SD2340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Design 2nd Review & Comnt Shp Drwgs - RW 102 Ramp C | FDOT - Review & Comment Shp Drwgs - RW 102 Ramp C | 0 |  |  | H
SD2320 | SD2330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Revise & Resubmit Shp Drwgs - RW 102 Ramp C | Design 2nd Review & Comnt Shp Drwgs - RW 102 Ramp C | 0 |  |  | H
SD2310 | SD2320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Designer Review & Comnt Shp Drwgs - RW 102 Ramp C | Revise & Resubmit Shp Drwgs - RW 102 Ramp C | 0 |  |  | H
SD2300 | SD2310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Develop & Submit Shp Drwgs - RW 102 Ramp C | Designer Review & Comnt Shp Drwgs - RW 102 Ramp C | 0 |  |  | H
SD2280 | SD2290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Design 2nd Review & Comnt Shp Drwgs - RW 104 Ramp EN | FDOT - Review & Comment Shp Drwgs - RW 104 Ramp EN | 0 |  |  | H
SD2270 | SD2280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Revise & Resubmit Shp Drwgs - RW 104 Ramp EN | Design 2nd Review & Comnt Shp Drwgs - RW 104 Ramp EN | 0 |  |  | H
SD2260 | SD2270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Designer Review & Comnt Shp Drwgs - RW 104 Ramp EN | Revise & Resubmit Shp Drwgs - RW 104 Ramp EN | 0 |  |  | H
SD2250 | SD2260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.9 R2 Shp Drwgs - Retaining Wall RW 104 Ramp EN | Develop & Submit Shp Drwgs - RW 104 Ramp EN | Designer Review & Comnt Shp Drwgs - RW 104 Ramp EN | 0 |  |  | H
SD2230 | SD2240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Design 2nd Review & Comnt Shp Drwgs - RW 103 Ramp EN | FDOT - Review & Comment Shp Drwgs - RW 103 Ramp EN | 0 |  |  | H
SD2220 | SD2230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Revise & Resubmit Shp Drwgs - RW 103 Ramp EN | Design 2nd Review & Comnt Shp Drwgs - RW 103 Ramp EN | 0 |  |  | H
SD2210 | SD2220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Designer Review & Comnt Shp Drwgs - RW 103 Ramp EN | Revise & Resubmit Shp Drwgs - RW 103 Ramp EN | 0 |  |  | H
SD2200 | SD2210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | I-275 - I-4 - IBL(all) - B1.4.4.7.3.8 R2 Shp Drwgs - Retaining Wall RW 103 Ramp EN | Develop & Submit Shp Drwgs - RW 103 Ramp EN | Designer Review & Comnt Shp Drwgs - RW 103 Ramp EN | 0 |  |  | H
SD2030 | SD2040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Design 2nd Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | FDOT - Review & Comment Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0 |  |  | H
SD2020 | SD2030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Revise & Resubmit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Design 2nd Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0 |  |  | H
SD2010 | SD2020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Designer Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Revise & Resubmit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0 |  |  | H
SD2000 | SD2010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Develop & Submit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Designer Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0 |  |  | H
SD1980 | SD1990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0 |  |  | H
SD1970 | SD1980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0 |  |  | H
SD1960 | SD1970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0 |  |  | H
SD1950 | SD1960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0 |  |  | H
SD1930 | SD1940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0 |  |  | H
SD1920 | SD1930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0 |  |  | H
SD1910 | SD1920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0 |  |  | H
SD1900 | SD1910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0 |  |  | H
SD1880 | SD1890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0 |  |  | H
SD1870 | SD1880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Revise & Resubmit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0 |  |  | H
SD1860 | SD1870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Designer Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Revise & Resubmit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0 |  |  | H
SD1850 | SD1860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Develop & Submit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Designer Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0 |  |  | H
SD1830 | SD1840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0 |  |  | H
SD1820 | SD1830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0 |  |  | H
SD1810 | SD1820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0 |  |  | H
SD1800 | SD1810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0 |  |  | H
SD1780 | SD1790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0 |  |  | H
SD1770 | SD1780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0 |  |  | H
SD1760 | SD1770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0 |  |  | H
SD1750 | SD1760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0 |  |  | H
SD1730 | SD1740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Design 2nd Review & Comnt Shp Drwgs - RW 7-2 Ramp EN / Br 7 | FDOT - Review & Comment Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
SD1720 | SD1730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Revise & Resubmit Shp Drwgs - RW 7-2 Ramp EN / Br 7 | Design 2nd Review & Comnt Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
SD1710 | SD1720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Designer Review & Comnt Shp Drwgs - RW 7-2 Ramp EN / Br 7 | Revise & Resubmit Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
SD1700 | SD1710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.3 R2 Shp Drwgs - Retaining Wall RW 7-2 - Ramp EN / Br 7 | Develop & Submit Shp Drwgs - RW 7-2 Ramp EN / Br 7 | Designer Review & Comnt Shp Drwgs - RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
SD1680 | SD1690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Design 2nd Review & Comnt Shp Drwgs - RW 7-1 Ramp EN / Br 7 | FDOT - Review & Comment Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
SD1670 | SD1680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Revise & Resubmit Shp Drwgs - RW 7-1 Ramp EN / Br 7 | Design 2nd Review & Comnt Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
SD1660 | SD1670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Designer Review & Comnt Shp Drwgs - RW 7-1 Ramp EN / Br 7 | Revise & Resubmit Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
SD1650 | SD1660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.2 R2 Shp Drwgs - Retaining Wall RW 7-1 - Ramp EN / Br 7 | Develop & Submit Shp Drwgs - RW 7-1 Ramp EN / Br 7 | Designer Review & Comnt Shp Drwgs - RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
SD1630 | SD1640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Design 2nd Review & Comnt Shp Drwgs - RW 6-1 Ramp EN / Br 6 | FDOT - Review & Comment Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
SD1620 | SD1630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Revise & Resubmit Shp Drwgs - RW 6-1 Ramp EN / Br 6 | Design 2nd Review & Comnt Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
SD1610 | SD1620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Designer Review & Comnt Shp Drwgs - RW 6-1 Ramp EN / Br 6 | Revise & Resubmit Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
SD1600 | SD1610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.4.4.7.3.1 R2 Shp Drwgs - Retaining Wall RW 6-1 - Ramp EN / Br 6 | Develop & Submit Shp Drwgs - RW 6-1 Ramp EN / Br 6 | Designer Review & Comnt Shp Drwgs - RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D2740 | D5060 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | 0 |  |  | H
D2740 | D5000 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | 0 |  |  | H
D2740 | D4940 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0 |  |  | H
D2740 | D4880 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D2740 | D4820 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D2740 | D4760 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D2740 | D4700 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D2740 | D4640 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D2740 | D4580 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D2740 | D5060 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | 0 |  |  | H
D2740 | D5000 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | 0 |  |  | H
D2740 | D4940 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0 |  |  | H
D2740 | D4880 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D2740 | D4820 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D2740 | D4760 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D2740 | D4700 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D2740 | D4640 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D2740 | D4580 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D2680 | D4520 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D2680 | D4520 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D2680 | D4460 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D2680 | D4460 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D2680 | D4400 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D2680 | D4400 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D1200 | D4340 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D1200 | D4280 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D1200 | D4220 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D1200 | D4160 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D1200 | D4100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D1200 | D4040 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D1200 | D3980 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D1200 | D3860 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D1200 | D3800 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D1200 | D3740 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D1200 | D3680 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
SD1040 | PC1110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.3 R1 Procurement - Retaining Wall RW 1-1 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Fab & Deliver - RW 1-1 - Ramp NE / Br 1 | 0 |  |  | H
D4390 | SD1550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4330 | SD1500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4270 | SD1450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Issue - RFC MSE Wall RW 4-2 Br 4 | Develop & Submit Shp Drwgs - RW 4-2 Br 4 | 0 |  |  | H
D4210 | SD1400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Issue - RFC MSE Wall RW 4-1 Br 4 | Develop & Submit Shp Drwgs - RW 4-1 Br 4 | 0 |  |  | H
D4150 | SD1350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Issue - RFC MSE Wall RW 3-2 Br 3 | Develop & Submit Shp Drwgs - RW 3-2 Br 3 | 0 |  |  | H
D4090 | SD1300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Issue - RFC MSE Wall RW 3-1 Br 3 | Develop & Submit Shp Drwgs - RW 3-1 Br 3 | 0 |  |  | H
D4030 | SD1250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Issue - RFC MSE Wall RW 2-4 Br 2 | Develop & Submit Shp Drwgs - RW 2-4 Br 2 | 0 |  |  | H
D3910 | SD1200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Develop & Submit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3850 | SD1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Develop & Submit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3790 | SD1100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Issue - RFC MSE Wall RW 2-1 - Br 2 | Develop & Submit Shp Drwgs - RW 2-1 Br 2 | 0 |  |  | H
D3730 | SD1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0 |  |  | H
SD1590 | PC1100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.13 R1 Procurement - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Fab & Deliver - RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
SD1540 | PC1090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.12 R1 Procurement - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Fab & Deliver - RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
SD1490 | PC1080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.11 R1 Procurement - Retaining Wall RW 4-2 Br 4 | FDOT - Review & Comment Shp Drwgs - RW 4-2 Br 4 | Fab & Deliver - RW 4-2 Br 4 | 0 |  |  | H
SD1440 | PC1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.10 R1 Procurement - Retaining Wall RW 4-1 Br 4 | FDOT - Review & Comment Shp Drwgs - RW 4-1 Br 4 | Fab & Deliver - RW 4-1 Br 4 | 0 |  |  | H
SD1390 | PC1060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.9 R1 Procurement - Retaining Wall RW 3-2 Br 3 | FDOT - Review & Comment Shp Drwgs - RW 3-2 Br 3 | Fab & Deliver - RW 3-2 Br 3 | 0 |  |  | H
SD1340 | PC1050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.8 R1 Procurement - Retaining Wall RW 3-1 Br 3 | FDOT - Review & Comment Shp Drwgs - RW 3-1 Br 3 | Fab & Deliver - RW 3-1 Br 3 | 0 |  |  | H
SD1290 | PC1040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.7 R1 Procurement - Retaining Wall RW 2-4 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-4 Br 2 | Fab & Deliver - RW 2-4 Br 2 | 0 |  |  | H
SD1240 | PC1030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.4.3.4.1.5 R1 Procurement - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | FDOT - Review & Comment Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Fab & Deliver - RW 2-3 - Ramp NE 125 to 130 RT | 0 |  |  | H
SD1190 | PC1020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.4.3.4.1.4 R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | FDOT - Review & Comment Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | 0 |  |  | H
SD1140 | PC1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.2 R1 Procurement - Retaining Wall RW 2-1 - Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-1 Br 2 | Fab & Deliver - RW 2-1 - Br 2 | 0 |  |  | H
SD1090 | PC1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D2310 | SD1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-1 | Develop & Submit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0 |  |  | H
PC1000 | A20450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 |  | ST-MSE | H
PC1000 | A21450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 |  | ST-MSE | H
PC1000 | A21010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 |  | ST-MSE | H
PC1000 | A21990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 |  | ST-MSE | H
SD1580 | SD1590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
SD1570 | SD1580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
SD1560 | SD1570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
SD1550 | SD1560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
SD1530 | SD1540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
SD1520 | SD1530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
SD1510 | SD1520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
SD1500 | SD1510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
SD1480 | SD1490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Design 2nd Review & Comnt Shp Drwgs - RW 4-2 Br 4 | FDOT - Review & Comment Shp Drwgs - RW 4-2 Br 4 | 0 |  |  | H
SD1470 | SD1480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Revise & Resubmit Shp Drwgs - RW 4-2 Br 4 | Design 2nd Review & Comnt Shp Drwgs - RW 4-2 Br 4 | 0 |  |  | H
SD1460 | SD1470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Designer Review & Comnt Shp Drwgs - RW 4-2 Br 4 | Revise & Resubmit Shp Drwgs - RW 4-2 Br 4 | 0 |  |  | H
SD1450 | SD1460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.11 R1 Shp Drwgs - Retaining Wall RW 4-2 Br 4 | Develop & Submit Shp Drwgs - RW 4-2 Br 4 | Designer Review & Comnt Shp Drwgs - RW 4-2 Br 4 | 0 |  |  | H
SD1430 | SD1440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Design 2nd Review & Comnt Shp Drwgs - RW 4-1 Br 4 | FDOT - Review & Comment Shp Drwgs - RW 4-1 Br 4 | 0 |  |  | H
SD1420 | SD1430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Revise & Resubmit Shp Drwgs - RW 4-1 Br 4 | Design 2nd Review & Comnt Shp Drwgs - RW 4-1 Br 4 | 0 |  |  | H
SD1410 | SD1420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Designer Review & Comnt Shp Drwgs - RW 4-1 Br 4 | Revise & Resubmit Shp Drwgs - RW 4-1 Br 4 | 0 |  |  | H
SD1400 | SD1410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.10 R1 Shp Drwgs - Retaining Wall RW 4-1 Br 4 | Develop & Submit Shp Drwgs - RW 4-1 Br 4 | Designer Review & Comnt Shp Drwgs - RW 4-1 Br 4 | 0 |  |  | H
SD1380 | SD1390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Design 2nd Review & Comnt Shp Drwgs - RW 3-2 Br 3 | FDOT - Review & Comment Shp Drwgs - RW 3-2 Br 3 | 0 |  |  | H
SD1370 | SD1380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Revise & Resubmit Shp Drwgs - RW 3-2 Br 3 | Design 2nd Review & Comnt Shp Drwgs - RW 3-2 Br 3 | 0 |  |  | H
SD1360 | SD1370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Designer Review & Comnt Shp Drwgs - RW 3-2 Br 3 | Revise & Resubmit Shp Drwgs - RW 3-2 Br 3 | 0 |  |  | H
SD1350 | SD1360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.9 R1 Shp Drwgs - Retaining Wall RW 3-2 Br 3 | Develop & Submit Shp Drwgs - RW 3-2 Br 3 | Designer Review & Comnt Shp Drwgs - RW 3-2 Br 3 | 0 |  |  | H
SD1330 | SD1340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Design 2nd Review & Comnt Shp Drwgs - RW 3-1 Br 3 | FDOT - Review & Comment Shp Drwgs - RW 3-1 Br 3 | 0 |  |  | H
SD1320 | SD1330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Revise & Resubmit Shp Drwgs - RW 3-1 Br 3 | Design 2nd Review & Comnt Shp Drwgs - RW 3-1 Br 3 | 0 |  |  | H
SD1310 | SD1320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Designer Review & Comnt Shp Drwgs - RW 3-1 Br 3 | Revise & Resubmit Shp Drwgs - RW 3-1 Br 3 | 0 |  |  | H
SD1300 | SD1310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.8 R1 Shp Drwgs - Retaining Wall RW 3-1 Br 3 | Develop & Submit Shp Drwgs - RW 3-1 Br 3 | Designer Review & Comnt Shp Drwgs - RW 3-1 Br 3 | 0 |  |  | H
SD1280 | SD1290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-4 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-4 Br 2 | 0 |  |  | H
SD1270 | SD1280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-4 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-4 Br 2 | 0 |  |  | H
SD1260 | SD1270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-4 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-4 Br 2 | 0 |  |  | H
SD1250 | SD1260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Develop & Submit Shp Drwgs - RW 2-4 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-4 Br 2 | 0 |  |  | H
SD1230 | SD1240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Design 2nd Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | FDOT - Review & Comment Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
SD1220 | SD1230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Revise & Resubmit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Design 2nd Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
SD1210 | SD1220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Designer Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Revise & Resubmit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
SD1200 | SD1210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Develop & Submit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Designer Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
SD1180 | SD1190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Design 2nd Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | FDOT - Review & Comment Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
SD1170 | SD1180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Revise & Resubmit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Design 2nd Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
SD1160 | SD1170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Designer Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Revise & Resubmit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
SD1150 | SD1160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Develop & Submit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Designer Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
SD1130 | SD1140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-1 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-1 Br 2 | 0 |  |  | H
SD1120 | SD1130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Revise & Resubmit Shp Drwgs - RW 2-1 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-1 Br 2 | 0 |  |  | H
SD1110 | SD1120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-1 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-1 Br 2 | 0 |  |  | H
SD1100 | SD1110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Develop & Submit Shp Drwgs - RW 2-1 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-1 Br 2 | 0 |  |  | H
SD1080 | SD1090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0 |  |  | H
SD1070 | SD1080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0 |  |  | H
SD1060 | SD1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0 |  |  | H
SD1050 | SD1060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0 |  |  | H
SD1030 | SD1040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0 |  |  | H
SD1020 | SD1030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0 |  |  | H
SD1010 | SD1020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0 |  |  | H
SD1000 | SD1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0 |  |  | H
Admin-1045 | D5060 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Begin Design | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | 0 |  |  | H
Admin-1045 | D5000 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Begin Design | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | 0 |  |  | H
Admin-1045 | D4940 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Begin Design | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0 |  |  | H
Admin-1045 | D4880 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Begin Design | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
Admin-1045 | D4820 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Begin Design | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
Admin-1045 | D4760 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Begin Design | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
Admin-1045 | D4700 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Begin Design | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
Admin-1045 | D4640 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Begin Design | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
Admin-1045 | D4580 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Begin Design | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
Admin-1045 | D4520 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Begin Design | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
Admin-1045 | D4460 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Begin Design | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
Admin-1045 | D4400 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Begin Design | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D1200 | D4340 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
Admin-1045 | D4340 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Begin Design | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D1200 | D4280 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
Admin-1045 | D4280 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Begin Design | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D1200 | D4220 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | 0 |  |  | H
Admin-1045 | D4220 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Begin Design | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D1200 | D4160 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | 0 |  |  | H
Admin-1045 | D4160 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Begin Design | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D1200 | D4100 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
Admin-1045 | D4100 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Begin Design | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D1200 | D4040 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
Admin-1045 | D4040 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Begin Design | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D1200 | D3980 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0 |  |  | H
Admin-1045 | D3980 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Begin Design | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D1200 | D3860 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
Admin-1045 | D3860 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Begin Design | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D1200 | D3800 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
Admin-1045 | D3800 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Begin Design | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D1200 | D3740 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
Admin-1045 | D3740 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Begin Design | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D1200 | D3680 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
Admin-1045 | D3680 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Begin Design | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D5090 | D5100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Review and Approve - Final MSE Wall RW 104 Ramp EN | Develop and Submit - Sign & Seal MSE Wall RW 104 Ramp EN | 0 |  |  | H
D5070 | D5080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Review and Approve - 90% MSE Wall RW 104 Ramp EN | Develop and Submit - Final MSE Wall RW 104 Ramp EN | 0 |  |  | H
D5060 | D5070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | Review and Approve - 90% MSE Wall RW 104 Ramp EN | 0 |  |  | H
D5080 | D5090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - Final MSE Wall RW 104 Ramp EN | Review and Approve - Final MSE Wall RW 104 Ramp EN | 0 |  |  | H
D5100 | D5110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 104 Ramp EN | Issue - RFC MSE Wall RW 104 Ramp EN | 0 |  |  | H
D5030 | D5040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Review and Approve - Final MSE Wall RW 103 Ramp EN | Develop and Submit - Sign & Seal MSE Wall RW 103 Ramp EN | 0 |  |  | H
D5010 | D5020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Review and Approve - 90% MSE Wall RW 103 Ramp EN | Develop and Submit - Final MSE Wall RW 103 Ramp EN | 0 |  |  | H
D5000 | D5010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | Review and Approve - 90% MSE Wall RW 103 Ramp EN | 0 |  |  | H
D5020 | D5030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - Final MSE Wall RW 103 Ramp EN | Review and Approve - Final MSE Wall RW 103 Ramp EN | 0 |  |  | H
D5040 | D5050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 103 Ramp EN | Issue - RFC MSE Wall RW 103 Ramp EN | 0 |  |  | H
D4970 | D4980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - Final MSE Wall RW 102 Ramp C | Develop and Submit - Sign & Seal MSE Wall RW 102 Ramp C | 0 |  |  | H
D4950 | D4960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | Develop and Submit - Final MSE Wall RW 102 Ramp C | 0 |  |  | H
D4940 | D4950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% MSE Wall RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | 0 |  |  | H
D4960 | D4970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Final MSE Wall RW 102 Ramp C | Review and Approve - Final MSE Wall RW 102 Ramp C | 0 |  |  | H
D4980 | D4990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Sign & Seal MSE Wall RW 102 Ramp C | Issue - RFC MSE Wall RW 102 Ramp C | 0 |  |  | H
D4910 | D4920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop and Submit - Sign & Seal MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4890 | D4900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop and Submit - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4880 | D4890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4900 | D4910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | Review and Approve - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4920 | D4930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Sign & Seal MSE Wall RW 100 I-4 EB (Br 3 & 4) | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4850 | D4860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Review and Approve - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4830 | D4840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4820 | D4830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4840 | D4850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4860 | D4870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 9-3 Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4790 | D4800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Review and Approve - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4770 | D4780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4760 | D4770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4780 | D4790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4800 | D4810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 9-2 Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4730 | D4740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Review and Approve - Final MSE Wall RW 9-1 Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D4710 | D4720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D4700 | D4710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D4720 | D4730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Final MSE Wall RW 9-1 Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D4740 | D4750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - Sign & Seal MSE Wall RW 9-1 Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D4670 | D4680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-2 Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4650 | D4660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4640 | D4650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4660 | D4670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-2 Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4680 | D4690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-2 Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4610 | D4620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-1 Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4590 | D4600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4580 | D4590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4600 | D4610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-1 Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4620 | D4630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-1 Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4550 | D4560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Review and Approve - Final MSE Wall RW 7-2 Ramp EN / Br 7 | Develop and Submit - Sign & Seal MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4530 | D4540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | Develop and Submit - Final MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4520 | D4530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4540 | D4550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - Final MSE Wall RW 7-2 Ramp EN / Br 7 | Review and Approve - Final MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4560 | D4570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - Sign & Seal MSE Wall RW 7-2 Ramp EN / Br 7 | Issue - RFC MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D4490 | D4500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Review and Approve - Final MSE Wall RW 7-1 Ramp EN / Br 7 | Develop and Submit - Sign & Seal MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4470 | D4480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Develop and Submit - Final MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4460 | D4470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4480 | D4490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - Final MSE Wall RW 7-1 Ramp EN / Br 7 | Review and Approve - Final MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4500 | D4510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - Sign & Seal MSE Wall RW 7-1 Ramp EN / Br 7 | Issue - RFC MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4430 | D4440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Review and Approve - Final MSE Wall RW 6-1 Ramp EN / Br 6 | Develop and Submit - Sign & Seal MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4410 | D4420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4400 | D4410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4420 | D4430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | Review and Approve - Final MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4440 | D4450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - Sign & Seal MSE Wall RW 6-1 Ramp EN / Br 6 | Issue - RFC MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4370 | D4380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4350 | D4360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4340 | D4350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4360 | D4370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4380 | D4390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-2 Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4310 | D4320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4290 | D4300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4280 | D4290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4300 | D4310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4320 | D4330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-1 Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4250 | D4260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Review and Approve - Final MSE Wall RW 4-2 Br 4 | Develop and Submit - Sign & Seal MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D4230 | D4240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Review and Approve - 90% MSE Wall RW 4-2 Br 4 | Develop and Submit - Final MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D4220 | D4230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | Review and Approve - 90% MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D4240 | D4250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - Final MSE Wall RW 4-2 Br 4 | Review and Approve - Final MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D4260 | D4270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - Sign & Seal MSE Wall RW 4-2 Br 4 | Issue - RFC MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D4190 | D4200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Review and Approve - Final MSE Wall RW 4-1 Br 4 | Develop and Submit - Sign & Seal MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D4170 | D4180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Review and Approve - 90% MSE Wall RW 4-1 Br 4 | Develop and Submit - Final MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D4160 | D4170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | Review and Approve - 90% MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D4180 | D4190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - Final MSE Wall RW 4-1 Br 4 | Review and Approve - Final MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D4200 | D4210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - Sign & Seal MSE Wall RW 4-1 Br 4 | Issue - RFC MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D4130 | D4140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Review and Approve - Final MSE Wall RW 3-2 Br 3 | Develop and Submit - Sign & Seal MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4110 | D4120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4100 | D4110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4120 | D4130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | Review and Approve - Final MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4140 | D4150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - Sign & Seal MSE Wall RW 3-2 Br 3 | Issue - RFC MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4070 | D4080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Review and Approve - Final MSE Wall RW 3-1 Br 3 | Develop and Submit - Sign & Seal MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4050 | D4060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4040 | D4050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4060 | D4070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | Review and Approve - Final MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4080 | D4090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - Sign & Seal MSE Wall RW 3-1 Br 3 | Issue - RFC MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4010 | D4020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - Final MSE Wall RW 2-4 Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D3990 | D4000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | Develop and Submit - Final MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D3980 | D3990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D4000 | D4010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Final MSE Wall RW 2-4 Br 2 | Review and Approve - Final MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D4020 | D4030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-4 Br 2 | Issue - RFC MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D3890 | D3900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Develop and Submit - Sign & Seal MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3870 | D3880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Develop and Submit - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3860 | D3870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3880 | D3890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Review and Approve - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3900 | D3910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Sign & Seal MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3830 | D3840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Develop and Submit - Sign & Seal MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3810 | D3820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Develop and Submit - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3800 | D3810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3820 | D3830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Review and Approve - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3840 | D3850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Sign & Seal MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3770 | D3780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - Final MSE Wall RW 2-1 - Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3750 | D3760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | Develop and Submit - Final MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3740 | D3750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3760 | D3770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Final MSE Wall RW 2-1 - Br 2 | Review and Approve - Final MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3780 | D3790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-1 - Br 2 | Issue - RFC MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3710 | D3720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3690 | D3700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3680 | D3690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3700 | D3710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3720 | D3730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-2 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3610 | A33880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Issue - RFC Cat1 Brg 12 Plans - R3 | Grading - Brg 100143 - End Bent 1 - R3 - P3 | 0 |  | EW- ALL EW | H
D3310 | A20420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Issue - RFC Cat1 Brg 01 Plans - R1 | Grading - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 |  | EW- ALL EW | H
D3310 | A21400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Issue - RFC Cat1 Brg 01 Plans - R1 | Grading - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 |  | EW- ALL EW | H
D3310 | A20340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Issue - RFC Cat1 Brg 01 Plans - R1 | Grading - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 |  | EW- ALL EW | H
D3310 | A21320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Issue - RFC Cat1 Brg 01 Plans - R1 | Grading - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 |  | EW- ALL EW | H
D1180 | D3440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 07 Plans - R2 | 0 |  |  | H
Admin-1045 | D3440 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D1180 | D3380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | 0 |  |  | H
Admin-1045 | D3380 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D1180 | D3320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | 0 |  |  | H
Admin-1045 | D3320 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D1180 | D3260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | 0 |  |  | H
Admin-1045 | D3260 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D1180 | D3560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 12 Plans - R3 | 0 |  |  | H
Admin-1045 | D3560 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Begin Design | Develop and Submit - 90% Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D1180 | D3620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0 |  |  | H
Admin-1045 | D3620 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Begin Design | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D1180 | D3500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | 0 |  |  | H
Admin-1045 | D3500 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3650 | D3660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Review and Approve - Final Cat1 Brg 11 Plans - R3 | Develop and Submit - Sign & Seal Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3630 | D3640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | Develop and Submit - Final Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3640 | D3650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - Final Cat1 Brg 11 Plans - R3 | Review and Approve - Final Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3620 | D3630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3660 | D3670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - Sign & Seal Cat1 Brg 11 Plans - R3 | Issue - RFC Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3590 | D3600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Review and Approve - Final Cat1 Brg 12 Plans - R3 | Develop and Submit - Sign & Seal Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3570 | D3580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Review and Approve - 90% Cat1 Brg 12 Plans - R3 | Develop and Submit - Final Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3580 | D3590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - Final Cat1 Brg 12 Plans - R3 | Review and Approve - Final Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3560 | D3570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - 90% Cat1 Brg 12 Plans - R3 | Review and Approve - 90% Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3600 | D3610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - Sign & Seal Cat1 Brg 12 Plans - R3 | Issue - RFC Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3530 | D3540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Review and Approve - Final Cat1 Brg 09 Plans - R3 | Develop and Submit - Sign & Seal Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3510 | D3520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | Develop and Submit - Final Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3520 | D3530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - Final Cat1 Brg 09 Plans - R3 | Review and Approve - Final Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3500 | D3510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3540 | D3550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 09 Plans - R3 | Issue - RFC Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3470 | D3480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Review and Approve - Final Cat1 Brg 07 Plans - R2 | Develop and Submit - Sign & Seal Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D3450 | D3460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Review and Approve - 90% Cat1 Brg 07 Plans - R2 | Develop and Submit - Final Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D3460 | D3470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Develop and Submit - Final Cat1 Brg 07 Plans - R2 | Review and Approve - Final Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D3440 | D3450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Develop and Submit - 90% Cat1 Brg 07 Plans - R2 | Review and Approve - 90% Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D3480 | D3490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 07 Plans - R2 | Issue - RFC Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D2930 | A35570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Issue - RFC Cat2 Brg 02 Plans - R1 | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 0 |  |  | H
D3410 | D3420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Review and Approve - Final Cat1 Brg 05 Plans - R1 | Develop and Submit - Sign & Seal Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3390 | D3400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | Develop and Submit - Final Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3400 | D3410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - Final Cat1 Brg 05 Plans - R1 | Review and Approve - Final Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3380 | D3390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3420 | D3430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 05 Plans - R1 | Issue - RFC Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3350 | D3360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Review and Approve - Final Cat1 Brg 04 Plans - R1 | Develop and Submit - Sign & Seal Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D3330 | D3340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Review and Approve - 90% Cat1 Brg 04 Plans - R1 | Develop and Submit - Final Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D3340 | D3350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Develop and Submit - Final Cat1 Brg 04 Plans - R1 | Review and Approve - Final Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D3320 | D3330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | Review and Approve - 90% Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D3360 | D3370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 04 Plans - R1 | Issue - RFC Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D3290 | D3300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Review and Approve - Final Cat1 Brg 01 Plans - R1 | Develop and Submit - Sign & Seal Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3270 | D3280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | Develop and Submit - Final Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3280 | D3290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - Final Cat1 Brg 01 Plans - R1 | Review and Approve - Final Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3260 | D3270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3300 | D3310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 01 Plans - R1 | Issue - RFC Cat1 Brg 01 Plans - R1 | 0 |  |  | H
A15010 | A15455 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 2 | 0 | PIPE | EW-SML | H
A15010 | A15450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | 0 | PIPE | EW-SML | H
A34540 | A36240 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 4 - R3 - Ramp C & G Gore | Install Lighting - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A34540 | A36190 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 4 - R3 - Ramp C & G Gore | Install ITS - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A34540 | A36160 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 4 - R3 - Ramp C & G Gore | Install Grass - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A34540 | A36130 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 4 - R3 - Ramp C & G Gore | Install Landscaping - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
D1200 | D1680 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-1 | 0 |  |  | H
A22600 | A23360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Excavate - Brg 100650 - Pier 1 - R2 - P1 | Temp Wall or SOE - Brg 100652 - End Bent 1 - R2 - P1 | 0 | EW-STR | EW-STR | H
P1380 | A35970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Procure Girders - Brg 2 - Cat 2 - Steel | Erect Girders - Brg 2 - Spans 3 - R1 - P2.S1 | 0 |  | ST-BEAM | H
P1380 | A35320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Procure Girders - Brg 2 - Cat 2 - Steel | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | 0 |  | ST-BEAM | H
P1380 | A35140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Procure Girders - Brg 2 - Cat 2 - Steel | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | 0 |  | ST-BEAM | H
P1380 | A35050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Procure Girders - Brg 2 - Cat 2 - Steel | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | 0 |  | ST-BEAM | H
P1380 | A34810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Procure Girders - Brg 2 - Cat 2 - Steel | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | 0 |  | ST-BEAM | H
Admin-1045 | D1230 | SS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | Begin Design | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | 0 |  |  | H
D1180 | D3040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 06 Plans - R2 | 0 |  |  | H
Admin-1045 | D3040 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3070 | D3080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Review and Approve - Final Cat1 Brg 06 Plans - R2 | Develop and Submit - Sign & Seal Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3050 | D3060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Review and Approve - 90% Cat1 Brg 06 Plans - R2 | Develop and Submit - Final Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3060 | D3070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Develop and Submit - Final Cat1 Brg 06 Plans - R2 | Review and Approve - Final Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3040 | D3050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Develop and Submit - 90% Cat1 Brg 06 Plans - R2 | Review and Approve - 90% Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3080 | D3090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 06 Plans - R2 | Issue - RFC Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D1200 | D1040 | FF | Not Started | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.3 Design Survey/SUE | Develop and Submit - 90% Roadway Plans - R1 | Perform Design Survey [LoE] | 0 |  |  | H
D1180 | D1030 | FF | Not Started | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | Review and Approve - Design Quality Management Plan | Develop and Submit - Preliminary IDR Submittal Schedule | 0 |  |  | H
D1170 | D2860 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Independent Design Review Kickoff Meeting | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D1170 | D1220 | FS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Independent Design Review Kickoff Meeting | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1180 | D2800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D1180 | D1220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Review and Approve - Design Quality Management Plan | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1180 | D1350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1180 | D1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Dry Utility Relocation Plans | 0 |  |  | H
D1180 | D2480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D1180 | D1420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1180 | D1000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Erosion and Sediment Control Plan | 0 |  |  | H
D2350 | A22210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | Issue - RFC Signing and Pavement Marking Plan | Install Perm. Signs - R1 - P3 | 0 |  | SUB-SIGN | H
D2310 | A20450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Issue - RFC MSE Wall RW 1-1 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 |  | ST-MSE | H
D2310 | A21450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Issue - RFC MSE Wall RW 1-1 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 |  | ST-MSE | H
D2310 | A21990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Issue - RFC MSE Wall RW 1-1 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 |  | ST-MSE | H
Admin-1045 | D1540 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Begin Design | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 0 |  |  | H
Admin-1045 | D1350 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | 0 |  |  | H
Admin-1045 | D2810 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Begin Design | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
Admin-1045 | D2800 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
A35540 | A35140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35470 | A34810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35550 | A35530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Const MSE Wall & Bkfill - RW 2-4 / Brg 2 - End Bent 2 - R1 - P2.S1 | FRP Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | 0 | ST-MSE | ST-ABUT | H
A35480 | A35460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Const MSE Wall & Bkfill - RW 2-1 / Brg 2 - End Bent 1 - R1 - P2.S1 | FRP Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 | ST-MSE | ST-ABUT | H
A35560 | A35500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Temp Wall or SOE - Brg 2 - End Bent 2 - R1 - P2.S1 | Grading - Brg 2 - End Bent 2 - R1 - P2.S1 | 0 | EW-STR | EW- ALL EW | H
A35520 | A35550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Drive Pile - Brg 2 - End Bent 2 - R1 - P2.S1 | Const MSE Wall & Bkfill - RW 2-4 / Brg 2 - End Bent 2 - R1 - P2.S1 | 0 | ST-PILE | ST-MSE | H
A35530 | A35540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | FRP Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | Cure/Strip Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | 0 | ST-ABUT |  | H
A35450 | A35480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Drive Pile - Brg 2 - End Bent 1 - R1 - P2.S1 | Const MSE Wall & Bkfill - RW 2-1 / Brg 2 - End Bent 1 - R1 - P2.S1 | 0 | ST-PILE | ST-MSE | H
A35490 | A35430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Temp Wall or SOE - Brg 2 - End Bent 1 - R1 - P2.S1 | Grading - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 | EW-STR | EW- ALL EW | H
A35460 | A35470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | FRP Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | Cure/Strip Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 | ST-ABUT |  | H
A35370 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 3 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A35310 | A35320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Cap - Brg 2 - Pier 3 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35310 | A35140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Cap - Brg 2 - Pier 3 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35040 | A35320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Cap - Brg 2 - Pier 2 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35330 | A35340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Install SIP - Brg 2 - Pour 3 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A35340 | A35350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Install Overhangs - Brg 2 - Pour 3 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A35350 | A35360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Reinforce Deck - Brg 2 - Pour 3 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A35360 | A35370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Place Deck - Brg 2 - Pour 3 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | ST-POUR |  | H
A35370 | A35380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Cure Deck - Brg 2 - Pour 3 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 3 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A35250 | A35260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Drive Pile - Brg 2 - Pier 3 - R1 - P2.S1 | FRP Footing - Brg 2 - Pier 3 - R1 - P2.S1 | 0 | ST-PILE | ST-FOOT | H
A35260 | A35270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | FRP Footing - Brg 2 - Pier 3 - R1 - P2.S1 | Cure/Strip Footing - Brg 2 - Pier 3 - R1 - P2.S1 | 0 | ST-FOOT |  | H
A35280 | A35290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | FRP Column - Brg 2 - Pier 3 - R1 - P2.S1 | Cure/Strip Column - Brg 2 - Pier 3 - R1 - P2.S1 | 0 | ST-COL |  | H
A35300 | A35310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | FRP Cap - Brg 2 - Pier 3 - R1 - P2.S1 | Cure/Strip Cap - Brg 2 - Pier 3 - R1 - P2.S1 | 0 | ST-CAP |  | H
A35270 | A35280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Cure/Strip Footing - Brg 2 - Pier 3 - R1 - P2.S1 | FRP Column - Brg 2 - Pier 3 - R1 - P2.S1 | 0 |  | ST-COL | H
A35290 | A35300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Cure/Strip Column - Brg 2 - Pier 3 - R1 - P2.S1 | FRP Cap - Brg 2 - Pier 3 - R1 - P2.S1 | 0 |  | ST-CAP | H
A34920 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Slip Barrier - Brg 2 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | SUB-DGRIND | H
A35190 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 4 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A35100 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 2 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A34860 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 1 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A35040 | A35050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Cap - Brg 2 - Pier 2 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35150 | A35160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Install SIP - Brg 2 - Pour 4 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 4 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A35160 | A35170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Install Overhangs - Brg 2 - Pour 4 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 4 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A35170 | A35180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Reinforce Deck - Brg 2 - Pour 4 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 4 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A35180 | A35190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Place Deck - Brg 2 - Pour 4 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 4 - R1 - P2.S1 | 0 | ST-POUR |  | H
A35190 | A35200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Cure Deck - Brg 2 - Pour 4 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 4 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A34800 | A35050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Cap - Brg 2 - Pier 1 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35060 | A35070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Install SIP - Brg 2 - Pour 2 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 2 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A35070 | A35080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Install Overhangs - Brg 2 - Pour 2 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A35080 | A35090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Reinforce Deck - Brg 2 - Pour 2 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A35090 | A35100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Place Deck - Brg 2 - Pour 2 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 2 - R1 - P2.S1 | 0 | ST-POUR |  | H
A35100 | A35110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Cure Deck - Brg 2 - Pour 2 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 2 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A34980 | A34990 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Drive Pile - Brg 2 - Pier 2 - R1 - P2.S1 | FRP Footing - Brg 2 - Pier 2 - R1 - P2.S1 | 0 | ST-PILE | ST-FOOT | H
A34990 | A35000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | FRP Footing - Brg 2 - Pier 2 - R1 - P2.S1 | Cure/Strip Footing - Brg 2 - Pier 2 - R1 - P2.S1 | 0 | ST-FOOT |  | H
A35010 | A35020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | FRP Column - Brg 2 - Pier 2 - R1 - P2.S1 | Cure/Strip Column - Brg 2 - Pier 2 - R1 - P2.S1 | 0 | ST-COL |  | H
A35030 | A35040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | FRP Cap - Brg 2 - Pier 2 - R1 - P2.S1 | Cure/Strip Cap - Brg 2 - Pier 2 - R1 - P2.S1 | 0 | ST-CAP |  | H
A35000 | A35010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Cure/Strip Footing - Brg 2 - Pier 2 - R1 - P2.S1 | FRP Column - Brg 2 - Pier 2 - R1 - P2.S1 | 0 |  | ST-COL | H
A35020 | A35030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Cure/Strip Column - Brg 2 - Pier 2 - R1 - P2.S1 | FRP Cap - Brg 2 - Pier 2 - R1 - P2.S1 | 0 |  | ST-CAP | H
A34940 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Groove Deck - Brg 2 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A34910 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | FRPS Approach Slab 2 - Brg 2 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 | ST-APPR | SUB-DGRIND | H
A34850 | A34900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | FRPS Approach Slab 1 - Brg 2 - R1 - P2.S1 | 0 | ST-POUR | ST-APPR | H
A34930 | A34940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Grind Deck - Brg 2 - R1 - P2.S1 | Groove Deck - Brg 2 - R1 - P2.S1 | 0 | SUB-DGRIND | SUB-ST-GROOVE | H
A34900 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | FRPS Approach Slab 1 - Brg 2 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 | ST-APPR | SUB-DGRIND | H
A34820 | A34830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Install SIP - Brg 2 - Pour 1 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A34830 | A34840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Install Overhangs - Brg 2 - Pour 1 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A34840 | A34850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Reinforce Deck - Brg 2 - Pour 1 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A34850 | A34860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-POUR |  | H
A34860 | A34870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Cure Deck - Brg 2 - Pour 1 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 1 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A34740 | A34750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Drive Pile - Brg 2 - Pier 1 - R1 - P2.S1 | FRP Footing - Brg 2 - Pier 1 - R1 - P2.S1 | 0 | ST-PILE | ST-FOOT | H
A34750 | A34760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | FRP Footing - Brg 2 - Pier 1 - R1 - P2.S1 | Cure/Strip Footing - Brg 2 - Pier 1 - R1 - P2.S1 | 0 | ST-FOOT |  | H
A34770 | A34780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | FRP Column - Brg 2 - Pier 1 - R1 - P2.S1 | Cure/Strip Column - Brg 2 - Pier 1 - R1 - P2.S1 | 0 | ST-COL |  | H
A34790 | A34800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | FRP Cap - Brg 2 - Pier 1 - R1 - P2.S1 | Cure/Strip Cap - Brg 2 - Pier 1 - R1 - P2.S1 | 0 | ST-CAP |  | H
A34760 | A34770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Cure/Strip Footing - Brg 2 - Pier 1 - R1 - P2.S1 | FRP Column - Brg 2 - Pier 1 - R1 - P2.S1 | 0 |  | ST-COL | H
A34780 | A34790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Cure/Strip Column - Brg 2 - Pier 1 - R1 - P2.S1 | FRP Cap - Brg 2 - Pier 1 - R1 - P2.S1 | 0 |  | ST-CAP | H
A34540 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Finish Phase 4 - R3 - Ramp C & G Gore | Substantial Completion (Sept. 4th, 2026) | 0 |  |  | H
A34540 | LoE350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 4 - R3 - Ramp C & G Gore | R3 Phase 4 - Ramp C & G Gore [LoE] | 0 |  |  | H
A34410 | LoE350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 3 - R3 - I-275 SB Right Widening | R3 Phase 4 - Ramp C & G Gore [LoE] | 0 |  |  | H
A34530 | A34540 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Guardrail - Ramp B /Ramp G Gore - R3 - P3 | Finish Phase 4 - R3 - Ramp C & G Gore | 0 | SUB-GRAIL |  | H
A34430 | A34450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.1 R3 - Ph4 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Shift Traffic - Ramp C Left - R3 - P4 | Cut/Fill to Grade - Ramp B / Ramp G Gore - R3 - P3 | 0 | TC-Maint. | EW-SML | H
A34520 | A34530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Asphalt Shoulder - Ramp B /Ramp G Gore - R3 - P4 | Install Guardrail - Ramp B /Ramp G Gore - R3 - P3 | 0 | SUB-ASPH | SUB-GRAIL | H
A34470 | A34480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Stabilization - Ramp B / Ramp G Gore - R3 - P4 | Place Asphalt Base - Ramp B /Ramp G Gore - R3 - P4 | 0 | EW-STAB | SUB-ASPH | H
A34450 | A34470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Cut/Fill to Grade - Ramp B / Ramp G Gore - R3 - P3 | Place Stabilization - Ramp B / Ramp G Gore - R3 - P4 | 0 | EW-SML | EW-STAB | H
A34510 | A34520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Shoulder GAB - Ramp B / Ramp G Gore - R3 - P4 | Place Asphalt Shoulder - Ramp B /Ramp G Gore - R3 - P4 | 0 | EW-ABC | SUB-ASPH | H
A34500 | A34510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Edge Drain - Ramp B /Ramp G Gore - R3 - P4 | Place Shoulder GAB - Ramp B / Ramp G Gore - R3 - P4 | 0 | PIPE | EW-ABC | H
A34490 | A34500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Concrete Pav - Ramp B /Ramp G Gore - R3 - P4 | Place Edge Drain - Ramp B /Ramp G Gore - R3 - P4 | 0 | CP-SLIP | PIPE | H
A34480 | A34490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Asphalt Base - Ramp B /Ramp G Gore - R3 - P4 | Place Concrete Pav - Ramp B /Ramp G Gore - R3 - P4 | 0 | SUB-ASPH | CP-SLIP | H
A25220 | A34440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Asphalt Shoulder - Ramp G Sta 802 to 805 - R3 - P3 | Install Guardrail - Ramp G Sta 802 to 805 - R3 - P3 | 0 | SUB-ASPH | SUB-GRAIL | H
A34440 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Guardrail - Ramp G Sta 802 to 805 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-GRAIL |  | H
A24830 | A24840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Stabilization - Ramp G Sta 802 to 805 - R3 - P3 | Place Asphalt Base - Ramp G Sta 802 to 805 - R3 - P3 | 0 | EW-STAB | SUB-ASPH | H
A24820 | A24830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Cut/Fill to Grade - Ramp G Sta 802 to 805 - R3 - P3 | Place Stabilization - Ramp G Sta 802 to 805 - R3 - P3 | 0 | EW-SML | EW-STAB | H
A32920 | A34300 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | FRPS Approach Slab 2 - Brg 100869 - R3 - P3 | Cut/Fill to Grade - Ramp C Sta 708 to 715 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A32910 | A34220 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | FRPS Approach Slab 1 - Brg 100869 - R3 - P3 | Cut/Fill to Grade - Ramp C Sta 701 to 707 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A31140 | A34220 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | FRPS Approach Slab 2 - Brg 100141 - R3 - P3 | Cut/Fill to Grade - Ramp C Sta 701 to 707 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A31130 | A34130 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | FRPS Approach Slab 1 - Brg 100141 - R3 - P3 | Cut/Fill to Grade - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A30580 | A34130 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | FRPS Approach Slab 2 - Brg 100139 - R3 - P3 | Cut/Fill to Grade - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A30570 | A31610 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | FRPS Approach Slab 1 - Brg 100139 - R3 - P3 | Cut/Fill to Grade - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | ST-APPR | EW-SML | H
A30360 | A33830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100143 - Pier 2 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A33440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100143 - Pier 1 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A34020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.20.7 R3 - Ph3 - Bridge 100143 - Demo | Shift Traffic - Ramp C Left - R3 - P3 | Demo Barrier - Brg 100143 - R3 - P3 | 0 | TC-Maint. | DM-BRIDGE | H
A34380 | A31370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Demo Substructure - Ramp B Brg Over 7th Ave - R3 - P3 | Excavate - Brg 100141 - Pier 2 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A34380 | A30980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Demo Substructure - Ramp B Brg Over 7th Ave - R3 - P3 | Excavate - Brg 100141 - Pier 1 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A34380 | A31550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Demo Substructure - Ramp B Brg Over 7th Ave - R3 - P3 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A34380 | A31480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Demo Substructure - Ramp B Brg Over 7th Ave - R3 - P3 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A34400 | A31920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Grading - Brg 100139 - Pier 5 - R3 - P3 | 0 | DM-BRIDGE | EW- ALL EW | H
A34400 | A31840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Grading - Brg 100139 - Pier 4 - R3 - P3 | 0 | DM-BRIDGE | EW- ALL EW | H
A34400 | A31760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Grading - Brg 100139 - Pier 3 - R3 - P3 | 0 | DM-BRIDGE | EW- ALL EW | H
A34400 | A31680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Grading - Brg 100139 - Pier 2 - R3 - P3 | 0 | DM-BRIDGE | EW- ALL EW | H
A34400 | A30420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Grading - Brg 100139 - Pier 1 - R3 - P3 | 0 | DM-BRIDGE | EW- ALL EW | H
A34400 | A30940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A34400 | A30870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A30360 | A33410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.4 R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | Shift Traffic - Ramp C Left - R3 - P3 | Demo Superstructure - Ramp B Brg Over Palm - R3 - P3 | 0 | TC-Maint. | DM-BRIDGE | H
A30360 | A34370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | Shift Traffic - Ramp C Left - R3 - P3 | Demo Superstructure - Ramp B Brg Over 7th Ave - R3 - P3 | 0 | TC-Maint. | DM-BRIDGE | H
A30360 | A34390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | Shift Traffic - Ramp C Left - R3 - P3 | Demo Superstructure - Ramp B Brg OverN Central - R3 - P3 | 0 | TC-Maint. | DM-BRIDGE | H
A30360 | A24820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Shift Traffic - Ramp C Left - R3 - P3 | Cut/Fill to Grade - Ramp G Sta 802 to 805 - R3 - P3 | 0 | TC-Maint. | EW-SML | H
A30360 | A31760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100139 - Pier 3 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A31680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100139 - Pier 2 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A31480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Shift Traffic - Ramp C Left - R3 - P3 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P3 | 0 | TC-Maint. | EW-STR | H
A30360 | A31550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Shift Traffic - Ramp C Left - R3 - P3 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P3 | 0 | TC-Maint. | EW-STR | H
A30360 | A31840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100139 - Pier 4 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A31920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100139 - Pier 5 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A30420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100139 - Pier 1 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A30870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Shift Traffic - Ramp C Left - R3 - P3 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P3 | 0 | TC-Maint. | EW-STR | H
A30360 | A30940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Shift Traffic - Ramp C Left - R3 - P3 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P3 | 0 | TC-Maint. | EW-STR | H
A30360 | A30980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Shift Traffic - Ramp C Left - R3 - P3 | Excavate - Brg 100141 - Pier 1 - R3 - P3 | 0 | TC-Maint. | EW-STR | H
A30360 | A31370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Shift Traffic - Ramp C Left - R3 - P3 | Excavate - Brg 100141 - Pier 2 - R3 - P3 | 0 | TC-Maint. | EW-STR | H
A33400 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp B Sta 621 to 627 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-ASPH |  | H
A34360 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp C Sta 708 to 715 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-ASPH |  | H
A34260 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp C Sta 701 to 707 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-ASPH |  | H
A34190 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - I-275 SB Sta 417 to 419 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-ASPH |  | H
A31650 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - I-275 SB Sta 409 to 413 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-ASPH |  | H
A33640 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100143 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-STRIP |  | H
A32960 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100869 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-STRIP |  | H
A31180 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100141 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-STRIP |  | H
A34410 | LoE340 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 3 - R3 - I-275 SB Right Widening | R3 Phase 3 - I-275 SB Right Widening [LoE] | 0 |  |  | H
A29350 | LoE340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | R3 Phase 3 - I-275 SB Right Widening [LoE] | 0 |  |  | H
A30620 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100139 - R3 - P3 | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 | SUB-STRIP |  | H
A29350 | A30370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | Install Temp Barrier - Ramp C - R3 - P3 | 0 |  | SUB-TC-PCB | H
A34390 | A34400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | I-275 - I-4 - IBL(all) - B1.2.5.5.15 R3 - Ph3 - Demo Existing Ramp B Over N Central | Demo Superstructure - Ramp B Brg OverN Central - R3 - P3 | Demo Substructure - Ramp B Brg N Central - R3 - P3 | 0 | DM-BRIDGE | DM-BRIDGE | H
A34370 | A34380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | Demo Superstructure - Ramp B Brg Over 7th Ave - R3 - P3 | Demo Substructure - Ramp B Brg Over 7th Ave - R3 - P3 | 0 | DM-BRIDGE | DM-BRIDGE | H
A34270 | A34310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Const MSE Wall & Bkfill - RW 102 - Ramp C Sta 708 to 715 - R3 - P3 | Place Stabilization - Ramp C Sta 708 to 715 - R3 - P3 | 0 | ST-MSE | EW-STAB | H
A34350 | A34360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Shoulder GAB - Ramp C Sta 708 to 715 - R3 - P3 | Place Asphalt Shoulder - Ramp C Sta 708 to 715 - R3 - P3 | 0 | EW-ABC | SUB-ASPH | H
A34340 | A34350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Edge Drain - Ramp C Sta 708 to 715 - R3 - P3 | Place Shoulder GAB - Ramp C Sta 708 to 715 - R3 - P3 | 0 | PIPE | EW-ABC | H
A34330 | A34340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Concrete Pav - Ramp C Sta 708 to 715 - R3 - P3 | Place Edge Drain - Ramp C Sta 708 to 715 - R3 - P3 | 0 | CP-SLIP | PIPE | H
A34320 | A34330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Asphalt Base - Ramp C Sta 708 to 715 - R3 - P3 | Place Concrete Pav - Ramp C Sta 708 to 715 - R3 - P3 | 0 | SUB-ASPH | CP-SLIP | H
A34280 | A34320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Wall Barrier - Ramp C Sta 708 to 715 - R3 - P3 | Place Asphalt Base - Ramp C Sta 708 to 715 - R3 - P3 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A34290 | A34280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Junction Slab - Ramp C Sta 708 to 715 - R3 - P3 | Place Wall Barrier - Ramp C Sta 708 to 715 - R3 - P3 | 0 | ST-CIP | SUB-BR-SLIP | H
A34310 | A34290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Place Stabilization - Ramp C Sta 708 to 715 - R3 - P3 | Place Junction Slab - Ramp C Sta 708 to 715 - R3 - P3 | 0 | EW-STAB | ST-CIP | H
A34300 | A34270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | I-275 - I-4 - IBL(all) - B1.2.5.5.23 R3 - Ph3 - Ramp C Widening - Sta. 708 to 715 | Cut/Fill to Grade - Ramp C Sta 708 to 715 - R3 - P3 | Const MSE Wall & Bkfill - RW 102 - Ramp C Sta 708 to 715 - R3 - P3 | 0 | EW-SML | ST-MSE | H
A34200 | A34240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Wall Barrier - Ramp C Sta 701 to 707 - R3 - P3 | Place Edge Drain - Ramp C Sta 701 to 707 - R3 - P3 | 0 | SUB-BR-SLIP | PIPE | H
A34220 | A34230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Cut/Fill to Grade - Ramp C Sta 701 to 707 - R3 - P3 | Place Stabilization - Ramp C Sta 701 to 707 - R3 - P3 | 0 | EW-SML | EW-STAB | H
A34250 | A34260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Shoulder GAB - Ramp C Sta 701 to 707 - R3 - P3 | Place Asphalt Shoulder - Ramp C Sta 701 to 707 - R3 - P3 | 0 | EW-ABC | SUB-ASPH | H
A34240 | A34250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Edge Drain - Ramp C Sta 701 to 707 - R3 - P3 | Place Shoulder GAB - Ramp C Sta 701 to 707 - R3 - P3 | 0 | PIPE | EW-ABC | H
A34210 | A34200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Junction Slab - Ramp C Sta 701 to 707 - R3 - P3 | Place Wall Barrier - Ramp C Sta 701 to 707 - R3 - P3 | 0 | ST-CIP | SUB-BR-SLIP | H
A34230 | A34210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.22 R3 - Ph3 - Ramp C Widening - Sta. 701 to 707 | Place Stabilization - Ramp C Sta 701 to 707 - R3 - P3 | Place Junction Slab - Ramp C Sta 701 to 707 - R3 - P3 | 0 | EW-STAB | ST-CIP | H
A34100 | A34140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Const MSE Wall & Bkfill - RW 9-1 - I-275 SB Sta 417 to 419 - R3 - P3 | Place Stabilization - I-275-SB Sta 417 to 419 - R3 - P3 | 0 | ST-MSE | EW-STAB | H
A34180 | A34190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Shoulder GAB - I-275 SB Sta 417 to 419 - R3 - P3 | Place Asphalt Shoulder - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | EW-ABC | SUB-ASPH | H
A34170 | A34180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Edge Drain - I-275 SB Sta 417 to 419 - R3 - P3 | Place Shoulder GAB - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | PIPE | EW-ABC | H
A34160 | A34170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Concrete Pav - I-275 SB Sta 417 to 419 - R3 - P3 | Place Edge Drain - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | CP-SLIP | PIPE | H
A34150 | A34160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Asphalt Base - I-275 SB Sta 417 to 419 - R3 - P3 | Place Concrete Pav - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | SUB-ASPH | CP-SLIP | H
A34110 | A34150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Wall Barrier - I-275 SB Sta 417 to 419 - R3 - P3 | Place Asphalt Base - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A34120 | A34110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Junction Slab - I-275 SB Sta 417 to 419 - R3 - P3 | Place Wall Barrier - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | ST-CIP | SUB-BR-SLIP | H
A34140 | A34120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Place Stabilization - I-275-SB Sta 417 to 419 - R3 - P3 | Place Junction Slab - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | EW-STAB | ST-CIP | H
A34130 | A34100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | Cut/Fill to Grade - I-275 SB Sta 417 to 419 - R3 - P3 | Const MSE Wall & Bkfill - RW 9-1 - I-275 SB Sta 417 to 419 - R3 - P3 | 0 | EW-SML | ST-MSE | H
A34020 | A33650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.7 R3 - Ph3 - Bridge 100143 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Demo Barrier - Brg 100143 - R3 - P3 | Erect Girders - Brg 100143 - Span 2 - R3 - P3 | 0 | DM-BRIDGE | ST-BEAM | H
A34020 | A33740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.7 R3 - Ph3 - Bridge 100143 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Demo Barrier - Brg 100143 - R3 - P3 | Erect Girders - Brg 100143 - Span 3 - R3 - P3 | 0 | DM-BRIDGE | ST-BEAM | H
A34020 | A33500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.7 R3 - Ph3 - Bridge 100143 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Demo Barrier - Brg 100143 - R3 - P3 | Erect Girders - Brg 100143 - Span 1 - R3 - P3 | 0 | DM-BRIDGE | ST-BEAM | H
A33870 | A33650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Cure/Strip Cap - Brg 100143 - Pier 2 - R3 - P3 | Erect Girders - Brg 100143 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
A33870 | A33740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Cure/Strip Cap - Brg 100143 - Pier 2 - R3 - P3 | Erect Girders - Brg 100143 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
A33990 | A33740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Cure/Strip Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | Erect Girders - Brg 100143 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
A33950 | A34040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Grading - Brg 100143 - End Bent 2 - R3 - P3 | Demo Abut - Brg 100143 - End Bent 2 - R3 - P3 | 0 | EW- ALL EW | DM-BRIDGE | H
A33880 | A34030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Grading - Brg 100143 - End Bent 1 - R3 - P3 | Demo Abut - Brg 100143 - End Bent 1 - R3 - P3 | 0 | EW- ALL EW | DM-BRIDGE | H
A33980 | A33990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | FRP Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | Cure/Strip Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | 0 | ST-ABUT |  | H
A33920 | A33500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Cure/Strip Abt Cap - Brg 100143 - End Bent 1 - R3 - P3 | Erect Girders - Brg 100143 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A33910 | A33920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | FRP Abt Cap - Brg 100143 - End Bent 1 - R3 - P3 | Cure/Strip Abt Cap - Brg 100143 - End Bent 1 - R3 - P3 | 0 | ST-ABUT |  | H
A33860 | A33870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | FRP Cap - Brg 100143 - Pier 2 - R3 - P3 | Cure/Strip Cap - Brg 100143 - Pier 2 - R3 - P3 | 0 | ST-CAP |  | H
A33850 | A33860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | Cure/Strip Column - Brg 100143 - Pier 2 - R3 - P3 | FRP Cap - Brg 100143 - Pier 2 - R3 - P3 | 0 |  | ST-CAP | H
A33810 | A33610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Strip Overhangs - Brg 100143 - Span 3 - R3 - P3 | Slip Barrier - Brg 100143 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A33800 | A33810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Install Reinf Barrier - Brg 100143 - Span 3 - R3 - P3 | Strip Overhangs - Brg 100143 - Span 3 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A33750 | A33760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Install SIP - Brg 100143 - Span 3 - R3 - P3 | Install Overhangs - Brg 100143 - Span 3 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A33760 | A33770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Install Overhangs - Brg 100143 - Span 3 - R3 - P3 | Reinforce Deck - Brg 100143 - Span 3 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A33770 | A33780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Reinforce Deck - Brg 100143 - Span 3 - R3 - P3 | Place Deck - Brg 100143 - Span 3 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A33780 | A33790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Place Deck - Brg 100143 - Span 3 - R3 - P3 | Cure Deck - Brg 100143 - Span 3 - R3 - P3 | 0 | ST-POUR |  | H
A33790 | A33800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Cure Deck - Brg 100143 - Span 3 - R3 - P3 | Install Reinf Barrier - Brg 100143 - Span 3 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A33490 | A33650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Cure/Strip Cap - Brg 100143 - Pier 1 - R3 - P3 | Erect Girders - Brg 100143 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
A33720 | A33610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Strip Overhangs - Brg 100143 - Span 2 - R3 - P3 | Slip Barrier - Brg 100143 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A33710 | A33720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Install Reinf Barrier - Brg 100143 - Span 2 - R3 - P3 | Strip Overhangs - Brg 100143 - Span 2 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A33660 | A33670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Install SIP - Brg 100143 - Span 2 - R3 - P3 | Install Overhangs - Brg 100143 - Span 2 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A33670 | A33680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Install Overhangs - Brg 100143 - Span 2 - R3 - P3 | Reinforce Deck - Brg 100143 - Span 2 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A33680 | A33690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Reinforce Deck - Brg 100143 - Span 2 - R3 - P3 | Place Deck - Brg 100143 - Span 2 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A33690 | A33700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Place Deck - Brg 100143 - Span 2 - R3 - P3 | Cure Deck - Brg 12 - Span 2 - R3 - P3 | 0 | ST-POUR |  | H
A33700 | A33710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Cure Deck - Brg 12 - Span 2 - R3 - P3 | Install Reinf Barrier - Brg 100143 - Span 2 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A33490 | A33500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Cure/Strip Cap - Brg 100143 - Pier 1 - R3 - P3 | Erect Girders - Brg 100143 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A33630 | A33640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Groove Deck - Brg 100143 - R3 - P3 | Perm Striping - Brg 100143 - R3 - P3 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A33570 | A33610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Strip Overhangs - Brg 100143 - Span 1 - R3 - P3 | Slip Barrier - Brg 100143 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A33560 | A33570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Install Reinf Barrier - Brg 100143 - Span 1 - R3 - P3 | Strip Overhangs - Brg 100143 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A33510 | A33520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Install SIP - Brg 100143 - Span 1 - R3 - P3 | Install Overhangs - Brg 100143 - Span 1 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A33520 | A33530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Install Overhangs - Brg 100143 - Span 1 - R3 - P3 | Reinforce Deck - Brg 100143 - Span 1 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A33530 | A33540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Reinforce Deck - Brg 100143 - Span 1 - R3 - P3 | Place Deck - Brg 100143 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A33540 | A33550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Place Deck - Brg 100143 - Span 1 - R3 - P3 | Cure Deck - Brg 100143 - Span 1 - R3 - P3 | 0 | ST-POUR |  | H
A33550 | A33560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Cure Deck - Brg 100143 - Span 1 - R3 - P3 | Install Reinf Barrier - Brg 100143 - Span 1 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A33480 | A33490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | FRP Cap - Brg 100143 - Pier 1 - R3 - P3 | Cure/Strip Cap - Brg 100143 - Pier 1 - R3 - P3 | 0 | ST-CAP |  | H
A33470 | A33480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | Cure/Strip Column - Brg 100143 - Pier 1 - R3 - P3 | FRP Cap - Brg 100143 - Pier 1 - R3 - P3 | 0 |  | ST-CAP | H
A33020 | A33000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P3 | FRP Abt Cap - Brg 100869 - End Bent 2 - R3 - P3 | 0 | ST-MSE | ST-ABUT | H
A32710 | A32690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P3 | FRP Abt Cap - Brg 100869 - End Bent 1 - R3 - P3 | 0 | ST-MSE | ST-ABUT | H
A33430 | A33350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P3 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P3 | 0 | EW-STR | EW-STAB | H
A33340 | A33350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P3 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P3 | 0 | EW-SML | EW-STAB | H
A33420 | A33300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.4 R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Demo Substructure - Ramp B Brg Over Palm - R3 - P3 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A33420 | A32720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.4 R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Demo Substructure - Ramp B Brg Over Palm - R3 - P3 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P3 | 0 | DM-BRIDGE | EW-STR | H
A33410 | A33420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.4 R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.5.4 R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | Demo Superstructure - Ramp B Brg Over Palm - R3 - P3 | Demo Substructure - Ramp B Brg Over Palm - R3 - P3 | 0 | DM-BRIDGE | DM-BRIDGE | H
A33020 | A33340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P3 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P3 | 0 | ST-MSE | EW-SML | H
A33310 | A33350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 1 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P3 | 0 | ST-MSE | EW-STAB | H
A33390 | A33400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Shoulder GAB - Ramp B Sta 621 to 627 - R3 - P3 | Place Asphalt Shoulder - Ramp B Sta 621 to 627 - R3 - P3 | 0 | EW-ABC | SUB-ASPH | H
A33380 | A33390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Edge Drain - Ramp B Sta 621 to 627 - R3 - P3 | Place Shoulder GAB - Ramp B Sta 621 to 627 - R3 - P3 | 0 | PIPE | EW-ABC | H
A33370 | A33380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Concrete Pav - Ramp B Sta 621 to 627 - R3 - P3 | Place Edge Drain - Ramp B Sta 621 to 627 - R3 - P3 | 0 | CP-SLIP | PIPE | H
A33360 | A33370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Asphalt Base - Ramp B Sta 621 to 627 - R3 - P3 | Place Concrete Pav - Ramp B Sta 621 to 627 - R3 - P3 | 0 | SUB-ASPH | CP-SLIP | H
A33320 | A33360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Wall Barrier - Ramp B Sta 621 to 627 - R3 - P3 | Place Asphalt Base - Ramp B Sta 621 to 627 - R3 - P3 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A33330 | A33320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Junction Slab - Ramp B Sta 621 to 627 - R3 - P3 | Place Wall Barrier - Ramp B Sta 621 to 627 - R3 - P3 | 0 | ST-CIP | SUB-BR-SLIP | H
A33350 | A33330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P3 | Place Junction Slab - Ramp B Sta 621 to 627 - R3 - P3 | 0 | EW-STAB | ST-CIP | H
A33340 | A33310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P3 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 1 | 0 | EW-SML | ST-MSE | H
A33300 | A32970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P3 | Grading - Brg 100869 - End Bent 2 - R3 - P3 | 0 | EW-STR | EW- ALL EW | H
A32930 | A32940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Slip Barrier - Brg 100869 - R3 - P3 | Grind Deck - Brg 100869 - R3 - P3 | 0 | SUB-ST-PARAPET | SUB-DGRIND | H
A32870 | A32940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Cure Deck - Brg 100869 - Span 1 - R3 - P3 | Grind Deck - Brg 100869 - R3 - P3 | 0 |  | SUB-DGRIND | H
A32700 | A32820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Cure/Strip Abt Cap - Brg 100869 - End Bent 1 - R3 - P3 | Erect Girders - Brg 100869 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A32990 | A33020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P3 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P3 | 0 | ST-PILE | ST-MSE | H
A33000 | A33010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | FRP Abt Cap - Brg 100869 - End Bent 2 - R3 - P3 | Cure/Strip Abt Cap - Brg 100869 - End Bent 2 - R3 - P3 | 0 | ST-ABUT |  | H
A32950 | A32960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Groove Deck - Brg 100869 - R3 - P3 | Perm Striping - Brg 100869 - R3 - P3 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A32920 | A32940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | FRPS Approach Slab 2 - Brg 100869 - R3 - P3 | Grind Deck - Brg 100869 - R3 - P3 | 0 | ST-APPR | SUB-DGRIND | H
A32890 | A32930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Strip Overhangs - Brg 100869 - Span 1 - R3 - P3 | Slip Barrier - Brg 100869 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A32860 | A32910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Place Deck - Brg 100869 - Span 1 - R3 - P3 | FRPS Approach Slab 1 - Brg 100869 - R3 - P3 | 0 | ST-POUR | ST-APPR | H
A32940 | A32950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Grind Deck - Brg 100869 - R3 - P3 | Groove Deck - Brg 100869 - R3 - P3 | 0 | SUB-DGRIND | SUB-ST-GROOVE | H
A32910 | A32940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | FRPS Approach Slab 1 - Brg 100869 - R3 - P3 | Grind Deck - Brg 100869 - R3 - P3 | 0 | ST-APPR | SUB-DGRIND | H
A32880 | A32890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Install Reinf Barrier - Brg 100869 - Span 1 - R3 - P3 | Strip Overhangs - Brg 100869 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A32830 | A32840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Install SIP - Brg 100869 - Span 1 - R3 - P3 | Install Overhangs - Brg 100869 - Span 1 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A32840 | A32850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Install Overhangs - Brg 100869 - Span 1 - R3 - P3 | Reinforce Deck - Brg 100869 - Span 1 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A32850 | A32860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Reinforce Deck - Brg 100869 - Span 1 - R3 - P3 | Place Deck - Brg 100869 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A32860 | A32870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Place Deck - Brg 100869 - Span 1 - R3 - P3 | Cure Deck - Brg 100869 - Span 1 - R3 - P3 | 0 | ST-POUR |  | H
A32870 | A32880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Cure Deck - Brg 100869 - Span 1 - R3 - P3 | Install Reinf Barrier - Brg 100869 - Span 1 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A32680 | A32710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P3 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P3 | 0 | ST-PILE | ST-MSE | H
A32720 | A32660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P3 | Grading - Brg 100869 - End Bent 1 - R3 - P3 | 0 | EW-STR | EW- ALL EW | H
A32690 | A32700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | FRP Abt Cap - Brg 100869 - End Bent 1 - R3 - P3 | Cure/Strip Abt Cap - Brg 100869 - End Bent 1 - R3 - P3 | 0 | ST-ABUT |  | H
A31590 | A31630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Wall Barrier - I-275 SB Sta 409 to 413 - R3 - P3 | Place Edge Drain - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | SUB-BR-SLIP | PIPE | H
A32650 | A31380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Cure/Strip Footing - Brg 100141 - Pier 2 - R3 - P3 | FRP Column - Brg 100141 - Pier 2 - R3 - P3 | 0 |  | ST-COL | H
A31370 | A32630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Excavate - Brg 100141 - Pier 2 - R3 - P3 | Drive Pile - Brg 100141 - Pier 2 - R3 - P3 | 0 | EW-STR | ST-PILE | H
A32630 | A32640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Drive Pile - Brg 100141 - Pier 2 - R3 - P3 | FRP Footing - Brg 100141 - Pier 2 - R3 - P3 | 0 | ST-PILE | ST-FOOT | H
A32640 | A32650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | FRP Footing - Brg 100141 - Pier 2 - R3 - P3 | Cure/Strip Footing - Brg 100141 - Pier 2 - R3 - P3 | 0 | ST-FOOT |  | H
A32620 | A31000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Cure/Strip Footing - Brg 100141 - Pier 1 - R3 - P3 | FRP Column - Brg 100141 - Pier 1 - R3 - P3 | 0 |  | ST-COL | H
A30990 | A32610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Drive Pile - Brg 100141 - Pier 1 - R3 - P3 | FRP Footing - Brg 100141 - Pier 1 - R3 - P3 | 0 | ST-PILE | ST-FOOT | H
A32610 | A32620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | FRP Footing - Brg 100141 - Pier 1 - R3 - P3 | Cure/Strip Footing - Brg 100141 - Pier 1 - R3 - P3 | 0 | ST-FOOT |  | H
A31970 | A32340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P3 | Erect Girders - Brg 100139 - Span 6 - R3 - P3 | 0 |  | ST-BEAM | H
A31970 | A32250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P3 | Erect Girders - Brg 100139 - Span 5 - R3 - P3 | 0 |  | ST-BEAM | H
A31890 | A32250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P3 | Erect Girders - Brg 100139 - Span 5 - R3 - P3 | 0 |  | ST-BEAM | H
A31890 | A32160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P3 | Erect Girders - Brg 100139 - Span 4 - R3 - P3 | 0 |  | ST-BEAM | H
A31810 | A32160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P3 | Erect Girders - Brg 100139 - Span 4 - R3 - P3 | 0 |  | ST-BEAM | H
A31810 | A30720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P3 | Erect Girders - Brg 100139 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
A31730 | A30720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P3 | Erect Girders - Brg 100139 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
A31730 | A30630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P3 | Erect Girders - Brg 100139 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
A32410 | A30590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 6 - R3 - P3 | Slip Barrier - Brg 100139 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A32320 | A30590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 5 - R3 - P3 | Slip Barrier - Brg 100139 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A32230 | A30590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 4 - R3 - P3 | Slip Barrier - Brg 100139 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A32400 | A32410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Install Reinf Barrier - Brg 100139 - Span 6 - R3 - P3 | Strip Overhangs - Brg 100139 - Span 6 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A32350 | A32360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Install SIP - Brg 100139 - Span 6 - R3 - P3 | Install Overhangs - Brg 100139 - Span 6 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A32360 | A32370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Install Overhangs - Brg 100139 - Span 6 - R3 - P3 | Reinforce Deck - Brg 100139 - Span 6 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A32370 | A32380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Reinforce Deck - Brg 100139 - Span 6 - R3 - P3 | Place Deck - Brg 100139 - Span 6 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A32380 | A32390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Place Deck - Brg 100139 - Span 6 - R3 - P3 | Cure Deck - Brg 100139 - Span 6 - R3 - P3 | 0 | ST-POUR |  | H
A32390 | A32400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Cure Deck - Brg 100139 - Span 6 - R3 - P3 | Install Reinf Barrier - Brg 100139 - Span 6 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A32310 | A32320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Install Reinf Barrier - Brg 100139 - Span 5 - R3 - P3 | Strip Overhangs - Brg 100139 - Span 5 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A32260 | A32270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Install SIP - Brg 100139 - Span 5 - R3 - P3 | Install Overhangs - Brg 100139 - Span 5 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A32270 | A32280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Install Overhangs - Brg 100139 - Span 5 - R3 - P3 | Reinforce Deck - Brg 100139 - Span 5 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A32280 | A32290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Reinforce Deck - Brg 100139 - Span 5 - R3 - P3 | Place Deck - Brg 100139 - Span 5 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A32290 | A32300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Place Deck - Brg 100139 - Span 5 - R3 - P3 | Cure Deck - Brg 100139 - Span 5 - R3 - P3 | 0 | ST-POUR |  | H
A32300 | A32310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Cure Deck - Brg 100139 - Span 5 - R3 - P3 | Install Reinf Barrier - Brg 100139 - Span 5 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A32220 | A32230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Install Reinf Barrier - Brg 100139 - Span 4 - R3 - P3 | Strip Overhangs - Brg 100139 - Span 4 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A32170 | A32180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Install SIP - Brg 100139 - Span 4 - R3 - P3 | Install Overhangs - Brg 100139 - Span 4 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A32180 | A32190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Install Overhangs - Brg 100139 - Span 4 - R3 - P3 | Reinforce Deck - Brg 100139 - Span 4 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A32190 | A32200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Reinforce Deck - Brg 100139 - Span 4 - R3 - P3 | Place Deck - Brg 100139 - Span 4 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A32200 | A32210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Place Deck - Brg 100139 - Span 4 - R3 - P3 | Cure Deck - Brg 100139 - Span 4 - R3 - P3 | 0 | ST-POUR |  | H
A32210 | A32220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Cure Deck - Brg 100139 - Span 4 - R3 - P3 | Install Reinf Barrier - Brg 100139 - Span 4 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A31990 | A31940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | Cure/Strip Footing - Brg 100139 - Pier 5 - R3 - P3 | FRP Column - Brg 100139 - Pier 5 - R3 - P3 | 0 |  | ST-COL | H
A31920 | A31930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | Grading - Brg 100139 - Pier 5 - R3 - P3 | Install Drilled Shaft - Brg 100139 - Pier 5 - R3 - P3 | 0 | EW- ALL EW | SUB-ST-DRSFT | H
A31940 | A31950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | FRP Column - Brg 100139 - Pier 5 - R3 - P3 | Cure/Strip Column - Brg 100139 - Pier 5 - R3 - P3 | 0 | ST-COL |  | H
A31960 | A31970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | FRP Cap - Brg 100139 - Pier 5 - R3 - P3 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P3 | 0 | ST-CAP |  | H
A31950 | A31960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.10 R3 - Ph3 - Bridge 100139 - Pier 5 | Cure/Strip Column - Brg 100139 - Pier 5 - R3 - P3 | FRP Cap - Brg 100139 - Pier 5 - R3 - P3 | 0 |  | ST-CAP | H
A31840 | A31850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | Grading - Brg 100139 - Pier 4 - R3 - P3 | Install Drilled Shaft - Brg 100139 - Pier 4 - R3 - P3 | 0 | EW- ALL EW | SUB-ST-DRSFT | H
A31860 | A31870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | FRP Column - Brg 100139 - Pier 4 - R3 - P3 | Cure/Strip Column - Brg 100139 - Pier 4 - R3 - P3 | 0 | ST-COL |  | H
A31880 | A31890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | FRP Cap - Brg 100139 - Pier 4 - R3 - P3 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P3 | 0 | ST-CAP |  | H
A31870 | A31880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.9 R3 - Ph3 - Bridge 100139 - Pier 4 | Cure/Strip Column - Brg 100139 - Pier 4 - R3 - P3 | FRP Cap - Brg 100139 - Pier 4 - R3 - P3 | 0 |  | ST-CAP | H
A31830 | A31780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | Cure/Strip Footing - Brg 100139 - Pier 3 - R3 - P3 | FRP Column - Brg 100139 - Pier 3 - R3 - P3 | 0 |  | ST-COL | H
A31760 | A31770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | Grading - Brg 100139 - Pier 3 - R3 - P3 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P3 | 0 | EW- ALL EW | SUB-ST-DRSFT | H
A31780 | A31790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | FRP Column - Brg 100139 - Pier 3 - R3 - P3 | Cure/Strip Column - Brg 100139 - Pier 3 - R3 - P3 | 0 | ST-COL |  | H
A31800 | A31810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | FRP Cap - Brg 100139 - Pier 3 - R3 - P3 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P3 | 0 | ST-CAP |  | H
A31790 | A31800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.8 R3 - Ph3 - Bridge 100139 - Pier 3 | Cure/Strip Column - Brg 100139 - Pier 3 - R3 - P3 | FRP Cap - Brg 100139 - Pier 3 - R3 - P3 | 0 |  | ST-CAP | H
A31750 | A31700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | Cure/Strip Footing - Brg 100139 - Pier 2 - R3 - P3 | FRP Column - Brg 100139 - Pier 2 - R3 - P3 | 0 |  | ST-COL | H
A31680 | A31690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | Grading - Brg 100139 - Pier 2 - R3 - P3 | Install Drilled Shaft - Brg 100139 - Pier 2 - R3 - P3 | 0 | EW- ALL EW | SUB-ST-DRSFT | H
A31700 | A31710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | FRP Column - Brg 100139 - Pier 2 - R3 - P3 | Cure/Strip Column - Brg 100139 - Pier 2 - R3 - P3 | 0 | ST-COL |  | H
A31720 | A31730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | FRP Cap - Brg 100139 - Pier 2 - R3 - P3 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P3 | 0 | ST-CAP |  | H
A31710 | A31720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.4 R3 - Ph3 - Bridge 100139 - Pier 2 | Cure/Strip Column - Brg 100139 - Pier 2 - R3 - P3 | FRP Cap - Brg 100139 - Pier 2 - R3 - P3 | 0 |  | ST-CAP | H
A31670 | A30440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | Cure/Strip Footing - Brg 100139 - Pier 1 - R3 - P3 | FRP Column - Brg 100139 - Pier 1 - R3 - P3 | 0 |  | ST-COL | H
A31610 | A31620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Cut/Fill to Grade - I-275 SB Sta 409 to 413 - R3 - P3 | Place Stabilization - I-275-SB Sta 409 to 413 - R3 - P3 | 0 | EW-SML | EW-STAB | H
A31640 | A31650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Shoulder GAB - I-275 SB Sta 409 to 413 - R3 - P3 | Place Asphalt Shoulder - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | EW-ABC | SUB-ASPH | H
A31630 | A31640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Edge Drain - I-275 SB Sta 409 to 413 - R3 - P3 | Place Shoulder GAB - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | PIPE | EW-ABC | H
A31600 | A31590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Junction Slab - I-275 SB Sta 409 to 413 - R3 - P3 | Place Wall Barrier - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | ST-CIP | SUB-BR-SLIP | H
A31620 | A31600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Place Stabilization - I-275-SB Sta 409 to 413 - R3 - P3 | Place Junction Slab - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | EW-STAB | ST-CIP | H
A31410 | A31190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P3 | Erect Girders - Brg 100141 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
A31410 | A31280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P3 | Erect Girders - Brg 100141 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
A31530 | A31280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P3 | Erect Girders - Brg 100141 - Span 3 - R3 - P3 | 0 |  | ST-BEAM | H
A31490 | A31580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Grading - Brg 100141 - End Bent 2 - R3 - P3 | Demo Abut - Brg 100141 - End Bent 2 - R3 - P3 | 0 | EW- ALL EW | DM-BRIDGE | H
A31420 | A31570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Grading - Brg 100141 - End Bent 1 - R3 - P3 | Demo Abut - Brg 100141 - End Bent 1 - R3 - P3 | 0 | EW- ALL EW | DM-BRIDGE | H
A31550 | A31490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P3 | Grading - Brg 100141 - End Bent 2 - R3 - P3 | 0 | EW-STR | EW- ALL EW | H
A31520 | A31530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | FRP Abt Cap - Brg 100141 - End Bent 2 - R3 - P3 | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P3 | 0 | ST-ABUT |  | H
A31460 | A31040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P3 | Erect Girders - Brg 100141 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A31480 | A31420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P3 | Grading - Brg 100141 - End Bent 1 - R3 - P3 | 0 | EW-STR | EW- ALL EW | H
A31450 | A31460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P3 | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P3 | 0 | ST-ABUT |  | H
A31380 | A31390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | FRP Column - Brg 100141 - Pier 2 - R3 - P3 | Cure/Strip Column - Brg 100141 - Pier 2 - R3 - P3 | 0 | ST-COL |  | H
A31400 | A31410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | FRP Cap - Brg 100141 - Pier 2 - R3 - P3 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P3 | 0 | ST-CAP |  | H
A31390 | A31400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.8 R3 - Ph3 - Bridge 100141 - Pier 2 | Cure/Strip Column - Brg 100141 - Pier 2 - R3 - P3 | FRP Cap - Brg 100141 - Pier 2 - R3 - P3 | 0 |  | ST-CAP | H
A31320 | A31140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Place Deck - Brg 100141 - Span 3 - R3 - P3 | FRPS Approach Slab 2 - Brg 100141 - R3 - P3 | 0 | ST-POUR | ST-APPR | H
A31350 | A31150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Strip Overhangs - Brg 100141 - Span 3 - R3 - P3 | Slip Barrier - Brg 100141 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A31340 | A31350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Install Reinf Barrier - Brg 100141 - Span 3 - R3 - P3 | Strip Overhangs - Brg 100141 - Span 3 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A31290 | A31300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Install SIP - Brg 100141 - Span 3 - R3 - P3 | Install Overhangs - Brg 100141 - Span 3 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A31300 | A31310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Install Overhangs - Brg 100141 - Span 3 - R3 - P3 | Reinforce Deck - Brg 100141 - Span 3 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A31310 | A31320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Reinforce Deck - Brg 100141 - Span 3 - R3 - P3 | Place Deck - Brg 100141 - Span 3 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A31320 | A31330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Place Deck - Brg 100141 - Span 3 - R3 - P3 | Cure Deck - Brg 100141 - Span 3 - R3 - P3 | 0 | ST-POUR |  | H
A31330 | A31340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Cure Deck - Brg 100141 - Span 3 - R3 - P3 | Install Reinf Barrier - Brg 100141 - Span 3 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A31030 | A31190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P3 | Erect Girders - Brg 100141 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
A31260 | A31150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Strip Overhangs - Brg 100141 - Span 2 - R3 - P3 | Slip Barrier - Brg 100141 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A31250 | A31260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Install Reinf Barrier - Brg 100141 - Span 2 - R3 - P3 | Strip Overhangs - Brg 100141 - Span 2 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A31200 | A31210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Install SIP - Brg 100141 - Span 2 - R3 - P3 | Install Overhangs - Brg 100141 - Span 2 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A31210 | A31220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Install Overhangs - Brg 100141 - Span 2 - R3 - P3 | Reinforce Deck - Brg 100141 - Span 2 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A31220 | A31230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Reinforce Deck - Brg 100141 - Span 2 - R3 - P3 | Place Deck - Brg 100141 - Span 2 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A31230 | A31240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Place Deck - Brg 100141 - Span 2 - R3 - P3 | Cure Deck - Brg 100141 - Span 2 - R3 - P3 | 0 | ST-POUR |  | H
A31240 | A31250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Cure Deck - Brg 100141 - Span 2 - R3 - P3 | Install Reinf Barrier - Brg 100141 - Span 2 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A31030 | A31040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P3 | Erect Girders - Brg 100141 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A31170 | A31180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Groove Deck - Brg 100141 - R3 - P3 | Perm Striping - Brg 100141 - R3 - P3 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A31110 | A31150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Strip Overhangs - Brg 100141 - Span 1 - R3 - P3 | Slip Barrier - Brg 100141 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A31080 | A31130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Place Deck - Brg 100141 - Span 1 - R3 - P3 | FRPS Approach Slab 1 - Brg 100141 - R3 - P3 | 0 | ST-POUR | ST-APPR | H
A31100 | A31110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Install Reinf Barrier - Brg 100141 - Span 1 - R3 - P3 | Strip Overhangs - Brg 100141 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A31050 | A31060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Install SIP - Brg 100141 - Span 1 - R3 - P3 | Install Overhangs - Brg 100141 - Span 1 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A31060 | A31070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Install Overhangs - Brg 100141 - Span 1 - R3 - P3 | Reinforce Deck - Brg 100141 - Span 1 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A31070 | A31080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Reinforce Deck - Brg 100141 - Span 1 - R3 - P3 | Place Deck - Brg 100141 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A31080 | A31090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Place Deck - Brg 100141 - Span 1 - R3 - P3 | Cure Deck - Brg 100141 - Span 1 - R3 - P3 | 0 | ST-POUR |  | H
A31090 | A31100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Cure Deck - Brg 100141 - Span 1 - R3 - P3 | Install Reinf Barrier - Brg 100141 - Span 1 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A30980 | A30990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Excavate - Brg 100141 - Pier 1 - R3 - P3 | Drive Pile - Brg 100141 - Pier 1 - R3 - P3 | 0 | EW-STR | ST-PILE | H
A31000 | A31010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | FRP Column - Brg 100141 - Pier 1 - R3 - P3 | Cure/Strip Column - Brg 100141 - Pier 1 - R3 - P3 | 0 | ST-COL |  | H
A31020 | A31030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | FRP Cap - Brg 100141 - Pier 1 - R3 - P3 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P3 | 0 | ST-CAP |  | H
A31010 | A31020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.1 R3 - Ph3 - Bridge 100141 - Pier 1 | Cure/Strip Column - Brg 100141 - Pier 1 - R3 - P3 | FRP Cap - Brg 100141 - Pier 1 - R3 - P3 | 0 |  | ST-CAP | H
A30880 | A30970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Grading - Brg 100139 - End Bent 2 - R3 - P3 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P3 | 0 | EW- ALL EW | DM-BRIDGE | H
A30810 | A30960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Grading - Brg 100139 - End Bent 1 - R3 - P3 | Demo Abut - Brg 100139 - End Bent 1 - R3 - P3 | 0 | EW- ALL EW | DM-BRIDGE | H
A30940 | A30880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P3 | Grading - Brg 100139 - End Bent 2 - R3 - P3 | 0 | EW-STR | EW- ALL EW | H
A30910 | A30920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | FRP Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | 0 | ST-ABUT |  | H
A30850 | A30480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P3 | Erect Girders - Brg 100139 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A30870 | A30810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P3 | Grading - Brg 100139 - End Bent 1 - R3 - P3 | 0 | EW-STR | EW- ALL EW | H
A30840 | A30850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | FRP Abt Cap - Brg 100139 - End Bent 1 - R3 - P3 | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P3 | 0 | ST-ABUT |  | H
A30760 | A30580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Place Deck - Brg 100139 - Span 3 - R3 - P3 | FRPS Approach Slab 2 - Brg 100139 - R3 - P3 | 0 | ST-POUR | ST-APPR | H
A30790 | A30590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 3 - R3 - P3 | Slip Barrier - Brg 100139 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A30780 | A30790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Install Reinf Barrier - Brg 100139 - Span 3 - R3 - P3 | Strip Overhangs - Brg 100139 - Span 3 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A30730 | A30740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Install SIP - Brg 100139 - Span 3 - R3 - P3 | Install Overhangs - Brg 100139 - Span 3 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A30740 | A30750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Install Overhangs - Brg 100139 - Span 3 - R3 - P3 | Reinforce Deck - Brg 100139 - Span 3 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A30750 | A30760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Reinforce Deck - Brg 100139 - Span 3 - R3 - P3 | Place Deck - Brg 100139 - Span 3 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A30760 | A30770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Place Deck - Brg 100139 - Span 3 - R3 - P3 | Cure Deck - Brg 100139 - Span 3 - R3 - P3 | 0 | ST-POUR |  | H
A30770 | A30780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Cure Deck - Brg 100139 - Span 3 - R3 - P3 | Install Reinf Barrier - Brg 100139 - Span 3 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A30470 | A30630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P3 | Erect Girders - Brg 100139 - Span 2 - R3 - P3 | 0 |  | ST-BEAM | H
A30700 | A30590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 2 - R3 - P3 | Slip Barrier - Brg 100139 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A30690 | A30700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Install Reinf Barrier - Brg 100139 - Span 2 - R3 - P3 | Strip Overhangs - Brg 100139 - Span 2 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A30640 | A30650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Install SIP - Brg 100139 - Span 2 - R3 - P3 | Install Overhangs - Brg 100139 - Span 2 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A30650 | A30660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Install Overhangs - Brg 100139 - Span 2 - R3 - P3 | Reinforce Deck - Brg 100139 - Span 2 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A30660 | A30670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Reinforce Deck - Brg 100139 - Span 2 - R3 - P3 | Place Deck - Brg 100139 - Span 2 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A30670 | A30680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Place Deck - Brg 100139 - Span 2 - R3 - P3 | Cure Deck - Brg 100139 - Span 2 - R3 - P3 | 0 | ST-POUR |  | H
A30680 | A30690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Cure Deck - Brg 100139 - Span 2 - R3 - P3 | Install Reinf Barrier - Brg 100139 - Span 2 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A30470 | A30480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P3 | Erect Girders - Brg 100139 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A30610 | A30620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Groove Deck - Brg 100139 - R3 - P3 | Perm Striping - Brg 100139 - R3 - P3 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A30550 | A30590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 1 - R3 - P3 | Slip Barrier - Brg 100139 - R3 - P3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A30520 | A30570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Place Deck - Brg 100139 - Span 1 - R3 - P3 | FRPS Approach Slab 1 - Brg 100139 - R3 - P3 | 0 | ST-POUR | ST-APPR | H
A30540 | A30550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Install Reinf Barrier - Brg 100139 - Span 1 - R3 - P3 | Strip Overhangs - Brg 100139 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-DECK | H
A30490 | A30500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Install SIP - Brg 100139 - Span 1 - R3 - P3 | Install Overhangs - Brg 100139 - Span 1 - R3 - P3 | 0 | SUB-ST-SIP | ST-DECK | H
A30500 | A30510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Install Overhangs - Brg 100139 - Span 1 - R3 - P3 | Reinforce Deck - Brg 100139 - Span 1 - R3 - P3 | 0 | ST-DECK | SUB-ST-REBAR | H
A30510 | A30520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Reinforce Deck - Brg 100139 - Span 1 - R3 - P3 | Place Deck - Brg 100139 - Span 1 - R3 - P3 | 0 | SUB-ST-REBAR | ST-POUR | H
A30520 | A30530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Place Deck - Brg 100139 - Span 1 - R3 - P3 | Cure Deck - Brg 100139 - Span 1 - R3 - P3 | 0 | ST-POUR |  | H
A30530 | A30540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Cure Deck - Brg 100139 - Span 1 - R3 - P3 | Install Reinf Barrier - Brg 100139 - Span 1 - R3 - P3 | 0 |  | SUB-ST-REBAR | H
A30420 | A30430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | Grading - Brg 100139 - Pier 1 - R3 - P3 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P3 | 0 | EW- ALL EW | SUB-ST-DRSFT | H
A30440 | A30450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | FRP Column - Brg 100139 - Pier 1 - R3 - P3 | Cure/Strip Column - Brg 100139 - Pier 1 - R3 - P3 | 0 | ST-COL |  | H
A30460 | A30470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | FRP Cap - Brg 100139 - Pier 1 - R3 - P3 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P3 | 0 | ST-CAP |  | H
A30450 | A30460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.1 R3 - Ph3 - Bridge 100139 - Pier 1 | Cure/Strip Column - Brg 100139 - Pier 1 - R3 - P3 | FRP Cap - Brg 100139 - Pier 1 - R3 - P3 | 0 |  | ST-CAP | H
A30370 | A30360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | Install Temp Barrier - Ramp C - R3 - P3 | Shift Traffic - Ramp C Left - R3 - P3 | 0 | SUB-TC-PCB | TC-Maint. | H
A29240 | A29300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Wall Barrier - I-275 SB Sta 411 to 422 - R3 - P2.S2 | Place Edge Drain - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | SUB-BR-SLIP | PIPE | H
A30350 | A28980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Cure/Strip Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | FRP Column - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 |  | ST-COL | H
A28960 | A30330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Excavate - Brg 100141 - Pier 2 - R3 - P2.S2 | Drive Pile - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | EW-STR | ST-PILE | H
A30330 | A30340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Drive Pile - Brg 100141 - Pier 2 - R3 - P2.S2 | FRP Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | ST-PILE | ST-FOOT | H
A30340 | A30350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | FRP Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | Cure/Strip Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A30320 | A28590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Cure/Strip Footing - Brg 100141 - Pier 1 - R3 - P2.S2 | FRP Column - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 |  | ST-COL | H
A29130 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 |  |  | H
A29060 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 |  |  | H
A29670 | A30040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29670 | A29950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 5 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29590 | A29950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 5 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29590 | A29860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 4 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29510 | A29860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 4 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29510 | A28200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 3 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29430 | A28200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 3 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29430 | A28110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 2 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A28490 | A30040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Demo Barrier - Brg 100139 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A28490 | A29950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Demo Barrier - Brg 100139 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A28490 | A29860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Demo Barrier - Brg 100139 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A30110 | A28070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 6 - R3 - P2.S2 | Slip Barrier - Brg 100139 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A30020 | A28070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 5 - R3 - P2.S2 | Slip Barrier - Brg 100139 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A29930 | A28070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 4 - R3 - P2.S2 | Slip Barrier - Brg 100139 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A27890 | A29620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Grading - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW- ALL EW | H
A27890 | A29540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Excavate - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A27890 | A29460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Excavate - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A27890 | A29380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Grading - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW- ALL EW | H
A27890 | A28490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Demo Barrier - Brg 100139 - R3 - P2.S2 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A27890 | A28480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A27890 | A28410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A27870 | A27880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | Shift Barrier - Ramp G - R3 - P2.S2 | Shift Traffic - I-275 SB Right - R3 - P2.S2 | 0 | SUB-TC-PCB | TC-Maint. | H
A27860 | A27870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | Shift Traffic Left on Ramp G - R3 - P2.S2 | Shift Barrier - Ramp G - R3 - P2.S2 | 0 | TC-Maint. | SUB-TC-PCB | H
A27840 | A27860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | Shift Traffic - I-4 WB on to Temp Diversion Ramp - R3 - P2.S2 | Shift Traffic Left on Ramp G - R3 - P2.S2 | 0 | TC-Maint. | TC-Maint. | H
A30100 | A30110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install Reinf Barrier - Brg 100139 - Span 6 - R3 - P2.S2 | Strip Overhangs - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A30050 | A30060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install SIP - Brg 100139 - Span 6 - R3 - P2.S2 | Install Overhangs - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A30060 | A30070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install Overhangs - Brg 100139 - Span 6 - R3 - P2.S2 | Reinforce Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A30070 | A30080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Reinforce Deck - Brg 100139 - Span 6 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A30080 | A30090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Place Deck - Brg 100139 - Span 6 - R3 - P2.S2 | Cure Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | ST-POUR |  | H
A30090 | A30100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Cure Deck - Brg 100139 - Span 6 - R3 - P2.S2 | Install Reinf Barrier - Brg 100139 - Span 6 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A30010 | A30020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Install Reinf Barrier - Brg 100139 - Span 5 - R3 - P2.S2 | Strip Overhangs - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A29960 | A29970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Install SIP - Brg 100139 - Span 5 - R3 - P2.S2 | Install Overhangs - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A29970 | A29980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Install Overhangs - Brg 100139 - Span 5 - R3 - P2.S2 | Reinforce Deck - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A29980 | A29990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Reinforce Deck - Brg 100139 - Span 5 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A29990 | A30000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Place Deck - Brg 100139 - Span 5 - R3 - P2.S2 | Cure Deck - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | ST-POUR |  | H
A30000 | A30010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Cure Deck - Brg 100139 - Span 5 - R3 - P2.S2 | Install Reinf Barrier - Brg 100139 - Span 5 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A29920 | A29930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Install Reinf Barrier - Brg 100139 - Span 4 - R3 - P2.S2 | Strip Overhangs - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A29870 | A29880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Install SIP - Brg 100139 - Span 4 - R3 - P2.S2 | Install Overhangs - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A29880 | A29890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Install Overhangs - Brg 100139 - Span 4 - R3 - P2.S2 | Reinforce Deck - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A29890 | A29900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Reinforce Deck - Brg 100139 - Span 4 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A29900 | A29910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Place Deck - Brg 100139 - Span 4 - R3 - P2.S2 | Cure Deck - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | ST-POUR |  | H
A29910 | A29920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Cure Deck - Brg 100139 - Span 4 - R3 - P2.S2 | Install Reinf Barrier - Brg 100139 - Span 4 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A29690 | A29640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Cure/Strip Footing - Brg 100139 - Pier 5 - R3 - P2.S2 | FRP Column - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 |  | ST-COL | H
A29630 | A29680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Drive Pile - Brg 100139 - Pier 5 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | ST-PILE | ST-FOOT | H
A29680 | A29690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | FRP Footing - Brg 100139 - Pier 5 - R3 - P2.S2 | Cure/Strip Footing - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A29620 | A29630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Grading - Brg 100139 - Pier 5 - R3 - P2.S2 | Drive Pile - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | EW- ALL EW | ST-PILE | H
A29640 | A29650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | FRP Column - Brg 100139 - Pier 5 - R3 - P2.S2 | Cure/Strip Column - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | ST-COL |  | H
A29660 | A29670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | FRP Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | Cure/Strip Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | ST-CAP |  | H
A29650 | A29660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Cure/Strip Column - Brg 100139 - Pier 5 - R3 - P2.S2 | FRP Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 |  | ST-CAP | H
A29610 | A29560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Cure/Strip Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | FRP Column - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 |  | ST-COL | H
A29550 | A29600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Drive Pile - Brg 100139 - Pier 4 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | ST-PILE | ST-FOOT | H
A29600 | A29610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | FRP Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | Cure/Strip Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A29540 | A29550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Excavate - Brg 100139 - Pier 4 - R3 - P2.S2 | Drive Pile - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | EW-STR | ST-PILE | H
A29560 | A29570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | FRP Column - Brg 100139 - Pier 4 - R3 - P2.S2 | Cure/Strip Column - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | ST-COL |  | H
A29580 | A29590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | FRP Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | Cure/Strip Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | ST-CAP |  | H
A29570 | A29580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Cure/Strip Column - Brg 100139 - Pier 4 - R3 - P2.S2 | FRP Cap - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 |  | ST-CAP | H
A29530 | A29480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Cure/Strip Footing - Brg 100139 - Pier 3 - R3 - P2.S2 | FRP Column - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 |  | ST-COL | H
A29460 | A29470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Excavate - Brg 100139 - Pier 3 - R3 - P2.S2 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | EW-STR | SUB-ST-DRSFT | H
A29480 | A29490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | FRP Column - Brg 100139 - Pier 3 - R3 - P2.S2 | Cure/Strip Column - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | ST-COL |  | H
A29500 | A29510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | FRP Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | Cure/Strip Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | ST-CAP |  | H
A29490 | A29500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Cure/Strip Column - Brg 100139 - Pier 3 - R3 - P2.S2 | FRP Cap - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 |  | ST-CAP | H
A29450 | A29400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Cure/Strip Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | FRP Column - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 |  | ST-COL | H
A29390 | A29440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Drive Pile - Brg 100139 - Pier 2 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | ST-PILE | ST-FOOT | H
A29440 | A29450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | FRP Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | Cure/Strip Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | ST-FOOT |  | H
A29380 | A29390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Grading - Brg 100139 - Pier 2 - R3 - P2.S2 | Drive Pile - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | EW- ALL EW | ST-PILE | H
A29400 | A29410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | FRP Column - Brg 100139 - Pier 2 - R3 - P2.S2 | Cure/Strip Column - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | ST-COL |  | H
A29420 | A29430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | FRP Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | Cure/Strip Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | ST-CAP |  | H
A29410 | A29420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Cure/Strip Column - Brg 100139 - Pier 2 - R3 - P2.S2 | FRP Cap - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 |  | ST-CAP | H
A29370 | A27920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Cure/Strip Footing - Brg 100139 - Pier 1 - R3 - P2.S2 | FRP Column - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 |  | ST-COL | H
A28460 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 |  |  | H
A28390 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 |  |  | H
A26670 | LoE320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 1 Stage 2 - R3 - Ramp F / B | R3 Phase 2 Stage 1 - I-4 Temp Diversion Ramp [LoE] | 0 |  |  | H
A26720 | LoE320 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 2 Stage 1 - R3 - Temp I-4 WB Diversion Ramp | R3 Phase 2 Stage 1 - I-4 Temp Diversion Ramp [LoE] | 0 |  |  | H
A26720 | LoE330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 2 Stage 1 - R3 - Temp I-4 WB Diversion Ramp | R3 Phase 2 Stage 2 - I-275 SB Left Widening [LoE] | 0 |  |  | H
A29350 | LoE330 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | R3 Phase 2 Stage 2 - I-275 SB Left Widening [LoE] | 0 |  |  | H
A29320 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - I-275 SB Sta 411 to 422 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 | SUB-ASPH |  | H
A28770 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100141 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 | SUB-STRIP |  | H
A28100 | A29350 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100139 - R3 - P2.S2 | Finish Phase 2 Stage 2 - R3 - I-275 SB Left Widening | 0 | SUB-STRIP |  | H
A28730 | A29260 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | FRPS Approach Slab 2 - Brg 100141 - R3 - P2.S2 | Cut/Fill to Grade - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | ST-APPR | EW-SML | H
A28720 | A29260 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | FRPS Approach Slab 1 - Brg 100141 - R3 - P2.S2 | Cut/Fill to Grade - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | ST-APPR | EW-SML | H
A28050 | A29260 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | FRPS Approach Slab 1 - Brg 100139 - R3 - P2.S2 | Cut/Fill to Grade - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | ST-APPR | EW-SML | H
A28060 | A29260 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | FRPS Approach Slab 2 - Brg 100139 - R3 - P2.S2 | Cut/Fill to Grade - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | ST-APPR | EW-SML | H
A29260 | A29270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Cut/Fill to Grade - I-275 SB Sta 411 to 422 - R3 - P2.S2 | Place Stabilization - I-275-SB Sta 411 to 422 - R3 - P2.S2 | 0 | EW-SML | EW-STAB | H
A29310 | A29320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Shoulder GAB - I-275 SB Sta 411 to 422 - R3 - P2.S2 | Place Asphalt Shoulder - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | EW-ABC | SUB-ASPH | H
A29300 | A29310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Edge Drain - I-275 SB Sta 411 to 422 - R3 - P2.S2 | Place Shoulder GAB - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | PIPE | EW-ABC | H
A29250 | A29240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Junction Slab - I-275 SB Sta 411 to 422 - R3 - P2.S2 | Place Wall Barrier - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | ST-CIP | SUB-BR-SLIP | H
A29270 | A29250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | I-275 - I-4 - IBL(all) - B1.2.5.4.5 R3 - Ph2, Stg2 - I-275 SB Widening - Sta. 411 to 422 | Place Stabilization - I-275-SB Sta 411 to 422 - R3 - P2.S2 | Place Junction Slab - I-275 SB Sta 411 to 422 - R3 - P2.S2 | 0 | EW-STAB | ST-CIP | H
A27890 | A28960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Excavate - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A27890 | A28570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Excavate - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A29160 | A28780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.7 R3 - Ph2, Stg2 - Bridge 100141 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Demo Barrier - Brg 100141 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A29160 | A28870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.7 R3 - Ph2, Stg2 - Bridge 100141 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Demo Barrier - Brg 100141 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A29160 | A28630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.7 R3 - Ph2, Stg2 - Bridge 100141 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Demo Barrier - Brg 100141 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A27890 | A29160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.12.7 R3 - Ph2, Stg2 - Bridge 100141 - Demo | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Demo Barrier - Brg 100141 - R3 - P2.S2 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A29010 | A28780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 2 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29010 | A28870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 3 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29130 | A28870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 3 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A27890 | A29150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A29090 | A29180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Grading - Brg 100141 - End Bent 2 - R3 - P2.S2 | Demo Abut - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A29020 | A29170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Grading - Brg 100141 - End Bent 1 - R3 - P2.S2 | Demo Abut - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A29150 | A29090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Temp Wall or SOE - Brg 100141 - End Bent 2 - R3 - P2.S2 | Grading - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 | EW-STR | EW- ALL EW | H
A29120 | A29130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | FRP Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | Cure/Strip Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 | ST-ABUT |  | H
A29060 | A28630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 1 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29080 | A29020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P2.S2 | Grading - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | EW-STR | EW- ALL EW | H
A27890 | A29080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Temp Wall or SOE - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A29050 | A29060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | Cure/Strip Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | ST-ABUT |  | H
A28980 | A28990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | FRP Column - Brg 100141 - Pier 2 - R3 - P2.S2 | Cure/Strip Column - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | ST-COL |  | H
A29000 | A29010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | FRP Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | Cure/Strip Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | ST-CAP |  | H
A28990 | A29000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Cure/Strip Column - Brg 100141 - Pier 2 - R3 - P2.S2 | FRP Cap - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 |  | ST-CAP | H
A28910 | A28730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Place Deck - Brg 100141 - Span 3 - R3 - P2.S2 | FRPS Approach Slab 2 - Brg 100141 - R3 - P2.S2 | 0 | ST-POUR | ST-APPR | H
A28940 | A28740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Strip Overhangs - Brg 100141 - Span 3 - R3 - P2.S2 | Slip Barrier - Brg 100141 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A28930 | A28940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Install Reinf Barrier - Brg 100141 - Span 3 - R3 - P2.S2 | Strip Overhangs - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A28880 | A28890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Install SIP - Brg 100141 - Span 3 - R3 - P2.S2 | Install Overhangs - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A28890 | A28900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Install Overhangs - Brg 100141 - Span 3 - R3 - P2.S2 | Reinforce Deck - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A28900 | A28910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Reinforce Deck - Brg 100141 - Span 3 - R3 - P2.S2 | Place Deck - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A28910 | A28920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Place Deck - Brg 100141 - Span 3 - R3 - P2.S2 | Cure Deck - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | ST-POUR |  | H
A28920 | A28930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Cure Deck - Brg 100141 - Span 3 - R3 - P2.S2 | Install Reinf Barrier - Brg 100141 - Span 3 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A28620 | A28780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 2 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A28850 | A28740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Strip Overhangs - Brg 100141 - Span 2 - R3 - P2.S2 | Slip Barrier - Brg 100141 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A28840 | A28850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Install Reinf Barrier - Brg 100141 - Span 2 - R3 - P2.S2 | Strip Overhangs - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A28790 | A28800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Install SIP - Brg 100141 - Span 2 - R3 - P2.S2 | Install Overhangs - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A28800 | A28810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Install Overhangs - Brg 100141 - Span 2 - R3 - P2.S2 | Reinforce Deck - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A28810 | A28820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Reinforce Deck - Brg 100141 - Span 2 - R3 - P2.S2 | Place Deck - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A28820 | A28830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Place Deck - Brg 100141 - Span 2 - R3 - P2.S2 | Cure Deck - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | ST-POUR |  | H
A28830 | A28840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Cure Deck - Brg 100141 - Span 2 - R3 - P2.S2 | Install Reinf Barrier - Brg 100141 - Span 2 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A28620 | A28630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | Erect Girders - Brg 100141 - Span 1 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A28760 | A28770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Groove Deck - Brg 100141 - R3 - P2.S2 | Perm Striping - Brg 100141 - R3 - P2.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A28700 | A28740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Strip Overhangs - Brg 100141 - Span 1 - R3 - P2.S2 | Slip Barrier - Brg 100141 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A28670 | A28720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Place Deck - Brg 100141 - Span 1 - R3 - P2.S2 | FRPS Approach Slab 1 - Brg 100141 - R3 - P2.S2 | 0 | ST-POUR | ST-APPR | H
A28690 | A28700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Install Reinf Barrier - Brg 100141 - Span 1 - R3 - P2.S2 | Strip Overhangs - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A28640 | A28650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Install SIP - Brg 100141 - Span 1 - R3 - P2.S2 | Install Overhangs - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A28650 | A28660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Install Overhangs - Brg 100141 - Span 1 - R3 - P2.S2 | Reinforce Deck - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A28660 | A28670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Reinforce Deck - Brg 100141 - Span 1 - R3 - P2.S2 | Place Deck - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A28670 | A28680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Place Deck - Brg 100141 - Span 1 - R3 - P2.S2 | Cure Deck - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | ST-POUR |  | H
A28680 | A28690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Cure Deck - Brg 100141 - Span 1 - R3 - P2.S2 | Install Reinf Barrier - Brg 100141 - Span 1 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A28570 | A28580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Excavate - Brg 100141 - Pier 1 - R3 - P2.S2 | Drive Pile - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | EW-STR | ST-PILE | H
A28590 | A28600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | FRP Column - Brg 100141 - Pier 1 - R3 - P2.S2 | Cure/Strip Column - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | ST-COL |  | H
A28610 | A28620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | FRP Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | Cure/Strip Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | ST-CAP |  | H
A28600 | A28610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Cure/Strip Column - Brg 100141 - Pier 1 - R3 - P2.S2 | FRP Cap - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 |  | ST-CAP | H
A27890 | A27900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Excavate - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | SUB-TC-PCB | EW-STR | H
A28490 | A28110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Demo Barrier - Brg 100139 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A28490 | A28200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Demo Barrier - Brg 100139 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A28490 | A27960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.7 R3 - Ph2, Stg2 - Bridge 100139 - Demo | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Demo Barrier - Brg 100139 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A28420 | A28510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Grading - Brg 100139 - End Bent 2 - R3 - P2.S2 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A28350 | A28500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Grading - Brg 100139 - End Bent 1 - R3 - P2.S2 | Demo Abut - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A28480 | A28420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Temp Wall or SOE - Brg 100139 - End Bent 2 - R3 - P2.S2 | Grading - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | EW-STR | EW- ALL EW | H
A28450 | A28460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | FRP Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | ST-ABUT |  | H
A28390 | A27960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 1 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A28410 | A28350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Temp Wall or SOE - Brg 100139 - End Bent 1 - R3 - P2.S2 | Grading - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 | EW-STR | EW- ALL EW | H
A27880 | A27890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | Shift Traffic - I-275 SB Right - R3 - P2.S2 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | 0 | TC-Maint. | SUB-TC-PCB | H
A28380 | A28390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | FRP Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | Cure/Strip Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 | ST-ABUT |  | H
A28240 | A28060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Place Deck - Brg 100139 - Span 3 - R3 - P2.S2 | FRPS Approach Slab 2 - Brg 100139 - R3 - P2.S2 | 0 | ST-POUR | ST-APPR | H
A28270 | A28070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 3 - R3 - P2.S2 | Slip Barrier - Brg 100139 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A28260 | A28270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Install Reinf Barrier - Brg 100139 - Span 3 - R3 - P2.S2 | Strip Overhangs - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A28210 | A28220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Install SIP - Brg 100139 - Span 3 - R3 - P2.S2 | Install Overhangs - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A28220 | A28230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Install Overhangs - Brg 100139 - Span 3 - R3 - P2.S2 | Reinforce Deck - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A28230 | A28240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Reinforce Deck - Brg 100139 - Span 3 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A28240 | A28250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Place Deck - Brg 100139 - Span 3 - R3 - P2.S2 | Cure Deck - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | ST-POUR |  | H
A28250 | A28260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Cure Deck - Brg 100139 - Span 3 - R3 - P2.S2 | Install Reinf Barrier - Brg 100139 - Span 3 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A27950 | A28110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 2 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A28180 | A28070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 2 - R3 - P2.S2 | Slip Barrier - Brg 100139 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A28170 | A28180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Install Reinf Barrier - Brg 100139 - Span 2 - R3 - P2.S2 | Strip Overhangs - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A28120 | A28130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Install SIP - Brg 100139 - Span 2 - R3 - P2.S2 | Install Overhangs - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A28130 | A28140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Install Overhangs - Brg 100139 - Span 2 - R3 - P2.S2 | Reinforce Deck - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A28140 | A28150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Reinforce Deck - Brg 100139 - Span 2 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A28150 | A28160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Place Deck - Brg 100139 - Span 2 - R3 - P2.S2 | Cure Deck - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | ST-POUR |  | H
A28160 | A28170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Cure Deck - Brg 100139 - Span 2 - R3 - P2.S2 | Install Reinf Barrier - Brg 100139 - Span 2 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A27950 | A27960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 1 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A28090 | A28100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Groove Deck - Brg 100139 - R3 - P2.S2 | Perm Striping - Brg 100139 - R3 - P2.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A28030 | A28070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Strip Overhangs - Brg 100139 - Span 1 - R3 - P2.S2 | Slip Barrier - Brg 100139 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A28000 | A28050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Place Deck - Brg 100139 - Span 1 - R3 - P2.S2 | FRPS Approach Slab 1 - Brg 100139 - R3 - P2.S2 | 0 | ST-POUR | ST-APPR | H
A28020 | A28030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Install Reinf Barrier - Brg 100139 - Span 1 - R3 - P2.S2 | Strip Overhangs - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A27970 | A27980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Install SIP - Brg 100139 - Span 1 - R3 - P2.S2 | Install Overhangs - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A27980 | A27990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Install Overhangs - Brg 100139 - Span 1 - R3 - P2.S2 | Reinforce Deck - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A27990 | A28000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Reinforce Deck - Brg 100139 - Span 1 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A28000 | A28010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Place Deck - Brg 100139 - Span 1 - R3 - P2.S2 | Cure Deck - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | ST-POUR |  | H
A28010 | A28020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Cure Deck - Brg 100139 - Span 1 - R3 - P2.S2 | Install Reinf Barrier - Brg 100139 - Span 1 - R3 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A27900 | A27910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Excavate - Brg 100139 - Pier 1 - R3 - P2.S2 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | EW-STR | SUB-ST-DRSFT | H
A27920 | A27930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | FRP Column - Brg 100139 - Pier 1 - R3 - P2.S2 | Cure/Strip Column - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | ST-COL |  | H
A27940 | A27950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | FRP Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | Cure/Strip Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | ST-CAP |  | H
A27930 | A27940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Cure/Strip Column - Brg 100139 - Pier 1 - R3 - P2.S2 | FRP Cap - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 |  | ST-CAP | H
A27650 | A27500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Install Temp Barrier - I-275 SB - R3 - P2.S1 | Temp Wall or SOE - I-4 Temp Diversion Ramp - R3 - P2.S1 | 0 | SUB-TC-PCB | EW-STR | H
A27490 | A27640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | Shift/Remove Temp Barrier - Ramp B - R3 - P2.S1 | Shift Traffic - I-275 SB to Inside - R3 - P2.S1 | 0 | SUB-TC-PCB | TC-Maint. | H
A27640 | A27650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | Shift Traffic - I-275 SB to Inside - R3 - P2.S1 | Install Temp Barrier - I-275 SB - R3 - P2.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A26830 | A27630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Place Asphalt Shoulder - Ramp G / B Gore - R3 - P2.S1 | Install Guardrail - Ramp G / B Gore - R3 - P2.S1 | 0 | SUB-ASPH | SUB-GRAIL | H
A27630 | A26720 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Guardrail - Ramp G / B Gore - R3 - P2.S1 | Finish Phase 2 Stage 1 - R3 - Temp I-4 WB Diversion Ramp | 0 | SUB-GRAIL |  | H
A27620 | A27550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Place GAB - I-4 Temp Diversion Ramp - R3 - P2.S1 | Place Temp Asphalt - I-4 Temp Diversion Ramp - R3 - P2.S1 | 0 | EW-ABC | SUB-ASPH | H
A27540 | A27620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Place Stabilization - I-4 Temp Diversion Ramp - R3 - P2.S1 | Place GAB - I-4 Temp Diversion Ramp - R3 - P2.S1 | 0 | EW-STAB | EW-ABC | H
A27550 | A26720 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Temp Asphalt - I-4 Temp Diversion Ramp - R3 - P2.S1 | Finish Phase 2 Stage 1 - R3 - Temp I-4 WB Diversion Ramp | 0 | SUB-ASPH |  | H
A27490 | A27530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Shift/Remove Temp Barrier - Ramp B - R3 - P2.S1 | Cut/Fill to Grade - I-4 Temp Diversion Ramp - R3 - P2.S1 | 0 | SUB-TC-PCB | EW-SML | H
A26780 | A26790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Place Stabilization - Ramp G / B Gore - R3 - P2.S1 | Place Asphalt Base - Ramp G / B Gore - R3 - P2.S1 | 0 | EW-STAB | SUB-ASPH | H
A26770 | A26780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Cut/Fill to Grade - Ramp G / B Gore - R3 - P2.S1 | Place Stabilization - Ramp G / B Gore - R3 - P2.S1 | 0 | EW-SML | EW-STAB | H
A27490 | A26770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Shift/Remove Temp Barrier - Ramp B - R3 - P2.S1 | Cut/Fill to Grade - Ramp G / B Gore - R3 - P2.S1 | 0 | SUB-TC-PCB | EW-SML | H
A27500 | A27540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Temp Wall or SOE - I-4 Temp Diversion Ramp - R3 - P2.S1 | Place Stabilization - I-4 Temp Diversion Ramp - R3 - P2.S1 | 0 | EW-STR | EW-STAB | H
A27530 | A27500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | I-275 - I-4 - IBL(all) - B1.2.5.3.2 R3 - Ph2, Stg1 - I-4 WB Temp Diversion Ramp | Cut/Fill to Grade - I-4 Temp Diversion Ramp - R3 - P2.S1 | Temp Wall or SOE - I-4 Temp Diversion Ramp - R3 - P2.S1 | 0 | EW-SML | EW-STR | H
A26850 | A27490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | Shift Traffic to New Ramp B & F - R3 - P2.S1 | Shift/Remove Temp Barrier - Ramp B - R3 - P2.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A26670 | A26850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | Finish Phase 1 Stage 2 - R3 - Ramp F / B | Shift Traffic to New Ramp B & F - R3 - P2.S1 | 0 |  | TC-Maint. | H
A16380 | A24100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Install DRG S-101 to S-105 - I-4 Sta 310 to 314 - R2 - P1 | Grading - 13th St /14th St Intersection - R2 - P1 | 0 | PIPE | EW- ALL EW | H
A16430 | A27080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Install DRG S-104 to S-113/S-112 - Ramp EN Sta 97 to 103 - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | PIPE | EW-SML | H
A16440 | A27080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Install DRG S-113 to O-101 - Ramp EN Sta 90 to 99 - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | PIPE | EW-SML | H
A16450 | A23990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Install DRG S-118 to S-123 - Pond SMF 4A - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | PIPE | EW-SML | H
A16460 | A23990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Install DRG S-126 to S-134 - Pond SMF 4A to Taliaferro Sta 21 - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | PIPE | EW-SML | H
A16470 | A22870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Install DRG S-136 to S-146 - Taliaferro Ave - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | PIPE | EW-SML | H
A16480 | A22870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Install DRG S-147 to S-151 - I-275 Sta 715 to 717 - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | PIPE | EW-SML | H
A27470 | A27480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place GAB - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | Place Asphalt - 14th Ave Shared Use Path Nebraska to Columbus - R2 - P1 | 0 | EW-ABC | SUB-ASPH | H
A27080 | A27450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | Grading - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 0 | EW-SML | EW- ALL EW | H
A24140 | A27450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place Sidewalk - 13th St /14th StIntersection - R2 - P1 | Grading - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 0 | FLATWORK | EW- ALL EW | H
A27460 | A27470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place Stabilization - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | Place GAB - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 0 | EW-STAB | EW-ABC | H
A27450 | A27460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Grading - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | Place Stabilization - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 0 | EW- ALL EW | EW-STAB | H
A24000 | A27410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Const MSE Wall & Bkfill - RW 7-2 - Ramp EN Sta 83 to 85 - R2 - P1 | Grading - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | 0 | ST-MSE | EW- ALL EW | H
A27420 | A27430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Place Stabilization - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | Place GAB - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | 0 | EW-STAB | EW-ABC | H
A27410 | A27420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Grading - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | Place Stabilization - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | 0 | EW- ALL EW | EW-STAB | H
A23580 | A27340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Slip Barrier - Brg 100652 - R2 - P1 | Grading - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | SUB-ST-PARAPET | EW- ALL EW | H
A27350 | A27360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Install DRG - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Place Stabilization - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | PIPE | EW-STAB | H
A27340 | A27350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Grading - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Install DRG - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | EW- ALL EW | PIPE | H
A27390 | A27400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Sidewalk - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Place Asphalt Surface - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | FLATWORK | SUB-ASPH | H
A27380 | A27390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Curb - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Place Sidewalk - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | FLATWORK | FLATWORK | H
A27370 | A27380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place GAB - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Place Curb - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | EW-ABC | FLATWORK | H
A27360 | A27370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Place Stabilization - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Place GAB - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | EW-STAB | EW-ABC | H
A27190 | A24100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Cut/Fill to Grade - I-4 Sta 311 to 320 - R2 - P1 | Grading - 13th St /14th St Intersection - R2 - P1 | 0 | EW-SML | EW- ALL EW | H
A22490 | A27190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Install Temp Barrier - Ramp EN - R2 - P1 | Cut/Fill to Grade - I-4 Sta 311 to 320 - R2 - P1 | 0 | SUB-TC-PCB | EW-SML | H
A27200 | A27170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Stabilization - I-4 Sta 311 to 320 - R2 - P1 | Place Wall Barrier - I-4 Sta 311 to 320 - R2 - P1 | 0 | EW-STAB | SUB-BR-SLIP | H
A27190 | A27200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Cut/Fill to Grade - I-4 Sta 311 to 320 - R2 - P1 | Place Stabilization - I-4 Sta 311 to 320 - R2 - P1 | 0 | EW-SML | EW-STAB | H
A22960 | A27080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Const MSE Wall & Bkfill - RW 6-1 / Brg 6 100650 - End Bent 2- R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | ST-MSE | EW-SML | H
A27090 | A27100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Stabilization - Ramp EN Sta 91 to 103 - R2 - P1 | Place Asphalt Base - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | EW-STAB | SUB-ASPH | H
A27080 | A27090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | Place Stabilization - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | EW-SML | EW-STAB | H
A27280 | A27290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Install DRG - 10th St / 14th Ave Intersection - R2 - P1 | Place Stabilization - 10th St /14th Ave Intersection - R2 - P1 | 0 | PIPE | EW-STAB | H
A27270 | A27280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Grading - 10th St /14th Ave Intersection - R2 - P1 | Install DRG - 10th St / 14th Ave Intersection - R2 - P1 | 0 | EW- ALL EW | PIPE | H
A27300 | A27310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Place GAB - 10th St /14th Ave Intersection - R2 - P1 | Place Curb - 10th St /14th Ave Intersection - R2 - P1 | 0 | EW-ABC | FLATWORK | H
A27290 | A27300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Place Stabilization - 10th St /14th Ave Intersection - R2 - P1 | Place GAB - 10th St /14th Ave Intersection - R2 - P1 | 0 | EW-STAB | EW-ABC | H
A27240 | A27250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Shoulder GAB - I-4 Sta 311 to 320 - R2 - P1 | Place Asphalt Shoulder - I-4 Sta 311 to 320 - R2 - P1 | 0 | EW-ABC | SUB-ASPH | H
A27230 | A27240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Edge Drain - I-4 Sta 311 to 320 - R2 - P1 | Place Shoulder GAB - I-4 Sta 311 to 320 - R2 - P1 | 0 | PIPE | EW-ABC | H
A27220 | A27230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Concrete Pav - I-4 Sta 311 to 320 - R2 - P1 | Place Edge Drain - I-4 Sta 311 to 320 - R2 - P1 | 0 | CP-SLIP | PIPE | H
A27210 | A27220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Asphalt Base - I-4 Sta 311 to 320 - R2 - P1 | Place Concrete Pav - I-4 Sta 311 to 320 - R2 - P1 | 0 | SUB-ASPH | CP-SLIP | H
A27170 | A27210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Wall Barrier - I-4 Sta 311 to 320 - R2 - P1 | Place Asphalt Base - I-4 Sta 311 to 320 - R2 - P1 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A27150 | A27090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place 3-Pour Barrier - Ramp EN Sta 91 to 103 - R2 - P1 | Place Stabilization - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | SUB-BR-SLIP | EW-STAB | H
A27080 | A27150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | Place 3-Pour Barrier - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | EW-SML | SUB-BR-SLIP | H
A27130 | A27140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Shoulder GAB - Ramp EN Sta 91 to 103 - R2 - P1 | Place Asphalt Shoulder - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | EW-ABC | SUB-ASPH | H
A27120 | A27130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Edge Drain - Ramp EN Sta 91 to 103 - R2 - P1 | Place Shoulder GAB - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | PIPE | EW-ABC | H
A27110 | A27120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Concrete Pav - Ramp EN Sta 91 to 103 - R2 - P1 | Place Edge Drain - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | CP-SLIP | PIPE | H
A27100 | A27110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Asphalt Base - Ramp EN Sta 91 to 103 - R2 - P1 | Place Concrete Pav - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | SUB-ASPH | CP-SLIP | H
A25600 | A25580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P1.S2 | FRP Abt Cap - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A25280 | A25260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P1.S2 | FRP Abt Cap - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A24910 | A24890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Const MSE Wall & Bkfill - RW 8-2 / Brg 100868 - End Bent 2 - R3 - P1.S2 | FRP Abt Cap - Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A24520 | A24500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Const MSE Wall & Bkfill - RW 8-1 / Brg 100868 - End Bent 1 - R3 - P1.S2 | FRP Abt Cap - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A23670 | A23650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Const MSE Wall & Bkfill - RW 7-1 / Brg 100652 - End Bent 2 - R2 - P1 | FRP Abt Cap - Brg 100652 - End Bent 2 - R2 - P1 | 0 | ST-MSE | ST-ABUT | H
A23350 | A23330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Const MSE Wall & Bkfill - RW 7-2 / Brg 100652 - End Bent 1 - R2 - P1 | FRP Abt Cap - Brg 100652 - End Bent 1 - R2 - P1 | 0 | ST-MSE | ST-ABUT | H
A22960 | A22940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Const MSE Wall & Bkfill - RW 6-1 / Brg 6 100650 - End Bent 2- R2 - P1 | FRP Abt Cap - Brg 100650 - End Bent 2 - R2 - P1 | 0 | ST-MSE | ST-ABUT | H
A21450 | A21430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | FRP Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 | ST-MSE | ST-ABUT | H
A21370 | A21350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S2 - right | FRP Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 | ST-MSE | ST-ABUT | H
A20450 | A20470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S3 - left | FRP Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 | ST-MSE | ST-ABUT | H
A20370 | A20390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S3 - left | FRP Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 | ST-MSE | ST-ABUT | H
A18090 | A18070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Const MSE Wall & Bkfill - RW 4-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | FRP Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A18010 | A17990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Const MSE Wall & Bkfill - RW 4-1 / Brg 100657 - End Bent 1 - R1 - P1.S2 | FRP Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A17390 | A17370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Const MSE Wall & Bkfill - RW 3-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | FRP Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A17300 | A17280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Const MSE Wall & Bkfill - RW 3-1 / Brg 100656 - End Bent 1 - R1 - P1.S2 | FRP Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | ST-MSE | ST-ABUT | H
A15080 | A15100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Const MSE Wall & Bkfill - RW 5-2 / Brg 100865 - End Bent 2 - R1 - P1.S1 | FRP Abt Cap - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | ST-MSE | ST-ABUT | H
A14670 | A1660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | FRP Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | ST-MSE | ST-ABUT | H
A26820 | A26830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Place Shoulder GAB - Ramp G / B Gore - R3 - P2.S1 | Place Asphalt Shoulder - Ramp G / B Gore - R3 - P2.S1 | 0 | EW-ABC | SUB-ASPH | H
A26810 | A26820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Place Edge Drain - Ramp G / B Gore - R3 - P2.S1 | Place Shoulder GAB - Ramp G / B Gore - R3 - P2.S1 | 0 | PIPE | EW-ABC | H
A26800 | A26810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Place Concrete Pav - Ramp G / B Gore - R3 - P2.S1 | Place Edge Drain - Ramp G / B Gore - R3 - P2.S1 | 0 | CP-SLIP | PIPE | H
A26790 | A26800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | I-275 - I-4 - IBL(all) - B1.2.5.3.7 R3 - Ph2, Stg1 - Ramp G / B Gore | Place Asphalt Base - Ramp G / B Gore - R3 - P2.S1 | Place Concrete Pav - Ramp G / B Gore - R3 - P2.S1 | 0 | SUB-ASPH | CP-SLIP | H
A26730 | A26170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | EW-STR | EW-STAB | H
A18390 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Surface - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 | SUB-ASPH |  | H
A18150 | A17710 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Install Fiberglass Panel on Barrier - Brg 100657 - R1 - P1.S2 | Perm Striping - Brg 100657 - R1 - P1.S2 | 0 | SUB-ST-RAILING | SUB-STRIP | H
A17450 | A16910 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Install Fiberglass Panel on Barrier - Brg 100656 - R1 - P1.S2 | Perm Striping - Brg 100656 - R1 - P1.S2 | 0 | SUB-ST-RAILING | SUB-STRIP | H
A16630 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 | SUB-ASPH |  | H
A14930 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - Brg 100865 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-STRIP |  | H
A26270 | A26280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Cut/Fill to Grade - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Stabilization - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | EW-SML | EW-STAB | H
A26160 | A26170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | EW-SML | EW-STAB | H
A26050 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | EW-SML | EW-STAB | H
A26710 | A23380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.7 R2 - Ph1 - Bridge 100652 Ramp EN - Demo | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Demo Barrier - Brg 100652 - R2 - P1 | Excavate - Brg 100652 - Pier 1 - R2 - P1 | 0 | DM-BRIDGE | EW-STR | H
A22490 | A26710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.9.7 R2 - Ph1 - Bridge 100652 Ramp EN - Demo | Install Temp Barrier - Ramp EN - R2 - P1 | Demo Barrier - Brg 100652 - R2 - P1 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A26700 | A22600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.7 R2 - Ph1 - Bridge 100650 Ramp EN - Demo | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Demo Barrier - Brg 100650 - R2 - P1 | Excavate - Brg 100650 - Pier 1 - R2 - P1 | 0 | DM-BRIDGE | EW-STR | H
A22490 | A26700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.4.7 R2 - Ph1 - Bridge 100650 Ramp EN - Demo | Install Temp Barrier - Ramp EN - R2 - P1 | Demo Barrier - Brg 100650 - R2 - P1 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A26690 | A25890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.1 R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Demo Substructure - Ramp F Brg Over Palm - R3 - P1.S2 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | DM-BRIDGE | EW-STR | H
A26690 | A25290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.1 R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Demo Substructure - Ramp F Brg Over Palm - R3 - P1.S2 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | DM-BRIDGE | EW-STR | H
A24360 | A26680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.3 R3 - Ph1, Stg2, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.2.1 R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | Install Temp Barrier - Ramp B - R3 - P1.S2 | Demo Superstructure - Ramp F Brg Over Palm - R3 - P1.S2 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A26670 | LoE310 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 1 Stage 2 - R3 - Ramp F / B | R3 Phase 1 Stage 2 - Ramp F / B [LoE] | 0 |  |  | H
A26660 | LoE300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 1 Stage 1 - R3 - Temp Ramp F | R3 Phase 1 Stage 1 - Temp Ramp F [LoE] | 0 |  |  | H
A26590 | LoE310 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | R3 Phase 1 Stage 2 - Ramp F / B [LoE] | 0 |  |  | H
A26590 | LoE300 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | R3 Phase 1 Stage 1 - Temp Ramp F [LoE] | 0 |  |  | H
A26580 | LoE290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | R3 Phase 0 - - 60" Drainage Systeming [LoE] | 0 |  |  | H
A26350 | LoE290 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.3 R3 Phase Durations | Start Construction - R3 | R3 Phase 0 - - 60" Drainage Systeming [LoE] | 0 |  |  | H
A23290 | LoE240 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | Finish Phase 2 - R2 - Right Ramp EN Construction | R2 Phase 2 - Right Ramp EN Construction [LoE] | 0 |  |  | H
LoE230 | LoE240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | R2 Phase 1 - Left Ramp EN Construction [LoE] | R2 Phase 2 - Right Ramp EN Construction [LoE] | 0 |  |  | H
A22250 | LoE230 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | Finish Phase 1 - R2 - Left Ramp EN Construction | R2 Phase 1 - Left Ramp EN Construction [LoE] | 0 |  |  | H
A16490 | LoE230 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | Start Construction - R2 | R2 Phase 1 - Left Ramp EN Construction [LoE] | 0 |  |  | H
A22240 | LoE220 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | R2 Phase 0 - Pond SMF 4A / Lower Drainage [LoE] | 0 |  |  | H
A16490 | LoE220 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.2 R2 Phase Durations | Start Construction - R2 | R2 Phase 0 - Pond SMF 4A / Lower Drainage [LoE] | 0 |  |  | H
A25600 | A26160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-SML | H
A24520 | A25950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Const MSE Wall & Bkfill - RW 8-1 / Brg 100868 - End Bent 1 - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | ST-MSE | EW-SML | H
A26010 | A26670 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp B Sta 601 to 606 - R3 - P1.S2 | Finish Phase 1 Stage 2 - R3 - Ramp F / B | 0 | SUB-ASPH |  | H
A26110 | A26670 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp B Sta 614 to 618 - R3 - P1.S2 | Finish Phase 1 Stage 2 - R3 - Ramp F / B | 0 | SUB-ASPH |  | H
A26220 | A26670 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp B Sta 621 to 627 - R3 - P1.S2 | Finish Phase 1 Stage 2 - R3 - Ramp F / B | 0 | SUB-ASPH |  | H
A26330 | A26670 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Shoulder - Ramp F Sta 506 to 511 - R3 - P1.S2 | Finish Phase 1 Stage 2 - R3 - Ramp F / B | 0 | SUB-ASPH |  | H
A25540 | A26670 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100869 - R3 - P1.S2 | Finish Phase 1 Stage 2 - R3 - Ramp F / B | 0 | SUB-STRIP |  | H
A24780 | A26670 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Perm Striping - Brg 100868 - R3 - P1.S2 | Finish Phase 1 Stage 2 - R3 - Ramp F / B | 0 | SUB-STRIP |  | H
A24230 | A26660 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.5 R3 - Ph1, Stg1, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Open Traffic to Temp Ramp F Close Exist Ramp F - R3 - P1.S1 | Finish Phase 1 Stage 1 - R3 - Temp Ramp F | 0 | TC-Maint. |  | H
A26660 | A26390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.2.4 R3 - Ph1, Stg2, Stp1 - MOT | Finish Phase 1 Stage 1 - R3 - Temp Ramp F | Shift Traffic - Ramp B to Right - R3 - P1.S2 | 0 |  | TC-Maint. | H
A26580 | A26590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | 0 |  |  | H
A26590 | A24170 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | Install MOT - Ramp B / C - R3 - P1.S1 | 0 |  | TC-Maint. | H
A26590 | A24930 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | Prep for Drill Shafts - Brg 100868 - Pier 2 - R3 - P1.S2 | 0 |  | EW-STR | H
A26590 | A24550 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | Prep for Drill Shafts - Brg 100868 - Pier 1 - R3 - P1.S2 | 0 |  | EW-STR | H
A26590 | A24530 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | Temp Wall or SOE - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 |  | EW-STR | H
A26590 | A25900 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | Temp Wall or SOE - Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 |  | EW-STR | H
A26590 | A26400 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Start Phase 1 Stage 1 and Stage 2 Brg Construction - R3 | Excavate - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 |  | EW-STR | H
A26560 | A24750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Strip Overhangs - Brg 100868 - Span 3 - R3 - P1.S2 | Slip Barrier - Brg 100868 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A26480 | A26490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Cure/Strip Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 3 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A26480 | A25110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Cure/Strip Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 4 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A25010 | A26490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Cure/Strip Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 3 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A26550 | A26560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Install Reinf Barrier - Brg 100868 - Span 3 - R3 - P1.S2 | Strip Overhangs - Brg 100868 - Span 3 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A26500 | A26510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Install SIP - Brg 100868 - Span 3 - R3 - P1.S2 | Install Overhangs - Brg 100868 - Span 3 - R3 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A26510 | A26520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Install Overhangs - Brg 100868 - Span 3 - R3 - P1.S2 | Reinforce Deck - Brg 100868 - Span 3 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A26520 | A26530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Reinforce Deck - Brg 100868 - Span 3 - R3 - P1.S2 | Place Deck - Brg 100868 - Span 3 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A26530 | A26540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Place Deck - Brg 100868 - Span 3 - R3 - P1.S2 | Cure Deck - Brg 100868 - Span 3 - R3 - P1.S2 | 0 | ST-POUR |  | H
A26540 | A26550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Cure Deck - Brg 100868 - Span 3 - R3 - P1.S2 | Install Reinf Barrier - Brg 100868 - Span 3 - R3 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A26420 | A26430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Drive Pile - Brg 100868 - Pier 3 - R3 - P1.S2 | FRP Footing - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 | ST-PILE | ST-FOOT | H
A26430 | A26440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | FRP Footing - Brg 100868 - Pier 3 - R3 - P1.S2 | Cure/Strip Footing - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 | ST-FOOT |  | H
A26450 | A26460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | FRP Column - Brg 100868 - Pier 3 - R3 - P1.S2 | Cure/Strip Column - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 | ST-COL |  | H
A26470 | A26480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | FRP Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | Cure/Strip Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 | ST-CAP |  | H
A26440 | A26450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Cure/Strip Footing - Brg 100868 - Pier 3 - R3 - P1.S2 | FRP Column - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 |  | ST-COL | H
A26460 | A26470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Cure/Strip Column - Brg 100868 - Pier 3 - R3 - P1.S2 | FRP Cap - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 |  | ST-CAP | H
A26390 | A24390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.4 R3 - Ph1, Stg2, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.2.5 R3 - Ph1, Stg2 - Left Ramp B - Temp Pavement - Sta. 600 to 603, 613 to 614 | Shift Traffic - Ramp B to Right - R3 - P1.S2 | Place Temp Asphalt - Ramp B - R3 - P1.S2 | 0 | TC-Maint. | SUB-ASPH | H
A24180 | A26380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | Shift Traffic - Ramp B & C to Outside - R3 - P1.S1 | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A26360 | A24230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.5 R3 - Ph1, Stg1, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.1.5 R3 - Ph1, Stg1, Stp2 - MOT | Shift Temp Barrier - Ramp F - R3 - P1.S1 | Open Traffic to Temp Ramp F Close Exist Ramp F - R3 - P1.S1 | 0 | SUB-TC-PCB | TC-Maint. | H
A24290 | A26360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.1 R3 - Ph1, Stg1 - Temp Ramp F - Sta. 706 to 711 | I-275 - I-4 - IBL(all) - B1.2.5.1.5 R3 - Ph1, Stg1, Stp2 - MOT | Place Temp Asphalt - Temp Ramp F - R3 - P1.S1 | Shift Temp Barrier - Ramp F - R3 - P1.S1 | 0 | SUB-ASPH | SUB-TC-PCB | H
A26240 | A26280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 1 | Place Stabilization - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26320 | A26330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Shoulder GAB - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Asphalt Shoulder - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | EW-ABC | SUB-ASPH | H
A26310 | A26320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Edge Drain - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Shoulder GAB - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | PIPE | EW-ABC | H
A26300 | A26310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Concrete Pav - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Edge Drain - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | CP-SLIP | PIPE | H
A26290 | A26300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Asphalt Base - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Concrete Pav - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | SUB-ASPH | CP-SLIP | H
A26250 | A26290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Wall Barrier - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Asphalt Base - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A26260 | A26250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Junction Slab - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Wall Barrier - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | ST-CIP | SUB-BR-SLIP | H
A26280 | A26260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Place Stabilization - Ramp F Sta 506 to 511 - R3 - P1.S2 | Place Junction Slab - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | EW-STAB | ST-CIP | H
A26270 | A26240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Cut/Fill to Grade - Ramp F Sta 506 to 511 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 1 | 0 | EW-SML | ST-MSE | H
A26130 | A26170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 1 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26210 | A26220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Shoulder GAB - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Asphalt Shoulder - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | EW-ABC | SUB-ASPH | H
A26200 | A26210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Edge Drain - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Shoulder GAB - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | PIPE | EW-ABC | H
A26190 | A26200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Concrete Pav - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Edge Drain - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | CP-SLIP | PIPE | H
A26180 | A26190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Asphalt Base - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Concrete Pav - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | SUB-ASPH | CP-SLIP | H
A26140 | A26180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Wall Barrier - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Asphalt Base - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A26150 | A26140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Junction Slab - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Wall Barrier - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-CIP | SUB-BR-SLIP | H
A26170 | A26150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | Place Junction Slab - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | EW-STAB | ST-CIP | H
A26160 | A26130 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 1 | 3 | EW-SML | ST-MSE | H
A26020 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26100 | A26110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Shoulder GAB - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Asphalt Shoulder - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | EW-ABC | SUB-ASPH | H
A26090 | A26100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Edge Drain - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Shoulder GAB - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | PIPE | EW-ABC | H
A26080 | A26090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Concrete Pav - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Edge Drain - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | CP-SLIP | PIPE | H
A26070 | A26080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Asphalt Base - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Concrete Pav - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | SUB-ASPH | CP-SLIP | H
A26030 | A26070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Wall Barrier - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Asphalt Base - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A26040 | A26030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Junction Slab - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Wall Barrier - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | ST-CIP | SUB-BR-SLIP | H
A26060 | A26040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | Place Junction Slab - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | EW-STAB | ST-CIP | H
A25920 | A25960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Const MSE Wall & Bkfill - RW 8-1 / Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Stabilization - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26000 | A26010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Shoulder GAB - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Asphalt Shoulder - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | EW-ABC | SUB-ASPH | H
A25990 | A26000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Edge Drain - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Shoulder GAB - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | PIPE | EW-ABC | H
A25980 | A25990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Concrete Pav - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Edge Drain - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | CP-SLIP | PIPE | H
A25970 | A25980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Asphalt Base - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Concrete Pav - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | SUB-ASPH | CP-SLIP | H
A25930 | A25970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Wall Barrier - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Asphalt Base - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A25940 | A25930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Junction Slab - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Wall Barrier - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | ST-CIP | SUB-BR-SLIP | H
A25960 | A25940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Place Stabilization - Ramp B Sta 601 to 606 - R3 - P1.S2 | Place Junction Slab - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | EW-STAB | ST-CIP | H
A25950 | A25920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Cut/Fill to Grade - Ramp B Sta 601 to 606 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 8-1 / Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | EW-SML | ST-MSE | H
A25900 | A24860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Temp Wall or SOE - Brg 100868 - End Bent 2 - R3 - P1.S2 | Grading - Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A25890 | A25550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P1.S2 | Grading - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A25510 | A25520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Slip Barrier - Brg 100869 - R3 - P1.S2 | Grind Deck - Brg 100869 - R3 - P1.S2 | 0 | SUB-ST-PARAPET | SUB-DGRIND | H
A25450 | A25520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Cure Deck - Brg 100869 - Span 1 - R3 - P1.S2 | Grind Deck - Brg 100869 - R3 - P1.S2 | 0 |  | SUB-DGRIND | H
A25270 | A25400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Cure/Strip Abt Cap - Brg 100869 - End Bent 1 - R3 - P1.S2 | Erect Girders - Brg 100869 - Span 1 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A25570 | A25600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A25580 | A25590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | FRP Abt Cap - Brg 100869 - End Bent 2 - R3 - P1.S2 | Cure/Strip Abt Cap - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | ST-ABUT |  | H
A25530 | A25540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Groove Deck - Brg 100869 - R3 - P1.S2 | Perm Striping - Brg 100869 - R3 - P1.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A25500 | A25520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | FRPS Approach Slab 2 - Brg 100869 - R3 - P1.S2 | Grind Deck - Brg 100869 - R3 - P1.S2 | 0 | ST-APPR | SUB-DGRIND | H
A25470 | A25510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Strip Overhangs - Brg 100869 - Span 1 - R3 - P1.S2 | Slip Barrier - Brg 100869 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A25440 | A25490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Place Deck - Brg 100869 - Span 1 - R3 - P1.S2 | FRPS Approach Slab 1 - Brg 100869 - R3 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A25520 | A25530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Grind Deck - Brg 100869 - R3 - P1.S2 | Groove Deck - Brg 100869 - R3 - P1.S2 | 0 | SUB-DGRIND | SUB-ST-GROOVE | H
A25490 | A25520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | FRPS Approach Slab 1 - Brg 100869 - R3 - P1.S2 | Grind Deck - Brg 100869 - R3 - P1.S2 | 0 | ST-APPR | SUB-DGRIND | H
A25460 | A25470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Install Reinf Barrier - Brg 100869 - Span 1 - R3 - P1.S2 | Strip Overhangs - Brg 100869 - Span 1 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A25410 | A25420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Install SIP - Brg 100869 - Span 1 - R3 - P1.S2 | Install Overhangs - Brg 100869 - Span 1 - R3 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A25420 | A25430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Install Overhangs - Brg 100869 - Span 1 - R3 - P1.S2 | Reinforce Deck - Brg 100869 - Span 1 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A25430 | A25440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Reinforce Deck - Brg 100869 - Span 1 - R3 - P1.S2 | Place Deck - Brg 100869 - Span 1 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A25440 | A25450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Place Deck - Brg 100869 - Span 1 - R3 - P1.S2 | Cure Deck - Brg 100869 - Span 1 - R3 - P1.S2 | 0 | ST-POUR |  | H
A25450 | A25460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Cure Deck - Brg 100869 - Span 1 - R3 - P1.S2 | Install Reinf Barrier - Brg 100869 - Span 1 - R3 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A25250 | A25280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A25290 | A25230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P1.S2 | Grading - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A25260 | A25270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | FRP Abt Cap - Brg 100869 - End Bent 1 - R3 - P1.S2 | Cure/Strip Abt Cap - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | ST-ABUT |  | H
A25210 | A25220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Shoulder GAB - Ramp G Sta 802 to 805 - R3 - P3 | Place Asphalt Shoulder - Ramp G Sta 802 to 805 - R3 - P3 | 0 | EW-ABC | SUB-ASPH | H
A25200 | A25210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Edge Drain - Ramp G Sta 802 to 805 - R3 - P3 | Place Shoulder GAB - Ramp G Sta 802 to 805 - R3 - P3 | 0 | PIPE | EW-ABC | H
A24850 | A25200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Concrete Pav - Ramp G Sta 802 to 805 - R3 - P3 | Place Edge Drain - Ramp G Sta 802 to 805 - R3 - P3 | 0 | CP-SLIP | PIPE | H
A24840 | A24850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | I-275 - I-4 - IBL(all) - B1.2.5.5.7 R3 - Ph3 - Ramp G - Start to Finish - Sta. 802 to 805 | Place Asphalt Base - Ramp G Sta 802 to 805 - R3 - P3 | Place Concrete Pav - Ramp G Sta 802 to 805 - R3 - P3 | 0 | SUB-ASPH | CP-SLIP | H
A25150 | A24740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Place Deck - Brg 100868 - Span 4 - R3 - P1.S2 | FRPS Approach Slab 2 - Brg 100868 - R3 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A24900 | A25110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Cure/Strip Abt Cap - Brg 100868 - End Bent 2 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 4 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A25010 | A25020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Cure/Strip Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 2 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A25180 | A24750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Strip Overhangs - Brg 100868 - Span 4 - R3 - P1.S2 | Slip Barrier - Brg 100868 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A25170 | A25180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Install Reinf Barrier - Brg 100868 - Span 4 - R3 - P1.S2 | Strip Overhangs - Brg 100868 - Span 4 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A25120 | A25130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Install SIP - Brg 100868 - Span 4 - R3 - P1.S2 | Install Overhangs - Brg 100868 - Span 4 - R3 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A25130 | A25140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Install Overhangs - Brg 100868 - Span 4 - R3 - P1.S2 | Reinforce Deck - Brg 100868 - Span 4 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A25140 | A25150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Reinforce Deck - Brg 100868 - Span 4 - R3 - P1.S2 | Place Deck - Brg 100868 - Span 4 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A25150 | A25160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Place Deck - Brg 100868 - Span 4 - R3 - P1.S2 | Cure Deck - Brg 100868 - Span 4 - R3 - P1.S2 | 0 | ST-POUR |  | H
A25160 | A25170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Cure Deck - Brg 100868 - Span 4 - R3 - P1.S2 | Install Reinf Barrier - Brg 100868 - Span 4 - R3 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A24630 | A25020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Cure/Strip Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 2 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A25090 | A24750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Strip Overhangs - Brg 100868 - Span 2 - R3 - P1.S2 | Slip Barrier - Brg 100868 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A25080 | A25090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Install Reinf Barrier - Brg 100868 - Span 2 - R3 - P1.S2 | Strip Overhangs - Brg 100868 - Span 2 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A25030 | A25040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Install SIP - Brg 100868 - Span 2 - R3 - P1.S2 | Install Overhangs - Brg 100868 - Span 2 - R3 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A25040 | A25050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Install Overhangs - Brg 100868 - Span 2 - R3 - P1.S2 | Reinforce Deck - Brg 100868 - Span 2 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A25050 | A25060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Reinforce Deck - Brg 100868 - Span 2 - R3 - P1.S2 | Place Deck - Brg 100868 - Span 2 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A25060 | A25070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Place Deck - Brg 100868 - Span 2 - R3 - P1.S2 | Cure Deck - Brg 100868 - Span 2 - R3 - P1.S2 | 0 | ST-POUR |  | H
A25070 | A25080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Cure Deck - Brg 100868 - Span 2 - R3 - P1.S2 | Install Reinf Barrier - Brg 100868 - Span 2 - R3 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A24510 | A24640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Cure/Strip Abt Cap - Brg 100868 - End Bent 1 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 1 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A24630 | A24640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Cure/Strip Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | Erect Girders - Brg 100868 - Span 1 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A24980 | A24990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | FRP Column - Brg 100868 - Pier 2 - R3 - P1.S2 | Cure/Strip Column - Brg 100868 - Pier 2 - R3 - P1.S2 | 0 | ST-COL |  | H
A25000 | A25010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | FRP Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | Cure/Strip Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | 0 | ST-CAP |  | H
A24990 | A25000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Cure/Strip Column - Brg 100868 - Pier 2 - R3 - P1.S2 | FRP Cap - Brg 100868 - Pier 2 - R3 - P1.S2 | 0 |  | ST-CAP | H
A24880 | A24910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Drive Pile - Brg 100868 - End Bent 2 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 8-2 / Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A24890 | A24900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | FRP Abt Cap - Brg 100868 - End Bent 2 - R3 - P1.S2 | Cure/Strip Abt Cap - Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 | ST-ABUT |  | H
A24770 | A24780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Groove Deck - Brg 100868 - R3 - P1.S2 | Perm Striping - Brg 100868 - R3 - P1.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A24730 | A24740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | FRPS Approach Slab 1 - Brg 100868 - R3 - P1.S2 | FRPS Approach Slab 2 - Brg 100868 - R3 - P1.S2 | 0 | ST-APPR | ST-APPR | H
A24710 | A24750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Strip Overhangs - Brg 100868 - Span 1 - R3 - P1.S2 | Slip Barrier - Brg 100868 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A24680 | A24730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Place Deck - Brg 100868 - Span 1 - R3 - P1.S2 | FRPS Approach Slab 1 - Brg 100868 - R3 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A24700 | A24710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Install Reinf Barrier - Brg 100868 - Span 1 - R3 - P1.S2 | Strip Overhangs - Brg 100868 - Span 1 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A24650 | A24660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Install SIP - Brg 100868 - Span 1 - R3 - P1.S2 | Install Overhangs - Brg 100868 - Span 1 - R3 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A24660 | A24670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Install Overhangs - Brg 100868 - Span 1 - R3 - P1.S2 | Reinforce Deck - Brg 100868 - Span 1 - R3 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A24670 | A24680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Reinforce Deck - Brg 100868 - Span 1 - R3 - P1.S2 | Place Deck - Brg 100868 - Span 1 - R3 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A24680 | A24690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Place Deck - Brg 100868 - Span 1 - R3 - P1.S2 | Cure Deck - Brg 100868 - Span 1 - R3 - P1.S2 | 0 | ST-POUR |  | H
A24690 | A24700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Cure Deck - Brg 100868 - Span 1 - R3 - P1.S2 | Install Reinf Barrier - Brg 100868 - Span 1 - R3 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A24600 | A24610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | FRP Column - Brg 100868 - Pier 1 - R3 - P1.S2 | Cure/Strip Column - Brg 100868 - Pier 1 - R3 - P1.S2 | 0 | ST-COL |  | H
A24620 | A24630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | FRP Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | Cure/Strip Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | 0 | ST-CAP |  | H
A24610 | A24620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Cure/Strip Column - Brg 100868 - Pier 1 - R3 - P1.S2 | FRP Cap - Brg 100868 - Pier 1 - R3 - P1.S2 | 0 |  | ST-CAP | H
A24530 | A24470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Temp Wall or SOE - Brg 100868 - End Bent 1 - R3 - P1.S2 | Grading - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A24500 | A24510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | FRP Abt Cap - Brg 100868 - End Bent 1 - R3 - P1.S2 | Cure/Strip Abt Cap - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | ST-ABUT |  | H
A24400 | A24350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.5 R3 - Ph1, Stg2 - Left Ramp B - Temp Pavement - Sta. 600 to 603, 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.3 R3 - Ph1, Stg2, Stp2 - MOT | Temp Striping - Ramp B - R3 - P1.S2 | Shift Traffic - Ramp B Left - R3 - P1.S2 | 0 | SUB-STRIP | TC-Maint. | H
A24390 | A24400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.5 R3 - Ph1, Stg2 - Left Ramp B - Temp Pavement - Sta. 600 to 603, 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.5 R3 - Ph1, Stg2 - Left Ramp B - Temp Pavement - Sta. 600 to 603, 613 to 614 | Place Temp Asphalt - Ramp B - R3 - P1.S2 | Temp Striping - Ramp B - R3 - P1.S2 | 0 | SUB-ASPH | SUB-STRIP | H
A24350 | A24360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.3 R3 - Ph1, Stg2, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.2.3 R3 - Ph1, Stg2, Stp2 - MOT | Shift Traffic - Ramp B Left - R3 - P1.S2 | Install Temp Barrier - Ramp B - R3 - P1.S2 | 0 | TC-Maint. | SUB-TC-PCB | H
A24280 | A24290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.1 R3 - Ph1, Stg1 - Temp Ramp F - Sta. 706 to 711 | I-275 - I-4 - IBL(all) - B1.2.5.1.1 R3 - Ph1, Stg1 - Temp Ramp F - Sta. 706 to 711 | Place GAB - Temp Ramp F - R3 - P1.S1 | Place Temp Asphalt - Temp Ramp F - R3 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A24170 | A24180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | Install MOT - Ramp B / C - R3 - P1.S1 | Shift Traffic - Ramp B & C to Outside - R3 - P1.S1 | 0 | TC-Maint. | TC-Maint. | H
A24160 | A24110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Install DRG - 13th St / 14th St Intersection - R2 - P1 | Place Stabilization - 13th St /14th St Intersection - R2 - P1 | 0 | PIPE | EW-STAB | H
A24100 | A24160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Grading - 13th St /14th St Intersection - R2 - P1 | Install DRG - 13th St / 14th St Intersection - R2 - P1 | 0 | EW- ALL EW | PIPE | H
A24140 | A24150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Place Sidewalk - 13th St /14th StIntersection - R2 - P1 | Place Asphalt Surface - 13th St /14th St Intersection - R2 - P1 | 0 | FLATWORK | SUB-ASPH | H
A24130 | A24140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Place Curb - 13th St /14th St Intersection - R2 - P1 | Place Sidewalk - 13th St /14th StIntersection - R2 - P1 | 0 | FLATWORK | FLATWORK | H
A24120 | A24130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Place GAB - 13th St /14th St Intersection - R2 - P1 | Place Curb - 13th St /14th St Intersection - R2 - P1 | 0 | EW-ABC | FLATWORK | H
A24110 | A24120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | Place Stabilization - 13th St /14th St Intersection - R2 - P1 | Place GAB - 13th St /14th St Intersection - R2 - P1 | 0 | EW-STAB | EW-ABC | H
A23350 | A23990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Const MSE Wall & Bkfill - RW 7-2 / Brg 100652 - End Bent 1 - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | ST-MSE | EW-SML | H
A24000 | A24020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Const MSE Wall & Bkfill - RW 7-2 - Ramp EN Sta 83 to 85 - R2 - P1 | Place Stabilization - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | ST-MSE | EW-STAB | H
A24080 | A24090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Shoulder GAB - Ramp EN Sta 83 to 88 - R2 - P1 | Place Asphalt Shoulder - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | EW-ABC | SUB-ASPH | H
A24070 | A24080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Edge Drain - Ramp EN Sta 83 to 88 - R2 - P1 | Place Shoulder GAB - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | PIPE | EW-ABC | H
A24060 | A24070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Concrete Pav - Ramp EN Sta 83 to 88 - R2 - P1 | Place Edge Drain - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | CP-SLIP | PIPE | H
A24050 | A24060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Asphalt Base - Ramp EN Sta 83 to 88 - R2 - P1 | Place Concrete Pav - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | SUB-ASPH | CP-SLIP | H
A24040 | A24050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Wall Barrier - Ramp EN Sta 83 to 88 - R2 - P1 | Place Asphalt Base - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A24030 | A24040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Junction Slab - Ramp EN Sta 83 to 88 - R2 - P1 | Place Wall Barrier - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | ST-CIP | SUB-BR-SLIP | H
A24020 | A24030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Place Stabilization - Ramp EN Sta 83 to 88 - R2 - P1 | Place Junction Slab - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | EW-STAB | ST-CIP | H
A23990 | A24000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | Const MSE Wall & Bkfill - RW 7-2 - Ramp EN Sta 83 to 85 - R2 - P1 | 0 | EW-SML | ST-MSE | H
A23980 | A22880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place 3-Pour Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | Place Stabilization - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | SUB-BR-SLIP | EW-STAB | H
A22870 | A23980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | Place 3-Pour Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | EW-SML | SUB-BR-SLIP | H
A22840 | A22880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 1 | Place Stabilization - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-MSE | EW-STAB | H
A22490 | A23960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Install Temp Barrier - Ramp EN - R2 - P1 | Temp Wall or SOE - Brg 100652 - End Bent 2 - R2 - P1 | 0 | SUB-TC-PCB | EW-STR | H
A22490 | A23360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Install Temp Barrier - Ramp EN - R2 - P1 | Temp Wall or SOE - Brg 100652 - End Bent 1 - R2 - P1 | 0 | SUB-TC-PCB | EW-STR | H
A23970 | A22910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Temp Wall or SOE - Brg 100650 - End Bent 2 - R2 - P1 | Grading - Brg 100650 - End Bent 2 - R2 - P1 | 0 | EW-STR | EW- ALL EW | H
A22490 | A23970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Install Temp Barrier - Ramp EN - R2 - P1 | Temp Wall or SOE - Brg 100650 - End Bent 2 - R2 - P1 | 0 | SUB-TC-PCB | EW-STR | H
A23960 | A23620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Temp Wall or SOE - Brg 100652 - End Bent 2 - R2 - P1 | Grading - Brg 100652 - End Bent 2 - R2 - P1 | 0 | EW-STR | EW- ALL EW | H
A23910 | A23570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Place Deck - Brg 100652 - Span 3 - R2 - P1 | FRPS Approach Slab 2 - Brg 100652 - R2 - P1 | 0 | ST-POUR | ST-APPR | H
A23660 | A23870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Cure/Strip Abt Cap - Brg 100652 - End Bent 2 - R2 - P1 | Erect Girders - Brg 100652 - Span 3 - R2 - P1 | 0 |  | ST-BEAM | H
A23770 | A23870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Cure/Strip Cap - Brg 100652 - Pier 2 - R2 - P1 | Erect Girders - Brg 100652 - Span 3 - R2 - P1 | 0 |  | ST-BEAM | H
A23770 | A23780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Cure/Strip Cap - Brg 100652 - Pier 2 - R2 - P1 | Erect Girders - Brg 100652 - Span 2 - R2 - P1 | 0 |  | ST-BEAM | H
A23940 | A23580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Strip Overhangs - Brg 100652 - Span 3 - R2 - P1 | Slip Barrier - Brg 100652 - R2 - P1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A23930 | A23940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Install Reinf Barrier - Brg 100652 - Span 3 - R2 - P1 | Strip Overhangs - Brg 100652 - Span 3 - R2 - P1 | 0 | SUB-ST-REBAR | ST-DECK | H
A23880 | A23890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Install SIP - Brg 100652 - Span 3 - R2 - P1 | Install Overhangs - Brg 100652 - Span 3 - R2 - P1 | 0 | SUB-ST-SIP | ST-DECK | H
A23890 | A23900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Install Overhangs - Brg 100652 - Span 3 - R2 - P1 | Reinforce Deck - Brg 100652 - Span 3 - R2 - P1 | 0 | ST-DECK | SUB-ST-REBAR | H
A23900 | A23910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Reinforce Deck - Brg 100652 - Span 3 - R2 - P1 | Place Deck - Brg 100652 - Span 3 - R2 - P1 | 0 | SUB-ST-REBAR | ST-POUR | H
A23910 | A23920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Place Deck - Brg 100652 - Span 3 - R2 - P1 | Cure Deck - Brg 100652 - Span 3 - R2 - P1 | 0 | ST-POUR |  | H
A23920 | A23930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Cure Deck - Brg 100652 - Span 3 - R2 - P1 | Install Reinf Barrier - Brg 100652 - Span 3 - R2 - P1 | 0 |  | SUB-ST-REBAR | H
A23460 | A23780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Cure/Strip Cap - Brg 100652 - Pier 1 - R2 - P1 | Erect Girders - Brg 100652 - Span 2 - R2 - P1 | 0 |  | ST-BEAM | H
A23850 | A23580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Strip Overhangs - Brg 100652 - Span 2 - R2 - P1 | Slip Barrier - Brg 100652 - R2 - P1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A23840 | A23850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Install Reinf Barrier - Brg 100652 - Span 2 - R2 - P1 | Strip Overhangs - Brg 100652 - Span 2 - R2 - P1 | 0 | SUB-ST-REBAR | ST-DECK | H
A23790 | A23800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Install SIP - Brg 100652 - Span 2 - R2 - P1 | Install Overhangs - Brg 100652 - Span 2 - R2 - P1 | 0 | SUB-ST-SIP | ST-DECK | H
A23800 | A23810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Install Overhangs - Brg 100652 - Span 2 - R2 - P1 | Reinforce Deck - Brg 100652 - Span 2 - R2 - P1 | 0 | ST-DECK | SUB-ST-REBAR | H
A23810 | A23820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Reinforce Deck - Brg 100652 - Span 2 - R2 - P1 | Place Deck - Brg 100652 - Span 2 - R2 - P1 | 0 | SUB-ST-REBAR | ST-POUR | H
A23820 | A23830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Place Deck - Brg 100652 - Span 2 - R2 - P1 | Cure Deck - Brg 100652 - Span 2 - R2 - P1 | 0 | ST-POUR |  | H
A23830 | A23840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Cure Deck - Brg 100652 - Span 2 - R2 - P1 | Install Reinf Barrier - Brg 100652 - Span 2 - R2 - P1 | 0 |  | SUB-ST-REBAR | H
A23340 | A23470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Cure/Strip Abt Cap - Brg 100652 - End Bent 1 - R2 - P1 | Erect Girders - Brg 100652 - Span 1 - R2 - P1 | 0 |  | ST-BEAM | H
A23460 | A23470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Cure/Strip Cap - Brg 100652 - Pier 1 - R2 - P1 | Erect Girders - Brg 100652 - Span 1 - R2 - P1 | 0 |  | ST-BEAM | H
A23710 | A23720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Drive Pile - Brg 100652 - Pier 2 - R2 - P1 | FRP Footing - Brg 100652 - Pier 2 - R2 - P1 | 0 | ST-PILE | ST-FOOT | H
A23720 | A23730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | FRP Footing - Brg 100652 - Pier 2 - R2 - P1 | Cure/Strip Footing - Brg 100652 - Pier 2 - R2 - P1 | 0 | ST-FOOT |  | H
A23740 | A23750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | FRP Column - Brg 100652 - Pier 2 - R2 - P1 | Cure/Strip Column - Brg 100652 - Pier 2 - R2 - P1 | 0 | ST-COL |  | H
A23760 | A23770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | FRP Cap - Brg 100652 - Pier 2 - R2 - P1 | Cure/Strip Cap - Brg 100652 - Pier 2 - R2 - P1 | 0 | ST-CAP |  | H
A23730 | A23740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Cure/Strip Footing - Brg 100652 - Pier 2 - R2 - P1 | FRP Column - Brg 100652 - Pier 2 - R2 - P1 | 0 |  | ST-COL | H
A23750 | A23760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Cure/Strip Column - Brg 100652 - Pier 2 - R2 - P1 | FRP Cap - Brg 100652 - Pier 2 - R2 - P1 | 0 |  | ST-CAP | H
A23640 | A23670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Drive Pile - Brg 100652 - End Bent 2 - R2 - P1 | Const MSE Wall & Bkfill - RW 7-1 / Brg 100652 - End Bent 2 - R2 - P1 | 0 | ST-PILE | ST-MSE | H
A23650 | A23660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | FRP Abt Cap - Brg 100652 - End Bent 2 - R2 - P1 | Cure/Strip Abt Cap - Brg 100652 - End Bent 2 - R2 - P1 | 0 | ST-ABUT |  | H
A23600 | A23610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Groove Deck - Brg 100652 - R2 - P1 | Perm Striping - Brg 100652 - R2 - P1 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A23540 | A23580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Strip Overhangs - Brg 100652 - Span 1 - R2 - P1 | Slip Barrier - Brg 100652 - R2 - P1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A23510 | A23560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Place Deck - Brg 100652 - Span 1 - R2 - P1 | FRPS Approach Slab 1 - Brg 100652 - R2 - P1 | 0 | ST-POUR | ST-APPR | H
A23530 | A23540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Install Reinf Barrier - Brg 100652 - Span 1 - R2 - P1 | Strip Overhangs - Brg 100652 - Span 1 - R2 - P1 | 0 | SUB-ST-REBAR | ST-DECK | H
A23480 | A23490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Install SIP - Brg 100652 - Span 1 - R2 - P1 | Install Overhangs - Brg 100652 - Span 1 - R2 - P1 | 0 | SUB-ST-SIP | ST-DECK | H
A23490 | A23500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Install Overhangs - Brg 100652 - Span 1 - R2 - P1 | Reinforce Deck - Brg 100652 - Span 1 - R2 - P1 | 0 | ST-DECK | SUB-ST-REBAR | H
A23500 | A23510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Reinforce Deck - Brg 100652 - Span 1 - R2 - P1 | Place Deck - Brg 100652 - Span 1 - R2 - P1 | 0 | SUB-ST-REBAR | ST-POUR | H
A23510 | A23520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Place Deck - Brg 100652 - Span 1 - R2 - P1 | Cure Deck - Brg 100652 - Span 1 - R2 - P1 | 0 | ST-POUR |  | H
A23520 | A23530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Cure Deck - Brg 100652 - Span 1 - R2 - P1 | Install Reinf Barrier - Brg 100652 - Span 1 - R2 - P1 | 0 |  | SUB-ST-REBAR | H
A23400 | A23410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Drive Pile - Brg 100652 - Pier 1 - R2 - P1 | FRP Footing - Brg 100652 - Pier 1 - R2 - P1 | 0 | ST-PILE | ST-FOOT | H
A23410 | A23420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | FRP Footing - Brg 100652 - Pier 1 - R2 - P1 | Cure/Strip Footing - Brg 100652 - Pier 1 - R2 - P1 | 0 | ST-FOOT |  | H
A23430 | A23440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | FRP Column - Brg 100652 - Pier 1 - R2 - P1 | Cure/Strip Column - Brg 100652 - Pier 1 - R2 - P1 | 0 | ST-COL |  | H
A23450 | A23460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | FRP Cap - Brg 100652 - Pier 1 - R2 - P1 | Cure/Strip Cap - Brg 100652 - Pier 1 - R2 - P1 | 0 | ST-CAP |  | H
A23420 | A23430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Cure/Strip Footing - Brg 100652 - Pier 1 - R2 - P1 | FRP Column - Brg 100652 - Pier 1 - R2 - P1 | 0 |  | ST-COL | H
A23440 | A23450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Cure/Strip Column - Brg 100652 - Pier 1 - R2 - P1 | FRP Cap - Brg 100652 - Pier 1 - R2 - P1 | 0 |  | ST-CAP | H
A23320 | A23350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Drive Pile - Brg 100652 - End Bent 1 - R2 - P1 | Const MSE Wall & Bkfill - RW 7-2 / Brg 100652 - End Bent 1 - R2 - P1 | 0 | ST-PILE | ST-MSE | H
A23360 | A23300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Temp Wall or SOE - Brg 100652 - End Bent 1 - R2 - P1 | Grading - Brg 100652 - End Bent 1 - R2 - P1 | 0 | EW-STR | EW- ALL EW | H
A23330 | A23340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | FRP Abt Cap - Brg 100652 - End Bent 1 - R2 - P1 | Cure/Strip Abt Cap - Brg 100652 - End Bent 1 - R2 - P1 | 0 | ST-ABUT |  | H
A22490 | A22980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Install Temp Barrier - Ramp EN - R2 - P1 | Excavate - Brg 100650 - Pier 2 - R2 - P1 | 0 | SUB-TC-PCB | EW-STR | H
D1380 | A22480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.2 Right of Way | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | Owner Right Of Way Acquisition Complete / Clear Date (7/1/24) | Shift Traffic - Ramp EN Left - R2 - P1 | 0 |  | TC-Maint. | H
A23260 | A23270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Shoulder GAB - Ramp EN Sta 68 to 79 - R2 - P1 | Place Asphalt Shoulder - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | EW-ABC | SUB-ASPH | H
A23250 | A23260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Edge Drain - Ramp EN Sta 68 to 79 - R2 - P1 | Place Shoulder GAB - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | PIPE | EW-ABC | H
A22900 | A23250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Concrete Pav - Ramp EN Sta 68 to 79 - R2 - P1 | Place Edge Drain - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | CP-SLIP | PIPE | H
A22890 | A22900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Asphalt Base - Ramp EN Sta 68 to 79 - R2 - P1 | Place Concrete Pav - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | SUB-ASPH | CP-SLIP | H
A22850 | A22890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Wall Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | Place Asphalt Base - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A22860 | A22850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Junction Slab - Ramp EN Sta 68 to 79 - R2 - P1 | Place Wall Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-CIP | SUB-BR-SLIP | H
A22880 | A22860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Place Stabilization - Ramp EN Sta 68 to 79 - R2 - P1 | Place Junction Slab - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | EW-STAB | ST-CIP | H
A23200 | A22790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Place Deck - Brg 100650 - Span 3 - R2 - P1 | FRPS Approach Slab 2 - Brg 100650 - R2 - P1 | 0 | ST-POUR | ST-APPR | H
A22950 | A23160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Cure/Strip Abt Cap - Brg 100650 - End Bent 2 - R2 - P1 | Erect Girders - Brg 100650 - Span 3 - R2 - P1 | 0 |  | ST-BEAM | H
A23060 | A23160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Cure/Strip Cap - Brg 100650 - Pier 2 - R2 - P1 | Erect Girders - Brg 100650 - Span 3 - R2 - P1 | 0 |  | ST-BEAM | H
A23060 | A23070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Cure/Strip Cap - Brg 100650 - Pier 2 - R2 - P1 | Erect Girders - Brg 100650 - Span 2 - R2 - P1 | 0 |  | ST-BEAM | H
A23230 | A22800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Strip Overhangs - Brg 100650 - Span 3 - R2 - P1 | Slip Barrier - Brg 100650 - R2 - P1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A23220 | A23230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Install Reinf Barrier - Brg 100650 - Span 3 - R2 - P1 | Strip Overhangs - Brg 100650 - Span 3 - R2 - P1 | 0 | SUB-ST-REBAR | ST-DECK | H
A23170 | A23180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Install SIP - Brg 100650 - Span 3 - R2 - P1 | Install Overhangs - Brg 100650 - Span 3 - R2 - P1 | 0 | SUB-ST-SIP | ST-DECK | H
A23180 | A23190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Install Overhangs - Brg 100650 - Span 3 - R2 - P1 | Reinforce Deck - Brg 100650 - Span 3 - R2 - P1 | 0 | ST-DECK | SUB-ST-REBAR | H
A23190 | A23200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Reinforce Deck - Brg 100650 - Span 3 - R2 - P1 | Place Deck - Brg 100650 - Span 3 - R2 - P1 | 0 | SUB-ST-REBAR | ST-POUR | H
A23200 | A23210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Place Deck - Brg 100650 - Span 3 - R2 - P1 | Cure Deck - Brg 100650 - Span 3 - R2 - P1 | 0 | ST-POUR |  | H
A23210 | A23220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Cure Deck - Brg 100650 - Span 3 - R2 - P1 | Install Reinf Barrier - Brg 100650 - Span 3 - R2 - P1 | 0 |  | SUB-ST-REBAR | H
A22680 | A23070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Cure/Strip Cap - Brg 100650 - Pier 1 - R2 - P1 | Erect Girders - Brg 100650 - Span 2 - R2 - P1 | 0 |  | ST-BEAM | H
A23140 | A22800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Strip Overhangs - Brg 100650 - Span 2 - R2 - P1 | Slip Barrier - Brg 100650 - R2 - P1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A23130 | A23140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Install Reinf Barrier - Brg 100650 - Span 2 - R2 - P1 | Strip Overhangs - Brg 100650 - Span 2 - R2 - P1 | 0 | SUB-ST-REBAR | ST-DECK | H
A23080 | A23090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Install SIP - Brg 100650 - Span 2 - R2 - P1 | Install Overhangs - Brg 100650 - Span 2 - R2 - P1 | 0 | SUB-ST-SIP | ST-DECK | H
A23090 | A23100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Install Overhangs - Brg 100650 - Span 2 - R2 - P1 | Reinforce Deck - Brg 100650 - Span 2 - R2 - P1 | 0 | ST-DECK | SUB-ST-REBAR | H
A23100 | A23110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Reinforce Deck - Brg 100650 - Span 2 - R2 - P1 | Place Deck - Brg 100650 - Span 2 - R2 - P1 | 0 | SUB-ST-REBAR | ST-POUR | H
A23110 | A23120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Place Deck - Brg 100650 - Span 2 - R2 - P1 | Cure Deck - Brg 100650 - Span 2 - R2 - P1 | 0 | ST-POUR |  | H
A23120 | A23130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Cure Deck - Brg 100650 - Span 2 - R2 - P1 | Install Reinf Barrier - Brg 100650 - Span 2 - R2 - P1 | 0 |  | SUB-ST-REBAR | H
A22560 | A22690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Cure/Strip Abt Cap - Brg 100650 - End Bent 1 - R2 - P1 | Erect Girders - Brg 100650 - Span 1 - R2 - P1 | 0 |  | ST-BEAM | H
A22680 | A22690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Cure/Strip Cap - Brg 100650 - Pier 1 - R2 - P1 | Erect Girders - Brg 100650 - Span 1 - R2 - P1 | 0 |  | ST-BEAM | H
A23000 | A23010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Drive Pile - Brg 100650 - Pier 2 - R2 - P1 | FRP Footing - Brg 100650 - Pier 2 - R2 - P1 | 0 | ST-PILE | ST-FOOT | H
A23010 | A23020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | FRP Footing - Brg 100650 - Pier 2 - R2 - P1 | Cure/Strip Footing - Brg 100650 - Pier 2 - R2 - P1 | 0 | ST-FOOT |  | H
A23030 | A23040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | FRP Column - Brg 100650 - Pier 2 - R2 - P1 | Cure/Strip Column - Brg 100650 - Pier 2 - R2 - P1 | 0 | ST-COL |  | H
A23050 | A23060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | FRP Cap - Brg 100650 - Pier 2 - R2 - P1 | Cure/Strip Cap - Brg 100650 - Pier 2 - R2 - P1 | 0 | ST-CAP |  | H
A23020 | A23030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Cure/Strip Footing - Brg 100650 - Pier 2 - R2 - P1 | FRP Column - Brg 100650 - Pier 2 - R2 - P1 | 0 |  | ST-COL | H
A23040 | A23050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Cure/Strip Column - Brg 100650 - Pier 2 - R2 - P1 | FRP Cap - Brg 100650 - Pier 2 - R2 - P1 | 0 |  | ST-CAP | H
A22930 | A22960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Drive Pile - Brg 100650 - End Bent 2 - R2 - P1 | Const MSE Wall & Bkfill - RW 6-1 / Brg 6 100650 - End Bent 2- R2 - P1 | 0 | ST-PILE | ST-MSE | H
A22940 | A22950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | FRP Abt Cap - Brg 100650 - End Bent 2 - R2 - P1 | Cure/Strip Abt Cap - Brg 100650 - End Bent 2 - R2 - P1 | 0 | ST-ABUT |  | H
A22870 | A22840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 1 | 0 | EW-SML | ST-MSE | H
A22820 | A22830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Groove Deck - Brg 100650 - R2 - P1 | Perm Striping - Brg 100650 - R2 - P1 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A22760 | A22800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Strip Overhangs - Brg 100650 - Span 1 - R2 - P1 | Slip Barrier - Brg 100650 - R2 - P1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A22730 | A22780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Place Deck - Brg 100650 - Span 1 - R2 - P1 | FRPS Approach Slab 1 - Brg 100650 - R2 - P1 | 0 | ST-POUR | ST-APPR | H
A22750 | A22760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Install Reinf Barrier - Brg 100650 - Span 1 - R2 - P1 | Strip Overhangs - Brg 100650 - Span 1 - R2 - P1 | 0 | SUB-ST-REBAR | ST-DECK | H
A22700 | A22710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Install SIP - Brg 100650 - Span 1 - R2 - P1 | Install Overhangs - Brg 100650 - Span 1 - R2 - P1 | 0 | SUB-ST-SIP | ST-DECK | H
A22710 | A22720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Install Overhangs - Brg 100650 - Span 1 - R2 - P1 | Reinforce Deck - Brg 100650 - Span 1 - R2 - P1 | 0 | ST-DECK | SUB-ST-REBAR | H
A22720 | A22730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Reinforce Deck - Brg 100650 - Span 1 - R2 - P1 | Place Deck - Brg 100650 - Span 1 - R2 - P1 | 0 | SUB-ST-REBAR | ST-POUR | H
A22730 | A22740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Place Deck - Brg 100650 - Span 1 - R2 - P1 | Cure Deck - Brg 100650 - Span 1 - R2 - P1 | 0 | ST-POUR |  | H
A22740 | A22750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Cure Deck - Brg 100650 - Span 1 - R2 - P1 | Install Reinf Barrier - Brg 100650 - Span 1 - R2 - P1 | 0 |  | SUB-ST-REBAR | H
A22620 | A22630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Drive Pile - Brg 100650 - Pier 1 - R2 - P1 | FRP Footing - Brg 100650 - Pier 1 - R2 - P1 | 0 | ST-PILE | ST-FOOT | H
A22630 | A22640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | FRP Footing - Brg 100650 - Pier 1 - R2 - P1 | Cure/Strip Footing - Brg 100650 - Pier 1 - R2 - P1 | 0 | ST-FOOT |  | H
A22650 | A22660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | FRP Column - Brg 100650 - Pier 1 - R2 - P1 | Cure/Strip Column - Brg 100650 - Pier 1 - R2 - P1 | 0 | ST-COL |  | H
A22670 | A22680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | FRP Cap - Brg 100650 - Pier 1 - R2 - P1 | Cure/Strip Cap - Brg 100650 - Pier 1 - R2 - P1 | 0 | ST-CAP |  | H
A22640 | A22650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Cure/Strip Footing - Brg 100650 - Pier 1 - R2 - P1 | FRP Column - Brg 100650 - Pier 1 - R2 - P1 | 0 |  | ST-COL | H
A22660 | A22670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Cure/Strip Column - Brg 100650 - Pier 1 - R2 - P1 | FRP Cap - Brg 100650 - Pier 1 - R2 - P1 | 0 |  | ST-CAP | H
A22580 | A22520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Temp Wall or SOE - Brg 100650 - End Bent 1 - R2 - P1 | Grading - Brg 100650 - End Bent 1 - R2 - P1 | 0 | EW-STR | EW- ALL EW | H
A22490 | A22580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Install Temp Barrier - Ramp EN - R2 - P1 | Temp Wall or SOE - Brg 100650 - End Bent 1 - R2 - P1 | 0 | SUB-TC-PCB | EW-STR | H
A22550 | A22560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | FRP Abt Cap - Brg 100650 - End Bent 1 - R2 - P1 | Cure/Strip Abt Cap - Brg 100650 - End Bent 1 - R2 - P1 | 0 | ST-ABUT |  | H
A22480 | A22490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | Shift Traffic - Ramp EN Left - R2 - P1 | Install Temp Barrier - Ramp EN - R2 - P1 | 0 | TC-Maint. | SUB-TC-PCB | H
A22470 | A22350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.5 R2 - Ph2, Stp3 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.1.5 R2 - Ph2, Stp3 - MOT | Remove MOT - I-4 WB & I-275 NB - R2 - P2 | Shift Traffic - I-4 Right; I-275 Traffic Right - R1 - P2 | 0 | TC-Maint. | TC-Maint. | H
A22440 | A22450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place Asphalt Shoulder - Ramp EN /I-4 - R2 - P2 | Install Guardrail - Ramp EN /I-4 - R2 - P2 | 0 | SUB-ASPH | SUB-GRAIL | H
A22420 | A22430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place Stabilization - Ramp EN / I-4 - R2 - P2 | Place Shoulder GAB - Ramp EN /I-4 - R2 - P2 | 0 | EW-STAB | EW-ABC | H
A22460 | A22420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place 3-Pour Barrier - Ramp EN / I-4 - R2 - P2 | Place Stabilization - Ramp EN / I-4 - R2 - P2 | 0 | SUB-BR-SLIP | EW-STAB | H
A22410 | A22460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Grading - Ramp EN /I-4 - R2 - P2 | Place 3-Pour Barrier - Ramp EN / I-4 - R2 - P2 | 0 | EW- ALL EW | SUB-BR-SLIP | H
A22430 | A22440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Place Shoulder GAB - Ramp EN /I-4 - R2 - P2 | Place Asphalt Shoulder - Ramp EN /I-4 - R2 - P2 | 0 | EW-ABC | SUB-ASPH | H
A22270 | A22320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.5.2 R2 - Ph0 - Ramp EN, I-4 WB - Temp Pavement - Sta. 82 to 95 | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | Place Temp Asphalt - Ramp EN /I-4 Sta 91 to 101 - R2 - P1 | 0 | TC-Maint. | SUB-ASPH | H
A16490 | A22260 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | Start Construction - R2 | Install MOT - Ramp EN /I-4 - R2 - P1.S1 | 0 |  | TC-Maint. | H
A22320 | A22330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.2 R2 - Ph0 - Ramp EN, I-4 WB - Temp Pavement - Sta. 82 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.5.2 R2 - Ph0 - Ramp EN, I-4 WB - Temp Pavement - Sta. 82 to 95 | Place Temp Asphalt - Ramp EN /I-4 Sta 91 to 101 - R2 - P1 | Temp Striping - Ramp EN /I-4 Sta 91 to 101 - R2 - P1 | 0 | SUB-ASPH | SUB-STRIP | H
A22260 | A22270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.5.4 R2 - Ph0 - MOT | Install MOT - Ramp EN /I-4 - R2 - P1.S1 | Shift Traffic - Ramp EN Left I-4 Traffic Right - R2 - P1.S1 | 0 | TC-Maint. | TC-Maint. | H
A16360 | A22240 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt - Pond SMF 4A Shared Use Path - R2 - P0 | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | 0 | SUB-ASPH |  | H
A22200 | LoE170 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 3 - R1 - Resurface Signs Markings | R1 Phase 3 - Resurface / Signs / Markings [LoE] | 0 |  |  | H
A20300 | LoE170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | R1 Phase 3 - Resurface / Signs / Markings [LoE] | 0 |  |  | H
A20300 | LoE160 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | R1 Phase 2 Stage 3 - Up-St Ramp NE Left Construction [LoE] | 0 |  |  | H
A20290 | LoE160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right | R1 Phase 2 Stage 3 - Up-St Ramp NE Left Construction [LoE] | 0 |  |  | H
A20290 | LoE150 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right | R1 Phase 2 Stage 2 - Up-St Ramp NE Right Construction [LoE] | 0 |  |  | H
A15920 | LoE140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | R1 Phase 1 Stage 2 - Dn-St Ramp NE / I-4 Widening [LoE] | 0 |  |  | H
A17500 | LoE140 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | R1 Phase 1 Stage 2 - Dn-St Ramp NE / I-4 Widening [LoE] | 0 |  |  | H
A15910 | A16640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Finish Phase 1 Stage 1 - R1 - 13th Ave | Remove Temp Barrier - Ramp WE-B - R1 - P1.S2 | 0 |  | SUB-TC-PCB | H
A15910 | LoE120 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 1 Stage 1 - R1 - 13th Ave | R1 Phase 1 Stage 1 - 13th Ave Construction [LoE] | 0 |  |  | H
A1050 | LoE120 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Start Construction - R1 | R1 Phase 1 Stage 1 - 13th Ave Construction [LoE] | 0 |  |  | H
A15920 | LoE110 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | R1 Phase 1 Stage 1 - Ramp WE-B / Dn-St Ramp NE Construction [LoE] | 0 |  |  | H
A1050 | LoE110 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Start Construction - R1 | R1 Phase 1 Stage 1 - Ramp WE-B / Dn-St Ramp NE Construction [LoE] | 0 |  |  | H
A16370 | A16360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place Curb - Pond SMF 4A Shared Use Path - R2 - P0 | Place Asphalt - Pond SMF 4A Shared Use Path - R2 - P0 | 0 | FLATWORK | SUB-ASPH | H
A22230 | A16370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place GAB - Pond SMF 4A Shared Use Path - R2 - P0 | Place Curb - Pond SMF 4A Shared Use Path - R2 - P0 | 0 | EW-ABC | FLATWORK | H
A16350 | A22230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Place Stabilization - Pond SMF 4A Shared Use Path - R2 - P0 | Place GAB - Pond SMF 4A Shared Use Path - R2 - P0 | 0 | EW-STAB | EW-ABC | H
A22200 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Finish Phase 3 - R1 - Resurface Signs Markings | Substantial Completion (Sept. 4th, 2026) | 0 |  |  | H
A22210 | A22200 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Perm. Signs - R1 - P3 | Finish Phase 3 - R1 - Resurface Signs Markings | 0 | SUB-SIGN |  | H
A22220 | A22200 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - R1 - P3 | Finish Phase 3 - R1 - Resurface Signs Markings | 0 | SUB-STRIP |  | H
A20300 | A22190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | Mill / Resurface Asphalt - R1 - P3 | 0 |  | SUB-ASPH | H
A22190 | A22220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | Mill / Resurface Asphalt - R1 - P3 | Perm Striping - R1 - P3 | 0 | SUB-ASPH | SUB-STRIP | H
A22130 | A22140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Stabilization - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place Asphalt Base - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | EW-STAB | SUB-ASPH | H
A22100 | A22130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place 3-Pour Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place Stabilization - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | SUB-BR-SLIP | EW-STAB | H
A22120 | A22100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place 3-Pour Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | EW-SML | SUB-BR-SLIP | H
A21450 | A22120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | ST-MSE | EW-SML | H
A22170 | A22180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Shoulder GAB - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place Asphalt Shoulder - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | EW-ABC | SUB-ASPH | H
A22160 | A22170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place Shoulder GAB - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | PIPE | EW-ABC | H
A22150 | A22160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Concrete Pav - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | CP-SLIP | PIPE | H
A22140 | A22150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Asphalt Base - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Place Concrete Pav - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | SUB-ASPH | CP-SLIP | H
A21990 | A22030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | ST-MSE | EW-STAB | H
A21370 | A22020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S2 - right | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | ST-MSE | EW-SML | H
A22070 | A22080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Shoulder GAB - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Asphalt Shoulder - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | EW-ABC | SUB-ASPH | H
A22060 | A22070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Shoulder GAB - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | PIPE | EW-ABC | H
A22050 | A22060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Concrete Pav - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | CP-SLIP | PIPE | H
A22040 | A22050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Asphalt Base - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Concrete Pav - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | SUB-ASPH | CP-SLIP | H
A22000 | A22040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Asphalt Base - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | SUB-BR-SLIP | SUB-ASPH | H
A22010 | A22000 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 8 | ST-CIP | SUB-BR-SLIP | H
A22030 | A22010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | EW-STAB | ST-CIP | H
A22020 | A21990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | EW-SML | ST-MSE | H
A21680 | A21690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Slip Barrier - Brg 100864 - R1 - P2.S2 | Grind Deck - Brg 100864 - R1 - P2.S2 | 0 | SUB-ST-PARAPET | SUB-DGRIND | H
A21360 | A21570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Cure/Strip Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S2 | 0 |  | ST-BEAM | H
A21620 | A21690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S2 | Grind Deck - Brg 100864 - R1 - P2.S2 | 0 |  | SUB-DGRIND | H
A21700 | A21710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Groove Deck - Brg 100864 - R1 - P2.S2 | Perm Striping - Brg 100864 - R1 - P2.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A21670 | A21690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | FRPS Approach Slab 2 - Brg 100864 - R1 - P2.S2 | Grind Deck - Brg 100864 - R1 - P2.S2 | 0 | ST-APPR | SUB-DGRIND | H
A21640 | A21680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Strip Overhangs - Brg 100864 - Span 1 - R1 - P2.S2 | Slip Barrier - Brg 100864 - R1 - P2.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A21610 | A21660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Place Deck - Brg 100864 - Span 1 - R1 - P2.S2 | FRPS Approach Slab 1 - Brg 100864 - R1 - P2.S2 | 0 | ST-POUR | ST-APPR | H
A21690 | A21700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Grind Deck - Brg 100864 - R1 - P2.S2 | Groove Deck - Brg 100864 - R1 - P2.S2 | 0 | SUB-DGRIND | SUB-ST-GROOVE | H
A21660 | A21690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | FRPS Approach Slab 1 - Brg 100864 - R1 - P2.S2 | Grind Deck - Brg 100864 - R1 - P2.S2 | 0 | ST-APPR | SUB-DGRIND | H
A21630 | A21640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Install Reinf Barrier - Brg 100864 - Span 1 - R1 - P2.S2 | Strip Overhangs - Brg 100864 - Span 1 - R1 - P2.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A21580 | A21590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Install SIP - Brg 100864 - Span 1 - R1 - P2.S2 | Install Overhangs - Brg 100864 - Span 1 - R1 - P2.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A21590 | A21600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Install Overhangs - Brg 100864 - Span 1 - R1 - P2.S2 | Reinforce Deck - Brg 100864 - Span 1 - R1 - P2.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A21600 | A21610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Reinforce Deck - Brg 100864 - Span 1 - R1 - P2.S2 | Place Deck - Brg 100864 - Span 1 - R1 - P2.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A21610 | A21620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Place Deck - Brg 100864 - Span 1 - R1 - P2.S2 | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S2 | 0 | ST-POUR |  | H
A21620 | A21630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S2 | Install Reinf Barrier - Brg 100864 - Span 1 - R1 - P2.S2 | 0 |  | SUB-ST-REBAR | H
A21310 | A21460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.10 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Demo Substructure - Brg 100864 - R1 - P2.S2 - right | Temp Wall or SOE - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 | DM-BRIDGE | EW-STR | H
A21420 | A21450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 | ST-PILE | ST-MSE | H
A21460 | A21400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Temp Wall or SOE - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | Grading - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 | EW-STR | EW- ALL EW | H
A21430 | A21440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | FRP Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | Cure/Strip Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 | ST-ABUT |  | H
A21310 | A21380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.10 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Demo Substructure - Brg 100864 - R1 - P2.S2 - right | Temp Wall or SOE - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 | DM-BRIDGE | EW-STR | H
A21340 | A21370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 | ST-PILE | ST-MSE | H
A21380 | A21320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Temp Wall or SOE - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | Grading - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 | EW-STR | EW- ALL EW | H
A21350 | A21360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | FRP Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | Cure/Strip Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 | ST-ABUT |  | H
A21300 | A21310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.10 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | I-275 - I-4 - IBL(all) - B1.2.2.11.10 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | Demo Superstructure - Brg 100864 - R1 - P2.S2 - right | Demo Substructure - Brg 100864 - R1 - P2.S2 - right | 0 | DM-BRIDGE | DM-BRIDGE | H
A21250 | A21260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Place GAB - NE Shared Use Path - R1 - P2.S3 | Place Curb - NE Shared Use Path - R1 - P2.S3 | 0 | EW-ABC | FLATWORK | H
A21230 | A21250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Place Stabilization - NE Shared Use Path - R1 - P2.S3 | Place GAB - NE Shared Use Path - R1 - P2.S3 | 0 | EW-STAB | EW-ABC | H
A20450 | A21110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S3 - left | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | ST-MSE | EW-SML | H
A21190 | A21200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Shoulder GAB - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Asphalt Shoulder - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | EW-ABC | SUB-ASPH | H
A21180 | A21190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Shoulder GAB - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | PIPE | EW-ABC | H
A21170 | A21180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Concrete Pav - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | CP-SLIP | PIPE | H
A21160 | A21170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Asphalt Base - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Concrete Pav - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | SUB-ASPH | CP-SLIP | H
A21150 | A21160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Wall Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Asphalt Base - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | SUB-BR-SLIP | SUB-ASPH | H
A21140 | A21150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Junction Slab - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Wall Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | ST-CIP | SUB-BR-SLIP | H
A21130 | A21140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Stabilization - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Junction Slab - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | EW-STAB | ST-CIP | H
A21010 | A21030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | ST-MSE | EW-STAB | H
A20370 | A21000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S3 - left | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | ST-MSE | EW-SML | H
A21090 | A21100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Shoulder GAB - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Asphalt Shoulder - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | EW-ABC | SUB-ASPH | H
A21080 | A21090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Shoulder GAB - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | PIPE | EW-ABC | H
A21070 | A21080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Concrete Pav - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | CP-SLIP | PIPE | H
A21060 | A21070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Asphalt Base - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Concrete Pav - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | SUB-ASPH | CP-SLIP | H
A21050 | A21060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Asphalt Base - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | SUB-BR-SLIP | SUB-ASPH | H
A21040 | A21050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Wall Barrier - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | ST-CIP | SUB-BR-SLIP | H
A21030 | A21040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Place Junction Slab - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | EW-STAB | ST-CIP | H
A21000 | A21010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Const MSE Wall & Bkfill - RW 1-1 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | EW-SML | ST-MSE | H
A14880 | A14910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Slip Barrier - Brg 100865 - R1 - P1.S1 | Grind Deck - Brg 100865 - R1 - P1.S1 | 0 | SUB-ST-PARAPET | SUB-DGRIND | H
A20690 | A20700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Slip Barrier - Brg 100864 - R1 - P2.S3 | Grind Deck - Brg 100864 - R1 - P2.S3 | 0 | SUB-ST-PARAPET | SUB-DGRIND | H
A20400 | A20580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Cure/Strip Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S3 | 0 |  | ST-BEAM | H
A20630 | A20700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S3 | Grind Deck - Brg 100864 - R1 - P2.S3 | 0 |  | SUB-DGRIND | H
A20710 | A20720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Groove Deck - Brg 100864 - R1 - P2.S3 | Perm Striping - Brg 100864 - R1 - P2.S3 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A20680 | A20700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | FRPS Approach Slab 2 - Brg 100864 - R1 - P2.S3 | Grind Deck - Brg 100864 - R1 - P2.S3 | 0 | ST-APPR | SUB-DGRIND | H
A20650 | A20690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Strip Overhangs - Brg 100864 - Span 1 - R1 - P2.S3 | Slip Barrier - Brg 100864 - R1 - P2.S3 | 0 | ST-DECK | SUB-ST-PARAPET | H
A20620 | A20670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Place Deck - Brg 100864 - Span 1 - R1 - P2.S3 | FRPS Approach Slab 1 - Brg 100864 - R1 - P2.S3 | 0 | ST-POUR | ST-APPR | H
A20700 | A20710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Grind Deck - Brg 100864 - R1 - P2.S3 | Groove Deck - Brg 100864 - R1 - P2.S3 | 0 | SUB-DGRIND | SUB-ST-GROOVE | H
A20670 | A20700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | FRPS Approach Slab 1 - Brg 100864 - R1 - P2.S3 | Grind Deck - Brg 100864 - R1 - P2.S3 | 0 | ST-APPR | SUB-DGRIND | H
A20640 | A20650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Install Reinf Barrier - Brg 100864 - Span 1 - R1 - P2.S3 | Strip Overhangs - Brg 100864 - Span 1 - R1 - P2.S3 | 0 | SUB-ST-REBAR | ST-DECK | H
A20590 | A20600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Install SIP - Brg 100864 - Span 1 - R1 - P2.S3 | Install Overhangs - Brg 100864 - Span 1 - R1 - P2.S3 | 0 | SUB-ST-SIP | ST-DECK | H
A20600 | A20610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Install Overhangs - Brg 100864 - Span 1 - R1 - P2.S3 | Reinforce Deck - Brg 100864 - Span 1 - R1 - P2.S3 | 0 | ST-DECK | SUB-ST-REBAR | H
A20610 | A20620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Reinforce Deck - Brg 100864 - Span 1 - R1 - P2.S3 | Place Deck - Brg 100864 - Span 1 - R1 - P2.S3 | 0 | SUB-ST-REBAR | ST-POUR | H
A20620 | A20630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Place Deck - Brg 100864 - Span 1 - R1 - P2.S3 | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S3 | 0 | ST-POUR |  | H
A20630 | A20640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Cure Deck - Brg 100864 - Span 1 - R1 - P2.S3 | Install Reinf Barrier - Brg 100864 - Span 1 - R1 - P2.S3 | 0 |  | SUB-ST-REBAR | H
A20320 | A20410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.10 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Demo Substructure - Brg 100864 - R1 - P2.S3 - left | Temp Wall or SOE - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 | DM-BRIDGE | EW-STR | H
A20440 | A20450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | Const MSE Wall & Bkfill - RW 1-1 / Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 | ST-PILE | ST-MSE | H
A20410 | A20420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Temp Wall or SOE - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | Grading - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 | EW-STR | EW- ALL EW | H
A20470 | A20480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | FRP Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | Cure/Strip Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 | ST-ABUT |  | H
A20320 | A20330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.10 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Demo Substructure - Brg 100864 - R1 - P2.S3 - left | Temp Wall or SOE - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 | DM-BRIDGE | EW-STR | H
A20360 | A20370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | Const MSE Wall & Bkfill - RW 1-2 / Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 | ST-PILE | ST-MSE | H
A20330 | A20340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Temp Wall or SOE - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | Grading - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 | EW-STR | EW- ALL EW | H
A20390 | A20400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | FRP Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | Cure/Strip Abt Cap - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 | ST-ABUT |  | H
A20310 | A20320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.10 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | I-275 - I-4 - IBL(all) - B1.2.2.6.10 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | Demo Superstructure - Brg 100864 - R1 - P2.S3 - left | Demo Substructure - Brg 100864 - R1 - P2.S3 - left | 0 | DM-BRIDGE | DM-BRIDGE | H
A20240 | A20250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Place GAB - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | Place Asphalt - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 0 | EW-ABC | SUB-ASPH | H
A20230 | A20240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Place Stabilization - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | Place GAB - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 0 | EW-STAB | EW-ABC | H
A20260 | A20270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.5 R1 - Ph2, Stg3, Step2 - MOT | Temp Striping - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | Shift Traffic - Ramp NE Right - R1 - P2.S3 Step 2 | 0 | SUB-STRIP | TC-Maint. | H
A20210 | A20220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.4 R1 - Ph2, Stg3, Step1 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Shift Traffic - Ramp NE Left - R1 - P2.S3 Step 1 | Grading - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 0 | TC-Maint. | EW- ALL EW | H
A20250 | A20260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Place Asphalt - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | Temp Striping - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 0 | SUB-ASPH | SUB-STRIP | H
A20220 | A20230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.6 R1 - Ph2, Stg3, Step1 - Ramp NE - Right Temp Pavement - Sta. 126 to 131 | Grading - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | Place Stabilization - Ramp NE Temp Pav Sta 126 to 131 - R1 - P2.S3 - right | 0 | EW- ALL EW | EW-STAB | H
A20200 | A20210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.4 R1 - Ph2, Stg3, Step1 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.6.4 R1 - Ph2, Stg3, Step1 - MOT | Install MOT - Ramp NE Left - R1 - P2.S3 Step 1 | Shift Traffic - Ramp NE Left - R1 - P2.S3 Step 1 | 0 | TC-Maint. | TC-Maint. | H
A18340 | A18350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Grading - 13th Ave - Right Sta 24 to 40 - R1 - P1.S2 | Place Stabilization - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 0 | EW- ALL EW | EW-STAB | H
A18360 | A18370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place GAB - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | Place Curb - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 0 | EW-ABC | FLATWORK | H
A18350 | A18360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place Stabilization - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | Place GAB - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 0 | EW-STAB | EW-ABC | H
A18330 | A1100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | Place GAB - 13th Ave Temp Pav - R1 - P0 | Place Asphalt - 13th Ave Temp Pav - R1 - P0 | 0 | EW-ABC | SUB-ASPH | H
A1090 | A18330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | Place Stabilization - 13th Ave Temp Pav - R1 - P0 | Place GAB - 13th Ave Temp Pav - R1 - P0 | 0 | EW-STAB | EW-ABC | H
A1050 | A18290 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Start Construction - R1 | Demo Existing Slope Pavement - Right 14th &15th St under I-4 - R1 - P1.S1 | 0 |  | DM-BRIDGE | H
A18320 | A16290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Brick Sidewalk - Right 14th & 15th St under I-4 - R1 - P1.S1 | Install Fencing - 13th Ave - R1 - P1.S1 | 0 | FLATWORK | SUB-FENCE | H
A18300 | A18320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Right 14th & 15th St under I-4 - R1 - P1.S1 | Place Brick Sidewalk - Right 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-CURB | FLATWORK | H
A18310 | A18300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Const Gravity Wall - Right 14th & 15th St under I-4 - R1 - P1.S1 | Form / Pour Slope Pavement - Right 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-CURB | H
A18290 | A18310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Right 14th &15th St under I-4 - R1 - P1.S1 | Const Gravity Wall - Right 14th & 15th St under I-4 - R1 - P1.S1 | 0 | DM-BRIDGE | SUB-BR-SLIP | H
A16260 | A16270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Left 14th & 15th St under I-4 - R1 - P1.S1 | Place Brick Sidewalk - Left 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-CURB | FLATWORK | H
A16280 | A16260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Const Gravity Wall - Left 14th & 15th St under I-4 - R1 - P1.S1 | Form / Pour Slope Pavement - Left 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-CURB | H
A16250 | A16280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Left 14th &15th St under I-4 - R1 - P1.S1 | Const Gravity Wall - Left 14th & 15th St under I-4 - R1 - P1.S1 | 0 | DM-BRIDGE | SUB-BR-SLIP | H
A18280 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - I-4 Sta 250 to 266 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 | SUB-ASPH |  | H
A17670 | A18200 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | FRPS Approach Slab 2 - Brg 100657 - R1 - P1.S2 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | ST-APPR | EW-SML | H
A17660 | A18200 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | FRPS Approach Slab 1 - Brg 100657 - R1 - P1.S2 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | ST-APPR | EW-SML | H
A16860 | A18200 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | FRPS Approach Slab 1 - Brg 100656 - R1 - P1.S2 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | ST-APPR | EW-SML | H
A16870 | A18200 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | FRPS Approach Slab 2 - Brg 100656 - R1 - P1.S2 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | ST-APPR | EW-SML | H
A18200 | A18210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | Place Stabilization - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | EW-SML | EW-STAB | H
A18270 | A18280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Shoulder GAB - I-4 Sta 250 to 266 - R1 - P1.S2 | Place Asphalt Shoulder - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | EW-ABC | SUB-ASPH | H
A18260 | A18270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Edge Drain - I-4 Sta 250 to 266 - R1 - P1.S2 | Place Shoulder GAB - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | PIPE | EW-ABC | H
A18250 | A18260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Concrete Pav - I-4 Sta 250 to 266 - R1 - P1.S2 | Place Edge Drain - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | CP-SLIP | PIPE | H
A18240 | A18250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Asphalt Base - I-4 Sta 250 to 266 - R1 - P1.S2 | Place Concrete Pav - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | SUB-ASPH | CP-SLIP | H
A17710 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - Brg 100657 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 | SUB-STRIP |  | H
A18170 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Column - Brg 100657 - End Bent 2 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 |  |  | H
A18190 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Column - Brg 100657 - End Bent 1 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 |  |  | H
A18000 | A18180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Cure/Strip Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | FRP Brick Column - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 |  | ST-BRIDGE-ALL | H
A18180 | A18190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | FRP Brick Column - Brg 100657 - End Bent 1 - R1 - P1.S2 | Cure/Strip Column - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | ST-BRIDGE-ALL |  | H
A18080 | A18160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Cure/Strip Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | FRP Brick Column - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 |  | ST-BRIDGE-ALL | H
A18160 | A18170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | FRP Brick Column - Brg 100657 - End Bent 2 - R1 - P1.S2 | Cure/Strip Column - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | ST-BRIDGE-ALL |  | H
A17680 | A18150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Slip Barrier - Brg 100657 - R1 - P1.S2 | Install Fiberglass Panel on Barrier - Brg 100657 - R1 - P1.S2 | 0 | SUB-ST-PARAPET | SUB-ST-RAILING | H
A16660 | A17900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Install Temp Barrier - I-4 - R1 - P1.S2 | Excavate - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A16660 | A17510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Install Temp Barrier - I-4 - R1 - P1.S2 | Excavate - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A18120 | A17720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.7 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Demo | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Demo Barrier - Brg 100657 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A18120 | A17810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.7 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Demo | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Demo Barrier - Brg 100657 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A18120 | A17570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.7 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Demo | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Demo Barrier - Brg 100657 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A16660 | A18120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.12.7 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Demo | Install Temp Barrier - I-4 - R1 - P1.S2 | Demo Barrier - Brg 100657 - R1 - P1.S2 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A17950 | A17720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Cure/Strip Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 2 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17950 | A17810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Cure/Strip Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 3 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A18080 | A17810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Cure/Strip Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 3 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A16660 | A18110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Install Temp Barrier - I-4 - R1 - P1.S2 | Temp Wall or SOE - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A18040 | A18140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Grading - Brg 100657 - End Bent 2 - R1 - P1.S2 | Demo Brick tower - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A17960 | A18130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Grading - Brg 100657 - End Bent 1 - R1 - P1.S2 | Demo Brick tower - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A18110 | A18040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Temp Wall or SOE - Brg 100657 - End Bent 2 - R1 - P1.S2 | Grading - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A18060 | A18090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Drive Pile - Brg 100657 - End Bent 2 - R1 - P1.S2 | Const MSE Wall & Bkfill - RW 4-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A18070 | A18080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | FRP Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | Cure/Strip Abt Cap - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | ST-ABUT |  | H
A18000 | A17570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Cure/Strip Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 1 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A18030 | A17960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Temp Wall or SOE - Brg 100657 - End Bent 1 - R1 - P1.S2 | Grading - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A16660 | A18030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Install Temp Barrier - I-4 - R1 - P1.S2 | Temp Wall or SOE - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A17980 | A18010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Drive Pile - Brg 100657 - End Bent 1 - R1 - P1.S2 | Const MSE Wall & Bkfill - RW 4-1 / Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A17990 | A18000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | FRP Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | Cure/Strip Abt Cap - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | ST-ABUT |  | H
A17910 | A17920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Drive Pile - Brg 100657 - Pier 2 - R1 - P1.S2 | FRP Column - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 | ST-PILE | ST-COL | H
A17900 | A17910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Excavate - Brg 100657 - Pier 2 - R1 - P1.S2 | Drive Pile - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 | EW-STR | ST-PILE | H
A17920 | A17930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | FRP Column - Brg 100657 - Pier 2 - R1 - P1.S2 | Cure/Strip Column - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 | ST-COL |  | H
A17940 | A17950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | FRP Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | Cure/Strip Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 | ST-CAP |  | H
A17930 | A17940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.8 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 2 | Cure/Strip Column - Brg 100657 - Pier 2 - R1 - P1.S2 | FRP Cap - Brg 100657 - Pier 2 - R1 - P1.S2 | 0 |  | ST-CAP | H
A17520 | A17530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Drive Pile - Brg 100657 - Pier 1 - R1 - P1.S2 | FRP Column - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 | ST-PILE | ST-COL | H
A17850 | A17670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Place Deck - Brg 100657 - Span 3 - R1 - P1.S2 | FRPS Approach Slab 2 - Brg 100657 - R1 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A17880 | A17680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Strip Overhangs - Brg 100657 - Span 3 - R1 - P1.S2 | Slip Barrier - Brg 100657 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A17870 | A17880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Install Reinf Barrier - Brg 100657 - Span 3 - R1 - P1.S2 | Strip Overhangs - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A17820 | A17830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Install SIP - Brg 100657 - Span 3 - R1 - P1.S2 | Install Overhangs - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A17830 | A17840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Install Overhangs - Brg 100657 - Span 3 - R1 - P1.S2 | Reinforce Deck - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A17840 | A17850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Reinforce Deck - Brg 100657 - Span 3 - R1 - P1.S2 | Place Deck - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A17850 | A17860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Place Deck - Brg 100657 - Span 3 - R1 - P1.S2 | Cure Deck - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | ST-POUR |  | H
A17860 | A17870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Cure Deck - Brg 100657 - Span 3 - R1 - P1.S2 | Install Reinf Barrier - Brg 100657 - Span 3 - R1 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A17560 | A17720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Cure/Strip Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 2 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17790 | A17680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Strip Overhangs - Brg 100657 - Span 2 - R1 - P1.S2 | Slip Barrier - Brg 100657 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A17780 | A17790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Install Reinf Barrier - Brg 100657 - Span 2 - R1 - P1.S2 | Strip Overhangs - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A17730 | A17740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Install SIP - Brg 100657 - Span 2 - R1 - P1.S2 | Install Overhangs - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A17740 | A17750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Install Overhangs - Brg 100657 - Span 2 - R1 - P1.S2 | Reinforce Deck - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A17750 | A17760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Reinforce Deck - Brg 100657 - Span 2 - R1 - P1.S2 | Place Deck - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A17760 | A17770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Place Deck - Brg 100657 - Span 2 - R1 - P1.S2 | Cure Deck - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | ST-POUR |  | H
A17770 | A17780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Cure Deck - Brg 100657 - Span 2 - R1 - P1.S2 | Install Reinf Barrier - Brg 100657 - Span 2 - R1 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A17560 | A17570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Cure/Strip Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | Erect Girders - Brg 100657 - Span 1 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17700 | A17710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Groove Deck - Brg 100657 - R1 - P1.S2 | Perm Striping - Brg 100657 - R1 - P1.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A17640 | A17680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Strip Overhangs - Brg 100657 - Span 1 - R1 - P1.S2 | Slip Barrier - Brg 100657 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A17610 | A17660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Place Deck - Brg 100657 - Span 1 - R1 - P1.S2 | FRPS Approach Slab 1 - Brg 100657 - R1 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A17630 | A17640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Install Reinf Barrier - Brg 100657 - Span 1 - R1 - P1.S2 | Strip Overhangs - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A17580 | A17590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Install SIP - Brg 100657 - Span 1 - R1 - P1.S2 | Install Overhangs - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A17590 | A17600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Install Overhangs - Brg 100657 - Span 1 - R1 - P1.S2 | Reinforce Deck - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A17600 | A17610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Reinforce Deck - Brg 100657 - Span 1 - R1 - P1.S2 | Place Deck - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A17610 | A17620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Place Deck - Brg 100657 - Span 1 - R1 - P1.S2 | Cure Deck - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | ST-POUR |  | H
A17620 | A17630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Cure Deck - Brg 100657 - Span 1 - R1 - P1.S2 | Install Reinf Barrier - Brg 100657 - Span 1 - R1 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A17510 | A17520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Excavate - Brg 100657 - Pier 1 - R1 - P1.S2 | Drive Pile - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 | EW-STR | ST-PILE | H
A17530 | A17540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | FRP Column - Brg 100657 - Pier 1 - R1 - P1.S2 | Cure/Strip Column - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 | ST-COL |  | H
A17550 | A17560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | FRP Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | Cure/Strip Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 | ST-CAP |  | H
A17540 | A17550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.1 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Pier 1 | Cure/Strip Column - Brg 100657 - Pier 1 - R1 - P1.S2 | FRP Cap - Brg 100657 - Pier 1 - R1 - P1.S2 | 0 |  | ST-CAP | H
A16910 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - Brg 100656 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 | SUB-STRIP |  | H
A17470 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 |  |  | H
A17490 | A17500 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Column - Brg 100656 - End Bent 1 - R1 - P1.S2 | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | 0 |  |  | H
A17290 | A17480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Cure/Strip Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | FRP Brick Column - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 |  | ST-BRIDGE-ALL | H
A17480 | A17490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | FRP Brick Column - Brg 100656 - End Bent 1 - R1 - P1.S2 | Cure/Strip Column - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | ST-BRIDGE-ALL |  | H
A17380 | A17460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Cure/Strip Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | FRP Brick Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 |  | ST-BRIDGE-ALL | H
A17460 | A17470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | FRP Brick Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | Cure/Strip Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | ST-BRIDGE-ALL |  | H
A16880 | A17450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Slip Barrier - Brg 100656 - R1 - P1.S2 | Install Fiberglass Panel on Barrier - Brg 100656 - R1 - P1.S2 | 0 | SUB-ST-PARAPET | SUB-ST-RAILING | H
A16660 | A17190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Install Temp Barrier - I-4 - R1 - P1.S2 | Excavate - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A16660 | A16680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Install Temp Barrier - I-4 - R1 - P1.S2 | Excavate - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A17420 | A17010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.7 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Demo | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Demo Barrier - Brg 100656 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A17420 | A17100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.7 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Demo | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Demo Barrier - Brg 100656 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A17420 | A16770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.7 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Demo | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Demo Barrier - Brg 100656 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-BEAM | H
A16660 | A17420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.3.7 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Demo | Install Temp Barrier - I-4 - R1 - P1.S2 | Demo Barrier - Brg 100656 - R1 - P1.S2 | 0 | SUB-TC-PCB | DM-BRIDGE | H
A17240 | A17010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Cure/Strip Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 2 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17240 | A17100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Cure/Strip Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 3 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17380 | A17100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Cure/Strip Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 3 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A16660 | A17410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Install Temp Barrier - I-4 - R1 - P1.S2 | Temp Wall or SOE - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A17340 | A17440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Grading - Brg 100656 - End Bent 2 - R1 - P1.S2 | Demo Brick tower - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A17250 | A17430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Grading - Brg 100656 - End Bent 1 - R1 - P1.S2 | Demo Brick tower - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | EW- ALL EW | DM-BRIDGE | H
A17410 | A17340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Temp Wall or SOE - Brg 100656 - End Bent 2 - R1 - P1.S2 | Grading - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A17360 | A17390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Drive Pile - Brg 100656 - End Bent 2 - R1 - P1.S2 | Const MSE Wall & Bkfill - RW 3-2 / Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A17370 | A17380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | FRP Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | Cure/Strip Abt Cap - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | ST-ABUT |  | H
A17290 | A16770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Cure/Strip Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 1 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17330 | A17250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Temp Wall or SOE - Brg 100656 - End Bent 1 - R1 - P1.S2 | Grading - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | EW-STR | EW- ALL EW | H
A16660 | A17330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Install Temp Barrier - I-4 - R1 - P1.S2 | Temp Wall or SOE - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-STR | H
A16670 | A16660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Shift Traffic - I-4 Left - R1 - P1.S2 | Install Temp Barrier - I-4 - R1 - P1.S2 | 0 | TC-Maint. | SUB-TC-PCB | H
A16650 | A16670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Open Ramp WE-B / Close I-4 EB Exit 1 - R1 - P1.S2 | Shift Traffic - I-4 Left - R1 - P1.S2 | 0 | TC-Maint. | TC-Maint. | H
A17270 | A17300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Drive Pile - Brg 100656 - End Bent 1 - R1 - P1.S2 | Const MSE Wall & Bkfill - RW 3-1 / Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | ST-PILE | ST-MSE | H
A17280 | A17290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | FRP Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | Cure/Strip Abt Cap - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | ST-ABUT |  | H
A17200 | A17210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Drive Pile - Brg 100656 - Pier 2 - R1 - P1.S2 | FRP Column - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 | ST-PILE | ST-COL | H
A17190 | A17200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Excavate - Brg 100656 - Pier 2 - R1 - P1.S2 | Drive Pile - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 | EW-STR | ST-PILE | H
A17210 | A17220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | FRP Column - Brg 100656 - Pier 2 - R1 - P1.S2 | Cure/Strip Column - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 | ST-COL |  | H
A17230 | A17240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | FRP Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | Cure/Strip Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 | ST-CAP |  | H
A17220 | A17230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.8 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 2 | Cure/Strip Column - Brg 100656 - Pier 2 - R1 - P1.S2 | FRP Cap - Brg 100656 - Pier 2 - R1 - P1.S2 | 0 |  | ST-CAP | H
A16690 | A16730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Drive Pile - Brg 100656 - Pier 1 - R1 - P1.S2 | FRP Column - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 | ST-PILE | ST-COL | H
A17140 | A16870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Place Deck - Brg 100656 - Span 3 - R1 - P1.S2 | FRPS Approach Slab 2 - Brg 100656 - R1 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A17170 | A16880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Strip Overhangs - Brg 100656 - Span 3 - R1 - P1.S2 | Slip Barrier - Brg 100656 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A17160 | A17170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Install Reinf Barrier - Brg 100656 - Span 3 - R1 - P1.S2 | Strip Overhangs - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A17110 | A17120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Install SIP - Brg 100656 - Span 3 - R1 - P1.S2 | Install Overhangs - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A17120 | A17130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Install Overhangs - Brg 100656 - Span 3 - R1 - P1.S2 | Reinforce Deck - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A17130 | A17140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Reinforce Deck - Brg 100656 - Span 3 - R1 - P1.S2 | Place Deck - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A17140 | A17150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Place Deck - Brg 100656 - Span 3 - R1 - P1.S2 | Cure Deck - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | ST-POUR |  | H
A17150 | A17160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Cure Deck - Brg 100656 - Span 3 - R1 - P1.S2 | Install Reinf Barrier - Brg 100656 - Span 3 - R1 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A16760 | A17010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Cure/Strip Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 2 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A17080 | A16880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Strip Overhangs - Brg 100656 - Span 2 - R1 - P1.S2 | Slip Barrier - Brg 100656 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A17070 | A17080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Install Reinf Barrier - Brg 100656 - Span 2 - R1 - P1.S2 | Strip Overhangs - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A17020 | A17030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Install SIP - Brg 100656 - Span 2 - R1 - P1.S2 | Install Overhangs - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A17030 | A17040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Install Overhangs - Brg 100656 - Span 2 - R1 - P1.S2 | Reinforce Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A17040 | A17050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Reinforce Deck - Brg 100656 - Span 2 - R1 - P1.S2 | Place Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A17050 | A17060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Place Deck - Brg 100656 - Span 2 - R1 - P1.S2 | Cure Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | ST-POUR |  | H
A17060 | A17070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Cure Deck - Brg 100656 - Span 2 - R1 - P1.S2 | Install Reinf Barrier - Brg 100656 - Span 2 - R1 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A16760 | A16770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Cure/Strip Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | Erect Girders - Brg 100656 - Span 1 - R1 - P1.S2 | 0 |  | ST-BEAM | H
A16900 | A16910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Groove Deck - Brg 100656 - R1 - P1.S2 | Perm Striping - Brg 100656 - R1 - P1.S2 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A16840 | A16880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Strip Overhangs - Brg 100656 - Span 1 - R1 - P1.S2 | Slip Barrier - Brg 100656 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-PARAPET | H
A16810 | A16860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Place Deck - Brg 100656 - Span 1 - R1 - P1.S2 | FRPS Approach Slab 1 - Brg 100656 - R1 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A16830 | A16840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Install Reinf Barrier - Brg 100656 - Span 1 - R1 - P1.S2 | Strip Overhangs - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-DECK | H
A16780 | A16790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Install SIP - Brg 100656 - Span 1 - R1 - P1.S2 | Install Overhangs - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | SUB-ST-SIP | ST-DECK | H
A16790 | A16800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Install Overhangs - Brg 100656 - Span 1 - R1 - P1.S2 | Reinforce Deck - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | ST-DECK | SUB-ST-REBAR | H
A16800 | A16810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Reinforce Deck - Brg 100656 - Span 1 - R1 - P1.S2 | Place Deck - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | SUB-ST-REBAR | ST-POUR | H
A16810 | A16820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Place Deck - Brg 100656 - Span 1 - R1 - P1.S2 | Cure Deck - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | ST-POUR |  | H
A16820 | A16830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Cure Deck - Brg 100656 - Span 1 - R1 - P1.S2 | Install Reinf Barrier - Brg 100656 - Span 1 - R1 - P1.S2 | 0 |  | SUB-ST-REBAR | H
A16680 | A16690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Excavate - Brg 100656 - Pier 1 - R1 - P1.S2 | Drive Pile - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 | EW-STR | ST-PILE | H
A16730 | A16740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | FRP Column - Brg 100656 - Pier 1 - R1 - P1.S2 | Cure/Strip Column - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 | ST-COL |  | H
A16750 | A16760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | FRP Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | Cure/Strip Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 | ST-CAP |  | H
A16740 | A16750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.1 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Pier 1 | Cure/Strip Column - Brg 100656 - Pier 1 - R1 - P1.S2 | FRP Cap - Brg 100656 - Pier 1 - R1 - P1.S2 | 0 |  | ST-CAP | H
A16500 | A16640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Shift Traffic - Ramp NE Right - R1 - P1.S2 | Remove Temp Barrier - Ramp WE-B - R1 - P1.S2 | 0 | TC-Maint. | SUB-TC-PCB | H
A16640 | A16650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Remove Temp Barrier - Ramp WE-B - R1 - P1.S2 | Open Ramp WE-B / Close I-4 EB Exit 1 - R1 - P1.S2 | 0 | SUB-TC-PCB | TC-Maint. | H
A16620 | A16630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Shoulder GAB - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Place Asphalt Shoulder - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 0 | EW-ABC | SUB-ASPH | H
A16610 | A16620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Edge Drain - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Place Shoulder GAB - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 0 | PIPE | EW-ABC | H
A16600 | A16610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Concrete Pav - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Place Edge Drain - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 0 | CP-SLIP | PIPE | H
A16590 | A16600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Asphalt Base - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Place Concrete Pav - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 0 | SUB-ASPH | CP-SLIP | H
A15920 | A16510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | Shift Traffic - Ramp NE Left - R1 - P1.S2 | 0 |  | TC-Maint. | H
A16510 | A16500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Shift Traffic - Ramp NE Left - R1 - P1.S2 | Shift Traffic - Ramp NE Right - R1 - P1.S2 | 0 | TC-Maint. | TC-Maint. | H
A16490 | A16340 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Start Construction - R2 | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 1 | 0 |  | EW-SML | H
A16340 | A16450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 1 | Install DRG S-118 to S-123 - Pond SMF 4A - R2 - P1 | 0 | EW-SML | PIPE | H
A16340 | A16350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 1 | Place Stabilization - Pond SMF 4A Shared Use Path - R2 - P0 | 0 | EW-SML | EW-STAB | H
A16290 | A15910 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Fencing - 13th Ave - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - 13th Ave | 0 | SUB-FENCE |  | H
A16230 | A15910 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Intersection Brick - 13th Ave at 14th & 15th St - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - 13th Ave | 0 | FLATWORK |  | H
A1050 | A16250 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Start Construction - R1 | Demo Existing Slope Pavement - Left 14th &15th St under I-4 - R1 - P1.S1 | 0 |  | DM-BRIDGE | H
A16270 | A16290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Brick Sidewalk - Left 14th & 15th St under I-4 - R1 - P1.S1 | Install Fencing - 13th Ave - R1 - P1.S1 | 0 | FLATWORK | SUB-FENCE | H
A16210 | A16240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Asphalt Surface - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | Remove Temp Barrier - 13th Ave - R1 - P1.S1 | 0 | SUB-ASPH | SUB-TC-PCB | H
A16070 | A16240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Asphalt Surface - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | Remove Temp Barrier - 13th Ave - R1 - P1.S1 | 0 | SUB-ASPH | SUB-TC-PCB | H
A16240 | A16220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Remove Temp Barrier - 13th Ave - R1 - P1.S1 | Mill / Resurface - 13th Ave Sta 13 to 35 - R1 - P1.S1 | 0 | SUB-TC-PCB | SUB-ASPH | H
A16220 | A16230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Mill / Resurface - 13th Ave Sta 13 to 35 - R1 - P1.S1 | Place Intersection Brick - 13th Ave at 14th & 15th St - R1 - P1.S1 | 0 | SUB-ASPH | FLATWORK | H
A16150 | A16160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.10 R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 2 | Cut/Fill to Grade - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 0 | SUB-TC-PCB | EW-SML | H
A16160 | A16170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Cut/Fill to Grade - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | Place Stabilization - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 0 | EW-SML | EW-STAB | H
A16180 | A16190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place GAB - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | Place Curb - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 0 | EW-ABC | FLATWORK | H
A16170 | A16180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place Stabilization - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | Place GAB - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 0 | EW-STAB | EW-ABC | H
A16150 | A16020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.10 R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 2 | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 0 | SUB-TC-PCB | EW-SML | H
A16130 | A16140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - IBL(all) - B1.2.2.12.10 R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | Place Asphalt Surface - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Shift Traffic - 13th Ave Left - R1 - P1.S1 Step 2 | 0 | SUB-ASPH | TC-Maint. | H
A16010 | A16140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.10 R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | Place Asphalt Surface - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | Shift Traffic - 13th Ave Left - R1 - P1.S1 Step 2 | 0 | SUB-ASPH | TC-Maint. | H
A16140 | A16150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.10 R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | I-275 - I-4 - IBL(all) - B1.2.2.12.10 R1 - Ph1, Stg1, Step 2 - 13th Ave MOT | Shift Traffic - 13th Ave Left - R1 - P1.S1 Step 2 | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 2 | 0 | TC-Maint. | SUB-TC-PCB | H
A15950 | A16080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | SUB-TC-PCB | EW-SML | H
A16080 | A16090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place Stabilization - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-SML | EW-STAB | H
A16100 | A16110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place GAB - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place Curb - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-ABC | FLATWORK | H
A16090 | A16100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Stabilization - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place GAB - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-STAB | EW-ABC | H
A16020 | A16030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | Place Stabilization - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 0 | EW-SML | EW-STAB | H
A16040 | A16050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place GAB - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | Place Curb - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 0 | EW-ABC | FLATWORK | H
A16030 | A16040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place Stabilization - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | Place GAB - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 0 | EW-STAB | EW-ABC | H
A15990 | A16000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place GAB - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | Place Curb - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 0 | EW-ABC | FLATWORK | H
A15980 | A15990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place Stabilization - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | Place GAB - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 0 | EW-STAB | EW-ABC | H
A15970 | A15980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Const MSE Wall & Bkfill - RW-100 - Left 13th Ave Sta 13 to 16 - R1 - P1.S1 | Place Stabilization - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 0 | ST-MSE | EW-STAB | H
A15950 | A15960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 0 | SUB-TC-PCB | EW-SML | H
A15960 | A15970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | Const MSE Wall & Bkfill - RW-100 - Left 13th Ave Sta 13 to 16 - R1 - P1.S1 | 0 | EW-SML | ST-MSE | H
A15020 | A15780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Curb - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Asphalt Base - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | FLATWORK | SUB-ASPH | H
A15770 | A15020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Stabilization - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Curb - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | EW-STAB | FLATWORK | H
A15940 | A15950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | I-275 - I-4 - IBL(all) - B1.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Shift Traffic - 13th Ave Right - R1 - P1.S1 Step 1 | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | 0 | TC-Maint. | SUB-TC-PCB | H
A15900 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-ASPH |  | H
A15820 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-ASPH |  | H
A15740 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-ASPH |  | H
A15660 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-ASPH |  | H
A15540 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-ASPH |  | H
A15410 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 | SUB-ASPH |  | H
A1150 | A15550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Install Temp Barrier - Ramp NE - R1 - P1.S1 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - left | 0 | SUB-TC-PCB | ST-MSE | H
A15430 | A15830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | Cut/Fill to Grade - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | PIPE | EW-SML | H
A15850 | A15860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Stabilization - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Place Asphalt Base - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | EW-STAB | SUB-ASPH | H
A15890 | A15900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Shoulder GAB - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Place Asphalt Shoulder - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A15880 | A15890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Edge Drain - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Place Shoulder GAB - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | PIPE | EW-ABC | H
A15870 | A15880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Concrete Pav - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Place Edge Drain - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | CP-SLIP | PIPE | H
A15860 | A15870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Place Asphalt Base - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Place Concrete Pav - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | SUB-ASPH | CP-SLIP | H
A15420 | A15450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | 0 | PIPE | EW-SML | H
A15440 | A15750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 - part 1 | 0 | PIPE | EW-SML | H
A15750 | A15760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Cut/Fill to Grade - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 - part 1 | Place 3-Pour Barrier - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | EW-SML | SUB-BR-SLIP | H
A15760 | A15770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place 3-Pour Barrier - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Stabilization - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | SUB-BR-SLIP | EW-STAB | H
A15810 | A15820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Shoulder GAB - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Asphalt Shoulder - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A15800 | A15810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Edge Drain - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Shoulder GAB - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | PIPE | EW-ABC | H
A15790 | A15800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Concrete Pav - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Edge Drain - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | CP-SLIP | PIPE | H
A15780 | A15790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Place Asphalt Base - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | Place Concrete Pav - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | SUB-ASPH | CP-SLIP | H
A15460 | A15670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 1 | Grading - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | ST-MSE | EW- ALL EW | H
A15690 | A15700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Stabilization - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place Asphalt Base - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | EW-STAB | SUB-ASPH | H
A15670 | A15680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Grading - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place 3-Pour Barrier - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | EW- ALL EW | SUB-BR-SLIP | H
A15680 | A15690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place 3-Pour Barrier - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place Stabilization - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | SUB-BR-SLIP | EW-STAB | H
A15730 | A15740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Shoulder GAB - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place Asphalt Shoulder - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A15720 | A15730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Edge Drain - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place Shoulder GAB - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | PIPE | EW-ABC | H
A15710 | A15720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Concrete Pav - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place Edge Drain - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | CP-SLIP | PIPE | H
A15700 | A15710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | I-275 - I-4 - IBL(all) - B1.2.2.2.9 R1 - Ph1, Stg1 - Ramp NE-B - 10th St. to 12th St. - Sta. 11 to 17 | Place Asphalt Base - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | Place Concrete Pav - Ramp NE-B Sta 11 to 17 - R1 - P1.S1 | 0 | SUB-ASPH | CP-SLIP | H
A15580 | A15590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Cut/Fill to Grade - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Stabilization - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | EW-SML | EW-STAB | H
A15650 | A15660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Shoulder GAB - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Asphalt Shoulder - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A15640 | A15650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Edge Drain - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Shoulder GAB - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | PIPE | EW-ABC | H
A15630 | A15640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Concrete Pav - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Edge Drain - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | CP-SLIP | PIPE | H
A15620 | A15630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Asphalt Base - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Concrete Pav - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | SUB-ASPH | CP-SLIP | H
A15610 | A15620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Wall Barrier - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Asphalt Base - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A15600 | A15610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Junction Slab - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Wall Barrier - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | ST-CIP | SUB-BR-SLIP | H
A15590 | A15600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Place Stabilization - Ramp NE Sta 110 to 116 - R1 - P1.S1 | Place Junction Slab - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | EW-STAB | ST-CIP | H
A15570 | A15470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place 3-Pour Barrier - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Stabilization - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | SUB-BR-SLIP | EW-STAB | H
A15550 | A15570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - left | Place 3-Pour Barrier - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | ST-MSE | SUB-BR-SLIP | H
A15560 | A14980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place 3-Pour Barrier - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Stabilization - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | SUB-BR-SLIP | EW-STAB | H
A14950 | A15560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Const MSE Wall & Bkfill - RW 5-1 - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place 3-Pour Barrier - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | ST-MSE | SUB-BR-SLIP | H
A15080 | A15450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 / Brg 100865 - End Bent 2 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | 0 | ST-MSE | EW-SML | H
A15530 | A15540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Shoulder GAB - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Asphalt Shoulder - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A15520 | A15530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Edge Drain - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Shoulder GAB - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | PIPE | EW-ABC | H
A15510 | A15520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Concrete Pav - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Edge Drain - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | CP-SLIP | PIPE | H
A15500 | A15510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Asphalt Base - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Concrete Pav - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | SUB-ASPH | CP-SLIP | H
A15490 | A15500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Wall Barrier - Ramp WE Sta 50 to 60 - R1 - P1.S1 | Place Asphalt Base - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A15480 | A15490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Junction Slab - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Wall Barrier - Ramp WE Sta 50 to 60 - R1 - P1.S1 | 0 | ST-CIP | SUB-BR-SLIP | H
A15470 | A15480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Place Stabilization - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | Place Junction Slab - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | EW-STAB | ST-CIP | H
A15450 | A15460 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 1 | 12 | EW-SML | ST-MSE | H
A15400 | A15410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Shoulder GAB - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Asphalt Shoulder - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | EW-ABC | SUB-ASPH | H
A15390 | A15400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Edge Drain - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Shoulder GAB - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | PIPE | EW-ABC | H
A15000 | A15390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Concrete Pav - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Edge Drain - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | CP-SLIP | PIPE | H
A14670 | A14940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | ST-MSE | EW-SML | H
A14990 | A15000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Asphalt Base - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Concrete Pav - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | SUB-ASPH | CP-SLIP | H
A14970 | A14990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Wall Barrier - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Asphalt Base - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-ASPH | H
A14960 | A14970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Junction Slab - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Wall Barrier - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | ST-CIP | SUB-BR-SLIP | H
A14980 | A14960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Place Stabilization - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Place Junction Slab - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | EW-STAB | ST-CIP | H
A15360 | A14910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Cure Deck - Brg 100865 - Span 3 - R1 - P1.S1 | Grind Deck - Brg 100865 - R1 - P1.S1 | 0 |  | SUB-DGRIND | H
A15270 | A14910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Cure Deck - Brg 100865 - Span 2 - R1 - P1.S1 | Grind Deck - Brg 100865 - R1 - P1.S1 | 0 |  | SUB-DGRIND | H
A14840 | A14910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Cure Deck - Brg 100865 - Span 1 - R1 - P1.S1 | Grind Deck - Brg 100865 - R1 - P1.S1 | 0 |  | SUB-DGRIND | H
A15350 | A14900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Place Deck - Brg 100865 - Span 3 - R1 - P1.S1 | FRPS Approach Slab 2 - Brg 100865 - R1 - P1.S1 | 0 | ST-POUR | ST-APPR | H
A15110 | A15300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Cure/Strip Abt Cap - Brg 100865 - End Bent 2- R1 - P1.S1 | Erect Girders - Brg 100865 - Span 3 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A15200 | A15300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 3 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A15200 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A15380 | A14880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Strip Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | Slip Barrier - Brg 100865 - R1 - P1.S1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A15370 | A15380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Install Reinf Barrier - Brg 100865 - Span 3 - R1 - P1.S1 | Strip Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-DECK | H
A15320 | A15330 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Install SIP - Brg 100865 - Span 3 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A15330 | A15340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Install Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | Reinforce Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A15340 | A15350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Reinforce Deck - Brg 100865 - Span 3 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A15350 | A15360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Place Deck - Brg 100865 - Span 3 - R1 - P1.S1 | Cure Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | ST-POUR |  | H
A15360 | A15370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Cure Deck - Brg 100865 - Span 3 - R1 - P1.S1 | Install Reinf Barrier - Brg 100865 - Span 3 - R1 - P1.S1 | 0 |  | SUB-ST-REBAR | H
A14780 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A15290 | A14880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Strip Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | Slip Barrier - Brg 100865 - R1 - P1.S1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A15280 | A15290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install Reinf Barrier - Brg 100865 - Span 2 - R1 - P1.S1 | Strip Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-DECK | H
A15230 | A15240 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install SIP - Brg 100865 - Span 2 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A15240 | A15250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | Reinforce Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A15250 | A15260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Reinforce Deck - Brg 100865 - Span 2 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A15260 | A15270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Place Deck - Brg 100865 - Span 2 - R1 - P1.S1 | Cure Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | ST-POUR |  | H
A15270 | A15280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Cure Deck - Brg 100865 - Span 2 - R1 - P1.S1 | Install Reinf Barrier - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | SUB-ST-REBAR | H
A1670 | A14790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Cure/Strip Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A14780 | A14790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A1050 | A15120 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Start Construction - R1 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | EW-STR | H
A15140 | A15150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-PILE | ST-FOOT | H
A15150 | A15160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | Cure/Strip Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-FOOT |  | H
A15170 | A15180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Column - Brg 100865 - Pier 2 - R1 - P1.S1 | Cure/Strip Column - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-COL |  | H
A15190 | A15200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-CAP |  | H
A15160 | A15170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | FRP Column - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | ST-COL | H
A15180 | A15190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Column - Brg 100865 - Pier 2 - R1 - P1.S1 | FRP Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | ST-CAP | H
A1050 | A14700 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Start Construction - R1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | EW-STR | H
A1000 | A1020 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Mobilization | Clear and Grub | 0 |  | SUB-EW-C&G | H
A1130 | A15050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | SUB-TC-PCB | EW- ALL EW | H
A15070 | A15080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | Const MSE Wall & Bkfill - RW 5-2 / Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | ST-PILE | ST-MSE | H
A15100 | A15110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | FRP Abt Cap - Brg 100865 - End Bent 2 - R1 - P1.S1 | Cure/Strip Abt Cap - Brg 100865 - End Bent 2- R1 - P1.S1 | 0 | ST-ABUT |  | H
A14940 | A14950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - IBL(all) - B1.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Cut/Fill to Grade - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Const MSE Wall & Bkfill - RW 5-1 - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | EW-SML | ST-MSE | H
A14920 | A14930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Groove Deck - Brg 100865 - R1 - P1.S1 | Perm Striping - Brg 100865 - R1 - P1.S1 | 0 | SUB-ST-GROOVE | SUB-STRIP | H
A14900 | A14910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | FRPS Approach Slab 2 - Brg 100865 - R1 - P1.S1 | Grind Deck - Brg 100865 - R1 - P1.S1 | 0 | ST-APPR | SUB-DGRIND | H
A14860 | A14880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Strip Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | Slip Barrier - Brg 100865 - R1 - P1.S1 | 0 | ST-DECK | SUB-ST-PARAPET | H
A14830 | A14890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Place Deck - Brg 100865 - Span 1 - R1 - P1.S1 | FRPS Approach Slab 1 - Brg 100865 - R1 - P1.S1 | 0 | ST-POUR | ST-APPR | H
A14910 | A14920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | Grind Deck - Brg 100865 - R1 - P1.S1 | Groove Deck - Brg 100865 - R1 - P1.S1 | 0 | SUB-DGRIND | SUB-ST-GROOVE | H
A14890 | A14910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.2.4.6 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Finishes | FRPS Approach Slab 1 - Brg 100865 - R1 - P1.S1 | Grind Deck - Brg 100865 - R1 - P1.S1 | 0 | ST-APPR | SUB-DGRIND | H
A14850 | A14860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install Reinf Barrier - Brg 100865 - Span 1 - R1 - P1.S1 | Strip Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-DECK | H
A14810 | A14820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | Reinforce Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A14820 | A14830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Reinforce Deck - Brg 100865 - Span 1 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A14830 | A14840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Place Deck - Brg 100865 - Span 1 - R1 - P1.S1 | Cure Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | ST-POUR |  | H
A14840 | A14850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Cure Deck - Brg 100865 - Span 1 - R1 - P1.S1 | Install Reinf Barrier - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | SUB-ST-REBAR | H
A14720 | A14730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-PILE | ST-FOOT | H
A14730 | A14740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | Cure/Strip Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-FOOT |  | H
A14750 | A14760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Column - Brg 100865 - Pier 1 - R1 - P1.S1 | Cure/Strip Column - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-COL |  | H
A14770 | A14780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-CAP |  | H
A14740 | A14750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Column - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | ST-COL | H
A14760 | A14770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Column - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | ST-CAP | H
A1650 | A14670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | ST-PILE | ST-MSE | H
A14680 | A1630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Temp Wall or SOE - Brg 100865 - End Bent 1 - R1 - P1.S1 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | EW-STR | EW- ALL EW | H
A1130 | A14680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Temp Wall or SOE - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | SUB-TC-PCB | EW-STR | H
A1660 | A1670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | FRP Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | Cure/Strip Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | ST-ABUT |  | H
A1130 | A1140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Shift Traffic - Ramp NE Left - R1 - P1.S1 | 0 | SUB-TC-PCB | TC-Maint. | H
A1140 | A1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp NE Left - R1 - P1.S1 | Install Temp Barrier - Ramp NE - R1 - P1.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A1120 | A1130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp WE Left - R1 - P1.S1 | Install Temp Barrier - Ramp WE - R1 - P1.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A1110 | A1060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - IBL(all) - B1.2.2.1.3 R1 - Ph0 - Traffic Shift | Temp Striping - 13th Ave Temp Pav - R1 - P0 | Shift Traffic - I-4 Exit 1 Ramp Left - R1 - P0 | 0 | SUB-STRIP | TC-Maint. | H
A1040 | A1080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.1 R1 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | Shift Traffic - I-4 Exit 1 Ramp Right - R1 - P0 | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | 0 | TC-Maint. | EW-SML | H
A1100 | A1110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | Place Asphalt - 13th Ave Temp Pav - R1 - P0 | Temp Striping - 13th Ave Temp Pav - R1 - P0 | 0 | SUB-ASPH | SUB-STRIP | H
A1080 | A1090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - IBL(all) - B1.2.2.1.2 R1 - Ph0 - Temp Pavement | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | Place Stabilization - 13th Ave Temp Pav - R1 - P0 | 0 | EW-SML | EW-STAB | H
A1050 | A1030 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.1.1 R1 - Ph0 - MOT | Start Construction - R1 | Install MOT - I-4 Exit Ramp - R1 - P0 | 0 |  | TC-Maint. | H
A1030 | A1040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.1 R1 - Ph0 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.1.1 R1 - Ph0 - MOT | Install MOT - I-4 Exit Ramp - R1 - P0 | Shift Traffic - I-4 Exit 1 Ramp Right - R1 - P0 | 0 | TC-Maint. | TC-Maint. | H
A1010 | A1020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Install Erosion Control Devices | Clear and Grub | 0 | SUB-EROSION | SUB-EW-C&G | H
A1000 | A1010 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | I-275 - I-4 - IBL(all) - B1.2.1 Mobilization | Mobilization | Install Erosion Control Devices | 0 |  | SUB-EROSION | H
D1780 | Admin-1060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Resolve Comments and Issue - Environmental Resource Permit (ERP) | Project Punchlist | 0 |  |  | H
D1670 | D1710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | Issue - RFC Roadway Plans - R1 | Modify and Submit - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1100 | LoE100 | FF | Not Started | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1.1 Phase Durations | Design Completion | Design Phase [LoE] | 0 |  |  | H
D1180 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Review and Approve - Design Quality Management Plan | Design Completion | 0 |  |  | H
D1000 | D1130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Develop and Submit - 90% Erosion and Sediment Control Plan | Develop and Submit - SWPPP & NOI | 0 |  |  | H
P1270 | P1300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | Develop and Submit - Girder Shop Drawings - Brg 2 - Cat 2 | Review and Comment - Girder Shop Drawings - Brg 2 - Cat 2 | 0 |  |  | H
P1310 | P1320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | Revise and Resubmit - Girder Shop Drawings - Brg 2 - Cat 2 | Review and Approve - Girder Shop Drawings - Brg 2 - Cat 2 | 0 |  |  | H
P1300 | P1310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | Review and Comment - Girder Shop Drawings - Brg 2 - Cat 2 | Revise and Resubmit - Girder Shop Drawings - Brg 2 - Cat 2 | 0 |  |  | H
Admin-1020 | P1010 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Construction Quality Control Plan | 0 |  |  | H
Admin-1020 | P1070 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Noise Management Plan | 0 |  |  | H
Admin-1020 | P1090 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Settlement and Vibration Monitoring Plan | 0 |  |  | H
Admin-1045 | D1220 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Begin Design | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D2160 | D2290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Review and Approve - Final Cat2 Brg 10 Plans - R3 | Develop and Submit - Sign & Seal Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1630 | D2010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Review and Approve - 90% Cat2 Brg 10 Plans - R3 | Develop and Submit - Final Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D2010 | D2160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - Final Cat2 Brg 10 Plans - R3 | Review and Approve - Final Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1450 | D1630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | Review and Approve - 90% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1220 | D1440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D2290 | D2370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - Sign & Seal Cat2 Brg 10 Plans - R3 | Issue - RFC Cat2 Brg 10 Plans - R3 | 0 |  |  | H
Admin-1020 | D2510 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2550 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC TTCP Plans - R3 Phase 1 | Design Completion | 0 |  |  | H
D2530 | D2540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Review and Approve - Final TTCP Plans - R3 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2510 | D2520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Review and Approve - 90% TTCP Plans - R3 Phase 1 | Develop and Submit - Final TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2480 | D2510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | Review and Approve - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2520 | D2530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - Final TTCP Plans - R3 Phase 1 | Review and Approve - Final TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2540 | D2550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 1 | Issue - RFC TTCP Plans - R3 Phase 1 | 0 |  |  | H
Admin-1045 | D2480 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Begin Design | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2230 | D2320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Develop and Submit- Sign & Seal ITS Plans | Develop and Submit - 90% Technical Specifications | 0 |  |  | H
D2240 | D2320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Develop and Submit - Sign & Seal Signing and Pavement Marking Plan | Develop and Submit - 90% Technical Specifications | 0 |  |  | H
Admin-1020 | D1950 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Landscape Plans | 0 |  |  | H
Admin-1020 | D1930 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Landscaping Opportunity Plan | 0 |  |  | H
Admin-1020 | D1870 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Lighting Plans | 0 |  |  | H
Admin-1020 | D1860 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Signing and Pavement Marking Plan | 0 |  |  | H
Admin-1020 | D1760 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% MoC Plan | 0 |  |  | H
Admin-1020 | D1920 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% ITS Plans | 0 |  |  | H
Admin-1020 | D1880 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Signalization Plans | 0 |  |  | H
Admin-1020 | D1900 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% MSE Wall RW 1-1 | 0 |  |  | H
Admin-1020 | D1460 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Roadway Plans - R1 | 0 |  |  | H
Admin-1020 | D2190 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
Admin-1020 | D1550 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
Admin-1020 | D1390 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R1 Phase 2 | 0 |  |  | H
Admin-1020 | D1400 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R1 Phase 1 | 0 |  |  | H
Admin-1020 | D2420 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Technical Specifications | 0 |  |  | H
Admin-1020 | D1120 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Erosion and Sediment Control Plan | 0 |  |  | H
Admin-1020 | D1140 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - SWPPP & NOI | 0 |  |  | H
Admin-1020 | D1740 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1020 | D1170 | SS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | Anticipated Notice to Proceed (Sept. 26th, 2022) | Independent Design Review Kickoff Meeting | 0 |  |  | H
Admin-1020 | D1080 | SS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Design Quality Management Plan | 0 |  |  | H
D1170 | Admin-1100 | FF | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Independent Design Review Kickoff Meeting | Design Completion | 0 |  |  | H
D2390 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Landscape Plans | Design Completion | 0 |  |  | H
D2380 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Landscaping Opportunity Plan | Design Completion | 0 |  |  | H
D2360 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Lighting Plans | Design Completion | 0 |  |  | H
D2350 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Signing and Pavement Marking Plan | Design Completion | 0 |  |  | H
D2140 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC MoC Plan | Design Completion | 0 |  |  | H
D2340 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC ITS Plans | Design Completion | 0 |  |  | H
D2330 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Signalization Plans | Design Completion | 0 |  |  | H
D1670 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Roadway Plans - R1 | Design Completion | 0 |  |  | H
D2460 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC TTCP Plans - R2 Phase 2 | Design Completion | 0 |  |  | H
D1830 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC TTCP Plans - R2 Phase 1 | Design Completion | 0 |  |  | H
D1580 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC TTCP Plans - R1 Phase 2 | Design Completion | 0 |  |  | H
D1590 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC TTCP Plans - R1 Phase 1 | Design Completion | 0 |  |  | H
D2500 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFP Technical Specifications | Design Completion | 0 |  |  | H
D1330 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Erosion and Sediment Control Plan | Design Completion | 0 |  |  | H
D2180 | D2280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Review and Approve - Final Landscape Plans | Develop and Submit - Sign & Seal Landscape Plans | 0 |  |  | H
D1950 | D2040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Review and Approve - 90% Landscape Plans | Develop and Submit - Final Landscape Plans | 0 |  |  | H
D1930 | D2030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Review and Approve - 90% Landscaping Opportunity Plan | Develop and Submit - Final Landscaping Opportunity Plan | 0 |  |  | H
D2170 | D2270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Review and Approve - Final Landscaping Opportunity Plan | Develop and Submit - Sign & Seal Landscaping Opportunity Plan | 0 |  |  | H
D2110 | D2250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Review and Approve - Final Lighting Plans | Develop and Submit - Sign & Seal Lighting Plans | 0 |  |  | H
D1870 | D1970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Review and Approve - 90% Lighting Plans | Develop and Submit - Final Lighting Plans | 0 |  |  | H
D1860 | D1960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Review and Approve - 90% Signing and Pavement Marking Plan | Develop and Submit - Final Signing and Pavement Marking Plan | 0 |  |  | H
D2100 | D2240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Review and Approve - Final Signing and Pavement Marking Plan | Develop and Submit - Sign & Seal Signing and Pavement Marking Plan | 0 |  |  | H
D1940 | D2060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Review and Approve - Final MoC Plan | Develop and Submit- Sign & Seal MoC Plan | 0 |  |  | H
D1760 | D1820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Review and Approve - 90% MoC Plan | Develop and Submit- Final MoC Plan | 0 |  |  | H
D2150 | D2230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Review and Approve - Final ITS Plans | Develop and Submit- Sign & Seal ITS Plans | 0 |  |  | H
D1920 | D2000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Review and Approve - 90% ITS Plans | Develop and Submit- Final ITS Plans | 0 |  |  | H
D2120 | D2220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Review and Approve - Final Signalization Plans | Develop and Submit - Sign & Seal Signalization Plans | 0 |  |  | H
D1880 | D1980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Review and Approve - 90% Signalization Plans | Develop and Submit - Final Signalization Plans | 0 |  |  | H
D2130 | D2210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-1 | Develop and Submit - Sign & Seal MSE Wall RW 1-1 | 0 |  |  | H
D1900 | D1990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-1 | Develop and Submit - Final MSE Wall RW 1-1 | 0 |  |  | H
D1890 | D2050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Review and Approve - Final Cat1 Brg 08 Plans - R3 | Develop and Submit - Sign & Seal Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1540 | D1810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | Develop and Submit - Final Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1570 | D1610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Review and Approve - Final Roadway Plans - R1 | Develop and Submit - Sign & Seal Roadway Plans - R1 | 0 |  |  | H
D1460 | D1490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Review and Approve - 90% Roadway Plans - R1 | Develop and Submit - Final Roadway Plans - R1 | 0 |  |  | H
D2400 | D2430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Review and Approve - Final TTCP Plans - R2 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2190 | D2260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Review and Approve - 90% TTCP Plans - R2 Phase 2 | Develop and Submit - Final TTCP Plans - R2 Phase 2 | 0 |  |  | H
D1620 | D1770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Review and Approve - Final TTCP Plans - R2 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1550 | D1600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Review and Approve - 90% TTCP Plans - R2 Phase 1 | Develop and Submit - Final TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1470 | D1510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Review and Approve - Final TTCP Plans - R1 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 | 0 |  |  | H
D1390 | D1410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Review and Approve - 90% TTCP Plans - R1 Phase 2 | Develop and Submit - Final TTCP Plans - R1 Phase 2 | 0 |  |  | H
D1480 | D1520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Review and Approve - Final TTCP Plans - R1 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1400 | D1430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Review and Approve - 90% TTCP Plans - R1 Phase 1 | Develop and Submit - Final TTCP Plans - R1 Phase 1 | 0 |  |  | H
D2470 | D2490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Review and Approve - Final Technical Specifications | Develop and Submit - Sign & Seal Technical Specifications | 0 |  |  | H
D2420 | D2450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Review and Approve - 90% Technical Specifications | Develop and Submit - Final Technical Specifications | 0 |  |  | H
D1270 | D1310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Review and Approve - Final Erosion and Sediment Control Plan | Develop and Submit - Sign & Seal Erosion and Sediment Control Plan | 0 |  |  | H
D1120 | D1210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Review and Approve - 90% Erosion and Sediment Control Plan | Develop and Submit - Final Erosion and Sediment Control Plan | 0 |  |  | H
Admin-1045 | D1420 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Begin Design | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
Admin-1045 | D1130 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Begin Design | Develop and Submit - SWPPP & NOI | 0 |  |  | H
Admin-1045 | D1710 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | Begin Design | Modify and Submit - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1015 | Admin-1020 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Prepare for Notice to Proceed | Anticipated Notice to Proceed (Sept. 26th, 2022) | 0 |  |  | H
Admin-1000 | Admin-1010 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Anticipated Contract Award Date | Execute Contract | 0 |  |  | H
Admin-1050 | Admin-1060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Substantial Completion (Sept. 4th, 2026) | Project Punchlist | 0 |  |  | H
Admin-1060 | Admin-1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Project Punchlist | Contract Completion (Nov. 3rd 2026) | 0 |  |  | H
Admin-1030 | Admin-1045 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Design Mobilization | Begin Design | 0 |  |  | H
Admin-1010 | Admin-1080 | FF | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Execute Contract | Anticipated Contract Execution Date | 0 |  |  | H
Admin-1080 | Admin-1015 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Anticipated Contract Execution Date | Prepare for Notice to Proceed | 0 |  |  | H
Admin-1020 | Admin-1040 | SS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Anticipated Notice to Proceed (Sept. 26th, 2022) | LOE - Project Duration | 0 |  |  | H
Admin-1000 | Admin-1030 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Anticipated Contract Award Date | Design Mobilization | 0 |  |  | H
P1040 | P1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | Develop and Submit - Noise Management Plan | Review and Comment - Noise Management Plan | 0 |  |  | H
P1100 | P1130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | Revise and Resubmit - Noise Management Plan | Review and Approve - Noise Management Plan | 0 |  |  | H
P1070 | P1100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | Review and Comment - Noise Management Plan | Revise and Resubmit - Noise Management Plan | 0 |  |  | H
Admin-1045 | P1040 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | Begin Design | Develop and Submit - Noise Management Plan | 0 |  |  | H
D1000 | D1120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Develop and Submit - 90% Erosion and Sediment Control Plan | Review and Approve - 90% Erosion and Sediment Control Plan | 0 |  |  | H
D1210 | D1270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Develop and Submit - Final Erosion and Sediment Control Plan | Review and Approve - Final Erosion and Sediment Control Plan | 0 |  |  | H
D1640 | D1860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Develop and Submit - 90% Signing and Pavement Marking Plan | Review and Approve - 90% Signing and Pavement Marking Plan | 0 |  |  | H
D1960 | D2100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Develop and Submit - Final Signing and Pavement Marking Plan | Review and Approve - Final Signing and Pavement Marking Plan | 0 |  |  | H
D1650 | D1870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Develop and Submit - 90% Lighting Plans | Review and Approve - 90% Lighting Plans | 0 |  |  | H
D1970 | D2110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Develop and Submit - Final Lighting Plans | Review and Approve - Final Lighting Plans | 0 |  |  | H
Admin-1045 | D1640 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Begin Design | Develop and Submit - 90% Signing and Pavement Marking Plan | 0 |  |  | H
Admin-1045 | D1650 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Begin Design | Develop and Submit - 90% Lighting Plans | 0 |  |  | H
D1660 | D1880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Develop and Submit - 90% Signalization Plans | Review and Approve - 90% Signalization Plans | 0 |  |  | H
D1980 | D2120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Develop and Submit - Final Signalization Plans | Review and Approve - Final Signalization Plans | 0 |  |  | H
D1700 | D1930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Develop and Submit - 90% Landscaping Opportunity Plan | Review and Approve - 90% Landscaping Opportunity Plan | 0 |  |  | H
D2030 | D2170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Develop and Submit - Final Landscaping Opportunity Plan | Review and Approve - Final Landscaping Opportunity Plan | 0 |  |  | H
Admin-1045 | D1700 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Begin Design | Develop and Submit - 90% Landscaping Opportunity Plan | 0 |  |  | H
Admin-1045 | D1660 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Begin Design | Develop and Submit - 90% Signalization Plans | 0 |  |  | H
D1010 | D1080 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | Develop and Submit - Design Quality Management Plan | Review and Comment - Design Quality Management Plan | 0 |  |  | H
D1160 | D1180 | FS | In Progress | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | Revise and Resubmit - Design Quality Management Plan | Review and Approve - Design Quality Management Plan | 0 |  |  | H
D1080 | D1160 | FS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | Review and Comment - Design Quality Management Plan | Revise and Resubmit - Design Quality Management Plan | 0 |  |  | H
P1000 | P1010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | Develop and Submit - Construction Quality Control Plan | Review and Comment - Construction Quality Control Plan | 0 |  |  | H
P1020 | P1030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | Revise and Resubmit - Construction Quality Control Plan | Review and Approve - Construction Quality Control Plan | 0 |  |  | H
P1010 | P1020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | Review and Comment - Construction Quality Control Plan | Revise and Resubmit - Construction Quality Control Plan | 0 |  |  | H
Admin-1045 | D1010 | SS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.1.1 Design Quality Management Plan | Begin Design | Develop and Submit - Design Quality Management Plan | 0 |  |  | H
D1710 | D1740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | Modify and Submit - Environmental Resource Permit (ERP) | Review and Comment - Environmental Resource Permit (ERP) | 0 |  |  | H
D1030 | D1170 | FS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | Develop and Submit - Preliminary IDR Submittal Schedule | Independent Design Review Kickoff Meeting | 0 |  |  | H
Admin-1045 | D1030 | SS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.1.2 Preliminary IDR Submittal Schedule | Begin Design | Develop and Submit - Preliminary IDR Submittal Schedule | 0 |  |  | H
Admin-1045 | P1000 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.4.1.2 Construction Quality Control Plan | Begin Design | Develop and Submit - Construction Quality Control Plan | 0 |  |  | H
D1560 | D1760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Develop and Submit - 90% MoC Plan | Review and Approve - 90% MoC Plan | 0 |  |  | H
D1820 | D1940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Develop and Submit- Final MoC Plan | Review and Approve - Final MoC Plan | 0 |  |  | H
Admin-1045 | D1560 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Begin Design | Develop and Submit - 90% MoC Plan | 0 |  |  | H
D1740 | D1780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | Review and Comment - Environmental Resource Permit (ERP) | Resolve Comments and Issue - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1045 | D1040 | SS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.3 Design Survey/SUE | Begin Design | Perform Design Survey [LoE] | 0 |  |  | H
Admin-1045 | D1000 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Begin Design | Develop and Submit - 90% Erosion and Sediment Control Plan | 0 |  |  | H
D1810 | D1890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - Final Cat1 Brg 08 Plans - R3 | Review and Approve - Final Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1350 | D1540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1200 | D1460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Develop and Submit - 90% Roadway Plans - R1 | Review and Approve - 90% Roadway Plans - R1 | 0 |  |  | H
Admin-1045 | D1200 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Begin Design | Develop and Submit - 90% Roadway Plans - R1 | 0 |  |  | H
D1490 | D1570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Develop and Submit - Final Roadway Plans - R1 | Review and Approve - Final Roadway Plans - R1 | 0 |  |  | H
D1610 | D1670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Develop and Submit - Sign & Seal Roadway Plans - R1 | Issue - RFC Roadway Plans - R1 | 0 |  |  | H
D1680 | D1900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-1 | Review and Approve - 90% MSE Wall RW 1-1 | 0 |  |  | H
D1990 | D2130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-1 | Review and Approve - Final MSE Wall RW 1-1 | 0 |  |  | H
Admin-1045 | D1680 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Begin Design | Develop and Submit - 90% MSE Wall RW 1-1 | 0 |  |  | H
D1730 | D1950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Develop and Submit - 90% Landscape Plans | Review and Approve - 90% Landscape Plans | 0 |  |  | H
D2040 | D2180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Develop and Submit - Final Landscape Plans | Review and Approve - Final Landscape Plans | 0 |  |  | H
Admin-1045 | LoE100 | SS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1.1 Phase Durations | Begin Design | Design Phase [LoE] | 0 |  |  | H
D1130 | D1140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | I-275 - I-4 - IBL(all) - B1.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Develop and Submit - SWPPP & NOI | Review and Approve - SWPPP & NOI | 0 |  |  | H
D1250 | D1390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 2 | Review and Approve - 90% TTCP Plans - R1 Phase 2 | 0 |  |  | H
D1410 | D1470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - Final TTCP Plans - R1 Phase 2 | Review and Approve - Final TTCP Plans - R1 Phase 2 | 0 |  |  | H
D1510 | D1580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 | Issue - RFC TTCP Plans - R1 Phase 2 | 0 |  |  | H
Admin-1045 | D1250 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 (ASI) | Begin Design | Develop and Submit - 90% TTCP Plans - R1 Phase 2 | 0 |  |  | H
D1420 | D1550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | Review and Approve - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1600 | D1620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - Final TTCP Plans - R2 Phase 1 | Review and Approve - Final TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1770 | D1830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | Issue - RFC TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1910 | D2190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | Review and Approve - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2260 | D2400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - Final TTCP Plans - R2 Phase 2 | Review and Approve - Final TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2430 | D2460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 2 | Issue - RFC TTCP Plans - R2 Phase 2 | 0 |  |  | H
Admin-1045 | D1910 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Begin Design | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
D1260 | D1400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | Review and Approve - 90% TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1430 | D1480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Develop and Submit - Final TTCP Plans - R1 Phase 1 | Review and Approve - Final TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1520 | D1590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 1 | Issue - RFC TTCP Plans - R1 Phase 1 | 0 |  |  | H
Admin-1045 | D1260 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | Begin Design | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | 0 |  |  | H
D2050 | D2080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 08 Plans - R3 | Issue - RFC Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D2210 | D2310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-1 | Issue - RFC MSE Wall RW 1-1 | 0 |  |  | H
P1060 | P1090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | Develop and Submit - Settlement and Vibration Monitoring Plan | Review and Comment - Settlement and Vibration Monitoring Plan | 0 |  |  | H
P1120 | P1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | Revise and Resubmit - Settlement and Vibration Monitoring Plan | Review and Approve - Settlement and Vibration Monitoring Plan | 0 |  |  | H
P1090 | P1120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | Review and Comment - Settlement and Vibration Monitoring Plan | Revise and Resubmit - Settlement and Vibration Monitoring Plan | 0 |  |  | H
Admin-1045 | P1060 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | Begin Design | Develop and Submit - Settlement and Vibration Monitoring Plan | 0 |  |  | H
D1310 | D1330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - IBL(all) - B1.3.5 Erosion and Sediment Control Plan | Develop and Submit - Sign & Seal Erosion and Sediment Control Plan | Issue - RFC Erosion and Sediment Control Plan | 0 |  |  | H
D2320 | D2420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Develop and Submit - 90% Technical Specifications | Review and Approve - 90% Technical Specifications | 0 |  |  | H
Admin-1045 | D2320 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Begin Design | Develop and Submit - 90% Technical Specifications | 0 |  |  | H
D2450 | D2470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Develop and Submit - Final Technical Specifications | Review and Approve - Final Technical Specifications | 0 |  |  | H
D2490 | D2500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | I-275 - I-4 - IBL(all) - B1.3.16 Technical Specifications Submittal | Develop and Submit - Sign & Seal Technical Specifications | Issue - RFP Technical Specifications | 0 |  |  | H
D2060 | D2140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.12 Maintenance of Communication (MoC) Plan (DRMP) | Develop and Submit- Sign & Seal MoC Plan | Issue - RFC MoC Plan | 0 |  |  | H
D2220 | D2330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | I-275 - I-4 - IBL(all) - B1.3.18.20 Signalization Plans (ASI) | Develop and Submit - Sign & Seal Signalization Plans | Issue - RFC Signalization Plans | 0 |  |  | H
D1690 | D1920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Develop and Submit - 90% ITS Plans | Review and Approve - 90% ITS Plans | 0 |  |  | H
D2000 | D2150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Develop and Submit- Final ITS Plans | Review and Approve - Final ITS Plans | 0 |  |  | H
D2230 | D2340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Develop and Submit- Sign & Seal ITS Plans | Issue - RFC ITS Plans | 0 |  |  | H
Admin-1045 | D1690 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.14 ITS Plans (DRMP) | Begin Design | Develop and Submit - 90% ITS Plans | 0 |  |  | H
D2240 | D2350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) (ASI/DRMP) | Develop and Submit - Sign & Seal Signing and Pavement Marking Plan | Issue - RFC Signing and Pavement Marking Plan | 0 |  |  | H
D2250 | D2360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | I-275 - I-4 - IBL(all) - B1.3.18.22 Lighting Plans (DRMP) | Develop and Submit - Sign & Seal Lighting Plans | Issue - RFC Lighting Plans | 0 |  |  | H
D2270 | D2380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Develop and Submit - Sign & Seal Landscaping Opportunity Plan | Issue - RFC Landscaping Opportunity Plan | 0 |  |  | H
D2280 | D2390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Develop and Submit - Sign & Seal Landscape Plans | Issue - RFC Landscape Plans | 0 |  |  | H
Admin-1045 | D1730 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Begin Design | Develop and Submit - 90% Landscape Plans | 0 |  |  | H
D1220 | D1450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1440 | D1630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | Review and Approve - 90% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1320 | D1340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Review and Approve - 100% Dry Utility Relocation Plans | Develop and Submit - Sign & Seal Dry Utility Relocation Plans | 0 |  |  | H
D1240 | D1300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Review and Approve - 90% Dry Utility Relocation Plans | Develop and Submit - 100% Dry Utility Relocation Plans | 0 |  |  | H
D1300 | D1320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - 100% Dry Utility Relocation Plans | Review and Approve - 100% Dry Utility Relocation Plans | 0 |  |  | H
D1150 | D1240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - 90% Dry Utility Relocation Plans | Review and Approve - 90% Dry Utility Relocation Plans | 0 |  |  | H
D1050 | D1070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - 60% Dry Utility Relocation Plans | Review and Approve - 60% Dry Utility Relocation Plans | 0 |  |  | H
D1340 | D1370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Develop and Submit - Sign & Seal Dry Utility Relocation Plans | Issue - RFC Dry Utility Relocation Plans | 0 |  |  | H
Admin-1045 | D1050 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Begin Design | Develop and Submit - 60% Dry Utility Relocation Plans | 0 |  |  | H
D1070 | D1150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Review and Approve - 60% Dry Utility Relocation Plans | Develop and Submit - 90% Dry Utility Relocation Plans | 0 |  |  | H
A27430 | A27440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | Place GAB - 14th Ave Shared Use Path - Nebraska to 15th - R2 - P1 | Place Asphalt - 14th Ave Shared Use Path Nebraska to 15th - R2 - P1 | 0 | EW-ABC | SUB-ASPH | H
D2590 | D2600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Review and Approve - Final TTCP Plans - R3 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2570 | D2580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Review and Approve - 90% TTCP Plans - R3 Phase 2 | Develop and Submit - Final TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2560 | D2570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | Review and Approve - 90% TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2580 | D2590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - Final TTCP Plans - R3 Phase 2 | Review and Approve - Final TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2600 | D2610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 2 | Issue - RFC TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2650 | D2660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Review and Approve - Final TTCP Plans - R3 Phase 3 & 4 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2630 | D2640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Review and Approve - 90% TTCP Plans - R3 Phase 3 & 4 | Develop and Submit - Final TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2620 | D2630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | Review and Approve - 90% TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2640 | D2650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - Final TTCP Plans - R3 Phase 3 & 4 | Review and Approve - Final TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2660 | D2670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 3 & 4 | Issue - RFC TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2710 | D2720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Review and Approve - Final Roadway Plans - R2 | Develop and Submit - Sign & Seal Roadway Plans - R2 | 0 |  |  | H
D2690 | D2700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Review and Approve - 90% Roadway Plans - R2 | Develop and Submit - Final Roadway Plans - R2 | 0 |  |  | H
D2680 | D2690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Develop and Submit - 90% Roadway Plans - R2 | Review and Approve - 90% Roadway Plans - R2 | 0 |  |  | H
D2700 | D2710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Develop and Submit - Final Roadway Plans - R2 | Review and Approve - Final Roadway Plans - R2 | 0 |  |  | H
D2720 | D2730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Develop and Submit - Sign & Seal Roadway Plans - R2 | Issue - RFC Roadway Plans - R2 | 0 |  |  | H
D2770 | D2780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Review and Approve - Final Roadway Plans - R3 | Develop and Submit - Sign & Seal Roadway Plans - R3 | 0 |  |  | H
D2750 | D2760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Review and Approve - 90% Roadway Plans - R3 | Develop and Submit - Final Roadway Plans - R3 | 0 |  |  | H
D2740 | D2750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Review and Approve - 90% Roadway Plans - R3 | 0 |  |  | H
D2760 | D2770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Develop and Submit - Final Roadway Plans - R3 | Review and Approve - Final Roadway Plans - R3 | 0 |  |  | H
D2780 | D2790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Develop and Submit - Sign & Seal Roadway Plans - R3 | Issue - RFC Roadway Plans - R3 | 0 |  |  | H
D2930 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Cat2 Brg 02 Plans - R1 | Design Completion | 0 |  |  | H
Admin-1045 | D2860 | SS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Begin Design | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2910 | D2920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Review and Approve - Final Cat2 Brg 02 Plans - R1 | Develop and Submit - Sign & Seal Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2890 | D2900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2900 | D2910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | Review and Approve - Final Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2880 | D2890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2860 | D2870 | FS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2920 | D2930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - Sign & Seal Cat2 Brg 02 Plans - R1 | Issue - RFC Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2830 | D2840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Review and Approve - Final Cat1 Brg 03 Plans - R1 | Develop and Submit - Sign & Seal Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2810 | D2820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | Develop and Submit - Final Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2820 | D2830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Develop and Submit - Final Cat1 Brg 03 Plans - R1 | Review and Approve - Final Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2800 | D2810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2840 | D2850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 03 Plans - R1 | Issue - RFC Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2860 | D2880 | FS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2870 | D2890 | FS | In Progress | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2930 | P1270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.4.4.2.6 R1- Shop Drawings - Steel Bridge Girders | Issue - RFC Cat2 Brg 02 Plans - R1 | Develop and Submit - Girder Shop Drawings - Brg 2 - Cat 2 | 0 |  |  | H
D1670 | A1120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Issue - RFC Roadway Plans - R1 | Shift Traffic - Ramp WE Left - R1 - P1.S1 | 0 |  | TC-Maint. | H
D1830 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Issue - RFC TTCP Plans - R2 Phase 1 | Start Construction - R2 | 0 |  |  | H
D2460 | A22480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | Issue - RFC TTCP Plans - R2 Phase 2 | Shift Traffic - Ramp EN Left - R2 - P1 | 0 |  | TC-Maint. | H
D2730 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC Roadway Plans - R2 | Design Completion | 0 |  |  | H
D2730 | D1700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.18.23 Landscape Opportunity Plans (MDG) | Issue - RFC Roadway Plans - R2 | Develop and Submit - 90% Landscaping Opportunity Plan | 0 |  |  | H
D2730 | D1710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.6.3 FDEP Environmental Resource Permit (ERP) | Issue - RFC Roadway Plans - R2 | Modify and Submit - Environmental Resource Permit (ERP) | 0 |  |  | H
D2730 | D1730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.18.11 Landscape/Irrigation Plans (MDG) | Issue - RFC Roadway Plans - R2 | Develop and Submit - 90% Landscape Plans | 0 |  |  | H
D2730 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Issue - RFC Roadway Plans - R2 | Start Construction - R2 | 0 |  |  | H
D2610 | A26850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.3.4 R3 - Ph2, Stg1 - MOT | Issue - RFC TTCP Plans - R3 Phase 2 | Shift Traffic to New Ramp B & F - R3 - P2.S1 | 0 |  | TC-Maint. | H
D2670 | A30360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | Issue - RFC TTCP Plans - R3 Phase 3 & 4 | Shift Traffic - Ramp C Left - R3 - P3 | 0 |  | TC-Maint. | H
Admin-1045 | D2560 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Begin Design | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | 0 |  |  | H
Admin-1045 | D2620 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Begin Design | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2480 | D2560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2560 | D2620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 (DRMP) | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D1420 | D1910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 (ACP) | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2680 | D1420 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 (ACP) | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 20 |  |  | H
D2740 | D2480 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 20 |  |  | H
A27080 | A27270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Cut/Fill to Grade - Ramp EN Sta 91 to 103 - R2 - P1 | Grading - 10th St /14th Ave Intersection - R2 - P1 | 0 | EW-SML | EW- ALL EW | H
A16430 | A27270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Install DRG S-104 to S-113/S-112 - Ramp EN Sta 97 to 103 - R2 - P1 | Grading - 10th St /14th Ave Intersection - R2 - P1 | 0 | PIPE | EW- ALL EW | H
A34590 | A34600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Install DRG S-## to S-103 / OUT-5 - N Central Roadway - R3 - P4 | Place Stabilization - N Central Roadway - R3 - P4 | 0 | PIPE | EW-STAB | H
A34580 | A34590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Grading - N Central Roadway - R3 - P4 | Install DRG S-## to S-103 / OUT-5 - N Central Roadway - R3 - P4 | 0 | EW- ALL EW | PIPE | H
A34630 | A34640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Place Sidewalk - N CentralRoadway - R3 - P4 | Place Asphalt Surface - N CentralRoadway - R3 - P4 | 0 | FLATWORK | SUB-ASPH | H
A34620 | A34630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Place Curb - N Central Roadway - R3 - P4 | Place Sidewalk - N CentralRoadway - R3 - P4 | 0 | FLATWORK | FLATWORK | H
A34610 | A34620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Place GAB - N Central Roadway - R3 - P4 | Place Curb - N Central Roadway - R3 - P4 | 0 | EW-ABC | FLATWORK | H
A34600 | A34610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Place Stabilization - N Central Roadway - R3 - P4 | Place GAB - N Central Roadway - R3 - P4 | 0 | EW-STAB | EW-ABC | H
A34410 | A34580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | Finish Phase 3 - R3 - I-275 SB Right Widening | Grading - N Central Roadway - R3 - P4 | 0 |  | EW- ALL EW | H
A27030 | A26130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Install DRG S-156 to S-160 - Ramp B Sta 624 to 629 - R3 - P0 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 1 | 0 | PIPE | ST-MSE | H
A34660 | A34670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Install DRG S-575 to S-127 - Mitchell /Ross Inter /Palm SUP - R3 - P4 | Place Stabilization - Mitchell /RossInter / Palm SUP - R3 - P4 | 0 | PIPE | EW-STAB | H
A34650 | A34660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Grading - Mitchell /Ross Inter / Palm SUP - R3 - P4 | Install DRG S-575 to S-127 - Mitchell /Ross Inter /Palm SUP - R3 - P4 | 0 | EW- ALL EW | PIPE | H
A34700 | A34710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Sidewalk - Mitchell /RossInter / Palm SUP - R3 - P4 | Place Asphalt Surface - Mitchell /RossInter / Palm SUP - R3 - P4 | 0 | FLATWORK | SUB-ASPH | H
A34690 | A34700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Curb - Mitchell /RossInter / Palm SUP - R3 - P4 | Place Sidewalk - Mitchell /RossInter / Palm SUP - R3 - P4 | 0 | FLATWORK | FLATWORK | H
A34680 | A34690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place GAB - Mitchell /RossInter / Palm SUP - R3 - P4 | Place Curb - Mitchell /RossInter / Palm SUP - R3 - P4 | 0 | EW-ABC | FLATWORK | H
A34670 | A34680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Place Stabilization - Mitchell /RossInter / Palm SUP - R3 - P4 | Place GAB - Mitchell /RossInter / Palm SUP - R3 - P4 | 0 | EW-STAB | EW-ABC | H
A34410 | A34650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | Finish Phase 3 - R3 - I-275 SB Right Widening | Grading - Mitchell /Ross Inter / Palm SUP - R3 - P4 | 0 |  | EW- ALL EW | H
A34710 | A34540 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Place Asphalt Surface - Mitchell /RossInter / Palm SUP - R3 - P4 | Finish Phase 4 - R3 - Ramp C & G Gore | 0 | SUB-ASPH |  | H
A27020 | A25600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Install DRG OUT-3 to S-149 to S-153 - Ramp F Sta 504 to 508 - R3 - P0 | Const MSE Wall & Bkfill - RW 9-2 / Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | PIPE | ST-MSE | H
A27010 | A25280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Install DRG S-136C to S-133 to S-132 - Pond SMF 3A /Ramp B - R3 - P0 | Const MSE Wall & Bkfill - RW 9-1 / Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | PIPE | ST-MSE | H
A27000 | A24910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Install DRG S-123 to S-122/ S-139 to S-137 - Pond SMF 3A - R3 - P0 | Const MSE Wall & Bkfill - RW 8-2 / Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 | PIPE | ST-MSE | H
P1130 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.26 Noise Management Plan | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Review and Approve - Noise Management Plan | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 |  |  | H
P1150 | A15920 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Review and Approve - Settlement and Vibration Monitoring Plan | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | 0 |  |  | H
A20480 | A20580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Cure/Strip Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S3 | 0 |  | ST-BEAM | H
A21440 | A21570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Cure/Strip Abt Cap - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S2 | 0 |  | ST-BEAM | H
A25590 | A25400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Cure/Strip Abt Cap - Brg 100869 - End Bent 2 - R3 - P1.S2 | Erect Girders - Brg 100869 - Span 1 - R3 - P1.S2 | 0 |  | ST-BEAM | H
A33010 | A32820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Cure/Strip Abt Cap - Brg 100869 - End Bent 2 - R3 - P3 | Erect Girders - Brg 100869 - Span 1 - R3 - P3 | 0 |  | ST-BEAM | H
A35410 | A34810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.9 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Install I-275 NB Detour - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | 0 | TC-Maint. | ST-BEAM | H
A35410 | A35050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.9 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Install I-275 NB Detour - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | 0 | TC-Maint. | ST-BEAM | H
A35410 | A35320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.9 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Install I-275 NB Detour - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | 0 | TC-Maint. | ST-BEAM | H
A35410 | A35140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.9 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Install I-275 NB Detour - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | 0 | TC-Maint. | ST-BEAM | H
A34950 | A19250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - Brg 2 - R1 - P2.S1 | Finish Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | 0 | SUB-STRIP |  | H
A19250 | A21280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.11.5 R1 - Ph2, Stg2 - MOT | Finish Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | Shift Traffic - Ramp NE Left - R1 - P2.S2 | 0 |  | TC-Maint. | H
A20290 | A20200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.6.4 R1 - Ph2, Stg3, Step1 - MOT | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right | Install MOT - Ramp NE Left - R1 - P2.S3 Step 1 | 0 |  | TC-Maint. | H
A20720 | A20300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - Brg 100864 - R1 - P2.S3 | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | 0 | SUB-STRIP |  | H
A21100 | A20300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | 0 | SUB-ASPH |  | H
A21200 | A20300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | 0 | SUB-ASPH |  | H
A21210 | A20300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt - NE Shared Use Path - R1 - P2.S3 | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | 0 | SUB-ASPH |  | H
A22080 | A20290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right | 0 | SUB-ASPH |  | H
A22180 | A20290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Place Asphalt Shoulder - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right | 0 | SUB-ASPH |  | H
A21710 | A20290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Perm Striping - Brg 100864 - R1 - P2.S2 | Finish Phase 2 Stage 2 - R1 - Up-St Ramp NE Right | 0 | SUB-STRIP |  | H
A21240 | A21230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Install DRG S-4A5 to S-4B5 - NE Shared UsePath - R1 - P2.S3 | Place Stabilization - NE Shared Use Path - R1 - P2.S3 | 0 | PIPE | EW-STAB | H
A21220 | A21240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Grading - NE Shared Use Path - R1 - P2.S3 | Install DRG S-4A5 to S-4B5 - NE Shared UsePath - R1 - P2.S3 | 0 | EW- ALL EW | PIPE | H
A21120 | A21220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 1 | Grading - NE Shared Use Path - R1 - P2.S3 | 0 | ST-MSE | EW- ALL EW | H
A35570 | A35490 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | Temp Wall or SOE - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 |  | EW-STR | H
A35570 | A34720 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | Excavate - Brg 2 - Pier 1 - R1 - P2.S1 | 0 |  | EW-STR | H
A35570 | A34960 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | Excavate - Brg 2 - Pier 2 - R1 - P2.S1 | 0 |  | EW-STR | H
A35570 | A35230 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | Excavate - Brg 2 - Pier 3 - R1 - P2.S1 | 0 |  | EW-STR | H
A35570 | A35560 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | Temp Wall or SOE - Brg 2 - End Bent 2 - R1 - P2.S1 | 0 |  | EW-STR | H
A35570 | LoE130 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | R1 Phase 2 Stage 1 Step 1 - New Ramp NE-C Substructure [LoE] | 0 |  |  | H
A19250 | LoE150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | R1 Phase 2 Stage 2 - Up-St Ramp NE Right Construction [LoE] | 0 |  |  | H
A35590 | LoE130 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | R1 Phase 2 Stage 1 Step 1 - New Ramp NE-C Substructure [LoE] | 0 |  |  | H
A35580 | LoE360 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Start Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | R1 Phase 2 Stage 1 Step 2 - New Ramp NE-C Superstructure [LoE] | 0 |  |  | H
A19250 | LoE360 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.1.1.1 R1 Phase Durations | Finish Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | R1 Phase 2 Stage 1 Step 2 - New Ramp NE-C Superstructure [LoE] | 0 |  |  | H
A35470 | A35590 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Abt Cap - Brg 2 - End Bent 1 - R1 - P2.S1 | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 0 |  |  | H
A34800 | A35590 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Cap - Brg 2 - Pier 1 - R1 - P2.S1 | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 0 |  |  | H
A35040 | A35590 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Cap - Brg 2 - Pier 2 - R1 - P2.S1 | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 0 |  |  | H
A35310 | A35590 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Cap - Brg 2 - Pier 3 - R1 - P2.S1 | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 0 |  |  | H
A35540 | A35590 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Cure/Strip Abt Cap - Brg 2 - End Bent 2 - R1 - P2.S1 | Finish Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | 0 |  |  | H
A35580 | A35410 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.9 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - MOT | Start Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | Install I-275 NB Detour - R1 - P2.S1 | 0 |  | TC-Maint. | H
A17500 | A35580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Finish Phase 1 Stage 2 - R1 - Dn-St Ramp NE / I-4 Brg Widening | Start Phase 2 Stage 1 Step 2 - R1 - Brg 2 Ramp NE Flyover Superstructure | 0 |  |  | H
A22330 | A22480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.5.2 R2 - Ph0 - Ramp EN, I-4 WB - Temp Pavement - Sta. 82 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.2.6 R2 - Ph1 - Ramp EN MOT | Temp Striping - Ramp EN /I-4 Sta 91 to 101 - R2 - P1 | Shift Traffic - Ramp EN Left - R2 - P1 | 0 | SUB-STRIP | TC-Maint. | H
A27480 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt - 14th Ave Shared Use Path Nebraska to Columbus - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A27440 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.14 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to 15th Ave | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt - 14th Ave Shared Use Path Nebraska to 15th - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A27400 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Surface - Taliaferro Ave Sta 20 to 25 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A27330 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Surface - 10th St /14th Ave Intersection - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A27250 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Shoulder - I-4 Sta 311 to 320 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A27140 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Shoulder - Ramp EN Sta 91 to 103 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A22830 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Perm Striping - Brg 100650 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-STRIP |  | H
A23610 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Perm Striping - Brg 100652 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-STRIP |  | H
A24090 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Shoulder - Ramp EN Sta 83 to 88 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A24150 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Surface - 13th St /14th St Intersection - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A23270 | A22250 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Place Asphalt Shoulder - Ramp EN Sta 68 to 79 - R2 - P1 | Finish Phase 1 - R2 - Left Ramp EN Construction | 0 | SUB-ASPH |  | H
A22450 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Guardrail - Ramp EN /I-4 - R2 - P2 | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 | SUB-GRAIL |  | H
D1380 | A16490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.2 Right of Way | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Owner Right Of Way Acquisition Complete / Clear Date (7/1/24) | Start Construction - R2 | 0 |  |  | H
A22240 | A23990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | 0 |  | EW-SML | H
A22250 | A22280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.1.3 R2 - Ph2, Stp2 - MOT | Finish Phase 1 - R2 - Left Ramp EN Construction | Shift Traffic - Ramp EN Left - R2 - P2 Stp2 | 0 |  | TC-Maint. | H
A22350 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.5 R2 - Ph2, Stp3 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Shift Traffic - I-4 Right; I-275 Traffic Right - R1 - P2 | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 | TC-Maint. |  | H
A33420 | A34370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.4 R3 - Ph3 - Demo Existing Ramp B Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.5.17 R3 - Ph3 - Demo Existing Ramp B Over 7th Ave | Demo Substructure - Ramp B Brg Over Palm - R3 - P3 | Demo Superstructure - Ramp B Brg Over 7th Ave - R3 - P3 | 0 | DM-BRIDGE | DM-BRIDGE | H
A35630 | A35640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Stabilization - Ramp C / I-275 SB Gore - R3 - P4 | Place Asphalt Base - Ramp C /I-275 SB Gore - R3 - P4 | 0 | EW-STAB | SUB-ASPH | H
A35610 | A35630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Cut/Fill to Grade - Ramp C / I-275 SB Gore - R3 - P3 | Place Stabilization - Ramp C / I-275 SB Gore - R3 - P4 | 0 | EW-SML | EW-STAB | H
A35620 | A35630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place 3-Pour Barrier - Ramp C / I-275 SB Gore - R3 - P3 | Place Stabilization - Ramp C / I-275 SB Gore - R3 - P4 | 0 | SUB-BR-SLIP | EW-STAB | H
A35610 | A35620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Cut/Fill to Grade - Ramp C / I-275 SB Gore - R3 - P3 | Place 3-Pour Barrier - Ramp C / I-275 SB Gore - R3 - P3 | 0 | EW-SML | SUB-BR-SLIP | H
A35670 | A35680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Shoulder GAB - Ramp C /I-275 SB Gore - R3 - P4 | Place Asphalt Shoulder - Ramp C /I-275 SB Gore - R3 - P4 | 0 | EW-ABC | SUB-ASPH | H
A35660 | A35670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Edge Drain - Ramp C /I-275 SB Gore - R3 - P4 | Place Shoulder GAB - Ramp C /I-275 SB Gore - R3 - P4 | 0 | PIPE | EW-ABC | H
A35650 | A35660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Concrete Pav - Ramp C /I-275 SB Gore - R3 - P4 | Place Edge Drain - Ramp C /I-275 SB Gore - R3 - P4 | 0 | CP-SLIP | PIPE | H
A35640 | A35650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Asphalt Base - Ramp C /I-275 SB Gore - R3 - P4 | Place Concrete Pav - Ramp C /I-275 SB Gore - R3 - P4 | 0 | SUB-ASPH | CP-SLIP | H
A35700 | A34540 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.6 R3 - Ph4 - Final MOT | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Shift Traffic - Ramp C Left - R3 - P4 - Final MOT | Finish Phase 4 - R3 - Ramp C & G Gore | 0 | TC-Maint. |  | H
A35720 | A35730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Install SIP - Brg 2 - Pour 5 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A35730 | A35740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Install Overhangs - Brg 2 - Pour 5 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A35740 | A35750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Reinforce Deck - Brg 2 - Pour 5 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A35750 | A35760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Place Deck - Brg 2 - Pour 5 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | ST-POUR |  | H
A35760 | A35770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Cure Deck - Brg 2 - Pour 5 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 5 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A35810 | A35820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Install SIP - Brg 2 - Pour 6 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A35820 | A35830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Install Overhangs - Brg 2 - Pour 6 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A35830 | A35840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Reinforce Deck - Brg 2 - Pour 6 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A35840 | A35850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Place Deck - Brg 2 - Pour 6 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | ST-POUR |  | H
A35850 | A35860 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Cure Deck - Brg 2 - Pour 6 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 6 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A35900 | A35910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Install SIP - Brg 2 - Pour 7 - R1 - P2.S1 | Install Overhangs - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A35910 | A35920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Install Overhangs - Brg 2 - Pour 7 - R1 - P2.S1 | Reinforce Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | ST-DECK | SUB-ST-REBAR | H
A35920 | A35930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Reinforce Deck - Brg 2 - Pour 7 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A35930 | A35940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Place Deck - Brg 2 - Pour 7 - R1 - P2.S1 | Cure Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | ST-POUR |  | H
A35940 | A35950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Cure Deck - Brg 2 - Pour 7 - R1 - P2.S1 | Install Reinf Barrier - Brg 2 - Pour 7 - R1 - P2.S1 | 0 |  | SUB-ST-REBAR | H
A35930 | A34910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Place Deck - Brg 2 - Pour 7 - R1 - P2.S1 | FRPS Approach Slab 2 - Brg 2 - R1 - P2.S1 | 0 | ST-POUR | ST-APPR | H
A35760 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 5 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A35850 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 6 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A35940 | A34930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Cure Deck - Brg 2 - Pour 7 - R1 - P2.S1 | Grind Deck - Brg 2 - R1 - P2.S1 | 0 |  | SUB-DGRIND | H
A24880 | A25290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Drive Pile - Brg 100868 - End Bent 2 - R3 - P1.S2 | Temp Wall or SOE - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | ST-PILE | EW-STR | H
A34800 | A35970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Cure/Strip Cap - Brg 2 - Pier 1 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 3 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A35990 | A34810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Erect Falsework - Brg 2 - Spans 1-2 - R1 - P2.S1 | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | 0 | ST-BEAM | ST-BEAM | H
A35570 | A35990 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | Start Phase 2 Stage 1 Step 1 - R1 - Brg 2 Ramp NE Flyover Substructure | Erect Falsework - Brg 2 - Spans 1-2 - R1 - P2.S1 | 0 |  | ST-BEAM | H
A34850 | A35360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | ST-POUR | ST-POUR | H
A35360 | A35750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Place Deck - Brg 2 - Pour 3 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | ST-POUR | ST-POUR | H
A35750 | A35930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Place Deck - Brg 2 - Pour 5 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | ST-POUR | ST-POUR | H
A35180 | A35840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Place Deck - Brg 2 - Pour 4 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | ST-POUR | ST-POUR | H
A14700 | A14720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | EW-STR | ST-PILE | H
A15120 | A15140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | EW-STR | ST-PILE | H
A1630 | A1650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - IBL(all) - B1.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | EW- ALL EW | ST-PILE | H
A15050 | A15070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | EW- ALL EW | ST-PILE | H
A17430 | A17270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | I-275 - I-4 - IBL(all) - B1.2.2.4.8 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 1 - Sta. 250 to 251 | Demo Brick tower - Brg 100656 - End Bent 1 - R1 - P1.S2 | Drive Pile - Brg 100656 - End Bent 1 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-PILE | H
A17440 | A17360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | Demo Brick tower - Brg 100656 - End Bent 2 - R1 - P1.S2 | Drive Pile - Brg 100656 - End Bent 2 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-PILE | H
A18130 | A17980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | Demo Brick tower - Brg 100657 - End Bent 1 - R1 - P1.S2 | Drive Pile - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-PILE | H
A18140 | A18060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | I-275 - I-4 - IBL(all) - B1.2.2.4.11 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 2 - Sta. 256 to 257 | Demo Brick tower - Brg 100657 - End Bent 2 - R1 - P1.S2 | Drive Pile - Brg 100657 - End Bent 2 - R1 - P1.S2 | 0 | DM-BRIDGE | ST-PILE | H
A35430 | A35450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | Grading - Brg 2 - End Bent 1 - R1 - P2.S1 | Drive Pile - Brg 2 - End Bent 1 - R1 - P2.S1 | 0 | EW- ALL EW | ST-PILE | H
A35500 | A35520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | I-275 - I-4 - IBL(all) - B1.2.2.3.13 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 2 - Sta. 126 to 127 | Grading - Brg 2 - End Bent 2 - R1 - P2.S1 | Drive Pile - Brg 2 - End Bent 2 - R1 - P2.S1 | 0 | EW- ALL EW | ST-PILE | H
A34720 | A34740 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Excavate - Brg 2 - Pier 1 - R1 - P2.S1 | Drive Pile - Brg 2 - Pier 1 - R1 - P2.S1 | 0 | EW-STR | ST-PILE | H
A34960 | A34980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Excavate - Brg 2 - Pier 2 - R1 - P2.S1 | Drive Pile - Brg 2 - Pier 2 - R1 - P2.S1 | 0 | EW-STR | ST-PILE | H
A35230 | A35250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Excavate - Brg 2 - Pier 3 - R1 - P2.S1 | Drive Pile - Brg 2 - Pier 3 - R1 - P2.S1 | 0 | EW-STR | ST-PILE | H
A21320 | A21340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Grading - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 | EW- ALL EW | ST-PILE | H
P1200 | A21340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.11.1 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Procure Pile - Bridge 1 - R1 | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S2 - right | 0 |  | ST-PILE | H
A21400 | A21420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Grading - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 | EW- ALL EW | ST-PILE | H
P1200 | A21420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.11.2 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Procure Pile - Bridge 1 - R1 | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S2 - right | 0 |  | ST-PILE | H
A20340 | A20360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Grading - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 | EW- ALL EW | ST-PILE | H
P1200 | A20360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.6.1 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 1 - Sta. 131 to 132 | Procure Pile - Bridge 1 - R1 | Drive Pile - Brg 100864 - End Bent 1 - R1 - P2.S3 - left | 0 |  | ST-PILE | H
A20420 | A20440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Grading - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 | EW- ALL EW | ST-PILE | H
P1200 | A20440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - IBL(all) - B1.2.2.6.2 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - End Bent 2 - Sta. 133 to 134 | Procure Pile - Bridge 1 - R1 | Drive Pile - Brg 100864 - End Bent 2 - R1 - P2.S3 - left | 0 |  | ST-PILE | H
A22600 | A22620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.1 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 1 | Excavate - Brg 100650 - Pier 1 - R2 - P1 | Drive Pile - Brg 100650 - Pier 1 - R2 - P1 | 0 | EW-STR | ST-PILE | H
A22980 | A23000 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.2 R2 - Ph1 - Bridge 100650 Ramp EN - Pier 2 | Excavate - Brg 100650 - Pier 2 - R2 - P1 | Drive Pile - Brg 100650 - Pier 2 - R2 - P1 | 0 | EW-STR | ST-PILE | H
A22520 | A22540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Grading - Brg 100650 - End Bent 1 - R2 - P1 | Drive Pile - Brg 100650 - End Bent 1 - R2 - P1 | 0 | EW- ALL EW | ST-PILE | H
A22910 | A22930 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | I-275 - I-4 - IBL(all) - B1.2.3.2.3 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 2 - Sta. 91 to 92 | Grading - Brg 100650 - End Bent 2 - R2 - P1 | Drive Pile - Brg 100650 - End Bent 2 - R2 - P1 | 0 | EW- ALL EW | ST-PILE | H
A23380 | A23400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.1 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 1 | Excavate - Brg 100652 - Pier 1 - R2 - P1 | Drive Pile - Brg 100652 - Pier 1 - R2 - P1 | 0 | EW-STR | ST-PILE | H
A23690 | A23710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Excavate - Brg 100652 - Pier 2 - R2 - P1 | Drive Pile - Brg 100652 - Pier 2 - R2 - P1 | 0 | EW-STR | ST-PILE | H
A23300 | A23320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | I-275 - I-4 - IBL(all) - B1.2.3.2.7 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 1 - Sta. 79 to 80 | Grading - Brg 100652 - End Bent 1 - R2 - P1 | Drive Pile - Brg 100652 - End Bent 1 - R2 - P1 | 0 | EW- ALL EW | ST-PILE | H
A23620 | A23640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | I-275 - I-4 - IBL(all) - B1.2.3.2.8 R2 - Ph1 - Bridge 100652 Ramp EN Over Columbus - End Bent 2 - Sta. 82 to 83 | Grading - Brg 100652 - End Bent 2 - R2 - P1 | Drive Pile - Brg 100652 - End Bent 2 - R2 - P1 | 0 | EW- ALL EW | ST-PILE | H
A24550 | A24570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Prep for Drill Shafts - Brg 100868 - Pier 1 - R3 - P1.S2 | Install Drilled Shaft - Brg 100868 - Pier 1 - R3 - P1.S2 | 0 | EW-STR | SUB-ST-DRSFT | H
A24930 | A24950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Prep for Drill Shafts - Brg 100868 - Pier 2 - R3 - P1.S2 | Install Drilled Shaft - Brg 100868 - Pier 2 - R3 - P1.S2 | 0 | EW-STR | SUB-ST-DRSFT | H
A26400 | A26420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Excavate - Brg 100868 - Pier 3 - R3 - P1.S2 | Drive Pile - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 | EW-STR | ST-PILE | H
A24950 | A26420 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.7 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 3 | Install Drilled Shaft - Brg 100868 - Pier 2 - R3 - P1.S2 | Drive Pile - Brg 100868 - Pier 3 - R3 - P1.S2 | 0 | SUB-ST-DRSFT | ST-PILE | H
A24470 | A24490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Grading - Brg 100868 - End Bent 1 - R3 - P1.S2 | Install Drilled Shaft - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | EW- ALL EW | SUB-ST-DRSFT | H
A24860 | A24880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | Grading - Brg 100868 - End Bent 2 - R3 - P1.S2 | Drive Pile - Brg 100868 - End Bent 2 - R3 - P1.S2 | 0 | EW- ALL EW | ST-PILE | H
A25230 | A25250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | Grading - Brg 100869 - End Bent 1 - R3 - P1.S2 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P1.S2 | 0 | EW- ALL EW | ST-PILE | H
A25230 | A25890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Grading - Brg 100869 - End Bent 1 - R3 - P1.S2 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | EW- ALL EW | EW-STR | H
A25550 | A25570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | Grading - Brg 100869 - End Bent 2 - R3 - P1.S2 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P1.S2 | 0 | EW- ALL EW | ST-PILE | H
A28500 | A28370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Demo Abut - Brg 100139 - End Bent 1 - R3 - P2.S2 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-PILE | H
A28510 | A28440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P2.S2 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-PILE | H
A29170 | A29040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Demo Abut - Brg 100141 - End Bent 1 - R3 - P2.S2 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-PILE | H
A29180 | A29110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Demo Abut - Brg 100141 - End Bent 2 - R3 - P2.S2 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 | DM-BRIDGE | ST-PILE | H
A30960 | A30830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Demo Abut - Brg 100139 - End Bent 1 - R3 - P3 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P3 | 0 | DM-BRIDGE | ST-PILE | H
A30970 | A30900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P3 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P3 | 0 | DM-BRIDGE | ST-PILE | H
A31570 | A31440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Demo Abut - Brg 100141 - End Bent 1 - R3 - P3 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P3 | 0 | DM-BRIDGE | ST-PILE | H
A31580 | A31510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Demo Abut - Brg 100141 - End Bent 2 - R3 - P3 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P3 | 0 | DM-BRIDGE | ST-PILE | H
A32660 | A32680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.5.6 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 1 - Sta. 618 to 619 | Grading - Brg 100869 - End Bent 1 - R3 - P3 | Drive Pile - Brg 100869 - End Bent 1 - R3 - P3 | 0 | EW- ALL EW | ST-PILE | H
A32970 | A32990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.5.14 R3 - Ph3 - Bridge 100869 - Ramp B Over Palm - End Bent 2 - Sta. 620 to 621 | Grading - Brg 100869 - End Bent 2 - R3 - P3 | Drive Pile - Brg 100869 - End Bent 2 - R3 - P3 | 0 | EW- ALL EW | ST-PILE | H
A30360 | A33880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.18 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bend 1 - Sta. 707 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100143 - End Bent 1 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A30360 | A33950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Shift Traffic - Ramp C Left - R3 - P3 | Grading - Brg 100143 - End Bent 2 - R3 - P3 | 0 | TC-Maint. | EW- ALL EW | H
A27910 | A29440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A29470 | A29600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | Install Drilled Shaft - Brg 100139 - Pier 3 - R3 - P2.S2 | FRP Footing - Brg 100139 - Pier 4 - R3 - P2.S2 | 0 | SUB-ST-DRSFT | ST-FOOT | H
A28580 | A30340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.8 R3 - Ph2, Stg2 - Bridge 100141 - Pier 2 | Drive Pile - Brg 100141 - Pier 1 - R3 - P2.S2 | FRP Footing - Brg 100141 - Pier 2 - R3 - P2.S2 | 0 | ST-PILE | ST-FOOT | H
A34060 | A33470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | Cure/Strip Footing - Brg 100143 - Pier 1 - R3 - P3 | Cure/Strip Column - Brg 100143 - Pier 1 - R3 - P3 | 0 |  |  | H
A34090 | A33850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | Cure/Strip Footing - Brg 100143 - Pier 2 - R3 - P3 | Cure/Strip Column - Brg 100143 - Pier 2 - R3 - P3 | 0 |  |  | H
A14790 | A14800 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | Install SIP - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A15210 | A15230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | Install SIP - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A15300 | A15320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Erect Girders - Brg 100865 - Span 3 - R1 - P1.S1 | Install SIP - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A16770 | A16780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | Erect Girders - Brg 100656 - Span 1 - R1 - P1.S2 | Install SIP - Brg 100656 - Span 1 - R1 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A17010 | A17020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Erect Girders - Brg 100656 - Span 2 - R1 - P1.S2 | Install SIP - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A17100 | A17110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | Erect Girders - Brg 100656 - Span 3 - R1 - P1.S2 | Install SIP - Brg 100656 - Span 3 - R1 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A17570 | A17580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | Erect Girders - Brg 100657 - Span 1 - R1 - P1.S2 | Install SIP - Brg 100657 - Span 1 - R1 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A17720 | A17730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | Erect Girders - Brg 100657 - Span 2 - R1 - P1.S2 | Install SIP - Brg 100657 - Span 2 - R1 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A17810 | A17820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | Erect Girders - Brg 100657 - Span 3 - R1 - P1.S2 | Install SIP - Brg 100657 - Span 3 - R1 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A34810 | A34820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35050 | A35150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 4 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35970 | A35330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Erect Girders - Brg 2 - Spans 3 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35320 | A35900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35140 | A35720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35140 | A35810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35140 | A34850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Erect Girders - Brg 2 - Spans 8-9 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-BEAM | ST-POUR | H
A35320 | A35720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35320 | A35810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35320 | A34850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Erect Girders - Brg 2 - Spans 6-7 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-BEAM | ST-POUR | H
A35050 | A35720 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A35050 | A34850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Erect Girders - Brg 2 - Spans 4-5 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-BEAM | ST-POUR | H
A35970 | A34850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Erect Girders - Brg 2 - Spans 3 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-BEAM | ST-POUR | H
A34810 | A34850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | Place Deck - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | ST-BEAM | ST-POUR | H
A21570 | A21580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S2 | Install SIP - Brg 100864 - Span 1 - R1 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A20580 | A20590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | Erect Girders - Brg 100864 - Span 1 - R1 - P2.S3 | Install SIP - Brg 100864 - Span 1 - R1 - P2.S3 | 0 | ST-BEAM | SUB-ST-SIP | H
A22690 | A22700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | Erect Girders - Brg 100650 - Span 1 - R2 - P1 | Install SIP - Brg 100650 - Span 1 - R2 - P1 | 0 | ST-BEAM | SUB-ST-SIP | H
A23070 | A23080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | Erect Girders - Brg 100650 - Span 2 - R2 - P1 | Install SIP - Brg 100650 - Span 2 - R2 - P1 | 0 | ST-BEAM | SUB-ST-SIP | H
A23160 | A23170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | Erect Girders - Brg 100650 - Span 3 - R2 - P1 | Install SIP - Brg 100650 - Span 3 - R2 - P1 | 0 | ST-BEAM | SUB-ST-SIP | H
A23470 | A23480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | Erect Girders - Brg 100652 - Span 1 - R2 - P1 | Install SIP - Brg 100652 - Span 1 - R2 - P1 | 0 | ST-BEAM | SUB-ST-SIP | H
A23780 | A23790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Erect Girders - Brg 100652 - Span 2 - R2 - P1 | Install SIP - Brg 100652 - Span 2 - R2 - P1 | 0 | ST-BEAM | SUB-ST-SIP | H
A23870 | A23880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Erect Girders - Brg 100652 - Span 3 - R2 - P1 | Install SIP - Brg 100652 - Span 3 - R2 - P1 | 0 | ST-BEAM | SUB-ST-SIP | H
A24640 | A24650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | Erect Girders - Brg 100868 - Span 1 - R3 - P1.S2 | Install SIP - Brg 100868 - Span 1 - R3 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A25020 | A25030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | Erect Girders - Brg 100868 - Span 2 - R3 - P1.S2 | Install SIP - Brg 100868 - Span 2 - R3 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A26490 | A26500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | Erect Girders - Brg 100868 - Span 3 - R3 - P1.S2 | Install SIP - Brg 100868 - Span 3 - R3 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A25110 | A25120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | Erect Girders - Brg 100868 - Span 4 - R3 - P1.S2 | Install SIP - Brg 100868 - Span 4 - R3 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A25400 | A25410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | Erect Girders - Brg 100869 - Span 1 - R3 - P1.S2 | Install SIP - Brg 100869 - Span 1 - R3 - P1.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A27960 | A27970 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | Erect Girders - Brg 100139 - Span 1 - R3 - P2.S2 | Install SIP - Brg 100139 - Span 1 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A28110 | A28120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | Erect Girders - Brg 100139 - Span 2 - R3 - P2.S2 | Install SIP - Brg 100139 - Span 2 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A28200 | A28210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | Erect Girders - Brg 100139 - Span 3 - R3 - P2.S2 | Install SIP - Brg 100139 - Span 3 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A29860 | A29870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.13 R3 - Ph2, Stg2 - Bridge 100139 - Span 4 | Erect Girders - Brg 100139 - Span 4 - R3 - P2.S2 | Install SIP - Brg 100139 - Span 4 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A29950 | A29960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | Erect Girders - Brg 100139 - Span 5 - R3 - P2.S2 | Install SIP - Brg 100139 - Span 5 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A30040 | A30050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | Install SIP - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A28630 | A28640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | Erect Girders - Brg 100141 - Span 1 - R3 - P2.S2 | Install SIP - Brg 100141 - Span 1 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A28780 | A28790 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | Erect Girders - Brg 100141 - Span 2 - R3 - P2.S2 | Install SIP - Brg 100141 - Span 2 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A28870 | A28880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | Erect Girders - Brg 100141 - Span 3 - R3 - P2.S2 | Install SIP - Brg 100141 - Span 3 - R3 - P2.S2 | 0 | ST-BEAM | SUB-ST-SIP | H
A30480 | A30490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | Erect Girders - Brg 100139 - Span 1 - R3 - P3 | Install SIP - Brg 100139 - Span 1 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A30720 | A30730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | Erect Girders - Brg 100139 - Span 3 - R3 - P3 | Install SIP - Brg 100139 - Span 3 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A32160 | A32170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.13 R3 - Ph3 - Bridge 100139 - Span 4 | Erect Girders - Brg 100139 - Span 4 - R3 - P3 | Install SIP - Brg 100139 - Span 4 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A32250 | A32260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.14 R3 - Ph3 - Bridge 100139 - Span 5 | Erect Girders - Brg 100139 - Span 5 - R3 - P3 | Install SIP - Brg 100139 - Span 5 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A32340 | A32350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Erect Girders - Brg 100139 - Span 6 - R3 - P3 | Install SIP - Brg 100139 - Span 6 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A31040 | A31050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | Erect Girders - Brg 100141 - Span 1 - R3 - P3 | Install SIP - Brg 100141 - Span 1 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A31190 | A31200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | Erect Girders - Brg 100141 - Span 2 - R3 - P3 | Install SIP - Brg 100141 - Span 2 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A31280 | A31290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | Erect Girders - Brg 100141 - Span 3 - R3 - P3 | Install SIP - Brg 100141 - Span 3 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A33500 | A33510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | Erect Girders - Brg 100143 - Span 1 - R3 - P3 | Install SIP - Brg 100143 - Span 1 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A33650 | A33660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | Erect Girders - Brg 100143 - Span 2 - R3 - P3 | Install SIP - Brg 100143 - Span 2 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A33740 | A33750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | Erect Girders - Brg 100143 - Span 3 - R3 - P3 | Install SIP - Brg 100143 - Span 3 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A32820 | A32830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | Erect Girders - Brg 100869 - Span 1 - R3 - P3 | Install SIP - Brg 100869 - Span 1 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A15910 | A36110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 1 Stage 1 - R1 - 13th Ave | Install Landscaping - Ramp NE / WE | 0 |  |  | H
A22240 | A36120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | Install Landscaping - Ramp EN | 0 |  |  | H
A36120 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Landscaping - Ramp EN | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 |  |  | H
A26580 | A36130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | Install Landscaping - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A15910 | A36140 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 1 Stage 1 - R1 - 13th Ave | Install Grass - Ramp NE / WE | 0 |  |  | H
A22240 | A36150 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | Install Grass - Ramp EN | 0 |  |  | H
A36150 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Grass - Ramp EN | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 |  |  | H
A26580 | A36160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | Install Grass - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A15910 | A36170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 1 Stage 1 - R1 - 13th Ave | Install ITS - Ramp NE / WE | 0 |  |  | H
A22240 | A36180 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | Install ITS - Ramp EN | 0 |  |  | H
A36180 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install ITS - Ramp EN | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 |  |  | H
A26580 | A36190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | Install ITS - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A15910 | A36200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 1 Stage 1 - R1 - 13th Ave | Install LIghting - Ramp NE / WE | 0 |  |  | H
A15910 | A36210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 1 Stage 1 - R1 - 13th Ave | Install Signals - Ramp NE / WE | 0 |  |  | H
A22240 | A36220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | Install Lighting - Ramp EN | 0 |  |  | H
A36220 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.6 R001.02 - Ramp EN Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Install Lighting - Ramp EN | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 |  |  | H
A26580 | A36240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | Finish Phase 0 - R3 - 60" Storm Drainage Sytem (incl Abandon exist) | Install Lighting - Ramp F / Ramp B / Ramp C / Ramp G / I | 0 |  |  | H
A30630 | A30640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | Erect Girders - Brg 100139 - Span 2 - R3 - P3 | Install SIP - Brg 100139 - Span 2 - R3 - P3 | 0 | ST-BEAM | SUB-ST-SIP | H
A22200 | A36110 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 3 - R1 - Resurface Signs Markings | Install Landscaping - Ramp NE / WE | 0 |  |  | H
A22200 | A36140 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 3 - R1 - Resurface Signs Markings | Install Grass - Ramp NE / WE | 0 |  |  | H
A22200 | A36170 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 3 - R1 - Resurface Signs Markings | Install ITS - Ramp NE / WE | 0 |  |  | H
A22200 | A36200 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 3 - R1 - Resurface Signs Markings | Install LIghting - Ramp NE / WE | 0 |  |  | H
A22200 | A36210 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Finish Phase 3 - R1 - Resurface Signs Markings | Install Signals - Ramp NE / WE | 0 |  |  | H
Admin-1070 | Admin-1040 | FF | Not Started | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Contract Completion (Nov. 3rd 2026) | LOE - Project Duration | 0 |  |  | H
D1200 | D1680 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-1 | 0 |  |  | H
A21260 | A21210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Place Curb - NE Shared Use Path - R1 - P2.S3 | Place Asphalt - NE Shared Use Path - R1 - P2.S3 | 0 | FLATWORK | SUB-ASPH | H
A16560 | A16590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Place Stabilization - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Place Asphalt Base - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 0 | EW-STAB | SUB-ASPH | H
A16500 | A16530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Shift Traffic - Ramp NE Right - R1 - P1.S2 | Const MSE Wall & Bkfill - RW 103 - I-4 Sta 311 to 320 - R2 - P1 | 0 | TC-Maint. | ST-MSE | H
A22020 | A21995 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Const MSE Wall & Bkfill - RW 2-3 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | EW-SML | ST-MSE | H
A21995 | A22030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 2-3 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | 0 | ST-MSE | EW-STAB | H
A21000 | A21015 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 1 | 0 | EW-SML | ST-MSE | H
A21015 | A21030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 1 | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | ST-MSE | EW-STAB | H
A22120 | A21120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 1 | 0 | EW-SML | ST-MSE | H
A21120 | A22100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 1 | Place 3-Pour Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | ST-MSE | SUB-BR-SLIP | H
A21110 | A21130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.8 R1 - Ph2, Stg3 - Left Ramp NE - Columbus to Start - Sta. 134 to 137 | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | Place Stabilization - Ramp NE Sta 134 to 137 - R1 - P2.S3 - left | 0 | EW-SML | EW-STAB | H
A21995 | A22120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 2-3 - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | ST-MSE | EW-SML | H
A17150 | A16900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.5 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Cure Deck - Brg 100656 - Span 3 - R1 - P1.S2 | Groove Deck - Brg 100656 - R1 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A17060 | A16900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Cure Deck - Brg 100656 - Span 2 - R1 - P1.S2 | Groove Deck - Brg 100656 - R1 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A16820 | A16900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | Cure Deck - Brg 100656 - Span 1 - R1 - P1.S2 | Groove Deck - Brg 100656 - R1 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A16870 | A16900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | FRPS Approach Slab 2 - Brg 100656 - R1 - P1.S2 | Groove Deck - Brg 100656 - R1 - P1.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A16860 | A16900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.3.6 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Finishes | FRPS Approach Slab 1 - Brg 100656 - R1 - P1.S2 | Groove Deck - Brg 100656 - R1 - P1.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A17860 | A17700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.5 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Cure Deck - Brg 100657 - Span 3 - R1 - P1.S2 | Groove Deck - Brg 100657 - R1 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A17770 | A17700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.2 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Cure Deck - Brg 100657 - Span 2 - R1 - P1.S2 | Groove Deck - Brg 100657 - R1 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A17620 | A17700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.3 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | Cure Deck - Brg 100657 - Span 1 - R1 - P1.S2 | Groove Deck - Brg 100657 - R1 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A17670 | A17700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | FRPS Approach Slab 2 - Brg 100657 - R1 - P1.S2 | Groove Deck - Brg 100657 - R1 - P1.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A17660 | A17700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.4.12.6 R1 - Ph1, Stg2 - Bridge 100657 Widening Over 15th St - Finishes | FRPS Approach Slab 1 - Brg 100657 - R1 - P1.S2 | Groove Deck - Brg 100657 - R1 - P1.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A18210 | A18240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Place Stabilization - I-4 Sta 250 to 266 - R1 - P1.S2 | Place Asphalt Base - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | EW-STAB | SUB-ASPH | H
A18370 | A18390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Place Curb - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | Place Asphalt Surface - 13th Ave Right Sta 24 to 40 - R1 - P1.S2 | 0 | FLATWORK | SUB-ASPH | H
A1060 | A15940 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.1.3 R1 - Ph0 - Traffic Shift | I-275 - I-4 - IBL(all) - B1.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Shift Traffic - I-4 Exit 1 Ramp Left - R1 - P0 | Shift Traffic - 13th Ave Right - R1 - P1.S1 Step 1 | 0 | TC-Maint. | TC-Maint. | H
A15080 | A15455 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 / Brg 100865 - End Bent 2 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 2 | 0 | ST-MSE | EW-SML | H
A15460 | A15570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 1 | Place 3-Pour Barrier - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | ST-MSE | SUB-BR-SLIP | H
A15450 | A15550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - left | 0 | EW-SML | ST-MSE | H
A15455 | A15465 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 2 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 2 | 0 | EW-SML | ST-MSE | H
A15450 | A15465 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Cut/Fill to Grade - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - part 1 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 2 | 0 | EW-SML | ST-MSE | H
A15465 | A15580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.8 R1 - Ph1, Stg1 - Ramp NE - Bridge to 10th St. - Sta. 110 to 116 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 2 | Cut/Fill to Grade - Ramp NE Sta 110 to 116 - R1 - P1.S1 | 0 | ST-MSE | EW-SML | H
A15465 | A15570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | I-275 - I-4 - IBL(all) - B1.2.2.2.7 R1 - Ph1, Stg1 - Ramp WE-B - Bridge to 12th St. - Sta. 50 to 60 | Const MSE Wall & Bkfill - RW 5-2 - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 - right - part 2 | Place 3-Pour Barrier - Ramp WE-B Sta 50 to 60 - R1 - P1.S1 | 0 | ST-MSE | SUB-BR-SLIP | H
A15830 | A15850 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | I-275 - I-4 - IBL(all) - B1.2.2.2.11 R1 - Ph1, Stg1 - Ramp NE - 10th St. to 14th St. - Sta. 97 to 110 | Cut/Fill to Grade - Ramp NE Sta 97 to 110 - R1 - P1.S1 | Place Stabilization - Ramp NE Sta 97 to 110 - R1 - P1.S1 | 0 | EW-SML | EW-STAB | H
A16000 | A16010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Place Curb - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | Place Asphalt Surface - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 0 | FLATWORK | SUB-ASPH | H
A16110 | A16130 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - IBL(all) - B1.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Curb - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place Asphalt Surface - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | FLATWORK | SUB-ASPH | H
A16050 | A16070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | I-275 - I-4 - IBL(all) - B1.2.2.12.1 R1 - Ph1, Stg1 - Right 13th Ave - 14th St. to 15th St. | Place Curb - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | Place Asphalt Surface - 13th Ave Sta 13 to 16 - R1 - P1.S1 - right | 0 | FLATWORK | SUB-ASPH | H
A16190 | A16210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | I-275 - I-4 - IBL(all) - B1.2.2.12.8 R1 - Ph1, Stg1 - Right 13th Ave - 15th St. to 20th St. - Sta. 16 to 24 | Place Curb - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | Place Asphalt Surface - 13th Ave Sta 16 to 24 - R1 - P1.S1 - right | 0 | FLATWORK | SUB-ASPH | H
A22240 | A23290 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | Finish Phase 0 - R2 - Pond SMF 4A / Lower Drainage | Finish Phase 2 - R2 - Right Ramp EN Construction | 0 |  |  | H
A23580 | A23600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Slip Barrier - Brg 100652 - R2 - P1 | Groove Deck - Brg 100652 - R2 - P1 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A23920 | A23600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Cure Deck - Brg 100652 - Span 3 - R2 - P1 | Groove Deck - Brg 100652 - R2 - P1 | 0 |  | SUB-ST-GROOVE | H
A23830 | A23600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Cure Deck - Brg 100652 - Span 2 - R2 - P1 | Groove Deck - Brg 100652 - R2 - P1 | 0 |  | SUB-ST-GROOVE | H
A23520 | A23600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | Cure Deck - Brg 100652 - Span 1 - R2 - P1 | Groove Deck - Brg 100652 - R2 - P1 | 0 |  | SUB-ST-GROOVE | H
A23570 | A23600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | FRPS Approach Slab 2 - Brg 100652 - R2 - P1 | Groove Deck - Brg 100652 - R2 - P1 | 0 | ST-APPR | SUB-ST-GROOVE | H
A23560 | A23600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.9.6 R2 - Ph1 - Bridge 100652 Ramp EN - Finishes | FRPS Approach Slab 1 - Brg 100652 - R2 - P1 | Groove Deck - Brg 100652 - R2 - P1 | 0 | ST-APPR | SUB-ST-GROOVE | H
A21280 | A21300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.5 R1 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.11.10 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE Over Columbus - Demo | Shift Traffic - Ramp NE Left - R1 - P2.S2 | Demo Superstructure - Brg 100864 - R1 - P2.S2 - right | 0 | TC-Maint. | DM-BRIDGE | H
A20270 | A20310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.5 R1 - Ph2, Stg3, Step2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.6.10 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE Over Columbus - Demo | Shift Traffic - Ramp NE Right - R1 - P2.S3 Step 2 | Demo Superstructure - Brg 100864 - R1 - P2.S3 - left | 0 | TC-Maint. | DM-BRIDGE | H
A26710 | A23690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.7 R2 - Ph1 - Bridge 100652 Ramp EN - Demo | I-275 - I-4 - IBL(all) - B1.2.3.2.9.2 R2 - Ph1 - Bridge 100652 Ramp EN - Pier 2 | Demo Barrier - Brg 100652 - R2 - P1 | Excavate - Brg 100652 - Pier 2 - R2 - P1 | 0 | DM-BRIDGE | EW-STR | H
A23510 | A23820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.3 R2 - Ph1 - Bridge 100652 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | Place Deck - Brg 100652 - Span 1 - R2 - P1 | Place Deck - Brg 100652 - Span 2 - R2 - P1 | 0 | ST-POUR | ST-POUR | H
A23820 | A23910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.4 R2 - Ph1 - Bridge 100652 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.9.5 R2 - Ph1 - Bridge 100652 Ramp EN - Span 3 | Place Deck - Brg 100652 - Span 2 - R2 - P1 | Place Deck - Brg 100652 - Span 3 - R2 - P1 | 0 | ST-POUR | ST-POUR | H
A23990 | A36260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Cut/Fill to Grade - Ramp EN Sta 83 to 88 - R2 - P1 | Const MSE Wall & Bkfill - RW 6-1 - Ramp EN Sta 85 to 88 - R2 - P1 | 0 | EW-SML | ST-MSE | H
A36260 | A24020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Const MSE Wall & Bkfill - RW 6-1 - Ramp EN Sta 85 to 88 - R2 - P1 | Place Stabilization - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | ST-MSE | EW-STAB | H
A22540 | A22550 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | Drive Pile - Brg 100650 - End Bent 1 - R2 - P1 | FRP Abt Cap - Brg 100650 - End Bent 1 - R2 - P1 | 0 | ST-PILE | ST-ABUT | H
A22540 | A22870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.2 R2 - Ph1 - Bridge 100650 Ramp EN Over Nebraska - End Bent 1 - Sta. 88 to 89 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Drive Pile - Brg 100650 - End Bent 1 - R2 - P1 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-PILE | EW-SML | H
A22800 | A22820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Slip Barrier - Brg 100650 - R2 - P1 | Groove Deck - Brg 100650 - R2 - P1 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A23210 | A22820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.5 R2 - Ph1 - Bridge 100650 Ramp EN - Span 3 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Cure Deck - Brg 100650 - Span 3 - R2 - P1 | Groove Deck - Brg 100650 - R2 - P1 | 0 |  | SUB-ST-GROOVE | H
A23120 | A22820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.4 R2 - Ph1 - Bridge 100650 Ramp EN - Span 2 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Cure Deck - Brg 100650 - Span 2 - R2 - P1 | Groove Deck - Brg 100650 - R2 - P1 | 0 |  | SUB-ST-GROOVE | H
A22740 | A22820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.3 R2 - Ph1 - Bridge 100650 Ramp EN - Span 1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | Cure Deck - Brg 100650 - Span 1 - R2 - P1 | Groove Deck - Brg 100650 - R2 - P1 | 0 |  | SUB-ST-GROOVE | H
A22790 | A22820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | FRPS Approach Slab 2 - Brg 100650 - R2 - P1 | Groove Deck - Brg 100650 - R2 - P1 | 0 | ST-APPR | SUB-ST-GROOVE | H
A22780 | A22820 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | I-275 - I-4 - IBL(all) - B1.2.3.2.4.6 R2 - Ph1 - Bridge 100650 Ramp EN - Finishes | FRPS Approach Slab 1 - Brg 100650 - R2 - P1 | Groove Deck - Brg 100650 - R2 - P1 | 0 | ST-APPR | SUB-ST-GROOVE | H
A22840 | A23980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 7-1 - Ramp EN Sta 76 to 79 - R2 - P1 - part 1 | Place 3-Pour Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-MSE | SUB-BR-SLIP | H
A36270 | A22880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 104 - Ramp EN Sta 68 to 72 - R2 - P1 | Place Stabilization - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-MSE | EW-STAB | H
A22870 | A36270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Cut/Fill to Grade - Ramp EN Sta 68 to 79 - R2 - P1 | Const MSE Wall & Bkfill - RW 104 - Ramp EN Sta 68 to 72 - R2 - P1 | 0 | EW-SML | ST-MSE | H
A36270 | A23980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | I-275 - I-4 - IBL(all) - B1.2.3.2.5 R2 - Ph1 - Ramp EN - Beginning to Columbus - Sta. 68 to 79 | Const MSE Wall & Bkfill - RW 104 - Ramp EN Sta 68 to 72 - R2 - P1 | Place 3-Pour Barrier - Ramp EN Sta 68 to 79 - R2 - P1 | 0 | ST-MSE | SUB-BR-SLIP | H
A27310 | A27450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.15 R2 - Ph1 - 14th Ave Shared Use Path - Nebraska to Columbus | Place Curb - 10th St /14th Ave Intersection - R2 - P1 | Grading - 14th Ave Shared Use Path - Nebraska to Columbus - R2 - P1 | 0 | FLATWORK | EW- ALL EW | H
A27310 | A27330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.12 R2 - Ph1 - 10th St / 14th Ave Intersection | Place Curb - 10th St /14th Ave Intersection - R2 - P1 | Place Asphalt Surface - 10th St /14th Ave Intersection - R2 - P1 | 0 | FLATWORK | SUB-ASPH | H
A22280 | A22470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.3 R2 - Ph2, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.1.5 R2 - Ph2, Stp3 - MOT | Shift Traffic - Ramp EN Left - R2 - P2 Stp2 | Remove MOT - I-4 WB & I-275 NB - R2 - P2 | 0 | TC-Maint. | TC-Maint. | H
A22280 | A22410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.1.3 R2 - Ph2, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.3.1.1 R2 - Ph2 - Rightt Ramp EN Widening - Sta. 86 to 89 & Sta. 91 to 95 | Shift Traffic - Ramp EN Left - R2 - P2 Stp2 | Grading - Ramp EN /I-4 - R2 - P2 | 0 | TC-Maint. | EW- ALL EW | H
A26380 | A24280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.1.4 R3 - Ph1, Stg1, Stp1 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.1.1 R3 - Ph1, Stg1 - Temp Ramp F - Sta. 706 to 711 | Install Temp Barrier - Ramp B / C - R3 - P1.S1 | Place GAB - Temp Ramp F - R3 - P1.S1 | 0 | SUB-TC-PCB | EW-ABC | H
A24570 | A24600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.1 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 1 | Install Drilled Shaft - Brg 100868 - Pier 1 - R3 - P1.S2 | FRP Column - Brg 100868 - Pier 1 - R3 - P1.S2 | 0 | SUB-ST-DRSFT | ST-COL | H
A24950 | A24980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.2 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Pier 2 | Install Drilled Shaft - Brg 100868 - Pier 2 - R3 - P1.S2 | FRP Column - Brg 100868 - Pier 2 - R3 - P1.S2 | 0 | SUB-ST-DRSFT | ST-COL | H
A26540 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.8 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Cure Deck - Brg 100868 - Span 3 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A24750 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Slip Barrier - Brg 100868 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A25160 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.5 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 4 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Cure Deck - Brg 100868 - Span 4 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A25070 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.4 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Cure Deck - Brg 100868 - Span 2 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A24690 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.3 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | Cure Deck - Brg 100868 - Span 1 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 |  | SUB-ST-GROOVE | H
A24740 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | FRPS Approach Slab 2 - Brg 100868 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A24730 | A24770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.2.12.6 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B - Finishes | FRPS Approach Slab 1 - Brg 100868 - R3 - P1.S2 | Groove Deck - Brg 100868 - R3 - P1.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A26023 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26026 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26028 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26053 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | EW-SML | EW-STAB | H
A26053 | A26020 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | 12 | EW-SML | ST-MSE | H
A26056 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | EW-SML | EW-STAB | H
A26058 | A26060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | Place Stabilization - Ramp B Sta 614 to 618 - R3 - P1.S2 | 0 | EW-SML | EW-STAB | H
A26058 | A26028 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | 0 | EW-SML | ST-MSE | H
A26133 | A26730 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 2 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-STR | H
A26133 | A26170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 2 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26160 | A26133 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 2 | 0 | EW-SML | ST-MSE | H
A27030 | A26133 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Install DRG S-156 to S-160 - Ramp B Sta 624 to 629 - R3 - P0 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 2 | 0 | PIPE | ST-MSE | H
A26136 | A26170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 3 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26160 | A26136 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 3 | 0 | EW-SML | ST-MSE | H
A27030 | A26136 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Install DRG S-156 to S-160 - Ramp B Sta 624 to 629 - R3 - P0 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 3 | 0 | PIPE | ST-MSE | H
A26242 | A26280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 2 | Place Stabilization - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | ST-MSE | EW-STAB | H
A26270 | A26242 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Cut/Fill to Grade - Ramp F Sta 506 to 511 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 9-2 - Ramp F Sta 506 to 511 - R3 - P1.S2 - part 2 | 0 | EW-SML | ST-MSE | H
A26720 | A27840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | Finish Phase 2 Stage 1 - R3 - Temp I-4 WB Diversion Ramp | Shift Traffic - I-4 WB on to Temp Diversion Ramp - R3 - P2.S2 | 0 |  | TC-Maint. | H
A28370 | A28380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.4.8 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P2.S2 | FRP Abt Cap - Brg 100139 - End Bent 1 - R3 - P2.S2 | 0 | ST-PILE | ST-ABUT | H
A28440 | A28450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P2.S2 | FRP Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | ST-PILE | ST-ABUT | H
A29660 | A30040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | FRP Cap - Brg 100139 - Pier 5 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | ST-CAP | ST-BEAM | H
A27890 | A30040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | SUB-TC-PCB | ST-BEAM | H
A27890 | A28440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.1 R3 - Ph2, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Install Temp Barrier - I-275 SB - R3 - P2.S2 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P2.S2 | 0 | SUB-TC-PCB | ST-PILE | H
A28250 | A28090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.5 R3 - Ph2, Stg2 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Cure Deck - Brg 100139 - Span 3 - R3 - P2.S2 | Groove Deck - Brg 100139 - R3 - P2.S2 | 0 |  | SUB-ST-GROOVE | H
A28160 | A28090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.2 R3 - Ph2, Stg2 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Cure Deck - Brg 100139 - Span 2 - R3 - P2.S2 | Groove Deck - Brg 100139 - R3 - P2.S2 | 0 |  | SUB-ST-GROOVE | H
A28010 | A28090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.3 R3 - Ph2, Stg2 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Cure Deck - Brg 100139 - Span 1 - R3 - P2.S2 | Groove Deck - Brg 100139 - R3 - P2.S2 | 0 |  | SUB-ST-GROOVE | H
A28060 | A28090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | FRPS Approach Slab 2 - Brg 100139 - R3 - P2.S2 | Groove Deck - Brg 100139 - R3 - P2.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A28050 | A28090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | FRPS Approach Slab 1 - Brg 100139 - R3 - P2.S2 | Groove Deck - Brg 100139 - R3 - P2.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A28070 | A28090 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.3.6 R3 - Ph2, Stg2 - Bridge 100139 - Finishes | Slip Barrier - Brg 100139 - R3 - P2.S2 | Groove Deck - Brg 100139 - R3 - P2.S2 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A29990 | A30080 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.14 R3 - Ph2, Stg2 - Bridge 100139 - Span 5 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Place Deck - Brg 100139 - Span 5 - R3 - P2.S2 | Place Deck - Brg 100139 - Span 6 - R3 - P2.S2 | 0 | ST-POUR | ST-POUR | H
A28460 | A30040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.15 R3 - Ph2, Stg2 - Bridge 100139 - Span 6 | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P2.S2 | Erect Girders - Brg 100139 - Span 6 - R3 - P2.S2 | 0 |  | ST-BEAM | H
A29040 | A29050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P2.S2 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | ST-PILE | ST-ABUT | H
A26990 | A29050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.9 R3 - Ph0 - Ramp B and F Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | Install DRG CS-3A to S-117A / S-120 - Pond SMF 3A - R3 - P0 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P2.S2 | 0 | PIPE | ST-ABUT | H
A29110 | A29120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.4.11 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P2.S2 | FRP Abt Cap - Brg 100141 - End Bent 2 - R3 - P2.S2 | 0 | ST-PILE | ST-ABUT | H
A28920 | A28760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.5 R3 - Ph2, Stg2 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Cure Deck - Brg 100141 - Span 3 - R3 - P2.S2 | Groove Deck - Brg 100141 - R3 - P2.S2 | 0 |  | SUB-ST-GROOVE | H
A28830 | A28760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.2 R3 - Ph2, Stg2 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Cure Deck - Brg 100141 - Span 2 - R3 - P2.S2 | Groove Deck - Brg 100141 - R3 - P2.S2 | 0 |  | SUB-ST-GROOVE | H
A28680 | A28760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.3 R3 - Ph2, Stg2 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Cure Deck - Brg 100141 - Span 1 - R3 - P2.S2 | Groove Deck - Brg 100141 - R3 - P2.S2 | 0 |  | SUB-ST-GROOVE | H
A28730 | A28760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | FRPS Approach Slab 2 - Brg 100141 - R3 - P2.S2 | Groove Deck - Brg 100141 - R3 - P2.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A28720 | A28760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | FRPS Approach Slab 1 - Brg 100141 - R3 - P2.S2 | Groove Deck - Brg 100141 - R3 - P2.S2 | 0 | ST-APPR | SUB-ST-GROOVE | H
A28740 | A28760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.4.12.6 R3 - Ph2, Stg2 - Bridge 100141 - Finishes | Slip Barrier - Brg 100141 - R3 - P2.S2 | Groove Deck - Brg 100141 - R3 - P2.S2 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A30360 | A31610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.1 R3 - Ph3 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.5.5 R3 - Ph3 - I-275 SB Widening - Sta. 409 to 413 | Shift Traffic - Ramp C Left - R3 - P3 | Cut/Fill to Grade - I-275 SB Sta 409 to 413 - R3 - P3 | 0 | TC-Maint. | EW-SML | H
A33830 | A33980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.8 R3 - Ph3 - Bridge 100143 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Grading - Brg 100143 - Pier 2 - R3 - P3 | FRP Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | 0 | EW- ALL EW | ST-ABUT | H
A33440 | A33980 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.1 R3 - Ph3 - Bridge 100143 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.19 R3 - Ph3 - Bridge 100143 Ramp C Over Palm Ave - End Bent 2 - Sta. 709 | Grading - Brg 100143 - Pier 1 - R3 - P3 | FRP Abt Cap - Brg 100143 - End Bent 2 - R3 - P3 | 0 | EW- ALL EW | ST-ABUT | H
A33790 | A33630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Cure Deck - Brg 100143 - Span 3 - R3 - P3 | Groove Deck - Brg 100143 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A33700 | A33630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.2 R3 - Ph3 - Bridge 100143 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Cure Deck - Brg 12 - Span 2 - R3 - P3 | Groove Deck - Brg 100143 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A33550 | A33630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Cure Deck - Brg 100143 - Span 1 - R3 - P3 | Groove Deck - Brg 100143 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A33610 | A33630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Slip Barrier - Brg 100143 - R3 - P3 | Groove Deck - Brg 100143 - R3 - P3 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A33540 | A33630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.3 R3 - Ph3 - Bridge 100143 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Place Deck - Brg 100143 - Span 1 - R3 - P3 | Groove Deck - Brg 100143 - R3 - P3 | 0 | ST-POUR | SUB-ST-GROOVE | H
A33780 | A33630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.5 R3 - Ph3 - Bridge 100143 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.20.6 R3 - Ph3 - Bridge 100143 - Finishes | Place Deck - Brg 100143 - Span 3 - R3 - P3 | Groove Deck - Brg 100143 - R3 - P3 | 0 | ST-POUR | SUB-ST-GROOVE | H
A33314 | A33430 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 2 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P3 | 0 | ST-MSE | EW-STR | H
A33314 | A33350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 2 | Place Stabilization - Ramp B Sta 621 to 627 - R3 - P3 | 0 | ST-MSE | EW-STAB | H
A33340 | A33314 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P3 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 2 | 0 | EW-SML | ST-MSE | H
A31440 | A31450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.5.10 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 1- Sta. 419 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P3 | FRP Abt Cap - Brg 100141 - End Bent 1 - R3 - P3 | 0 | ST-PILE | ST-ABUT | H
A31510 | A31520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | I-275 - I-4 - IBL(all) - B1.2.5.5.11 R3 - Ph3 - Bridge 100141 Over 7th Ave Bridge - End Bent 2 - Sta. 421 | Drive Pile - Brg 100141 - End Bent 2 - R3 - P3 | FRP Abt Cap - Brg 100141 - End Bent 2 - R3 - P3 | 0 | ST-PILE | ST-ABUT | H
A31330 | A31170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.5 R3 - Ph3 - Bridge 100141 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Cure Deck - Brg 100141 - Span 3 - R3 - P3 | Groove Deck - Brg 100141 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A31240 | A31170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.2 R3 - Ph3 - Bridge 100141 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Cure Deck - Brg 100141 - Span 2 - R3 - P3 | Groove Deck - Brg 100141 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A31090 | A31170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.3 R3 - Ph3 - Bridge 100141 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Cure Deck - Brg 100141 - Span 1 - R3 - P3 | Groove Deck - Brg 100141 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A31140 | A31170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | FRPS Approach Slab 2 - Brg 100141 - R3 - P3 | Groove Deck - Brg 100141 - R3 - P3 | 0 | ST-APPR | SUB-ST-GROOVE | H
A31130 | A31170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | FRPS Approach Slab 1 - Brg 100141 - R3 - P3 | Groove Deck - Brg 100141 - R3 - P3 | 0 | ST-APPR | SUB-ST-GROOVE | H
A31150 | A31170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.12.6 R3 - Ph3 - Bridge 100141 - Finishes | Slip Barrier - Brg 100141 - R3 - P3 | Groove Deck - Brg 100141 - R3 - P3 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A30830 | A30840 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | I-275 - I-4 - IBL(all) - B1.2.5.5.8 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 1 - Sta. 413 | Drive Pile - Brg 100139 - End Bent 1 - R3 - P3 | FRP Abt Cap - Brg 100139 - End Bent 1 - R3 - P3 | 0 | ST-PILE | ST-ABUT | H
A30900 | A30910 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | Drive Pile - Brg 100139 - End Bent 2 - R3 - P3 | FRP Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | 0 | ST-PILE | ST-ABUT | H
A34410 | A34430 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | I-275 - I-4 - IBL(all) - B1.2.5.6.1 R3 - Ph4 - MOT | Finish Phase 3 - R3 - I-275 SB Right Widening | Shift Traffic - Ramp C Left - R3 - P4 | 0 |  | TC-Maint. | H
A35680 | A35700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.6 R3 - Ph4 - Final MOT | Place Asphalt Shoulder - Ramp C /I-275 SB Gore - R3 - P4 | Shift Traffic - Ramp C Left - R3 - P4 - Final MOT | 0 | SUB-ASPH | TC-Maint. | H
A34640 | A35700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.5 R3 - Ph4 - N Central Drainage / Roadway | I-275 - I-4 - IBL(all) - B1.2.5.6.6 R3 - Ph4 - Final MOT | Place Asphalt Surface - N CentralRoadway - R3 - P4 | Shift Traffic - Ramp C Left - R3 - P4 - Final MOT | 0 | SUB-ASPH | TC-Maint. | H
A15440 | A15755 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 - part 2 | 0 | PIPE | EW-SML | H
A15755 | A15760 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | I-275 - I-4 - IBL(all) - B1.2.2.2.10 R1 - Ph1, Stg1 - Ramp WE-B - 12th St. to 14th St. - Sta. 60 to 70 | Cut/Fill to Grade - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 - part 2 | Place 3-Pour Barrier - Ramp WE-B Sta 60 to 70 - R1 - P1.S1 | 0 | EW-SML | SUB-BR-SLIP | H
A27190 | A16530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Cut/Fill to Grade - I-4 Sta 311 to 320 - R2 - P1 | Const MSE Wall & Bkfill - RW 103 - I-4 Sta 311 to 320 - R2 - P1 | 0 | EW-SML | ST-MSE | H
A16530 | A27200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Const MSE Wall & Bkfill - RW 103 - I-4 Sta 311 to 320 - R2 - P1 | Place Stabilization - I-4 Sta 311 to 320 - R2 - P1 | 0 | ST-MSE | EW-STAB | H
A16500 | A16560 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | Shift Traffic - Ramp NE Right - R1 - P1.S2 | Place Stabilization - Ramp NE Sta 110 to 105 - R1 - P1.S2 | 0 | TC-Maint. | EW-STAB | H
A16490 | A16345 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.4 R2 - Milestones | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Start Construction - R2 | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 2 | 0 |  | EW-SML | H
A16345 | A16450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 2 | Install DRG S-118 to S-123 - Pond SMF 4A - R2 - P1 | 0 | EW-SML | PIPE | H
A16345 | A16350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | I-275 - I-4 - IBL(all) - B1.2.3.3 R2 - Phase 0 - Nebraska/Columbus Pond SMF 4A | Cut/Fill to Grade - Pond SMF 4A - R2 - P0 - part 2 | Place Stabilization - Pond SMF 4A Shared Use Path - R2 - P0 | 0 | EW-SML | EW-STAB | H
A30770 | A30610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.5 R3 - Ph3 - Bridge 100139 - Span 3 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Cure Deck - Brg 100139 - Span 3 - R3 - P3 | Groove Deck - Brg 100139 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A30680 | A30610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.2 R3 - Ph3 - Bridge 100139 - Span 2 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Cure Deck - Brg 100139 - Span 2 - R3 - P3 | Groove Deck - Brg 100139 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A30530 | A30610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.3 R3 - Ph3 - Bridge 100139 - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Cure Deck - Brg 100139 - Span 1 - R3 - P3 | Groove Deck - Brg 100139 - R3 - P3 | 0 |  | SUB-ST-GROOVE | H
A30580 | A30610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | FRPS Approach Slab 2 - Brg 100139 - R3 - P3 | Groove Deck - Brg 100139 - R3 - P3 | 0 | ST-APPR | SUB-ST-GROOVE | H
A30570 | A30610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | FRPS Approach Slab 1 - Brg 100139 - R3 - P3 | Groove Deck - Brg 100139 - R3 - P3 | 0 | ST-APPR | SUB-ST-GROOVE | H
A30590 | A30610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Slip Barrier - Brg 100139 - R3 - P3 | Groove Deck - Brg 100139 - R3 - P3 | 0 | SUB-ST-PARAPET | SUB-ST-GROOVE | H
A30920 | A30580 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.6 R3 - Ph3 - Bridge 100139 - Finishes | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | FRPS Approach Slab 2 - Brg 100139 - R3 - P3 | 0 |  | ST-APPR | H
A30920 | A32340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.9 R3 - Ph3 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.5.3.15 R3 - Ph3 - Bridge 100139 - Span 6 | Cure/Strip Abt Cap - Brg 100139 - End Bent 2 - R3 - P3 | Erect Girders - Brg 100139 - Span 6 - R3 - P3 | 0 |  | ST-BEAM | H
A16810 | A17050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.3 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.4.3.2 R1 - Ph1, Stg2 - Bridge 100656 Widening Over 14th St - Span 2 | Place Deck - Brg 100656 - Span 1 - R1 - P1.S2 | Place Deck - Brg 100656 - Span 2 - R1 - P1.S2 | 0 | ST-POUR | ST-POUR | H
A17460 | A18030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.9 R1 - Ph1, Stg2 - Bridge 100656 - End Bent 2 - Sta. 252 to 253 | I-275 - I-4 - IBL(all) - B1.2.2.4.10 R1 - Ph1, Stg2 - Bridge 100657 - End Bent 1 - Sta. 254 to 255 | FRP Brick Column - Brg 100656 - End Bent 2 - R1 - P1.S2 | Temp Wall or SOE - Brg 100657 - End Bent 1 - R1 - P1.S2 | 0 | ST-BRIDGE-ALL | EW-STR | H
A26130 | A26730 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-3 - Ramp B Sta 621 to 627 - R3 - P1.S2 - part 1 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-STR | H
A26050 | A26020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | 0 | EW-SML | ST-MSE | H
A26053 | A26023 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | Const MSE Wall & Bkfill - RW 8-2 - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | 0 | EW-SML | ST-MSE | H
A33310 | A33430 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | I-275 - I-4 - IBL(all) - B1.2.5.5.16 R3 - Ph3 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-2 - Ramp B Sta 621 to 627 - R3 - P3 - part 1 | Temp Wall or SOE - Ramp B Sta 621 to 627 - R3 - P3 | 0 | ST-MSE | EW-STR | H
A26028 | A26160 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.16 R3 - Ph1, Stg2 - Ramp B - Palm Ave to End - Sta. 621 to 627 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 2 | Cut/Fill to Grade - Ramp B Sta 621 to 627 - R3 - P1.S2 | 0 | ST-MSE | EW-SML | H
D3230 | D3240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Review and Approve - Final - 60" Drainage System - R3 | Develop and Submit - Sign & Seal - 60" Drainage System - R3 | 0 |  |  | H
D3210 | D3220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Review and Approve - 90% - 60" Drainage System - R3 | Develop and Submit - Final - 60" Drainage System - R3 | 0 |  |  | H
D3220 | D3230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Develop and Submit - Final - 60" Drainage System - R3 | Review and Approve - Final - 60" Drainage System - R3 | 0 |  |  | H
D3200 | D3210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Develop and Submit - 90% - 60" Drainage System - R3 | Review and Approve - 90% - 60" Drainage System - R3 | 0 |  |  | H
D3180 | D3190 | FS | In Progress | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Develop and Submit - 60% - 60" Drainage System - R3 | Review and Approve - 60% - 60" Drainage System - R3 | 0 |  |  | H
D3240 | D3250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Develop and Submit - Sign & Seal - 60" Drainage System - R3 | Issue - RFC - 60" Drainage System - R3 | 0 |  |  | H
A22120 | A36280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Cut/Fill to Grade - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 2 | 0 | EW-SML | ST-MSE | H
A36280 | A21220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 2 | Grading - NE Shared Use Path - R1 - P2.S3 | 0 | ST-MSE | EW- ALL EW | H
A36280 | A22100 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Const MSE Wall & Bkfill - RW 1-2 - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right - part 2 | Place 3-Pour Barrier - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | ST-MSE | SUB-BR-SLIP | H
A21000 | A21018 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Cut/Fill to Grade - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 2 | 0 | EW-SML | ST-MSE | H
A21018 | A21030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.6.7 R1 - Ph2, Stg3 - FLYOVER - Left Ramp NE to Columbus - Sta. 127 to 131 | Const MSE Wall & Bkfill - RW 2-2 - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left - part 2 | Place Stabilization - Ramp NE Sta 127 to 131 - R1 - P2.S3 - left | 0 | ST-MSE | EW-STAB | H
A24360 | A25950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.3 R3 - Ph1, Stg2, Stp2 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.2.10 R3 - Ph1, Stg2 - Ramp B - Start to Central Ave - Sta. 601 to 606 | Install Temp Barrier - Ramp B - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 601 to 606 - R3 - P1.S2 | 0 | SUB-TC-PCB | EW-SML | H
A24860 | A26050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Grading - Brg 100868 - End Bent 2 - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 1 | 0 | EW- ALL EW | EW-SML | H
A24860 | A26053 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.13 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 2 - Sta. 613 to 614 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Grading - Brg 100868 - End Bent 2 - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 614 to 616 - R3 - P1.S2 - part 2 | 0 | EW- ALL EW | EW-SML | H
A26056 | A26026 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | Const MSE Wall & Bkfill - RW 9-1 - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | 0 | EW-SML | ST-MSE | H
A25230 | A26056 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.11 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 1 - Sta. 618 to 619 | I-275 - I-4 - IBL(all) - B1.2.5.2.15 R3 - Ph1, Stg2 - Ramp B - 7th Ave to Palm Ave - Sta. 614 to 618 | Grading - Brg 100869 - End Bent 1 - R3 - P1.S2 | Cut/Fill to Grade - Ramp B Sta 616 to 619 - R3 - P1.S2 - part 1 | 0 | EW- ALL EW | EW-SML | H
A16610 | A16480 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.2 R1 - Ph1, Stg2 - Ramp NE - Bridge to 12th St. - Sta. 110 to 105 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | Place Edge Drain - Ramp NE Sta 110 to 105 - R1 - P1.S2 | Install DRG S-147 to S-151 - I-275 Sta 715 to 717 - R2 - P1 | 0 | PIPE | PIPE | H
A16380 | A27350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.1 R2 - Ph1 - Ramp EN Lower Drainage | I-275 - I-4 - IBL(all) - B1.2.3.2.13 R2 - Ph1 - Taliaferro Ave - Sta. 20 to 25 | Install DRG S-101 to S-105 - I-4 Sta 310 to 314 - R2 - P1 | Install DRG - Taliaferro Ave Sta 20 to 25 - R2 - P1 | 0 | PIPE | PIPE | H
A24160 | A24070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.11 R2 - Ph1 - 13th St / 14th Ave Intersection | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | Install DRG - 13th St / 14th St Intersection - R2 - P1 | Place Edge Drain - Ramp EN Sta 83 to 88 - R2 - P1 | 0 | PIPE | PIPE | H
A24070 | A27230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.10 R2 - Ph1 - Ramp EN - Nebraska to Columbus - Sta. 83 to 88 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | Place Edge Drain - Ramp EN Sta 83 to 88 - R2 - P1 | Place Edge Drain - I-4 Sta 311 to 320 - R2 - P1 | 0 | PIPE | PIPE | H
A27230 | A27120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.3.2.17 R2 - Ph1 - I-4 - 12th St. to Avenida - Sta. 311 to 320 | I-275 - I-4 - IBL(all) - B1.2.3.2.16 R2 - Ph1 - Ramp EN - Nebraska to 12th St. - Sta. 91 to 103 | Place Edge Drain - I-4 Sta 311 to 320 - R2 - P1 | Place Edge Drain - Ramp EN Sta 91 to 103 - R2 - P1 | 0 | PIPE | PIPE | H
A22060 | A22160 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.7 R1 - Ph2, Stg2 - FLYOVER - Right Ramp NE to Columbus - Sta. 127 to 131 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | Place Edge Drain - Ramp NE Sta 127 to 131 - R1 - P2.S2 - right | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | 0 | PIPE | PIPE | H
A22160 | A21240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.8 R1 - Ph2, Stg2 - Right Ramp NE - Columbus to Start - Sta. 134 to 137 | I-275 - I-4 - IBL(all) - B1.2.2.6.9 R1 - Ph2, Stg3 - NE Shared Use Path | Place Edge Drain - Ramp NE Sta 134 to 137 - R1 - P2.S2 - right | Install DRG S-4A5 to S-4B5 - NE Shared UsePath - R1 - P2.S3 | 0 | PIPE | PIPE | H
A34660 | A34500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.4 R3 - Ph4 - Mitchell / Ross Intersection / Palm Shared Use Path | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Install DRG S-575 to S-127 - Mitchell /Ross Inter /Palm SUP - R3 - P4 | Place Edge Drain - Ramp B /Ramp G Gore - R3 - P4 | 0 | PIPE | PIPE | H
A34500 | A35660 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Edge Drain - Ramp B /Ramp G Gore - R3 - P4 | Place Edge Drain - Ramp C /I-275 SB Gore - R3 - P4 | 0 | PIPE | PIPE | H
A34160 | A34490 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.21 R3 - Ph3 - I-275 SB Widening - Sta. 417 to 419 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | Place Concrete Pav - I-275 SB Sta 417 to 419 - R3 - P3 | Place Concrete Pav - Ramp B /Ramp G Gore - R3 - P4 | 0 | CP-SLIP | CP-SLIP | H
A34490 | A35650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.2 R3 - Ph4 - Ramp B / Ramp G Gore | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Place Concrete Pav - Ramp B /Ramp G Gore - R3 - P4 | Place Concrete Pav - Ramp C /I-275 SB Gore - R3 - P4 | 0 | CP-SLIP | CP-SLIP | H
A28510 | A27900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.9 R3 - Ph2, Stg2 - Bridge 100139 Over N Central Bridge - End Bent 2 - Sta. 417 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | Demo Abut - Brg 100139 - End Bent 2 - R3 - P2.S2 | Excavate - Brg 100139 - Pier 1 - R3 - P2.S2 | 0 | DM-BRIDGE | EW-STR | H
A27900 | A29380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Excavate - Brg 100139 - Pier 1 - R3 - P2.S2 | Grading - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | EW-STR | EW- ALL EW | H
A29380 | A29460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.8 R3 - Ph2, Stg2 - Bridge 100139 - Pier 3 | Grading - Brg 100139 - Pier 2 - R3 - P2.S2 | Excavate - Brg 100139 - Pier 3 - R3 - P2.S2 | 0 | EW- ALL EW | EW-STR | H
A29540 | A29620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.9 R3 - Ph2, Stg2 - Bridge 100139 - Pier 4 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.10 R3 - Ph2, Stg2 - Bridge 100139 - Pier 5 | Excavate - Brg 100139 - Pier 4 - R3 - P2.S2 | Grading - Brg 100139 - Pier 5 - R3 - P2.S2 | 0 | EW-STR | EW- ALL EW | H
A29040 | A28570 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.10 R3 - Ph2, Stg2 - Bridge 100141 Over 7th Ave Bridge - End Bent 1 - Sta. 419 | I-275 - I-4 - IBL(all) - B1.2.5.4.12.1 R3 - Ph2, Stg2 - Bridge 100141 - Pier 1 | Drive Pile - Brg 100141 - End Bent 1 - R3 - P2.S2 | Excavate - Brg 100141 - Pier 1 - R3 - P2.S2 | 0 | ST-PILE | EW-STR | H
A27910 | A29380 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.1 R3 - Ph2, Stg2 - Bridge 100139 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.5.4.3.4 R3 - Ph2, Stg2 - Bridge 100139 - Pier 2 | Install Drilled Shaft - Brg 100139 - Pier 1 - R3 - P2.S2 | Grading - Brg 100139 - Pier 2 - R3 - P2.S2 | 0 | SUB-ST-DRSFT | EW- ALL EW | H
A25890 | A26270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.8 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B Over Palm - End Bent 2 - Sta. 620 to 621 | I-275 - I-4 - IBL(all) - B1.2.5.2.17 R3 - Ph1, Stg2 - Ramp F - Palm Ave to End - Sta. 506 to 511 | Temp Wall or SOE - Brg 100869 - End Bent 2 - R3 - P1.S2 | Cut/Fill to Grade - Ramp F Sta 506 to 511 - R3 - P1.S2 | 0 | EW-STR | EW-SML | H
A35450 | A34720 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.14 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - End Bent 1 - Sta. 114 to 115 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | Drive Pile - Brg 2 - End Bent 1 - R1 - P2.S1 | Excavate - Brg 2 - Pier 1 - R1 - P2.S1 | 0 | ST-PILE | EW-STR | H
A34740 | A34960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.1 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | Drive Pile - Brg 2 - Pier 1 - R1 - P2.S1 | Excavate - Brg 2 - Pier 2 - R1 - P2.S1 | 0 | ST-PILE | EW-STR | H
A34980 | A35230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.2 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.7 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pier 3 | Drive Pile - Brg 2 - Pier 2 - R1 - P2.S1 | Excavate - Brg 2 - Pier 3 - R1 - P2.S1 | 0 | ST-PILE | EW-STR | H
A36010 | A36020 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-6 - R3 | Excav for 60" Str - OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36020 | A36030 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-5 - R3 | Excav for 60" Str - OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36030 | A36040 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-4 - R3 | Excav for 60" Str - OUT-3 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36040 | A36050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-3 - R3 | Excav for 60" Str - OUT-2 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36050 | A36060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - IBL(all) - B1.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-2 - R3 | Excav for 60" Str - OUT-1 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36590 | A36600 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-6 - R3 | Install Str for 60" Drainage - OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36600 | A36610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-5 - R3 | Install Str for 60" Drainage - OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36610 | A36620 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-4 - R3 | Install Str for 60" Drainage - OUT-3 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36620 | A36630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-3 - R3 | Install Str for 60" Drainage - OUT-2 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36630 | A36640 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | I-275 - I-4 - IBL(all) - B1.2.5.8.3 R3 - Ph0 - 60" Drainage - Structures | Install Str for 60" Drainage - OUT-2 - R3 | Install Str for 60" Drainage - OUT-1 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | H
A36170 | A36110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install ITS - Ramp NE / WE | Install Landscaping - Ramp NE / WE | 0 |  |  | H
A36200 | A36110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install LIghting - Ramp NE / WE | Install Landscaping - Ramp NE / WE | 0 |  |  | H
A36210 | A36110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | Install Signals - Ramp NE / WE | Install Landscaping - Ramp NE / WE | 0 |  |  | H
A36140 | A20300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Grass - Ramp NE / WE | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | 0 |  |  | H
A36110 | A20300 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.5 R001.01 - Ramp NE / Ramp WE Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | Install Landscaping - Ramp NE / WE | Finish Phase 2 Stage 3 - R1 - Up-St Ramp NE Left | 0 |  |  | H
A36240 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Lighting - Ramp F / Ramp B / Ramp C / Ramp G / I | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 |  |  | H
A36130 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Landscaping - Ramp F / Ramp B / Ramp C / Ramp G / I | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 |  |  | H
A36160 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install Grass - Ramp F / Ramp B / Ramp C / Ramp G / I | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 |  |  | H
A36190 | A34410 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.10 R001.03 - Ramp F / Ramp B / Ramp C / Ramp G / I-275 SB Construction Landscaping / Grassing / ITS | I-275 - I-4 - IBL(all) - B1.2.5.7 R3 - Milestones | Install ITS - Ramp F / Ramp B / Ramp C / Ramp G / I | Finish Phase 3 - R3 - I-275 SB Right Widening | 0 |  |  | H
D1040 | D1050 | FS | In Progress | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.3 Design Survey/SUE | I-275 - I-4 - IBL(all) - B1.3.25.2 Dry Utility Relocation Plans - TECO/FTR | Perform Design Survey [LoE] | Develop and Submit - 60% Dry Utility Relocation Plans | 0 |  |  | H
U1260 | A22190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.4.2.3.2 Uniti Fiber/Southern Light - During Construction | I-275 - I-4 - IBL(all) - B1.2.2.9 R1 - Phase 3 - Signing / Milling / Pavement Markings | Adj HH to grade 24x36x36- (256+20, 105' RT) - Uniti | Mill / Resurface Asphalt - R1 - P3 | 0 |  | SUB-ASPH | H
A34810 | A35060 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.15 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Girder Erection | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Erect Girders - Brg 2 - Spans 1-2 - R1 - P2.S1 | Install SIP - Brg 2 - Pour 2 - R1 - P2.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A34920 | A35960 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 7 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A34910 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | FRPS Approach Slab 2 - Brg 2 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | ST-APPR | SUB-ST-PARAPET | H
A34900 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | FRPS Approach Slab 1 - Brg 2 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | ST-APPR | SUB-ST-PARAPET | H
A35950 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 7 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A35860 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 6 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A35770 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 5 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A35200 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 4 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A35380 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 3 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A35110 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 2 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A34870 | A34920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Install Reinf Barrier - Brg 2 - Pour 1 - R1 - P2.S1 | Slip Barrier - Brg 2 - R1 - P2.S1 | 0 | SUB-ST-REBAR | SUB-ST-PARAPET | H
A35960 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.12 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 7 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 7 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A34920 | A35870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 6 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A35870 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.11 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 6 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 6 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A34920 | A35780 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 5 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A35780 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.10 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 5 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 5 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A34920 | A35210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 4 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A35210 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.5 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 4 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 4 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A34920 | A35390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 3 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A35390 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.8 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 3 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 3 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A34920 | A35120 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 2 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A35120 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.4 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 2 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 2 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A34920 | A34880 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | Slip Barrier - Brg 2 - R1 - P2.S1 | Strip Overhangs - Brg 2 - Pour 1 - R1 - P2.S1 | 0 | SUB-ST-PARAPET | ST-DECK | H
A34880 | A34950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.3.3 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Pour 1 | I-275 - I-4 - IBL(all) - B1.2.2.3.6 R1 - Ph2, Stg1 - Ramp NE-C Bridge 2 - Finishes | Strip Overhangs - Brg 2 - Pour 1 - R1 - P2.S1 | Perm Striping - Brg 2 - R1 - P2.S1 | 0 | ST-DECK | SUB-STRIP | H
A24490 | A36680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Install Drilled Shaft - Brg 100868 - End Bent 1 - R3 - P1.S2 | Cure and Test Drilled shaft - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT | H
A36680 | A36690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Cure and Test Drilled shaft - Brg 100868 - End Bent 1 - R3 - P1.S2 | Pour Drilled Shaft Extensions - Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT | H
A36690 | A24520 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | I-275 - I-4 - IBL(all) - B1.2.5.2.14 R3 - Ph1, Stg2 - Bridge 100868 - Ramp B Over N Central - End Bent 1 - Sta. 606 to 607 | Pour Drilled Shaft Extensions - Brg 100868 - End Bent 1 - R3 - P1.S2 | Const MSE Wall & Bkfill - RW 8-1 / Brg 100868 - End Bent 1 - R3 - P1.S2 | 0 | SUB-ST-DRSFT | ST-MSE | H
A14820 | A15260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Reinforce Deck - Brg 100865 - Span 1 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A14820 | A15350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Reinforce Deck - Brg 100865 - Span 1 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A15250 | A14830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Reinforce Deck - Brg 100865 - Span 2 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A15250 | A15350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Reinforce Deck - Brg 100865 - Span 2 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A15340 | A15260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Reinforce Deck - Brg 100865 - Span 3 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A15340 | A14830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Reinforce Deck - Brg 100865 - Span 3 - R1 - P1.S1 | Place Deck - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | SUB-ST-REBAR | ST-POUR | H
A14790 | A14810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | ST-BEAM | ST-DECK | H
A15210 | A15240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | ST-BEAM | ST-DECK | H
A14800 | A14810 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install SIP - Brg 100865 - Span 1 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A15300 | A15330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | I-275 - I-4 - IBL(all) - B1.2.2.2.4.5 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 3 | Erect Girders - Brg 100865 - Span 3 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 3 - R1 - P1.S1 | 0 | ST-BEAM | ST-DECK | H
A18400 | A18410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Shift Traffic - 13th Ave Left - R1 - P1.S2 | Install Temp Barrier -13th Ave - R1 - P1.S2 | 0 | TC-Maint. | SUB-TC-PCB | H
A18410 | A18200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.5 R1 - Ph1, Stg2 - I-4 - 14th St. to 15th St. - Sta. 250 to 266 | Install Temp Barrier -13th Ave - R1 - P1.S2 | Cut/Fill to Grade - I-4 Sta 250 to 266 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW-SML | H
A18410 | A18340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | I-275 - I-4 - IBL(all) - B1.2.2.4.7 R1 - Ph1, Stg2 - 13th Ave - 17th St. to 21st St. - Sta. 24 to 40 | Install Temp Barrier -13th Ave - R1 - P1.S2 | Grading - 13th Ave - Right Sta 24 to 40 - R1 - P1.S2 | 0 | SUB-TC-PCB | EW- ALL EW | H
A15920 | A18400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.7 R1 - Milestones | I-275 - I-4 - IBL(all) - B1.2.2.4.1 R1 - Ph1, Stg2 - MOT | Finish Phase 1 Stage 1 - R1 - Ramp WE-B / NE | Shift Traffic - 13th Ave Left - R1 - P1.S2 | 0 |  | TC-Maint. | H
A20620 | A20680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.3 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.6.3.6 R1 - Ph2, Stg3 - Brg 100864 - Left Ramp NE - Finishes | Place Deck - Brg 100864 - Span 1 - R1 - P2.S3 | FRPS Approach Slab 2 - Brg 100864 - R1 - P2.S3 | 0 | ST-POUR | ST-APPR | H
A21610 | A21670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.3 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Span 1 | I-275 - I-4 - IBL(all) - B1.2.2.11.3.6 R1 - Ph2, Stg2 - Brg 100864 - Right Ramp NE - Finishes | Place Deck - Brg 100864 - Span 1 - R1 - P2.S2 | FRPS Approach Slab 2 - Brg 100864 - R1 - P2.S2 | 0 | ST-POUR | ST-APPR | H
A25440 | A25500 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.3 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.2.9.6 R3 - Ph1, Stg2 - Bridge 100869 - Ramp F/B - Finishes | Place Deck - Brg 100869 - Span 1 - R3 - P1.S2 | FRPS Approach Slab 2 - Brg 100869 - R3 - P1.S2 | 0 | ST-POUR | ST-APPR | H
A26680 | A26690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.2.1 R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | I-275 - I-4 - IBL(all) - B1.2.5.2.1 R3 - Ph1, Stg2 - Demo Existing Ramp F Bridge Over Palm | Demo Superstructure - Ramp F Brg Over Palm - R3 - P1.S2 | Demo Substructure - Ramp F Brg Over Palm - R3 - P1.S2 | 0 | DM-BRIDGE | DM-BRIDGE | H
A32860 | A32920 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.3 R3 - Ph3 - Bridge 100869 - Ramp B - Span 1 | I-275 - I-4 - IBL(all) - B1.2.5.5.13.6 R3 - Ph3 - Bridge 100869 - Ramp B - Finishes | Place Deck - Brg 100869 - Span 1 - R3 - P3 | FRPS Approach Slab 2 - Brg 100869 - R3 - P3 | 0 | ST-POUR | ST-APPR | H
A34430 | A35610 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.2.5.6.1 R3 - Ph4 - MOT | I-275 - I-4 - IBL(all) - B1.2.5.6.3 R3 - Ph4 - Ramp C / I-275 SB Gore | Shift Traffic - Ramp C Left - R3 - P4 | Cut/Fill to Grade - Ramp C / I-275 SB Gore - R3 - P3 | 0 | TC-Maint. | EW-SML | H
D3190 | D3200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | Review and Approve - 60% - 60" Drainage System - R3 | Develop and Submit - 90% - 60" Drainage System - R3 | 0 |  |  | H
D1260 | D5180 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | Develop and Submit - 90% TTCP Plans - R1 Phase 3 | 20 |  |  | H
Admin-1020 | D5190 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R1 Phase 3 | 0 |  |  | H
D5230 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | I-275 - I-4 - IBL(all) - B1.1 Project Administration | Issue - RFC TTCP Plans - R1 Phase 3 | Design Completion | 0 |  |  | H
D5210 | D5220 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Review and Approve - Final TTCP Plans - R1 Phase 3 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 3 | 0 |  |  | H
D5190 | D5200 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Review and Approve - 90% TTCP Plans - R1 Phase 3 | Develop and Submit - Final TTCP Plans - R1 Phase 3 | 0 |  |  | H
D5180 | D5190 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - 90% TTCP Plans - R1 Phase 3 | Review and Approve - 90% TTCP Plans - R1 Phase 3 | 0 |  |  | H
D5200 | D5210 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - Final TTCP Plans - R1 Phase 3 | Review and Approve - Final TTCP Plans - R1 Phase 3 | 0 |  |  | H
D5220 | D5230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 3 | Issue - RFC TTCP Plans - R1 Phase 3 | 0 |  |  | H
Admin-1045 | D5180 | SS | Completed | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.1 Project Administration | I-275 - I-4 - IBL(all) - B1.3.11.6 Temporary Traffic Control Plans (TTCP) - R1 Phase 3 (ASI) | Begin Design | Develop and Submit - 90% TTCP Plans - R1 Phase 3 | 0 |  |  | H
D5290 | D5300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 100% Wet Utility Relocation Plans (COT) | Develop and Submit - Sign & Seal Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5270 | D5280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 90% Wet Utility Relocation Plans (COT) | Develop and Submit - 100% Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5280 | D5290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - 100% Wet Utility Relocation Plans (COT) | Review and Approve - 100% Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5260 | D5270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - 90% Wet Utility Relocation Plans (COT) | Review and Approve - 90% Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5240 | D5250 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - 60% Wet Utility Relocation Plans (COT) | Review and Approve - 60% Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5300 | D5310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Develop and Submit - Sign & Seal Wet Utility Relocation Plans (COT) | Issue - RFC Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5250 | D5260 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 60% Wet Utility Relocation Plans (COT) | Develop and Submit - 90% Wet Utility Relocation Plans (COT) | 0 |  |  | H
D5310 | U1530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | 0 |  |  | H
D5310 | U1540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.2 City of Tampa Water Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | 0 |  |  | H
D5310 | U1670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | 0 |  |  | H
D5310 | U1690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | 0 |  |  | H
D5310 | U1680 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | 0 |  |  | H
D5310 | U1700 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | 0 |  |  | H
D5310 | U1710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Wet Utility Relocation Plans (COT) | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | 0 |  |  | H
D5310 | U1270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | 0 |  |  | H
D5310 | U1280 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | 0 |  |  | H
D5310 | U1290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | 0 |  |  | H
D5310 | U1300 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | 0 |  |  | H
D5310 | U1310 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | 0 |  |  | H
D5310 | U1320 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | 0 |  |  | H
D5310 | U1330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | 0 |  |  | H
D5310 | U1340 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | 0 |  |  | H
D5310 | U1350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | 0 |  |  | H
D5310 | U1370 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | 0 |  |  | H
D5310 | U1360 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | 0 |  |  | H
D5310 | U1390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | 0 |  |  | H
D5310 | U1380 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | 0 |  |  | H
D5310 | U1410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | 0 |  |  | H
D5310 | U1400 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | I-275 - I-4 - IBL(all) - B1.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Wet Utility Relocation Plans (COT) | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | 0 |  |  | H
D3190 | D5240 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.3 R3 60" Drainage System Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.25.1 Wet Utility Relocation Plans - City Of Tampa (DRMP) | Review and Approve - 60% - 60" Drainage System - R3 | Develop and Submit - 60% Wet Utility Relocation Plans (COT) | 0 |  |  | H
D1220 | D5320 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | Perform Geotechnical Investigation - Cat2 Brg 10 - R3 | 0 |  |  | H
D5320 | D1440 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.10.5.1 R3 Bridge 10 - Design Category 2 | Perform Geotechnical Investigation - Cat2 Brg 10 - R3 | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1350 | D5330 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | Perform Geotechnical Investigation - Cat1 Brg 08 - R3 | 0 |  |  | H
D5330 | D1540 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.2 R3 Bridge 08 - Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 08 - R3 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D3500 | D5340 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | Perform Geotechnical Investigation - Cat1 Brg 09 - R3 | 0 |  |  | H
D5340 | D3510 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.10.5.3 R3 Bridge 09 - Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 09 - R3 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3620 | D5350 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | Perform Geotechnical Investigation - Cat1 Brg 11 - R3 | 0 |  |  | H
D5350 | D3630 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.5 R3 Bridge 11 - Design Category 1 (DRMP) | Perform Geotechnical Investigation - Cat1 Brg 11 - R3 | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | 0 |  |  | H
D3560 | D5360 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Develop and Submit - 90% Cat1 Brg 12 Plans - R3 | Perform Geotechnical Investigation - Cat1 Brg 12 - R3 | 0 |  |  | H
D5360 | D3570 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.5.4 R3 Bridge 12 - Design Category 1 (DRMP) | Perform Geotechnical Investigation - Cat1 Brg 12 - R3 | Review and Approve - 90% Cat1 Brg 12 Plans - R3 | 0 |  |  | H
D3440 | D5370 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Develop and Submit - 90% Cat1 Brg 07 Plans - R2 | Perform Geotechnical Investigation - Cat1 Brg 07 - R2 | 0 |  |  | H
D5370 | D3450 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.2 R2 Bridge 07 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 07 - R2 | Review and Approve - 90% Cat1 Brg 07 Plans - R2 | 0 |  |  | H
D3040 | D5380 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Develop and Submit - 90% Cat1 Brg 06 Plans - R2 | Perform Geotechnical Investigation - Cat1 Brg 06 - R2 | 0 |  |  | H
D5380 | D3050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.12.4.1 R2 Bridge 06 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 06 - R2 | Review and Approve - 90% Cat1 Brg 06 Plans - R2 | 0 |  |  | H
D3380 | D5390 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | Perform Geotechnical Investigation - Cat1 Brg 05 - R1 | 0 |  |  | H
D5390 | D3390 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.3 R1 Bridge 05 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 05 - R1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3320 | D5400 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Develop and Submit - 90% Cat1 Brg 04 Plans - R1 | Perform Geotechnical Investigation - Cat1 Brg 04 - R1 | 0 |  |  | H
D5400 | D3330 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.4 R1 Bridge 04 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 04 - R1 | Review and Approve - 90% Cat1 Brg 04 Plans - R1 | 0 |  |  | H
D2800 | D5410 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | Perform Geotechnical Investigation - Cat1 Brg 03 - R1 | 0 |  |  | H
D5410 | D2810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.6 R1 Bridge 03 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 03 - R1 | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2860 | D5420 | SS | Completed | Completed | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | Perform Geotechnical Investigation - Cat2 Brg 02 - R1 | 0 |  |  | H
D5420 | D2870 | FS | Completed | In Progress | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - IBL(all) - B1.3.11.4.2 R1 Bridge 02 Design Category 2 | Perform Geotechnical Investigation - Cat2 Brg 02 - R1 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D3260 | D5430 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | Perform Geotechnical Investigation - Cat1 Brg 01 - R1 | 0 |  |  | H
D5430 | D3270 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - IBL(all) - B1.3.11.4.1 R1 Bridge 01 Design Category 1 | Perform Geotechnical Investigation - Cat1 Brg 01 - R1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D1680 | D5440 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-1 | Perform Geotechnical Investigation - MSE Wall RW 1-1 | 0 |  |  | H
D5440 | D1900 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Perform Geotechnical Investigation - MSE Wall RW 1-1 | Review and Approve - 90% MSE Wall RW 1-1 | 0 |  |  | H
D3680 | D5450 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | Perform Geotechnical Investigation - MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D5450 | D3690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - IBL(all) - B1.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Perform Geotechnical Investigation - MSE Wall RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3740 | D5460 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | Perform Geotechnical Investigation - MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D5460 | D3750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Perform Geotechnical Investigation - MSE Wall RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3800 | D5470 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Perform Geotechnical Investigation - MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D5470 | D3810 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - IBL(all) - B1.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Perform Geotechnical Investigation - MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3860 | D5480 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Perform Geotechnical Investigation - MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D5480 | D3870 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - IBL(all) - B1.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Perform Geotechnical Investigation - MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3980 | D5490 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | Perform Geotechnical Investigation - MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D5490 | D3990 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - IBL(all) - B1.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Perform Geotechnical Investigation - MSE Wall RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D4040 | D5500 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | Perform Geotechnical Investigation - MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D5500 | D4050 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Perform Geotechnical Investigation - MSE Wall RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4100 | D5510 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | Perform Geotechnical Investigation - MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D5510 | D4110 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - IBL(all) - B1.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Perform Geotechnical Investigation - MSE Wall RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4160 | D5520 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Develop and Submit - 90% MSE Wall RW 4-1 Br 4 | Perform Geotechnical Investigation - MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D5520 | D4170 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.10 R1 - Retaining Wall Design RW 4-1 Br 4 | Perform Geotechnical Investigation - MSE Wall RW 4-1 Br 4 | Review and Approve - 90% MSE Wall RW 4-1 Br 4 | 0 |  |  | H
D4220 | D5530 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Develop and Submit - 90% MSE Wall RW 4-2 Br 4 | Perform Geotechnical Investigation - MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D5530 | D4230 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | I-275 - I-4 - IBL(all) - B1.3.11.1.11 R1 - Retaining Wall Design RW 4-2 Br 4 | Perform Geotechnical Investigation - MSE Wall RW 4-2 Br 4 | Review and Approve - 90% MSE Wall RW 4-2 Br 4 | 0 |  |  | H
D4280 | D5540 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | Perform Geotechnical Investigation - MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D5540 | D4290 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Perform Geotechnical Investigation - MSE Wall RW 5-1 Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4340 | D5550 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | Perform Geotechnical Investigation - MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D5550 | D4350 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - IBL(all) - B1.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Perform Geotechnical Investigation - MSE Wall RW 5-2 Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4880 | D5560 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Perform Geotechnical Investigation - MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D5560 | D4890 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - IBL(all) - B1.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Perform Geotechnical Investigation - MSE Wall RW 100 I-4 EB (Br 3 & 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4400 | D5570 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Perform Geotechnical Investigation - MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D5570 | D4410 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - IBL(all) - B1.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Perform Geotechnical Investigation - MSE Wall RW 6-1 Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4460 | D5580 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Perform Geotechnical Investigation - MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D5580 | D4470 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Perform Geotechnical Investigation - MSE Wall RW 7-1 Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0 |  |  | H
D4520 | D5590 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | Perform Geotechnical Investigation - MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D5590 | D4530 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - IBL(all) - B1.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Perform Geotechnical Investigation - MSE Wall RW 7-2 Ramp EN / Br 7 | Review and Approve - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0 |  |  | H
D5000 | D5600 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 103 Ramp EN | Perform Geotechnical Investigation - MSE Wall RW 103 Ramp EN | 0 |  |  | H
D5600 | D5010 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.8 R2 - Retaining Wall Design RW 103 Ramp EN (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 103 Ramp EN | Review and Approve - 90% MSE Wall RW 103 Ramp EN | 0 |  |  | H
D5060 | D5610 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Develop and Submit - 90% MSE Wall RW 104 Ramp EN | Perform Geotechnical Investigation - MSE Wall RW 104 Ramp EN | 0 |  |  | H
D5610 | D5070 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | I-275 - I-4 - IBL(all) - B1.3.12.1.9 R2 - Retaining Wall Design RW 104 Ramp EN (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 104 Ramp EN | Review and Approve - 90% MSE Wall RW 104 Ramp EN | 0 |  |  | H
D4580 | D5620 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | Perform Geotechnical Investigation - MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D5620 | D4590 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Perform Geotechnical Investigation - MSE Wall RW 8-1 Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4640 | D5630 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | Perform Geotechnical Investigation - MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D5630 | D4650 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - IBL(all) - B1.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Perform Geotechnical Investigation - MSE Wall RW 8-2 Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4700 | D5640 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | Perform Geotechnical Investigation - MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D5640 | D4710 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 9 (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 9-1 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 9 | 0 |  |  | H
D4760 | D5650 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | Perform Geotechnical Investigation - MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D5650 | D4770 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 9-2 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4820 | D5660 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | Perform Geotechnical Investigation - MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D5660 | D4830 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 (DRMP) | Perform Geotechnical Investigation - MSE Wall RW 9-3 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4940 | D5670 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% MSE Wall RW 102 Ramp C | Perform Geotechnical Investigation - MSE Wall RW 102 Ramp C | 0 |  |  | H
D5670 | D4950 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - IBL(all) - B1.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Perform Geotechnical Investigation - MSE Wall RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | 0 |  |  | H
D1200 | D5680 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Develop and Submit - 90% Roadway Plans - R1 | Perform Geotechnical Investigation - Roadway - R1 | 0 |  |  | H
D5680 | D1460 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | I-275 - I-4 - IBL(all) - B1.3.11.19 R1 Roadway Design (ASI) | Perform Geotechnical Investigation - Roadway - R1 | Review and Approve - 90% Roadway Plans - R1 | 0 |  |  | H
D2680 | D5690 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Develop and Submit - 90% Roadway Plans - R2 | Perform Geotechnical Investigation - Roadway - R2 | 0 |  |  | H
D5690 | D2690 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | I-275 - I-4 - IBL(all) - B1.3.12.10 R2 Roadway Plans (ACP) | Perform Geotechnical Investigation - Roadway - R2 | Review and Approve - 90% Roadway Plans - R2 | 0 |  |  | H
D2740 | D5700 | SS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Develop and Submit - 90% Roadway Plans - R3 | Perform Geotechnical Investigation - Roadway - R3 | 0 |  |  | H
D5700 | D2750 | FS | Not Started | Not Started | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1 | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | I-275 - I-4 - IBL(all) - B1.3.10.24 R3 Roadway Design (DRMP) | Perform Geotechnical Investigation - Roadway - R3 | Review and Approve - 90% Roadway Plans - R3 | 0 |  |  | H

## TASKRSRC
rsrc_id | task_id | TASK__status_code | role_id | acct_id | rsrc_type | start_date | end_date | delete_record_flag
Resource ID | Activity ID | (*)Activity Status | Role ID | Cost Account ID | (*)Resource Type | (*)Start | (*)Finish | Delete This Row
DRAIN | A36670 | Not Started | Crews.Drainage Crew |  | Labor | 2024-04-29 08:00 | 2024-05-29 16:00
TC-Maint. | A1070 | Not Started |  |  | Labor | 2023-06-22 08:00 | 2023-06-29 16:00
SUB-TUNNEL | A36660 | Not Started |  |  | Labor | 2023-12-21 08:00 | 2024-01-09 16:00
SUB-TUNNEL | A36650 | Not Started |  |  | Labor | 2023-12-07 08:00 | 2023-12-19 16:00
SUB-TUNNEL | A36640 | Not Started |  |  | Labor | 2024-04-15 08:00 | 2024-04-26 16:00
SUB-TUNNEL | A36630 | Not Started |  |  | Labor | 2024-04-03 08:00 | 2024-04-12 16:00
SUB-TUNNEL | A36620 | Not Started |  |  | Labor | 2024-03-05 08:00 | 2024-03-18 16:00
SUB-TUNNEL | A36610 | Not Started |  |  | Labor | 2024-02-08 08:00 | 2024-02-20 16:00
SUB-TUNNEL | A36600 | Not Started |  |  | Labor | 2024-01-25 08:00 | 2024-02-06 16:00
SUB-TUNNEL | A36590 | Not Started |  |  | Labor | 2024-01-10 08:00 | 2024-01-23 16:00
SUB-TUNNEL | A36580 | Not Started |  |  | Labor | 2023-11-21 08:00 | 2023-12-05 16:00
SUB-TUNNEL | A36570 | Not Started |  |  | Labor | 2023-06-22 08:00 | 2023-07-17 16:00
SUB-TUNNEL | A36560 | Not Started |  |  | Labor | 2023-05-26 08:00 | 2023-06-20 16:00
SUB-TUNNEL | A36550 | Not Started |  |  | Labor | 2023-06-13 08:00 | 2023-07-25 16:00
SUB-TUNNEL | A36540 | Not Started |  |  | Labor | 2023-07-27 08:00 | 2023-09-15 16:00
SUB-TUNNEL | A36500 | Not Started |  |  | Labor | 2023-11-30 08:00 | 2024-01-30 16:00
SUB-TUNNEL | A36440 | Not Started |  |  | Labor | 2023-05-26 08:00 | 2023-06-12 16:00
SUB-TUNNEL | A36450 | Not Started |  |  | Labor | 2023-09-18 08:00 | 2023-10-16 16:00
SUB-TUNNEL | A36480 | Not Started |  |  | Labor | 2023-10-17 08:00 | 2023-11-29 16:00
SUB-TUNNEL | A36510 | Not Started |  |  | Labor | 2024-02-01 08:00 | 2024-03-04 16:00
SUB-TUNNEL | A36530 | Not Started |  |  | Labor | 2024-03-05 08:00 | 2024-04-02 16:00
ST-FOOT | A36430 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-18 08:00 | 2026-01-15 16:00
ST-FOOT | A36410 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-18 08:00 | 2026-01-15 16:00
ST-FOOT | A36400 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-18 08:00 | 2026-01-15 16:00
ST-FOOT | A36390 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-18 08:00 | 2026-01-15 16:00
ST-FOOT | A36380 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-18 08:00 | 2026-01-15 16:00
ST-FOOT | A36370 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-27 08:00 | 2025-11-13 16:00
ST-PILE | A36360 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-22 08:00 | 2025-10-24 16:00
ST-FOOT | A36350 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-27 08:00 | 2025-11-13 16:00
ST-PILE | A36340 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-22 08:00 | 2025-10-24 16:00
ST-PILE | A36330 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-24 08:00 | 2025-10-28 16:00
ST-PILE | A36320 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-23 08:00 | 2025-10-27 16:00
ST-FOOT | A36310 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-23 08:00 | 2025-07-11 16:00
ST-FOOT | A36300 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-25 08:00 | 2025-07-29 16:00
ST-FOOT | A36290 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-11 08:00 | 2025-07-15 16:00
ST-MSE | A21018 | Not Started | Crews.Wall Crew |  | Labor | 2026-02-10 08:00 | 2026-03-19 16:00
ST-MSE | A36280 | Not Started | Crews.Wall Crew |  | Labor | 2025-09-15 08:00 | 2025-10-09 16:00
ST-MSE | A22845 | Not Started | Crews.Wall Crew |  | Labor | 2025-03-31 08:00 | 2025-04-28 16:00
EW-SML | A16345 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-07-25 08:00 | 2024-08-22 16:00
EW-SML | A15755 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-08-21 08:00 | 2023-10-04 16:00
ST-MSE | A33314 | Not Started | Crews.Wall Crew |  | Labor | 2026-01-22 08:00 | 2026-02-27 16:00
ST-MSE | A26242 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-13 08:00 | 2024-10-21 16:00
ST-MSE | A26136 | Not Started | Crews.Wall Crew |  | Labor | 2024-11-01 08:00 | 2024-12-13 16:00
ST-MSE | A26133 | Not Started | Crews.Wall Crew |  | Labor | 2024-11-01 08:00 | 2024-12-13 16:00
EW-SML | A26058 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-22 08:00 | 2024-09-27 16:00
EW-SML | A26056 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-22 08:00 | 2024-09-27 16:00
EW-SML | A26053 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-06-05 08:00 | 2024-07-09 16:00
ST-MSE | A26028 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-30 08:00 | 2024-10-30 16:00
ST-MSE | A26026 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-30 08:00 | 2024-10-30 16:00
ST-MSE | A26023 | Not Started | Crews.Wall Crew |  | Labor | 2024-07-10 08:00 | 2024-08-19 16:00
ST-MSE | A36270 | Not Started | Crews.Wall Crew |  | Labor | 2025-06-04 08:00 | 2025-06-24 16:00
ST-MSE | A36260 | Not Started | Crews.Wall Crew |  | Labor | 2025-01-31 08:00 | 2025-03-06 16:00
ST-MSE | A15465 | Not Started | Crews.Wall Crew |  | Labor | 2024-03-28 08:00 | 2024-05-13 16:00
EW-SML | A15455 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-02-16 08:00 | 2024-03-27 16:00
ST-MSE | A21015 | Not Started | Crews.Wall Crew |  | Labor | 2026-02-10 08:00 | 2026-03-19 16:00
ST-MSE | A21995 | Not Started | Crews.Wall Crew |  | Labor | 2025-07-30 08:00 | 2025-09-05 16:00
SUB-TUNNEL | A36060 | Not Started |  |  | Labor | 2024-03-05 08:00 | 2024-03-28 16:00
SUB-TUNNEL | A36050 | Not Started |  |  | Labor | 2024-02-01 08:00 | 2024-02-26 16:00
SUB-TUNNEL | A36040 | Not Started |  |  | Labor | 2023-11-30 08:00 | 2024-01-02 16:00
SUB-TUNNEL | A36030 | Not Started |  |  | Labor | 2023-10-17 08:00 | 2023-11-07 16:00
SUB-TUNNEL | A36020 | Not Started |  |  | Labor | 2023-09-18 08:00 | 2023-10-10 16:00
SUB-TUNNEL | A36010 | Not Started |  |  | Labor | 2023-07-27 08:00 | 2023-08-17 16:00
SUB-TUNNEL | A36000 | Not Started |  |  | Labor | 2023-05-04 08:00 | 2023-05-25 16:00
ST-BEAM | A35990 | Not Started | Crews.Structures Crew |  | Labor | 2023-10-02 08:00 | 2023-10-06 16:00
ST-BEAM | A35970 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-30 08:00 | 2025-02-05 16:00
ST-DECK | A35960 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-23 16:00
SUB-ST-REBAR | A35950 | Not Started |  |  | Labor | 2025-05-02 08:00 | 2025-05-06 16:00
ST-POUR | A35930 | Not Started |  |  | Labor | 2025-04-24 08:00 | 2025-04-24 16:00
SUB-ST-REBAR | A35920 | Not Started |  |  | Labor | 2025-04-09 08:00 | 2025-04-22 16:00
ST-DECK | A35910 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-11 08:00 | 2025-04-08 16:00
SUB-ST-SIP | A35900 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-10 16:00
ST-DECK | A35870 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-22 16:00
SUB-ST-REBAR | A35860 | Not Started |  |  | Labor | 2025-04-18 08:00 | 2025-04-22 16:00
ST-POUR | A35840 | Not Started |  |  | Labor | 2025-04-10 08:00 | 2025-04-10 16:00
SUB-ST-REBAR | A35830 | Not Started |  |  | Labor | 2025-04-03 08:00 | 2025-04-09 16:00
ST-DECK | A35820 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-11 08:00 | 2025-04-02 16:00
SUB-ST-SIP | A35810 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-10 16:00
ST-DECK | A35780 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-22 16:00
SUB-ST-REBAR | A35770 | Not Started |  |  | Labor | 2025-04-25 08:00 | 2025-04-29 16:00
ST-POUR | A35750 | Not Started |  |  | Labor | 2025-04-17 08:00 | 2025-04-17 16:00
SUB-ST-REBAR | A35740 | Not Started |  |  | Labor | 2025-04-03 08:00 | 2025-04-09 16:00
ST-DECK | A35730 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-11 08:00 | 2025-04-02 16:00
SUB-ST-SIP | A35720 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-10 16:00
TC-Maint. | A35700 | Not Started |  |  | Labor | 2026-07-27 08:00 | 2026-07-27 16:00
SUB-BR-SLIP | A35620 | Not Started |  |  | Labor | 2026-06-08 08:00 | 2026-06-25 16:00
SUB-ASPH | A35680 | Not Started |  |  | Labor | 2026-07-16 08:00 | 2026-07-16 16:00
EW-ABC | A35670 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-07-13 08:00 | 2026-07-14 16:00
PIPE | A35660 | Not Started | Crews.Drainage Crew |  | Labor | 2026-07-09 08:00 | 2026-07-10 16:00
CP-SLIP | A35650 | Not Started | Crews.Paving Crew |  | Labor | 2026-07-01 08:00 | 2026-07-07 16:00
SUB-ASPH | A35640 | Not Started |  |  | Labor | 2026-06-30 08:00 | 2026-06-30 16:00
EW-STAB | A35630 | Not Started |  |  | Labor | 2026-06-26 08:00 | 2026-06-29 16:00
EW-SML | A35610 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-06-05 08:00 | 2026-06-05 16:00
EW-STR | A35560 | Not Started |  |  | Labor | 2023-10-02 08:00 | 2023-11-03 16:00
ST-MSE | A35550 | Not Started | Crews.Wall Crew |  | Labor | 2024-02-08 08:00 | 2024-02-15 16:00
ST-ABUT | A35530 | Not Started | Crews.Structures Crew |  | Labor | 2024-02-16 08:00 | 2024-03-04 16:00
ST-PILE | A35520 | Not Started | Crews.Structures Crew |  | Labor | 2023-11-07 08:00 | 2023-11-16 16:00
EW- ALL EW | A35500 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-11-06 08:00 | 2023-11-06 16:00
EW-STR | A35490 | Not Started |  |  | Labor | 2023-10-02 08:00 | 2023-10-12 16:00
ST-MSE | A35480 | Not Started | Crews.Wall Crew |  | Labor | 2024-02-08 08:00 | 2024-03-22 16:00
ST-ABUT | A35460 | Not Started | Crews.Structures Crew |  | Labor | 2024-03-25 08:00 | 2024-04-08 16:00
ST-PILE | A35450 | Not Started | Crews.Structures Crew |  | Labor | 2023-10-16 08:00 | 2023-10-23 16:00
EW- ALL EW | A35430 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-10-13 08:00 | 2023-10-13 16:00
TC-Maint. | A35410 | Not Started |  |  | Labor | 2025-02-21 08:00 | 2025-02-25 16:00
ST-DECK | A35390 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-22 16:00
SUB-ST-REBAR | A35380 | Not Started |  |  | Labor | 2025-04-24 08:00 | 2025-04-28 16:00
ST-POUR | A35360 | Not Started |  |  | Labor | 2025-04-15 08:00 | 2025-04-15 16:00
SUB-ST-REBAR | A35350 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-14 16:00
ST-DECK | A35340 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-10 08:00 | 2025-03-06 16:00
SUB-ST-SIP | A35330 | Not Started |  |  | Labor | 2025-02-06 08:00 | 2025-02-07 16:00
ST-BEAM | A35320 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-27 08:00 | 2025-03-06 16:00
ST-CAP | A35300 | Not Started | Crews.Structures Crew |  | Labor | 2024-02-09 08:00 | 2024-02-23 16:00
ST-COL | A35280 | Not Started | Crews.Structures Crew |  | Labor | 2024-01-19 08:00 | 2024-02-01 16:00
ST-FOOT | A35260 | Not Started | Crews.Structures Crew |  | Labor | 2024-01-09 08:00 | 2024-01-11 16:00
ST-PILE | A35250 | Not Started | Crews.Structures Crew |  | Labor | 2023-12-12 08:00 | 2024-01-08 16:00
EW-STR | A35230 | Not Started |  |  | Labor | 2023-12-08 08:00 | 2023-12-11 16:00
ST-DECK | A35210 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-21 16:00
SUB-ST-REBAR | A35200 | Not Started |  |  | Labor | 2025-04-17 08:00 | 2025-04-21 16:00
ST-POUR | A35180 | Not Started |  |  | Labor | 2025-04-08 08:00 | 2025-04-08 16:00
SUB-ST-REBAR | A35170 | Not Started |  |  | Labor | 2025-04-01 08:00 | 2025-04-07 16:00
ST-DECK | A35160 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-11 08:00 | 2025-03-31 16:00
SUB-ST-SIP | A35150 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-10 16:00
ST-BEAM | A35140 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-27 08:00 | 2025-03-06 16:00
ST-DECK | A35120 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-22 16:00
SUB-ST-REBAR | A35110 | Not Started |  |  | Labor | 2025-04-17 08:00 | 2025-04-21 16:00
ST-POUR | A35090 | Not Started |  |  | Labor | 2025-04-09 08:00 | 2025-04-09 16:00
SUB-ST-REBAR | A35080 | Not Started |  |  | Labor | 2025-04-02 08:00 | 2025-04-08 16:00
ST-DECK | A35070 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-11 08:00 | 2025-04-01 16:00
SUB-ST-SIP | A35060 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-10 16:00
ST-BEAM | A35050 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-27 08:00 | 2025-03-06 16:00
ST-CAP | A35030 | Not Started | Crews.Structures Crew |  | Labor | 2024-01-16 08:00 | 2024-01-30 16:00
ST-COL | A35010 | Not Started | Crews.Structures Crew |  | Labor | 2023-12-15 08:00 | 2024-01-08 16:00
ST-FOOT | A34990 | Not Started | Crews.Structures Crew |  | Labor | 2023-12-04 08:00 | 2023-12-07 16:00
ST-PILE | A34980 | Not Started | Crews.Structures Crew |  | Labor | 2023-11-16 08:00 | 2023-12-07 16:00
EW-STR | A34960 | Not Started |  |  | Labor | 2023-11-13 08:00 | 2023-11-14 16:00
SUB-STRIP | A34950 | Not Started |  |  | Labor | 2025-06-02 08:00 | 2025-06-02 16:00
SUB-ST-GROOVE | A34940 | Not Started |  |  | Labor | 2025-05-27 08:00 | 2025-05-30 16:00
SUB-DGRIND | A34930 | Not Started |  |  | Labor | 2025-05-19 08:00 | 2025-05-23 16:00
SUB-ST-PARAPET | A34920 | Not Started |  |  | Labor | 2025-05-08 08:00 | 2025-05-16 16:00
ST-APPR | A34910 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-25 08:00 | 2025-05-05 16:00
ST-APPR | A34900 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-15 08:00 | 2025-04-25 16:00
ST-DECK | A34880 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-19 08:00 | 2025-05-22 16:00
SUB-ST-REBAR | A34870 | Not Started |  |  | Labor | 2025-04-22 08:00 | 2025-04-25 16:00
ST-POUR | A34850 | Not Started |  |  | Labor | 2025-04-14 08:00 | 2025-04-14 16:00
SUB-ST-REBAR | A34840 | Not Started |  |  | Labor | 2025-04-07 08:00 | 2025-04-11 16:00
ST-DECK | A34830 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-11 08:00 | 2025-04-04 16:00
SUB-ST-SIP | A34820 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-10 16:00
ST-BEAM | A34810 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-27 08:00 | 2025-03-06 16:00
ST-CAP | A34790 | Not Started | Crews.Structures Crew |  | Labor | 2023-12-14 08:00 | 2024-01-04 16:00
ST-COL | A34770 | Not Started | Crews.Structures Crew |  | Labor | 2023-11-27 08:00 | 2023-12-05 16:00
ST-FOOT | A34750 | Not Started | Crews.Structures Crew |  | Labor | 2023-11-13 08:00 | 2023-11-16 16:00
ST-PILE | A34740 | Not Started | Crews.Structures Crew |  | Labor | 2023-10-24 08:00 | 2023-11-09 16:00
EW-STR | A34720 | Not Started |  |  | Labor | 2023-10-20 08:00 | 2023-10-23 16:00
PIPE | A34660 | Not Started | Crews.Drainage Crew |  | Labor | 2026-06-05 08:00 | 2026-07-06 16:00
SUB-ASPH | A34710 | Not Started |  |  | Labor | 2026-07-23 08:00 | 2026-07-23 16:00
FLATWORK | A34690 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2026-07-17 08:00 | 2026-07-17 16:00
EW-ABC | A34680 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-07-14 08:00 | 2026-07-16 16:00
EW-STAB | A34670 | Not Started |  |  | Labor | 2026-07-07 08:00 | 2026-07-13 16:00
EW- ALL EW | A34650 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-06-04 08:00 | 2026-06-04 16:00
FLATWORK | A34700 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2026-07-20 08:00 | 2026-07-21 16:00
PIPE | A34590 | Not Started | Crews.Drainage Crew |  | Labor | 2026-06-05 08:00 | 2026-07-06 16:00
SUB-ASPH | A34640 | Not Started |  |  | Labor | 2026-07-24 08:00 | 2026-07-24 16:00
FLATWORK | A34620 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2026-07-14 08:00 | 2026-07-20 16:00
EW-ABC | A34610 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-07-10 08:00 | 2026-07-13 16:00
EW-STAB | A34600 | Not Started |  |  | Labor | 2026-07-07 08:00 | 2026-07-09 16:00
EW- ALL EW | A34580 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-06-04 08:00 | 2026-06-04 16:00
FLATWORK | A34630 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2026-07-21 08:00 | 2026-07-23 16:00
SUB-GRAIL | A34530 | Not Started |  |  | Labor | 2026-07-13 08:00 | 2026-07-13 16:00
SUB-ASPH | A34520 | Not Started |  |  | Labor | 2026-07-10 08:00 | 2026-07-10 16:00
EW-ABC | A34510 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-07-09 08:00 | 2026-07-09 16:00
PIPE | A34500 | Not Started | Crews.Drainage Crew |  | Labor | 2026-07-07 08:00 | 2026-07-07 16:00
CP-SLIP | A34490 | Not Started | Crews.Paving Crew |  | Labor | 2026-06-12 08:00 | 2026-06-15 16:00
SUB-ASPH | A34480 | Not Started |  |  | Labor | 2026-06-11 08:00 | 2026-06-11 16:00
EW-STAB | A34470 | Not Started |  |  | Labor | 2026-06-09 08:00 | 2026-06-09 16:00
EW-SML | A34450 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-06-05 08:00 | 2026-06-08 16:00
SUB-GRAIL | A34440 | Not Started |  |  | Labor | 2025-11-06 08:00 | 2025-11-07 16:00
TC-Maint. | A34430 | Not Started |  |  | Labor | 2026-06-04 08:00 | 2026-06-04 16:00
DM-BRIDGE | A34400 | Not Started | Crews.Demolition Crew |  | Labor | 2025-11-21 08:00 | 2025-12-09 16:00
DM-BRIDGE | A34390 | Not Started | Crews.Demolition Crew |  | Labor | 2025-10-21 08:00 | 2025-11-20 16:00
DM-BRIDGE | A34380 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-15 08:00 | 2025-12-16 16:00
DM-BRIDGE | A34370 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-01 08:00 | 2025-12-12 16:00
SUB-ASPH | A34360 | Not Started |  |  | Labor | 2026-04-14 08:00 | 2026-04-14 16:00
EW-ABC | A34350 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-04-10 08:00 | 2026-04-13 16:00
PIPE | A34340 | Not Started | Crews.Drainage Crew |  | Labor | 2026-04-07 08:00 | 2026-04-09 16:00
CP-SLIP | A34330 | Not Started | Crews.Paving Crew |  | Labor | 2026-03-30 08:00 | 2026-04-06 16:00
SUB-ASPH | A34320 | Not Started |  |  | Labor | 2026-03-27 08:00 | 2026-03-27 16:00
EW-STAB | A34310 | Not Started |  |  | Labor | 2026-03-10 08:00 | 2026-03-12 16:00
EW-SML | A34300 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
ST-CIP | A34290 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-13 08:00 | 2026-03-23 16:00
SUB-BR-SLIP | A34280 | Not Started |  |  | Labor | 2026-03-24 08:00 | 2026-03-26 16:00
ST-MSE | A34270 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-03 08:00 | 2026-03-09 16:00
SUB-ASPH | A34260 | Not Started |  |  | Labor | 2026-03-27 08:00 | 2026-03-27 16:00
EW-ABC | A34250 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-03-24 08:00 | 2026-03-26 16:00
PIPE | A34240 | Not Started | Crews.Drainage Crew |  | Labor | 2026-03-19 08:00 | 2026-03-23 16:00
EW-STAB | A34230 | Not Started |  |  | Labor | 2026-03-03 08:00 | 2026-03-04 16:00
EW-SML | A34220 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
ST-CIP | A34210 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-05 08:00 | 2026-03-13 16:00
SUB-BR-SLIP | A34200 | Not Started |  |  | Labor | 2026-03-16 08:00 | 2026-03-17 16:00
SUB-ASPH | A34190 | Not Started |  |  | Labor | 2026-04-27 08:00 | 2026-04-27 16:00
EW-ABC | A34180 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-04-24 08:00 | 2026-04-24 16:00
PIPE | A34170 | Not Started | Crews.Drainage Crew |  | Labor | 2026-04-23 08:00 | 2026-04-23 16:00
CP-SLIP | A34160 | Not Started | Crews.Paving Crew |  | Labor | 2026-04-20 08:00 | 2026-04-21 16:00
SUB-ASPH | A34150 | Not Started |  |  | Labor | 2026-04-17 08:00 | 2026-04-17 16:00
EW-STAB | A34140 | Not Started |  |  | Labor | 2026-04-09 08:00 | 2026-04-10 16:00
EW-SML | A34130 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-03-04 08:00 | 2026-03-05 16:00
ST-CIP | A34120 | Not Started | Crews.Wall Crew |  | Labor | 2026-04-13 08:00 | 2026-04-14 16:00
SUB-BR-SLIP | A34110 | Not Started |  |  | Labor | 2026-04-16 08:00 | 2026-04-16 16:00
ST-MSE | A34100 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-06 08:00 | 2026-04-08 16:00
DM-BRIDGE | A34040 | Not Started | Crews.Demolition Crew |  | Labor | 2025-10-22 08:00 | 2025-10-23 16:00
DM-BRIDGE | A34030 | Not Started | Crews.Demolition Crew |  | Labor | 2025-10-22 08:00 | 2025-10-22 16:00
DM-BRIDGE | A34020 | Not Started | Crews.Demolition Crew |  | Labor | 2025-10-21 08:00 | 2025-10-28 16:00
ST-ABUT | A33980 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-29 08:00 | 2025-10-29 16:00
EW- ALL EW | A33950 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-21 08:00 | 2025-10-21 16:00
ST-ABUT | A33910 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-28 08:00 | 2025-10-28 16:00
EW- ALL EW | A33880 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-21 08:00 | 2025-10-21 16:00
ST-CAP | A33860 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-01 08:00 | 2025-12-01 16:00
EW- ALL EW | A33830 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-21 08:00 | 2025-10-21 16:00
ST-DECK | A33810 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-06 08:00 | 2026-01-06 16:00
SUB-ST-REBAR | A33800 | Not Started |  |  | Labor | 2026-01-05 08:00 | 2026-01-05 16:00
ST-POUR | A33780 | Not Started |  |  | Labor | 2025-12-16 08:00 | 2025-12-16 16:00
SUB-ST-REBAR | A33770 | Not Started |  |  | Labor | 2025-12-15 08:00 | 2025-12-15 16:00
ST-DECK | A33760 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-09 08:00 | 2025-12-12 16:00
SUB-ST-SIP | A33750 | Not Started |  |  | Labor | 2025-12-08 08:00 | 2025-12-08 16:00
ST-BEAM | A33740 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-05 08:00 | 2025-12-05 16:00
ST-DECK | A33720 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-06 08:00 | 2026-01-06 16:00
SUB-ST-REBAR | A33710 | Not Started |  |  | Labor | 2026-01-05 08:00 | 2026-01-05 16:00
ST-POUR | A33690 | Not Started |  |  | Labor | 2025-12-18 08:00 | 2025-12-18 16:00
SUB-ST-REBAR | A33680 | Not Started |  |  | Labor | 2025-12-16 08:00 | 2025-12-16 16:00
ST-DECK | A33670 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-09 08:00 | 2025-12-15 16:00
SUB-ST-SIP | A33660 | Not Started |  |  | Labor | 2025-12-08 08:00 | 2025-12-08 16:00
ST-BEAM | A33650 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-05 08:00 | 2025-12-05 16:00
SUB-STRIP | A33640 | Not Started |  |  | Labor | 2026-01-09 08:00 | 2026-01-09 16:00
SUB-ST-GROOVE | A33630 | Not Started |  |  | Labor | 2026-01-08 08:00 | 2026-01-08 16:00
SUB-ST-PARAPET | A33610 | Not Started |  |  | Labor | 2026-01-07 08:00 | 2026-01-07 16:00
ST-DECK | A33570 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-06 08:00 | 2026-01-06 16:00
SUB-ST-REBAR | A33560 | Not Started |  |  | Labor | 2026-01-05 08:00 | 2026-01-05 16:00
ST-POUR | A33540 | Not Started |  |  | Labor | 2025-12-16 08:00 | 2025-12-16 16:00
SUB-ST-REBAR | A33530 | Not Started |  |  | Labor | 2025-12-15 08:00 | 2025-12-15 16:00
ST-DECK | A33520 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-09 08:00 | 2025-12-12 16:00
SUB-ST-SIP | A33510 | Not Started |  |  | Labor | 2025-12-08 08:00 | 2025-12-08 16:00
ST-BEAM | A33500 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-05 08:00 | 2025-12-05 16:00
ST-CAP | A33480 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-01 08:00 | 2025-12-01 16:00
EW- ALL EW | A33440 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-21 08:00 | 2025-10-21 16:00
EW-STR | A33430 | Not Started |  |  | Labor | 2026-01-22 08:00 | 2026-02-12 16:00
DM-BRIDGE | A33420 | Not Started | Crews.Demolition Crew |  | Labor | 2025-11-07 08:00 | 2025-11-25 16:00
DM-BRIDGE | A33410 | Not Started | Crews.Demolition Crew |  | Labor | 2025-10-21 08:00 | 2025-11-06 16:00
SUB-ASPH | A33400 | Not Started |  |  | Labor | 2026-06-03 08:00 | 2026-06-03 16:00
EW-ABC | A33390 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-06-02 08:00 | 2026-06-02 16:00
PIPE | A33380 | Not Started | Crews.Drainage Crew |  | Labor | 2026-05-28 08:00 | 2026-06-01 16:00
CP-SLIP | A33370 | Not Started | Crews.Paving Crew |  | Labor | 2026-04-09 08:00 | 2026-05-27 16:00
SUB-ASPH | A33360 | Not Started |  |  | Labor | 2026-04-08 08:00 | 2026-04-08 16:00
EW-STAB | A33350 | Not Started |  |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
EW-SML | A33340 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-01-08 08:00 | 2026-01-20 16:00
ST-CIP | A33330 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-03 08:00 | 2026-03-10 16:00
SUB-BR-SLIP | A33320 | Not Started |  |  | Labor | 2026-03-12 08:00 | 2026-04-07 16:00
ST-MSE | A33310 | Not Started | Crews.Wall Crew |  | Labor | 2026-01-22 08:00 | 2026-02-27 16:00
EW-STR | A33300 | Not Started |  |  | Labor | 2025-12-01 08:00 | 2025-12-12 16:00
ST-MSE | A33020 | Not Started | Crews.Wall Crew |  | Labor | 2026-01-05 08:00 | 2026-01-07 16:00
ST-ABUT | A33000 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-08 08:00 | 2026-01-13 16:00
ST-PILE | A32990 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-16 08:00 | 2025-12-23 16:00
EW- ALL EW | A32970 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-15 08:00 | 2025-12-15 16:00
SUB-STRIP | A32960 | Not Started |  |  | Labor | 2026-03-23 08:00 | 2026-03-23 16:00
SUB-ST-GROOVE | A32950 | Not Started |  |  | Labor | 2026-03-20 08:00 | 2026-03-20 16:00
SUB-DGRIND | A32940 | Not Started |  |  | Labor | 2026-03-19 08:00 | 2026-03-19 16:00
SUB-ST-PARAPET | A32930 | Not Started |  |  | Labor | 2026-03-17 08:00 | 2026-03-17 16:00
ST-APPR | A32920 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-02 08:00 | 2026-03-12 16:00
ST-APPR | A32910 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-02 08:00 | 2026-03-09 16:00
ST-DECK | A32890 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-12 08:00 | 2026-03-16 16:00
SUB-ST-REBAR | A32880 | Not Started |  |  | Labor | 2026-03-09 08:00 | 2026-03-10 16:00
ST-POUR | A32860 | Not Started |  |  | Labor | 2026-02-27 08:00 | 2026-02-27 16:00
SUB-ST-REBAR | A32850 | Not Started |  |  | Labor | 2026-02-23 08:00 | 2026-02-26 16:00
ST-DECK | A32840 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-30 08:00 | 2026-02-20 16:00
SUB-ST-SIP | A32830 | Not Started |  |  | Labor | 2026-01-29 08:00 | 2026-01-29 16:00
ST-BEAM | A32820 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-26 08:00 | 2026-01-27 16:00
EW-STR | A32720 | Not Started |  |  | Labor | 2025-12-01 08:00 | 2025-12-12 16:00
ST-MSE | A32710 | Not Started | Crews.Wall Crew |  | Labor | 2026-01-05 08:00 | 2026-01-13 16:00
ST-ABUT | A32690 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-15 08:00 | 2026-01-22 16:00
ST-PILE | A32680 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-16 08:00 | 2025-12-23 16:00
EW- ALL EW | A32660 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-15 08:00 | 2025-12-15 16:00
ST-FOOT | A32640 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-08 08:00 | 2026-01-12 16:00
ST-PILE | A32630 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-19 08:00 | 2026-01-07 16:00
ST-FOOT | A32610 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-08 08:00 | 2026-01-16 16:00
ST-DECK | A32410 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-05 08:00 | 2026-03-06 16:00
SUB-ST-REBAR | A32400 | Not Started |  |  | Labor | 2026-03-04 08:00 | 2026-03-04 16:00
ST-POUR | A32380 | Not Started |  |  | Labor | 2026-02-24 08:00 | 2026-02-24 16:00
SUB-ST-REBAR | A32370 | Not Started |  |  | Labor | 2026-02-23 08:00 | 2026-02-23 16:00
ST-DECK | A32360 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-12 08:00 | 2026-02-20 16:00
SUB-ST-SIP | A32350 | Not Started |  |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-BEAM | A32340 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
ST-DECK | A32320 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-12 08:00 | 2026-03-13 16:00
SUB-ST-REBAR | A32310 | Not Started |  |  | Labor | 2026-03-10 08:00 | 2026-03-10 16:00
ST-POUR | A32290 | Not Started |  |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
SUB-ST-REBAR | A32280 | Not Started |  |  | Labor | 2026-02-27 08:00 | 2026-02-27 16:00
ST-DECK | A32270 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-13 08:00 | 2026-02-26 16:00
SUB-ST-SIP | A32260 | Not Started |  |  | Labor | 2026-02-12 08:00 | 2026-02-12 16:00
ST-BEAM | A32250 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-DECK | A32230 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-16 08:00 | 2026-03-19 16:00
SUB-ST-REBAR | A32220 | Not Started |  |  | Labor | 2026-03-13 08:00 | 2026-03-13 16:00
ST-POUR | A32200 | Not Started |  |  | Labor | 2026-03-05 08:00 | 2026-03-05 16:00
SUB-ST-REBAR | A32190 | Not Started |  |  | Labor | 2026-03-03 08:00 | 2026-03-04 16:00
ST-DECK | A32180 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-13 08:00 | 2026-03-02 16:00
SUB-ST-SIP | A32170 | Not Started |  |  | Labor | 2026-02-12 08:00 | 2026-02-12 16:00
ST-BEAM | A32160 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-CAP | A31960 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-03 08:00 | 2026-02-05 16:00
ST-COL | A31940 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-23 08:00 | 2026-01-26 16:00
SUB-ST-DRSFT | A31930 | Not Started |  |  | Labor | 2025-12-12 08:00 | 2025-12-16 16:00
EW- ALL EW | A31920 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-11 08:00 | 2025-12-11 16:00
ST-CAP | A31880 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-03 08:00 | 2026-02-06 16:00
ST-COL | A31860 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-23 08:00 | 2026-01-26 16:00
SUB-ST-DRSFT | A31850 | Not Started |  |  | Labor | 2025-12-12 08:00 | 2025-12-16 16:00
EW- ALL EW | A31840 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-11 08:00 | 2025-12-11 16:00
ST-CAP | A31800 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-03 08:00 | 2026-02-06 16:00
ST-COL | A31780 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-23 08:00 | 2026-01-26 16:00
SUB-ST-DRSFT | A31770 | Not Started |  |  | Labor | 2025-12-12 08:00 | 2025-12-16 16:00
EW- ALL EW | A31760 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-11 08:00 | 2025-12-11 16:00
ST-CAP | A31720 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-03 08:00 | 2026-02-05 16:00
ST-COL | A31700 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-23 08:00 | 2026-01-26 16:00
SUB-ST-DRSFT | A31690 | Not Started |  |  | Labor | 2025-12-12 08:00 | 2025-12-16 16:00
EW- ALL EW | A31680 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-11 08:00 | 2025-12-11 16:00
SUB-ASPH | A31650 | Not Started |  |  | Labor | 2026-03-20 08:00 | 2026-03-20 16:00
EW-ABC | A31640 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-03-17 08:00 | 2026-03-19 16:00
PIPE | A31630 | Not Started | Crews.Drainage Crew |  | Labor | 2026-03-13 08:00 | 2026-03-16 16:00
EW-STAB | A31620 | Not Started |  |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
EW-SML | A31610 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-02-26 08:00 | 2026-02-27 16:00
ST-CIP | A31600 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-03 08:00 | 2026-03-09 16:00
SUB-BR-SLIP | A31590 | Not Started |  |  | Labor | 2026-03-10 08:00 | 2026-03-12 16:00
DM-BRIDGE | A31580 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-22 08:00 | 2025-12-22 16:00
DM-BRIDGE | A31570 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-22 08:00 | 2025-12-23 16:00
EW-STR | A31550 | Not Started |  |  | Labor | 2025-12-18 08:00 | 2025-12-18 16:00
ST-ABUT | A31520 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-05 08:00 | 2026-01-06 16:00
ST-PILE | A31510 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-23 08:00 | 2025-12-23 16:00
EW- ALL EW | A31490 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-19 08:00 | 2025-12-19 16:00
EW-STR | A31480 | Not Started |  |  | Labor | 2025-12-18 08:00 | 2025-12-18 16:00
ST-ABUT | A31450 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-06 08:00 | 2026-01-07 16:00
ST-PILE | A31440 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-05 08:00 | 2026-01-05 16:00
EW- ALL EW | A31420 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-19 08:00 | 2025-12-19 16:00
ST-CAP | A31400 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-29 08:00 | 2026-02-02 16:00
ST-COL | A31380 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-20 08:00 | 2026-01-20 16:00
EW-STR | A31370 | Not Started |  |  | Labor | 2025-12-18 08:00 | 2025-12-18 16:00
ST-DECK | A31350 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-27 08:00 | 2026-02-27 16:00
SUB-ST-REBAR | A31340 | Not Started |  |  | Labor | 2026-02-26 08:00 | 2026-02-26 16:00
ST-POUR | A31320 | Not Started |  |  | Labor | 2026-02-17 08:00 | 2026-02-17 16:00
SUB-ST-REBAR | A31310 | Not Started |  |  | Labor | 2026-02-16 08:00 | 2026-02-16 16:00
ST-DECK | A31300 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-10 08:00 | 2026-02-13 16:00
SUB-ST-SIP | A31290 | Not Started |  |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
ST-BEAM | A31280 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-06 08:00 | 2026-02-06 16:00
ST-DECK | A31260 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-04 08:00 | 2026-03-04 16:00
SUB-ST-REBAR | A31250 | Not Started |  |  | Labor | 2026-03-03 08:00 | 2026-03-03 16:00
ST-POUR | A31230 | Not Started |  |  | Labor | 2026-02-23 08:00 | 2026-02-23 16:00
SUB-ST-REBAR | A31220 | Not Started |  |  | Labor | 2026-02-19 08:00 | 2026-02-20 16:00
ST-DECK | A31210 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-12 08:00 | 2026-02-17 16:00
SUB-ST-SIP | A31200 | Not Started |  |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-BEAM | A31190 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
SUB-STRIP | A31180 | Not Started |  |  | Labor | 2026-03-10 08:00 | 2026-03-10 16:00
SUB-ST-GROOVE | A31170 | Not Started |  |  | Labor | 2026-03-06 08:00 | 2026-03-09 16:00
SUB-ST-PARAPET | A31150 | Not Started |  |  | Labor | 2026-03-05 08:00 | 2026-03-05 16:00
ST-APPR | A31140 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-19 08:00 | 2026-02-20 16:00
ST-APPR | A31130 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-20 08:00 | 2026-02-23 16:00
ST-DECK | A31110 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
SUB-ST-REBAR | A31100 | Not Started |  |  | Labor | 2026-02-27 08:00 | 2026-02-27 16:00
ST-POUR | A31080 | Not Started |  |  | Labor | 2026-02-19 08:00 | 2026-02-19 16:00
SUB-ST-REBAR | A31070 | Not Started |  |  | Labor | 2026-02-17 08:00 | 2026-02-17 16:00
ST-DECK | A31060 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-12 08:00 | 2026-02-16 16:00
SUB-ST-SIP | A31050 | Not Started |  |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-BEAM | A31040 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
ST-CAP | A31020 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-03 08:00 | 2026-02-05 16:00
ST-COL | A31000 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-26 08:00 | 2026-01-26 16:00
ST-PILE | A30990 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-19 08:00 | 2026-01-07 16:00
EW-STR | A30980 | Not Started |  |  | Labor | 2025-12-18 08:00 | 2025-12-18 16:00
DM-BRIDGE | A30970 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-18 08:00 | 2025-12-18 16:00
DM-BRIDGE | A30960 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-18 08:00 | 2025-12-19 16:00
EW-STR | A30940 | Not Started |  |  | Labor | 2025-12-11 08:00 | 2025-12-15 16:00
ST-ABUT | A30910 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-22 08:00 | 2026-01-05 16:00
ST-PILE | A30900 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-19 08:00 | 2025-12-19 16:00
EW- ALL EW | A30880 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-16 08:00 | 2025-12-16 16:00
EW-STR | A30870 | Not Started |  |  | Labor | 2025-12-11 08:00 | 2025-12-15 16:00
ST-ABUT | A30840 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-05 08:00 | 2026-01-08 16:00
ST-PILE | A30830 | Not Started | Crews.Structures Crew |  | Labor | 2025-12-22 08:00 | 2025-12-23 16:00
EW- ALL EW | A30810 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-16 08:00 | 2025-12-16 16:00
ST-DECK | A30790 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-13 08:00 | 2026-03-17 16:00
SUB-ST-REBAR | A30780 | Not Started |  |  | Labor | 2026-03-12 08:00 | 2026-03-12 16:00
ST-POUR | A30760 | Not Started |  |  | Labor | 2026-03-03 08:00 | 2026-03-03 16:00
SUB-ST-REBAR | A30750 | Not Started |  |  | Labor | 2026-03-02 08:00 | 2026-03-02 16:00
ST-DECK | A30740 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-13 08:00 | 2026-02-27 16:00
SUB-ST-SIP | A30730 | Not Started |  |  | Labor | 2026-02-12 08:00 | 2026-02-12 16:00
ST-BEAM | A30720 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-DECK | A30700 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-05 08:00 | 2026-03-06 16:00
SUB-ST-REBAR | A30690 | Not Started |  |  | Labor | 2026-03-04 08:00 | 2026-03-04 16:00
ST-POUR | A30670 | Not Started |  |  | Labor | 2026-02-24 08:00 | 2026-02-24 16:00
SUB-ST-REBAR | A30660 | Not Started |  |  | Labor | 2026-02-23 08:00 | 2026-02-23 16:00
ST-DECK | A30650 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-12 08:00 | 2026-02-20 16:00
SUB-ST-SIP | A30640 | Not Started |  |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-BEAM | A30630 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
SUB-STRIP | A30620 | Not Started |  |  | Labor | 2026-03-26 08:00 | 2026-03-26 16:00
SUB-ST-GROOVE | A30610 | Not Started |  |  | Labor | 2026-03-24 08:00 | 2026-03-24 16:00
SUB-ST-PARAPET | A30590 | Not Started |  |  | Labor | 2026-03-20 08:00 | 2026-03-23 16:00
ST-APPR | A30580 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-04 08:00 | 2026-03-05 16:00
ST-APPR | A30570 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-26 08:00 | 2026-02-27 16:00
ST-DECK | A30550 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-05 08:00 | 2026-03-06 16:00
SUB-ST-REBAR | A30540 | Not Started |  |  | Labor | 2026-03-04 08:00 | 2026-03-04 16:00
ST-POUR | A30520 | Not Started |  |  | Labor | 2026-02-24 08:00 | 2026-02-24 16:00
SUB-ST-REBAR | A30510 | Not Started |  |  | Labor | 2026-02-23 08:00 | 2026-02-23 16:00
ST-DECK | A30500 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-12 08:00 | 2026-02-20 16:00
SUB-ST-SIP | A30490 | Not Started |  |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-BEAM | A30480 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
ST-CAP | A30460 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-02 08:00 | 2026-02-05 16:00
ST-COL | A30440 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-23 08:00 | 2026-01-23 16:00
SUB-ST-DRSFT | A30430 | Not Started |  |  | Labor | 2025-12-12 08:00 | 2025-12-16 16:00
EW- ALL EW | A30420 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-12-11 08:00 | 2025-12-11 16:00
SUB-TC-PCB | A30370 | Not Started |  |  | Labor | 2025-10-17 08:00 | 2025-10-17 16:00
TC-Maint. | A30360 | Not Started |  |  | Labor | 2025-10-20 08:00 | 2025-10-20 16:00
ST-FOOT | A30340 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-23 08:00 | 2025-07-11 16:00
ST-PILE | A30330 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-06 08:00 | 2025-06-16 16:00
ST-DECK | A30110 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-07 08:00 | 2025-10-09 16:00
SUB-ST-REBAR | A30100 | Not Started |  |  | Labor | 2025-10-06 08:00 | 2025-10-06 16:00
ST-POUR | A30080 | Not Started |  |  | Labor | 2025-09-26 08:00 | 2025-09-26 16:00
SUB-ST-REBAR | A30070 | Not Started |  |  | Labor | 2025-08-01 08:00 | 2025-08-04 16:00
ST-DECK | A30060 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-24 08:00 | 2025-07-31 16:00
SUB-ST-SIP | A30050 | Not Started |  |  | Labor | 2025-07-22 08:00 | 2025-07-22 16:00
ST-BEAM | A30040 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-21 08:00 | 2025-07-21 16:00
ST-DECK | A30020 | Not Started | Crews.Structures Crew |  | Labor | 2025-10-06 08:00 | 2025-10-07 16:00
SUB-ST-REBAR | A30010 | Not Started |  |  | Labor | 2025-10-03 08:00 | 2025-10-03 16:00
ST-POUR | A29990 | Not Started |  |  | Labor | 2025-09-25 08:00 | 2025-09-25 16:00
SUB-ST-REBAR | A29980 | Not Started |  |  | Labor | 2025-09-23 08:00 | 2025-09-23 16:00
ST-DECK | A29970 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-11 08:00 | 2025-09-22 16:00
SUB-ST-SIP | A29960 | Not Started |  |  | Labor | 2025-09-09 08:00 | 2025-09-09 16:00
ST-BEAM | A29950 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-08 08:00 | 2025-09-08 16:00
ST-DECK | A29930 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-29 08:00 | 2025-09-29 16:00
SUB-ST-REBAR | A29920 | Not Started |  |  | Labor | 2025-09-26 08:00 | 2025-09-26 16:00
ST-POUR | A29900 | Not Started |  |  | Labor | 2025-09-18 08:00 | 2025-09-18 16:00
SUB-ST-REBAR | A29890 | Not Started |  |  | Labor | 2025-09-15 08:00 | 2025-09-16 16:00
ST-DECK | A29880 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-11 08:00 | 2025-09-12 16:00
SUB-ST-SIP | A29870 | Not Started |  |  | Labor | 2025-09-09 08:00 | 2025-09-09 16:00
ST-BEAM | A29860 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-08 08:00 | 2025-09-08 16:00
ST-FOOT | A29680 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-12 08:00 | 2025-06-16 16:00
ST-CAP | A29660 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-07 08:00 | 2025-07-15 16:00
ST-COL | A29640 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-24 08:00 | 2025-06-27 16:00
ST-PILE | A29630 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-06 08:00 | 2025-06-10 16:00
EW- ALL EW | A29620 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-05 08:00 | 2025-06-05 16:00
ST-FOOT | A29600 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-25 08:00 | 2025-08-01 16:00
ST-CAP | A29580 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-21 08:00 | 2025-09-02 16:00
ST-COL | A29560 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-11 08:00 | 2025-08-12 16:00
ST-PILE | A29550 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-05 08:00 | 2025-06-09 16:00
EW-STR | A29540 | Not Started |  |  | Labor | 2025-06-04 08:00 | 2025-06-04 16:00
ST-CAP | A29500 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-15 08:00 | 2025-08-25 16:00
ST-COL | A29480 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-06 08:00 | 2025-08-07 16:00
SUB-ST-DRSFT | A29470 | Not Started |  |  | Labor | 2025-07-15 08:00 | 2025-07-24 16:00
EW-STR | A29460 | Not Started |  |  | Labor | 2025-07-11 08:00 | 2025-07-14 16:00
ST-FOOT | A29440 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-17 08:00 | 2025-07-21 16:00
ST-CAP | A29420 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-08 08:00 | 2025-08-19 16:00
ST-COL | A29400 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-29 08:00 | 2025-07-31 16:00
ST-PILE | A29390 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-11 08:00 | 2025-07-15 16:00
EW- ALL EW | A29380 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-07-10 08:00 | 2025-07-10 16:00
SUB-ASPH | A29320 | Not Started |  |  | Labor | 2025-10-06 08:00 | 2025-10-06 16:00
EW-ABC | A29310 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-02 08:00 | 2025-10-03 16:00
PIPE | A29300 | Not Started | Crews.Drainage Crew |  | Labor | 2025-09-30 08:00 | 2025-10-01 16:00
EW-STAB | A29270 | Not Started |  |  | Labor | 2025-09-22 08:00 | 2025-09-23 16:00
EW-SML | A29260 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-09-18 08:00 | 2025-09-19 16:00
ST-CIP | A29250 | Not Started | Crews.Wall Crew |  | Labor | 2025-09-25 08:00 | 2025-09-26 16:00
SUB-BR-SLIP | A29240 | Not Started |  |  | Labor | 2025-09-29 08:00 | 2025-09-29 16:00
DM-BRIDGE | A29180 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-06 08:00 | 2025-06-06 16:00
DM-BRIDGE | A29170 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-06 08:00 | 2025-06-06 16:00
DM-BRIDGE | A29160 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-04 08:00 | 2025-06-06 16:00
EW-STR | A29150 | Not Started |  |  | Labor | 2025-06-04 08:00 | 2025-06-04 16:00
ST-ABUT | A29120 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-12 08:00 | 2025-06-13 16:00
ST-PILE | A29110 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-09 08:00 | 2025-06-10 16:00
EW- ALL EW | A29090 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-05 08:00 | 2025-06-05 16:00
EW-STR | A29080 | Not Started |  |  | Labor | 2025-06-04 08:00 | 2025-06-04 16:00
ST-ABUT | A29050 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-12 08:00 | 2025-06-13 16:00
ST-PILE | A29040 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-09 08:00 | 2025-06-10 16:00
EW- ALL EW | A29020 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-05 08:00 | 2025-06-05 16:00
ST-CAP | A29000 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-01 08:00 | 2025-08-11 16:00
ST-COL | A28980 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-21 08:00 | 2025-07-24 16:00
EW-STR | A28960 | Not Started |  |  | Labor | 2025-06-04 08:00 | 2025-06-05 16:00
ST-DECK | A28940 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-04 08:00 | 2025-09-04 16:00
SUB-ST-REBAR | A28930 | Not Started |  |  | Labor | 2025-09-03 08:00 | 2025-09-03 16:00
ST-POUR | A28910 | Not Started |  |  | Labor | 2025-08-26 08:00 | 2025-08-26 16:00
SUB-ST-REBAR | A28900 | Not Started |  |  | Labor | 2025-08-25 08:00 | 2025-08-25 16:00
ST-DECK | A28890 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-19 08:00 | 2025-08-22 16:00
SUB-ST-SIP | A28880 | Not Started |  |  | Labor | 2025-08-18 08:00 | 2025-08-18 16:00
ST-BEAM | A28870 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-15 08:00 | 2025-08-15 16:00
ST-DECK | A28850 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-12 08:00 | 2025-09-12 16:00
SUB-ST-REBAR | A28840 | Not Started |  |  | Labor | 2025-09-11 08:00 | 2025-09-11 16:00
ST-POUR | A28820 | Not Started |  |  | Labor | 2025-09-02 08:00 | 2025-09-02 16:00
SUB-ST-REBAR | A28810 | Not Started |  |  | Labor | 2025-08-26 08:00 | 2025-08-28 16:00
ST-DECK | A28800 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-19 08:00 | 2025-08-25 16:00
SUB-ST-SIP | A28790 | Not Started |  |  | Labor | 2025-08-18 08:00 | 2025-08-18 16:00
ST-BEAM | A28780 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-15 08:00 | 2025-08-15 16:00
SUB-STRIP | A28770 | Not Started |  |  | Labor | 2025-09-19 08:00 | 2025-09-19 16:00
SUB-ST-GROOVE | A28760 | Not Started |  |  | Labor | 2025-09-16 08:00 | 2025-09-18 16:00
SUB-ST-PARAPET | A28740 | Not Started |  |  | Labor | 2025-09-15 08:00 | 2025-09-15 16:00
ST-APPR | A28730 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-28 08:00 | 2025-09-03 16:00
ST-APPR | A28720 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-28 08:00 | 2025-09-03 16:00
ST-DECK | A28700 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-04 08:00 | 2025-09-04 16:00
SUB-ST-REBAR | A28690 | Not Started |  |  | Labor | 2025-09-03 08:00 | 2025-09-03 16:00
ST-POUR | A28670 | Not Started |  |  | Labor | 2025-08-26 08:00 | 2025-08-26 16:00
SUB-ST-REBAR | A28660 | Not Started |  |  | Labor | 2025-08-25 08:00 | 2025-08-25 16:00
ST-DECK | A28650 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-19 08:00 | 2025-08-22 16:00
SUB-ST-SIP | A28640 | Not Started |  |  | Labor | 2025-08-18 08:00 | 2025-08-18 16:00
ST-BEAM | A28630 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-15 08:00 | 2025-08-15 16:00
ST-CAP | A28610 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-01 08:00 | 2025-08-11 16:00
ST-COL | A28590 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-21 08:00 | 2025-07-24 16:00
ST-PILE | A28580 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-12 08:00 | 2025-06-20 16:00
EW-STR | A28570 | Not Started |  |  | Labor | 2025-06-09 08:00 | 2025-06-10 16:00
DM-BRIDGE | A28510 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-10 08:00 | 2025-06-12 16:00
DM-BRIDGE | A28500 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-10 08:00 | 2025-06-13 16:00
DM-BRIDGE | A28490 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-04 08:00 | 2025-06-09 16:00
EW-STR | A28480 | Not Started |  |  | Labor | 2025-06-04 08:00 | 2025-06-06 16:00
ST-ABUT | A28450 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-19 08:00 | 2025-06-24 16:00
ST-PILE | A28440 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-13 08:00 | 2025-06-17 16:00
EW- ALL EW | A28420 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-09 08:00 | 2025-06-09 16:00
EW-STR | A28410 | Not Started |  |  | Labor | 2025-06-04 08:00 | 2025-06-06 16:00
ST-ABUT | A28380 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-19 08:00 | 2025-06-27 16:00
ST-PILE | A28370 | Not Started | Crews.Structures Crew |  | Labor | 2025-06-16 08:00 | 2025-06-17 16:00
EW- ALL EW | A28350 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-09 08:00 | 2025-06-09 16:00
ST-DECK | A28270 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-29 08:00 | 2025-09-30 16:00
SUB-ST-REBAR | A28260 | Not Started |  |  | Labor | 2025-09-25 08:00 | 2025-09-26 16:00
ST-POUR | A28240 | Not Started |  |  | Labor | 2025-09-16 08:00 | 2025-09-16 16:00
SUB-ST-REBAR | A28230 | Not Started |  |  | Labor | 2025-09-15 08:00 | 2025-09-15 16:00
ST-DECK | A28220 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-04 08:00 | 2025-09-12 16:00
SUB-ST-SIP | A28210 | Not Started |  |  | Labor | 2025-09-03 08:00 | 2025-09-03 16:00
ST-BEAM | A28200 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-02 08:00 | 2025-09-02 16:00
ST-DECK | A28180 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-25 08:00 | 2025-09-26 16:00
SUB-ST-REBAR | A28170 | Not Started |  |  | Labor | 2025-09-23 08:00 | 2025-09-23 16:00
ST-POUR | A28150 | Not Started |  |  | Labor | 2025-09-15 08:00 | 2025-09-15 16:00
SUB-ST-REBAR | A28140 | Not Started |  |  | Labor | 2025-09-11 08:00 | 2025-09-12 16:00
ST-DECK | A28130 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-28 08:00 | 2025-09-09 16:00
SUB-ST-SIP | A28120 | Not Started |  |  | Labor | 2025-08-26 08:00 | 2025-08-26 16:00
ST-BEAM | A28110 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-25 08:00 | 2025-08-25 16:00
SUB-STRIP | A28100 | Not Started |  |  | Labor | 2025-10-16 08:00 | 2025-10-16 16:00
SUB-ST-GROOVE | A28090 | Not Started |  |  | Labor | 2025-10-14 08:00 | 2025-10-14 16:00
SUB-ST-PARAPET | A28070 | Not Started |  |  | Labor | 2025-10-10 08:00 | 2025-10-13 16:00
ST-APPR | A28060 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-18 08:00 | 2025-09-22 16:00
ST-APPR | A28050 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-08 08:00 | 2025-09-11 16:00
ST-DECK | A28030 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-16 08:00 | 2025-09-18 16:00
SUB-ST-REBAR | A28020 | Not Started |  |  | Labor | 2025-09-15 08:00 | 2025-09-15 16:00
ST-POUR | A28000 | Not Started |  |  | Labor | 2025-09-05 08:00 | 2025-09-05 16:00
SUB-ST-REBAR | A27990 | Not Started |  |  | Labor | 2025-09-03 08:00 | 2025-09-04 16:00
ST-DECK | A27980 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-21 08:00 | 2025-09-02 16:00
SUB-ST-SIP | A27970 | Not Started |  |  | Labor | 2025-08-19 08:00 | 2025-08-19 16:00
ST-BEAM | A27960 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-18 08:00 | 2025-08-18 16:00
ST-CAP | A27940 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-04 08:00 | 2025-08-12 16:00
ST-COL | A27920 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-24 08:00 | 2025-07-25 16:00
SUB-ST-DRSFT | A27910 | Not Started |  |  | Labor | 2025-06-16 08:00 | 2025-07-10 16:00
EW-STR | A27900 | Not Started |  |  | Labor | 2025-06-13 08:00 | 2025-06-13 16:00
SUB-TC-PCB | A27890 | Not Started |  |  | Labor | 2025-05-29 08:00 | 2025-06-03 16:00
TC-Maint. | A27880 | Not Started |  |  | Labor | 2025-05-28 08:00 | 2025-05-28 16:00
SUB-TC-PCB | A27870 | Not Started |  |  | Labor | 2025-05-27 08:00 | 2025-05-27 16:00
TC-Maint. | A27860 | Not Started |  |  | Labor | 2025-05-23 08:00 | 2025-05-23 16:00
TC-Maint. | A27840 | Not Started |  |  | Labor | 2025-05-22 08:00 | 2025-05-22 16:00
SUB-TC-PCB | A27650 | Not Started |  |  | Labor | 2025-04-08 08:00 | 2025-04-08 16:00
TC-Maint. | A27640 | Not Started |  |  | Labor | 2025-04-07 08:00 | 2025-04-07 16:00
SUB-GRAIL | A27630 | Not Started |  |  | Labor | 2025-04-22 08:00 | 2025-04-24 16:00
EW-ABC | A27620 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-05-19 08:00 | 2025-05-20 16:00
SUB-ASPH | A27550 | Not Started |  |  | Labor | 2025-05-21 08:00 | 2025-05-21 16:00
EW-STAB | A27540 | Not Started |  |  | Labor | 2025-05-15 08:00 | 2025-05-16 16:00
EW-SML | A27530 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-04-07 08:00 | 2025-04-14 16:00
EW-STR | A27500 | Not Started |  |  | Labor | 2025-04-15 08:00 | 2025-05-13 16:00
SUB-TC-PCB | A27490 | Not Started |  |  | Labor | 2025-03-28 08:00 | 2025-04-04 16:00
EW-ABC | A27470 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-07-02 08:00 | 2025-07-18 16:00
SUB-ASPH | A27480 | Not Started |  |  | Labor | 2025-07-21 08:00 | 2025-07-21 16:00
EW-STAB | A27460 | Not Started |  |  | Labor | 2025-06-23 08:00 | 2025-07-01 16:00
EW- ALL EW | A27450 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-20 08:00 | 2025-06-20 16:00
EW-ABC | A27430 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-03-04 08:00 | 2025-03-14 16:00
SUB-ASPH | A27440 | Not Started |  |  | Labor | 2025-03-17 08:00 | 2025-03-17 16:00
EW-STAB | A27420 | Not Started |  |  | Labor | 2025-02-20 08:00 | 2025-03-03 16:00
EW- ALL EW | A27410 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-02-18 08:00 | 2025-02-18 16:00
PIPE | A27350 | Not Started | Crews.Drainage Crew |  | Labor | 2025-04-10 08:00 | 2025-05-08 16:00
SUB-ASPH | A27400 | Not Started |  |  | Labor | 2025-05-20 08:00 | 2025-05-20 16:00
FLATWORK | A27380 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2025-05-13 08:00 | 2025-05-16 16:00
EW-ABC | A27370 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-05-12 08:00 | 2025-05-12 16:00
EW-STAB | A27360 | Not Started |  |  | Labor | 2025-05-09 08:00 | 2025-05-09 16:00
EW- ALL EW | A27340 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-04-09 08:00 | 2025-04-09 16:00
FLATWORK | A27390 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2025-05-19 08:00 | 2025-05-19 16:00
PIPE | A27280 | Not Started | Crews.Drainage Crew |  | Labor | 2025-05-09 08:00 | 2025-06-05 16:00
SUB-ASPH | A27330 | Not Started |  |  | Labor | 2025-06-20 08:00 | 2025-06-20 16:00
FLATWORK | A27310 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2025-06-19 08:00 | 2025-06-19 16:00
EW-ABC | A27300 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-16 08:00 | 2025-06-17 16:00
EW-STAB | A27290 | Not Started |  |  | Labor | 2025-06-06 08:00 | 2025-06-13 16:00
EW- ALL EW | A27270 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-05-08 08:00 | 2025-05-08 16:00
SUB-ASPH | A27250 | Not Started |  |  | Labor | 2025-06-13 08:00 | 2025-06-13 16:00
EW-ABC | A27240 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-12 08:00 | 2025-06-12 16:00
PIPE | A27230 | Not Started | Crews.Drainage Crew |  | Labor | 2025-06-06 08:00 | 2025-06-10 16:00
CP-SLIP | A27220 | Not Started | Crews.Paving Crew |  | Labor | 2025-05-06 08:00 | 2025-05-22 16:00
SUB-ASPH | A27210 | Not Started |  |  | Labor | 2025-05-05 08:00 | 2025-05-05 16:00
EW-STAB | A27200 | Not Started |  |  | Labor | 2025-04-29 08:00 | 2025-04-29 16:00
EW-SML | A27190 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-20 08:00 | 2024-08-20 16:00
SUB-BR-SLIP | A27170 | Not Started |  |  | Labor | 2025-04-30 08:00 | 2025-05-02 16:00
SUB-BR-SLIP | A27150 | Not Started |  |  | Labor | 2025-05-08 08:00 | 2025-06-13 16:00
SUB-ASPH | A27140 | Not Started |  |  | Labor | 2025-07-29 08:00 | 2025-07-29 16:00
EW-ABC | A27130 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-07-28 08:00 | 2025-07-28 16:00
PIPE | A27120 | Not Started | Crews.Drainage Crew |  | Labor | 2025-07-21 08:00 | 2025-07-25 16:00
CP-SLIP | A27110 | Not Started | Crews.Paving Crew |  | Labor | 2025-06-20 08:00 | 2025-07-18 16:00
SUB-ASPH | A27100 | Not Started |  |  | Labor | 2025-06-19 08:00 | 2025-06-19 16:00
EW-STAB | A27090 | Not Started |  |  | Labor | 2025-06-16 08:00 | 2025-06-17 16:00
EW-SML | A27080 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-03-24 08:00 | 2025-05-06 16:00
PIPE | A27030 | Not Started | Crews.Drainage Crew |  | Labor | 2024-06-07 08:00 | 2024-07-08 16:00
PIPE | A27020 | Not Started | Crews.Drainage Crew |  | Labor | 2024-06-14 08:00 | 2024-07-12 16:00
PIPE | A27010 | Not Started | Crews.Drainage Crew |  | Labor | 2024-06-07 08:00 | 2024-07-08 16:00
PIPE | A27000 | Not Started | Crews.Drainage Crew |  | Labor | 2024-06-07 08:00 | 2024-07-08 16:00
PIPE | A26990 | Not Started | Crews.Drainage Crew |  | Labor | 2024-06-14 08:00 | 2024-07-12 16:00
TC-Maint. | A26850 | Not Started |  |  | Labor | 2025-03-27 08:00 | 2025-03-27 16:00
SUB-ASPH | A26830 | Not Started |  |  | Labor | 2025-04-21 08:00 | 2025-04-21 16:00
EW-ABC | A26820 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-04-18 08:00 | 2025-04-18 16:00
PIPE | A26810 | Not Started | Crews.Drainage Crew |  | Labor | 2025-04-17 08:00 | 2025-04-17 16:00
CP-SLIP | A26800 | Not Started | Crews.Paving Crew |  | Labor | 2025-04-14 08:00 | 2025-04-15 16:00
SUB-ASPH | A26790 | Not Started |  |  | Labor | 2025-04-11 08:00 | 2025-04-11 16:00
EW-STAB | A26780 | Not Started |  |  | Labor | 2025-04-10 08:00 | 2025-04-10 16:00
EW-SML | A26770 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-04-07 08:00 | 2025-04-09 16:00
EW-STR | A26730 | Not Started |  |  | Labor | 2024-11-07 08:00 | 2024-12-02 16:00
DM-BRIDGE | A26710 | Not Started | Crews.Demolition Crew |  | Labor | 2024-12-17 08:00 | 2025-01-06 16:00
DM-BRIDGE | A26700 | Not Started | Crews.Demolition Crew |  | Labor | 2024-08-20 08:00 | 2024-08-29 16:00
DM-BRIDGE | A26690 | Not Started | Crews.Demolition Crew |  | Labor | 2024-07-18 08:00 | 2024-08-06 16:00
DM-BRIDGE | A26680 | Not Started | Crews.Demolition Crew |  | Labor | 2024-07-02 08:00 | 2024-07-16 16:00
ST-DECK | A26560 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-15 08:00 | 2024-10-21 16:00
SUB-ST-REBAR | A26550 | Not Started |  |  | Labor | 2024-10-10 08:00 | 2024-10-14 16:00
ST-POUR | A26530 | Not Started |  |  | Labor | 2024-10-02 08:00 | 2024-10-02 16:00
SUB-ST-REBAR | A26520 | Not Started |  |  | Labor | 2024-09-24 08:00 | 2024-10-01 16:00
ST-DECK | A26510 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-23 08:00 | 2024-09-23 16:00
SUB-ST-SIP | A26500 | Not Started |  |  | Labor | 2024-08-20 08:00 | 2024-08-22 16:00
ST-BEAM | A26490 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-19 08:00 | 2024-08-19 16:00
ST-CAP | A26470 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-01 08:00 | 2024-08-13 16:00
ST-COL | A26450 | Not Started | Crews.Structures Crew |  | Labor | 2024-07-18 08:00 | 2024-07-23 16:00
ST-FOOT | A26430 | Not Started | Crews.Structures Crew |  | Labor | 2024-07-01 08:00 | 2024-07-09 16:00
ST-PILE | A26420 | Not Started | Crews.Structures Crew |  | Labor | 2024-06-20 08:00 | 2024-06-28 16:00
EW-STR | A26400 | Not Started |  |  | Labor | 2024-05-30 08:00 | 2024-05-30 16:00
TC-Maint. | A26390 | Not Started |  |  | Labor | 2024-06-14 08:00 | 2024-06-14 16:00
SUB-TC-PCB | A26380 | Not Started |  |  | Labor | 2024-06-03 08:00 | 2024-06-06 16:00
SUB-TC-PCB | A26360 | Not Started |  |  | Labor | 2024-06-11 08:00 | 2024-06-11 16:00
SUB-ASPH | A26330 | Not Started |  |  | Labor | 2025-01-16 08:00 | 2025-01-16 16:00
EW-ABC | A26320 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-01-14 08:00 | 2025-01-14 16:00
PIPE | A26310 | Not Started | Crews.Drainage Crew |  | Labor | 2025-01-10 08:00 | 2025-01-13 16:00
CP-SLIP | A26300 | Not Started | Crews.Paving Crew |  | Labor | 2024-12-23 08:00 | 2025-01-09 16:00
SUB-ASPH | A26290 | Not Started |  |  | Labor | 2024-12-20 08:00 | 2024-12-20 16:00
EW-STAB | A26280 | Not Started |  |  | Labor | 2024-10-22 08:00 | 2024-10-22 16:00
EW-SML | A26270 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-09-06 08:00 | 2024-09-12 16:00
ST-CIP | A26260 | Not Started | Crews.Wall Crew |  | Labor | 2024-10-23 08:00 | 2024-11-14 16:00
SUB-BR-SLIP | A26250 | Not Started |  |  | Labor | 2024-11-15 08:00 | 2024-12-19 16:00
ST-MSE | A26240 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-13 08:00 | 2024-10-21 16:00
SUB-ASPH | A26220 | Not Started |  |  | Labor | 2025-03-26 08:00 | 2025-03-26 16:00
EW-ABC | A26210 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-03-24 08:00 | 2025-03-25 16:00
PIPE | A26200 | Not Started | Crews.Drainage Crew |  | Labor | 2025-03-18 08:00 | 2025-03-21 16:00
CP-SLIP | A26190 | Not Started | Crews.Paving Crew |  | Labor | 2025-03-06 08:00 | 2025-03-17 16:00
SUB-ASPH | A26180 | Not Started |  |  | Labor | 2025-03-04 08:00 | 2025-03-04 16:00
EW-STAB | A26170 | Not Started |  |  | Labor | 2024-12-16 08:00 | 2024-12-17 16:00
EW-SML | A26160 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-09-30 08:00 | 2024-10-31 16:00
ST-CIP | A26150 | Not Started | Crews.Wall Crew |  | Labor | 2024-12-19 08:00 | 2025-01-28 16:00
SUB-BR-SLIP | A26140 | Not Started |  |  | Labor | 2025-01-30 08:00 | 2025-03-03 16:00
ST-MSE | A26130 | Not Started | Crews.Wall Crew |  | Labor | 2024-10-03 08:00 | 2024-11-06 16:00
SUB-ASPH | A26110 | Not Started |  |  | Labor | 2025-01-30 08:00 | 2025-01-30 16:00
EW-ABC | A26100 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-01-27 08:00 | 2025-01-28 16:00
PIPE | A26090 | Not Started | Crews.Drainage Crew |  | Labor | 2025-01-23 08:00 | 2025-01-24 16:00
CP-SLIP | A26080 | Not Started | Crews.Paving Crew |  | Labor | 2024-12-19 08:00 | 2025-01-21 16:00
SUB-ASPH | A26070 | Not Started |  |  | Labor | 2024-12-17 08:00 | 2024-12-17 16:00
EW-STAB | A26060 | Not Started |  |  | Labor | 2024-10-31 08:00 | 2024-11-01 16:00
EW-SML | A26050 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-06-05 08:00 | 2024-07-09 16:00
ST-CIP | A26040 | Not Started | Crews.Wall Crew |  | Labor | 2024-11-04 08:00 | 2024-11-12 16:00
SUB-BR-SLIP | A26030 | Not Started |  |  | Labor | 2024-11-14 08:00 | 2024-12-16 16:00
ST-MSE | A26020 | Not Started | Crews.Wall Crew |  | Labor | 2024-07-10 08:00 | 2024-08-19 16:00
SUB-ASPH | A26010 | Not Started |  |  | Labor | 2024-11-22 08:00 | 2024-11-22 16:00
EW-ABC | A26000 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-11-19 08:00 | 2024-11-21 16:00
PIPE | A25990 | Not Started | Crews.Drainage Crew |  | Labor | 2024-11-15 08:00 | 2024-11-18 16:00
CP-SLIP | A25980 | Not Started | Crews.Paving Crew |  | Labor | 2024-10-25 08:00 | 2024-11-14 16:00
SUB-ASPH | A25970 | Not Started |  |  | Labor | 2024-10-24 08:00 | 2024-10-24 16:00
EW-STAB | A25960 | Not Started |  |  | Labor | 2024-09-12 08:00 | 2024-09-13 16:00
EW-SML | A25950 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-07-19 08:00 | 2024-08-02 16:00
ST-CIP | A25940 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-16 08:00 | 2024-10-02 16:00
SUB-BR-SLIP | A25930 | Not Started |  |  | Labor | 2024-10-03 08:00 | 2024-10-23 16:00
ST-MSE | A25920 | Not Started | Crews.Wall Crew |  | Labor | 2024-08-05 08:00 | 2024-09-10 16:00
EW-STR | A25900 | Not Started |  |  | Labor | 2024-05-30 08:00 | 2024-06-03 16:00
EW-STR | A25890 | Not Started |  |  | Labor | 2024-08-22 08:00 | 2024-09-05 16:00
ST-MSE | A25600 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-17 08:00 | 2024-09-23 16:00
ST-ABUT | A25580 | Not Started | Crews.Structures Crew |  | Labor | 2024-09-24 08:00 | 2024-10-08 16:00
ST-PILE | A25570 | Not Started | Crews.Structures Crew |  | Labor | 2024-09-09 08:00 | 2024-09-16 16:00
EW- ALL EW | A25550 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-09-06 08:00 | 2024-09-06 16:00
SUB-STRIP | A25540 | Not Started |  |  | Labor | 2024-12-16 08:00 | 2024-12-16 16:00
SUB-ST-GROOVE | A25530 | Not Started |  |  | Labor | 2024-12-13 08:00 | 2024-12-13 16:00
SUB-DGRIND | A25520 | Not Started |  |  | Labor | 2024-12-12 08:00 | 2024-12-12 16:00
SUB-ST-PARAPET | A25510 | Not Started |  |  | Labor | 2024-12-10 08:00 | 2024-12-10 16:00
ST-APPR | A25500 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-22 08:00 | 2024-12-06 16:00
ST-APPR | A25490 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-22 08:00 | 2024-12-05 16:00
ST-DECK | A25470 | Not Started | Crews.Structures Crew |  | Labor | 2024-12-05 08:00 | 2024-12-09 16:00
SUB-ST-REBAR | A25460 | Not Started |  |  | Labor | 2024-12-02 08:00 | 2024-12-03 16:00
ST-POUR | A25440 | Not Started |  |  | Labor | 2024-11-21 08:00 | 2024-11-21 16:00
SUB-ST-REBAR | A25430 | Not Started |  |  | Labor | 2024-11-08 08:00 | 2024-11-19 16:00
ST-DECK | A25420 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-22 08:00 | 2024-11-07 16:00
SUB-ST-SIP | A25410 | Not Started |  |  | Labor | 2024-10-17 08:00 | 2024-10-21 16:00
ST-BEAM | A25400 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-14 08:00 | 2024-10-15 16:00
EW-STR | A25290 | Not Started |  |  | Labor | 2024-08-07 08:00 | 2024-08-19 16:00
ST-MSE | A25280 | Not Started | Crews.Wall Crew |  | Labor | 2024-09-03 08:00 | 2024-09-12 16:00
ST-ABUT | A25260 | Not Started | Crews.Structures Crew |  | Labor | 2024-09-13 08:00 | 2024-09-26 16:00
ST-PILE | A25250 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-22 08:00 | 2024-08-29 16:00
EW- ALL EW | A25230 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-20 08:00 | 2024-08-20 16:00
SUB-ASPH | A25220 | Not Started |  |  | Labor | 2025-11-05 08:00 | 2025-11-05 16:00
EW-ABC | A25210 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-11-04 08:00 | 2025-11-04 16:00
PIPE | A25200 | Not Started | Crews.Drainage Crew |  | Labor | 2025-11-03 08:00 | 2025-11-03 16:00
ST-DECK | A25180 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-18 08:00 | 2024-10-23 16:00
SUB-ST-REBAR | A25170 | Not Started |  |  | Labor | 2024-10-14 08:00 | 2024-10-17 16:00
ST-POUR | A25150 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-04 16:00
SUB-ST-REBAR | A25140 | Not Started |  |  | Labor | 2024-09-27 08:00 | 2024-10-03 16:00
ST-DECK | A25130 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-26 08:00 | 2024-09-26 16:00
SUB-ST-SIP | A25120 | Not Started |  |  | Labor | 2024-08-20 08:00 | 2024-08-23 16:00
ST-BEAM | A25110 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-19 08:00 | 2024-08-19 16:00
ST-DECK | A25090 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-07 08:00 | 2024-10-11 16:00
SUB-ST-REBAR | A25080 | Not Started |  |  | Labor | 2024-10-02 08:00 | 2024-10-04 16:00
ST-POUR | A25060 | Not Started |  |  | Labor | 2024-09-24 08:00 | 2024-09-24 16:00
SUB-ST-REBAR | A25050 | Not Started |  |  | Labor | 2024-09-16 08:00 | 2024-09-23 16:00
ST-DECK | A25040 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-15 08:00 | 2024-09-13 16:00
SUB-ST-SIP | A25030 | Not Started |  |  | Labor | 2024-08-12 08:00 | 2024-08-13 16:00
ST-BEAM | A25020 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-09 08:00 | 2024-08-09 16:00
ST-CAP | A25000 | Not Started | Crews.Structures Crew |  | Labor | 2024-07-05 08:00 | 2024-08-05 16:00
ST-COL | A24980 | Not Started | Crews.Structures Crew |  | Labor | 2024-06-20 08:00 | 2024-06-27 16:00
SUB-ST-DRSFT | A24950 | Not Started |  |  | Labor | 2024-05-31 08:00 | 2024-06-18 16:00
EW-STR | A24930 | Not Started |  |  | Labor | 2024-05-30 08:00 | 2024-05-30 16:00
ST-MSE | A24910 | Not Started | Crews.Wall Crew |  | Labor | 2024-07-09 08:00 | 2024-07-22 16:00
ST-ABUT | A24890 | Not Started | Crews.Structures Crew |  | Labor | 2024-07-23 08:00 | 2024-08-01 16:00
ST-PILE | A24880 | Not Started | Crews.Structures Crew |  | Labor | 2024-06-05 08:00 | 2024-06-05 16:00
EW- ALL EW | A24860 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-06-04 08:00 | 2024-06-04 16:00
CP-SLIP | A24850 | Not Started | Crews.Paving Crew |  | Labor | 2025-10-28 08:00 | 2025-10-31 16:00
SUB-ASPH | A24840 | Not Started |  |  | Labor | 2025-10-27 08:00 | 2025-10-27 16:00
EW-STAB | A24830 | Not Started |  |  | Labor | 2025-10-24 08:00 | 2025-10-24 16:00
EW-SML | A24820 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-21 08:00 | 2025-10-23 16:00
SUB-STRIP | A24780 | Not Started |  |  | Labor | 2024-11-04 08:00 | 2024-11-04 16:00
SUB-ST-GROOVE | A24770 | Not Started |  |  | Labor | 2024-10-30 08:00 | 2024-11-01 16:00
SUB-ST-PARAPET | A24750 | Not Started |  |  | Labor | 2024-10-24 08:00 | 2024-10-29 16:00
ST-APPR | A24740 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-07 08:00 | 2024-10-23 16:00
ST-APPR | A24730 | Not Started | Crews.Structures Crew |  | Labor | 2024-09-05 08:00 | 2024-09-26 16:00
ST-DECK | A24710 | Not Started | Crews.Structures Crew |  | Labor | 2024-09-16 08:00 | 2024-09-19 16:00
SUB-ST-REBAR | A24700 | Not Started |  |  | Labor | 2024-09-12 08:00 | 2024-09-13 16:00
ST-POUR | A24680 | Not Started |  |  | Labor | 2024-09-04 08:00 | 2024-09-04 16:00
SUB-ST-REBAR | A24670 | Not Started |  |  | Labor | 2024-08-26 08:00 | 2024-09-03 16:00
ST-DECK | A24660 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-08 08:00 | 2024-08-23 16:00
SUB-ST-SIP | A24650 | Not Started |  |  | Labor | 2024-08-06 08:00 | 2024-08-07 16:00
ST-BEAM | A24640 | Not Started | Crews.Structures Crew |  | Labor | 2024-08-05 08:00 | 2024-08-05 16:00
ST-CAP | A24620 | Not Started | Crews.Structures Crew |  | Labor | 2024-07-02 08:00 | 2024-08-01 16:00
ST-COL | A24600 | Not Started | Crews.Structures Crew |  | Labor | 2024-06-20 08:00 | 2024-06-24 16:00
SUB-ST-DRSFT | A24570 | Not Started |  |  | Labor | 2024-05-31 08:00 | 2024-06-18 16:00
EW-STR | A24550 | Not Started |  |  | Labor | 2024-05-30 08:00 | 2024-05-30 16:00
EW-STR | A24530 | Not Started |  |  | Labor | 2024-05-30 08:00 | 2024-06-03 16:00
ST-MSE | A24520 | Not Started | Crews.Wall Crew |  | Labor | 2024-07-11 08:00 | 2024-07-18 16:00
ST-ABUT | A24500 | Not Started | Crews.Structures Crew |  | Labor | 2024-07-19 08:00 | 2024-07-30 16:00
SUB-ST-DRSFT | A24490 | Not Started |  |  | Labor | 2024-06-05 08:00 | 2024-06-24 16:00
EW- ALL EW | A24470 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-06-04 08:00 | 2024-06-04 16:00
SUB-STRIP | A24400 | Not Started |  |  | Labor | 2024-06-20 08:00 | 2024-06-20 16:00
SUB-ASPH | A24390 | Not Started |  |  | Labor | 2024-06-17 08:00 | 2024-06-18 16:00
SUB-TC-PCB | A24360 | Not Started |  |  | Labor | 2024-06-24 08:00 | 2024-07-01 16:00
TC-Maint. | A24350 | Not Started |  |  | Labor | 2024-06-21 08:00 | 2024-06-21 16:00
SUB-ASPH | A24290 | Not Started |  |  | Labor | 2024-06-10 08:00 | 2024-06-10 16:00
EW-ABC | A24280 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-06-07 08:00 | 2024-06-07 16:00
TC-Maint. | A24230 | Not Started |  |  | Labor | 2024-06-13 08:00 | 2024-06-13 16:00
TC-Maint. | A24180 | Not Started |  |  | Labor | 2024-05-31 08:00 | 2024-05-31 16:00
TC-Maint. | A24170 | Not Started |  |  | Labor | 2024-05-30 08:00 | 2024-05-30 16:00
PIPE | A24160 | Not Started | Crews.Drainage Crew |  | Labor | 2024-08-29 08:00 | 2024-09-30 16:00
SUB-ASPH | A24150 | Not Started |  |  | Labor | 2024-10-18 08:00 | 2024-10-18 16:00
FLATWORK | A24130 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-10-04 08:00 | 2024-10-08 16:00
EW-ABC | A24120 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-10-03 08:00 | 2024-10-03 16:00
EW-STAB | A24110 | Not Started |  |  | Labor | 2024-10-01 08:00 | 2024-10-02 16:00
EW- ALL EW | A24100 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-27 08:00 | 2024-08-27 16:00
FLATWORK | A24140 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-10-10 08:00 | 2024-10-17 16:00
SUB-ASPH | A24090 | Not Started |  |  | Labor | 2025-06-10 08:00 | 2025-06-10 16:00
EW-ABC | A24080 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-06-06 08:00 | 2025-06-09 16:00
PIPE | A24070 | Not Started | Crews.Drainage Crew |  | Labor | 2025-06-04 08:00 | 2025-06-05 16:00
CP-SLIP | A24060 | Not Started | Crews.Paving Crew |  | Labor | 2025-05-19 08:00 | 2025-06-03 16:00
SUB-ASPH | A24050 | Not Started |  |  | Labor | 2025-05-16 08:00 | 2025-05-16 16:00
EW-STAB | A24020 | Not Started |  |  | Labor | 2025-03-07 08:00 | 2025-03-11 16:00
EW-SML | A23990 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-01-13 08:00 | 2025-01-30 16:00
ST-CIP | A24030 | Not Started | Crews.Wall Crew |  | Labor | 2025-03-13 08:00 | 2025-04-09 16:00
SUB-BR-SLIP | A24040 | Not Started |  |  | Labor | 2025-04-10 08:00 | 2025-05-15 16:00
ST-MSE | A24000 | Not Started | Crews.Wall Crew |  | Labor | 2025-01-31 08:00 | 2025-02-17 16:00
SUB-BR-SLIP | A23980 | Not Started |  |  | Labor | 2025-06-26 08:00 | 2025-07-14 16:00
EW-STR | A23970 | Not Started |  |  | Labor | 2024-08-20 08:00 | 2024-08-22 16:00
EW-STR | A23960 | Not Started |  |  | Labor | 2024-08-20 08:00 | 2024-08-22 16:00
ST-DECK | A23940 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-07 08:00 | 2025-04-07 16:00
SUB-ST-REBAR | A23930 | Not Started |  |  | Labor | 2025-04-04 08:00 | 2025-04-04 16:00
ST-POUR | A23910 | Not Started |  |  | Labor | 2025-03-27 08:00 | 2025-03-27 16:00
SUB-ST-REBAR | A23900 | Not Started |  |  | Labor | 2025-03-21 08:00 | 2025-03-21 16:00
ST-DECK | A23890 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-17 08:00 | 2025-03-20 16:00
SUB-ST-SIP | A23880 | Not Started |  |  | Labor | 2025-03-14 08:00 | 2025-03-14 16:00
ST-BEAM | A23870 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-13 16:00
ST-DECK | A23850 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-04 08:00 | 2025-04-07 16:00
SUB-ST-REBAR | A23840 | Not Started |  |  | Labor | 2025-04-03 08:00 | 2025-04-03 16:00
ST-POUR | A23820 | Not Started |  |  | Labor | 2025-03-26 08:00 | 2025-03-26 16:00
SUB-ST-REBAR | A23810 | Not Started |  |  | Labor | 2025-03-25 08:00 | 2025-03-25 16:00
ST-DECK | A23800 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-17 08:00 | 2025-03-24 16:00
SUB-ST-SIP | A23790 | Not Started |  |  | Labor | 2025-03-14 08:00 | 2025-03-14 16:00
ST-BEAM | A23780 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-13 16:00
ST-CAP | A23760 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-10 08:00 | 2025-02-13 16:00
ST-COL | A23740 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-30 08:00 | 2025-01-31 16:00
ST-FOOT | A23720 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-16 08:00 | 2025-01-21 16:00
ST-PILE | A23710 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-08 08:00 | 2025-01-14 16:00
EW-STR | A23690 | Not Started |  |  | Labor | 2025-01-07 08:00 | 2025-01-07 16:00
ST-MSE | A23670 | Not Started | Crews.Wall Crew |  | Labor | 2025-01-06 08:00 | 2025-01-10 16:00
ST-ABUT | A23650 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-13 08:00 | 2025-01-14 16:00
ST-PILE | A23640 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-03 08:00 | 2025-01-03 16:00
EW- ALL EW | A23620 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-23 08:00 | 2024-08-23 16:00
SUB-STRIP | A23610 | Not Started |  |  | Labor | 2025-04-10 08:00 | 2025-04-10 16:00
SUB-ST-GROOVE | A23600 | Not Started |  |  | Labor | 2025-04-09 08:00 | 2025-04-09 16:00
SUB-ST-PARAPET | A23580 | Not Started |  |  | Labor | 2025-04-08 08:00 | 2025-04-08 16:00
ST-APPR | A23570 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-28 08:00 | 2025-04-01 16:00
ST-APPR | A23560 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-25 08:00 | 2025-03-27 16:00
ST-DECK | A23540 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-02 08:00 | 2025-04-02 16:00
SUB-ST-REBAR | A23530 | Not Started |  |  | Labor | 2025-04-01 08:00 | 2025-04-01 16:00
ST-POUR | A23510 | Not Started |  |  | Labor | 2025-03-24 08:00 | 2025-03-24 16:00
SUB-ST-REBAR | A23500 | Not Started |  |  | Labor | 2025-03-21 08:00 | 2025-03-21 16:00
ST-DECK | A23490 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-17 08:00 | 2025-03-20 16:00
SUB-ST-SIP | A23480 | Not Started |  |  | Labor | 2025-03-14 08:00 | 2025-03-14 16:00
ST-BEAM | A23470 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-13 16:00
ST-CAP | A23450 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-10 08:00 | 2025-02-13 16:00
ST-COL | A23430 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-30 08:00 | 2025-01-31 16:00
ST-FOOT | A23410 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-16 08:00 | 2025-01-21 16:00
ST-PILE | A23400 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-08 08:00 | 2025-01-14 16:00
EW-STR | A23380 | Not Started |  |  | Labor | 2025-01-07 08:00 | 2025-01-07 16:00
EW-STR | A23360 | Not Started |  |  | Labor | 2024-12-17 08:00 | 2024-12-19 16:00
ST-MSE | A23350 | Not Started | Crews.Wall Crew |  | Labor | 2025-01-06 08:00 | 2025-01-10 16:00
ST-ABUT | A23330 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-13 08:00 | 2025-01-17 16:00
ST-PILE | A23320 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-03 08:00 | 2025-01-03 16:00
EW- ALL EW | A23300 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-12-20 08:00 | 2024-12-20 16:00
SUB-ASPH | A23270 | Not Started |  |  | Labor | 2025-10-30 08:00 | 2025-10-30 16:00
EW-ABC | A23260 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-28 08:00 | 2025-10-29 16:00
PIPE | A23250 | Not Started | Crews.Drainage Crew |  | Labor | 2025-10-22 08:00 | 2025-10-27 16:00
ST-DECK | A23230 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-09 08:00 | 2025-05-09 16:00
SUB-ST-REBAR | A23220 | Not Started |  |  | Labor | 2025-05-08 08:00 | 2025-05-08 16:00
ST-POUR | A23200 | Not Started |  |  | Labor | 2025-04-30 08:00 | 2025-04-30 16:00
SUB-ST-REBAR | A23190 | Not Started |  |  | Labor | 2025-04-29 08:00 | 2025-04-29 16:00
ST-DECK | A23180 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-24 08:00 | 2025-04-28 16:00
SUB-ST-SIP | A23170 | Not Started |  |  | Labor | 2025-04-22 08:00 | 2025-04-22 16:00
ST-BEAM | A23160 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-21 08:00 | 2025-04-21 16:00
ST-DECK | A23140 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-13 08:00 | 2025-05-15 16:00
SUB-ST-REBAR | A23130 | Not Started |  |  | Labor | 2025-05-12 08:00 | 2025-05-12 16:00
ST-POUR | A23110 | Not Started |  |  | Labor | 2025-05-02 08:00 | 2025-05-02 16:00
SUB-ST-REBAR | A23100 | Not Started |  |  | Labor | 2025-05-01 08:00 | 2025-05-01 16:00
ST-DECK | A23090 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-24 08:00 | 2025-04-30 16:00
SUB-ST-SIP | A23080 | Not Started |  |  | Labor | 2025-04-22 08:00 | 2025-04-22 16:00
ST-BEAM | A23070 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-21 08:00 | 2025-04-21 16:00
ST-CAP | A23050 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-10 08:00 | 2025-04-15 16:00
ST-COL | A23030 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-01 08:00 | 2025-04-02 16:00
ST-FOOT | A23010 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-20 08:00 | 2025-03-24 16:00
ST-PILE | A23000 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-18 16:00
EW-STR | A22980 | Not Started |  |  | Labor | 2024-12-17 08:00 | 2024-12-17 16:00
ST-MSE | A22960 | Not Started | Crews.Wall Crew |  | Labor | 2025-03-14 08:00 | 2025-03-21 16:00
ST-ABUT | A22940 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-24 08:00 | 2025-03-25 16:00
ST-PILE | A22930 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-13 16:00
EW- ALL EW | A22910 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-23 08:00 | 2024-08-23 16:00
CP-SLIP | A22900 | Not Started | Crews.Paving Crew |  | Labor | 2025-10-01 08:00 | 2025-10-21 16:00
SUB-ASPH | A22890 | Not Started |  |  | Labor | 2025-09-30 08:00 | 2025-09-30 16:00
EW-STAB | A22880 | Not Started |  |  | Labor | 2025-07-15 08:00 | 2025-07-17 16:00
EW-SML | A22870 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-03-14 08:00 | 2025-03-28 16:00
ST-CIP | A22860 | Not Started | Crews.Wall Crew |  | Labor | 2025-07-18 08:00 | 2025-08-18 16:00
SUB-BR-SLIP | A22850 | Not Started |  |  | Labor | 2025-08-19 08:00 | 2025-09-29 16:00
ST-MSE | A22840 | Not Started | Crews.Wall Crew |  | Labor | 2025-03-31 08:00 | 2025-04-28 16:00
SUB-STRIP | A22830 | Not Started |  |  | Labor | 2025-05-20 08:00 | 2025-05-20 16:00
SUB-ST-GROOVE | A22820 | Not Started |  |  | Labor | 2025-05-19 08:00 | 2025-05-19 16:00
SUB-ST-PARAPET | A22800 | Not Started |  |  | Labor | 2025-05-16 08:00 | 2025-05-16 16:00
ST-APPR | A22790 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-01 08:00 | 2025-05-05 16:00
ST-APPR | A22780 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-01 08:00 | 2025-05-05 16:00
ST-DECK | A22760 | Not Started | Crews.Structures Crew |  | Labor | 2025-05-09 08:00 | 2025-05-09 16:00
SUB-ST-REBAR | A22750 | Not Started |  |  | Labor | 2025-05-08 08:00 | 2025-05-08 16:00
ST-POUR | A22730 | Not Started |  |  | Labor | 2025-04-30 08:00 | 2025-04-30 16:00
SUB-ST-REBAR | A22720 | Not Started |  |  | Labor | 2025-04-29 08:00 | 2025-04-29 16:00
ST-DECK | A22710 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-24 08:00 | 2025-04-28 16:00
SUB-ST-SIP | A22700 | Not Started |  |  | Labor | 2025-04-22 08:00 | 2025-04-22 16:00
ST-BEAM | A22690 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-21 08:00 | 2025-04-21 16:00
ST-CAP | A22670 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-10 08:00 | 2025-04-15 16:00
ST-COL | A22650 | Not Started | Crews.Structures Crew |  | Labor | 2025-04-01 08:00 | 2025-04-02 16:00
ST-FOOT | A22630 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-20 08:00 | 2025-03-24 16:00
ST-PILE | A22620 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-18 16:00
EW-STR | A22600 | Not Started |  |  | Labor | 2024-09-03 08:00 | 2024-09-03 16:00
EW-STR | A22580 | Not Started |  |  | Labor | 2024-08-20 08:00 | 2024-08-22 16:00
ST-ABUT | A22550 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-14 08:00 | 2025-03-17 16:00
ST-PILE | A22540 | Not Started | Crews.Structures Crew |  | Labor | 2025-03-13 08:00 | 2025-03-13 16:00
EW- ALL EW | A22520 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-08-23 08:00 | 2024-08-23 16:00
SUB-TC-PCB | A22490 | Not Started |  |  | Labor | 2024-08-02 08:00 | 2024-08-19 16:00
TC-Maint. | A22480 | Not Started |  |  | Labor | 2024-08-01 08:00 | 2024-08-01 16:00
TC-Maint. | A22470 | Not Started |  |  | Labor | 2025-11-03 08:00 | 2025-11-04 16:00
SUB-BR-SLIP | A22460 | Not Started |  |  | Labor | 2025-11-04 08:00 | 2025-11-05 16:00
SUB-GRAIL | A22450 | Not Started |  |  | Labor | 2025-11-17 08:00 | 2025-11-18 16:00
SUB-ASPH | A22440 | Not Started |  |  | Labor | 2025-11-14 08:00 | 2025-11-14 16:00
EW-ABC | A22430 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-11-13 08:00 | 2025-11-13 16:00
EW-STAB | A22420 | Not Started |  |  | Labor | 2025-11-06 08:00 | 2025-11-10 16:00
EW- ALL EW | A22410 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-11-03 08:00 | 2025-11-03 16:00
TC-Maint. | A22350 | Not Started |  |  | Labor | 2025-11-05 08:00 | 2025-11-05 16:00
SUB-STRIP | A22330 | Not Started |  |  | Labor | 2024-07-30 08:00 | 2024-07-30 16:00
SUB-ASPH | A22320 | Not Started |  |  | Labor | 2024-07-29 08:00 | 2024-07-29 16:00
TC-Maint. | A22280 | Not Started |  |  | Labor | 2025-10-31 08:00 | 2025-10-31 16:00
TC-Maint. | A22270 | Not Started |  |  | Labor | 2024-07-26 08:00 | 2024-07-26 16:00
TC-Maint. | A22260 | Not Started |  |  | Labor | 2024-07-25 08:00 | 2024-07-25 16:00
EW-ABC | A22230 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-09-04 08:00 | 2024-09-09 16:00
SUB-STRIP | A22220 | Not Started |  |  | Labor | 2026-04-27 08:00 | 2026-05-18 16:00
SUB-SIGN | A22210 | Not Started |  |  | Labor | 2026-03-17 08:00 | 2026-04-16 16:00
SUB-ASPH | A22190 | Not Started |  |  | Labor | 2026-04-17 08:00 | 2026-04-24 16:00
SUB-ASPH | A22180 | Not Started |  |  | Labor | 2025-11-04 08:00 | 2025-11-04 16:00
EW-ABC | A22170 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-11-03 08:00 | 2025-11-03 16:00
PIPE | A22160 | Not Started | Crews.Drainage Crew |  | Labor | 2025-10-31 08:00 | 2025-10-31 16:00
CP-SLIP | A22150 | Not Started | Crews.Paving Crew |  | Labor | 2025-10-22 08:00 | 2025-10-27 16:00
SUB-ASPH | A22140 | Not Started |  |  | Labor | 2025-10-21 08:00 | 2025-10-21 16:00
EW-STAB | A22130 | Not Started |  |  | Labor | 2025-10-20 08:00 | 2025-10-20 16:00
EW-SML | A22120 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-09-08 08:00 | 2025-09-12 16:00
SUB-BR-SLIP | A22100 | Not Started |  |  | Labor | 2025-10-10 08:00 | 2025-10-17 16:00
SUB-ASPH | A22080 | Not Started |  |  | Labor | 2025-11-03 08:00 | 2025-11-03 16:00
EW-ABC | A22070 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-31 08:00 | 2025-10-31 16:00
PIPE | A22060 | Not Started | Crews.Drainage Crew |  | Labor | 2025-10-29 08:00 | 2025-10-30 16:00
CP-SLIP | A22050 | Not Started | Crews.Paving Crew |  | Labor | 2025-10-24 08:00 | 2025-10-28 16:00
SUB-ASPH | A22040 | Not Started |  |  | Labor | 2025-10-23 08:00 | 2025-10-23 16:00
EW-STAB | A22030 | Not Started |  |  | Labor | 2025-09-08 08:00 | 2025-09-08 16:00
EW-SML | A22020 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-07-17 08:00 | 2025-07-29 16:00
ST-CIP | A22010 | Not Started | Crews.Wall Crew |  | Labor | 2025-09-09 08:00 | 2025-10-06 16:00
SUB-BR-SLIP | A22000 | Not Started |  |  | Labor | 2025-09-23 08:00 | 2025-10-22 16:00
ST-MSE | A21990 | Not Started | Crews.Wall Crew |  | Labor | 2025-07-30 08:00 | 2025-08-14 16:00
SUB-STRIP | A21710 | Not Started |  |  | Labor | 2025-09-18 08:00 | 2025-09-18 16:00
SUB-ST-GROOVE | A21700 | Not Started |  |  | Labor | 2025-09-16 08:00 | 2025-09-16 16:00
SUB-DGRIND | A21690 | Not Started |  |  | Labor | 2025-09-15 08:00 | 2025-09-15 16:00
SUB-ST-PARAPET | A21680 | Not Started |  |  | Labor | 2025-09-12 08:00 | 2025-09-12 16:00
ST-APPR | A21670 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-02 08:00 | 2025-09-05 16:00
ST-APPR | A21660 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-02 08:00 | 2025-09-05 16:00
ST-DECK | A21640 | Not Started | Crews.Structures Crew |  | Labor | 2025-09-09 08:00 | 2025-09-11 16:00
SUB-ST-REBAR | A21630 | Not Started |  |  | Labor | 2025-09-05 08:00 | 2025-09-08 16:00
ST-POUR | A21610 | Not Started |  |  | Labor | 2025-08-28 08:00 | 2025-08-28 16:00
SUB-ST-REBAR | A21600 | Not Started |  |  | Labor | 2025-08-19 08:00 | 2025-08-26 16:00
ST-DECK | A21590 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-06 08:00 | 2025-08-18 16:00
SUB-ST-SIP | A21580 | Not Started |  |  | Labor | 2025-08-04 08:00 | 2025-08-05 16:00
ST-BEAM | A21570 | Not Started | Crews.Structures Crew |  | Labor | 2025-08-01 08:00 | 2025-08-01 16:00
EW-STR | A21460 | Not Started |  |  | Labor | 2025-07-01 08:00 | 2025-07-02 16:00
ST-MSE | A21450 | Not Started | Crews.Wall Crew |  | Labor | 2025-07-11 08:00 | 2025-07-15 16:00
ST-ABUT | A21430 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-17 08:00 | 2025-07-22 16:00
ST-PILE | A21420 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-07 08:00 | 2025-07-10 16:00
EW- ALL EW | A21400 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-07-03 08:00 | 2025-07-03 16:00
EW-STR | A21380 | Not Started |  |  | Labor | 2025-07-01 08:00 | 2025-07-02 16:00
ST-MSE | A21370 | Not Started | Crews.Wall Crew |  | Labor | 2025-07-11 08:00 | 2025-07-15 16:00
ST-ABUT | A21350 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-17 08:00 | 2025-07-28 16:00
ST-PILE | A21340 | Not Started | Crews.Structures Crew |  | Labor | 2025-07-07 08:00 | 2025-07-10 16:00
EW- ALL EW | A21320 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-07-03 08:00 | 2025-07-03 16:00
DM-BRIDGE | A21310 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-13 08:00 | 2025-06-30 16:00
DM-BRIDGE | A21300 | Not Started | Crews.Demolition Crew |  | Labor | 2025-06-04 08:00 | 2025-06-12 16:00
TC-Maint. | A21280 | Not Started |  |  | Labor | 2025-06-03 08:00 | 2025-06-03 16:00
FLATWORK | A21260 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2026-01-13 08:00 | 2026-01-20 16:00
EW-ABC | A21250 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-01-09 08:00 | 2026-01-12 16:00
PIPE | A21240 | Not Started | Crews.Drainage Crew |  | Labor | 2025-11-03 08:00 | 2025-12-05 16:00
SUB-ASPH | A21210 | Not Started |  |  | Labor | 2026-01-22 08:00 | 2026-01-22 16:00
EW-STAB | A21230 | Not Started |  |  | Labor | 2025-12-08 08:00 | 2026-01-08 16:00
EW- ALL EW | A21220 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-10-10 08:00 | 2025-10-13 16:00
SUB-ASPH | A21200 | Not Started |  |  | Labor | 2026-03-30 08:00 | 2026-03-30 16:00
EW-ABC | A21190 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-03-27 08:00 | 2026-03-27 16:00
PIPE | A21180 | Not Started | Crews.Drainage Crew |  | Labor | 2026-03-26 08:00 | 2026-03-26 16:00
CP-SLIP | A21170 | Not Started | Crews.Paving Crew |  | Labor | 2026-03-19 08:00 | 2026-03-24 16:00
SUB-ASPH | A21160 | Not Started |  |  | Labor | 2026-03-17 08:00 | 2026-03-17 16:00
EW-STAB | A21130 | Not Started |  |  | Labor | 2026-02-04 08:00 | 2026-02-04 16:00
EW-SML | A21110 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-01-29 08:00 | 2026-02-03 16:00
ST-CIP | A21140 | Not Started | Crews.Wall Crew |  | Labor | 2026-02-05 08:00 | 2026-02-23 16:00
SUB-BR-SLIP | A21150 | Not Started |  |  | Labor | 2026-02-24 08:00 | 2026-03-16 16:00
ST-MSE | A21120 | Not Started | Crews.Wall Crew |  | Labor | 2025-09-15 08:00 | 2025-10-09 16:00
SUB-ASPH | A21100 | Not Started |  |  | Labor | 2026-04-16 08:00 | 2026-04-16 16:00
EW-ABC | A21090 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-04-14 08:00 | 2026-04-14 16:00
PIPE | A21080 | Not Started | Crews.Drainage Crew |  | Labor | 2026-04-10 08:00 | 2026-04-13 16:00
CP-SLIP | A21070 | Not Started | Crews.Paving Crew |  | Labor | 2026-04-07 08:00 | 2026-04-09 16:00
SUB-ASPH | A21060 | Not Started |  |  | Labor | 2026-04-06 08:00 | 2026-04-06 16:00
EW-STAB | A21030 | Not Started |  |  | Labor | 2026-03-20 08:00 | 2026-03-20 16:00
EW-SML | A21000 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-01-29 08:00 | 2026-02-09 16:00
ST-CIP | A21040 | Not Started | Crews.Wall Crew |  | Labor | 2026-03-23 08:00 | 2026-03-27 16:00
SUB-BR-SLIP | A21050 | Not Started |  |  | Labor | 2026-03-30 08:00 | 2026-04-03 16:00
ST-MSE | A21010 | Not Started | Crews.Wall Crew |  | Labor | 2026-02-10 08:00 | 2026-02-20 16:00
SUB-STRIP | A20720 | Not Started |  |  | Labor | 2026-03-24 08:00 | 2026-03-24 16:00
SUB-ST-GROOVE | A20710 | Not Started |  |  | Labor | 2026-03-23 08:00 | 2026-03-23 16:00
SUB-DGRIND | A20700 | Not Started |  |  | Labor | 2026-03-20 08:00 | 2026-03-20 16:00
SUB-ST-PARAPET | A20690 | Not Started |  |  | Labor | 2026-03-19 08:00 | 2026-03-19 16:00
ST-APPR | A20680 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-04 08:00 | 2026-03-10 16:00
ST-APPR | A20670 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-04 08:00 | 2026-03-12 16:00
ST-DECK | A20650 | Not Started | Crews.Structures Crew |  | Labor | 2026-03-16 08:00 | 2026-03-17 16:00
SUB-ST-REBAR | A20640 | Not Started |  |  | Labor | 2026-03-12 08:00 | 2026-03-13 16:00
ST-POUR | A20620 | Not Started |  |  | Labor | 2026-03-03 08:00 | 2026-03-03 16:00
SUB-ST-REBAR | A20610 | Not Started |  |  | Labor | 2026-02-26 08:00 | 2026-03-02 16:00
ST-DECK | A20600 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-12 08:00 | 2026-02-24 16:00
SUB-ST-SIP | A20590 | Not Started |  |  | Labor | 2026-02-10 08:00 | 2026-02-10 16:00
ST-BEAM | A20580 | Not Started | Crews.Structures Crew |  | Labor | 2026-02-09 08:00 | 2026-02-09 16:00
EW-STR | A20410 | Not Started |  |  | Labor | 2026-01-12 08:00 | 2026-01-15 16:00
ST-MSE | A20450 | Not Started | Crews.Wall Crew |  | Labor | 2026-01-23 08:00 | 2026-01-27 16:00
ST-ABUT | A20470 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-29 08:00 | 2026-02-04 16:00
ST-PILE | A20440 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-20 08:00 | 2026-01-22 16:00
EW- ALL EW | A20420 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-01-16 08:00 | 2026-01-16 16:00
EW-STR | A20330 | Not Started |  |  | Labor | 2026-01-12 08:00 | 2026-01-15 16:00
ST-MSE | A20370 | Not Started | Crews.Wall Crew |  | Labor | 2026-01-26 08:00 | 2026-01-27 16:00
ST-ABUT | A20390 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-29 08:00 | 2026-02-04 16:00
ST-PILE | A20360 | Not Started | Crews.Structures Crew |  | Labor | 2026-01-20 08:00 | 2026-01-23 16:00
EW- ALL EW | A20340 | Not Started | Crews.Earthwork Crew |  | Labor | 2026-01-16 08:00 | 2026-01-16 16:00
DM-BRIDGE | A20320 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-16 08:00 | 2026-01-09 16:00
DM-BRIDGE | A20310 | Not Started | Crews.Demolition Crew |  | Labor | 2025-12-05 08:00 | 2025-12-15 16:00
EW-ABC | A20240 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-11-24 08:00 | 2025-11-25 16:00
SUB-STRIP | A20260 | Not Started |  |  | Labor | 2025-12-02 08:00 | 2025-12-02 16:00
SUB-ASPH | A20250 | Not Started |  |  | Labor | 2025-12-01 08:00 | 2025-12-01 16:00
EW-STAB | A20230 | Not Started |  |  | Labor | 2025-11-10 08:00 | 2025-11-21 16:00
EW- ALL EW | A20220 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-11-07 08:00 | 2025-11-07 16:00
TC-Maint. | A20270 | Not Started |  |  | Labor | 2025-12-04 08:00 | 2025-12-04 16:00
TC-Maint. | A20210 | Not Started |  |  | Labor | 2025-11-06 08:00 | 2025-11-06 16:00
TC-Maint. | A20200 | Not Started |  |  | Labor | 2025-11-05 08:00 | 2025-11-05 16:00
SUB-TC-PCB | A18410 | Not Started |  |  | Labor | 2024-09-16 08:00 | 2024-09-26 16:00
TC-Maint. | A18400 | Not Started |  |  | Labor | 2024-09-13 08:00 | 2024-09-13 16:00
SUB-ASPH | A18390 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-04 16:00
FLATWORK | A18370 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-10-02 08:00 | 2024-10-03 16:00
EW-ABC | A18360 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-10-01 08:00 | 2024-10-01 16:00
EW-STAB | A18350 | Not Started |  |  | Labor | 2024-09-30 08:00 | 2024-09-30 16:00
EW- ALL EW | A18340 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-09-27 08:00 | 2024-09-27 16:00
EW-ABC | A18330 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-09-06 08:00 | 2023-09-06 16:00
SUB-BR-SLIP | A18310 | Not Started |  |  | Labor | 2023-07-03 08:00 | 2023-07-13 16:00
SUB-CURB | A18300 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2023-07-14 08:00 | 2023-07-21 16:00
DM-BRIDGE | A18290 | Not Started | Crews.Demolition Crew |  | Labor | 2023-06-30 08:00 | 2023-06-30 16:00
FLATWORK | A18320 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2023-07-24 08:00 | 2023-08-14 16:00
SUB-ASPH | A18280 | Not Started |  |  | Labor | 2025-02-20 08:00 | 2025-02-20 16:00
EW-ABC | A18270 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-02-17 08:00 | 2025-02-18 16:00
PIPE | A18260 | Not Started | Crews.Drainage Crew |  | Labor | 2025-02-14 08:00 | 2025-02-14 16:00
CP-SLIP | A18250 | Not Started | Crews.Paving Crew |  | Labor | 2025-02-06 08:00 | 2025-02-13 16:00
SUB-ASPH | A18240 | Not Started |  |  | Labor | 2025-02-04 08:00 | 2025-02-05 16:00
EW-STAB | A18210 | Not Started |  |  | Labor | 2025-01-28 08:00 | 2025-02-03 16:00
EW-SML | A18200 | Not Started | Crews.Earthwork Crew |  | Labor | 2025-01-27 08:00 | 2025-01-27 16:00
ST-BRIDGE-ALL | A18180 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-13 08:00 | 2025-01-30 16:00
ST-BRIDGE-ALL | A18160 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-13 08:00 | 2025-01-30 16:00
SUB-ST-RAILING | A18150 | Not Started |  |  | Labor | 2025-02-06 08:00 | 2025-02-13 16:00
DM-BRIDGE | A18140 | Not Started | Crews.Demolition Crew |  | Labor | 2024-10-15 08:00 | 2024-10-17 16:00
DM-BRIDGE | A18130 | Not Started | Crews.Demolition Crew |  | Labor | 2024-11-25 08:00 | 2024-11-26 16:00
DM-BRIDGE | A18120 | Not Started | Crews.Demolition Crew |  | Labor | 2024-10-04 08:00 | 2024-10-07 16:00
EW-STR | A18110 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-11 16:00
ST-MSE | A18090 | Not Started | Crews.Wall Crew |  | Labor | 2025-01-03 08:00 | 2025-01-06 16:00
ST-ABUT | A18070 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-07 08:00 | 2025-01-08 16:00
ST-PILE | A18060 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-18 08:00 | 2024-10-18 16:00
EW- ALL EW | A18040 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-10-14 08:00 | 2024-10-14 16:00
EW-STR | A18030 | Not Started |  |  | Labor | 2024-11-14 08:00 | 2024-11-21 16:00
ST-MSE | A18010 | Not Started | Crews.Wall Crew |  | Labor | 2025-01-03 08:00 | 2025-01-06 16:00
ST-ABUT | A17990 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-07 08:00 | 2025-01-07 16:00
ST-PILE | A17980 | Not Started | Crews.Structures Crew |  | Labor | 2024-12-02 08:00 | 2024-12-02 16:00
EW- ALL EW | A17960 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-11-22 08:00 | 2024-11-22 16:00
ST-CAP | A17940 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-21 08:00 | 2024-10-21 16:00
ST-COL | A17920 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-10 08:00 | 2024-10-11 16:00
ST-PILE | A17910 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-07 08:00 | 2024-10-08 16:00
EW-STR | A17900 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-04 16:00
ST-DECK | A17880 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-04 08:00 | 2025-02-04 16:00
SUB-ST-REBAR | A17870 | Not Started |  |  | Labor | 2025-02-03 08:00 | 2025-02-03 16:00
ST-POUR | A17850 | Not Started |  |  | Labor | 2025-01-24 08:00 | 2025-01-24 16:00
SUB-ST-REBAR | A17840 | Not Started |  |  | Labor | 2025-01-23 08:00 | 2025-01-23 16:00
ST-DECK | A17830 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-16 08:00 | 2025-01-21 16:00
SUB-ST-SIP | A17820 | Not Started |  |  | Labor | 2025-01-14 08:00 | 2025-01-14 16:00
ST-BEAM | A17810 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-13 08:00 | 2025-01-13 16:00
ST-DECK | A17790 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-14 08:00 | 2024-11-14 16:00
SUB-ST-REBAR | A17780 | Not Started |  |  | Labor | 2024-11-12 08:00 | 2024-11-12 16:00
ST-POUR | A17760 | Not Started |  |  | Labor | 2024-11-04 08:00 | 2024-11-04 16:00
SUB-ST-REBAR | A17750 | Not Started |  |  | Labor | 2024-11-01 08:00 | 2024-11-01 16:00
ST-DECK | A17740 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-29 08:00 | 2024-10-31 16:00
SUB-ST-SIP | A17730 | Not Started |  |  | Labor | 2024-10-28 08:00 | 2024-10-28 16:00
ST-BEAM | A17720 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-25 08:00 | 2024-10-25 16:00
SUB-STRIP | A17710 | Not Started |  |  | Labor | 2025-02-13 08:00 | 2025-02-13 16:00
SUB-ST-GROOVE | A17700 | Not Started |  |  | Labor | 2025-02-03 08:00 | 2025-02-03 16:00
SUB-ST-PARAPET | A17680 | Not Started |  |  | Labor | 2025-02-05 08:00 | 2025-02-05 16:00
ST-APPR | A17670 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-27 08:00 | 2025-01-30 16:00
ST-APPR | A17660 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-27 08:00 | 2025-01-30 16:00
ST-DECK | A17640 | Not Started | Crews.Structures Crew |  | Labor | 2025-02-04 08:00 | 2025-02-04 16:00
SUB-ST-REBAR | A17630 | Not Started |  |  | Labor | 2025-02-03 08:00 | 2025-02-03 16:00
ST-POUR | A17610 | Not Started |  |  | Labor | 2025-01-24 08:00 | 2025-01-24 16:00
SUB-ST-REBAR | A17600 | Not Started |  |  | Labor | 2025-01-23 08:00 | 2025-01-23 16:00
ST-DECK | A17590 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-16 08:00 | 2025-01-21 16:00
SUB-ST-SIP | A17580 | Not Started |  |  | Labor | 2025-01-14 08:00 | 2025-01-14 16:00
ST-BEAM | A17570 | Not Started | Crews.Structures Crew |  | Labor | 2025-01-13 08:00 | 2025-01-13 16:00
ST-CAP | A17550 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-21 08:00 | 2024-10-21 16:00
ST-COL | A17530 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-10 08:00 | 2024-10-11 16:00
ST-PILE | A17520 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-07 08:00 | 2024-10-08 16:00
EW-STR | A17510 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-04 16:00
ST-BRIDGE-ALL | A17480 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-29 08:00 | 2024-11-12 16:00
ST-BRIDGE-ALL | A17460 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-29 08:00 | 2024-11-12 16:00
SUB-ST-RAILING | A17450 | Not Started |  |  | Labor | 2024-12-02 08:00 | 2024-12-09 16:00
DM-BRIDGE | A17440 | Not Started | Crews.Demolition Crew |  | Labor | 2024-10-17 08:00 | 2024-10-18 16:00
DM-BRIDGE | A17430 | Not Started | Crews.Demolition Crew |  | Labor | 2024-10-17 08:00 | 2024-10-18 16:00
DM-BRIDGE | A17420 | Not Started | Crews.Demolition Crew |  | Labor | 2024-10-04 08:00 | 2024-10-07 16:00
EW-STR | A17410 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-14 16:00
ST-MSE | A17390 | Not Started | Crews.Wall Crew |  | Labor | 2024-10-22 08:00 | 2024-10-23 16:00
ST-ABUT | A17370 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-24 08:00 | 2024-10-25 16:00
ST-PILE | A17360 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-21 08:00 | 2024-10-21 16:00
EW- ALL EW | A17340 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-10-15 08:00 | 2024-10-15 16:00
EW-STR | A17330 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-14 16:00
ST-MSE | A17300 | Not Started | Crews.Wall Crew |  | Labor | 2024-10-22 08:00 | 2024-10-23 16:00
ST-ABUT | A17280 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-24 08:00 | 2024-10-25 16:00
ST-PILE | A17270 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-21 08:00 | 2024-10-21 16:00
EW- ALL EW | A17250 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-10-15 08:00 | 2024-10-15 16:00
ST-CAP | A17230 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-18 08:00 | 2024-10-22 16:00
ST-COL | A17210 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-10 08:00 | 2024-10-10 16:00
ST-PILE | A17200 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-07 08:00 | 2024-10-08 16:00
EW-STR | A17190 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-04 16:00
ST-DECK | A17170 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-22 08:00 | 2024-11-25 16:00
SUB-ST-REBAR | A17160 | Not Started |  |  | Labor | 2024-11-21 08:00 | 2024-11-21 16:00
ST-POUR | A17140 | Not Started |  |  | Labor | 2024-11-12 08:00 | 2024-11-12 16:00
SUB-ST-REBAR | A17130 | Not Started |  |  | Labor | 2024-11-08 08:00 | 2024-11-08 16:00
ST-DECK | A17120 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-31 08:00 | 2024-11-07 16:00
SUB-ST-SIP | A17110 | Not Started |  |  | Labor | 2024-10-30 08:00 | 2024-10-30 16:00
ST-BEAM | A17100 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-29 08:00 | 2024-10-29 16:00
ST-DECK | A17080 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-22 08:00 | 2024-11-25 16:00
SUB-ST-REBAR | A17070 | Not Started |  |  | Labor | 2024-11-21 08:00 | 2024-11-21 16:00
ST-POUR | A17050 | Not Started |  |  | Labor | 2024-11-12 08:00 | 2024-11-12 16:00
SUB-ST-REBAR | A17040 | Not Started |  |  | Labor | 2024-11-07 08:00 | 2024-11-07 16:00
ST-DECK | A17030 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-30 08:00 | 2024-11-06 16:00
SUB-ST-SIP | A17020 | Not Started |  |  | Labor | 2024-10-29 08:00 | 2024-10-29 16:00
ST-BEAM | A17010 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-28 08:00 | 2024-10-28 16:00
SUB-STRIP | A16910 | Not Started |  |  | Labor | 2024-12-09 08:00 | 2024-12-09 16:00
SUB-ST-GROOVE | A16900 | Not Started |  |  | Labor | 2024-11-21 08:00 | 2024-11-21 16:00
SUB-ST-PARAPET | A16880 | Not Started |  |  | Labor | 2024-11-26 08:00 | 2024-11-26 16:00
ST-APPR | A16870 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-14 08:00 | 2024-11-19 16:00
ST-APPR | A16860 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-12 08:00 | 2024-11-15 16:00
ST-DECK | A16840 | Not Started | Crews.Structures Crew |  | Labor | 2024-11-19 08:00 | 2024-11-19 16:00
SUB-ST-REBAR | A16830 | Not Started |  |  | Labor | 2024-11-18 08:00 | 2024-11-18 16:00
ST-POUR | A16810 | Not Started |  |  | Labor | 2024-11-08 08:00 | 2024-11-08 16:00
SUB-ST-REBAR | A16800 | Not Started |  |  | Labor | 2024-11-07 08:00 | 2024-11-07 16:00
ST-DECK | A16790 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-31 08:00 | 2024-11-06 16:00
SUB-ST-SIP | A16780 | Not Started |  |  | Labor | 2024-10-30 08:00 | 2024-10-30 16:00
ST-BEAM | A16770 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-29 08:00 | 2024-10-29 16:00
ST-CAP | A16750 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-18 08:00 | 2024-10-22 16:00
ST-COL | A16730 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-10 08:00 | 2024-10-10 16:00
ST-PILE | A16690 | Not Started | Crews.Structures Crew |  | Labor | 2024-10-07 08:00 | 2024-10-08 16:00
EW-STR | A16680 | Not Started |  |  | Labor | 2024-10-04 08:00 | 2024-10-04 16:00
SUB-TC-PCB | A16660 | Not Started |  |  | Labor | 2024-09-23 08:00 | 2024-10-03 16:00
TC-Maint. | A16670 | Not Started |  |  | Labor | 2024-09-20 08:00 | 2024-09-20 16:00
SUB-TC-PCB | A16640 | Not Started |  |  | Labor | 2024-09-17 08:00 | 2024-09-17 16:00
TC-Maint. | A16650 | Not Started |  |  | Labor | 2024-09-19 08:00 | 2024-09-19 16:00
SUB-ASPH | A16630 | Not Started |  |  | Labor | 2024-10-02 08:00 | 2024-10-02 16:00
EW-ABC | A16620 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-10-01 08:00 | 2024-10-01 16:00
PIPE | A16610 | Not Started | Crews.Drainage Crew |  | Labor | 2024-09-30 08:00 | 2024-09-30 16:00
CP-SLIP | A16600 | Not Started | Crews.Paving Crew |  | Labor | 2024-09-24 08:00 | 2024-09-27 16:00
SUB-ASPH | A16590 | Not Started |  |  | Labor | 2024-09-23 08:00 | 2024-09-23 16:00
EW-STAB | A16560 | Not Started |  |  | Labor | 2024-09-17 08:00 | 2024-09-20 16:00
ST-MSE | A16530 | Not Started | Crews.Wall Crew |  | Labor | 2025-03-25 08:00 | 2025-04-28 16:00
TC-Maint. | A16510 | Not Started |  |  | Labor | 2024-09-13 08:00 | 2024-09-13 16:00
TC-Maint. | A16500 | Not Started |  |  | Labor | 2024-09-16 08:00 | 2024-09-16 16:00
PIPE | A16480 | Not Started | Crews.Drainage Crew |  | Labor | 2024-10-01 08:00 | 2024-10-28 16:00
PIPE | A16470 | Not Started | Crews.Drainage Crew |  | Labor | 2024-07-29 08:00 | 2024-08-26 16:00
PIPE | A16460 | Not Started | Crews.Drainage Crew |  | Labor | 2024-07-29 08:00 | 2024-08-26 16:00
PIPE | A16450 | Not Started | Crews.Drainage Crew |  | Labor | 2024-08-23 08:00 | 2024-09-24 16:00
PIPE | A16440 | Not Started | Crews.Drainage Crew |  | Labor | 2024-07-29 08:00 | 2024-08-26 16:00
PIPE | A16430 | Not Started | Crews.Drainage Crew |  | Labor | 2024-07-29 08:00 | 2024-08-26 16:00
PIPE | A16380 | Not Started | Crews.Drainage Crew |  | Labor | 2024-07-29 08:00 | 2024-08-26 16:00
FLATWORK | A16370 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-09-10 08:00 | 2024-09-20 16:00
SUB-ASPH | A16360 | Not Started |  |  | Labor | 2024-09-23 08:00 | 2024-09-24 16:00
EW-STAB | A16350 | Not Started |  |  | Labor | 2024-08-23 08:00 | 2024-09-03 16:00
EW-SML | A16340 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-07-25 08:00 | 2024-08-22 16:00
SUB-FENCE | A16290 | Not Started |  |  | Labor | 2023-08-17 08:00 | 2023-08-21 16:00
SUB-BR-SLIP | A16280 | Not Started |  |  | Labor | 2023-07-05 08:00 | 2023-07-14 16:00
SUB-CURB | A16260 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2023-07-17 08:00 | 2023-07-24 16:00
DM-BRIDGE | A16250 | Not Started | Crews.Demolition Crew |  | Labor | 2023-06-30 08:00 | 2023-07-03 16:00
FLATWORK | A16270 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2023-07-25 08:00 | 2023-08-15 16:00
SUB-TC-PCB | A16240 | Not Started |  |  | Labor | 2024-04-23 08:00 | 2024-05-01 16:00
FLATWORK | A16230 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-05-06 08:00 | 2024-06-13 16:00
SUB-ASPH | A16220 | Not Started |  |  | Labor | 2024-05-02 08:00 | 2024-05-03 16:00
SUB-ASPH | A16210 | Not Started |  |  | Labor | 2024-04-22 08:00 | 2024-04-22 16:00
FLATWORK | A16190 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-04-12 08:00 | 2024-04-19 16:00
EW-ABC | A16180 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-04-11 08:00 | 2024-04-11 16:00
EW-STAB | A16170 | Not Started |  |  | Labor | 2024-04-10 08:00 | 2024-04-10 16:00
EW-SML | A16160 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-03-27 08:00 | 2024-04-09 16:00
SUB-TC-PCB | A16150 | Not Started |  |  | Labor | 2024-03-25 08:00 | 2024-03-26 16:00
TC-Maint. | A16140 | Not Started |  |  | Labor | 2024-03-22 08:00 | 2024-03-22 16:00
SUB-ASPH | A16130 | Not Started |  |  | Labor | 2023-10-23 08:00 | 2023-10-23 16:00
FLATWORK | A16110 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2023-10-13 08:00 | 2023-10-20 16:00
EW-ABC | A16100 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-10-12 08:00 | 2023-10-12 16:00
EW-STAB | A16090 | Not Started |  |  | Labor | 2023-10-10 08:00 | 2023-10-10 16:00
EW-SML | A16080 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-09-28 08:00 | 2023-10-09 16:00
SUB-ASPH | A16070 | Not Started |  |  | Labor | 2024-04-15 08:00 | 2024-04-15 16:00
FLATWORK | A16050 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-04-12 08:00 | 2024-04-12 16:00
EW-ABC | A16040 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-04-11 08:00 | 2024-04-11 16:00
EW-STAB | A16030 | Not Started |  |  | Labor | 2024-04-10 08:00 | 2024-04-10 16:00
EW-SML | A16020 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-03-27 08:00 | 2024-04-09 16:00
SUB-ASPH | A16010 | Not Started |  |  | Labor | 2024-03-21 08:00 | 2024-03-21 16:00
FLATWORK | A16000 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2024-03-18 08:00 | 2024-03-19 16:00
EW-ABC | A15990 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-03-15 08:00 | 2024-03-15 16:00
EW-STAB | A15980 | Not Started |  |  | Labor | 2024-03-14 08:00 | 2024-03-14 16:00
EW-SML | A15960 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-09-28 08:00 | 2023-10-09 16:00
ST-MSE | A15970 | Not Started | Crews.Wall Crew |  | Labor | 2024-02-08 08:00 | 2024-03-12 16:00
SUB-TC-PCB | A15950 | Not Started |  |  | Labor | 2023-09-14 08:00 | 2023-09-26 16:00
TC-Maint. | A15940 | Not Started |  |  | Labor | 2023-09-12 08:00 | 2023-09-12 16:00
SUB-ASPH | A15900 | Not Started |  |  | Labor | 2023-11-02 08:00 | 2023-11-02 16:00
EW-ABC | A15890 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-11-01 08:00 | 2023-11-01 16:00
PIPE | A15880 | Not Started | Crews.Drainage Crew |  | Labor | 2023-10-25 08:00 | 2023-10-31 16:00
CP-SLIP | A15870 | Not Started | Crews.Paving Crew |  | Labor | 2023-10-06 08:00 | 2023-10-24 16:00
SUB-ASPH | A15860 | Not Started |  |  | Labor | 2023-10-05 08:00 | 2023-10-05 16:00
EW-STAB | A15850 | Not Started |  |  | Labor | 2023-10-04 08:00 | 2023-10-04 16:00
EW-SML | A15830 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-08-29 08:00 | 2023-10-03 16:00
SUB-BR-SLIP | A15760 | Not Started |  |  | Labor | 2023-10-05 08:00 | 2023-10-25 16:00
SUB-ASPH | A15820 | Not Started |  |  | Labor | 2023-12-01 08:00 | 2023-12-01 16:00
EW-ABC | A15810 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-11-30 08:00 | 2023-11-30 16:00
PIPE | A15800 | Not Started | Crews.Drainage Crew |  | Labor | 2023-11-21 08:00 | 2023-11-29 16:00
CP-SLIP | A15790 | Not Started | Crews.Paving Crew |  | Labor | 2023-11-01 08:00 | 2023-11-20 16:00
SUB-ASPH | A15780 | Not Started |  |  | Labor | 2023-10-31 08:00 | 2023-10-31 16:00
EW-STAB | A15770 | Not Started |  |  | Labor | 2023-10-26 08:00 | 2023-10-26 16:00
EW-SML | A15750 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-08-21 08:00 | 2023-10-04 16:00
SUB-BR-SLIP | A15680 | Not Started |  |  | Labor | 2024-04-25 08:00 | 2024-05-01 16:00
SUB-ASPH | A15740 | Not Started |  |  | Labor | 2024-05-21 08:00 | 2024-05-21 16:00
EW-ABC | A15730 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-05-20 08:00 | 2024-05-20 16:00
PIPE | A15720 | Not Started | Crews.Drainage Crew |  | Labor | 2024-05-16 08:00 | 2024-05-17 16:00
CP-SLIP | A15710 | Not Started | Crews.Paving Crew |  | Labor | 2024-05-07 08:00 | 2024-05-14 16:00
SUB-ASPH | A15700 | Not Started |  |  | Labor | 2024-05-06 08:00 | 2024-05-06 16:00
EW-STAB | A15690 | Not Started |  |  | Labor | 2024-05-02 08:00 | 2024-05-03 16:00
EW- ALL EW | A15670 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-04-23 08:00 | 2024-04-23 16:00
SUB-ASPH | A15660 | Not Started |  |  | Labor | 2024-07-26 08:00 | 2024-07-26 16:00
EW-ABC | A15650 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-07-25 08:00 | 2024-07-25 16:00
PIPE | A15640 | Not Started | Crews.Drainage Crew |  | Labor | 2024-07-19 08:00 | 2024-07-23 16:00
CP-SLIP | A15630 | Not Started | Crews.Paving Crew |  | Labor | 2024-07-11 08:00 | 2024-07-18 16:00
SUB-ASPH | A15620 | Not Started |  |  | Labor | 2024-07-10 08:00 | 2024-07-10 16:00
EW-STAB | A15590 | Not Started |  |  | Labor | 2024-06-14 08:00 | 2024-06-17 16:00
EW-SML | A15580 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-05-14 08:00 | 2024-06-13 16:00
ST-CIP | A15600 | Not Started | Crews.Wall Crew |  | Labor | 2024-06-18 08:00 | 2024-06-27 16:00
SUB-BR-SLIP | A15610 | Not Started |  |  | Labor | 2024-06-28 08:00 | 2024-07-09 16:00
SUB-BR-SLIP | A15570 | Not Started |  |  | Labor | 2024-05-14 08:00 | 2024-06-13 16:00
SUB-BR-SLIP | A15560 | Not Started |  |  | Labor | 2024-02-28 08:00 | 2024-03-01 16:00
ST-MSE | A15550 | Not Started | Crews.Wall Crew |  | Labor | 2024-03-28 08:00 | 2024-05-07 16:00
SUB-ASPH | A15540 | Not Started |  |  | Labor | 2024-09-12 08:00 | 2024-09-12 16:00
EW-ABC | A15530 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-09-09 08:00 | 2024-09-10 16:00
PIPE | A15520 | Not Started | Crews.Drainage Crew |  | Labor | 2024-09-03 08:00 | 2024-09-06 16:00
CP-SLIP | A15510 | Not Started | Crews.Paving Crew |  | Labor | 2024-08-13 08:00 | 2024-08-29 16:00
SUB-ASPH | A15500 | Not Started |  |  | Labor | 2024-08-12 08:00 | 2024-08-12 16:00
EW-STAB | A15470 | Not Started |  |  | Labor | 2024-06-14 08:00 | 2024-06-17 16:00
EW-SML | A15450 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-02-16 08:00 | 2024-03-27 16:00
ST-CIP | A15480 | Not Started | Crews.Wall Crew |  | Labor | 2024-06-18 08:00 | 2024-08-05 16:00
SUB-BR-SLIP | A15490 | Not Started |  |  | Labor | 2024-08-06 08:00 | 2024-08-09 16:00
ST-MSE | A15460 | Not Started | Crews.Wall Crew |  | Labor | 2024-03-07 08:00 | 2024-04-22 16:00
PIPE | A15440 | Not Started | Crews.Drainage Crew |  | Labor | 2023-07-24 08:00 | 2023-08-18 16:00
PIPE | A15430 | Not Started | Crews.Drainage Crew |  | Labor | 2023-08-01 08:00 | 2023-08-28 16:00
PIPE | A15420 | Not Started | Crews.Drainage Crew |  | Labor | 2023-07-24 08:00 | 2023-08-18 16:00
SUB-ASPH | A15410 | Not Started |  |  | Labor | 2024-04-22 08:00 | 2024-04-22 16:00
EW-ABC | A15400 | Not Started | Crews.Earthwork Crew |  | Labor | 2024-04-19 08:00 | 2024-04-19 16:00
PIPE | A15390 | Not Started | Crews.Drainage Crew |  | Labor | 2024-04-15 08:00 | 2024-04-18 16:00
ST-DECK | A15380 | Not Started | Crews.Structures Crew |  | Labor | 2024-04-09 08:00 | 2024-04-11 16:00
SUB-ST-REBAR | A15370 | Not Started |  |  | Labor | 2024-04-05 08:00 | 2024-04-08 16:00
ST-POUR | A15350 | Not Started |  |  | Labor | 2024-03-28 08:00 | 2024-03-28 16:00
SUB-ST-REBAR | A15340 | Not Started |  |  | Labor | 2024-03-22 08:00 | 2024-03-27 16:00
ST-DECK | A15330 | Not Started | Crews.Structures Crew |  | Labor | 2024-03-04 08:00 | 2024-03-21 16:00
SUB-ST-SIP | A15320 | Not Started |  |  | Labor | 2024-03-04 08:00 | 2024-03-04 16:00
ST-BEAM | A15300 | Not Started | Crews.Structures Crew |  | Labor | 2024-02-26 08:00 | 2024-03-01 16:00
ST-DECK | A15290 | Not Started | Crews.Structures Crew |  | Labor | 2024-04-09 08:00 | 2024-04-12 16:00
SUB-ST-REBAR | A15280 | Not Started |  |  | Labor | 2024-04-05 08:00 | 2024-04-08 16:00
ST-POUR | A15260 | Not Started |  |  | Labor | 2024-03-28 08:00 | 2024-03-28 16:00
SUB-ST-REBAR | A15250 | Not Started |  |  | Labor | 2023-10-24 08:00 | 2023-10-30 16:00
ST-DECK | A15240 | Not Started | Crews.Structures Crew |  | Labor | 2023-09-28 08:00 | 2023-10-23 16:00
SUB-ST-SIP | A15230 | Not Started |  |  | Labor | 2023-09-28 08:00 | 2023-09-28 16:00
ST-BEAM | A15210 | Not Started | Crews.Structures Crew |  | Labor | 2023-09-19 08:00 | 2023-09-26 16:00
ST-CAP | A15190 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-10 08:00 | 2023-08-17 16:00
ST-COL | A15170 | Not Started | Crews.Structures Crew |  | Labor | 2023-07-28 08:00 | 2023-08-02 16:00
ST-FOOT | A15150 | Not Started | Crews.Structures Crew |  | Labor | 2023-07-17 08:00 | 2023-07-20 16:00
ST-PILE | A15140 | Not Started | Crews.Structures Crew |  | Labor | 2023-07-06 08:00 | 2023-07-14 16:00
EW-STR | A15120 | Not Started |  |  | Labor | 2023-06-30 08:00 | 2023-06-30 16:00
ST-MSE | A15080 | Not Started | Crews.Wall Crew |  | Labor | 2024-02-08 08:00 | 2024-02-15 16:00
ST-ABUT | A15100 | Not Started | Crews.Structures Crew |  | Labor | 2024-02-16 08:00 | 2024-02-20 16:00
ST-PILE | A15070 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-03 08:00 | 2023-08-04 16:00
EW- ALL EW | A15050 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-08-02 08:00 | 2023-08-02 16:00
FLATWORK | A15020 | Not Started | Crews.Misc Concrete Crew |  | Labor | 2023-10-27 08:00 | 2023-10-30 16:00
PIPE | A15010 | Not Started | Crews.Drainage Crew |  | Labor | 2023-07-24 08:00 | 2023-08-18 16:00
CP-SLIP | A15000 | Not Started | Crews.Paving Crew |  | Labor | 2024-04-05 08:00 | 2024-04-12 16:00
SUB-ASPH | A14990 | Not Started |  |  | Labor | 2024-04-04 08:00 | 2024-04-04 16:00
EW-STAB | A14980 | Not Started |  |  | Labor | 2024-03-04 08:00 | 2024-03-04 16:00
EW-SML | A14940 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-08-10 08:00 | 2023-08-18 16:00
ST-CIP | A14960 | Not Started | Crews.Wall Crew |  | Labor | 2024-03-05 08:00 | 2024-03-19 16:00
SUB-BR-SLIP | A14970 | Not Started |  |  | Labor | 2024-03-21 08:00 | 2024-04-03 16:00
ST-MSE | A14950 | Not Started | Crews.Wall Crew |  | Labor | 2024-02-08 08:00 | 2024-02-27 16:00
SUB-STRIP | A14930 | Not Started |  |  | Labor | 2024-04-25 08:00 | 2024-04-25 16:00
SUB-ST-GROOVE | A14920 | Not Started |  |  | Labor | 2024-04-23 08:00 | 2024-04-23 16:00
SUB-DGRIND | A14910 | Not Started |  |  | Labor | 2024-04-19 08:00 | 2024-04-22 16:00
SUB-ST-PARAPET | A14880 | Not Started |  |  | Labor | 2024-04-15 08:00 | 2024-04-18 16:00
ST-APPR | A14900 | Not Started | Crews.Structures Crew |  | Labor | 2024-03-29 08:00 | 2024-04-05 16:00
ST-APPR | A14890 | Not Started | Crews.Structures Crew |  | Labor | 2024-03-29 08:00 | 2024-04-05 16:00
ST-DECK | A14860 | Not Started | Crews.Structures Crew |  | Labor | 2024-04-09 08:00 | 2024-04-11 16:00
SUB-ST-REBAR | A14850 | Not Started |  |  | Labor | 2024-04-05 08:00 | 2024-04-08 16:00
ST-POUR | A14830 | Not Started |  |  | Labor | 2024-03-28 08:00 | 2024-03-28 16:00
SUB-ST-REBAR | A14820 | Not Started |  |  | Labor | 2023-10-17 08:00 | 2023-10-23 16:00
ST-DECK | A14810 | Not Started | Crews.Structures Crew |  | Labor | 2023-09-28 08:00 | 2023-10-16 16:00
SUB-ST-SIP | A14800 | Not Started |  |  | Labor | 2023-09-28 08:00 | 2023-09-28 16:00
ST-BEAM | A14790 | Not Started | Crews.Structures Crew |  | Labor | 2023-09-19 08:00 | 2023-09-26 16:00
ST-CAP | A14770 | Not Started | Crews.Structures Crew |  | Labor | 2023-09-05 08:00 | 2023-09-11 16:00
ST-COL | A14750 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-24 08:00 | 2023-08-28 16:00
ST-FOOT | A14730 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-11 08:00 | 2023-08-15 16:00
ST-PILE | A14720 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-03 08:00 | 2023-08-10 16:00
EW-STR | A14700 | Not Started |  |  | Labor | 2023-08-02 08:00 | 2023-08-02 16:00
EW-STR | A14680 | Not Started |  |  | Labor | 2023-07-24 08:00 | 2023-07-31 16:00
ST-MSE | A14670 | Not Started | Crews.Wall Crew |  | Labor | 2023-08-04 08:00 | 2023-08-09 16:00
ST-ABUT | A1660 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-10 08:00 | 2023-08-14 16:00
ST-PILE | A1650 | Not Started | Crews.Structures Crew |  | Labor | 2023-08-02 08:00 | 2023-08-03 16:00
EW- ALL EW | A1630 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-08-01 08:00 | 2023-08-01 16:00
SUB-TC-PCB | A1150 | Not Started |  |  | Labor | 2023-07-25 08:00 | 2023-07-31 16:00
TC-Maint. | A1140 | Not Started |  |  | Labor | 2023-07-24 08:00 | 2023-07-24 16:00
SUB-TC-PCB | A1130 | Not Started |  |  | Labor | 2023-07-21 08:00 | 2023-07-21 16:00
TC-Maint. | A1120 | Not Started |  |  | Labor | 2023-07-20 08:00 | 2023-07-20 16:00
SUB-STRIP | A1110 | Not Started |  |  | Labor | 2023-09-08 08:00 | 2023-09-08 16:00
SUB-ASPH | A1100 | Not Started |  |  | Labor | 2023-09-07 08:00 | 2023-09-07 16:00
EW-STAB | A1090 | Not Started |  |  | Labor | 2023-08-10 08:00 | 2023-09-05 16:00
EW-SML | A1080 | Not Started | Crews.Earthwork Crew |  | Labor | 2023-07-27 08:00 | 2023-08-09 16:00
TC-Maint. | A1060 | Not Started |  |  | Labor | 2023-09-11 08:00 | 2023-09-11 16:00
TC-Maint. | A1040 | Not Started |  |  | Labor | 2023-07-03 08:00 | 2023-07-03 16:00
TC-Maint. | A1030 | Not Started |  |  | Labor | 2023-06-30 08:00 | 2023-06-30 16:00
SUB-EW-C&G | A1020 | Not Started |  |  | Labor | 2023-07-18 08:00 | 2023-08-09 16:00
SUB-EROSION | A1010 | Not Started |  |  | Labor | 2023-06-30 08:00 | 2023-07-17 16:00
SUB-ST-DRSFT | A36680 | Not Started |  |  | Labor | 2024-06-25 08:00 | 2024-07-02 16:00
SUB-ST-DRSFT | A36690 | Not Started |  |  | Labor | 2024-07-03 08:00 | 2024-07-10 16:00

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Day DateFormat=M/d/yyyy CurrencyFormat=Dollar