## TASK
task_code | status_code | wbs_id | wbs_name | task_name | critical_flag | start_date | end_date | act_start_date | act_end_date | target_drtn_hr_cnt | act_drtn_hr_cnt | remain_drtn_hr_cnt | total_float_hr_cnt | float_path | resource_list | actv_code_crew_type_id | actv_code_work_type_id | delete_record_flag
Activity ID | Activity Status | WBS Code | (*)WBS Name | Activity Name | (*)Critical | (*)Start | (*)Finish | Actual Start | Actual Finish | Original Duration(d) | (*)Actual Duration(d) | Remaining Duration(d) | (*)Total Float(d) | (*)Float Path | (*)Resources | CREW TYPE | WORK TYPE | Delete This Row
Admin-1045 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Begin Design | N | 2022-08-01 08:00 |  | 2022-08-01 08:00 |  | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1070 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Contract Completion (Nov. 7th 2026) | Y |  | 2026-11-07 16:00 |  |  | 0 | 0 | 0 | 0 | 1 |  | MS | MS
Admin-1060 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Project Punchlist | Y | 2026-09-09 08:00 | 2026-11-07 16:00 |  |  | 60 | 0 | 60 | 0 | 1 |  | MS | MS
Admin-1050 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Substantial Completion (Sept. 8th, 2026) | Y |  | 2026-09-08 16:00 |  |  | 0 | 0 | 0 | 0 | 1 |  | MS | MS
Admin-1010 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Execute Contract | N | 2022-07-13 08:00 | 2022-07-27 16:00 | 2022-07-13 08:00 | 2022-07-27 16:00 | 15 | 15 | 0 |  |  |  | MS | MS
Admin-1020 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Anticipated Notice to Proceed (Sept. 26th, 2022) | N | 2022-09-26 08:00 |  | 2022-09-26 08:00 |  | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1030 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Design Mobilization | N | 2022-07-13 08:00 | 2022-08-01 16:00 | 2022-07-13 08:00 | 2022-08-01 16:00 | 75 | 20 | 0 |  |  |  | MS | MS
Admin-1040 | In Progress | I-275 - I-4 - FDOT - S2.1 | Project Administration | LOE - Project Duration | N | 2022-09-26 08:00 | 2026-11-07 16:00 | 2022-09-26 08:00 |  | 1500 | 83 | 1421 | 0 |  |  | LOE | MS
Admin-1000 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Anticipated Contract Award Date | N | 2022-07-13 08:00 |  | 2022-07-13 08:00 |  | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1015 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Prepare for Notice to Proceed | N | 2022-07-29 08:00 | 2022-09-26 16:00 | 2022-07-29 08:00 | 2022-09-26 16:00 | 60 | 60 | 0 |  |  |  | MS | MS
Admin-1080 | Completed | I-275 - I-4 - FDOT - S2.1 | Project Administration | Anticipated Contract Execution Date | N |  | 2022-07-27 08:00 |  | 2022-07-27 08:00 | 0 | 0 | 0 |  |  |  | MS | MS
Admin-1100 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Design Completion | N |  | 2024-07-24 16:00 |  |  | 0 | 0 | 0 | 776 |  |  | MS | MS
A1000 | Not Started | I-275 - I-4 - FDOT - S2.2.1 | Mobilization | Mobilization | N | 2023-06-02 08:00 | 2023-06-02 16:00 |  |  | 1 | 0 | 1 | 67 |  |  | OFFICE | OFFICE
P1040 | Not Started | I-275 - I-4 - FDOT - S2.4.1.26 | Noise Management Plan | Develop and Submit - Noise Management Plan | N | 2022-12-27 08:00 | 2023-01-25 16:00 |  |  | 20 | 0 | 20 | 193 |  |  | OFFICE | OFFICE
P1070 | Not Started | I-275 - I-4 - FDOT - S2.4.1.26 | Noise Management Plan | Review and Comment - Noise Management Plan | N | 2023-01-26 08:00 | 2023-02-15 16:00 |  |  | 15 | 0 | 15 | 193 |  |  | OWNER.Design Review | OWNER
P1100 | Not Started | I-275 - I-4 - FDOT - S2.4.1.26 | Noise Management Plan | Revise and Resubmit - Noise Management Plan | N | 2023-02-16 08:00 | 2023-02-22 16:00 |  |  | 5 | 0 | 5 | 193 |  |  | OFFICE | OFFICE
P1130 | Not Started | I-275 - I-4 - FDOT - S2.4.1.26 | Noise Management Plan | Review and Approve - Noise Management Plan | N | 2023-02-23 08:00 | 2023-03-15 16:00 |  |  | 15 | 0 | 15 | 193 |  |  | OWNER.Design Review | OWNER
D1000 | Not Started | I-275 - I-4 - FDOT - S2.3.5 | Erosion and Sediment Control Plan | Develop and Submit - 90% Erosion and Sediment Control Plan | N | 2022-12-19 08:00 | 2023-02-01 16:00 |  |  | 30 | 0 | 30 | 103 |  |  | DESIGN | DESIGN
D1120 | Not Started | I-275 - I-4 - FDOT - S2.3.5 | Erosion and Sediment Control Plan | Review and Approve - 90% Erosion and Sediment Control Plan | N | 2023-02-02 08:00 | 2023-02-22 16:00 |  |  | 15 | 0 | 15 | 103 |  |  | OWNER.Design Review | OWNER
D1210 | Not Started | I-275 - I-4 - FDOT - S2.3.5 | Erosion and Sediment Control Plan | Develop and Submit - Final Erosion and Sediment Control Plan | N | 2023-02-23 08:00 | 2023-03-15 16:00 |  |  | 15 | 0 | 15 | 103 |  |  | DESIGN | DESIGN
D1270 | Not Started | I-275 - I-4 - FDOT - S2.3.5 | Erosion and Sediment Control Plan | Review and Approve - Final Erosion and Sediment Control Plan | N | 2023-03-16 08:00 | 2023-04-05 16:00 |  |  | 15 | 0 | 15 | 103 |  |  | OWNER.Design Review | OWNER
D1640 | Not Started | I-275 - I-4 - FDOT - S2.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) | Develop and Submit - 90% Signing and Pavement Marking Plan | N | 2023-06-14 08:00 | 2023-08-09 16:00 |  |  | 40 | 0 | 40 | 40 |  |  | DESIGN | DESIGN
D1860 | Not Started | I-275 - I-4 - FDOT - S2.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) | Review and Approve - 90% Signing and Pavement Marking Plan | N | 2023-08-10 08:00 | 2023-08-30 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1960 | Not Started | I-275 - I-4 - FDOT - S2.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) | Develop and Submit - Final Signing and Pavement Marking Plan | N | 2023-08-31 08:00 | 2023-09-28 16:00 |  |  | 20 | 0 | 20 | 40 |  |  | DESIGN | DESIGN
D2100 | Not Started | I-275 - I-4 - FDOT - S2.3.18.21 | Signing and Pavement Marking Plan (Incl Misc Structures) | Review and Approve - Final Signing and Pavement Marking Plan | N | 2023-09-29 08:00 | 2023-10-19 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1650 | Not Started | I-275 - I-4 - FDOT - S2.3.18.22 | Lighting Plans | Develop and Submit - 90% Lighting Plans | N | 2023-06-14 08:00 | 2023-08-09 16:00 |  |  | 40 | 0 | 40 | 40 |  |  | DESIGN | DESIGN
D1870 | Not Started | I-275 - I-4 - FDOT - S2.3.18.22 | Lighting Plans | Review and Approve - 90% Lighting Plans | N | 2023-08-10 08:00 | 2023-08-30 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1970 | Not Started | I-275 - I-4 - FDOT - S2.3.18.22 | Lighting Plans | Develop and Submit - Final Lighting Plans | N | 2023-08-31 08:00 | 2023-09-28 16:00 |  |  | 20 | 0 | 20 | 40 |  |  | DESIGN | DESIGN
D2110 | Not Started | I-275 - I-4 - FDOT - S2.3.18.22 | Lighting Plans | Review and Approve - Final Lighting Plans | N | 2023-09-29 08:00 | 2023-10-19 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1660 | Not Started | I-275 - I-4 - FDOT - S2.3.18.20 | Signalization Plans | Develop and Submit - 90% Signalization Plans | N | 2023-06-14 08:00 | 2023-08-09 16:00 |  |  | 40 | 0 | 40 | 40 |  |  | DESIGN | DESIGN
D1880 | Not Started | I-275 - I-4 - FDOT - S2.3.18.20 | Signalization Plans | Review and Approve - 90% Signalization Plans | N | 2023-08-10 08:00 | 2023-08-30 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1980 | Not Started | I-275 - I-4 - FDOT - S2.3.18.20 | Signalization Plans | Develop and Submit - Final Signalization Plans | N | 2023-08-31 08:00 | 2023-09-28 16:00 |  |  | 20 | 0 | 20 | 40 |  |  | DESIGN | DESIGN
D2120 | Not Started | I-275 - I-4 - FDOT - S2.3.18.20 | Signalization Plans | Review and Approve - Final Signalization Plans | N | 2023-09-29 08:00 | 2023-10-19 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1700 | Not Started | I-275 - I-4 - FDOT - S2.3.18.23 | Landscape Opportunity Plans | Develop and Submit - 90% Landscaping Opportunity Plan | N | 2023-08-07 08:00 | 2023-10-02 16:00 |  |  | 40 | 0 | 40 | 3 | 3 |  | DESIGN | DESIGN
D1930 | Not Started | I-275 - I-4 - FDOT - S2.3.18.23 | Landscape Opportunity Plans | Review and Approve - 90% Landscaping Opportunity Plan | N | 2023-10-03 08:00 | 2023-10-23 16:00 |  |  | 15 | 0 | 15 | 3 | 3 |  | OWNER.Design Review | OWNER
D2030 | Not Started | I-275 - I-4 - FDOT - S2.3.18.23 | Landscape Opportunity Plans | Develop and Submit - Final Landscaping Opportunity Plan | N | 2023-10-24 08:00 | 2023-11-21 16:00 |  |  | 20 | 0 | 20 | 3 | 3 |  | DESIGN | DESIGN
D2170 | Not Started | I-275 - I-4 - FDOT - S2.3.18.23 | Landscape Opportunity Plans | Review and Approve - Final Landscaping Opportunity Plan | N | 2023-11-22 08:00 | 2023-12-14 16:00 |  |  | 15 | 0 | 15 | 3 | 3 |  | OWNER.Design Review | OWNER
D1010 | Completed | I-275 - I-4 - FDOT - S2.3.1.1 | Design Quality Management Plan | Develop and Submit - Design Quality Management Plan | N | 2022-09-13 08:00 | 2022-09-27 16:00 | 2022-09-13 08:00 | 2022-09-27 16:00 | 14 | 11 | 0 |  |  |  | DESIGN | DESIGN
D1080 | Completed | I-275 - I-4 - FDOT - S2.3.1.1 | Design Quality Management Plan | Review and Comment - Design Quality Management Plan | N | 2022-09-27 08:00 | 2022-10-25 16:00 | 2022-09-27 08:00 | 2022-10-25 16:00 | 10 | 21 | 0 |  |  |  | DESIGN | OWNER
D1160 | Completed | I-275 - I-4 - FDOT - S2.3.1.1 | Design Quality Management Plan | Revise and Resubmit - Design Quality Management Plan | N | 2022-10-25 08:00 | 2022-12-01 16:00 | 2022-10-25 08:00 | 2022-12-01 16:00 | 5 | 25 | 0 |  |  |  | DESIGN | DESIGN
D1180 | Completed | I-275 - I-4 - FDOT - S2.3.1.1 | Design Quality Management Plan | Review and Approve - Design Quality Management Plan | N | 2022-12-01 08:00 | 2022-12-14 16:00 | 2022-12-01 08:00 | 2022-12-14 16:00 | 10 | 10 | 0 |  |  |  | OWNER.Design Review | OWNER
P1000 | Not Started | I-275 - I-4 - FDOT - S2.4.1.2 | Construction Quality Control Plan | Develop and Submit - Construction Quality Control Plan | N | 2022-12-19 08:00 | 2023-01-18 16:00 |  |  | 20 | 0 | 20 | 125 |  |  | OFFICE | OFFICE
P1010 | Not Started | I-275 - I-4 - FDOT - S2.4.1.2 | Construction Quality Control Plan | Review and Comment - Construction Quality Control Plan | N | 2023-01-19 08:00 | 2023-02-08 16:00 |  |  | 15 | 0 | 15 | 125 |  |  | OWNER.Design Review | OWNER
P1020 | Not Started | I-275 - I-4 - FDOT - S2.4.1.2 | Construction Quality Control Plan | Revise and Resubmit - Construction Quality Control Plan | N | 2023-02-09 08:00 | 2023-02-15 16:00 |  |  | 5 | 0 | 5 | 125 |  |  | OFFICE | OFFICE
P1030 | Not Started | I-275 - I-4 - FDOT - S2.4.1.2 | Construction Quality Control Plan | Review and Approve - Construction Quality Control Plan | N | 2023-02-16 08:00 | 2023-03-08 16:00 |  |  | 15 | 0 | 15 | 125 |  |  | OWNER.Design Review | OWNER
D1710 | Not Started | I-275 - I-4 - FDOT - S2.3.6.3 | FDEP Environmental Resource Permit (ERP) | Modify and Submit - Environmental Resource Permit (ERP) | N | 2023-08-07 08:00 | 2023-08-11 16:00 |  |  | 5 | 0 | 5 | 12 | 23 |  | PERMIT | PERMIT
D1740 | Not Started | I-275 - I-4 - FDOT - S2.3.6.3 | FDEP Environmental Resource Permit (ERP) | Review and Comment - Environmental Resource Permit (ERP) | N | 2023-08-14 08:00 | 2024-02-20 16:00 |  |  | 130 | 0 | 130 | 12 | 23 |  | 3rd PARTY | 3rd Party
D1030 | Completed | I-275 - I-4 - FDOT - S2.3.1.2 | Preliminary IDR Submittal Schedule | Develop and Submit - Preliminary IDR Submittal Schedule | N | 2022-10-10 08:00 | 2022-10-28 16:00 | 2022-10-10 08:00 | 2022-10-28 16:00 | 15 | 15 | 0 |  |  |  | DESIGN | DESIGN
D1170 | Completed | I-275 - I-4 - FDOT - S2.3.1.2 | Preliminary IDR Submittal Schedule | Independent Design Review Kickoff Meeting | N | 2022-10-25 08:00 | 2022-10-25 16:00 | 2022-10-25 08:00 | 2022-10-25 16:00 | 1 | 1 | 0 |  |  |  | DESIGN | DESIGN
D1560 | Not Started | I-275 - I-4 - FDOT - S2.3.18.12 | Maintenance of Communication (MoC) Plan | Develop and Submit - 90% MoC Plan | N | 2023-06-16 08:00 | 2023-08-11 16:00 |  |  | 40 | 0 | 40 | 23 |  |  | DESIGN | DESIGN
D1760 | Not Started | I-275 - I-4 - FDOT - S2.3.18.12 | Maintenance of Communication (MoC) Plan | Review and Approve - 90% MoC Plan | N | 2023-08-14 08:00 | 2023-09-01 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D1820 | Not Started | I-275 - I-4 - FDOT - S2.3.18.12 | Maintenance of Communication (MoC) Plan | Develop and Submit- Final MoC Plan | N | 2023-09-05 08:00 | 2023-10-02 16:00 |  |  | 20 | 0 | 20 | 23 |  |  | DESIGN | DESIGN
D1940 | Not Started | I-275 - I-4 - FDOT - S2.3.18.12 | Maintenance of Communication (MoC) Plan | Review and Approve - Final MoC Plan | N | 2023-10-03 08:00 | 2023-10-23 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D1040 | In Progress | I-275 - I-4 - FDOT - S2.3.3 | Design Survey/SUE | Perform Design Survey [LoE] | N | 2022-08-01 08:00 | 2023-03-13 16:00 | 2022-08-01 08:00 |  | 90 | 96 | 58 | 23 |  |  | LOE | SURVEY
D1090 | Not Started | I-275 - I-4 - FDOT - S2.3.9 | Geotechnical Investigations | Perform Geotechnical Investigations - Brgs | N | 2022-12-19 08:00 | 2023-02-08 16:00 |  |  | 35 | 0 | 35 | 12 | 14 |  | DESIGN | DESIGN
D1190 | Not Started | I-275 - I-4 - FDOT - S2.3.9 | Geotechnical Investigations | Perform Geotechnical Investigations - Retaining Walls | N | 2023-01-19 08:00 | 2023-02-15 16:00 |  |  | 20 | 0 | 20 | 2 | 2 |  | DESIGN | DESIGN
D1350 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | N | 2023-02-09 08:00 | 2023-05-03 16:00 |  |  | 60 | 0 | 60 | 35 |  |  | DESIGN | DESIGN
D1540 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | OWNER.Design Review | OWNER
D1810 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Develop and Submit - Final Cat1 Brg 08 Plans - R3 | N | 2023-05-25 08:00 | 2023-06-22 16:00 |  |  | 20 | 0 | 20 | 35 |  |  | DESIGN | DESIGN
D1890 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Review and Approve - Final Cat1 Brg 08 Plans - R3 | N | 2023-06-23 08:00 | 2023-07-14 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | OWNER.Design Review | OWNER
D1200 | In Progress | I-275 - I-4 - FDOT - S2.3.11.19 | R1 Roadway Design | Develop and Submit - 90% Roadway Plans - R1 | N | 2022-10-31 08:00 | 2023-03-13 16:00 | 2022-10-31 08:00 |  | 90 | 32 | 58 | 23 |  |  | DESIGN | DESIGN
D1460 | Not Started | I-275 - I-4 - FDOT - S2.3.11.19 | R1 Roadway Design | Review and Approve - 90% Roadway Plans - R1 | N | 2023-03-14 08:00 | 2023-04-03 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | OWNER.Design Review | OWNER
D1490 | Not Started | I-275 - I-4 - FDOT - S2.3.11.19 | R1 Roadway Design | Develop and Submit - Final Roadway Plans - R1 | N | 2023-04-04 08:00 | 2023-05-01 16:00 |  |  | 20 | 0 | 20 | 35 |  |  | DESIGN | DESIGN
D1570 | Not Started | I-275 - I-4 - FDOT - S2.3.11.19 | R1 Roadway Design | Review and Approve - Final Roadway Plans - R1 | N | 2023-05-02 08:00 | 2023-05-22 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | OWNER.Design Review | OWNER
D1610 | Not Started | I-275 - I-4 - FDOT - S2.3.11.19 | R1 Roadway Design | Develop and Submit - Sign & Seal Roadway Plans - R1 | N | 2023-05-23 08:00 | 2023-06-13 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | DESIGN | DESIGN
D1670 | Not Started | I-275 - I-4 - FDOT - S2.3.11.19 | R1 Roadway Design | Issue - RFC Roadway Plans - R1 | N | 2023-06-14 08:00 | 2023-06-20 16:00 |  |  | 5 | 0 | 5 | 35 |  |  | DESIGN | DESIGN
D1680 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-1 | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 31 |  | DESIGN | DESIGN
D1900 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-1 | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 31 |  | OWNER.Design Review | OWNER
D1990 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-1 | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 31 |  | DESIGN | DESIGN
D2130 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-1 | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 31 |  | OWNER.Design Review | OWNER
D1730 | Not Started | I-275 - I-4 - FDOT - S2.3.18.11 | Landscape/Irrigation Plans | Develop and Submit - 90% Landscape Plans | N | 2023-08-07 08:00 | 2023-10-02 16:00 |  |  | 40 | 0 | 40 | 3 | 4 |  | DESIGN | DESIGN
D1950 | Not Started | I-275 - I-4 - FDOT - S2.3.18.11 | Landscape/Irrigation Plans | Review and Approve - 90% Landscape Plans | N | 2023-10-03 08:00 | 2023-10-23 16:00 |  |  | 15 | 0 | 15 | 3 | 4 |  | OWNER.Design Review | OWNER
D2040 | Not Started | I-275 - I-4 - FDOT - S2.3.18.11 | Landscape/Irrigation Plans | Develop and Submit - Final Landscape Plans | N | 2023-10-24 08:00 | 2023-11-21 16:00 |  |  | 20 | 0 | 20 | 3 | 4 |  | DESIGN | DESIGN
D2180 | Not Started | I-275 - I-4 - FDOT - S2.3.18.11 | Landscape/Irrigation Plans | Review and Approve - Final Landscape Plans | N | 2023-11-22 08:00 | 2023-12-14 16:00 |  |  | 15 | 0 | 15 | 3 | 4 |  | OWNER.Design Review | OWNER
D1130 | Not Started | I-275 - I-4 - FDOT - S2.3.6.12 | Stormwater Pollution Prevention Plan (SWPPP) | Develop and Submit - SWPPP & NOI | N | 2023-02-02 08:00 | 2023-02-02 16:00 |  |  | 1 | 0 | 1 | 134 |  |  | PERMIT | PERMIT
D1140 | Not Started | I-275 - I-4 - FDOT - S2.3.6.12 | Stormwater Pollution Prevention Plan (SWPPP) | Review and Approve - SWPPP & NOI | N | 2023-02-03 08:00 | 2023-02-23 16:00 |  |  | 15 | 0 | 15 | 134 |  |  | 3rd PARTY | 3rd Party
D1250 | Not Started | I-275 - I-4 - FDOT - S2.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - 90% TTCP Plans - R1 Phase 2 & 3 | N | 2023-01-19 08:00 | 2023-03-15 16:00 |  |  | 40 | 0 | 40 | 23 |  |  | DESIGN | DESIGN
D1390 | Not Started | I-275 - I-4 - FDOT - S2.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Review and Approve - 90% TTCP Plans - R1 Phase 2 & 3 | N | 2023-03-16 08:00 | 2023-04-05 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D1410 | Not Started | I-275 - I-4 - FDOT - S2.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - Final TTCP Plans - R1 Phase 2 & 3 | N | 2023-04-06 08:00 | 2023-05-03 16:00 |  |  | 20 | 0 | 20 | 23 |  |  | DESIGN | DESIGN
D1470 | Not Started | I-275 - I-4 - FDOT - S2.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Review and Approve - Final TTCP Plans - R1 Phase 2 & 3 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D1510 | Not Started | I-275 - I-4 - FDOT - S2.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 & 3 | N | 2023-05-25 08:00 | 2023-06-15 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | DESIGN | DESIGN
D1580 | Not Started | I-275 - I-4 - FDOT - S2.3.11.5 | Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Issue - RFC TTCP Plans - R1 Phase 2 & 3 | N | 2023-06-16 08:00 | 2023-06-22 16:00 |  |  | 5 | 0 | 5 | 177 |  |  | DESIGN | DESIGN
D1420 | Not Started | I-275 - I-4 - FDOT - S2.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | N | 2023-01-19 08:00 | 2023-03-15 16:00 |  |  | 40 | 0 | 40 | 23 |  |  | DESIGN | DESIGN
D1550 | Not Started | I-275 - I-4 - FDOT - S2.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Review and Approve - 90% TTCP Plans - R2 Phase 1 | N | 2023-03-16 08:00 | 2023-04-05 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D1600 | Not Started | I-275 - I-4 - FDOT - S2.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - Final TTCP Plans - R2 Phase 1 | N | 2023-04-06 08:00 | 2023-05-03 16:00 |  |  | 20 | 0 | 20 | 23 |  |  | DESIGN | DESIGN
D1620 | Not Started | I-275 - I-4 - FDOT - S2.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Review and Approve - Final TTCP Plans - R2 Phase 1 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D1770 | Not Started | I-275 - I-4 - FDOT - S2.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | N | 2023-05-25 08:00 | 2023-06-15 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | DESIGN | DESIGN
D1830 | Not Started | I-275 - I-4 - FDOT - S2.3.12.3 | Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Issue - RFC TTCP Plans - R2 Phase 1 | N | 2023-06-16 08:00 | 2023-06-22 16:00 |  |  | 5 | 0 | 5 | 123 |  |  | DESIGN | DESIGN
D1910 | Not Started | I-275 - I-4 - FDOT - S2.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | N | 2023-03-16 08:00 | 2023-05-10 16:00 |  |  | 40 | 0 | 40 | 83 |  |  | DESIGN | DESIGN
D2190 | Not Started | I-275 - I-4 - FDOT - S2.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Review and Approve - 90% TTCP Plans - R2 Phase 2 | N | 2023-05-11 08:00 | 2023-06-01 16:00 |  |  | 15 | 0 | 15 | 83 |  |  | OWNER.Design Review | OWNER
D2260 | Not Started | I-275 - I-4 - FDOT - S2.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - Final TTCP Plans - R2 Phase 2 | N | 2023-06-02 08:00 | 2023-06-29 16:00 |  |  | 20 | 0 | 20 | 83 |  |  | DESIGN | DESIGN
D2400 | Not Started | I-275 - I-4 - FDOT - S2.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Review and Approve - Final TTCP Plans - R2 Phase 2 | N | 2023-06-30 08:00 | 2023-07-21 16:00 |  |  | 15 | 0 | 15 | 83 |  |  | OWNER.Design Review | OWNER
D2430 | Not Started | I-275 - I-4 - FDOT - S2.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 2 | N | 2023-07-24 08:00 | 2023-08-11 16:00 |  |  | 15 | 0 | 15 | 83 |  |  | DESIGN | DESIGN
D2460 | Not Started | I-275 - I-4 - FDOT - S2.3.12.2 | Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Issue - RFC TTCP Plans - R2 Phase 2 | N | 2023-08-14 08:00 | 2023-08-18 16:00 |  |  | 5 | 0 | 5 | 83 |  |  | DESIGN | DESIGN
D1260 | Not Started | I-275 - I-4 - FDOT - S2.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | N | 2022-12-19 08:00 | 2023-02-15 16:00 |  |  | 40 | 0 | 40 | 23 |  |  | DESIGN | DESIGN
D1400 | Not Started | I-275 - I-4 - FDOT - S2.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Review and Approve - 90% TTCP Plans - R1 Phase 1 | N | 2023-02-16 08:00 | 2023-03-08 16:00 |  |  | 15 | 0 | 15 | 66 |  |  | OWNER.Design Review | OWNER
D1430 | Not Started | I-275 - I-4 - FDOT - S2.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - Final TTCP Plans - R1 Phase 1 | N | 2023-03-09 08:00 | 2023-04-05 16:00 |  |  | 20 | 0 | 20 | 66 |  |  | DESIGN | DESIGN
D1480 | Not Started | I-275 - I-4 - FDOT - S2.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Review and Approve - Final TTCP Plans - R1 Phase 1 | N | 2023-04-06 08:00 | 2023-04-26 16:00 |  |  | 15 | 0 | 15 | 66 |  |  | OWNER.Design Review | OWNER
D1520 | Not Started | I-275 - I-4 - FDOT - S2.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 1 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 66 |  |  | DESIGN | DESIGN
D1590 | Not Started | I-275 - I-4 - FDOT - S2.3.11.3 | Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Issue - RFC TTCP Plans - R1 Phase 1 | N | 2023-05-18 08:00 | 2023-05-24 16:00 |  |  | 5 | 0 | 5 | 66 |  |  | DESIGN | DESIGN
D2050 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 08 Plans - R3 | N | 2023-07-17 08:00 | 2023-07-28 16:00 |  |  | 10 | 0 | 10 | 35 |  |  | DESIGN | DESIGN
D2080 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.2 | R3 Bridge 08 - Design Category 1 | Issue - RFC Cat1 Brg 08 Plans - R3 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 35 |  |  | DESIGN | DESIGN
D2210 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-1 | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 31 |  | DESIGN | DESIGN
D2310 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.3 | R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-1 | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 31 |  | DESIGN | DESIGN
D1840 | Not Started | I-275 - I-4 - FDOT - S2.3.18.2 | Temporary Retaining Wall Design | Develop and Submit - 90% Temporary Retaining Wall Plans | N | 2023-06-16 08:00 | 2023-08-11 16:00 |  |  | 40 | 0 | 40 | 23 |  |  | DESIGN | DESIGN
D2070 | Not Started | I-275 - I-4 - FDOT - S2.3.18.2 | Temporary Retaining Wall Design | Review and Approve - 90% Temporary Retaining Wall Plans | N | 2023-08-14 08:00 | 2023-09-01 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D2200 | Not Started | I-275 - I-4 - FDOT - S2.3.18.2 | Temporary Retaining Wall Design | Develop and Submit - Final Temporary Retaining Wall Plans | N | 2023-09-05 08:00 | 2023-10-02 16:00 |  |  | 20 | 0 | 20 | 23 |  |  | DESIGN | DESIGN
D2300 | Not Started | I-275 - I-4 - FDOT - S2.3.18.2 | Temporary Retaining Wall Design | Review and Approve - Final Temporary Retaining Wall Plans | N | 2023-10-03 08:00 | 2023-10-23 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | OWNER.Design Review | OWNER
D2410 | Not Started | I-275 - I-4 - FDOT - S2.3.18.2 | Temporary Retaining Wall Design | Develop and Submit - Sign & Seal Temporary Retaining Wall Plans | N | 2023-10-24 08:00 | 2023-11-14 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | DESIGN | DESIGN
P1060 | Not Started | I-275 - I-4 - FDOT - S2.4.1.3 | Settlement and Vibration Monitoring Plan | Develop and Submit - Settlement and Vibration Monitoring Plan | N | 2022-12-27 08:00 | 2023-01-25 16:00 |  |  | 20 | 0 | 20 | 74 |  |  | OFFICE | OFFICE
P1090 | Not Started | I-275 - I-4 - FDOT - S2.4.1.3 | Settlement and Vibration Monitoring Plan | Review and Comment - Settlement and Vibration Monitoring Plan | N | 2023-01-26 08:00 | 2023-02-15 16:00 |  |  | 15 | 0 | 15 | 74 |  |  | OWNER.Design Review | OWNER
P1120 | Not Started | I-275 - I-4 - FDOT - S2.4.1.3 | Settlement and Vibration Monitoring Plan | Revise and Resubmit - Settlement and Vibration Monitoring Plan | N | 2023-02-16 08:00 | 2023-02-22 16:00 |  |  | 5 | 0 | 5 | 74 |  |  | OFFICE | OFFICE
P1150 | Not Started | I-275 - I-4 - FDOT - S2.4.1.3 | Settlement and Vibration Monitoring Plan | Review and Approve - Settlement and Vibration Monitoring Plan | N | 2023-02-23 08:00 | 2023-03-15 16:00 |  |  | 15 | 0 | 15 | 74 |  |  | OWNER.Design Review | OWNER
D1310 | Not Started | I-275 - I-4 - FDOT - S2.3.5 | Erosion and Sediment Control Plan | Develop and Submit - Sign & Seal Erosion and Sediment Control Plan | N | 2023-04-06 08:00 | 2023-04-19 16:00 |  |  | 10 | 0 | 10 | 103 |  |  | DESIGN | DESIGN
D1330 | Not Started | I-275 - I-4 - FDOT - S2.3.5 | Erosion and Sediment Control Plan | Issue - RFC Erosion and Sediment Control Plan | N | 2023-04-20 08:00 | 2023-04-26 16:00 |  |  | 5 | 0 | 5 | 103 |  |  | DESIGN | DESIGN
D2060 | Not Started | I-275 - I-4 - FDOT - S2.3.18.12 | Maintenance of Communication (MoC) Plan | Develop and Submit- Sign & Seal MoC Plan | N | 2023-10-24 08:00 | 2023-11-14 16:00 |  |  | 15 | 0 | 15 | 23 |  |  | DESIGN | DESIGN
D1690 | Not Started | I-275 - I-4 - FDOT - S2.3.18.14 | ITS Plans | Develop and Submit - 90% ITS Plans | N | 2023-06-14 08:00 | 2023-08-09 16:00 |  |  | 40 | 0 | 40 | 40 |  |  | DESIGN | DESIGN
D1920 | Not Started | I-275 - I-4 - FDOT - S2.3.18.14 | ITS Plans | Review and Approve - 90% ITS Plans | N | 2023-08-10 08:00 | 2023-08-30 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D2000 | Not Started | I-275 - I-4 - FDOT - S2.3.18.14 | ITS Plans | Develop and Submit- Final ITS Plans | N | 2023-08-31 08:00 | 2023-09-28 16:00 |  |  | 20 | 0 | 20 | 40 |  |  | DESIGN | DESIGN
D2150 | Not Started | I-275 - I-4 - FDOT - S2.3.18.14 | ITS Plans | Review and Approve - Final ITS Plans | N | 2023-09-29 08:00 | 2023-10-19 16:00 |  |  | 15 | 0 | 15 | 40 |  |  | OWNER.Design Review | OWNER
D1100 | Not Started | I-275 - I-4 - FDOT - S2.3.9 | Geotechnical Investigations | Perform Geotechnical Investigations - Roadway | N | 2022-12-19 08:00 | 2023-01-18 16:00 |  |  | 20 | 0 | 20 | 2 | 2 |  | DESIGN | DESIGN
D2480 | Not Started | I-275 - I-4 - FDOT - S2.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | N | 2023-01-19 08:00 | 2023-03-15 16:00 |  |  | 40 | 0 | 40 | 43 |  |  | DESIGN | DESIGN
D2510 | Not Started | I-275 - I-4 - FDOT - S2.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Review and Approve - 90% TTCP Plans - R3 Phase 1 | N | 2023-03-16 08:00 | 2023-04-05 16:00 |  |  | 15 | 0 | 15 | 123 |  |  | OWNER.Design Review | OWNER
D2520 | Not Started | I-275 - I-4 - FDOT - S2.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - Final TTCP Plans - R3 Phase 1 | N | 2023-04-06 08:00 | 2023-05-03 16:00 |  |  | 20 | 0 | 20 | 123 |  |  | DESIGN | DESIGN
D2530 | Not Started | I-275 - I-4 - FDOT - S2.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Review and Approve - Final TTCP Plans - R3 Phase 1 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 123 |  |  | OWNER.Design Review | OWNER
D2540 | Not Started | I-275 - I-4 - FDOT - S2.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 1 | N | 2023-05-25 08:00 | 2023-06-15 16:00 |  |  | 15 | 0 | 15 | 123 |  |  | DESIGN | DESIGN
D2550 | Not Started | I-275 - I-4 - FDOT - S2.3.10.4 | Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Issue - RFC TTCP Plans - R3 Phase 1 | N | 2023-06-16 08:00 | 2023-06-22 16:00 |  |  | 5 | 0 | 5 | 123 |  |  | DESIGN | DESIGN
D1220 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | N | 2023-08-07 08:00 | 2023-10-30 16:00 |  |  | 60 | 0 | 60 | 12 | 14 |  | DESIGN | DESIGN
D1440 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | N | 2023-10-31 08:00 | 2023-11-30 16:00 |  |  | 20 | 0 | 20 | 13 | 14 |  | OWNER.Design Review | OWNER
D1450 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.1 | R3 Bridge 10 - Design Category 2 | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | N | 2023-10-31 08:00 | 2024-02-20 16:00 |  |  | 75 | 0 | 75 | 12 | 22 |  | DESIGN | DESIGN
P1200 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 1 - R1 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 85 |  |  | PROCURE | PROCUREMENT
D1050 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Develop and Submit - 60% Utility Relocation Plans | N | 2022-12-19 08:00 | 2023-01-10 16:00 |  |  | 15 | 0 | 15 | 24 | 8 |  | DESIGN | DESIGN
D1070 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Review and Approve - 60% Utility Relocation Plans | N | 2023-01-11 08:00 | 2023-02-01 16:00 |  |  | 15 | 0 | 15 | 24 | 8 |  | 3rd PARTY | 3rd Party
D1150 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Develop and Submit - 90% Utility Relocation Plans | N | 2023-02-02 08:00 | 2023-03-08 16:00 |  |  | 25 | 0 | 25 | 24 | 8 |  | DESIGN | DESIGN
D1240 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Review and Approve - 90% Utility Relocation Plans | N | 2023-03-09 08:00 | 2023-03-29 16:00 |  |  | 15 | 0 | 15 | 24 | 8 |  | 3rd PARTY | 3rd Party
D1300 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Develop and Submit - 100% Utility Relocation Plans | N | 2023-03-30 08:00 | 2023-04-05 16:00 |  |  | 5 | 0 | 5 | 24 | 8 |  | DESIGN | DESIGN
D1320 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Review and Approve - 100% Utility Relocation Plans | N | 2023-04-06 08:00 | 2023-04-26 16:00 |  |  | 15 | 0 | 15 | 24 | 8 |  | 3rd PARTY | 3rd Party
D1340 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Develop and Submit - Sign & Seal Utility Relocation Plans | N | 2023-04-27 08:00 | 2023-05-03 16:00 |  |  | 5 | 0 | 5 | 24 | 8 |  | DESIGN | DESIGN
D1370 | Not Started | I-275 - I-4 - FDOT - S2.3.25 | Utility Relocation Plans | Issue - RFC Utility Relocation Plans | N | 2023-05-04 08:00 | 2023-05-10 16:00 |  |  | 5 | 0 | 5 | 24 | 8 |  | DESIGN | DESIGN
A1010 | Not Started | I-275 - I-4 - FDOT - S2.2.1 | Mobilization | Install Erosion Control Devices | N | 2023-06-02 08:00 | 2023-06-15 16:00 |  |  | 10 | 0 | 10 | 67 |  | Sub - Erosion Control Crew | SUB.EROSION | EROSION
A1020 | Not Started | I-275 - I-4 - FDOT - S2.2.1 | Mobilization | Clear and Grub | N | 2023-06-16 08:00 | 2023-07-06 16:00 |  |  | 15 | 0 | 15 | 67 |  | Sub - Clearing & Grubbing Crew | SUB.EARTH.C&G | EARTH.Clear&Grub
A1030 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.1 | R1 - Ph0 - MOT | Install MOT - I-4 Exit Ramp - R1 - P0 | N | 2023-06-08 08:00 | 2023-06-08 16:00 |  |  | 1 | 0 | 1 | 76 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1040 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.1 | R1 - Ph0 - MOT | Shift Traffic - I-4 Exit 1 Ramp Right - R1 - P0 | N | 2023-06-09 08:00 | 2023-06-09 16:00 |  |  | 1 | 0 | 1 | 76 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1050 | Not Started | I-275 - I-4 - FDOT - S2.2.2.7 | R1 - Milestones | Start Construction - R1 | N | 2023-06-08 08:00 |  |  |  | 0 | 0 | 0 | 76 |  |  | MS | MS
A1060 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.3 | R1 - Ph0 - Traffic Shift | Shift Traffic - I-4 Exit 1 Ramp Left - R1 - P0 | N | 2023-08-01 08:00 | 2023-08-01 16:00 |  |  | 1 | 0 | 1 | 67 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1080 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.2 | R1 - Ph0 - Temp Pavement | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | N | 2023-06-23 08:00 | 2023-07-06 16:00 |  |  | 10 | 0 | 10 | 67 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.Small | EARTH.Excavate
A1090 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.2 | R1 - Ph0 - Temp Pavement | Place Stabilization - 13th Ave Temp Pav - R1 - P0 | N | 2023-07-07 08:00 | 2023-07-26 16:00 |  |  | 14 | 0 | 14 | 67 |  | Subgrade Stabilization Crew | LANE.EARTH.STAB | EARTH.Soil-Stab.Lime
A1100 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.2 | R1 - Ph0 - Temp Pavement | Place Asphalt - 13th Ave Temp Pav - R1 - P0 | N | 2023-07-28 08:00 | 2023-07-28 16:00 |  |  | 1 | 0 | 1 | 67 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A1110 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.2 | R1 - Ph0 - Temp Pavement | Temp Striping - 13th Ave Temp Pav - R1 - P0 | N | 2023-07-31 08:00 | 2023-07-31 16:00 |  |  | 1 | 0 | 1 | 67 |  | Sub - Striping Crew | SUB.STRIPE | STRIPE.Stripe - Temp
A1120 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp WE Left - R1 - P1.S1 | N | 2023-06-21 08:00 | 2023-06-21 16:00 |  |  | 1 | 0 | 1 | 56 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1130 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Install Temp Barrier - Ramp WE - R1 - P1.S1 | N | 2023-06-22 08:00 | 2023-06-22 16:00 |  |  | 1 | 0 | 1 | 56 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A1140 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp NE Left - R1 - P1.S1 | N | 2023-06-23 08:00 | 2023-06-23 16:00 |  |  | 1 | 0 | 1 | 105 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A1150 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.1 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Install Temp Barrier - Ramp NE - R1 - P1.S1 | N | 2023-06-26 08:00 | 2023-06-29 16:00 |  |  | 4 | 0 | 4 | 105 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A1630 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | N | 2023-06-30 08:00 | 2023-06-30 16:00 |  |  | 1 | 0 | 1 | 70 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A1650 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | N | 2023-07-03 08:00 | 2023-07-04 16:00 |  |  | 2 | 0 | 2 | 70 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A1660 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | FRP Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | N | 2023-07-11 08:00 | 2023-07-13 16:00 |  |  | 3 | 0 | 3 | 92 |  | Abutment Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Abutment
A1670 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Cure/Strip Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | N | 2023-07-14 08:00 | 2023-07-16 16:00 |  |  | 3 | 0 | 3 | 130 |  |  | CURE | CURE
A14670 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | N | 2023-07-05 08:00 | 2023-07-10 16:00 |  |  | 4 | 0 | 4 | 92 |  | MSE Wall Crew | LANE.STRUCTURE.Wall.MSE | STRUCTURE.Wall.MSE
A14680 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Temp Wall or SOE - Brg 100865 - End Bent 1 - R1 - P1.S1 | N | 2023-06-23 08:00 | 2023-06-29 16:00 |  |  | 5 | 0 | 5 | 70 |  | Structural Earthwork Crew | LANE.EARTH.STR | EARTH.STR Excavation
A14700 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-07-03 08:00 | 2023-07-03 16:00 |  |  | 1 | 0 | 1 | 71 |  | Structural Earthwork Crew | LANE.EARTH.STR | EARTH.STR Excavation
A14720 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-07-05 08:00 | 2023-07-12 16:00 |  |  | 6 | 0 | 6 | 70 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A14730 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-07-13 08:00 | 2023-07-17 16:00 |  |  | 3 | 0 | 3 | 70 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A14740 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-07-18 08:00 | 2023-07-24 16:00 |  |  | 7 | 0 | 7 | 98 |  |  | CURE | CURE
A14750 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Column - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-07-25 08:00 | 2023-07-27 16:00 |  |  | 3 | 0 | 3 | 70 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A14760 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Column - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-07-28 08:00 | 2023-08-03 16:00 |  |  | 7 | 0 | 7 | 98 |  |  | CURE | CURE
A14770 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-08-04 08:00 | 2023-08-10 16:00 |  |  | 5 | 0 | 5 | 70 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A14780 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.1 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | N | 2023-08-11 08:00 | 2023-08-17 16:00 |  |  | 7 | 0 | 7 | 98 |  |  | CURE | CURE
A14790 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | N | 2023-08-18 08:00 | 2023-08-24 16:00 |  |  | 5 | 0 | 5 | 70 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A14800 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install SIP - Brg 100865 - Span 1 - R1 - P1.S1 | N | 2023-08-25 08:00 | 2023-08-25 16:00 |  |  | 1 | 0 | 1 | 70 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A14810 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | N | 2023-08-28 08:00 | 2023-09-12 16:00 |  |  | 12 | 0 | 12 | 70 |  | Deck Crew | LANE.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.Overhang
A14940 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.5 | R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Cut/Fill to Grade - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | N | 2023-07-11 08:00 | 2023-07-18 16:00 |  |  | 6 | 0 | 6 | 110 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.Small | EARTH.Excavate
A15010 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | N | 2023-06-23 08:00 | 2023-07-18 16:00 |  |  | 18 | 0 | 18 | 56 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15050 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | N | 2023-07-21 08:00 | 2023-07-21 16:00 |  |  | 1 | 0 | 1 | 105 |  | Earthwork Grade Crew - Combo | LANE.EARTH.EW-ALL | EARTH.EW Balance
A15070 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.3 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | N | 2023-07-24 08:00 | 2023-07-25 16:00 |  |  | 2 | 0 | 2 | 105 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A15120 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-07-04 08:00 | 2023-07-04 16:00 |  |  | 1 | 0 | 1 | 81 |  | Structural Earthwork Crew | LANE.EARTH.STR | EARTH.STR Excavation
A15140 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-07-13 08:00 | 2023-07-20 16:00 |  |  | 6 | 0 | 6 | 75 |  | Pile Driving Crew | LANE.STRUCTURE.Pile | STRUCTURE.Pile
A15150 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-07-21 08:00 | 2023-07-25 16:00 |  |  | 3 | 0 | 3 | 75 |  | Footing Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Footing
A15160 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-07-26 08:00 | 2023-08-01 16:00 |  |  | 7 | 0 | 7 | 105 |  |  | CURE | CURE
A15170 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Column - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-08-02 08:00 | 2023-08-07 16:00 |  |  | 4 | 0 | 4 | 75 |  | Column Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Column
A15180 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Column - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-08-08 08:00 | 2023-08-14 16:00 |  |  | 7 | 0 | 7 | 105 |  |  | CURE | CURE
A15190 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-08-15 08:00 | 2023-08-21 16:00 |  |  | 5 | 0 | 5 | 75 |  | Cap Crew | LANE.STRUCTURE.Bridge.Substruct | STRUCTURE.Bridge.Cap
A15200 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.2 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | N | 2023-08-22 08:00 | 2023-08-28 16:00 |  |  | 7 | 0 | 7 | 105 |  |  | CURE | CURE
A15210 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | N | 2023-08-29 08:00 | 2023-09-04 16:00 |  |  | 5 | 0 | 5 | 75 |  | Erection Crew | LANE.STRUCTURE.Bridge.Beam | STRUCTURE.Bridge.Beam
A15230 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.4.4 | R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Install SIP - Brg 100865 - Span 2 - R1 - P1.S1 | N | 2023-09-05 08:00 | 2023-09-05 16:00 |  |  | 1 | 0 | 1 | 75 |  | Sub - Bridge SIP Sub Crew | SUB.STRUCTURE.Bridge.Deck | STRUCTURE.Bridge.SIP Forms
A15420 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | N | 2023-07-19 08:00 | 2023-08-11 16:00 |  |  | 18 | 0 | 18 | 56 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15430 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | N | 2023-09-07 08:00 | 2023-10-02 16:00 |  |  | 18 | 0 | 18 | 56 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15440 | Not Started | I-275 - I-4 - FDOT - S2.2.2.2.6 | R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | N | 2023-08-14 08:00 | 2023-09-06 16:00 |  |  | 18 | 0 | 18 | 56 |  | Storm Drain Crew | LANE.DRAIN.Pipe | DRAIN.Storm Drain
A15940 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.9 | R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Shift Traffic - 13th Ave Right - R1 - P1.S1 Step 1 | N | 2023-08-02 08:00 | 2023-08-02 16:00 |  |  | 1 | 0 | 1 | 67 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
A15950 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.9 | R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | N | 2023-08-03 08:00 | 2023-08-14 16:00 |  |  | 8 | 0 | 8 | 67 |  | Sub - TCPB - Barrier Installation Crew | SUB.TRAFFIC.PCB | TRAFFIC.Temp Barrier
A15960 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.4 | R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | N | 2023-08-15 08:00 | 2023-08-24 16:00 |  |  | 8 | 0 | 8 | 67 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.Small | EARTH.Excavate
A16080 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | N | 2023-08-25 08:00 | 2023-09-05 16:00 |  |  | 8 | 0 | 8 | 67 |  | Light Cut/Fill Earthwork Crew | LANE.EARTH.Small | EARTH.Excavate
A16090 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Stabilization - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | N | 2023-09-06 08:00 | 2023-09-06 16:00 |  |  | 1 | 0 | 1 | 67 |  | Subgrade Stabilization Crew | LANE.EARTH.STAB | EARTH.Soil-Stab.Lime
A16100 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place GAB - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | N | 2023-09-07 08:00 | 2023-09-07 16:00 |  |  | 1 | 0 | 1 | 67 |  | Agg Base Crew | LANE.EARTH.ABC | BASE.ABC
A16110 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Curb - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 67 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Conc Curb
A16130 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.7 | R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Asphalt Surface - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | N | 2023-09-15 08:00 | 2023-09-15 16:00 |  |  | 1 | 0 | 1 | 67 |  | Sub - Asphalt Paving Crew | SUB.ASPHALT | ASPHALT
A16270 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Place Brick Sidewalk - Left 14th & 15th St under I-4 - R1 - P1.S1 | N | 2023-06-28 08:00 | 2023-07-18 16:00 |  |  | 15 | 0 | 15 | 107 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A16250 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Left 14th &15th St under I-4 - R1 - P1.S1 | N | 2023-06-08 08:00 | 2023-06-09 16:00 |  |  | 2 | 0 | 2 | 107 |  | Demo Bridge Crew | LANE.STRUCTURE.Bridge.Demo Bridg | DEMO.Flatwork Demo
A16260 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Left 14th & 15th St under I-4 - R1 - P1.S1 | N | 2023-06-21 08:00 | 2023-06-27 16:00 |  |  | 5 | 0 | 5 | 107 |  | Sub - Concrete Flatwork Crew | SUB.FLATWRK | FLATWORK.Ditch Pave
A16280 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.2 | R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Const Gravity Wall - Left 14th & 15th St under I-4 - R1 - P1.S1 | N | 2023-06-12 08:00 | 2023-06-20 16:00 |  |  | 7 | 0 | 7 | 107 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A16290 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.11 | R1 - Ph1, Stg1 - 13th Ave - Finishes | Install Fencing - 13th Ave - R1 - P1.S1 | N | 2023-07-19 08:00 | 2023-07-21 16:00 |  |  | 3 | 0 | 3 | 107 |  | Sub - Fence Installation Crew | SUB.FENCE | FENCE
A18320 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Place Brick Sidewalk - Right 14th & 15th St under I-4 - R1 - P1.S1 | N | 2023-06-27 08:00 | 2023-07-17 16:00 |  |  | 15 | 0 | 15 | 108 |  | Concrete Flatwork Crew | LANE.CONC-MISC.Flatwork | FLATWORK.Sidewalk
A18290 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Right 14th &15th St under I-4 - R1 - P1.S1 | N | 2023-06-08 08:00 | 2023-06-08 16:00 |  |  | 1 | 0 | 1 | 108 |  | Demo Bridge Crew | LANE.STRUCTURE.Bridge.Demo Bridg | DEMO.Flatwork Demo
A18300 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Right 14th & 15th St under I-4 - R1 - P1.S1 | N | 2023-06-20 08:00 | 2023-06-26 16:00 |  |  | 5 | 0 | 5 | 108 |  | Sub - Concrete Flatwork Crew | SUB.FLATWRK | FLATWORK.Ditch Pave
A18310 | Not Started | I-275 - I-4 - FDOT - S2.2.2.12.5 | R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Const Gravity Wall - Right 14th & 15th St under I-4 - R1 - P1.S1 | N | 2023-06-09 08:00 | 2023-06-19 16:00 |  |  | 7 | 0 | 7 | 108 |  | Sub - Concrete Barrier - Slip Crew | SUB.BARRIER | Concrete Barrier
A18330 | Not Started | I-275 - I-4 - FDOT - S2.2.2.1.2 | R1 - Ph0 - Temp Pavement | Place GAB - 13th Ave Temp Pav - R1 - P0 | N | 2023-07-27 08:00 | 2023-07-27 16:00 |  |  | 1 | 0 | 1 | 67 |  | Agg Base Crew | LANE.EARTH.ABC | BASE.ABC
A26350 | Not Started | I-275 - I-4 - FDOT - S2.2.5.7 | R3 - Milestones | Start Construction - R3 | N | 2023-06-12 08:00 |  |  |  | 0 | 0 | 0 | 13 | 6 |  | MS | MS
D2560 | Not Started | I-275 - I-4 - FDOT - S2.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | N | 2023-03-16 08:00 | 2023-05-10 16:00 |  |  | 40 | 0 | 40 | 43 |  |  | DESIGN | DESIGN
D2570 | Not Started | I-275 - I-4 - FDOT - S2.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Review and Approve - 90% TTCP Plans - R3 Phase 2 | N | 2023-05-11 08:00 | 2023-06-01 16:00 |  |  | 15 | 0 | 15 | 83 |  |  | OWNER.Design Review | OWNER
D2580 | Not Started | I-275 - I-4 - FDOT - S2.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - Final TTCP Plans - R3 Phase 2 | N | 2023-06-02 08:00 | 2023-06-29 16:00 |  |  | 20 | 0 | 20 | 83 |  |  | DESIGN | DESIGN
D2590 | Not Started | I-275 - I-4 - FDOT - S2.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Review and Approve - Final TTCP Plans - R3 Phase 2 | N | 2023-06-30 08:00 | 2023-07-21 16:00 |  |  | 15 | 0 | 15 | 83 |  |  | OWNER.Design Review | OWNER
D2600 | Not Started | I-275 - I-4 - FDOT - S2.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 2 | N | 2023-07-24 08:00 | 2023-08-11 16:00 |  |  | 15 | 0 | 15 | 83 |  |  | DESIGN | DESIGN
D2610 | Not Started | I-275 - I-4 - FDOT - S2.3.10.6 | Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Issue - RFC TTCP Plans - R3 Phase 2 | N | 2023-08-14 08:00 | 2023-08-18 16:00 |  |  | 5 | 0 | 5 | 83 |  |  | DESIGN | DESIGN
D2620 | Not Started | I-275 - I-4 - FDOT - S2.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | N | 2023-05-11 08:00 | 2023-07-07 16:00 |  |  | 40 | 0 | 40 | 43 |  |  | DESIGN | DESIGN
D2630 | Not Started | I-275 - I-4 - FDOT - S2.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Review and Approve - 90% TTCP Plans - R3 Phase 3 & 4 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 43 |  |  | OWNER.Design Review | OWNER
D2640 | Not Started | I-275 - I-4 - FDOT - S2.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - Final TTCP Plans - R3 Phase 3 & 4 | N | 2023-07-31 08:00 | 2023-08-25 16:00 |  |  | 20 | 0 | 20 | 43 |  |  | DESIGN | DESIGN
D2650 | Not Started | I-275 - I-4 - FDOT - S2.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Review and Approve - Final TTCP Plans - R3 Phase 3 & 4 | N | 2023-08-28 08:00 | 2023-09-18 16:00 |  |  | 15 | 0 | 15 | 43 |  |  | OWNER.Design Review | OWNER
D2660 | Not Started | I-275 - I-4 - FDOT - S2.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 3 & 4 | N | 2023-09-19 08:00 | 2023-10-09 16:00 |  |  | 15 | 0 | 15 | 43 |  |  | DESIGN | DESIGN
D2670 | Not Started | I-275 - I-4 - FDOT - S2.3.10.7 | Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Issue - RFC TTCP Plans - R3 Phase 3 & 4 | N | 2023-10-10 08:00 | 2023-10-16 16:00 |  |  | 5 | 0 | 5 | 43 |  |  | DESIGN | DESIGN
D2680 | Not Started | I-275 - I-4 - FDOT - S2.3.12.10 | R2 Roadway Plans | Develop and Submit - 90% Roadway Plans - R2 | N | 2022-12-19 08:00 | 2023-04-26 16:00 |  |  | 90 | 0 | 90 | 3 | 3 |  | DESIGN | DESIGN
D2690 | Not Started | I-275 - I-4 - FDOT - S2.3.12.10 | R2 Roadway Plans | Review and Approve - 90% Roadway Plans - R2 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 3 | 3 |  | OWNER.Design Review | OWNER
D2700 | Not Started | I-275 - I-4 - FDOT - S2.3.12.10 | R2 Roadway Plans | Develop and Submit - Final Roadway Plans - R2 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 3 | 3 |  | DESIGN | DESIGN
D2710 | Not Started | I-275 - I-4 - FDOT - S2.3.12.10 | R2 Roadway Plans | Review and Approve - Final Roadway Plans - R2 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 3 | 3 |  | OWNER.Design Review | OWNER
D2720 | Not Started | I-275 - I-4 - FDOT - S2.3.12.10 | R2 Roadway Plans | Develop and Submit - Sign & Seal Roadway Plans - R2 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 3 | 3 |  | DESIGN | DESIGN
D2730 | Not Started | I-275 - I-4 - FDOT - S2.3.12.10 | R2 Roadway Plans | Issue - RFC Roadway Plans - R2 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 3 | 3 |  | DESIGN | DESIGN
D2740 | Not Started | I-275 - I-4 - FDOT - S2.3.10.24 | R3 Roadway Design | Develop and Submit - 90% Roadway Plans - R3 | Y | 2022-12-19 08:00 | 2023-04-26 16:00 |  |  | 90 | 0 | 90 | 0 | 1 |  | DESIGN | DESIGN
D2750 | Not Started | I-275 - I-4 - FDOT - S2.3.10.24 | R3 Roadway Design | Review and Approve - 90% Roadway Plans - R3 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 93 |  |  | OWNER.Design Review | OWNER
D2760 | Not Started | I-275 - I-4 - FDOT - S2.3.10.24 | R3 Roadway Design | Develop and Submit - Final Roadway Plans - R3 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 93 |  |  | DESIGN | DESIGN
D2770 | Not Started | I-275 - I-4 - FDOT - S2.3.10.24 | R3 Roadway Design | Review and Approve - Final Roadway Plans - R3 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 93 |  |  | OWNER.Design Review | OWNER
D2780 | Not Started | I-275 - I-4 - FDOT - S2.3.10.24 | R3 Roadway Design | Develop and Submit - Sign & Seal Roadway Plans - R3 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 93 |  |  | DESIGN | DESIGN
D2790 | Not Started | I-275 - I-4 - FDOT - S2.3.10.24 | R3 Roadway Design | Issue - RFC Roadway Plans - R3 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 93 |  |  | DESIGN | DESIGN
D2800 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.6 | R1 Bridge 03 Design Category 1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | N | 2023-03-23 08:00 | 2023-06-15 16:00 |  |  | 60 | 0 | 60 | 105 |  |  | DESIGN | DESIGN
D2810 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.6 | R1 Bridge 03 Design Category 1 | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 113 |  |  | OWNER.Design Review | OWNER
D2860 | Completed | I-275 - I-4 - FDOT - S2.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | N | 2022-08-01 08:00 | 2022-11-07 16:00 | 2022-08-01 08:00 | 2022-11-07 16:00 | 60 | 70 | 0 |  |  |  | DESIGN | DESIGN
D2870 | In Progress | I-275 - I-4 - FDOT - S2.3.11.4.2 | R1 Bridge 02 Design Category 2 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | N | 2022-11-08 08:00 | 2022-12-23 16:00 | 2022-11-08 08:00 |  | 30 | 26 | 5 | 74 |  |  | OWNER.Design Review | OWNER
D2880 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | N | 2023-02-09 08:00 | 2023-05-24 16:00 |  |  | 75 | 0 | 75 | 63 |  |  | DESIGN | DESIGN
D2890 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.2 | R1 Bridge 02 Design Category 2 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | N | 2023-05-25 08:00 | 2023-08-18 16:00 |  |  | 60 | 0 | 60 | 63 |  |  | OWNER.Design Review | OWNER
D2900 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.2 | R1 Bridge 02 Design Category 2 | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | N | 2023-08-21 08:00 | 2023-09-18 16:00 |  |  | 20 | 0 | 20 | 63 |  |  | DESIGN | DESIGN
A36000 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-9 - R3 | N | 2023-06-12 08:00 | 2023-06-30 16:00 |  |  | 15 | 0 | 15 | 13 | 6 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36010 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-6 - R3 | N | 2023-08-21 08:00 | 2023-09-08 16:00 |  |  | 15 | 0 | 15 | 42 |  | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36020 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-5 - R3 | N | 2023-10-03 08:00 | 2023-10-23 16:00 |  |  | 15 | 0 | 15 | 26 |  | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36030 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-4 - R3 | N | 2023-10-27 08:00 | 2023-11-16 16:00 |  |  | 15 | 0 | 15 | 23 |  | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
D1230 | In Progress | I-275 - I-4 - FDOT - S2.3.1.1 | Design Quality Management Plan | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | N | 2022-10-17 08:00 | 2023-09-14 16:00 | 2022-10-17 08:00 |  | 230 | 42 | 188 | 65 |  |  | DESIGN | DESIGN
P1430 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 08 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 85 |  |  | PROCURE | PROCUREMENT
D3180 | In Progress | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Develop and Submit - 60% - 60" Drainage System - R3 | N | 2022-11-01 08:00 | 2023-01-11 16:00 | 2022-11-01 08:00 |  | 15 | 31 | 16 | 13 | 6 |  | DESIGN | DESIGN
D3190 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Review and Approve - 60% - 60" Drainage System - R3 | N | 2023-01-12 08:00 | 2023-02-23 16:00 |  |  | 30 | 0 | 30 | 13 | 6 |  | OWNER.Design Review | OWNER
D3200 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Develop and Submit - 90% - 60" Drainage System - R3 | N | 2023-01-12 08:00 | 2023-02-23 16:00 |  |  | 30 | 0 | 30 | 13 | 7 |  | DESIGN | DESIGN
D3210 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Review and Approve - 90% - 60" Drainage System - R3 | N | 2023-02-24 08:00 | 2023-04-06 16:00 |  |  | 30 | 0 | 30 | 13 | 6 |  | OWNER.Design Review | OWNER
D3220 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Develop and Submit - Final - 60" Drainage System - R3 | N | 2023-04-07 08:00 | 2023-04-27 16:00 |  |  | 15 | 0 | 15 | 13 | 6 |  | DESIGN | DESIGN
D3230 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Review and Approve - Final - 60" Drainage System - R3 | N | 2023-04-28 08:00 | 2023-05-18 16:00 |  |  | 15 | 0 | 15 | 13 | 6 |  | OWNER.Design Review | OWNER
D3240 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Develop and Submit - Sign & Seal - 60" Drainage System - R3 | N | 2023-05-19 08:00 | 2023-06-02 16:00 |  |  | 10 | 0 | 10 | 13 | 6 |  | DESIGN | DESIGN
D3250 | Not Started | I-275 - I-4 - FDOT - S2.3.10.3 | R3 60" Drainage System Design | Issue - RFC - 60" Drainage System - R3 | N | 2023-06-05 08:00 | 2023-06-09 16:00 |  |  | 5 | 0 | 5 | 13 | 6 |  | DESIGN | DESIGN
D3260 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.1 | R1 Bridge 01 Design Category 1 | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | N | 2023-02-09 08:00 | 2023-05-03 16:00 |  |  | 60 | 0 | 60 | 35 |  |  | DESIGN | DESIGN
D3270 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.1 | R1 Bridge 01 Design Category 1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | OWNER.Design Review | OWNER
D3280 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.1 | R1 Bridge 01 Design Category 1 | Develop and Submit - Final Cat1 Brg 01 Plans - R1 | N | 2023-05-25 08:00 | 2023-06-22 16:00 |  |  | 20 | 0 | 20 | 35 |  |  | DESIGN | DESIGN
D3290 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.1 | R1 Bridge 01 Design Category 1 | Review and Approve - Final Cat1 Brg 01 Plans - R1 | N | 2023-06-23 08:00 | 2023-07-14 16:00 |  |  | 15 | 0 | 15 | 35 |  |  | OWNER.Design Review | OWNER
D3300 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.1 | R1 Bridge 01 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 01 Plans - R1 | N | 2023-07-17 08:00 | 2023-07-28 16:00 |  |  | 10 | 0 | 10 | 35 |  |  | DESIGN | DESIGN
D3310 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.1 | R1 Bridge 01 Design Category 1 | Issue - RFC Cat1 Brg 01 Plans - R1 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 35 |  |  | DESIGN | DESIGN
D3380 | Completed | I-275 - I-4 - FDOT - S2.3.11.4.3 | R1 Bridge 05 Design Category 1 | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | N | 2022-09-09 08:00 | 2022-12-05 16:00 | 2022-09-09 08:00 | 2022-12-05 16:00 | 60 | 59 | 0 |  |  |  | DESIGN | DESIGN
D3390 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.3 | R1 Bridge 05 Design Category 1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | N | 2022-12-19 08:00 | 2023-01-10 16:00 |  |  | 15 | 0 | 15 | 105 |  |  | OWNER.Design Review | OWNER
D3400 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.3 | R1 Bridge 05 Design Category 1 | Develop and Submit - Final Cat1 Brg 05 Plans - R1 | N | 2023-01-11 08:00 | 2023-02-08 16:00 |  |  | 20 | 0 | 20 | 105 |  |  | DESIGN | DESIGN
D3410 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.3 | R1 Bridge 05 Design Category 1 | Review and Approve - Final Cat1 Brg 05 Plans - R1 | N | 2023-02-09 08:00 | 2023-03-01 16:00 |  |  | 15 | 0 | 15 | 105 |  |  | OWNER.Design Review | OWNER
D3420 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.3 | R1 Bridge 05 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 05 Plans - R1 | N | 2023-03-02 08:00 | 2023-03-15 16:00 |  |  | 10 | 0 | 10 | 105 |  |  | DESIGN | DESIGN
D3430 | Not Started | I-275 - I-4 - FDOT - S2.3.11.4.3 | R1 Bridge 05 Design Category 1 | Issue - RFC Cat1 Brg 05 Plans - R1 | N | 2023-03-16 08:00 | 2023-03-22 16:00 |  |  | 5 | 0 | 5 | 105 |  |  | DESIGN | DESIGN
D3500 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | N | 2023-02-09 08:00 | 2023-05-03 16:00 |  |  | 60 | 0 | 60 | 12 | 14 |  | DESIGN | DESIGN
D3510 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 12 | 14 |  | OWNER.Design Review | OWNER
D3520 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Develop and Submit - Final Cat1 Brg 09 Plans - R3 | N | 2023-05-25 08:00 | 2023-06-22 16:00 |  |  | 20 | 0 | 20 | 12 | 14 |  | DESIGN | DESIGN
D3530 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Review and Approve - Final Cat1 Brg 09 Plans - R3 | N | 2023-06-23 08:00 | 2023-07-14 16:00 |  |  | 15 | 0 | 15 | 12 | 14 |  | OWNER.Design Review | OWNER
D3540 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 09 Plans - R3 | N | 2023-07-17 08:00 | 2023-07-28 16:00 |  |  | 10 | 0 | 10 | 12 | 14 |  | DESIGN | DESIGN
D3550 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.3 | R3 Bridge 09 - Design Category 1 | Issue - RFC Cat1 Brg 09 Plans - R3 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 12 | 14 |  | DESIGN | DESIGN
D3620 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.5 | R3 Bridge 11 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | N | 2023-08-07 08:00 | 2023-10-30 16:00 |  |  | 60 | 0 | 60 | 18 | 49 |  | DESIGN | DESIGN
D3630 | Not Started | I-275 - I-4 - FDOT - S2.3.10.5.5 | R3 Bridge 11 - Design Category 1 | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | N | 2023-10-31 08:00 | 2023-11-21 16:00 |  |  | 15 | 0 | 15 | 18 | 49 |  | OWNER.Design Review | OWNER
D3680 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 24 |  | DESIGN | DESIGN
D3690 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 24 |  | OWNER.Design Review | OWNER
D3700 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 24 |  | DESIGN | DESIGN
D3710 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 24 |  | OWNER.Design Review | OWNER
D3720 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-2 - Ramp NE / Br 1 | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 24 |  | DESIGN | DESIGN
D3730 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.1 | R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 24 |  | DESIGN | DESIGN
D3740 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 25 |  | DESIGN | DESIGN
D3750 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 25 |  | OWNER.Design Review | OWNER
D3760 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Final MSE Wall RW 2-1 - Br 2 | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 25 |  | DESIGN | DESIGN
D3770 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - Final MSE Wall RW 2-1 - Br 2 | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 25 |  | OWNER.Design Review | OWNER
D3780 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-1 - Br 2 | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 25 |  | DESIGN | DESIGN
D3790 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.2 | R1 - Retaining Wall Design RW 2-1 - Br 2 | Issue - RFC MSE Wall RW 2-1 - Br 2 | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 25 |  | DESIGN | DESIGN
D3800 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 26 |  | DESIGN | DESIGN
D3810 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 26 |  | OWNER.Design Review | OWNER
D3820 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 26 |  | DESIGN | DESIGN
D3830 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 26 |  | OWNER.Design Review | OWNER
D3840 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Sign & Seal MSE Wall RW 2-2 Ramp NE 126 to 130 LT | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 26 |  | DESIGN | DESIGN
D3850 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.4 | R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 26 |  | DESIGN | DESIGN
D3860 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 27 |  | DESIGN | DESIGN
D3870 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 27 |  | OWNER.Design Review | OWNER
D3880 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 27 |  | DESIGN | DESIGN
D3890 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 27 |  | OWNER.Design Review | OWNER
D3900 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Sign & Seal MSE Wall RW 2-3 Ramp NE 125 to 130 RT | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 27 |  | DESIGN | DESIGN
D3910 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.5 | R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 27 |  | DESIGN | DESIGN
D3980 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 28 |  | DESIGN | DESIGN
D3990 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 28 |  | OWNER.Design Review | OWNER
D4000 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Final MSE Wall RW 2-4 Br 2 | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 28 |  | DESIGN | DESIGN
D4010 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - Final MSE Wall RW 2-4 Br 2 | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 28 |  | OWNER.Design Review | OWNER
D4020 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-4 Br 2 | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 28 |  | DESIGN | DESIGN
D4030 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.7 | R1 - Retaining Wall Design RW 2-4 Br 2 | Issue - RFC MSE Wall RW 2-4 Br 2 | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 28 |  | DESIGN | DESIGN
D4040 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | N | 2023-03-23 08:00 | 2023-05-30 16:00 |  |  | 48 | 0 | 48 | 105 |  |  | DESIGN | DESIGN
D4050 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | N | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 105 |  |  | OWNER.Design Review | OWNER
D4060 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.8 | R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | N | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 105 |  |  | DESIGN | DESIGN
D4100 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | N | 2023-03-23 08:00 | 2023-05-30 16:00 |  |  | 48 | 0 | 48 | 105 |  |  | DESIGN | DESIGN
D4110 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | N | 2023-05-31 08:00 | 2023-06-20 16:00 |  |  | 15 | 0 | 15 | 105 |  |  | OWNER.Design Review | OWNER
D4120 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.9 | R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | N | 2023-06-21 08:00 | 2023-07-19 16:00 |  |  | 20 | 0 | 20 | 105 |  |  | DESIGN | DESIGN
D4280 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 29 |  | DESIGN | DESIGN
D4290 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 29 |  | OWNER.Design Review | OWNER
D4300 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 29 |  | DESIGN | DESIGN
D4310 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 29 |  | OWNER.Design Review | OWNER
D4320 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-1 Ramp WE-B / Br 5 | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 29 |  | DESIGN | DESIGN
D4330 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.12 | R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 29 |  | DESIGN | DESIGN
D4340 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | N | 2023-02-16 08:00 | 2023-04-24 16:00 |  |  | 48 | 0 | 48 | 12 | 30 |  | DESIGN | DESIGN
D4350 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | N | 2023-04-25 08:00 | 2023-05-15 16:00 |  |  | 15 | 0 | 15 | 12 | 30 |  | OWNER.Design Review | OWNER
D4360 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | N | 2023-05-16 08:00 | 2023-06-13 16:00 |  |  | 20 | 0 | 20 | 12 | 30 |  | DESIGN | DESIGN
D4370 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | N | 2023-06-14 08:00 | 2023-07-05 16:00 |  |  | 15 | 0 | 15 | 12 | 30 |  | OWNER.Design Review | OWNER
D4380 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-2 Ramp WE-B / Br 5 | N | 2023-07-06 08:00 | 2023-07-26 16:00 |  |  | 15 | 0 | 15 | 12 | 30 |  | DESIGN | DESIGN
D4390 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.13 | R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | N | 2023-07-27 08:00 | 2023-08-02 16:00 |  |  | 5 | 0 | 5 | 12 | 30 |  | DESIGN | DESIGN
D4400 | Not Started | I-275 - I-4 - FDOT - S2.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Y | 2023-08-07 08:00 | 2023-10-12 16:00 |  |  | 48 | 0 | 48 | 0 | 1 |  | DESIGN | DESIGN
D4410 | Not Started | I-275 - I-4 - FDOT - S2.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | N | 2023-10-13 08:00 | 2023-11-02 16:00 |  |  | 15 | 0 | 15 | 10 | 5 |  | OWNER.Design Review | OWNER
D4420 | Not Started | I-275 - I-4 - FDOT - S2.3.12.1.12 | R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | N | 2023-11-03 08:00 | 2023-12-05 16:00 |  |  | 20 | 0 | 20 | 10 | 5 |  | DESIGN | DESIGN
D4460 | Not Started | I-275 - I-4 - FDOT - S2.3.12.1.1 | R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Y | 2023-10-13 08:00 | 2023-12-19 16:00 |  |  | 45 | 0 | 45 | 0 | 1 |  | DESIGN | DESIGN
D4520 | Not Started | I-275 - I-4 - FDOT - S2.3.12.1.2 | R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | Y | 2023-10-13 08:00 | 2023-12-19 16:00 |  |  | 45 | 0 | 45 | 0 | 1 |  | DESIGN | DESIGN
D4580 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | N | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 10 | 15 |  | DESIGN | DESIGN
D4590 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 10 | 15 |  | OWNER.Design Review | OWNER
D4600 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-1 Ramp B / Br 8 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 10 | 15 |  | DESIGN | DESIGN
D4610 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-1 Ramp B / Br 8 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 10 | 15 |  | OWNER.Design Review | OWNER
D4620 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-1 Ramp B / Br 8 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 10 | 15 |  | DESIGN | DESIGN
D4630 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.1 | R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 10 | 15 |  | DESIGN | DESIGN
D4640 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | N | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 10 | 16 |  | DESIGN | DESIGN
D4650 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 10 | 16 |  | OWNER.Design Review | OWNER
D4660 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-2 Ramp B / Br 8 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 10 | 16 |  | DESIGN | DESIGN
D4670 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-2 Ramp B / Br 8 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 10 | 16 |  | OWNER.Design Review | OWNER
D4680 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-2 Ramp B / Br 8 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 10 | 16 |  | DESIGN | DESIGN
D4690 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.2 | R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 10 | 16 |  | DESIGN | DESIGN
D4700 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | N | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 10 | 17 |  | DESIGN | DESIGN
D4710 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 10 | 17 |  | OWNER.Design Review | OWNER
D4720 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - Final MSE Wall RW 9-1 Ramp B/F / Br 8 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 10 | 17 |  | DESIGN | DESIGN
D4730 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Review and Approve - Final MSE Wall RW 9-1 Ramp B/F / Br 8 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 10 | 17 |  | OWNER.Design Review | OWNER
D4740 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 9-1 Ramp B/F / Br 8 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 10 | 17 |  | DESIGN | DESIGN
D4750 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.3 | R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 8 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 10 | 17 |  | DESIGN | DESIGN
D4760 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | N | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 10 | 18 |  | DESIGN | DESIGN
D4770 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 10 | 18 |  | OWNER.Design Review | OWNER
D4780 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 10 | 18 |  | DESIGN | DESIGN
D4790 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 10 | 18 |  | OWNER.Design Review | OWNER
D4800 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-2 Ramp B/F / Br 9 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 10 | 18 |  | DESIGN | DESIGN
D4810 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.4 | R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 10 | 18 |  | DESIGN | DESIGN
D4820 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | N | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 10 | 19 |  | DESIGN | DESIGN
D4830 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 10 | 19 |  | OWNER.Design Review | OWNER
D4840 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 10 | 19 |  | DESIGN | DESIGN
D4850 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 10 | 19 |  | OWNER.Design Review | OWNER
D4860 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-3 Ramp B/F / Br 9 | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 10 | 19 |  | DESIGN | DESIGN
D4870 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.5 | R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 10 | 19 |  | DESIGN | DESIGN
D4880 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Y | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 0 | 1 |  | DESIGN | DESIGN
D4890 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Y | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 0 | 1 |  | OWNER.Design Review | OWNER
D4900 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | Y | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 0 | 1 |  | DESIGN | DESIGN
D4910 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | Y | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 0 | 1 |  | OWNER.Design Review | OWNER
D4920 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Sign & Seal MSE Wall RW 100 I-4 EB (Br 3 & 4) | Y | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 0 | 1 |  | DESIGN | DESIGN
D4930 | Not Started | I-275 - I-4 - FDOT - S2.3.11.1.6 | R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | Y | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 0 | 1 |  | DESIGN | DESIGN
D4940 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% MSE Wall RW 102 Ramp C | N | 2023-02-20 08:00 | 2023-04-26 16:00 |  |  | 48 | 0 | 48 | 10 | 21 |  | DESIGN | DESIGN
D4950 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | N | 2023-04-27 08:00 | 2023-05-17 16:00 |  |  | 15 | 0 | 15 | 10 | 21 |  | OWNER.Design Review | OWNER
D4960 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Final MSE Wall RW 102 Ramp C | N | 2023-05-18 08:00 | 2023-06-15 16:00 |  |  | 20 | 0 | 20 | 10 | 21 |  | DESIGN | DESIGN
D4970 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - Final MSE Wall RW 102 Ramp C | N | 2023-06-16 08:00 | 2023-07-07 16:00 |  |  | 15 | 0 | 15 | 10 | 21 |  | OWNER.Design Review | OWNER
D4980 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Sign & Seal MSE Wall RW 102 Ramp C | N | 2023-07-10 08:00 | 2023-07-28 16:00 |  |  | 15 | 0 | 15 | 10 | 21 |  | DESIGN | DESIGN
D4990 | Not Started | I-275 - I-4 - FDOT - S2.3.10.1.7 | R3 - Retaining Wall Design RW 102 Ramp C | Issue - RFC MSE Wall RW 102 Ramp C | N | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 10 | 21 |  | DESIGN | DESIGN
SD1000 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 31 |  | OFFICE | OFFICE
SD1010 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 31 |  | DESIGN | DESIGN
SD1020 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 31 |  | OFFICE | OFFICE
SD1030 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 31 |  | DESIGN | DESIGN
SD1040 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.3 | R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-1 Ramp NE / Br 1 | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 31 |  | OWNER.Shp Drwg Review | OWNER
SD1050 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 24 |  | OFFICE | OFFICE
SD1060 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 24 |  | DESIGN | DESIGN
SD1070 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 24 |  | OFFICE | OFFICE
SD1080 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 24 |  | DESIGN | DESIGN
SD1090 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.1 | R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-2 Ramp NE / Br 1 | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 24 |  | OWNER.Shp Drwg Review | OWNER
SD1100 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Develop & Submit Shp Drwgs - RW 2-1 Br 2 | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 25 |  | OFFICE | OFFICE
SD1110 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-1 Br 2 | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 25 |  | DESIGN | DESIGN
SD1120 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Revise & Resubmit Shp Drwgs - RW 2-1 Br 2 | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 25 |  | OFFICE | OFFICE
SD1130 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-1 Br 2 | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 25 |  | DESIGN | DESIGN
SD1140 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.2 | R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-1 Br 2 | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 25 |  | OWNER.Shp Drwg Review | OWNER
SD1150 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Develop & Submit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 26 |  | OFFICE | OFFICE
SD1160 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Designer Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 26 |  | DESIGN | DESIGN
SD1170 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Revise & Resubmit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 26 |  | OFFICE | OFFICE
SD1180 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Design 2nd Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 26 |  | DESIGN | DESIGN
SD1190 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.4 | R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | FDOT - Review & Comment Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 26 |  | OWNER.Shp Drwg Review | OWNER
SD1200 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Develop & Submit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 27 |  | OFFICE | OFFICE
SD1210 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Designer Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 27 |  | DESIGN | DESIGN
SD1220 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Revise & Resubmit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 27 |  | OFFICE | OFFICE
SD1230 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Design 2nd Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 27 |  | DESIGN | DESIGN
SD1240 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.5 | R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | FDOT - Review & Comment Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 27 |  | OWNER.Shp Drwg Review | OWNER
SD1250 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Develop & Submit Shp Drwgs - RW 2-4 Br 2 | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 28 |  | OFFICE | OFFICE
SD1260 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-4 Br 2 | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 28 |  | DESIGN | DESIGN
SD1270 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-4 Br 2 | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 28 |  | OFFICE | OFFICE
SD1280 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-4 Br 2 | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 28 |  | DESIGN | DESIGN
SD1290 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.7 | R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-4 Br 2 | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 28 |  | OWNER.Shp Drwg Review | OWNER
SD1500 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 29 |  | OFFICE | OFFICE
SD1510 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 29 |  | DESIGN | DESIGN
SD1520 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 29 |  | OFFICE | OFFICE
SD1530 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 29 |  | DESIGN | DESIGN
SD1540 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.12 | R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 29 |  | OWNER.Shp Drwg Review | OWNER
SD1550 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | N | 2023-08-03 08:00 | 2023-08-16 16:00 |  |  | 10 | 0 | 10 | 12 | 30 |  | OFFICE | OFFICE
SD1560 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | N | 2023-08-17 08:00 | 2023-09-07 16:00 |  |  | 15 | 0 | 15 | 12 | 30 |  | DESIGN | DESIGN
SD1570 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | N | 2023-09-08 08:00 | 2023-09-14 16:00 |  |  | 5 | 0 | 5 | 12 | 30 |  | OFFICE | OFFICE
SD1580 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | N | 2023-09-15 08:00 | 2023-09-21 16:00 |  |  | 5 | 0 | 5 | 12 | 30 |  | DESIGN | DESIGN
SD1590 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.13 | R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | N | 2023-09-22 08:00 | 2023-10-12 16:00 |  |  | 15 | 0 | 15 | 12 | 30 |  | OWNER.Shp Drwg Review | OWNER
PC1000 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.1 | R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 24 |  | PROCURE | PROCUREMENT
PC1010 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.2 | R1 Procurement - Retaining Wall RW 2-1 - Br 2 | Fab & Deliver - RW 2-1 - Br 2 | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 25 |  | PROCURE | PROCUREMENT
PC1020 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.4 | R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 26 |  | PROCURE | PROCUREMENT
PC1030 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.5 | R1 Procurement - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Fab & Deliver - RW 2-3 - Ramp NE 125 to 130 RT | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 27 |  | PROCURE | PROCUREMENT
PC1040 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.7 | R1 Procurement - Retaining Wall RW 2-4 Br 2 | Fab & Deliver - RW 2-4 Br 2 | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 28 |  | PROCURE | PROCUREMENT
PC1090 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.12 | R1 Procurement - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Fab & Deliver - RW 5-1 Ramp WE-B / Br 5 | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 29 |  | PROCURE | PROCUREMENT
PC1100 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.13 | R1 Procurement - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Fab & Deliver - RW 5-2 Ramp WE-B / Br 5 | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 30 |  | PROCURE | PROCUREMENT
PC1110 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.3 | R1 Procurement - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Fab & Deliver - RW 1-1 - Ramp NE / Br 1 | N | 2023-10-13 08:00 | 2024-02-20 16:00 |  |  | 90 | 0 | 90 | 12 | 31 |  | PROCURE | PROCUREMENT
SD1750 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 15 |  | OFFICE | OFFICE
SD1760 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 15 |  | DESIGN | DESIGN
SD1770 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 15 |  | OFFICE | OFFICE
SD1780 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 15 |  | DESIGN | DESIGN
SD1790 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.4 | R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-1 - Ramp B / Br 8 | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 15 |  | OWNER.Shp Drwg Review | OWNER
SD1800 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 16 |  | OFFICE | OFFICE
SD1810 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 16 |  | DESIGN | DESIGN
SD1820 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 16 |  | OFFICE | OFFICE
SD1830 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 16 |  | DESIGN | DESIGN
SD1840 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.1 | R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-2 - Ramp B / Br 8 | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 16 |  | OWNER.Shp Drwg Review | OWNER
SD1850 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Develop & Submit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 17 |  | OFFICE | OFFICE
SD1860 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Designer Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 17 |  | DESIGN | DESIGN
SD1870 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Revise & Resubmit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 17 |  | OFFICE | OFFICE
SD1880 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 17 |  | DESIGN | DESIGN
SD1890 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.2 | R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 17 |  | OWNER.Shp Drwg Review | OWNER
SD1900 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 18 |  | OFFICE | OFFICE
SD1910 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 18 |  | DESIGN | DESIGN
SD1920 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 18 |  | OFFICE | OFFICE
SD1930 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 18 |  | DESIGN | DESIGN
SD1940 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.3 | R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 18 |  | OWNER.Shp Drwg Review | OWNER
SD1950 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 19 |  | OFFICE | OFFICE
SD1960 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 19 |  | DESIGN | DESIGN
SD1970 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 19 |  | OFFICE | OFFICE
SD1980 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 19 |  | DESIGN | DESIGN
SD1990 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.5 | R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 19 |  | OWNER.Shp Drwg Review | OWNER
SD2000 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Develop & Submit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 20 |  | OFFICE | OFFICE
SD2010 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Designer Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 20 |  | DESIGN | DESIGN
SD2020 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Revise & Resubmit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 20 |  | OFFICE | OFFICE
SD2030 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Design 2nd Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 20 |  | DESIGN | DESIGN
SD2040 | Not Started | I-275 - I-4 - FDOT - S2.4.4.2.1.6 | R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | FDOT - Review & Comment Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 20 |  | OWNER.Shp Drwg Review | OWNER
SD2300 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Develop & Submit Shp Drwgs - RW 102 Ramp C | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 10 | 21 |  | OFFICE | OFFICE
SD2310 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Designer Review & Comnt Shp Drwgs - RW 102 Ramp C | N | 2023-08-21 08:00 | 2023-09-11 16:00 |  |  | 15 | 0 | 15 | 10 | 21 |  | DESIGN | DESIGN
SD2320 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Revise & Resubmit Shp Drwgs - RW 102 Ramp C | N | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 10 | 21 |  | OFFICE | OFFICE
SD2330 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Design 2nd Review & Comnt Shp Drwgs - RW 102 Ramp C | N | 2023-09-19 08:00 | 2023-09-25 16:00 |  |  | 5 | 0 | 5 | 10 | 21 |  | DESIGN | DESIGN
SD2340 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.4.7 | R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | FDOT - Review & Comment Shp Drwgs - RW 102 Ramp C | N | 2023-09-26 08:00 | 2023-10-16 16:00 |  |  | 15 | 0 | 15 | 10 | 21 |  | OWNER.Shp Drwg Review | OWNER
PC1150 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.3.4 | R3 Procurement - Retaining Wall RW 8-1 - Ramp B / Br 8 | Fab & Deliver - RW 8-1 - Ramp B / Br 8 | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 15 |  | PROCURE | PROCUREMENT
PC1160 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.3.1 | R3 Procurement - Retaining Wall RW 8-2 - Ramp B / Br 8 | Fab & Deliver - RW 8-2 - Ramp B / Br 8 | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 16 |  | PROCURE | PROCUREMENT
PC1170 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.3.2 | R3 Procurement - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Fab & Deliver - RW 9-1 - Ramp B/F / Br 8 | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 17 |  | PROCURE | PROCUREMENT
PC1180 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.3.3 | R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 18 |  | PROCURE | PROCUREMENT
PC1190 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.3.5 | R3 Procurement - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-3 - Ramp B/F / Br 9 | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 19 |  | PROCURE | PROCUREMENT
PC1200 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.1.6 | R1 Procurement - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Fab & Deliver - RW 100 I-4 EB (Br 3 & Br 4) | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 20 |  | PROCURE | PROCUREMENT
PC1210 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.3.7 | R3 Procurement - Retaining Wall RW 102 Ramp C | Fab & Deliver - RW 102 Ramp C | N | 2023-10-17 08:00 | 2024-02-22 16:00 |  |  | 90 | 0 | 90 | 10 | 21 |  | PROCURE | PROCUREMENT
D1500 | In Progress | I-275 - I-4 - FDOT - S2.3.2 | Right of Way | Owner Right of Way Acquisition | N | 2022-07-27 08:00 | 2024-07-05 16:00 | 2022-07-27 08:00 |  | 710 | 144 | 566 | 95 |  |  | ROW | OWNER
PC1440 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6 | R3 Procurement | Fab & Deliver 60" Drainage Structures | N | 2023-08-22 08:00 | 2023-12-28 16:00 |  |  | 90 | 0 | 90 | 49 |  |  | PROCURE | PROCUREMENT
SD2350 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Develop & Submit Shp Drwgs - 60" Drainage Str | N | 2023-06-12 08:00 | 2023-06-23 16:00 |  |  | 10 | 0 | 10 | 49 |  |  | OFFICE | OFFICE
SD2360 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Designer Review & Comnt Shp Drwgs - 60" Drainage Str | N | 2023-06-26 08:00 | 2023-07-17 16:00 |  |  | 15 | 0 | 15 | 49 |  |  | DESIGN | DESIGN
SD2370 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Revise & Resubmit Shp Drwgs - 60" Drainage Str | N | 2023-07-18 08:00 | 2023-07-24 16:00 |  |  | 5 | 0 | 5 | 49 |  |  | OFFICE | OFFICE
SD2380 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | Design 2nd Review & Comnt Shp Drwgs - 60" Drainage Str | N | 2023-07-25 08:00 | 2023-07-31 16:00 |  |  | 5 | 0 | 5 | 49 |  |  | DESIGN | DESIGN
SD2390 | Not Started | I-275 - I-4 - FDOT - S2.4.4.8.2 | R3 Shop Drawings - 60" Drainage Structures | FDOT - Review & Comment Shp Drwgs - 60" Drainage Str | N | 2023-08-01 08:00 | 2023-08-21 16:00 |  |  | 15 | 0 | 15 | 49 |  |  | OWNER.Shp Drwg Review | OWNER
A36480 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | N | 2023-10-27 08:00 | 2023-11-30 16:00 |  |  | 25 | 0 | 25 | 13 | 6 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36450 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | N | 2023-10-03 08:00 | 2023-10-26 16:00 |  |  | 18 | 0 | 18 | 13 | 6 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36440 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | N | 2023-07-03 08:00 | 2023-07-14 16:00 |  |  | 10 | 0 | 10 | 13 | 6 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36540 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | N | 2023-08-21 08:00 | 2023-10-02 16:00 |  |  | 31 | 0 | 31 | 13 | 6 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36550 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.2 | R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | N | 2023-07-17 08:00 | 2023-08-18 16:00 |  |  | 25 | 0 | 25 | 13 | 6 | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36560 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-8 - R3 | N | 2023-07-03 08:00 | 2023-07-21 16:00 |  |  | 15 | 0 | 15 | 47 |  | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
A36570 | Not Started | I-275 - I-4 - FDOT - S2.2.5.8.1 | R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-7 - R3 | N | 2023-07-24 08:00 | 2023-08-11 16:00 |  |  | 15 | 0 | 15 | 47 |  | Sub - Tunneling Crew | SUB.TUNNEL | TUNNEL
P1450 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Bridge 5 | N | 2023-03-23 08:00 | 2023-06-15 16:00 |  |  | 60 | 0 | 60 | 112 |  |  | PROCURE | PROCUREMENT
P1480 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.2 | R1 Procurement - Bridge Girders | Procure Girders - Bridge 1 | N | 2023-08-07 08:00 | 2023-10-30 16:00 |  |  | 60 | 0 | 60 | 35 |  |  | PROCURE | PROCUREMENT
P1510 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 8 | N | 2023-08-07 08:00 | 2023-10-30 16:00 |  |  | 60 | 0 | 60 | 35 |  |  | PROCURE | PROCUREMENT
P1520 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.1 | R3 Procurement - Bridge Girders | Procure Girders - Bridge 9 | N | 2023-08-07 08:00 | 2023-10-30 16:00 |  |  | 60 | 0 | 60 | 35 |  |  | PROCURE | PROCUREMENT
P1590 | Not Started | I-275 - I-4 - FDOT - S2.4.3.4.3 | R1 Procurement - Bridge Pile | Procure Pile - Bridge 5 - R1 | N | 2023-03-23 08:00 | 2023-04-05 16:00 |  |  | 10 | 0 | 10 | 129 |  |  | PROCURE | PROCUREMENT
A1070 | Not Started | I-275 - I-4 - FDOT - S2.2.1 | Mobilization | Install Advanced Warning signs | N | 2023-05-25 08:00 | 2023-05-31 16:00 |  |  | 5 | 0 | 5 | 68 |  | Maintenance of Traffic Crew | LANE.TRAFFIC.MAINT | TRAFFIC.Traffic Maint
D5120 | Not Started | I-275 - I-4 - FDOT - S2.3.11.2 | R1 Early Package Design | Develop and Submit - 90% Early Pkg Eros - R1 | N | 2022-12-19 08:00 | 2023-02-22 16:00 |  |  | 45 | 0 | 45 | 65 |  |  | DESIGN | DESIGN
D5130 | Not Started | I-275 - I-4 - FDOT - S2.3.11.2 | R1 Early Package Design | Review and Approve - 90% Early Pkg Eros - R1 | N | 2023-02-23 08:00 | 2023-03-15 16:00 |  |  | 15 | 0 | 15 | 65 |  |  | OWNER.Design Review | OWNER
D5140 | Not Started | I-275 - I-4 - FDOT - S2.3.11.2 | R1 Early Package Design | Develop and Submit - Final Early Pkg Eros - R1 | N | 2023-03-16 08:00 | 2023-04-12 16:00 |  |  | 20 | 0 | 20 | 65 |  |  | DESIGN | DESIGN
D5150 | Not Started | I-275 - I-4 - FDOT - S2.3.11.2 | R1 Early Package Design | Review and Approve - Final Early Pkg Eros - R1 | N | 2023-04-13 08:00 | 2023-05-03 16:00 |  |  | 15 | 0 | 15 | 65 |  |  | OWNER.Design Review | OWNER
D5160 | Not Started | I-275 - I-4 - FDOT - S2.3.11.2 | R1 Early Package Design | Develop and Submit - Sign & Seal Early Pkg Eros - R1 | N | 2023-05-04 08:00 | 2023-05-24 16:00 |  |  | 15 | 0 | 15 | 65 |  |  | DESIGN | DESIGN
D5170 | Not Started | I-275 - I-4 - FDOT - S2.3.11.2 | R1 Early Package Design | Issue - RFC Early Pkg Eros - R1 | N | 2023-05-25 08:00 | 2023-06-01 16:00 |  |  | 5 | 0 | 5 | 65 |  |  | DESIGN | DESIGN
P1610 | Not Started | I-275 - I-4 - FDOT - S2.4.3.6.2 | R3 Procurement - Bridge Pile | Procure Pile - Bridge 09 | N | 2023-08-07 08:00 | 2023-08-18 16:00 |  |  | 10 | 0 | 10 | 85 |  |  | PROCURE | PROCUREMENT
U1000 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 55 |  | UTILITIES | UTILITY
U1010 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 56 |  | UTILITIES | UTILITY
U1020 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 57 |  | UTILITIES | UTILITY
U1030 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 58 |  | UTILITIES | UTILITY
U1040 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 59 |  | UTILITIES | UTILITY
U1050 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 78 |  | UTILITIES | UTILITY
U1060 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 79 |  | UTILITIES | UTILITY
U1070 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 80 |  | UTILITIES | UTILITY
U1080 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | N | 2023-05-11 08:00 | 2023-05-15 16:00 |  |  | 3 | 0 | 3 | 32 | 50 |  | UTILITIES | UTILITY
U1090 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 81 |  | UTILITIES | UTILITY
U1100 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 82 |  | UTILITIES | UTILITY
U1110 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 60 |  | UTILITIES | UTILITY
U1120 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | N | 2023-05-11 08:00 | 2023-05-15 16:00 |  |  | 3 | 0 | 3 | 32 | 51 |  | UTILITIES | UTILITY
U1130 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 83 |  | UTILITIES | UTILITY
U1140 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.2 | Frontier Florida LLC During Construction | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 84 |  | UTILITIES | UTILITY
U1150 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 61 |  | UTILITIES | UTILITY
U1160 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 3" WI GM (E 7th Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 62 |  | UTILITIES | UTILITY
U1170 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 6" PE GM (SMF 3A) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 63 |  | UTILITIES | UTILITY
U1180 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-24 16:00 |  |  | 10 | 0 | 10 | 25 | 8 |  | UTILITIES | UTILITY
U1190 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 2" BS GM (E Oak Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-15 16:00 |  |  | 3 | 0 | 3 | 32 | 52 |  | UTILITIES | UTILITY
U1200 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-15 16:00 |  |  | 3 | 0 | 3 | 32 | 53 |  | UTILITIES | UTILITY
U1210 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 8" PE GM (E Columbus Dr) - TPG | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 85 |  | UTILITIES | UTILITY
U1220 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 64 |  | UTILITIES | UTILITY
U1230 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 33 |  | UTILITIES | UTILITY
U1240 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 65 |  | UTILITIES | UTILITY
U1250 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.2 | TECO Peoples Gas - During Construction | Remove Existing 6" CS GM (Ramp NE) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 66 |  | UTILITIES | UTILITY
U1260 | Not Started | I-275 - I-4 - FDOT - S2.4.2.3.2 | Uniti Fiber/Southern Light - During Construction | Adj HH to grade 24x36x36- (256+20, 105' RT) - Uniti | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 158 |  |  | UTILITIES | UTILITY
U1270 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 34 |  | UTILITIES | UTILITY
U1280 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 35 |  | UTILITIES | UTILITY
U1290 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 36 |  | UTILITIES | UTILITY
U1300 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 37 |  | UTILITIES | UTILITY
U1310 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 38 |  | UTILITIES | UTILITY
U1320 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 39 |  | UTILITIES | UTILITY
U1330 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 40 |  | UTILITIES | UTILITY
U1340 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 86 |  | UTILITIES | UTILITY
U1350 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 41 |  | UTILITIES | UTILITY
U1360 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 87 |  | UTILITIES | UTILITY
U1370 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 42 |  | UTILITIES | UTILITY
U1380 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 88 |  | UTILITIES | UTILITY
U1390 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 43 |  | UTILITIES | UTILITY
U1400 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 89 |  | UTILITIES | UTILITY
U1410 | Not Started | I-275 - I-4 - FDOT - S2.4.2.4.2 | City of Tampa Wastewater Dept - During Construction | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 90 |  | UTILITIES | UTILITY
U1420 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | N | 2023-05-11 08:00 | 2023-05-15 16:00 |  |  | 3 | 0 | 3 | 31 | 48 |  | UTILITIES | UTILITY
U1430 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | N | 2023-05-16 08:00 | 2023-05-16 16:00 |  |  | 1 | 0 | 1 | 31 | 48 |  | UTILITIES | UTILITY
U1440 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 317+70, 73 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 91 |  | UTILITIES | UTILITY
U1450 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 91+25, 40 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 92 |  | UTILITIES | UTILITY
U1460 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 92+45, 50 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 93 |  | UTILITIES | UTILITY
U1470 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 93+35, 50 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 94 |  | UTILITIES | UTILITY
U1480 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 93+80, 60 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 95 |  | UTILITIES | UTILITY
U1490 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 94+40, 60 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 96 |  | UTILITIES | UTILITY
U1500 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 95+15, 60 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 97 |  | UTILITIES | UTILITY
U1510 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 95+95, 60 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 98 |  | UTILITIES | UTILITY
U1520 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 96+40, 65 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 99 |  | UTILITIES | UTILITY
U1530 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.2 | City of Tampa Water Dept - During Construction | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | N | 2023-05-11 08:00 | 2023-05-24 16:00 |  |  | 10 | 0 | 10 | 25 | 9 |  | UTILITIES | UTILITY
U1540 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.2 | City of Tampa Water Dept - During Construction | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | N | 2023-05-11 08:00 | 2023-05-24 16:00 |  |  | 10 | 0 | 10 | 25 | 10 |  | UTILITIES | UTILITY
U1550 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1802+90, 10 R - TECO | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 67 |  | UTILITIES | UTILITY
U1560 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1803+90, 10 R - TECO | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 68 |  | UTILITIES | UTILITY
U1570 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1805+30, 25 R - TECO | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 69 |  | UTILITIES | UTILITY
U1580 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1806+15, 10 R - TECO | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 70 |  | UTILITIES | UTILITY
U1590 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole - sta. 1806+90, 20 R - TECO | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 71 |  | UTILITIES | UTILITY
U1600 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | N | 2023-05-11 08:00 | 2023-05-15 16:00 |  |  | 3 | 0 | 3 | 32 | 54 |  | UTILITIES | UTILITY
U1610 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 | 100 |  | UTILITIES | UTILITY
U1620 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 1802+90, 10 L - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1630 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 1805+55, 130 R - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1640 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole - sta. 1806+90, 85 R - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1650 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 72 |  | UTILITIES | UTILITY
U1660 | Not Started | I-275 - I-4 - FDOT - S2.4.2.5.1 | Tampa Electric Company (TECO) - Prior to Construction | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1670 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | N | 2023-05-11 08:00 | 2023-05-31 16:00 |  |  | 15 | 0 | 15 | 81 |  |  | UTILITIES | UTILITY
U1680 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 44 |  | UTILITIES | UTILITY
U1690 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | N | 2023-05-11 08:00 | 2023-05-24 16:00 |  |  | 10 | 0 | 10 | 25 | 11 |  | UTILITIES | UTILITY
U1700 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | N | 2023-05-11 08:00 | 2023-05-19 16:00 |  |  | 7 | 0 | 7 | 28 | 32 |  | UTILITIES | UTILITY
U1710 | Not Started | I-275 - I-4 - FDOT - S2.4.2.8.1 | City of Tampa Water Dept - Prior to Construction | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | N | 2023-05-11 08:00 | 2023-05-24 16:00 |  |  | 10 | 0 | 10 | 25 | 12 |  | UTILITIES | UTILITY
U1720 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install Fiber Distrib HUB - 207+04, 100 L - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 73 |  | UTILITIES | UTILITY
U1730 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install Fiber XBOX - 207+04, 110 L - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 74 |  | UTILITIES | UTILITY
U1740 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | N | 2023-05-11 08:00 | 2023-05-17 16:00 |  |  | 5 | 0 | 5 | 30 | 45 |  | UTILITIES | UTILITY
U1750 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1760 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1770 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Fiber XBOX - 207+00, 5 L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1780 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1790 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | N | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 34 |  |  | UTILITIES | UTILITY
U1800 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 75 |  | UTILITIES | UTILITY
U1810 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 76 |  | UTILITIES | UTILITY
U1820 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Install all Copper/Fiber Cables within project limits - FTR | N | 2023-05-11 08:00 | 2023-05-24 16:00 |  |  | 10 | 0 | 10 | 25 | 13 |  | UTILITIES | UTILITY
U1830 | Not Started | I-275 - I-4 - FDOT - S2.4.2.1.1 | Frontier Florida LLC Prior to Construction | Splice/Cutover new facilities within project limits - FTR | N | 2023-05-11 08:00 | 2023-06-07 16:00 |  |  | 20 | 0 | 20 | 76 |  |  | UTILITIES | UTILITY
U1840 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.1 | TECO Peoples Gas - Prior to Construction | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | N | 2023-05-11 08:00 | 2023-05-12 16:00 |  |  | 2 | 0 | 2 | 33 | 77 |  | UTILITIES | UTILITY
U1850 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.1 | TECO Peoples Gas - Prior to Construction | Install 6" PE GM (E Columbus Dr) - TPG | N | 2023-05-11 08:00 | 2023-05-16 16:00 |  |  | 4 | 0 | 4 | 31 | 46 |  | UTILITIES | UTILITY
U1860 | Not Started | I-275 - I-4 - FDOT - S2.4.2.2.1 | TECO Peoples Gas - Prior to Construction | Install 6" PE GM (N Mitchell Ave) - TPG | N | 2023-05-11 08:00 | 2023-05-16 16:00 |  |  | 4 | 0 | 4 | 31 | 47 |  | UTILITIES | UTILITY
Admin-1090 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Complete project - Critical Path (under development) | Y | 2023-12-20 08:00 | 2026-09-08 16:00 |  |  | 994 | 0 | 994 | 0 | 1
Admin-1110 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Complete Project - Remaining activities (under development) | N | 2024-02-23 08:00 | 2026-08-25 16:00 |  |  | 915 | 0 | 915 | 14 | 15
Admin-1120 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Complete Project - ROW / Permit Impacts (under development) | N | 2024-07-06 08:00 | 2026-06-05 16:00 |  |  | 700 | 0 | 700 | 95
Admin-1130 | Not Started | I-275 - I-4 - FDOT - S2.1 | Project Administration | Continue Project Design (under development) | N | 2024-02-21 08:00 | 2024-07-24 16:00 |  |  | 155 | 0 | 155 | 776

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | comments | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(d) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Comments | Delete This Row
P1150 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Review and Approve - Settlement and Vibration Monitoring Plan | Start Construction - R3 | 0
P1150 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Review and Approve - Settlement and Vibration Monitoring Plan | Start Construction - R1 | 0
D1090 | D2880 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | 0
Admin-1100 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Design Completion | Substantial Completion (Sept. 8th, 2026) | 0
A26350 | A36000 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Start Construction - R3 | Excav for 60" Str - OUT-9 - R3 | 0 |  | SUB-TUNNEL
D2460 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R2 Phase 2 | Complete project - Critical Path (under development) | 0
D1830 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R2 Phase 1 | Complete project - Critical Path (under development) | 0
D1450 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | Complete Project - Remaining activities (under development) | 0
D2550 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R3 Phase 1 | Complete project - Critical Path (under development) | 0
D1580 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R1 Phase 2 & 3 | Complete Project - Remaining activities (under development) | 0
D1740 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Comment - Environmental Resource Permit (ERP) | Complete Project - Remaining activities (under development) | 0
D2180 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Landscape Plans | Continue Project Design (under development) | 0
D2170 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Landscaping Opportunity Plan | Continue Project Design (under development) | 0
D2110 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Lighting Plans | Continue Project Design (under development) | 0
D2100 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Signing and Pavement Marking Plan | Continue Project Design (under development) | 0
D2060 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit- Sign & Seal MoC Plan | Continue Project Design (under development) | 0
D2150 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final ITS Plans | Continue Project Design (under development) | 0
D2120 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Signalization Plans | Continue Project Design (under development) | 0
D2410 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Sign & Seal Temporary Retaining Wall Plans | Continue Project Design (under development) | 0
D3630 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | Continue Project Design (under development) | 0
D1450 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | Continue Project Design (under development) | 0
D4520 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | Continue Project Design (under development) | 0
D4460 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Continue Project Design (under development) | 0
D4420 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | Continue Project Design (under development) | 0
D4120 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | Continue Project Design (under development) | 0
D4060 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | Continue Project Design (under development) | 0
D2810 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | Continue Project Design (under development) | 0
D2900 | Admin-1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | Continue Project Design (under development) | 0
D1330 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Issue - RFC Erosion and Sediment Control Plan | Start Construction - R1 | 0
Admin-1130 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Continue Project Design (under development) | Design Completion | 0
Admin-1120 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Complete Project - ROW / Permit Impacts (under development) | Substantial Completion (Sept. 8th, 2026) | 0
D1500 | Admin-1120 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.2 Right of Way | I-275 - I-4 - FDOT - S2.1 Project Administration | Owner Right of Way Acquisition | Complete Project - ROW / Permit Impacts (under development) | 0
Admin-1110 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Complete Project - Remaining activities (under development) | Substantial Completion (Sept. 8th, 2026) | 0
PC1210 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.3.7 R3 Procurement - Retaining Wall RW 102 Ramp C | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 102 Ramp C | Complete Project - Remaining activities (under development) | 0
PC1190 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.3.5 R3 Procurement - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 9-3 - Ramp B/F / Br 9 | Complete Project - Remaining activities (under development) | 0
PC1180 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.3.3 R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | Complete Project - Remaining activities (under development) | 0
PC1170 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.3.2 R3 Procurement - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 9-1 - Ramp B/F / Br 8 | Complete Project - Remaining activities (under development) | 0
PC1160 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.3.1 R3 Procurement - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 8-2 - Ramp B / Br 8 | Complete Project - Remaining activities (under development) | 0
PC1150 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.3.4 R3 Procurement - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 8-1 - Ramp B / Br 8 | Complete Project - Remaining activities (under development) | 0
PC1440 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6 R3 Procurement | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver 60" Drainage Structures | Complete Project - Remaining activities (under development) | 0
PC1200 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.6 R1 Procurement - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 100 I-4 EB (Br 3 & Br 4) | Complete Project - Remaining activities (under development) | 0
PC1100 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.13 R1 Procurement - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 5-2 Ramp WE-B / Br 5 | Complete Project - Remaining activities (under development) | 0
PC1090 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.12 R1 Procurement - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 5-1 Ramp WE-B / Br 5 | Complete Project - Remaining activities (under development) | 0
PC1040 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.7 R1 Procurement - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 2-4 Br 2 | Complete Project - Remaining activities (under development) | 0
PC1030 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.5 R1 Procurement - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 2-3 - Ramp NE 125 to 130 RT | Complete Project - Remaining activities (under development) | 0
PC1020 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.4 R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | Complete Project - Remaining activities (under development) | 0
PC1010 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.2 R1 Procurement - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 2-1 - Br 2 | Complete Project - Remaining activities (under development) | 0
PC1000 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | Complete Project - Remaining activities (under development) | 0
PC1110 | Admin-1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.1.3 R1 Procurement - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Fab & Deliver - RW 1-1 - Ramp NE / Br 1 | Complete Project - Remaining activities (under development) | 0
D4520 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | Complete project - Critical Path (under development) | 0
D4460 | D4520 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0
D2060 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit- Sign & Seal MoC Plan | Complete project - Critical Path (under development) | 0
D2180 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Landscape Plans | Complete project - Critical Path (under development) | 0
D2170 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Landscaping Opportunity Plan | Complete project - Critical Path (under development) | 0
A15230 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Install SIP - Brg 100865 - Span 2 - R1 - P1.S1 | Complete project - Critical Path (under development) | 0 | SUB-ST-SIP
D2410 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Sign & Seal Temporary Retaining Wall Plans | Complete project - Critical Path (under development) | 0
A14810 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | Complete project - Critical Path (under development) | 0 | ST-DECK
D2150 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final ITS Plans | Complete project - Critical Path (under development) | 0
D2120 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Signalization Plans | Complete project - Critical Path (under development) | 0
D2110 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Lighting Plans | Complete project - Critical Path (under development) | 0
D2100 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Final Signing and Pavement Marking Plan | Complete project - Critical Path (under development) | 0
D4120 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | Complete project - Critical Path (under development) | 0
D4060 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | Complete project - Critical Path (under development) | 0
D3630 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | Complete project - Critical Path (under development) | 0
D2810 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | Complete project - Critical Path (under development) | 0
D2670 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R3 Phase 3 & 4 | Complete project - Critical Path (under development) | 0
D1440 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | Complete project - Critical Path (under development) | 0
D4420 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | Complete project - Critical Path (under development) | 0
A36480 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.1 Project Administration | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | Complete project - Critical Path (under development) | 0 | SUB-TUNNEL
A36030 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.1 Project Administration | Excav for 60" Str - OUT-4 - R3 | Complete project - Critical Path (under development) | 0 | SUB-TUNNEL
A15430 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - FDOT - S2.1 Project Administration | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | Complete project - Critical Path (under development) | 0 | PIPE
A16130 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - FDOT - S2.1 Project Administration | Place Asphalt Surface - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Complete project - Critical Path (under development) | 0 | SUB-ASPH
A15070 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - FDOT - S2.1 Project Administration | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | Complete project - Critical Path (under development) | 0 | ST-PILE
D2610 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R3 Phase 2 | Complete project - Critical Path (under development) | 0
A14940 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | I-275 - I-4 - FDOT - S2.1 Project Administration | Cut/Fill to Grade - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | Complete project - Critical Path (under development) | 0 | EW-SML
P1150 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Settlement and Vibration Monitoring Plan | Complete project - Critical Path (under development) | 0
P1130 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | I-275 - I-4 - FDOT - S2.1 Project Administration | Review and Approve - Noise Management Plan | Complete project - Critical Path (under development) | 0
P1610 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.1 Project Administration | Procure Pile - Bridge 09 | Complete project - Critical Path (under development) | 0
P1520 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - FDOT - S2.1 Project Administration | Procure Girders - Bridge 9 | Complete project - Critical Path (under development) | 0
P1510 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.1 R3 Procurement - Bridge Girders | I-275 - I-4 - FDOT - S2.1 Project Administration | Procure Girders - Bridge 8 | Complete project - Critical Path (under development) | 0
P1480 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - FDOT - S2.1 Project Administration | Procure Girders - Bridge 1 | Complete project - Critical Path (under development) | 0
P1430 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.6.2 R3 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.1 Project Administration | Procure Pile - Bridge 08 | Complete project - Critical Path (under development) | 0
A16290 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | I-275 - I-4 - FDOT - S2.1 Project Administration | Install Fencing - 13th Ave - R1 - P1.S1 | Complete project - Critical Path (under development) | 0 | SUB-FENCE
P1200 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.1 Project Administration | Procure Pile - Bridge 1 - R1 | Complete project - Critical Path (under development) | 0
D2790 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC Roadway Plans - R3 | Complete project - Critical Path (under development) | 0
U1260 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.3.2 Uniti Fiber/Southern Light - During Construction | I-275 - I-4 - FDOT - S2.1 Project Administration | Adj HH to grade 24x36x36- (256+20, 105' RT) - Uniti | Complete project - Critical Path (under development) | 0
D1230 | Admin-1090 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.1 Project Administration | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | Complete project - Critical Path (under development) | 0
D2900 | Admin-1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | Complete project - Critical Path (under development) | 0
Admin-1090 | Admin-1050 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Complete project - Critical Path (under development) | Substantial Completion (Sept. 8th, 2026) | 0
D3190 | D3210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Review and Approve - 60% - 60" Drainage System - R3 | Review and Approve - 90% - 60" Drainage System - R3 | 0 |  |  | H
D3180 | D3200 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Develop and Submit - 60% - 60" Drainage System - R3 | Develop and Submit - 90% - 60" Drainage System - R3 | 0 |  |  | H
D3240 | D3250 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Develop and Submit - Sign & Seal - 60" Drainage System - R3 | Issue - RFC - 60" Drainage System - R3 | 0 |  |  | H
D3180 | D3190 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Develop and Submit - 60% - 60" Drainage System - R3 | Review and Approve - 60% - 60" Drainage System - R3 | 0 |  |  | H
D3200 | D3210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Develop and Submit - 90% - 60" Drainage System - R3 | Review and Approve - 90% - 60" Drainage System - R3 | 0 |  |  | H
D3220 | D3230 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Develop and Submit - Final - 60" Drainage System - R3 | Review and Approve - Final - 60" Drainage System - R3 | 0 |  |  | H
D3210 | D3220 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Review and Approve - 90% - 60" Drainage System - R3 | Develop and Submit - Final - 60" Drainage System - R3 | 0 |  |  | H
D3230 | D3240 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Review and Approve - Final - 60" Drainage System - R3 | Develop and Submit - Sign & Seal - 60" Drainage System - R3 | 0 |  |  | H
A15960 | A16080 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-SML | EW-SML
A16110 | A16130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Curb - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place Asphalt Surface - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | FLATWORK | SUB-ASPH | H
A14790 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | ST-BEAM | ST-BEAM
A14730 | A15150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-FOOT | ST-FOOT | S
A15140 | A15070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | ST-PILE | ST-PILE
A14720 | A15140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-PILE | ST-PILE | S
A1650 | A14720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-PILE | ST-PILE | S
A15440 | A15430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | 0 | PIPE | PIPE | S
A15420 | A15440 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | 0 | PIPE | PIPE | S
A1060 | A15940 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.3 R1 - Ph0 - Traffic Shift | I-275 - I-4 - FDOT - S2.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Shift Traffic - I-4 Exit 1 Ramp Left - R1 - P0 | Shift Traffic - 13th Ave Right - R1 - P1.S1 Step 1 | 0 | TC-Maint. | TC-Maint. | H
D1200 | D1680 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-1 | 0
A15210 | A15230 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | Install SIP - Brg 100865 - Span 2 - R1 - P1.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A14790 | A14800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | Install SIP - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | ST-BEAM | SUB-ST-SIP | H
A15050 | A15070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | EW- ALL EW | ST-PILE | H
A1630 | A1650 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | EW- ALL EW | ST-PILE | H
A15120 | A15140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | EW-STR | ST-PILE | H
A14700 | A14720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | EW-STR | ST-PILE | H
A36020 | A36030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-5 - R3 | Excav for 60" Str - OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | S
A36010 | A36020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-6 - R3 | Excav for 60" Str - OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL | S
D2740 | D2480 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 20 |  |  | H
D2680 | D1420 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 20 |  |  | H
D1420 | D1910 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2560 | D2620 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2480 | D2560 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | 0 |  |  | H
Admin-1045 | D2620 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Begin Design | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
Admin-1045 | D2560 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Begin Design | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2730 | D1730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Issue - RFC Roadway Plans - R2 | Develop and Submit - 90% Landscape Plans | 0 |  |  | H
D2730 | D1710 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | Issue - RFC Roadway Plans - R2 | Modify and Submit - Environmental Resource Permit (ERP) | 0 |  |  | H
D2730 | D1700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Issue - RFC Roadway Plans - R2 | Develop and Submit - 90% Landscaping Opportunity Plan | 0 |  |  | H
D1670 | A1120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Issue - RFC Roadway Plans - R1 | Shift Traffic - Ramp WE Left - R1 - P1.S1 | 0 |  | TC-Maint. | H
D1100 | D2680 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Perform Geotechnical Investigations - Roadway | Develop and Submit - 90% Roadway Plans - R2 | 0 |  |  | H
D1100 | D2740 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Perform Geotechnical Investigations - Roadway | Develop and Submit - 90% Roadway Plans - R3 | 0 |  |  | H
D2870 | D2890 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2860 | D2880 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2800 | D2810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 0 |  |  | H
D2860 | D2870 | FS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2880 | D2890 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Develop and Submit - 90% Cat2 Brg 02 Plans - R1 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2890 | D2900 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Review and Approve - 90% Cat2 Brg 02 Plans - R1 | Develop and Submit - Final Cat2 Brg 02 Plans - R1 | 0 |  |  | H
Admin-1045 | D2860 | SS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Begin Design | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | 0 |  |  | H
D2870 | P1060 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | Develop and Submit - Settlement and Vibration Monitoring Plan | 0 |  |  | S
D2870 | P1040 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | Review and Approve - 60% Cat2 Brg 02 Plans - R1 | Develop and Submit - Noise Management Plan | 0 |  |  | S
D2780 | D2790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Develop and Submit - Sign & Seal Roadway Plans - R3 | Issue - RFC Roadway Plans - R3 | 0 |  |  | H
D2760 | D2770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Develop and Submit - Final Roadway Plans - R3 | Review and Approve - Final Roadway Plans - R3 | 0 |  |  | H
D2740 | D2750 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Develop and Submit - 90% Roadway Plans - R3 | Review and Approve - 90% Roadway Plans - R3 | 0 |  |  | H
D2750 | D2760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Review and Approve - 90% Roadway Plans - R3 | Develop and Submit - Final Roadway Plans - R3 | 0 |  |  | H
D2770 | D2780 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Review and Approve - Final Roadway Plans - R3 | Develop and Submit - Sign & Seal Roadway Plans - R3 | 0 |  |  | H
D2720 | D2730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Develop and Submit - Sign & Seal Roadway Plans - R2 | Issue - RFC Roadway Plans - R2 | 0 |  |  | H
D2700 | D2710 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Develop and Submit - Final Roadway Plans - R2 | Review and Approve - Final Roadway Plans - R2 | 0 |  |  | H
D2680 | D2690 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Develop and Submit - 90% Roadway Plans - R2 | Review and Approve - 90% Roadway Plans - R2 | 0 |  |  | H
D2690 | D2700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Review and Approve - 90% Roadway Plans - R2 | Develop and Submit - Final Roadway Plans - R2 | 0 |  |  | H
D2710 | D2720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Review and Approve - Final Roadway Plans - R2 | Develop and Submit - Sign & Seal Roadway Plans - R2 | 0 |  |  | H
D2660 | D2670 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 3 & 4 | Issue - RFC TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2640 | D2650 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - Final TTCP Plans - R3 Phase 3 & 4 | Review and Approve - Final TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2620 | D2630 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Develop and Submit - 90% TTCP Plans - R3 Phase 3 & 4 | Review and Approve - 90% TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2630 | D2640 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Review and Approve - 90% TTCP Plans - R3 Phase 3 & 4 | Develop and Submit - Final TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2650 | D2660 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | I-275 - I-4 - FDOT - S2.3.10.7 Temporary Traffic Control Plans (TTCP) - R3 Phase 3 & 4 | Review and Approve - Final TTCP Plans - R3 Phase 3 & 4 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 3 & 4 | 0 |  |  | H
D2600 | D2610 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 2 | Issue - RFC TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2580 | D2590 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - Final TTCP Plans - R3 Phase 2 | Review and Approve - Final TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2560 | D2570 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Develop and Submit - 90% TTCP Plans - R3 Phase 2 | Review and Approve - 90% TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2570 | D2580 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Review and Approve - 90% TTCP Plans - R3 Phase 2 | Develop and Submit - Final TTCP Plans - R3 Phase 2 | 0 |  |  | H
D2590 | D2600 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | I-275 - I-4 - FDOT - S2.3.10.6 Temporary Traffic Control Plans (TTCP) - R3 Phase 2 | Review and Approve - Final TTCP Plans - R3 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 2 | 0 |  |  | H
D1070 | D1150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Review and Approve - 60% Utility Relocation Plans | Develop and Submit - 90% Utility Relocation Plans | 0 |  |  | H
Admin-1045 | D1050 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Begin Design | Develop and Submit - 60% Utility Relocation Plans | 0 |  |  | H
D1340 | D1370 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Develop and Submit - Sign & Seal Utility Relocation Plans | Issue - RFC Utility Relocation Plans | 0 |  |  | H
D1050 | D1070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Develop and Submit - 60% Utility Relocation Plans | Review and Approve - 60% Utility Relocation Plans | 0 |  |  | H
D1150 | D1240 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Develop and Submit - 90% Utility Relocation Plans | Review and Approve - 90% Utility Relocation Plans | 0 |  |  | H
D1300 | D1320 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Develop and Submit - 100% Utility Relocation Plans | Review and Approve - 100% Utility Relocation Plans | 0 |  |  | H
D1240 | D1300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Review and Approve - 90% Utility Relocation Plans | Develop and Submit - 100% Utility Relocation Plans | 0 |  |  | H
D1320 | D1340 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Review and Approve - 100% Utility Relocation Plans | Develop and Submit - Sign & Seal Utility Relocation Plans | 0 |  |  | H
D1220 | D1450 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | Develop and Submit - 90% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
Admin-1045 | D1730 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Begin Design | Develop and Submit - 90% Landscape Plans | 0 |  |  | H
Admin-1045 | D1690 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | Begin Design | Develop and Submit - 90% ITS Plans | 0 |  |  | H
D2000 | D2150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | Develop and Submit- Final ITS Plans | Review and Approve - Final ITS Plans | 0 |  |  | H
D1690 | D1920 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | Develop and Submit - 90% ITS Plans | Review and Approve - 90% ITS Plans | 0 |  |  | H
D1190 | D1840 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% Temporary Retaining Wall Plans | 0 |  |  | H
D1190 | D1680 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 1-1 | 0 |  |  | H
D1310 | D1330 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Develop and Submit - Sign & Seal Erosion and Sediment Control Plan | Issue - RFC Erosion and Sediment Control Plan | 0 |  |  | H
Admin-1045 | P1060 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | Begin Design | Develop and Submit - Settlement and Vibration Monitoring Plan | 0 |  |  | H
P1090 | P1120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | Review and Comment - Settlement and Vibration Monitoring Plan | Revise and Resubmit - Settlement and Vibration Monitoring Plan | 0 |  |  | H
P1120 | P1150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | Revise and Resubmit - Settlement and Vibration Monitoring Plan | Review and Approve - Settlement and Vibration Monitoring Plan | 0 |  |  | H
P1060 | P1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | Develop and Submit - Settlement and Vibration Monitoring Plan | Review and Comment - Settlement and Vibration Monitoring Plan | 0 |  |  | H
Admin-1045 | D1840 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Begin Design | Develop and Submit - 90% Temporary Retaining Wall Plans | 0 |  |  | H
D2200 | D2300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Develop and Submit - Final Temporary Retaining Wall Plans | Review and Approve - Final Temporary Retaining Wall Plans | 0 |  |  | H
D1840 | D2070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Develop and Submit - 90% Temporary Retaining Wall Plans | Review and Approve - 90% Temporary Retaining Wall Plans | 0 |  |  | H
D2210 | D2310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-1 | Issue - RFC MSE Wall RW 1-1 | 0 |  |  | H
D2050 | D2080 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 08 Plans - R3 | Issue - RFC Cat1 Brg 08 Plans - R3 | 0 |  |  | H
Admin-1045 | D1260 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Begin Design | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1520 | D1590 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 1 | Issue - RFC TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1430 | D1480 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - Final TTCP Plans - R1 Phase 1 | Review and Approve - Final TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1260 | D1400 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | Review and Approve - 90% TTCP Plans - R1 Phase 1 | 0 |  |  | H
Admin-1045 | D1910 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Begin Design | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2430 | D2460 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 2 | Issue - RFC TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2260 | D2400 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - Final TTCP Plans - R2 Phase 2 | Review and Approve - Final TTCP Plans - R2 Phase 2 | 0 |  |  | H
D1910 | D2190 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Develop and Submit - 90% TTCP Plans - R2 Phase 2 | Review and Approve - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
D1770 | D1830 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | Issue - RFC TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1600 | D1620 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - Final TTCP Plans - R2 Phase 1 | Review and Approve - Final TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1420 | D1550 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | Review and Approve - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
Admin-1045 | D1250 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Begin Design | Develop and Submit - 90% TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
D1510 | D1580 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 & 3 | Issue - RFC TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
D1410 | D1470 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - Final TTCP Plans - R1 Phase 2 & 3 | Review and Approve - Final TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
D1250 | D1390 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - 90% TTCP Plans - R1 Phase 2 & 3 | Review and Approve - 90% TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
D1130 | D1140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | I-275 - I-4 - FDOT - S2.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Develop and Submit - SWPPP & NOI | Review and Approve - SWPPP & NOI | 0 |  |  | H
D2040 | D2180 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Develop and Submit - Final Landscape Plans | Review and Approve - Final Landscape Plans | 0 |  |  | H
D1730 | D1950 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Develop and Submit - 90% Landscape Plans | Review and Approve - 90% Landscape Plans | 0 |  |  | H
Admin-1045 | D1680 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Begin Design | Develop and Submit - 90% MSE Wall RW 1-1 | 0 |  |  | H
D1990 | D2130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-1 | Review and Approve - Final MSE Wall RW 1-1 | 0 |  |  | H
D1680 | D1900 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-1 | Review and Approve - 90% MSE Wall RW 1-1 | 0 |  |  | H
D1610 | D1670 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Develop and Submit - Sign & Seal Roadway Plans - R1 | Issue - RFC Roadway Plans - R1 | 0 |  |  | H
D1490 | D1570 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Develop and Submit - Final Roadway Plans - R1 | Review and Approve - Final Roadway Plans - R1 | 0 |  |  | H
Admin-1045 | D1200 | SS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Begin Design | Develop and Submit - 90% Roadway Plans - R1 | 0 |  |  | H
D1200 | D1460 | FS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Develop and Submit - 90% Roadway Plans - R1 | Review and Approve - 90% Roadway Plans - R1 | 0 |  |  | H
D1350 | D1540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1810 | D1890 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Develop and Submit - Final Cat1 Brg 08 Plans - R3 | Review and Approve - Final Cat1 Brg 08 Plans - R3 | 0 |  |  | H
Admin-1045 | D1000 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Begin Design | Develop and Submit - 90% Erosion and Sediment Control Plan | 0 |  |  | H
Admin-1020 | D1190 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | Anticipated Notice to Proceed (Sept. 26th, 2022) | Perform Geotechnical Investigations - Retaining Walls | 0 |  |  | H
Admin-1020 | D1090 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | Anticipated Notice to Proceed (Sept. 26th, 2022) | Perform Geotechnical Investigations - Brgs | 0 |  |  | H
Admin-1045 | D1040 | SS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.3 Design Survey/SUE | Begin Design | Perform Design Survey [LoE] | 0 |  |  | H
Admin-1045 | D1560 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Begin Design | Develop and Submit - 90% MoC Plan | 0 |  |  | H
D1820 | D1940 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Develop and Submit- Final MoC Plan | Review and Approve - Final MoC Plan | 0 |  |  | H
D1560 | D1760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Develop and Submit - 90% MoC Plan | Review and Approve - 90% MoC Plan | 0 |  |  | H
Admin-1045 | P1000 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | Begin Design | Develop and Submit - Construction Quality Control Plan | 0 |  |  | H
Admin-1045 | D1030 | SS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.1.2 Preliminary IDR Submittal Schedule | Begin Design | Develop and Submit - Preliminary IDR Submittal Schedule | 0 |  |  | H
D1030 | D1170 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - FDOT - S2.3.1.2 Preliminary IDR Submittal Schedule | Develop and Submit - Preliminary IDR Submittal Schedule | Independent Design Review Kickoff Meeting | 0 |  |  | H
D1710 | D1740 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | Modify and Submit - Environmental Resource Permit (ERP) | Review and Comment - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1045 | D1010 | SS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | Begin Design | Develop and Submit - Design Quality Management Plan | 0 |  |  | H
P1010 | P1020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | Review and Comment - Construction Quality Control Plan | Revise and Resubmit - Construction Quality Control Plan | 0 |  |  | H
P1020 | P1030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | Revise and Resubmit - Construction Quality Control Plan | Review and Approve - Construction Quality Control Plan | 0 |  |  | H
P1000 | P1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | Develop and Submit - Construction Quality Control Plan | Review and Comment - Construction Quality Control Plan | 0 |  |  | H
D1080 | D1160 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | Review and Comment - Design Quality Management Plan | Revise and Resubmit - Design Quality Management Plan | 0 |  |  | H
D1160 | D1180 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | Revise and Resubmit - Design Quality Management Plan | Review and Approve - Design Quality Management Plan | 0 |  |  | H
D1010 | D1080 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | Develop and Submit - Design Quality Management Plan | Review and Comment - Design Quality Management Plan | 0 |  |  | H
Admin-1045 | D1660 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | Begin Design | Develop and Submit - 90% Signalization Plans | 0 |  |  | H
Admin-1045 | D1700 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Begin Design | Develop and Submit - 90% Landscaping Opportunity Plan | 0 |  |  | H
D2030 | D2170 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Develop and Submit - Final Landscaping Opportunity Plan | Review and Approve - Final Landscaping Opportunity Plan | 0 |  |  | H
D1700 | D1930 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Develop and Submit - 90% Landscaping Opportunity Plan | Review and Approve - 90% Landscaping Opportunity Plan | 0 |  |  | H
D1980 | D2120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | Develop and Submit - Final Signalization Plans | Review and Approve - Final Signalization Plans | 0 |  |  | H
D1660 | D1880 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | Develop and Submit - 90% Signalization Plans | Review and Approve - 90% Signalization Plans | 0 |  |  | H
Admin-1045 | D1650 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | Begin Design | Develop and Submit - 90% Lighting Plans | 0 |  |  | H
Admin-1045 | D1640 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | Begin Design | Develop and Submit - 90% Signing and Pavement Marking Plan | 0 |  |  | H
D1970 | D2110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | Develop and Submit - Final Lighting Plans | Review and Approve - Final Lighting Plans | 0 |  |  | H
D1650 | D1870 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | Develop and Submit - 90% Lighting Plans | Review and Approve - 90% Lighting Plans | 0 |  |  | H
D1960 | D2100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | Develop and Submit - Final Signing and Pavement Marking Plan | Review and Approve - Final Signing and Pavement Marking Plan | 0 |  |  | H
D1640 | D1860 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | Develop and Submit - 90% Signing and Pavement Marking Plan | Review and Approve - 90% Signing and Pavement Marking Plan | 0 |  |  | H
D1210 | D1270 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Develop and Submit - Final Erosion and Sediment Control Plan | Review and Approve - Final Erosion and Sediment Control Plan | 0 |  |  | H
D1000 | D1120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Develop and Submit - 90% Erosion and Sediment Control Plan | Review and Approve - 90% Erosion and Sediment Control Plan | 0 |  |  | H
Admin-1045 | P1040 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | Begin Design | Develop and Submit - Noise Management Plan | 0 |  |  | H
P1070 | P1100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | Review and Comment - Noise Management Plan | Revise and Resubmit - Noise Management Plan | 0 |  |  | H
P1100 | P1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | Revise and Resubmit - Noise Management Plan | Review and Approve - Noise Management Plan | 0 |  |  | H
P1040 | P1070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | Develop and Submit - Noise Management Plan | Review and Comment - Noise Management Plan | 0 |  |  | H
Admin-1000 | Admin-1030 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Anticipated Contract Award Date | Design Mobilization | 0 |  |  | H
Admin-1020 | Admin-1040 | SS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Anticipated Notice to Proceed (Sept. 26th, 2022) | LOE - Project Duration | 0 |  |  | H
Admin-1080 | Admin-1015 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Anticipated Contract Execution Date | Prepare for Notice to Proceed | 0 |  |  | H
Admin-1010 | Admin-1080 | FF | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Execute Contract | Anticipated Contract Execution Date | 0 |  |  | H
Admin-1030 | Admin-1045 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Design Mobilization | Begin Design | 0 |  |  | H
Admin-1060 | Admin-1070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Project Punchlist | Contract Completion (Nov. 7th 2026) | 0 |  |  | H
Admin-1050 | Admin-1060 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Substantial Completion (Sept. 8th, 2026) | Project Punchlist | 0 |  |  | H
Admin-1000 | Admin-1010 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Anticipated Contract Award Date | Execute Contract | 0 |  |  | H
Admin-1015 | Admin-1020 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | Prepare for Notice to Proceed | Anticipated Notice to Proceed (Sept. 26th, 2022) | 0 |  |  | H
Admin-1045 | D1710 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | Begin Design | Modify and Submit - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1045 | D1130 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Begin Design | Develop and Submit - SWPPP & NOI | 0 |  |  | H
Admin-1045 | D1420 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Begin Design | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1120 | D1210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Review and Approve - 90% Erosion and Sediment Control Plan | Develop and Submit - Final Erosion and Sediment Control Plan | 0 |  |  | H
D1270 | D1310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Review and Approve - Final Erosion and Sediment Control Plan | Develop and Submit - Sign & Seal Erosion and Sediment Control Plan | 0 |  |  | H
D1400 | D1430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Review and Approve - 90% TTCP Plans - R1 Phase 1 | Develop and Submit - Final TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1480 | D1520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Review and Approve - Final TTCP Plans - R1 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 1 | 0 |  |  | H
D1390 | D1410 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Review and Approve - 90% TTCP Plans - R1 Phase 2 & 3 | Develop and Submit - Final TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
D1470 | D1510 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Review and Approve - Final TTCP Plans - R1 Phase 2 & 3 | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
D1550 | D1600 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Review and Approve - 90% TTCP Plans - R2 Phase 1 | Develop and Submit - Final TTCP Plans - R2 Phase 1 | 0 |  |  | H
D1620 | D1770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Review and Approve - Final TTCP Plans - R2 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | 0 |  |  | H
D2190 | D2260 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Review and Approve - 90% TTCP Plans - R2 Phase 2 | Develop and Submit - Final TTCP Plans - R2 Phase 2 | 0 |  |  | H
D2400 | D2430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Review and Approve - Final TTCP Plans - R2 Phase 2 | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 2 | 0 |  |  | H
D1460 | D1490 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Review and Approve - 90% Roadway Plans - R1 | Develop and Submit - Final Roadway Plans - R1 | 0 |  |  | H
D1570 | D1610 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Review and Approve - Final Roadway Plans - R1 | Develop and Submit - Sign & Seal Roadway Plans - R1 | 0 |  |  | H
D1540 | D1810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | Develop and Submit - Final Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1890 | D2050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Review and Approve - Final Cat1 Brg 08 Plans - R3 | Develop and Submit - Sign & Seal Cat1 Brg 08 Plans - R3 | 0 |  |  | H
D1900 | D1990 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-1 | Develop and Submit - Final MSE Wall RW 1-1 | 0 |  |  | H
D2130 | D2210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-1 | Develop and Submit - Sign & Seal MSE Wall RW 1-1 | 0 |  |  | H
D2070 | D2200 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Review and Approve - 90% Temporary Retaining Wall Plans | Develop and Submit - Final Temporary Retaining Wall Plans | 0 |  |  | H
D2300 | D2410 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Review and Approve - Final Temporary Retaining Wall Plans | Develop and Submit - Sign & Seal Temporary Retaining Wall Plans | 0 |  |  | H
D1880 | D1980 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | Review and Approve - 90% Signalization Plans | Develop and Submit - Final Signalization Plans | 0 |  |  | H
D1920 | D2000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | Review and Approve - 90% ITS Plans | Develop and Submit- Final ITS Plans | 0 |  |  | H
D1760 | D1820 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Review and Approve - 90% MoC Plan | Develop and Submit- Final MoC Plan | 0 |  |  | H
D1940 | D2060 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Review and Approve - Final MoC Plan | Develop and Submit- Sign & Seal MoC Plan | 0 |  |  | H
D1860 | D1960 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | Review and Approve - 90% Signing and Pavement Marking Plan | Develop and Submit - Final Signing and Pavement Marking Plan | 0 |  |  | H
D1870 | D1970 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | Review and Approve - 90% Lighting Plans | Develop and Submit - Final Lighting Plans | 0 |  |  | H
D1930 | D2030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Review and Approve - 90% Landscaping Opportunity Plan | Develop and Submit - Final Landscaping Opportunity Plan | 0 |  |  | H
D1950 | D2040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Review and Approve - 90% Landscape Plans | Develop and Submit - Final Landscape Plans | 0 |  |  | H
D1580 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R1 Phase 2 & 3 | Design Completion | 0 |  |  | H
D1830 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R2 Phase 1 | Design Completion | 0 |  |  | H
D2460 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R2 Phase 2 | Design Completion | 0 |  |  | H
Admin-1020 | D1080 | SS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Design Quality Management Plan | 0 |  |  | H
Admin-1020 | D1170 | SS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.1.2 Preliminary IDR Submittal Schedule | Anticipated Notice to Proceed (Sept. 26th, 2022) | Independent Design Review Kickoff Meeting | 0 |  |  | H
Admin-1020 | D1740 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Environmental Resource Permit (ERP) | 0 |  |  | H
Admin-1020 | D1140 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - SWPPP & NOI | 0 |  |  | H
Admin-1020 | D1120 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Erosion and Sediment Control Plan | 0 |  |  | H
Admin-1020 | D1400 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R1 Phase 1 | 0 |  |  | H
Admin-1020 | D1390 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R1 Phase 2 & 3 | 0 |  |  | H
Admin-1020 | D1550 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R2 Phase 1 | 0 |  |  | H
Admin-1020 | D2190 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.2 Temporary Traffic Control Plans (TTCP) - R2 Phase 2 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R2 Phase 2 | 0 |  |  | H
Admin-1020 | D1460 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Roadway Plans - R1 | 0 |  |  | H
Admin-1020 | D1900 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% MSE Wall RW 1-1 | 0 |  |  | H
Admin-1020 | D2070 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Temporary Retaining Wall Plans | 0 |  |  | H
Admin-1020 | D1880 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Signalization Plans | 0 |  |  | H
Admin-1020 | D1920 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% ITS Plans | 0 |  |  | H
Admin-1020 | D1760 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% MoC Plan | 0 |  |  | H
Admin-1020 | D1860 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Signing and Pavement Marking Plan | 0 |  |  | H
Admin-1020 | D1870 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Lighting Plans | 0 |  |  | H
Admin-1020 | D1930 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Landscaping Opportunity Plan | 0 |  |  | H
Admin-1020 | D1950 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% Landscape Plans | 0 |  |  | H
D1100 | D1190 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | Perform Geotechnical Investigations - Roadway | Perform Geotechnical Investigations - Retaining Walls | 0 |  |  | S
D1100 | D1200 | FF | Not Started | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Perform Geotechnical Investigations - Roadway | Develop and Submit - 90% Roadway Plans - R1 | 0 |  |  | H
D1200 | D1260 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | 20 |  |  | S
Admin-1045 | D2480 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Begin Design | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2540 | D2550 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 1 | Issue - RFC TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2520 | D2530 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - Final TTCP Plans - R3 Phase 1 | Review and Approve - Final TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2480 | D2510 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | Review and Approve - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2510 | D2520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Review and Approve - 90% TTCP Plans - R3 Phase 1 | Develop and Submit - Final TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2530 | D2540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Review and Approve - Final TTCP Plans - R3 Phase 1 | Develop and Submit - Sign & Seal TTCP Plans - R3 Phase 1 | 0 |  |  | H
D2550 | Admin-1100 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | I-275 - I-4 - FDOT - S2.1 Project Administration | Issue - RFC TTCP Plans - R3 Phase 1 | Design Completion | 0 |  |  | H
Admin-1020 | D2510 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Approve - 90% TTCP Plans - R3 Phase 1 | 0 |  |  | H
D1610 | D1660 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.18.20 Signalization Plans | Develop and Submit - Sign & Seal Roadway Plans - R1 | Develop and Submit - 90% Signalization Plans | 0 |  |  | S
D1610 | D1690 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.18.14 ITS Plans | Develop and Submit - Sign & Seal Roadway Plans - R1 | Develop and Submit - 90% ITS Plans | 0 |  |  | S
D1770 | D1840 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | I-275 - I-4 - FDOT - S2.3.18.2 Temporary Retaining Wall Design | Develop and Submit - Sign & Seal TTCP Plans - R2 Phase 1 | Develop and Submit - 90% Temporary Retaining Wall Plans | 0 |  |  | S
D1510 | D1560 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | I-275 - I-4 - FDOT - S2.3.18.12 Maintenance of Communication (MoC) Plan | Develop and Submit - Sign & Seal TTCP Plans - R1 Phase 2 & 3 | Develop and Submit - 90% MoC Plan | 0 |  |  | S
D1610 | D1640 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.18.21 Signing and Pavement Marking Plan (Incl Misc Structures) | Develop and Submit - Sign & Seal Roadway Plans - R1 | Develop and Submit - 90% Signing and Pavement Marking Plan | 0 |  |  | S
D1610 | D1650 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.18.22 Lighting Plans | Develop and Submit - Sign & Seal Roadway Plans - R1 | Develop and Submit - 90% Lighting Plans | 0 |  |  | S
D1670 | D1700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.18.23 Landscape Opportunity Plans | Issue - RFC Roadway Plans - R1 | Develop and Submit - 90% Landscaping Opportunity Plan | 0 |  |  | S
D1670 | D1730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.18.11 Landscape/Irrigation Plans | Issue - RFC Roadway Plans - R1 | Develop and Submit - 90% Landscape Plans | 0 |  |  | S
D1220 | D1440 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | Review and Approve - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
Admin-1045 | D1220 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Begin Design | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
D1090 | D1220 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0 |  |  | H
Admin-1020 | P1090 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.4.1.3 Settlement and Vibration Monitoring Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Settlement and Vibration Monitoring Plan | 0 |  |  | H
Admin-1020 | P1070 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.4.1.26 Noise Management Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Noise Management Plan | 0 |  |  | H
Admin-1020 | P1010 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | Anticipated Notice to Proceed (Sept. 26th, 2022) | Review and Comment - Construction Quality Control Plan | 0 |  |  | H
D1000 | D1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | I-275 - I-4 - FDOT - S2.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | Develop and Submit - 90% Erosion and Sediment Control Plan | Develop and Submit - SWPPP & NOI | 0 |  |  | H
Admin-1020 | D1100 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | Anticipated Notice to Proceed (Sept. 26th, 2022) | Perform Geotechnical Investigations - Roadway | 0 |  |  | H
D1670 | D1710 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.6.3 FDEP Environmental Resource Permit (ERP) | Issue - RFC Roadway Plans - R1 | Modify and Submit - Environmental Resource Permit (ERP) | 0 |  |  | H
A1000 | A1010 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Mobilization | Install Erosion Control Devices | 0 |  | SUB-EROSION | H
A1010 | A1020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Install Erosion Control Devices | Clear and Grub | 0 | SUB-EROSION | SUB-EW-C&G | H
A1030 | A1040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.1 R1 - Ph0 - MOT | I-275 - I-4 - FDOT - S2.2.2.1.1 R1 - Ph0 - MOT | Install MOT - I-4 Exit Ramp - R1 - P0 | Shift Traffic - I-4 Exit 1 Ramp Right - R1 - P0 | 0 | TC-Maint. | TC-Maint. | H
A1050 | A1030 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | I-275 - I-4 - FDOT - S2.2.2.1.1 R1 - Ph0 - MOT | Start Construction - R1 | Install MOT - I-4 Exit Ramp - R1 - P0 | 0 |  | TC-Maint. | H
A1080 | A1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | Place Stabilization - 13th Ave Temp Pav - R1 - P0 | 0 | EW-SML | EW-STAB | H
A1100 | A1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | Place Asphalt - 13th Ave Temp Pav - R1 - P0 | Temp Striping - 13th Ave Temp Pav - R1 - P0 | 0 | SUB-ASPH | SUB-STRIP | H
A1040 | A1080 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.1 R1 - Ph0 - MOT | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | Shift Traffic - I-4 Exit 1 Ramp Right - R1 - P0 | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | 0 | TC-Maint. | EW-SML | H
A1110 | A1060 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - FDOT - S2.2.2.1.3 R1 - Ph0 - Traffic Shift | Temp Striping - 13th Ave Temp Pav - R1 - P0 | Shift Traffic - I-4 Exit 1 Ramp Left - R1 - P0 | 0 | SUB-STRIP | TC-Maint. | H
A1120 | A1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp WE Left - R1 - P1.S1 | Install Temp Barrier - Ramp WE - R1 - P1.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A1140 | A1150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Shift Traffic - Ramp NE Left - R1 - P1.S1 | Install Temp Barrier - Ramp NE - R1 - P1.S1 | 0 | TC-Maint. | SUB-TC-PCB | H
A1130 | A1140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Shift Traffic - Ramp NE Left - R1 - P1.S1 | 0 | SUB-TC-PCB | TC-Maint. | H
A1660 | A1670 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | FRP Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | Cure/Strip Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | ST-ABUT |  | H
A1130 | A14680 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Temp Wall or SOE - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | SUB-TC-PCB | EW-STR | H
A14680 | A1630 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Temp Wall or SOE - Brg 100865 - End Bent 1 - R1 - P1.S1 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | EW-STR | EW- ALL EW | H
A1650 | A14670 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | ST-PILE | ST-MSE | H
A14760 | A14770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Column - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | ST-CAP | H
A14740 | A14750 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Cure/Strip Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Column - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | ST-COL | H
A14770 | A14780 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-CAP |  | H
A14750 | A14760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Column - Brg 100865 - Pier 1 - R1 - P1.S1 | Cure/Strip Column - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-COL |  | H
A14730 | A14740 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | Cure/Strip Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-FOOT |  | H
A14720 | A14730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | FRP Footing - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | ST-PILE | ST-FOOT | H
A14800 | A14810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Install SIP - Brg 100865 - Span 1 - R1 - P1.S1 | Install Overhangs - Brg 100865 - Span 1 - R1 - P1.S1 | 0 | SUB-ST-SIP | ST-DECK | H
A1130 | A15050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | SUB-TC-PCB | EW- ALL EW | H
A1000 | A1020 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Mobilization | Clear and Grub | 0 |  | SUB-EW-C&G | H
A1050 | A14700 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Start Construction - R1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | EW-STR | H
A15180 | A15190 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Column - Brg 100865 - Pier 2 - R1 - P1.S1 | FRP Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | ST-CAP | H
A15160 | A15170 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Cure/Strip Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | FRP Column - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | ST-COL | H
A15190 | A15200 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-CAP |  | H
A15170 | A15180 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Column - Brg 100865 - Pier 2 - R1 - P1.S1 | Cure/Strip Column - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-COL |  | H
A15150 | A15160 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | Cure/Strip Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-FOOT |  | H
A15140 | A15150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | FRP Footing - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | ST-PILE | ST-FOOT | H
A1050 | A15120 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Start Construction - R1 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | EW-STR | H
A14780 | A14790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A1670 | A14790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Cure/Strip Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A14780 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Cure/Strip Cap - Brg 100865 - Pier 1 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A15200 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Cure/Strip Cap - Brg 100865 - Pier 2 - R1 - P1.S1 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | ST-BEAM | H
A14670 | A14940 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.5 R1 - Ph1, Stg1 - Ramp WE-B - Beginning to Bridge - Sta. 40 to 45 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | Cut/Fill to Grade - Ramp WE-B Sta 40 to 45 - R1 - P1.S1 | 0 | ST-MSE | EW-SML | H
A15010 | A15420 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | 0 | PIPE | PIPE | S
A15940 | A15950 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | I-275 - I-4 - FDOT - S2.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | Shift Traffic - 13th Ave Right - R1 - P1.S1 Step 1 | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | 0 | TC-Maint. | SUB-TC-PCB | H
A15950 | A15960 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | I-275 - I-4 - FDOT - S2.2.2.12.4 R1 - Ph1, Stg1 - Left 13th Ave - 14th St. to 15th St. | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | Cut/Fill to Grade - 13th Ave Sta 13 to 16 - R1 - P1.S1 - left | 0 | SUB-TC-PCB | EW-SML | H
A16090 | A16100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place Stabilization - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place GAB - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-STAB | EW-ABC | H
A16100 | A16110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Place GAB - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place Curb - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-ABC | FLATWORK | H
A16080 | A16090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | Place Stabilization - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | EW-SML | EW-STAB | H
A15950 | A16080 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.9 R1 - Ph1, Stg1, Step 1 - 13th Ave MOT | I-275 - I-4 - FDOT - S2.2.2.12.7 R1 - Ph1, Stg1 - Left 13th Ave - 15th St. to 20th St. - Sta. 16 to 35 | Install Temp Barrier - 13th Ave - R1 - P1.S1 Step 1 | Cut/Fill to Grade - 13th Ave Sta 16 to 35 - R1 - P1.S1 - Left | 0 | SUB-TC-PCB | EW-SML | H
A16270 | A16290 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Brick Sidewalk - Left 14th & 15th St under I-4 - R1 - P1.S1 | Install Fencing - 13th Ave - R1 - P1.S1 | 0 | FLATWORK | SUB-FENCE | H
A1050 | A16250 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Start Construction - R1 | Demo Existing Slope Pavement - Left 14th &15th St under I-4 - R1 - P1.S1 | 0 |  | DM-BRIDGE | H
A16250 | A16280 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Left 14th &15th St under I-4 - R1 - P1.S1 | Const Gravity Wall - Left 14th & 15th St under I-4 - R1 - P1.S1 | 0 | DM-BRIDGE | SUB-BR-SLIP | H
A16280 | A16260 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Const Gravity Wall - Left 14th & 15th St under I-4 - R1 - P1.S1 | Form / Pour Slope Pavement - Left 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-CURB | H
A16260 | A16270 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.2 R1 - Ph1, Stg1 - Left 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Left 14th & 15th St under I-4 - R1 - P1.S1 | Place Brick Sidewalk - Left 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-CURB | FLATWORK | H
A18290 | A18310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Demo Existing Slope Pavement - Right 14th &15th St under I-4 - R1 - P1.S1 | Const Gravity Wall - Right 14th & 15th St under I-4 - R1 - P1.S1 | 0 | DM-BRIDGE | SUB-BR-SLIP | H
A18310 | A18300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Const Gravity Wall - Right 14th & 15th St under I-4 - R1 - P1.S1 | Form / Pour Slope Pavement - Right 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-BR-SLIP | SUB-CURB | H
A18300 | A18320 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Form / Pour Slope Pavement - Right 14th & 15th St under I-4 - R1 - P1.S1 | Place Brick Sidewalk - Right 14th & 15th St under I-4 - R1 - P1.S1 | 0 | SUB-CURB | FLATWORK | H
A18320 | A16290 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | I-275 - I-4 - FDOT - S2.2.2.12.11 R1 - Ph1, Stg1 - 13th Ave - Finishes | Place Brick Sidewalk - Right 14th & 15th St under I-4 - R1 - P1.S1 | Install Fencing - 13th Ave - R1 - P1.S1 | 0 | FLATWORK | SUB-FENCE | H
A1050 | A18290 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | I-275 - I-4 - FDOT - S2.2.2.12.5 R1 - Ph1, Stg1 - Right 14th & 15th St. - Under I-4 | Start Construction - R1 | Demo Existing Slope Pavement - Right 14th &15th St under I-4 - R1 - P1.S1 | 0 |  | DM-BRIDGE | H
A1090 | A18330 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | Place Stabilization - 13th Ave Temp Pav - R1 - P0 | Place GAB - 13th Ave Temp Pav - R1 - P0 | 0 | EW-STAB | EW-ABC | H
A18330 | A1100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | Place GAB - 13th Ave Temp Pav - R1 - P0 | Place Asphalt - 13th Ave Temp Pav - R1 - P0 | 0 | EW-ABC | SUB-ASPH | H
A14670 | A1660 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Const MSE Wall & Bkfill - RW 5-1 / Brg 100865 - End Bent 1 - R1 - P1.S1 | FRP Abt Cap - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 | ST-MSE | ST-ABUT | H
Admin-1045 | D2800 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0
Admin-1045 | D2810 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Begin Design | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 0
D1090 | D2800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0
D1090 | D2810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Perform Geotechnical Investigations - Brgs | Review and Approve - 90% Cat1 Brg 03 Plans - R1 | 0
Admin-1045 | D1350 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | 0
Admin-1045 | D1540 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Begin Design | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 0
D1090 | D1350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | 0
D1090 | D1540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Perform Geotechnical Investigations - Brgs | Review and Approve - 90% Cat1 Brg 08 Plans - R3 | 0
D1180 | D1000 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.5 Erosion and Sediment Control Plan | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Erosion and Sediment Control Plan | 0
D1180 | D1420 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.12.3 Temporary Traffic Control Plans (TTCP) - R2 Phase 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% TTCP Plans - R2 Phase 1 | 0
D1180 | D2480 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.10.4 Temporary Traffic Control Plans (TTCP) - R3 Phase 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% TTCP Plans - R3 Phase 1 | 0
D1180 | D1150 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Utility Relocation Plans | 0
D1180 | D1350 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 08 Plans - R3 | 0
D1180 | D1220 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Review and Approve - Design Quality Management Plan | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0
D1180 | D2800 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0
D1170 | D1220 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Independent Design Review Kickoff Meeting | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0
D1170 | D2860 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.2 Preliminary IDR Submittal Schedule | I-275 - I-4 - FDOT - S2.3.11.4.2 R1 Bridge 02 Design Category 2 | Independent Design Review Kickoff Meeting | Develop and Submit - 60% Cat2 Brg 02 Plans - R1 | 0
Admin-1045 | D1230 | SS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | Begin Design | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | 0
D1200 | D1680 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-1 | 0
D3300 | D3310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 01 Plans - R1 | Issue - RFC Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3260 | D3270 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3280 | D3290 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Develop and Submit - Final Cat1 Brg 01 Plans - R1 | Review and Approve - Final Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3270 | D3280 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Review and Approve - 90% Cat1 Brg 01 Plans - R1 | Develop and Submit - Final Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3290 | D3300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Review and Approve - Final Cat1 Brg 01 Plans - R1 | Develop and Submit - Sign & Seal Cat1 Brg 01 Plans - R1 | 0 |  |  | H
D3420 | D3430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 05 Plans - R1 | Issue - RFC Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3380 | D3390 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3400 | D3410 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Develop and Submit - Final Cat1 Brg 05 Plans - R1 | Review and Approve - Final Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3390 | D3400 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Review and Approve - 90% Cat1 Brg 05 Plans - R1 | Develop and Submit - Final Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3410 | D3420 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Review and Approve - Final Cat1 Brg 05 Plans - R1 | Develop and Submit - Sign & Seal Cat1 Brg 05 Plans - R1 | 0 |  |  | H
D3540 | D3550 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - Sign & Seal Cat1 Brg 09 Plans - R3 | Issue - RFC Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3500 | D3510 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3520 | D3530 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Develop and Submit - Final Cat1 Brg 09 Plans - R3 | Review and Approve - Final Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3510 | D3520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Review and Approve - 90% Cat1 Brg 09 Plans - R3 | Develop and Submit - Final Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3530 | D3540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Review and Approve - Final Cat1 Brg 09 Plans - R3 | Develop and Submit - Sign & Seal Cat1 Brg 09 Plans - R3 | 0 |  |  | H
D3620 | D3630 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | Review and Approve - 90% Cat1 Brg 11 Plans - R3 | 0 |  |  | H
Admin-1045 | D3500 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | 0
D1180 | D3500 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | 0
D1090 | D3500 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 90% Cat1 Brg 09 Plans - R3 | 0
Admin-1045 | D3620 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0
D1180 | D3620 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0
D1090 | D3620 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0
Admin-1045 | D3260 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | 0
D1180 | D3260 | FS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | 0
D1090 | D3260 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | Perform Geotechnical Investigations - Brgs | Develop and Submit - 90% Cat1 Brg 01 Plans - R1 | 0
Admin-1045 | D3380 | SS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Begin Design | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | 0
D1180 | D3380 | FS | Completed | Completed | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.1.1 Design Quality Management Plan | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | Review and Approve - Design Quality Management Plan | Develop and Submit - 90% Cat1 Brg 05 Plans - R1 | 0
D3720 | D3730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-2 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3700 | D3710 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3680 | D3690 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3690 | D3700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3710 | D3720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Review and Approve - Final MSE Wall RW 1-2 - Ramp NE / Br 1 | Develop and Submit - Sign & Seal MSE Wall RW 1-2 - Ramp NE / Br 1 | 0 |  |  | H
D3780 | D3790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-1 - Br 2 | Issue - RFC MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3760 | D3770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - Final MSE Wall RW 2-1 - Br 2 | Review and Approve - Final MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3740 | D3750 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3750 | D3760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - 90% MSE Wall RW 2-1 - Br 2 | Develop and Submit - Final MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3770 | D3780 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Review and Approve - Final MSE Wall RW 2-1 - Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-1 - Br 2 | 0 |  |  | H
D3840 | D3850 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Sign & Seal MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3820 | D3830 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Review and Approve - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3800 | D3810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3810 | D3820 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Develop and Submit - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3830 | D3840 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Review and Approve - Final MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Develop and Submit - Sign & Seal MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0 |  |  | H
D3900 | D3910 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Sign & Seal MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3880 | D3890 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Review and Approve - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3860 | D3870 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3870 | D3880 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Develop and Submit - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D3890 | D3900 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Review and Approve - Final MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Develop and Submit - Sign & Seal MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0 |  |  | H
D4020 | D4030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-4 Br 2 | Issue - RFC MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D4000 | D4010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - Final MSE Wall RW 2-4 Br 2 | Review and Approve - Final MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D3980 | D3990 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D3990 | D4000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - 90% MSE Wall RW 2-4 Br 2 | Develop and Submit - Final MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D4010 | D4020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Review and Approve - Final MSE Wall RW 2-4 Br 2 | Develop and Submit - Sign & Seal MSE Wall RW 2-4 Br 2 | 0 |  |  | H
D4040 | D4050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4050 | D4060 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Review and Approve - 90% MSE Wall RW 3-1 Br 3 | Develop and Submit - Final MSE Wall RW 3-1 Br 3 | 0 |  |  | H
D4100 | D4110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4110 | D4120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Review and Approve - 90% MSE Wall RW 3-2 Br 3 | Develop and Submit - Final MSE Wall RW 3-2 Br 3 | 0 |  |  | H
D4320 | D4330 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-1 Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4300 | D4310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4280 | D4290 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4290 | D4300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4310 | D4320 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-1 Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0 |  |  | H
D4380 | D4390 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-2 Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4360 | D4370 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4340 | D4350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4350 | D4360 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | Develop and Submit - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4370 | D4380 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Review and Approve - Final MSE Wall RW 5-2 Ramp WE-B / Br 5 | Develop and Submit - Sign & Seal MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0 |  |  | H
D4400 | D4410 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4410 | D4420 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Review and Approve - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Develop and Submit - Final MSE Wall RW 6-1 Ramp EN / Br 6 | 0 |  |  | H
D4620 | D4630 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-1 Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4600 | D4610 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-1 Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4580 | D4590 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4590 | D4600 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-1 Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4610 | D4620 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-1 Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-1 Ramp B / Br 8 | 0 |  |  | H
D4680 | D4690 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-2 Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4660 | D4670 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-2 Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4640 | D4650 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4650 | D4660 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - 90% MSE Wall RW 8-2 Ramp B / Br 8 | Develop and Submit - Final MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4670 | D4680 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Review and Approve - Final MSE Wall RW 8-2 Ramp B / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 8-2 Ramp B / Br 8 | 0 |  |  | H
D4740 | D4750 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 9-1 Ramp B/F / Br 8 | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 8 | 0 |  |  | H
D4720 | D4730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - Final MSE Wall RW 9-1 Ramp B/F / Br 8 | Review and Approve - Final MSE Wall RW 9-1 Ramp B/F / Br 8 | 0 |  |  | H
D4700 | D4710 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | 0 |  |  | H
D4710 | D4720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Review and Approve - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | Develop and Submit - Final MSE Wall RW 9-1 Ramp B/F / Br 8 | 0 |  |  | H
D4730 | D4740 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Review and Approve - Final MSE Wall RW 9-1 Ramp B/F / Br 8 | Develop and Submit - Sign & Seal MSE Wall RW 9-1 Ramp B/F / Br 8 | 0 |  |  | H
D4800 | D4810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-2 Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4780 | D4790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4760 | D4770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4770 | D4780 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4790 | D4800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-2 Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-2 Ramp B/F / Br 9 | 0 |  |  | H
D4860 | D4870 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-3 Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4840 | D4850 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4820 | D4830 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4830 | D4840 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Review and Approve - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | Develop and Submit - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4850 | D4860 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Review and Approve - Final MSE Wall RW 9-3 Ramp B/F / Br 9 | Develop and Submit - Sign & Seal MSE Wall RW 9-3 Ramp B/F / Br 9 | 0 |  |  | H
D4920 | D4930 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Sign & Seal MSE Wall RW 100 I-4 EB (Br 3 & 4) | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4900 | D4910 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | Review and Approve - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4880 | D4890 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4890 | D4900 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop and Submit - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4910 | D4920 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Review and Approve - Final MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop and Submit - Sign & Seal MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0 |  |  | H
D4980 | D4990 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Sign & Seal MSE Wall RW 102 Ramp C | Issue - RFC MSE Wall RW 102 Ramp C | 0 |  |  | H
D4960 | D4970 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - Final MSE Wall RW 102 Ramp C | Review and Approve - Final MSE Wall RW 102 Ramp C | 0 |  |  | H
D4940 | D4950 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% MSE Wall RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | 0 |  |  | H
D4950 | D4960 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - 90% MSE Wall RW 102 Ramp C | Develop and Submit - Final MSE Wall RW 102 Ramp C | 0 |  |  | H
D4970 | D4980 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Review and Approve - Final MSE Wall RW 102 Ramp C | Develop and Submit - Sign & Seal MSE Wall RW 102 Ramp C | 0 |  |  | H
Admin-1045 | D3680 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Begin Design | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0
D1190 | D3680 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0
D1200 | D3680 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0
Admin-1045 | D3740 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Begin Design | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0
D1190 | D3740 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0
D1200 | D3740 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0
Admin-1045 | D3800 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Begin Design | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0
D1190 | D3800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0
D1200 | D3800 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0
Admin-1045 | D3860 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Begin Design | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0
D1190 | D3860 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0
D1200 | D3860 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0
Admin-1045 | D3980 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Begin Design | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0
D1190 | D3980 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0
D1200 | D3980 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0
Admin-1045 | D4040 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Begin Design | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0
D1190 | D4040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0
D1200 | D4040 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0
Admin-1045 | D4100 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Begin Design | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0
D1190 | D4100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0
D1200 | D4100 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0
Admin-1045 | D4280 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Begin Design | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0
D1190 | D4280 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0
D1200 | D4280 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0
Admin-1045 | D4340 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Begin Design | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0
D1190 | D4340 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0
D1200 | D4340 | SS | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0
Admin-1045 | D4400 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Begin Design | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0
D1190 | D4400 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0
Admin-1045 | D4460 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Begin Design | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0
D1190 | D4460 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0
Admin-1045 | D4520 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Begin Design | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0
D1190 | D4520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0
Admin-1045 | D4580 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Begin Design | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0
D1190 | D4580 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0
Admin-1045 | D4640 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Begin Design | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0
D1190 | D4640 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0
Admin-1045 | D4700 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Begin Design | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | 0
D1190 | D4700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | 0
Admin-1045 | D4760 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Begin Design | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0
D1190 | D4760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0
Admin-1045 | D4820 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Begin Design | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0
D1190 | D4820 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0
Admin-1045 | D4880 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Begin Design | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0
D1190 | D4880 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0
Admin-1045 | D4940 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Begin Design | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0
D1190 | D4940 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.9 Geotechnical Investigations | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Perform Geotechnical Investigations - Retaining Walls | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0
SD1000 | SD1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0
SD1010 | SD1020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0
SD1020 | SD1030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0
SD1030 | SD1040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-1 Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0
SD1050 | SD1060 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0
SD1060 | SD1070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Designer Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0
SD1070 | SD1080 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Revise & Resubmit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0
SD1080 | SD1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Design 2nd Review & Comnt Shp Drwgs - RW 1-2 Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0
SD1100 | SD1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Develop & Submit Shp Drwgs - RW 2-1 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-1 Br 2 | 0
SD1110 | SD1120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-1 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-1 Br 2 | 0
SD1120 | SD1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Revise & Resubmit Shp Drwgs - RW 2-1 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-1 Br 2 | 0
SD1130 | SD1140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-1 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-1 Br 2 | 0
SD1150 | SD1160 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Develop & Submit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Designer Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0
SD1160 | SD1170 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Designer Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Revise & Resubmit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0
SD1170 | SD1180 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Revise & Resubmit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Design 2nd Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0
SD1180 | SD1190 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Design 2nd Review & Comnt Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | FDOT - Review & Comment Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0
SD1200 | SD1210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Develop & Submit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Designer Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0
SD1210 | SD1220 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Designer Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Revise & Resubmit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0
SD1220 | SD1230 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Revise & Resubmit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Design 2nd Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0
SD1230 | SD1240 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Design 2nd Review & Comnt Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | FDOT - Review & Comment Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0
SD1250 | SD1260 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Develop & Submit Shp Drwgs - RW 2-4 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-4 Br 2 | 0
SD1260 | SD1270 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Designer Review & Comnt Shp Drwgs - RW 2-4 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-4 Br 2 | 0
SD1270 | SD1280 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Revise & Resubmit Shp Drwgs - RW 2-4 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-4 Br 2 | 0
SD1280 | SD1290 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Design 2nd Review & Comnt Shp Drwgs - RW 2-4 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-4 Br 2 | 0
SD1500 | SD1510 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0
SD1510 | SD1520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0
SD1520 | SD1530 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0
SD1530 | SD1540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0
SD1550 | SD1560 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0
SD1560 | SD1570 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Designer Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0
SD1570 | SD1580 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Revise & Resubmit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0
SD1580 | SD1590 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Design 2nd Review & Comnt Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0
D2310 | SD1000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.3 R1 - Retaining Wall Design RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-1 | Develop & Submit Shp Drwgs - RW 1-1 Ramp NE / Br 1 | 0
SD1090 | PC1000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.3.4.1.1 R1 Procurement - Retaining Wall RW 1-2 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-2 Ramp NE / Br 1 | Fab & Deliver - RW 1-2 - Ramp NE / Br 1 | 0
SD1140 | PC1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.4.3.4.1.2 R1 Procurement - Retaining Wall RW 2-1 - Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-1 Br 2 | Fab & Deliver - RW 2-1 - Br 2 | 0
SD1190 | PC1020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.4.3.4.1.4 R1 Procurement - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | FDOT - Review & Comment Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | Fab & Deliver - RW 2-2 - Ramp NE 126 to 130 LT | 0
SD1240 | PC1030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.4.3.4.1.5 R1 Procurement - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | FDOT - Review & Comment Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | Fab & Deliver - RW 2-3 - Ramp NE 125 to 130 RT | 0
SD1290 | PC1040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.4.3.4.1.7 R1 Procurement - Retaining Wall RW 2-4 Br 2 | FDOT - Review & Comment Shp Drwgs - RW 2-4 Br 2 | Fab & Deliver - RW 2-4 Br 2 | 0
SD1540 | PC1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.3.4.1.12 R1 Procurement - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | Fab & Deliver - RW 5-1 Ramp WE-B / Br 5 | 0
SD1590 | PC1100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.3.4.1.13 R1 Procurement - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | FDOT - Review & Comment Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | Fab & Deliver - RW 5-2 Ramp WE-B / Br 5 | 0
D3730 | SD1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.4.2.1.1 R1 Shp Drwgs - Retaining Wall RW 1-2 - Ramp NE / Br 1 | Issue - RFC MSE Wall RW 1-2 - Ramp NE / Br 1 | Develop & Submit Shp Drwgs - RW 1-2 Ramp NE / Br 1 | 0
D3790 | SD1100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.2 R1 Shp Drwgs - Retaining Wall RW 2-1 - Br 2 | Issue - RFC MSE Wall RW 2-1 - Br 2 | Develop & Submit Shp Drwgs - RW 2-1 Br 2 | 0
D3850 | SD1150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | I-275 - I-4 - FDOT - S2.4.4.2.1.4 R1 Shp Drwgs - Retaining Wall RW 2-2 - Ramp NE 126 to 130 LT | Issue - RFC MSE Wall RW 2-2 Ramp NE 126 to 130 LT | Develop & Submit Shp Drwgs - RW 2-2 Ramp NE 126 to 130 LT | 0
D3910 | SD1200 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | I-275 - I-4 - FDOT - S2.4.4.2.1.5 R1 Shp Drwgs - Retaining Wall RW 2-3 - Ramp NE 125 to 130 RT | Issue - RFC MSE Wall RW 2-3 Ramp NE 125 to 130 RT | Develop & Submit Shp Drwgs - RW 2-3 Ramp NE 125 to 130 RT | 0
D4030 | SD1250 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | I-275 - I-4 - FDOT - S2.4.4.2.1.7 R1 Shp Drwgs - Retaining Wall RW 2-4 Br 2 | Issue - RFC MSE Wall RW 2-4 Br 2 | Develop & Submit Shp Drwgs - RW 2-4 Br 2 | 0
D4330 | SD1500 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.12 R1 Shp Drwgs - Retaining Wall RW 5-1 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-1 Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-1 Ramp WE-B / Br 5 | 0
D4390 | SD1550 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | I-275 - I-4 - FDOT - S2.4.4.2.1.13 R1 Shp Drwgs - Retaining Wall RW 5-2 - Ramp WE-B / Br 5 | Issue - RFC MSE Wall RW 5-2 Ramp WE-B / Br 5 | Develop & Submit Shp Drwgs - RW 5-2 Ramp WE-B / Br 5 | 0
SD1040 | PC1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.3 R1 Shp Drwgs - Retaining Wall RW 1-1 - Ramp NE / Br 1 | I-275 - I-4 - FDOT - S2.4.3.4.1.3 R1 Procurement - Retaining Wall RW 1-1 - Ramp NE / Br 1 | FDOT - Review & Comment Shp Drwgs - RW 1-1 Ramp NE / Br 1 | Fab & Deliver - RW 1-1 - Ramp NE / Br 1 | 0 |  |  | H
D1200 | D3680 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.1 R1 - Retaining Wall Design RW 1-2 - Ramp NE / Br 1 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 1-2 - Ramp NE / Br 1 | 0
D1200 | D3740 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.2 R1 - Retaining Wall Design RW 2-1 - Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-1 - Br 2 | 0
D1200 | D3800 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.4 R1 - Retaining Wall Design RW 2-2 - Ramp NE 126 to 130 LT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-2 Ramp NE 126 to 130 LT | 0
D1200 | D3860 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.5 R1 - Retaining Wall Design RW 2-3 - Ramp NE 125 to 130 RT | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-3 Ramp NE 125 to 130 RT | 0
D1200 | D3980 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.7 R1 - Retaining Wall Design RW 2-4 Br 2 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 2-4 Br 2 | 0
D1200 | D4040 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0
D1200 | D4100 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0
D1200 | D4280 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.12 R1 - Retaining Wall Design RW 5-1 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-1 Ramp WE-B / Br 5 | 0
D1200 | D4340 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.13 R1 - Retaining Wall Design RW 5-2 - Ramp WE-B / Br 5 | Develop and Submit - 90% Roadway Plans - R1 | Develop and Submit - 90% MSE Wall RW 5-2 Ramp WE-B / Br 5 | 0
D2680 | D4400 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0
D2680 | D4400 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0
D2680 | D4460 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0
D2680 | D4460 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0
D2680 | D4520 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0
D2680 | D4520 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% Roadway Plans - R2 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0
D2740 | D4580 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0
D2740 | D4640 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0
D2740 | D4700 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | 0
D2740 | D4760 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0
D2740 | D4820 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0
D2740 | D4880 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0
D2740 | D4940 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0
D2740 | D4580 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-1 Ramp B / Br 8 | 0
D2740 | D4640 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 8-2 Ramp B / Br 8 | 0
D2740 | D4700 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-1 Ramp B/F / Br 8 | 0
D2740 | D4760 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-2 Ramp B/F / Br 9 | 0
D2740 | D4820 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 9-3 Ramp B/F / Br 9 | 0
D2740 | D4880 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 100 I-4 EB (Br 3 & 4) | 0
D2740 | D4940 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | Develop and Submit - 90% Roadway Plans - R3 | Develop and Submit - 90% MSE Wall RW 102 Ramp C | 0
SD1750 | SD1760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0
SD1760 | SD1770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0
SD1770 | SD1780 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0
SD1780 | SD1790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-1 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0
SD1800 | SD1810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0
SD1810 | SD1820 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Designer Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0
SD1820 | SD1830 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Revise & Resubmit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0
SD1830 | SD1840 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 8-2 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0
SD1850 | SD1860 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Develop & Submit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Designer Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0
SD1860 | SD1870 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Designer Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Revise & Resubmit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0
SD1870 | SD1880 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Revise & Resubmit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0
SD1880 | SD1890 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Design 2nd Review & Comnt Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0
SD1900 | SD1910 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0
SD1910 | SD1920 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0
SD1920 | SD1930 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0
SD1930 | SD1940 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0
SD1950 | SD1960 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0
SD1960 | SD1970 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Designer Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0
SD1970 | SD1980 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Revise & Resubmit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0
SD1980 | SD1990 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Design 2nd Review & Comnt Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0
SD2000 | SD2010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Develop & Submit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Designer Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0
SD2010 | SD2020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Designer Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Revise & Resubmit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0
SD2020 | SD2030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Revise & Resubmit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Design 2nd Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0
SD2030 | SD2040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Design 2nd Review & Comnt Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | FDOT - Review & Comment Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0
SD2300 | SD2310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Develop & Submit Shp Drwgs - RW 102 Ramp C | Designer Review & Comnt Shp Drwgs - RW 102 Ramp C | 0
SD2310 | SD2320 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Designer Review & Comnt Shp Drwgs - RW 102 Ramp C | Revise & Resubmit Shp Drwgs - RW 102 Ramp C | 0
SD2320 | SD2330 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Revise & Resubmit Shp Drwgs - RW 102 Ramp C | Design 2nd Review & Comnt Shp Drwgs - RW 102 Ramp C | 0
SD2330 | SD2340 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Design 2nd Review & Comnt Shp Drwgs - RW 102 Ramp C | FDOT - Review & Comment Shp Drwgs - RW 102 Ramp C | 0
D4630 | SD1750 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.1 R3 - Retaining Wall Design RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-1 Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-1 - Ramp B / Br 8 | 0
D4690 | SD1800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.2 R3 - Retaining Wall Design RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | Issue - RFC MSE Wall RW 8-2 Ramp B / Br 8 | Develop & Submit Shp Drwgs - RW 8-2 - Ramp B / Br 8 | 0
D4750 | SD1850 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.3 R3 - Retaining Wall Design RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | Issue - RFC MSE Wall RW 9-1 Ramp B/F / Br 8 | Develop & Submit Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | 0
D4810 | SD1900 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.4 R3 - Retaining Wall Design RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-2 Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | 0
D4870 | SD1950 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.5 R3 - Retaining Wall Design RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | Issue - RFC MSE Wall RW 9-3 Ramp B/F / Br 9 | Develop & Submit Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | 0
D4930 | SD2000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop & Submit Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | 0
D4990 | SD2300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.1.7 R3 - Retaining Wall Design RW 102 Ramp C | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | Issue - RFC MSE Wall RW 102 Ramp C | Develop & Submit Shp Drwgs - RW 102 Ramp C | 0
SD1790 | PC1150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.4 R3 Shp Drwgs - Retaining Wall RW 8-1 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.3.6.3.4 R3 Procurement - Retaining Wall RW 8-1 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-1 - Ramp B / Br 8 | Fab & Deliver - RW 8-1 - Ramp B / Br 8 | 0
SD1840 | PC1160 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.1 R3 Shp Drwgs - Retaining Wall RW 8-2 - Ramp B / Br 8 | I-275 - I-4 - FDOT - S2.4.3.6.3.1 R3 Procurement - Retaining Wall RW 8-2 - Ramp B / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 8-2 - Ramp B / Br 8 | Fab & Deliver - RW 8-2 - Ramp B / Br 8 | 0
SD1890 | PC1170 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.2 R3 Shp Drwgs - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | I-275 - I-4 - FDOT - S2.4.3.6.3.2 R3 Procurement - Retaining Wall RW 9-1 - Ramp B/F / Br 8 | FDOT - Review & Comment Shp Drwgs - RW 9-1 - Ramp B/F / Br 8 | Fab & Deliver - RW 9-1 - Ramp B/F / Br 8 | 0
SD1940 | PC1180 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.3 R3 Shp Drwgs - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.3.6.3.3 R3 Procurement - Retaining Wall RW 9-2 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-2 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-2 - Ramp B/F / Br 9 | 0
SD1990 | PC1190 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.5 R3 Shp Drwgs - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | I-275 - I-4 - FDOT - S2.4.3.6.3.5 R3 Procurement - Retaining Wall RW 9-3 - Ramp B/F / Br 9 | FDOT - Review & Comment Shp Drwgs - RW 9-3 - Ramp B/F / Br 9 | Fab & Deliver - RW 9-3 - Ramp B/F / Br 9 | 0
SD2040 | PC1200 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.2.1.6 R1 Shp Drwgs - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.4.3.4.1.6 R1 Procurement - Retaining Wall RW 100 I-4 EB (BR 3 & Br 4) | FDOT - Review & Comment Shp Drwgs - RW 100 I-4 EB (Br 3 & Br 4) | Fab & Deliver - RW 100 I-4 EB (Br 3 & Br 4) | 0
SD2340 | PC1210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.4.7 R3 Shp Drwgs - Retaining Wall RW 102 Ramp C | I-275 - I-4 - FDOT - S2.4.3.6.3.7 R3 Procurement - Retaining Wall RW 102 Ramp C | FDOT - Review & Comment Shp Drwgs - RW 102 Ramp C | Fab & Deliver - RW 102 Ramp C | 0
D3430 | A14700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Issue - RFC Cat1 Brg 05 Plans - R1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | EW-STR
D3430 | A15120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Issue - RFC Cat1 Brg 05 Plans - R1 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | EW-STR
Admin-1080 | D1500 | FS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.2 Right of Way | Anticipated Contract Execution Date | Owner Right of Way Acquisition | 0
A1150 | A15430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp NE - R1 - P1.S1 | Install DRG S-708 to S-717 - Ramp NE-B Sta 99 to 106 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
A1130 | A15010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Install DRG S-700 to S-703 - Ramp WE-B Sta 51 to 55 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
A1130 | A15420 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Install DRG S-705 to S-713/708 - Ramp WE-B Sta 55 to 60 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
A1130 | A15440 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.1 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE MOT | I-275 - I-4 - FDOT - S2.2.2.2.6 R1 - Ph1, Stg1 - Ramp WE-B / Ramp NE - Drainage | Install Temp Barrier - Ramp WE - R1 - P1.S1 | Install DRG S-718 to S-720 - Ramp WE-B Sta 66 to 69 - R1 - P1.S1 | 0 | SUB-TC-PCB | PIPE | H
D3550 | D1220 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.1 R3 Bridge 10 - Design Category 2 | Issue - RFC Cat1 Brg 09 Plans - R3 | Develop and Submit - 60% Cat2 Brg 10 Plans - R3 | 0
D3550 | D3620 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.3.10.5.5 R3 Bridge 11 - Design Category 1 | Issue - RFC Cat1 Brg 09 Plans - R3 | Develop and Submit - 90% Cat1 Brg 11 Plans - R3 | 0
D4040 | D4100 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | I-275 - I-4 - FDOT - S2.3.11.1.9 R1 - Retaining Wall Design RW 3-2 Br 3 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | Develop and Submit - 90% MSE Wall RW 3-2 Br 3 | 0
D2800 | D4040 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.1.8 R1 - Retaining Wall Design RW 3-1 Br 3 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | Develop and Submit - 90% MSE Wall RW 3-1 Br 3 | 0
D3430 | D2800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.3.11.4.6 R1 Bridge 03 Design Category 1 | Issue - RFC Cat1 Brg 05 Plans - R1 | Develop and Submit - 90% Cat1 Brg 03 Plans - R1 | 0
D4930 | D4400 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.1.6 R1 - Retaining Wall Design RW 100 I-4 EB (BR 3 & Br 4) | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | Issue - RFC MSE Wall RW 100 I-4 EB (Br 3 & 4) | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | 0
D4400 | D4460 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.12 R2 - Retaining Wall Design RW 6-1 - Ramp EN / Br 6 | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 6-1 Ramp EN / Br 6 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | 0
D4460 | D4520 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.12.1.1 R2 - Retaining Wall Design RW 7-1 - Ramp EN / Br 7 | I-275 - I-4 - FDOT - S2.3.12.1.2 R2 - Retaining Wall Design RW 7-2 - Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-1 Ramp EN / Br 7 | Develop and Submit - 90% MSE Wall RW 7-2 Ramp EN / Br 7 | 0
Admin-1045 | D3180 | SS | Completed | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | Begin Design | Develop and Submit - 60% - 60" Drainage System - R3 | 0
SD2350 | SD2360 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Develop & Submit Shp Drwgs - 60" Drainage Str | Designer Review & Comnt Shp Drwgs - 60" Drainage Str | 0
SD2360 | SD2370 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Designer Review & Comnt Shp Drwgs - 60" Drainage Str | Revise & Resubmit Shp Drwgs - 60" Drainage Str | 0
SD2370 | SD2380 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Revise & Resubmit Shp Drwgs - 60" Drainage Str | Design 2nd Review & Comnt Shp Drwgs - 60" Drainage Str | 0
SD2380 | SD2390 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Design 2nd Review & Comnt Shp Drwgs - 60" Drainage Str | FDOT - Review & Comment Shp Drwgs - 60" Drainage Str | 0
D3250 | SD2350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | Issue - RFC - 60" Drainage System - R3 | Develop & Submit Shp Drwgs - 60" Drainage Str | 0
SD2390 | PC1440 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.4.8.2 R3 Shop Drawings - 60" Drainage Structures | I-275 - I-4 - FDOT - S2.4.3.6 R3 Procurement | FDOT - Review & Comment Shp Drwgs - 60" Drainage Str | Fab & Deliver 60" Drainage Structures | 0
A36440 | A36550 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36550 | A36540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36540 | A36450 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36450 | A36480 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | Const 60" Storm Drainage - OUT-5 to OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36000 | A36560 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-9 - R3 | Excav for 60" Str - OUT-8 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36560 | A36570 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-8 - R3 | Excav for 60" Str - OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36570 | A36010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Excav for 60" Str - OUT-7 - R3 | Excav for 60" Str - OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36000 | A36440 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | Excav for 60" Str - OUT-9 - R3 | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36440 | A36570 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-9 to OUT-8 - R3 | Excav for 60" Str - OUT-7 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
D3250 | A36000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Issue - RFC - 60" Drainage System - R3 | Excav for 60" Str - OUT-9 - R3 | 0 |  | SUB-TUNNEL
A36550 | A36010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-8 to OUT-7 - R3 | Excav for 60" Str - OUT-6 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36540 | A36020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-7 to OUT-6 - R3 | Excav for 60" Str - OUT-5 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
A36450 | A36030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.5.8.2 R3 - Ph0 - 60" Drainage System | I-275 - I-4 - FDOT - S2.2.5.8.1 R3 - Ph0 - 60" Drainage - Str Excavation | Const 60" Storm Drainage - OUT-6 to OUT-5 - R3 | Excav for 60" Str - OUT-4 - R3 | 0 | SUB-TUNNEL | SUB-TUNNEL
D3430 | P1450 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.4.2 R1 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 05 Plans - R1 | Procure Girders - Bridge 5 | 0
P1450 | A14790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - FDOT - S2.2.2.2.4.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 1 | Procure Girders - Bridge 5 | Erect Girders - Brg 100865 - Span 1 - R1 - P1.S1 | 0 |  | ST-BEAM
P1450 | A15210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.2 R1 Procurement - Bridge Girders | I-275 - I-4 - FDOT - S2.2.2.2.4.4 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Span 2 | Procure Girders - Bridge 5 | Erect Girders - Brg 100865 - Span 2 - R1 - P1.S1 | 0 |  | ST-BEAM
D3310 | P1480 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.4.2 R1 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 01 Plans - R1 | Procure Girders - Bridge 1 | 0
D2080 | P1510 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 08 Plans - R3 | Procure Girders - Bridge 8 | 0
D3550 | P1520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.6.1 R3 Procurement - Bridge Girders | Issue - RFC Cat1 Brg 09 Plans - R3 | Procure Girders - Bridge 9 | 0
D3310 | P1200 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.1 R1 Bridge 01 Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 01 Plans - R1 | Procure Pile - Bridge 1 - R1 | 0
D2080 | P1430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.2 R3 Bridge 08 - Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 08 Plans - R3 | Procure Pile - Bridge 08 | 0
D3430 | P1590 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.4.3 R1 Bridge 05 Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 05 Plans - R1 | Procure Pile - Bridge 5 - R1 | 0
P1590 | A1650 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - End Bent 1 - R1 - P1.S1 | 0 |  | ST-PILE
P1590 | A15070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 |  | ST-PILE
P1590 | A14720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 |  | ST-PILE
P1590 | A15140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.3.4.3 R1 Procurement - Bridge Pile | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Procure Pile - Bridge 5 - R1 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 |  | ST-PILE
D1590 | A1070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Issue - RFC TTCP Plans - R1 Phase 1 | Install Advanced Warning signs | 0 |  | TC-Maint.
A1070 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Advanced Warning signs | Start Construction - R1 | 0 | TC-Maint.
D1590 | A1030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.2.2.1.1 R1 - Ph0 - MOT | Issue - RFC TTCP Plans - R1 Phase 1 | Install MOT - I-4 Exit Ramp - R1 - P0 | 0 |  | TC-Maint.
D5160 | D5170 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | Develop and Submit - Sign & Seal Early Pkg Eros - R1 | Issue - RFC Early Pkg Eros - R1 | 0 |  |  | H
D5140 | D5150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | Develop and Submit - Final Early Pkg Eros - R1 | Review and Approve - Final Early Pkg Eros - R1 | 0 |  |  | H
D5120 | D5130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | Develop and Submit - 90% Early Pkg Eros - R1 | Review and Approve - 90% Early Pkg Eros - R1 | 0 |  |  | H
D5130 | D5140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | Review and Approve - 90% Early Pkg Eros - R1 | Develop and Submit - Final Early Pkg Eros - R1 | 0 |  |  | H
D5150 | D5160 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | Review and Approve - Final Early Pkg Eros - R1 | Develop and Submit - Sign & Seal Early Pkg Eros - R1 | 0 |  |  | H
Admin-1045 | D5120 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | Begin Design | Develop and Submit - 90% Early Pkg Eros - R1 | 0
D5170 | A1000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Issue - RFC Early Pkg Eros - R1 | Mobilization | 0
A1020 | A1080 | FF | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | I-275 - I-4 - FDOT - S2.2.2.1.2 R1 - Ph0 - Temp Pavement | Clear and Grub | Cut/Fill to Grade - 13th Ave Temp Pav - R1 - P0 | 0 | SUB-EW-C&G | EW-SML
D3550 | P1610 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.5.3 R3 Bridge 09 - Design Category 1 | I-275 - I-4 - FDOT - S2.4.3.6.2 R3 Procurement - Bridge Pile | Issue - RFC Cat1 Brg 09 Plans - R3 | Procure Pile - Bridge 09 | 0
D1370 | U1000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | 0
D1370 | U1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | 0
D1370 | U1020 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | 0
D1370 | U1030 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | 0
D1370 | U1040 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | 0
D1370 | U1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | 0
D1370 | U1060 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | 0
D1370 | U1070 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | 0
D1370 | U1080 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | 0
D1370 | U1090 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | 0
D1370 | U1100 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | 0
D1370 | U1110 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | 0
D1370 | U1120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | 0
D1370 | U1130 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | 0
D1370 | U1140 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | Issue - RFC Utility Relocation Plans | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | 0
D1370 | U1150 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | 0
D1370 | U1160 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 3" WI GM (E 7th Ave) - TPG | 0
D1370 | U1170 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 6" PE GM (SMF 3A) - TPG | 0
D1370 | U1180 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | 0
D1370 | U1190 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 2" BS GM (E Oak Ave) - TPG | 0
D1370 | U1200 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | 0
D1370 | U1210 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 8" PE GM (E Columbus Dr) - TPG | 0
D1370 | U1220 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | 0
D1370 | U1230 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | 0
D1370 | U1240 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | 0
D1370 | U1250 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | Issue - RFC Utility Relocation Plans | Remove Existing 6" CS GM (Ramp NE) - TPG | 0
D1370 | U1260 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.3.2 Uniti Fiber/Southern Light - During Construction | Issue - RFC Utility Relocation Plans | Adj HH to grade 24x36x36- (256+20, 105' RT) - Uniti | 0
D1370 | U1270 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | 0
D1370 | U1280 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | 0
D1370 | U1290 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | 0
D1370 | U1300 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | 0
D1370 | U1310 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | 0
D1370 | U1320 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | 0
D1370 | U1330 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | 0
D1370 | U1340 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | 0
D1370 | U1350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | 0
D1370 | U1360 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | 0
D1370 | U1370 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | 0
D1370 | U1380 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | 0
D1370 | U1390 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | 0
D1370 | U1400 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | 0
D1370 | U1410 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | Issue - RFC Utility Relocation Plans | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | 0
D1260 | D1250 | SS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.3.11.5 Temporary Traffic Control Plans (TTCP) - R1 Phase 2 & 3 | Develop and Submit - 90% TTCP Plans - R1 Phase 1 | Develop and Submit - 90% TTCP Plans - R1 Phase 2 & 3 | 20
D5170 | A1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.2 R1 Early Package Design | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Issue - RFC Early Pkg Eros - R1 | Install Erosion Control Devices | 0 |  | SUB-EROSION
Admin-1045 | D2680 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.12.10 R2 Roadway Plans | Begin Design | Develop and Submit - 90% Roadway Plans - R2 | 0
Admin-1045 | D2740 | SS | Completed | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.3.10.24 R3 Roadway Design | Begin Design | Develop and Submit - 90% Roadway Plans - R3 | 0
A1630 | A14700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | 0 | EW- ALL EW | EW-STR
A1630 | A15050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 1 - Sta. 45 to 46 | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Grading - Brg 100865 - End Bent 1 - R1 - P1.S1 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | EW- ALL EW | EW- ALL EW
A15140 | A15050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | I-275 - I-4 - FDOT - S2.2.2.2.3 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - End Bent 2 - Sta. 49 to 50 | Drive Pile - Brg 100865 - Pier 2 - R1 - P1.S1 | Grading - Brg 100865 - End Bent 2 - R1 - P1.S1 | 0 | ST-PILE | EW- ALL EW
A14700 | A15120 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.2.2.4.1 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 1 | I-275 - I-4 - FDOT - S2.2.2.2.4.2 R1 - Ph1, Stg1 - Bridge 100865 - Ramp WE-B - Pier 2 | Excavate - Brg 100865 - Pier 1 - R1 - P1.S1 | Excavate - Brg 100865 - Pier 2 - R1 - P1.S1 | 0 | EW-STR | EW-STR
A1070 | A1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Install Advanced Warning signs | Install Erosion Control Devices | 0 | TC-Maint. | SUB-EROSION
D1590 | A1000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.11.3 Temporary Traffic Control Plans (TTCP) - R1 Phase 1 | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Issue - RFC TTCP Plans - R1 Phase 1 | Mobilization | 0
D3250 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.10.3 R3 60" Drainage System Design | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Issue - RFC - 60" Drainage System - R3 | Start Construction - R3 | 0
U1420 | U1430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | 0
D1370 | U1420 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | 0
D1370 | U1430 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | 0
D1370 | U1440 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 317+70, 73 L - TECO | 0
D1370 | U1450 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 91+25, 40 L - TECO | 0
D1370 | U1460 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 92+45, 50 L - TECO | 0
D1370 | U1470 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 93+35, 50 L - TECO | 0
D1370 | U1480 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 93+80, 60 L - TECO | 0
D1370 | U1490 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 94+40, 60 L - TECO | 0
D1370 | U1500 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 95+15, 60 L - TECO | 0
D1370 | U1510 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 95+95, 60 L - TECO | 0
D1370 | U1520 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 96+40, 65 L - TECO | 0
D1370 | U1530 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.2 City of Tampa Water Dept - During Construction | Issue - RFC Utility Relocation Plans | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | 0
D1370 | U1540 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.2 City of Tampa Water Dept - During Construction | Issue - RFC Utility Relocation Plans | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | 0
D1370 | U1550 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole - sta. 1802+90, 10 R - TECO | 0
D1370 | U1560 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole - sta. 1803+90, 10 R - TECO | 0
D1370 | U1570 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole - sta. 1805+30, 25 R - TECO | 0
D1370 | U1580 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole - sta. 1806+15, 10 R - TECO | 0
D1370 | U1590 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole - sta. 1806+90, 20 R - TECO | 0
D1370 | U1600 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | 0
D1370 | U1610 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | 0
D1370 | U1620 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 1802+90, 10 L - TECO | 0
D1370 | U1630 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 1805+55, 130 R - TECO | 0
D1370 | U1640 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole - sta. 1806+90, 85 R - TECO | 0
D1370 | U1650 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | 0
D1370 | U1660 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | 0
D1370 | U1670 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Utility Relocation Plans | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | 0
D1370 | U1680 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Utility Relocation Plans | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | 0
D1370 | U1690 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | 0
D1370 | U1700 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Utility Relocation Plans | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | 0
D1370 | U1710 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | Issue - RFC Utility Relocation Plans | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | 0
D1140 | A1010 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.6.12 Stormwater Pollution Prevention Plan (SWPPP) | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Review and Approve - SWPPP & NOI | Install Erosion Control Devices | 0 |  | SUB-EROSION
P1030 | A1000 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.1.2 Construction Quality Control Plan | I-275 - I-4 - FDOT - S2.2.1 Mobilization | Review and Approve - Construction Quality Control Plan | Mobilization | 0
D1370 | U1720 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Install Fiber Distrib HUB - 207+04, 100 L - FTR | 0
D1370 | U1730 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Install Fiber XBOX - 207+04, 110 L - FTR | 0
D1370 | U1740 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | 0
D1370 | U1750 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | 0
D1370 | U1760 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | 0
D1370 | U1770 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Fiber XBOX - 207+00, 5 L - FTR | 0
D1370 | U1780 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | 0
D1370 | U1790 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | 0
D1370 | U1800 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | 0
D1370 | U1810 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | 0
D1370 | U1820 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Install all Copper/Fiber Cables within project limits - FTR | 0
D1370 | U1830 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | Issue - RFC Utility Relocation Plans | Splice/Cutover new facilities within project limits - FTR | 0
U1730 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Fiber XBOX - 207+04, 110 L - FTR | Start Construction - R3 | 0
U1730 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Fiber XBOX - 207+04, 110 L - FTR | Start Construction - R1 | 0
U1740 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | Start Construction - R3 | 0
U1740 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 2-4 conduits (980’) - 207+10, 115 L to Nebraska/15th Ave - FTR | Start Construction - R1 | 0
U1750 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | Start Construction - R3 | 0
U1750 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Buried Fiber Tail - 213+70, 46 L to 214+00, 46 L - FTR | Start Construction - R1 | 0
U1760 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | Start Construction - R3 | 0
U1760 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Fiber Distrib HUB - 207+00, 1 L - FTR | Start Construction - R1 | 0
U1770 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Fiber XBOX - 207+00, 5 L - FTR | Start Construction - R3 | 0
U1770 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Fiber XBOX - 207+00, 5 L - FTR | Start Construction - R1 | 0
U1780 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | Start Construction - R3 | 0
U1780 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Buried Fiber Cable - 207+00, 1 L to 207+00, 84 L - FTR | Start Construction - R1 | 0
U1790 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | Start Construction - R3 | 0
U1790 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Aerial Fiber Cable - 207+00, 2 R to 207+00, 80 R - FTR | Start Construction - R1 | 0
U1800 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | Start Construction - R3 | 0
U1800 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove 3-4 conduits - 100+18, 14 L to 107+00, 23 L - FTR | Start Construction - R1 | 0
U1810 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | Start Construction - R3 | 0
U1810 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove 2-4 conduits - 100+18, 16 L to 100+58, 16 L - FTR | Start Construction - R1 | 0
U1820 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install all Copper/Fiber Cables within project limits - FTR | Start Construction - R3 | 0
U1820 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install all Copper/Fiber Cables within project limits - FTR | Start Construction - R1 | 0
U1830 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Splice/Cutover new facilities within project limits - FTR | Start Construction - R1 | 0
U1670 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 16" DIP Watermain - Sta. 43+50, 299 RT to sta. 43+50, 315 RT - COTW | Start Construction - R1 | 0
U1680 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | Start Construction - R3 | 0
U1680 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Place out of service 16" CAS Watermain - Sta. 43+50, 299 RT to sta. 120+50, 439 RT - COTW | Start Construction - R1 | 0
U1690 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R3 | 0
U1690 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove 16" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R1 | 0
U1700 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R3 | 0
U1700 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove 6" CAS Watermain - Sta. 120+40, 439 RT to sta. 120+40, 902 RT - COTW | Start Construction - R1 | 0
U1710 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | Start Construction - R3 | 0
U1710 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.1 City of Tampa Water Dept - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Restrain 6" CAS Watermain - Sta. 132+40, 45 LT to sta. 137+40, 47 LT - COTW | Start Construction - R1 | 0
U1420 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Start Construction - R3 | 0
U1420 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 311+72, 95 L to 313+95, 90L - TECO | Start Construction - R1 | 0
U1440 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 317+70, 73 L - TECO | Start Construction - R3 | 0
U1440 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 317+70, 73 L - TECO | Start Construction - R1 | 0
U1450 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 91+25, 40 L - TECO | Start Construction - R3 | 0
U1450 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 91+25, 40 L - TECO | Start Construction - R1 | 0
U1460 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 92+45, 50 L - TECO | Start Construction - R3 | 0
U1460 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 92+45, 50 L - TECO | Start Construction - R1 | 0
U1470 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 93+35, 50 L - TECO | Start Construction - R3 | 0
U1470 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 93+35, 50 L - TECO | Start Construction - R1 | 0
U1480 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 93+80, 60 L - TECO | Start Construction - R3 | 0
U1480 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 93+80, 60 L - TECO | Start Construction - R1 | 0
U1490 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 94+40, 60 L - TECO | Start Construction - R3 | 0
U1490 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 94+40, 60 L - TECO | Start Construction - R1 | 0
U1500 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 95+15, 60 L - TECO | Start Construction - R3 | 0
U1500 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 95+15, 60 L - TECO | Start Construction - R1 | 0
U1510 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 95+95, 60 L - TECO | Start Construction - R3 | 0
U1510 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 95+95, 60 L - TECO | Start Construction - R1 | 0
U1520 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 96+40, 65 L - TECO | Start Construction - R3 | 0
U1520 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 96+40, 65 L - TECO | Start Construction - R1 | 0
U1550 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole - sta. 1802+90, 10 R - TECO | Start Construction - R3 | 0
U1550 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole - sta. 1802+90, 10 R - TECO | Start Construction - R1 | 0
U1560 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole - sta. 1803+90, 10 R - TECO | Start Construction - R3 | 0
U1560 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole - sta. 1803+90, 10 R - TECO | Start Construction - R1 | 0
U1570 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole - sta. 1805+30, 25 R - TECO | Start Construction - R3 | 0
U1570 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole - sta. 1805+30, 25 R - TECO | Start Construction - R1 | 0
U1580 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole - sta. 1806+15, 10 R - TECO | Start Construction - R3 | 0
U1580 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole - sta. 1806+15, 10 R - TECO | Start Construction - R1 | 0
U1590 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole - sta. 1806+90, 20 R - TECO | Start Construction - R3 | 0
U1590 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole - sta. 1806+90, 20 R - TECO | Start Construction - R1 | 0
U1600 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | Start Construction - R3 | 0
U1600 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole & 13.2 KV OH Elec - sta. 1802-90, 10 R to 1806+90, 20 R - TECO | Start Construction - R1 | 0
U1610 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | Start Construction - R3 | 0
U1610 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pole & 240V OH Elec - sta. 1806-90, 85 R to 1807-60, 60 R - TECO | Start Construction - R1 | 0
U1620 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 1802+90, 10 L - TECO | Start Construction - R3 | 0
U1620 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 1802+90, 10 L - TECO | Start Construction - R1 | 0
U1630 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 1805+55, 130 R - TECO | Start Construction - R3 | 0
U1630 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 1805+55, 130 R - TECO | Start Construction - R1 | 0
U1640 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole - sta. 1806+90, 85 R - TECO | Start Construction - R3 | 0
U1640 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole - sta. 1806+90, 85 R - TECO | Start Construction - R1 | 0
U1650 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | Start Construction - R3 | 0
U1650 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole & 13.2 KV OH Elec - sta. 1802-90, 10 L to 1807+60, 60 R - TECO | Start Construction - R1 | 0
U1660 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | Start Construction - R3 | 0
U1660 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole & 240V OH Elec - sta. 1806-90, 85 R - TECO | Start Construction - R1 | 0
U1430 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | Start Construction - R3 | 0
U1430 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.5.1 Tampa Electric Company (TECO) - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Pole & 13.2 KV Overhead Elec - sta. 311+72, 73 L to 313+35, 90 L - TECO | Start Construction - R1 | 0
U1840 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | Start Construction - R3 | 0
U1840 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | Start Construction - R1 | 0
U1850 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 6" PE GM (E Columbus Dr) - TPG | Start Construction - R3 | 0
U1850 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 6" PE GM (E Columbus Dr) - TPG | Start Construction - R1 | 0
U1860 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 6" PE GM (N Mitchell Ave) - TPG | Start Construction - R3 | 0
U1860 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 6" PE GM (N Mitchell Ave) - TPG | Start Construction - R1 | 0
U1720 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Fiber Distrib HUB - 207+04, 100 L - FTR | Start Construction - R3 | 0
U1720 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.1 Frontier Florida LLC Prior to Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Fiber Distrib HUB - 207+04, 100 L - FTR | Start Construction - R1 | 0
U1000 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | Start Construction - R3 | 0
U1000 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Buried Cable - 717+54+/- B/L I-275 to 717+54+/- B/L I-275 - FTR | Start Construction - R1 | 0
U1010 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | Start Construction - R3 | 0
U1010 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 4-4 U/G System - 90+05+/-RAMP EN, 13’L +/- to 90+05+/-RAMP EN, 13’L+/- - FTR | Start Construction - R1 | 0
U1020 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | Start Construction - R3 | 0
U1020 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 6-4 U/G System - 90+46+/- RAMP EN, to 90+46+/- RAMP EN, - FTR | Start Construction - R1 | 0
U1030 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | Start Construction - R3 | 0
U1030 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 1- BT 200 - 70+03 RAMP WE-B to 70+03 RAMP WE-B - FTR | Start Construction - R1 | 0
U1040 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | Start Construction - R3 | 0
U1040 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Manhole & 4 Way Con - 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) to 1809+20+/-, 60R, PED TRAIL (NEBRASKA AVE.) | Start Construction - R1 | 0
U1050 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | Start Construction - R3 | 0
U1050 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pull Box - 415+87, 215’L to 415+87, 215’L - FTR | Start Construction - R1 | 0
U1060 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | Start Construction - R3 | 0
U1060 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 2-4 conduits (23’) - 415+87, 215’L to 414+87, 196’L - FTR | Start Construction - R1 | 0
U1070 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | Start Construction - R3 | 0
U1070 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pull Box - 414+87, 196’L to 414+87, 196’L - FTR | Start Construction - R1 | 0
U1080 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | Start Construction - R3 | 0
U1080 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 2-4 conduits (435’ - 415+13, 196’L to 416+86, 182’R - FTR | Start Construction - R1 | 0
U1090 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | Start Construction - R3 | 0
U1090 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Pull Box - 416+86, 182’R to 416+86, 182’R - FTR | Start Construction - R1 | 0
U1100 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | Start Construction - R3 | 0
U1100 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 2-4 conduits (43’) - 416+86, 182’R to 417+22, 166’R - FTR | Start Construction - R1 | 0
U1110 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | Start Construction - R3 | 0
U1110 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Manhole - 415+25, 1’L to 415+25, 1’L - FTR | Start Construction - R1 | 0
U1120 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | Start Construction - R3 | 0
U1120 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 4-4 conduits (437’) - 415+03, 215’L to 417+29, 164’R - FTR | Start Construction - R1 | 0
U1130 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | Start Construction - R3 | 0
U1130 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install O.O.S. Aerial Cable - 20+00 N. Central Ave., 36’L to 27+10 N. Lamar Ave., 105’L - FTR | Start Construction - R1 | 0
U1140 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | Start Construction - R3 | 0
U1140 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.1.2 Frontier Florida LLC During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install Anchor & Guy - 33+78, 7’R B/L const. of sdwlk, north of 7th Ave. to 33+78, 7’R B/L const. of sdwlk, north of 7t | Start Construction - R1 | 0
U1150 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | Start Construction - R3 | 0
U1150 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Retire & Remove Existing 6" PE GM (E 7th Ave) - TPG | Start Construction - R1 | 0
U1160 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 3" WI GM (E 7th Ave) - TPG | Start Construction - R3 | 0
U1160 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 3" WI GM (E 7th Ave) - TPG | Start Construction - R1 | 0
U1170 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 6" PE GM (SMF 3A) - TPG | Start Construction - R3 | 0
U1170 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 6" PE GM (SMF 3A) - TPG | Start Construction - R1 | 0
U1180 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | Start Construction - R3 | 0
U1180 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 8" PE GM/12" CS GM (N Central Ave) - TPG | Start Construction - R1 | 0
U1190 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 2" BS GM (E Oak Ave) - TPG | Start Construction - R3 | 0
U1190 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 2" BS GM (E Oak Ave) - TPG | Start Construction - R1 | 0
U1200 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | Start Construction - R3 | 0
U1200 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Retire & Remove Existing 6" PE GM (E Columbus Dr & Taliaferro Ave) - TPG | Start Construction - R1 | 0
U1210 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 8" PE GM (E Columbus Dr) - TPG | Start Construction - R3 | 0
U1210 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 8" PE GM (E Columbus Dr) - TPG | Start Construction - R1 | 0
U1220 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | Start Construction - R3 | 0
U1220 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Retire & Remove Existing 2" PE GM (N 10th St and E 14th Ave) - TPG | Start Construction - R1 | 0
U1230 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | Start Construction - R3 | 0
U1230 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 2" PE & 4" CS GM (Along E 14th Ave) - TPG | Start Construction - R1 | 0
U1240 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | Start Construction - R3 | 0
U1240 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 4" & 8" CI GM (E 14th Ave and N 12th St) - TPG | Start Construction - R1 | 0
U1250 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Remove Existing 6" CS GM (Ramp NE) - TPG | Start Construction - R3 | 0
U1250 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.2.2 TECO Peoples Gas - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Remove Existing 6" CS GM (Ramp NE) - TPG | Start Construction - R1 | 0
U1270 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | Start Construction - R3 | 0
U1270 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 609+52.68, 19.41’ Lt. - COTWW | Start Construction - R1 | 0
U1280 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | Start Construction - R3 | 0
U1280 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 611+58.10, 67.32’ Lt. - COTWW | Start Construction - R1 | 0
U1290 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | Start Construction - R3 | 0
U1290 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 59+95.22, 5.96’ Rt. - COTWW | Start Construction - R1 | 0
U1300 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | Start Construction - R3 | 0
U1300 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | WW Lamp Hole Sta. 63+6.75, Baseline - COTWW | Start Construction - R1 | 0
U1310 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | Start Construction - R3 | 0
U1310 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 504+48.46, 10.14’ Lt. - COTWW | Start Construction - R1 | 0
U1320 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | Start Construction - R3 | 0
U1320 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 504+65.12, 13.85’ Lt. - COTWW | Start Construction - R1 | 0
U1330 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | Start Construction - R3 | 0
U1330 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 507+64.19, 19.40’ Lt. - COTWW | Start Construction - R1 | 0
U1340 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | Start Construction - R3 | 0
U1340 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | WW Manhole Sta. 131+85, 286 ‘ Rt. - COTWW | Start Construction - R1 | 0
U1350 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | Start Construction - R3 | 0
U1350 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 131+85, 286’ Rt. to Sta. 132+36, 286’ Rt. - COTWW | Start Construction - R1 | 0
U1360 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | Start Construction - R3 | 0
U1360 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | WW Manhole Sta. 128+19, 531’ Rt. - COTWW | Start Construction - R1 | 0
U1370 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R3 | 0
U1370 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 128+19, 531’ Rt. to Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R1 | 0
U1380 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R3 | 0
U1380 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | WW Manhole Sta. 130+25, 553’ Rt. - COTWW | Start Construction - R1 | 0
U1390 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | Start Construction - R3 | 0
U1390 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | 8" VCP WW (Lined) - Sta. 130+25, 553’ Rt. to Sta. 132+35, 553’ Rt. - COTWW | Start Construction - R1 | 0
U1400 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | Start Construction - R3 | 0
U1400 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | WW Manhole Sta. 66+29, 3’ Lt. - COTWW | Start Construction - R1 | 0
U1410 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | Start Construction - R3 | 0
U1410 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.4.2 City of Tampa Wastewater Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | WW Manhole Sta. 16+32, 5’ Rt. - COTWW | Start Construction - R1 | 0
U1530 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | Start Construction - R3 | 0
U1530 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 60" Steel Casing - Sta. 61+50, 72 LT to sta. 61+50, 56 RT - COTW | Start Construction - R1 | 0
U1540 | A26350 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - FDOT - S2.2.5.7 R3 - Milestones | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | Start Construction - R3 | 0
U1540 | A1050 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.4.2.8.2 City of Tampa Water Dept - During Construction | I-275 - I-4 - FDOT - S2.2.2.7 R1 - Milestones | Install 30" Steel Casing - Sta. 66+50, 82 LT to sta. 66+50, 44 RT - COTW | Start Construction - R1 | 0
D1370 | U1840 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | Issue - RFC Utility Relocation Plans | Cut & Cap Existing 2" PE GM (NE Corner) - TPG | 0
D1370 | U1850 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | Issue - RFC Utility Relocation Plans | Install 6" PE GM (E Columbus Dr) - TPG | 0
D1370 | U1860 | FS | Not Started | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.25 Utility Relocation Plans | I-275 - I-4 - FDOT - S2.4.2.2.1 TECO Peoples Gas - Prior to Construction | Issue - RFC Utility Relocation Plans | Install 6" PE GM (N Mitchell Ave) - TPG | 0
Admin-1040 | Admin-1070 | FF | In Progress | Not Started | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.1 Project Administration | I-275 - I-4 - FDOT - S2.1 Project Administration | LOE - Project Duration | Contract Completion (Nov. 7th 2026) | 0
D1040 | D1200 | FF | In Progress | In Progress | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2 | I-275 - I-4 - FDOT - S2.3.3 Design Survey/SUE | I-275 - I-4 - FDOT - S2.3.11.19 R1 Roadway Design | Perform Design Survey [LoE] | Develop and Submit - 90% Roadway Plans - R1 | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Day DateFormat=M/d/yyyy CurrencyFormat=Dollar