## TASK
task_code | status_code | wbs_id | wbs_name | task_name | start_date | end_date | act_start_date | act_end_date | target_drtn_hr_cnt | act_drtn_hr_cnt | remain_drtn_hr_cnt | total_float_hr_cnt | float_path | resource_list | actv_code_crew_type_id | actv_code_work_type_id | delete_record_flag
Activity ID | Activity Status | WBS Code | (*)WBS Name | Activity Name | (*)Start | (*)Finish | Actual Start | Actual Finish | Original Duration(d) | (*)Actual Duration(d) | Remaining Duration(d) | (*)Total Float(d) | (*)Float Path | (*)Resources | CREW TYPE | WORK TYPE | Delete This Row
DEMO | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | Demo Traffic Railing 100201 - NB: over Floribraska - Ph1-S1 | 2022-02-14 21:00 | 2022-02-19 03:00 | 2022-02-14 21:00 | 2022-02-19 03:00 | 3 | 5 | 0 |  |  | Demolition Crews
EGC110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | 2022-03-18 08:00 | 2022-05-14 16:00 | 2022-03-18 08:00 | 2022-05-14 16:00 | 6 | 41 | 0 |  |  | Light Cut/Fill Earthwork Crew
PAV170 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 2022-10-04 08:00 | 2022-10-07 16:00 | 2022-10-04 08:00 | 2022-10-07 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
STAB180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 2022-12-01 08:00 | 2022-12-12 16:00 |  |  | 8 | 0 | 8 | 10 |  | Cement Subgrade Crew
BASE180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Black Base - NB: 735+46-746+91 - Ph1-S1 | 2023-01-30 08:00 | 2023-02-07 16:00 |  |  | 7 | 0 | 7 | -2 | 1 | Agg Base Crew
DEMO1310 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | Demo Edge of Deck 100201 - NB: over Floribraska - Ph1-S1 | 2022-02-16 21:00 | 2022-02-19 | 2022-02-16 21:00 | 2022-02-19 | 6 | 2 | 0 |  |  | Demo Bridge Crew
PAV310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | 2023-03-10 08:00 | 2023-03-14 16:00 |  |  | 3 | 0 | 3 | 8 |  | Sub - Asphalt Paving Crew
DEMO1330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | Demo End of Existing End Bent - NB: over Floribraska - Ph1-S1 | 2022-02-19 08:00 | 2022-02-19 16:00 | 2022-02-19 08:00 | 2022-02-19 16:00 | 4 | 0 | 0 |  |  | Demo Bridge Crew
CP110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | 2023-02-08 08:00 | 2023-02-22 16:00 |  |  | 11 | 0 | 11 | -2 | 1 | Concrete Paving Crews
PILE100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 4 | 14 | 0 |  |  | Pile Driving Crew
DRG100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: Existing to S-28 to S-29 to Existing (36") - NB: 736-737 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-12 16:00 | 2022-07-11 08:00 | 2022-07-12 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DS100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Install 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | 2022-03-03 08:00 | 2022-03-18 16:00 | 2022-03-03 08:00 | 2022-03-18 16:00 | 10 | 12 | 0 |  |  | Sub - Drilled Shaft Crew
EGC300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | 2023-04-10 08:00 | 2023-04-17 16:00 |  |  | 6 | 0 | 6 | 23 |  | Light Cut/Fill Earthwork Crew
SUBS100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-11 08:00 | 2022-08-19 16:00 | 2022-07-11 08:00 | 2022-08-19 16:00 | 5 | 30 | 0 |  |  | Substructure Crew
STAB500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 2023-10-12 08:00 | 2023-10-25 16:00 |  |  | 10 | 0 | 10 | -2 | 10 | Cement Subgrade Crew
SUBS110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 2022-04-06 08:00 | 2022-04-16 16:00 | 2022-04-06 08:00 | 2022-04-16 16:00 | 5 | 8 | 0 |  |  | Substructure Crew
BASE700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Black Base - SB: 735+46-746+91 - Ph1-S1 | 2023-11-06 08:00 | 2023-11-14 16:00 |  |  | 6 | 0 | 6 | 0 | 13 | Agg Base Crew
PAV470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | 2023-12-19 08:00 | 2023-12-21 16:00 |  |  | 3 | 0 | 3 | 14 |  | Sub - Asphalt Paving Crew
SUBS120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 2022-04-07 08:00 | 2022-04-16 16:00 | 2022-04-07 08:00 | 2022-04-16 16:00 | 5 | 7 | 0 |  |  | Substructure Crew
CP440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | 2023-11-15 08:00 | 2023-11-21 16:00 |  |  | 5 | 0 | 5 | 19 |  | Concrete Paving Crews
DRG1000 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | 2023-04-27 08:00 | 2023-05-02 16:00 |  |  | 4 | 0 | 4 | 30 |  | Drainage Crew - Combo
SUBS130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-11 08:00 | 2022-07-15 16:00 | 2022-07-11 08:00 | 2022-07-15 16:00 | 5 | 5 | 0 |  |  | Substructure Crew
SUBS180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-11 08:00 | 2022-07-12 16:00 | 2022-07-11 08:00 | 2022-07-12 16:00 | 5 | 2 | 0 |  |  | Substructure Crew
EGC120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | 2022-04-18 08:00 | 2022-05-30 16:00 | 2022-04-18 08:00 | 2022-05-30 16:00 | 10 | 30 | 0 |  |  | Light Cut/Fill Earthwork Crew
SUBS190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-05-23 08:00 | 2022-06-08 16:00 | 2022-05-23 08:00 | 2022-06-08 16:00 | 5 | 12 | 0 |  |  | Substructure Crew
STAB190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 2022-12-12 08:00 | 2022-12-15 16:00 |  |  | 4 | 0 | 4 | 7 |  | Cement Subgrade Crew
BBM100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 2022-11-08 08:00 | 2022-11-09 16:00 | 2022-11-08 08:00 | 2022-11-09 16:00 | 3 | 1 | 0 |  |  | Erection Crew
BASE190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Black Base - NB: 748+30-757+10 - Ph1-S1 | 2023-02-08 08:00 | 2023-02-16 16:00 |  |  | 7 | 0 | 7 | 2 |  | Agg Base Crew
SUPR100 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Overhang 100201 - NB: over Floribraska - Ph1-S1 | 2022-11-09 08:00 | 2022-11-18 01:00 | 2022-11-09 08:00 |  | 5 | 1 | 5 | -2 | 7 | Super-Structure Crew
PAV330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | 2023-03-27 08:00 | 2023-03-29 16:00 |  |  | 3 | 0 | 3 | 8 |  | Sub - Asphalt Paving Crew
SIP100 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install SIP Deck Pans 100201 - NB: over Floribraska - Ph1-S1 | 2022-11-10 08:00 | 2022-11-18 01:00 | 2022-11-10 08:00 |  | 5 | 0 | 5 | -2 | 1 | Deck Crew
CP120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | 2023-02-23 08:00 | 2023-03-08 16:00 |  |  | 10 | 0 | 10 | -2 | 1 | Concrete Paving Crews
DRG240 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | 2022-08-18 08:00 | 2022-08-19 16:00 | 2022-08-18 08:00 | 2022-08-19 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
MS-IP1F | Not Started | 3462-FDOT-Owner-12.4.IP1.1 | Construction: Initial Phase 1: Milestones | End of Initial Phase 1 |  | 2023-02-03 16:00 |  |  | 0 | 0 | 0 | 61
EGC290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 2023-03-10 08:00 | 2023-03-20 16:00 |  |  | 7 | 0 | 7 | 37 |  | Light Cut/Fill Earthwork Crew
SUPR110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | 2022-11-18 08:00 | 2022-11-30 16:00 |  |  | 6 | 0 | 6 | -2 | 1 | Super-Structure Crew
MS-P1S1F | Not Started | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | End of Phase 1, Stage 1 |  | 2024-04-11 16:00 |  |  | 0 | 0 | 0 | -4 | 1
SUPR120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Set Deck Screed 100201 - NB: over Floribraska - Ph1-S1 | 2022-12-05 08:00 | 2022-12-06 16:00 |  |  | 2 | 0 | 2 | -2 | 1 | Super-Structure Crew
STAB470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 2023-09-26 08:00 | 2023-10-06 16:00 |  |  | 9 | 0 | 9 | 1 | 23 | Cement Subgrade Crew
MS-P1S1S | Completed | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Start of Phase 1, Stage 1 | 2021-12-08 08:00 |  | 2021-12-08 08:00 |  | 0 | 0 | 0
SUPR170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Pour Deck 100201 - NB: over Floribraska - Ph1-S1 | 2022-12-06 21:00 | 2022-12-07 05:00 |  |  | 1 | 0 | 1 | -2 | 1 | Super-Structure Crew
MS-P1S1S1S | Completed | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Start of Phase 1, Stage 1, Step 1 | 2021-11-08 08:00 |  | 2021-11-08 08:00 |  | 0 | 0 | 0
BASE660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Black Base - SB: 748+30-757+10 - Ph1-S1 | 2023-10-26 08:00 | 2023-11-01 16:00 |  |  | 5 | 0 | 5 | 0 | 13 | Agg Base Crew
B1200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Deck Cure 100201 - NB: over Floribraska - Ph1-S1 | 2022-12-07 08:00 | 2022-12-20 16:00 |  |  | 14 | 0 | 14 | -2 | 1
PAV460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | 2023-11-30 08:00 | 2023-12-04 16:00 |  |  | 3 | 0 | 3 | 4 |  | Sub - Asphalt Paving Crew
CP430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | 2023-11-02 08:00 | 2023-11-08 16:00 |  |  | 5 | 0 | 5 | 4 |  | Concrete Paving Crews
SUPR230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100201 - NB: over Floribraska - Ph1-S1 | 2022-12-21 08:00 | 2023-01-05 16:00 |  |  | 6 | 0 | 6 | -2 | 1 | Approach Slab Crew
MS-P1S1S1F | Not Started | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | End of Phase 1, Stage 1, Step 1 |  | 2022-12-15 16:00 |  |  | 0 | 0 | 0 | 584
DRG1020 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-10 16:00 |  |  | 2 | 0 | 2 | 30 |  | Drainage Crew - Combo
MS-P1S1S2S | Not Started | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Start of Phase 1, Stage 1, Step 2 | 2022-11-16 08:00 |  |  |  | 0 | 0 | 0 | 628
EGC130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | 2022-05-02 08:00 | 2022-06-10 16:00 | 2022-05-02 08:00 | 2022-06-10 16:00 | 5 | 29 | 0 |  |  | Light Cut/Fill Earthwork Crew
STAB200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 2022-12-16 08:00 | 2023-01-03 16:00 |  |  | 7 | 0 | 7 | 13 |  | Cement Subgrade Crew
B1220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Approach Slabs Cure 100201 - NB: over Floribraska - Ph1-S1 | 2023-01-06 08:00 | 2023-01-19 16:00 |  |  | 14 | 0 | 14 | 3
MS-P1S1S2F | Not Started | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | End of Phase 1, Stage 1, Step 2 |  | 2023-01-10 16:00 |  |  | 0 | 0 | 0 | 78
BASE200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Black Base - NB: 757+10-759+97 - Ph1-S1 | 2023-02-20 08:00 | 2023-02-24 16:00 |  |  | 5 | 0 | 5 | 10 |  | Agg Base Crew
BW540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | 2023-01-20 08:00 | 2023-01-27 16:00 |  |  | 6 | 0 | 6 | 1 |  | Concrete Barrier Crew
TCC120 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.0 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | 2021-11-01 08:00 | 2021-11-01 16:00 | 2021-11-01 08:00 | 2021-11-01 16:00 | 2 | 1 | 0 |  |  | Maintenance of Traffic Crew
CP170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-11 16:00 |  |  | 3 | 0 | 3 | -2 | 1 | Concrete Paving Crews
DEMO1340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | 2022-02-17 21:00 | 2022-02-19 05:00 | 2022-02-17 21:00 | 2022-02-19 05:00 | 3 | 1 | 0 |  |  | Demolition Crews
CP130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | 2023-03-09 08:00 | 2023-03-13 16:00 |  |  | 3 | 0 | 3 | 2 |  | Concrete Paving Crews
DEMO120 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Demo Existing Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | 2021-11-11 08:00 | 2021-11-11 16:00 | 2021-11-11 08:00 | 2021-11-11 16:00 | 3 | 0 | 0 |  |  | Demolition Crews
EGC280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | 2023-02-27 08:00 | 2023-03-09 16:00 |  |  | 9 | 0 | 9 | 37 |  | Light Cut/Fill Earthwork Crew
STAB450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Stabilization - SB: 757+10-759+97 - Ph1-S1 | 2023-09-18 08:00 | 2023-09-25 16:00 |  |  | 6 | 0 | 6 | 0 | 13 | Cement Subgrade Crew
R610 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | 2022-02-01 08:00 | 2022-02-16 16:00 | 2022-02-01 08:00 | 2022-02-16 16:00 | 12 | 12 | 0 |  |  | CIP Wall Crew
DEMO1350 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Edge of Deck 100207 - NB: over East Lake - Ph1-S1 | 2022-02-18 03:00 | 2022-02-19 04:00 | 2022-02-18 03:00 | 2022-02-19 04:00 | 4 | 0 | 0 |  |  | Demo Bridge Crew
R615 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Pour Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | 2022-01-26 08:00 | 2022-04-15 16:00 | 2022-01-26 08:00 | 2022-04-15 16:00 | 8 | 58 | 0 |  |  | Concrete Flatwork Crew
BASE640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Black Base - SB: 757+10-759+97 - Ph1-S1 | 2023-10-23 08:00 | 2023-10-25 16:00 |  |  | 3 | 0 | 3 | 0 | 14 | Agg Base Crew
DEMO1370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | 2022-02-21 08:00 | 2022-02-24 16:00 | 2022-02-21 08:00 | 2022-02-24 16:00 | 4 | 4 | 0 |  |  | Demo Bridge Crew
PILE130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 4 | 14 | 0 |  |  | Pile Driving Crew
CP520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | 2023-11-20 08:00 | 2023-11-29 16:00 |  |  | 5 | 0 | 5 | 16 |  | Concrete Paving Crews
R620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Pour Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | 2022-11-14 08:00 | 2022-11-21 16:00 |  |  | 6 | 0 | 6 | 95 |  | Concrete Flatwork Crew
PAV160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | 2022-12-07 08:00 | 2022-12-13 16:00 |  |  | 5 | 0 | 5 | 87 |  | Sub - Asphalt Paving Crew
CP410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | 2023-10-26 08:00 | 2023-10-27 16:00 |  |  | 2 | 0 | 2 | 6 |  | Concrete Paving Crews
DS110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | 2022-03-22 08:00 | 2022-04-05 16:00 | 2022-03-22 08:00 | 2022-04-05 16:00 | 10 | 11 | 0 |  |  | Sub - Drilled Shaft Crew
EGC140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | 2022-05-13 08:00 | 2022-06-10 16:00 | 2022-05-13 08:00 | 2022-06-10 16:00 | 8 | 20 | 0 |  |  | Light Cut/Fill Earthwork Crew
DEMO160 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Demo Existing Slope Pavement @ East Lake Ave.- South Side - Ph1-S1-S1 | 2021-11-01 08:00 | 2021-11-01 16:00 | 2021-11-01 08:00 | 2021-11-01 16:00 | 4 | 1 | 0 |  |  | Demolition Crews
SUBS200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 2022-07-20 08:00 | 2022-07-26 16:00 | 2022-07-20 08:00 | 2022-07-26 16:00 | 5 | 5 | 0 |  |  | Substructure Crew
SUBS210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 2022-04-21 08:00 | 2022-05-14 16:00 | 2022-04-21 08:00 | 2022-05-14 16:00 | 5 | 17 | 0 |  |  | Substructure Crew
SUBS220 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 2022-05-26 08:00 | 2022-06-09 16:00 | 2022-05-26 08:00 | 2022-06-09 16:00 | 5 | 10 | 0 |  |  | Substructure Crew
R635 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Reinforce / Pour Gravity Wall W-5D @ East Lake Ave. - South Side - Ph1-S1-S1 | 2021-11-04 08:00 | 2021-11-23 16:00 | 2021-11-04 08:00 | 2021-11-23 16:00 | 12 | 13 | 0 |  |  | CIP Wall Crew
STAB210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 2023-01-09 08:00 | 2023-01-17 16:00 |  |  | 6 | 0 | 6 | 10 |  | Cement Subgrade Crew
SUBS310 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 2022-07-12 08:00 | 2022-07-14 16:00 | 2022-07-12 08:00 | 2022-07-14 16:00 | 5 | 3 | 0 |  |  | Substructure Crew
R640 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Pour Slope Pavement @ East Lake Ave. - South Side - Ph1-S1-S1 | 2022-01-24 08:00 | 2022-04-16 16:00 | 2022-01-24 08:00 | 2022-04-16 16:00 | 5 | 60 | 0 |  |  | Concrete Flatwork Crew
SUBS290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | 2022-05-25 08:00 | 2022-06-08 16:00 | 2022-05-25 08:00 | 2022-06-08 16:00 | 5 | 10 | 0 |  |  | Substructure Crew
BASE220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Black Base - NB: 761+67-767+00 - Ph1-S1 | 2023-03-08 08:00 | 2023-03-16 16:00 |  |  | 7 | 0 | 7 | 12 |  | Agg Base Crew
R645 | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Pour Sidewalk @ East Lake Ave. - South Side - Ph1-S1-S1 | 2022-04-19 08:00 | 2022-11-15 16:00 | 2022-04-19 08:00 |  | 5 | 144 | 2 | 400 |  | Concrete Flatwork Crew
SUBS300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 2022-07-04 08:00 | 2022-07-07 16:00 | 2022-07-04 08:00 | 2022-07-07 16:00 | 5 | 3 | 0 |  |  | Substructure Crew
CP180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | 2023-04-19 08:00 | 2023-04-27 16:00 |  |  | 7 | 0 | 7 | 9 |  | Concrete Paving Crews
DEMO180 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 2022-01-12 08:00 | 2022-01-15 16:00 | 2022-01-12 08:00 | 2022-01-15 16:00 | 5 | 3 | 0 |  |  | Demolition Crews
CP140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | 2023-03-17 08:00 | 2023-03-23 16:00 |  |  | 5 | 0 | 5 | 12 |  | Concrete Paving Crews
BBM110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 2022-11-14 21:00 | 2022-11-17 03:00 |  |  | 3 | 0 | 3 | 7 |  | Erection Crew
SUPR130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Overhang 100207 - NB: over East Lake - Ph1-S1 | 2022-11-17 03:00 | 2022-11-28 22:00 |  |  | 5 | 0 | 5 | 7 |  | Super-Structure Crew
DRG330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-59 to S-60 (36") - NB: 764-765 - Ph1-S1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
SIP110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install SIP Deck Pans100207 - NB: over East Lake - Ph1-S1 | 2022-11-17 03:00 | 2022-11-28 22:00 |  |  | 5 | 0 | 5 | 7 |  | Deck Crew
R655 | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | 2022-06-06 08:00 | 2022-11-16 16:00 | 2022-06-06 08:00 |  | 10 | 111 | 3 | 160 |  | CIP Wall Crew
EGC260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 2023-02-07 08:00 | 2023-02-15 16:00 |  |  | 7 | 0 | 7 | 23 |  | Light Cut/Fill Earthwork Crew
R660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Pour Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 2022-11-17 08:00 | 2022-11-22 16:00 |  |  | 4 | 0 | 4 | 396 |  | Concrete Flatwork Crew
SUPR180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form Deck 100207 - NB: over East Lake - Ph1-S1 | 2022-11-29 08:00 | 2022-12-06 16:00 |  |  | 6 | 0 | 6 | 5 |  | Super-Structure Crew
STAB430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 2023-08-18 08:00 | 2023-08-25 16:00 |  |  | 6 | 0 | 6 | 13 |  | Cement Subgrade Crew
R665 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Pour Sidewalk @ MLK Blvd.- South Side - Ph1-S1-S1 | 2022-11-28 08:00 | 2022-12-02 16:00 |  |  | 5 | 0 | 5 | 396 |  | Concrete Flatwork Crew
DEMO220 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Demo Existing Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | 2021-11-18 08:00 | 2021-11-18 16:00 | 2021-11-18 08:00 | 2021-11-18 16:00 | 4 | 1 | 0 |  |  | Demolition Crews
SUPR210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Set Deck Screed 100207 - NB: over East Lake - Ph1-S1 | 2022-12-12 08:00 | 2022-12-13 16:00 |  |  | 2 | 0 | 2 | 5 |  | Super-Structure Crew
SUPR240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Pour Deck 100207 - NB: over East Lake - Ph1-S1 | 2022-12-13 21:00 | 2022-12-14 05:00 |  |  | 1 | 0 | 1 | 6 |  | Super-Structure Crew
R675 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | 2021-12-01 08:00 | 2022-02-18 16:00 | 2021-12-01 08:00 | 2022-02-18 16:00 | 12 | 51 | 0 |  |  | CIP Wall Crew
B1440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - NB: over East Lake - Ph1-S1 | 2022-12-14 08:00 | 2022-12-27 16:00 |  |  | 14 | 0 | 14 | 7
R680 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Pour Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | 2022-01-27 08:00 | 2022-04-16 16:00 | 2022-01-27 08:00 | 2022-04-16 16:00 | 6 | 57 | 0 |  |  | Concrete Flatwork Crew
SUPR310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | 2023-01-06 08:00 | 2023-01-13 16:00 |  |  | 6 | 0 | 6 | -2 | 1 | Approach Slab Crew
B1460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Approach Slabs Cure 100207 - NB: over East Lake - Ph1-S1 | 2023-01-14 08:00 | 2023-01-27 16:00 |  |  | 14 | 0 | 14 | -2 | 1
BASE610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Black Base - SB: 761+67-767+00 - Ph1-S1 | 2023-10-18 08:00 | 2023-10-20 16:00 |  |  | 3 | 0 | 3 | 0 | 14 | Agg Base Crew
R690 | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Pour Sidewalk @ Chelsea St.- South Side - Ph1-S1-S1 | 2022-05-11 08:00 | 2022-11-14 16:00 | 2022-05-11 08:00 |  | 5 | 128 | 1 | 407 |  | Concrete Flatwork Crew
B1470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | 2023-03-17 08:00 | 2023-03-27 16:00 |  |  | 7 | 0 | 7 | 12 |  | Concrete Barrier Crew
DEMO250 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Demo Existing Slope Pavement @ E. Osborne Ave.- South Side - Ph1-S1-S1 | 2021-11-23 08:00 | 2021-11-23 16:00 | 2021-11-23 08:00 | 2021-11-23 16:00 | 4 | 1 | 0 |  |  | Demolition Crews
CP510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | 2023-11-13 08:00 | 2023-11-17 16:00 |  |  | 5 | 0 | 5 | 14 |  | Concrete Paving Crews
DEMO1540 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 2022-09-26 05:00 | 2022-09-30 06:00 | 2022-09-26 05:00 | 2022-09-30 06:00 | 8 | 5 | 0 |  |  | Demolition Crews
CP400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | 2023-10-23 08:00 | 2023-10-25 16:00 |  |  | 3 | 0 | 3 | 6 |  | Concrete Paving Crews
R700 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | 2022-02-08 08:00 | 2022-02-18 16:00 | 2022-02-08 08:00 | 2022-02-18 16:00 | 11 | 9 | 0 |  |  | CIP Wall Crew
EGC150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 2022-05-24 08:00 | 2022-06-05 16:00 | 2022-05-24 08:00 | 2022-06-05 16:00 | 7 | 8 | 0 |  |  | Light Cut/Fill Earthwork Crew
DEMO1620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Existing Deck 100207 - SB: over East Lake - Ph1-S1 | 2022-09-26 02:00 | 2022-09-30 05:00 | 2022-09-26 02:00 | 2022-09-30 05:00 | 15 | 5 | 0 |  |  | Demo Bridge Crew
R705 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Pour Slope Pavement @ E. Osborne Ave - South Side - Ph1-S1-S1 | 2022-01-27 08:00 | 2022-02-18 16:00 | 2022-01-27 08:00 | 2022-02-18 16:00 | 7 | 17 | 0 |  |  | Concrete Flatwork Crew
STAB220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 2023-01-31 08:00 | 2023-02-08 16:00 |  |  | 7 | 0 | 7 | 10 |  | Cement Subgrade Crew
SUPR770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / SIP / Reinforce / Pour Replacement Deck 100207 - SB: over East Lake - Ph1-S1 | 2023-06-16 05:00 | 2023-07-11 05:00 |  |  | 18 | 0 | 18 | 53 |  | Super-Structure Crew
R710 | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Pour Sidewalk @ E. Osborne Ave - South Side - Ph1-S1-S1 | 2022-05-03 08:00 | 2022-11-14 16:00 | 2022-05-03 08:00 |  | 5 | 134 | 1 | 410 |  | Concrete Flatwork Crew
BASE230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Black Base - NB: 767+00-773+42 - Ph1-S1 | 2023-03-22 08:00 | 2023-03-30 16:00 |  |  | 7 | 0 | 7 | 10 |  | Agg Base Crew
B1510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - SB: over East Lake - Ph1-S1 | 2023-07-11 08:00 | 2023-07-24 16:00 |  |  | 14 | 0 | 14 | 71
CP200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | 2023-04-28 08:00 | 2023-05-08 16:00 |  |  | 7 | 0 | 7 | 9 |  | Concrete Paving Crews
B1520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 2024-01-24 08:00 | 2024-02-01 16:00 |  |  | 7 | 0 | 7 | 0 |  | Concrete Barrier Crew
CP150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | 2023-03-31 08:00 | 2023-04-05 16:00 |  |  | 4 | 0 | 4 | 10 |  | Concrete Paving Crews
DEMO270 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 2022-03-08 08:00 | 2022-03-09 16:00 | 2022-03-08 08:00 | 2022-03-09 16:00 | 6 | 2 | 0 |  |  | Demolition Crews
DEMO1360 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-02-18 21:00 | 2022-02-19 04:00 | 2022-02-18 21:00 | 2022-02-19 04:00 | 3 | 0 | 0 |  |  | Demolition Crews
DRG380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: CD-3 to S-78 (48") - NB: 767-768 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Drainage Crew - Combo
EGC270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 2023-02-16 08:00 | 2023-02-24 16:00 |  |  | 7 | 0 | 7 | 23 |  | Light Cut/Fill Earthwork Crew
R720 | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | 2022-07-18 08:00 | 2022-11-29 16:00 | 2022-07-18 08:00 |  | 13 | 82 | 9 | 69 |  | CIP Wall Crew
DEMO1380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Edge of Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-02-18 05:00 | 2022-03-02 05:00 | 2022-02-18 05:00 | 2022-03-02 05:00 | 8 | 9 | 0 |  |  | Demo Bridge Crew
R725 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Slope Pavement @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 2022-11-30 08:00 | 2022-12-07 16:00 |  |  | 6 | 0 | 6 | 397 |  | Concrete Flatwork Crew
STAB410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 2023-06-21 08:00 | 2023-06-30 16:00 |  |  | 8 | 0 | 8 | 46 |  | Cement Subgrade Crew
R730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 2022-12-08 08:00 | 2022-12-14 16:00 |  |  | 5 | 0 | 5 | 397 |  | Concrete Flatwork Crew
BASE570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Black Base - SB: 767+00-773+42 - Ph1-S1 | 2023-09-27 08:00 | 2023-10-03 16:00 |  |  | 5 | 0 | 5 | 10 |  | Agg Base Crew
TCC150 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.0 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Traffic Control | Detour North Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S2 | 2022-06-22 08:00 | 2022-06-23 16:00 | 2022-06-22 08:00 | 2022-06-23 16:00 | 1 | 2 | 0 |  |  | Maintenance of Traffic Crew
CP500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | 2023-10-31 08:00 | 2023-11-06 16:00 |  |  | 5 | 0 | 5 | 15 |  | Concrete Paving Crews
DEMO1400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-02-24 08:00 | 2022-03-02 16:00 | 2022-02-24 08:00 | 2022-03-02 16:00 | 4 | 5 | 0 |  |  | Demo Bridge Crew
DEMO970 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Demo Existing Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | 2022-02-14 08:00 | 2022-02-18 16:00 | 2022-02-14 08:00 | 2022-02-18 16:00 | 4 | 5 | 0 |  |  | Demolition Crews
CP380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | 2023-10-04 08:00 | 2023-10-06 16:00 |  |  | 3 | 0 | 3 | 16 |  | Concrete Paving Crews
PILE150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Drive Production H-Piles 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-02-01 08:00 | 2022-03-18 16:00 | 2022-02-01 08:00 | 2022-03-18 16:00 | 4 | 34 | 0 |  |  | Pile Driving Crew
DS120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-06 08:00 | 2022-09-16 16:00 | 2022-09-06 08:00 | 2022-09-16 16:00 | 10 | 9 | 0 |  |  | Sub - Drilled Shaft Crew
DRG1070 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | 2023-03-17 08:00 | 2023-03-21 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
R745 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Reinforce / Pour Gravity Wall W-3A @ Floribraska - North Side - Ph1-S1-S2 | 2022-02-17 08:00 | 2022-03-03 16:00 | 2022-02-17 08:00 | 2022-03-03 16:00 | 12 | 11 | 0 |  |  | CIP Wall Crew
EGC160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 7 | 5 | 0 |  |  | Light Cut/Fill Earthwork Crew
SUBS240 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-06-20 08:00 | 2022-06-24 16:00 | 2022-06-20 08:00 | 2022-06-24 16:00 | 6 | 5 | 0 |  |  | Substructure Crew
R750 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Pour Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | 2022-04-12 08:00 | 2022-04-15 16:00 | 2022-04-12 08:00 | 2022-04-15 16:00 | 5 | 4 | 0 |  |  | Concrete Flatwork Crew
SUBS330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-13 08:00 | 2022-09-14 16:00 | 2022-09-13 08:00 | 2022-09-14 16:00 | 8 | 2 | 0 |  |  | Substructure Crew
R755 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Pour Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 78 |  | Concrete Flatwork Crew
SUBS340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-13 08:00 | 2022-09-15 16:00 | 2022-09-13 08:00 | 2022-09-15 16:00 | 8 | 3 | 0 |  |  | Substructure Crew
STAB230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 2023-02-20 08:00 | 2023-02-27 16:00 |  |  | 6 | 0 | 6 | 10 |  | Cement Subgrade Crew
PAV280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Miscellaneous Asphalt Paving @ Floribraska - North Side - Ph1-S1-S2 | 2022-12-14 08:00 | 2022-12-15 16:00 |  |  | 2 | 0 | 2 | 87 |  | Sub - Asphalt Paving Crew
SUBS400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-05-14 08:00 | 2022-06-24 16:00 | 2022-05-14 08:00 | 2022-06-24 16:00 | 6 | 29 | 0 |  |  | Substructure Crew
DEMO1000 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Demo Existing Slope Pavement @ East Lake Ave.- North Side - Ph1-S1-S2 | 2022-02-14 08:00 | 2022-02-17 16:00 | 2022-02-14 08:00 | 2022-02-17 16:00 | 4 | 4 | 0 |  |  | Demolition Crews
BASE240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Black Base - NB: 774+82-780+00 - Ph1-S1 | 2023-03-31 08:00 | 2023-04-06 16:00 |  |  | 5 | 0 | 5 | 14 |  | Agg Base Crew
SUBS410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-11-16 08:00 | 2022-11-30 16:00 |  |  | 8 | 0 | 8 | 9 |  | Substructure Crew
CP210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | 2023-05-09 08:00 | 2023-05-15 16:00 |  |  | 5 | 0 | 5 | 16 |  | Concrete Paving Crews
SUBS420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-10-05 08:00 | 2022-10-14 16:00 | 2022-10-05 08:00 | 2022-10-14 16:00 | 8 | 8 | 0 |  |  | Substructure Crew
BBM120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-11 21:00 | 2022-12-14 03:00 |  |  | 3 | 0 | 3 | 11 |  | Erection Crew
R770 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Reinforce / Pour Gravity Wall W-7A @ East Lake Ave. - North Side - Ph1-S1-S2 | 2022-02-09 08:00 | 2022-03-16 16:00 | 2022-02-09 08:00 | 2022-03-16 16:00 | 12 | 26 | 0 |  |  | CIP Wall Crew
CP160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-12 16:00 |  |  | 4 | 0 | 4 | 18 |  | Concrete Paving Crews
SUPR190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Overhang 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-14 03:00 | 2022-12-20 22:00 |  |  | 5 | 0 | 5 | 11 |  | Super-Structure Crew
R775 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Slope Pavement @ East Lake Ave. - North Side - Ph1-S1-S2 | 2022-04-11 08:00 | 2022-04-15 16:00 | 2022-04-11 08:00 | 2022-04-15 16:00 | 5 | 5 | 0 |  |  | Concrete Flatwork Crew
DRG440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-106 to S-110 (18") - NB: 779-781 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 66 |  | Drainage Crew - Combo
R780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | 2022-11-21 08:00 | 2022-11-30 16:00 |  |  | 5 | 0 | 5 | 78 |  | Concrete Flatwork Crew
SIP120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install SIP Deck Pans100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-14 03:00 | 2022-12-20 22:00 |  |  | 5 | 0 | 5 | 11 |  | Deck Crew
DEMO1030 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | 2022-02-15 08:00 | 2022-02-19 16:00 | 2022-02-15 08:00 | 2022-02-19 16:00 | 5 | 4 | 0 |  |  | Demolition Crews
EGC250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 2023-01-25 08:00 | 2023-02-06 16:00 |  |  | 9 | 0 | 9 | 23 |  | Light Cut/Fill Earthwork Crew
R790 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - East Half - North Side - Ph1-S1-S2 | 2022-07-05 08:00 | 2022-07-20 08:00 | 2022-07-05 08:00 | 2022-07-20 08:00 | 13 | 11 | 0 |  |  | CIP Wall Crew
SUPR250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-21 08:00 | 2023-01-05 16:00 |  |  | 6 | 0 | 6 | 9 |  | Super-Structure Crew
R795 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Pour Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 80 |  | Concrete Flatwork Crew
R800 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Pour Sidewalk @ MLK Blvd.- North Side - Ph1-S1-S2 | 2022-12-01 08:00 | 2022-12-08 16:00 |  |  | 6 | 0 | 6 | 78 |  | Concrete Flatwork Crew
STAB390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 2023-06-07 08:00 | 2023-06-14 16:00 |  |  | 6 | 0 | 6 | 50 |  | Cement Subgrade Crew
SUPR300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set Deck Screed 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-01-11 08:00 | 2023-01-12 16:00 |  |  | 2 | 0 | 2 | 9 |  | Super-Structure Crew
DEMO1060 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Demo Existing Slope Pavement @ Chelsea St.- North Side - Ph1-S1-S2 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 4 | 14 | 0 |  |  | Demolition Crews
SUPR320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pour Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-01-12 21:00 | 2023-01-13 05:00 |  |  | 1 | 0 | 1 | 10 |  | Super-Structure Crew
BASE560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Black Base - SB: 774+82-780+00 - Ph1-S1 | 2023-09-20 08:00 | 2023-09-26 16:00 |  |  | 5 | 0 | 5 | 10 |  | Agg Base Crew
B1730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-01-13 08:00 | 2023-01-26 16:00 |  |  | 14 | 0 | 14 | 14
CP480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | 2023-10-24 08:00 | 2023-10-30 16:00 |  |  | 5 | 0 | 5 | 13 |  | Concrete Paving Crews
R810 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | 2022-02-02 08:00 | 2022-02-17 16:00 | 2022-02-02 08:00 | 2022-02-17 16:00 | 12 | 12 | 0 |  |  | CIP Wall Crew
SUPR360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-01-27 08:00 | 2023-02-03 16:00 |  |  | 6 | 0 | 6 | 10 |  | Approach Slab Crew
CP370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | 2023-09-27 08:00 | 2023-09-29 16:00 |  |  | 3 | 0 | 3 | 18 |  | Concrete Paving Crews
B1750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Approach Slabs Cure 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-02-04 08:00 | 2023-02-17 16:00 |  |  | 14 | 0 | 14 | 16
R815 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Pour Slope Pavement @ Chelsea St.- North Side - Ph1-S1-S2 | 2022-03-28 08:00 | 2022-04-16 16:00 | 2022-03-28 08:00 | 2022-04-16 16:00 | 8 | 15 | 0 |  |  | Concrete Flatwork Crew
R820 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | 2022-12-09 08:00 | 2022-12-16 16:00 |  |  | 6 | 0 | 6 | 78 |  | Concrete Flatwork Crew
DRGS65 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | 2022-12-16 08:00 | 2022-12-16 16:00 |  |  | 1 | 0 | 1 | 32 |  | Drainage Crew - Combo
B1760 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-04-12 08:00 | 2023-04-21 16:00 |  |  | 8 | 0 | 8 | 19 |  | Concrete Barrier Crew
DEMO1090 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Demo Existing Slope Pavement @ E. Osborne Ave.- North Side - Ph1-S1-S2 | 2022-01-20 08:00 | 2022-01-24 16:00 | 2022-01-20 08:00 | 2022-01-24 16:00 | 4 | 3 | 0 |  |  | Demolition Crews
DEMO1510 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Traffic Railing 100204 - SB: over MLK - Ph1-S1 | 2022-08-09 05:00 | 2022-08-12 | 2022-08-09 05:00 | 2022-08-12 | 5 | 3 | 0 |  |  | Demolition Crews
EGC170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 8 | 5 | 0 |  |  | Light Cut/Fill Earthwork Crew
STAB240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 2023-02-28 08:00 | 2023-03-07 16:00 |  |  | 6 | 0 | 6 | 12 |  | Cement Subgrade Crew
R830 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | 2022-01-25 08:00 | 2022-02-08 16:00 | 2022-01-25 08:00 | 2022-02-08 16:00 | 11 | 11 | 0 |  |  | CIP Wall Crew
DEMO1600 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | 2022-08-15 04:00 | 2022-08-19 03:00 | 2022-08-15 04:00 | 2022-08-19 03:00 | 10 | 4 | 0 |  |  | Demo Bridge Crew
R835 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Pour Slope Pavement @ E. Osborne Ave - North Side - Ph1-S1-S2 | 2022-03-28 08:00 | 2022-04-16 16:00 | 2022-03-28 08:00 | 2022-04-16 16:00 | 8 | 15 | 0 |  |  | Concrete Flatwork Crew
DEMO1610 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo End of Existing End Bent 100204 - SB: over MLK - Ph1-S1 | 2022-09-26 08:00 | 2022-09-30 16:00 | 2022-09-26 08:00 | 2022-09-30 16:00 | 6 | 5 | 0 |  |  | Demo Bridge Crew
PILE340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Drive Production H-Piles 100204 - SB: over MLK - Ph1-S1 | 2022-03-10 08:00 | 2022-03-18 16:00 | 2022-03-10 08:00 | 2022-03-18 16:00 | 4 | 7 | 0 |  |  | Pile Driving Crew
BASE320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Black Base - NB: 780+00-786+69 - Ph1-S1 | 2023-04-11 08:00 | 2023-04-19 16:00 |  |  | 7 | 0 | 7 | 12 |  | Agg Base Crew
R840 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | 2022-12-19 08:00 | 2023-01-03 16:00 |  |  | 6 | 0 | 6 | 78 |  | Concrete Flatwork Crew
CP230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | 2023-05-17 08:00 | 2023-05-24 16:00 |  |  | 6 | 0 | 6 | 15 |  | Concrete Paving Crews
DS190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 2022-09-26 08:00 | 2022-09-30 16:00 | 2022-09-26 08:00 | 2022-09-30 16:00 | 10 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO1130 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 2022-02-11 08:00 | 2022-02-18 16:00 | 2022-02-11 08:00 | 2022-02-18 16:00 | 6 | 6 | 0 |  |  | Demolition Crews
CP190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | 2023-04-20 08:00 | 2023-04-26 16:00 |  |  | 5 | 0 | 5 | 14 |  | Concrete Paving Crews
R850 | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - East Half - North Side - Ph1-S1-S2 | 2022-07-13 08:00 | 2022-11-29 16:00 | 2022-07-13 08:00 |  | 13 | 85 | 9 | 72 |  | CIP Wall Crew
SUBS1360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 2022-11-18 08:00 | 2022-11-29 16:00 |  |  | 5 | 0 | 5 | 159 |  | Substructure Crew
SUBS1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 2022-11-16 08:00 | 2022-11-30 16:00 |  |  | 8 | 0 | 8 | 144 |  | Substructure Crew
R855 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Pour Slope Pavement @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 2022-11-30 08:00 | 2022-12-06 16:00 |  |  | 5 | 0 | 5 | 92 |  | Concrete Flatwork Crew
DRG450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-114 to S-115 (18") - NB: 781-782 - Ph1-S1 | 2022-08-08 08:00 | 2022-08-09 16:00 | 2022-08-08 08:00 | 2022-08-09 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
SUBS1120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 2022-10-10 08:00 | 2022-10-14 16:00 | 2022-10-10 08:00 | 2022-10-14 16:00 | 8 | 5 | 0 |  |  | Substructure Crew
R860 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Pour Sidewalk @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 2023-01-04 08:00 | 2023-01-10 16:00 |  |  | 5 | 0 | 5 | 78 |  | Concrete Flatwork Crew
EGC240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 2023-01-13 08:00 | 2023-01-24 16:00 |  |  | 7 | 0 | 7 | 23 |  | Light Cut/Fill Earthwork Crew
MSE1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2023-04-04 08:00 | 2023-04-06 16:00 |  |  | 3 | 0 | 3 | 92 |  | Sub - MSE Wall Crew
SUBS1320 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 2022-10-14 08:00 | 2022-11-14 08:00 | 2022-10-14 08:00 |  | 5 | 20 | 0 | 168 |  | Substructure Crew
MSE190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-06-22 08:00 | 2022-07-04 16:00 | 2022-06-22 08:00 | 2022-07-04 16:00 | 3 | 8 | 0 |  |  | Sub - MSE Wall Crew
STAB380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 2023-05-26 08:00 | 2023-06-05 16:00 |  |  | 6 | 0 | 6 | 44 |  | Cement Subgrade Crew
MSE230 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-06-01 08:00 | 2022-06-01 16:00 | 2022-06-01 08:00 | 2022-06-01 16:00 | 2 | 1 | 0 |  |  | Sub - MSE Wall Crew
SUBS1170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 2022-12-12 08:00 | 2022-12-21 16:00 |  |  | 8 | 0 | 8 | 141 |  | Substructure Crew
BASE550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Black Base - SB: 780+00-786+69 - Ph1-S1 | 2023-09-13 08:00 | 2023-09-19 16:00 |  |  | 5 | 0 | 5 | 10 |  | Agg Base Crew
MSE260 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 | Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Leveling Pad - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 2022-06-22 08:00 | 2022-07-05 16:00 | 2022-06-22 08:00 | 2022-07-05 16:00 | 2 | 9 | 0 |  |  | Sub - MSE Wall Crew
SUBS1190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | 2022-10-17 08:00 | 2022-10-21 16:00 | 2022-10-17 08:00 | 2022-10-21 16:00 | 8 | 5 | 0 |  |  | Substructure Crew
CP450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | 2023-10-10 08:00 | 2023-10-23 16:00 |  |  | 10 | 0 | 10 | 11 |  | Concrete Paving Crews
MSE300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2022-04-25 08:00 | 2022-07-12 16:00 | 2022-04-25 08:00 | 2022-07-12 16:00 | 2 | 55 | 0 |  |  | Sub - MSE Wall Crew
BBM190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 2023-05-11 04:00 | 2023-05-15 02:00 |  |  | 2 | 0 | 2 | 62 |  | Erection Crew
MSE1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2023-03-22 08:00 | 2023-03-23 16:00 |  |  | 2 | 0 | 2 | 87 |  | Sub - MSE Wall Crew
CP360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | 2023-09-20 08:00 | 2023-09-22 16:00 |  |  | 3 | 0 | 3 | 11 |  | Concrete Paving Crews
MSE340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-08-15 08:00 | 2022-08-17 16:00 | 2022-08-15 08:00 | 2022-08-17 16:00 | 2 | 3 | 0 |  |  | Sub - MSE Wall Crew
SUPR640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Overhang 100204 - SB: over MLK - Ph1-S1 | 2023-05-15 02:00 | 2023-05-19 06:00 |  |  | 5 | 0 | 5 | 62 |  | Super-Structure Crew
MSE1070 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 2023-02-27 08:00 | 2023-03-01 16:00 |  |  | 3 | 0 | 3 | 87 |  | Sub - MSE Wall Crew
MSE390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2022-07-28 08:00 | 2022-08-12 16:00 | 2022-07-28 08:00 | 2022-08-12 16:00 | 2 | 12 | 0 |  |  | Sub - MSE Wall Crew
DRG1200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | 2023-01-25 08:00 | 2023-01-27 16:00 |  |  | 3 | 0 | 3 | 26 |  | Drainage Crew - Combo
SIP190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install SIP Deck Pans100204 - SB: over MLK - Ph1-S1 | 2023-05-15 02:00 | 2023-05-19 06:00 |  |  | 5 | 0 | 5 | 62 |  | Deck Crew
MSE500 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 2022-08-08 08:00 | 2022-08-11 16:00 | 2022-08-08 08:00 | 2022-08-11 16:00 | 4 | 4 | 0 |  |  | Sub - MSE Wall Crew
EGC180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | 2022-09-09 08:00 | 2022-09-19 16:00 | 2022-09-09 08:00 | 2022-09-19 16:00 | 7 | 7 | 0 |  |  | Light Cut/Fill Earthwork Crew
MSE550 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 2022-09-14 08:00 | 2022-10-07 16:00 | 2022-09-14 08:00 | 2022-10-07 16:00 | 4 | 18 | 0 |  |  | Sub - MSE Wall Crew
MSE890 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 2023-03-29 08:00 | 2023-03-31 16:00 |  |  | 3 | 0 | 3 | 23 |  | Sub - MSE Wall Crew
SUPR700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form Deck 100204 - SB: over MLK - Ph1-S1 | 2023-05-19 08:00 | 2023-05-26 16:00 |  |  | 6 | 0 | 6 | 55 |  | Super-Structure Crew
MSE830 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2023-03-16 08:00 | 2023-03-17 16:00 |  |  | 2 | 0 | 2 | 23 |  | Sub - MSE Wall Crew
STAB250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 2023-03-08 08:00 | 2023-03-17 16:00 |  |  | 8 | 0 | 8 | 12 |  | Cement Subgrade Crew
MSE790 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2023-03-01 08:00 | 2023-03-02 16:00 |  |  | 2 | 0 | 2 | 23 |  | Sub - MSE Wall Crew
SUPR750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set Deck Screed 100204 - SB: over MLK - Ph1-S1 | 2023-06-14 08:00 | 2023-06-15 16:00 |  |  | 2 | 0 | 2 | 47 |  | Super-Structure Crew
MSE610 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Leveling Pad - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 2022-10-19 08:00 | 2022-10-21 16:00 | 2022-10-19 08:00 | 2022-10-21 16:00 | 2 | 3 | 0 |  |  | Sub - MSE Wall Crew
BASE340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Black Base - NB: 788+09-800+00 - Ph1-S1 | 2023-04-20 08:00 | 2023-04-28 16:00 |  |  | 7 | 0 | 7 | 12 |  | Agg Base Crew
SUPR760 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pour Deck 100204 - SB: over MLK - Ph1-S1 | 2023-06-15 21:00 | 2023-06-16 05:00 |  |  | 1 | 0 | 1 | 53 |  | Super-Structure Crew
B1970 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - SB: over MLK - Ph1-S1 | 2023-06-16 08:00 | 2023-06-29 16:00 |  |  | 14 | 0 | 14 | 88
MSE750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 2023-02-16 08:00 | 2023-02-20 16:00 |  |  | 3 | 0 | 3 | 23 |  | Sub - MSE Wall Crew
CP250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | 2023-05-31 08:00 | 2023-06-14 16:00 |  |  | 11 | 0 | 11 | 12 |  | Concrete Paving Crews
SUPR800 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | 2023-09-26 08:00 | 2023-10-03 16:00 |  |  | 6 | 0 | 6 | 0 | 13 | Approach Slab Crew
MSE710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 2023-01-09 08:00 | 2023-01-11 16:00 |  |  | 3 | 0 | 3 | 29 |  | Sub - MSE Wall Crew
CP220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | 2023-05-01 08:00 | 2023-05-12 16:00 |  |  | 10 | 0 | 10 | 12 |  | Concrete Paving Crews
B1990 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Approach Slabs Cure 100204 - SB: over MLK - Ph1-S1 | 2023-10-04 08:00 | 2023-10-17 16:00 |  |  | 14 | 0 | 14 | 0 | 14
MSE1030 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 2023-02-07 08:00 | 2023-02-09 16:00 |  |  | 3 | 0 | 3 | 87 |  | Sub - MSE Wall Crew
B2000 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - SB: over MLK - Ph1-S1 | 2024-01-04 08:00 | 2024-01-16 16:00 |  |  | 8 | 0 | 8 | -4 | 1 | Concrete Barrier Crew
DRG490 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 OF to S-128 (18") - NB: 795-796 - Ph1-S1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
MSE990 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Leveling Pad - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 2022-11-07 08:00 | 2022-11-08 16:00 | 2022-11-07 08:00 | 2022-11-08 16:00 | 2 | 2 | 0 |  |  | Sub - MSE Wall Crew
DEMO1390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-03-13 21:00 | 2022-03-17 01:00 | 2022-03-13 21:00 | 2022-03-17 01:00 | 5 | 4 | 0 |  |  | Demolition Crews
EGC230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 2023-01-05 08:00 | 2023-01-12 16:00 |  |  | 6 | 0 | 6 | 23 |  | Light Cut/Fill Earthwork Crew
MSE660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2022-11-21 08:00 | 2022-11-28 16:00 |  |  | 3 | 0 | 3 | 40 |  | Sub - MSE Wall Crew
MS380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Form / Reinforce / Pour Moment Slab - MSE Wall W-1A, 1B, 1C - RAMP NE: 714+80.00-717+20.23 - Ph1-S1 | 2023-09-05 08:00 | 2023-09-20 16:00 |  |  | 12 | 0 | 12 | 13 |  | Concrete Paving Crews
MS130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Form / Reinforce / Pour Moment Slab - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-11-15 08:00 | 2022-11-22 16:00 |  |  | 6 | 0 | 6 | 7 |  | Concrete Paving Crews
DEMO1410 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-03-13 21:00 | 2022-03-17 22:00 | 2022-03-13 21:00 | 2022-03-17 22:00 | 8 | 5 | 0 |  |  | Demo Bridge Crew
STAB360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 2023-05-16 08:00 | 2023-05-25 16:00 |  |  | 8 | 0 | 8 | 44 |  | Cement Subgrade Crew
MS140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Form / Reinforce / Pour Moment Slab - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-21 16:00 |  |  | 6 | 0 | 6 | 8 |  | Concrete Paving Crews
DEMO1420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-03-13 08:00 | 2022-03-18 16:00 | 2022-03-13 08:00 | 2022-03-18 16:00 | 6 | 5 | 0 |  |  | Demo Bridge Crew
MS150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 | Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Form / Reinforce / Pour Moment Slab - MSE Wall W-4A, W-4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 2022-10-17 08:00 | 2022-10-21 16:00 | 2022-10-17 08:00 | 2022-10-21 16:00 | 8 | 5 | 0 |  |  | Concrete Paving Crews
BASE530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Black Base - SB: 788+09-800+00 - Ph1-S1 | 2023-07-31 08:00 | 2023-08-04 16:00 |  |  | 5 | 0 | 5 | 22 |  | Agg Base Crew
PILE160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-03-28 08:00 | 2022-04-04 16:00 | 2022-03-28 08:00 | 2022-04-04 16:00 | 4 | 6 | 0 |  |  | Pile Driving Crew
MS160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Form / Reinforce / Pour Moment Slab - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 12 |  | Concrete Paving Crews
CP420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | 2023-09-19 08:00 | 2023-10-05 16:00 |  |  | 13 | 0 | 13 | 13 |  | Concrete Paving Crews
MS370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2023-06-21 08:00 | 2023-07-03 16:00 |  |  | 9 | 0 | 9 | 55 |  | Concrete Paving Crews
DS130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Install 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-04-04 08:00 | 2022-04-16 16:00 | 2022-04-04 08:00 | 2022-04-16 16:00 | 10 | 10 | 0 |  |  | Sub - Drilled Shaft Crew
CP340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | 2023-08-09 08:00 | 2023-08-18 16:00 |  |  | 8 | 0 | 8 | 20 |  | Concrete Paving Crews
SUBS430 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-06-01 08:00 | 2022-06-11 16:00 | 2022-06-01 08:00 | 2022-06-11 16:00 | 8 | 8 | 0 |  |  | Substructure Crew
MS170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Form / Reinforce / Pour Moment Slab - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-22 16:00 |  |  | 7 | 0 | 7 | 17 |  | Concrete Paving Crews
MS360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | 2023-06-07 08:00 | 2023-06-20 16:00 |  |  | 10 | 0 | 10 | 46 |  | Concrete Paving Crews
SUBS450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-05-11 08:00 | 2022-05-14 16:00 | 2022-05-11 08:00 | 2022-05-14 16:00 | 8 | 3 | 0 |  |  | Substructure Crew
DRG1270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | 2023-02-09 08:00 | 2023-02-10 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
MS180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Form / Reinforce / Pour Moment Slab - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-22 16:00 |  |  | 7 | 0 | 7 | 45 |  | Concrete Paving Crews
EGC190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 2022-08-25 08:00 | 2022-09-06 16:00 | 2022-08-25 08:00 | 2022-09-06 16:00 | 7 | 7 | 0 |  |  | Light Cut/Fill Earthwork Crew
SUBS460 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-06-10 08:00 | 2022-06-13 16:00 | 2022-06-10 08:00 | 2022-06-13 16:00 | 8 | 2 | 0 |  |  | Substructure Crew
STAB260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-29 16:00 |  |  | 8 | 0 | 8 | 20 |  | Cement Subgrade Crew
SUBS470 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-09-09 08:00 | 2022-09-12 16:00 | 2022-09-09 08:00 | 2022-09-12 16:00 | 8 | 2 | 0 |  |  | Substructure Crew
BASE350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Black Base - NB: 800+00-813+16 - Ph1-S1 | 2023-05-01 08:00 | 2023-05-11 16:00 |  |  | 9 | 0 | 9 | 13 |  | Agg Base Crew
MS210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Form / Reinforce / Pour Moment Slab - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 2022-12-21 08:00 | 2023-01-10 16:00 |  |  | 9 | 0 | 9 | 45 |  | Concrete Paving Crews
SUBS540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-12-12 08:00 | 2022-12-21 16:00 |  |  | 8 | 0 | 8 | 17 |  | Substructure Crew
CP270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | 2023-06-20 08:00 | 2023-07-06 16:00 |  |  | 12 | 0 | 12 | 12 |  | Concrete Paving Crews
MS350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Form / Reinforce / Pour Moment Slab - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 2023-05-23 08:00 | 2023-06-06 16:00 |  |  | 10 | 0 | 10 | 46 |  | Concrete Paving Crews
SUBS550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-11-17 08:00 | 2022-12-01 16:00 |  |  | 8 | 0 | 8 | 31 |  | Substructure Crew
MS340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 2023-05-12 08:00 | 2023-05-22 16:00 |  |  | 7 | 0 | 7 | 46 |  | Concrete Paving Crews
CP240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | 2023-05-15 08:00 | 2023-05-30 16:00 |  |  | 11 | 0 | 11 | 12 |  | Concrete Paving Crews
BBM130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-04 21:00 | 2023-01-06 04:00 |  |  | 2 | 0 | 2 | 23 |  | Erection Crew
MS220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Form / Reinforce / Pour Moment Slab - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 2022-12-22 08:00 | 2023-01-10 16:00 |  |  | 8 | 0 | 8 | 31 |  | Concrete Paving Crews
SUPR260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Overhang 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-06 04:00 | 2023-01-12 23:00 |  |  | 5 | 0 | 5 | 23 |  | Super-Structure Crew
DRG520 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-144 OF to S-144 (30") - NB: 801 - 802 - IPh1 | 2022-01-24 08:00 | 2022-01-26 16:00 | 2022-01-24 08:00 | 2022-01-26 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
SIP130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install SIP Deck Pans100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-06 04:00 | 2023-01-12 23:00 |  |  | 5 | 0 | 5 | 23 |  | Deck Crew
MS320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 2023-04-18 08:00 | 2023-04-27 16:00 |  |  | 8 | 0 | 8 | 23 |  | Concrete Paving Crews
EGC220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 2022-12-15 08:00 | 2023-01-04 16:00 |  |  | 9 | 0 | 9 | 6 |  | Light Cut/Fill Earthwork Crew
MS300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Form / Reinforce / Pour Moment Slab - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2023-04-06 08:00 | 2023-04-11 16:00 |  |  | 4 | 0 | 4 | 23 |  | Concrete Paving Crews
STAB340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 2023-05-08 08:00 | 2023-05-15 16:00 |  |  | 6 | 0 | 6 | 17 |  | Cement Subgrade Crew
SUPR290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-13 08:00 | 2023-01-23 16:00 |  |  | 6 | 0 | 6 | 20 |  | Super-Structure Crew
MS290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2023-03-27 08:00 | 2023-04-05 16:00 |  |  | 8 | 0 | 8 | 23 |  | Concrete Paving Crews
MS240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 2023-01-20 08:00 | 2023-02-02 16:00 |  |  | 10 | 0 | 10 | 31 |  | Concrete Paving Crews
SUPR340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set Deck Screed 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-27 08:00 | 2023-01-30 16:00 |  |  | 2 | 0 | 2 | 20 |  | Super-Structure Crew
MS270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | 2023-03-10 08:00 | 2023-03-17 16:00 |  |  | 6 | 0 | 6 | 24 |  | Concrete Paving Crews
MS260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 2023-02-20 08:00 | 2023-03-02 16:00 |  |  | 9 | 0 | 9 | 29 |  | Concrete Paving Crews
BASE480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Black Base - SB: 800+00-813+16 - Ph1-S1 | 2023-07-19 08:00 | 2023-07-28 16:00 |  |  | 8 | 0 | 8 | 19 |  | Agg Base Crew
SUPR350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pour Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-30 21:00 | 2023-01-31 05:00 |  |  | 1 | 0 | 1 | 23 |  | Super-Structure Crew
MS250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2023-02-03 08:00 | 2023-02-15 16:00 |  |  | 9 | 0 | 9 | 31 |  | Concrete Paving Crews
B2210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-31 08:00 | 2023-02-13 16:00 |  |  | 14 | 0 | 14 | 28
DEMO110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Demo / Grade - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-09-12 08:00 | 2022-09-14 16:00 | 2022-09-12 08:00 | 2022-09-14 16:00 | 44 | 3 | 0 |  |  | Demolition Crews
SUPR370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-02-28 08:00 | 2023-03-07 16:00 |  |  | 6 | 0 | 6 | 10 |  | Approach Slab Crew
CP390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | 2023-09-06 08:00 | 2023-09-18 16:00 |  |  | 9 | 0 | 9 | 13 |  | Concrete Paving Crews
B2230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-03-08 08:00 | 2023-03-21 16:00 |  |  | 14 | 0 | 14 | 14
CP320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | 2023-07-31 08:00 | 2023-08-08 16:00 |  |  | 7 | 0 | 7 | 19 |  | Concrete Paving Crews
DRG1340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | 2023-01-05 08:00 | 2023-01-06 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
B2240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-05-01 08:00 | 2023-05-09 16:00 |  |  | 7 | 0 | 7 | 24 |  | Concrete Barrier Crew
DEMO1690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 | Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | 2023-11-16 08:00 | 2023-11-17 16:00 |  |  | 2 | 0 | 2 | -2 | 11 | Demolition Crews
EGC200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 2022-08-01 08:00 | 2022-08-10 16:00 | 2022-08-01 08:00 | 2022-08-10 16:00 | 8 | 8 | 0 |  |  | Light Cut/Fill Earthwork Crew
DEMO1500 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-08-08 01:00 | 2022-08-09 05:00 | 2022-08-08 01:00 | 2022-08-09 05:00 | 5 | 2 | 0 |  |  | Demolition Crews
DEMO1680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Demo / Grade - MLK Ramp A - Ph1-S1 | 2023-10-05 08:00 | 2023-10-06 16:00 |  |  | 2 | 0 | 2 | 9 |  | Demolition Crews
DEMO1580 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Edge of Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-08-15 05:00 | 2022-08-19 04:00 | 2022-08-15 05:00 | 2022-08-19 04:00 | 10 | 4 | 0 |  |  | Demo Bridge Crew
STAB290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 2023-03-30 08:00 | 2023-04-14 16:00 |  |  | 12 | 0 | 12 | 20 |  | Cement Subgrade Crew
DEMO380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Demo / Grade - MLK Ramp B - Ph1-S1 | 2022-12-23 08:00 | 2023-01-03 16:00 |  |  | 2 | 0 | 2 | 19 |  | Demolition Crews
BASE400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 815+20-839+61 - Ph1-S1 | 2023-05-25 08:00 | 2023-06-09 16:00 |  |  | 11 | 0 | 11 | 13 |  | Agg Base Crew
DEMO1590 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-08-08 08:00 | 2022-08-11 16:00 | 2022-08-08 08:00 | 2022-08-11 16:00 | 6 | 4 | 0 |  |  | Demo Bridge Crew
DEMO570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Demo / Grade - MLK Ramp C - Ph1-S1 | 2023-02-09 08:00 | 2023-02-10 16:00 |  |  | 2 | 0 | 2 | 10 |  | Demolition Crews
CP290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | 2023-07-14 08:00 | 2023-07-27 16:00 |  |  | 10 | 0 | 10 | 14 |  | Concrete Paving Crews
PILE320 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Drive Production H-Piles 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-04-08 08:00 | 2022-04-16 16:00 | 2022-04-08 08:00 | 2022-04-16 16:00 | 4 | 6 | 0 |  |  | Pile Driving Crew
DEMO1670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Demo / Grade - MLK Ramp D - Ph1-S1 | 2023-08-24 08:00 | 2023-08-28 16:00 |  |  | 3 | 0 | 3 | 25 |  | Demolition Crews
CP260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | 2023-06-12 08:00 | 2023-06-23 16:00 |  |  | 10 | 0 | 10 | 13 |  | Concrete Paving Crews
DEMO1660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 | Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 2023-08-21 08:00 | 2023-08-23 16:00 |  |  | 3 | 0 | 3 | 10 |  | Demolition Crews
DS180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-04-11 08:00 | 2022-05-11 16:00 | 2022-04-11 08:00 | 2022-05-11 16:00 | 10 | 23 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | 2023-03-23 08:00 | 2023-03-29 16:00 |  |  | 5 | 0 | 5 | 33 |  | Demolition Crews
SUBS1330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-09-02 08:00 | 2022-09-17 16:00 | 2022-09-02 08:00 | 2022-09-17 16:00 | 6 | 9 | 0 |  |  | Substructure Crew
DRG670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 19 |  | Drainage Crew - Combo
DEMO1630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | 2023-04-13 08:00 | 2023-04-14 16:00 |  |  | 2 | 0 | 2 | 59 |  | Demolition Crews
SUBS1020 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-06-06 08:00 | 2022-06-09 16:00 | 2022-06-06 08:00 | 2022-06-09 16:00 | 10 | 4 | 0 |  |  | Substructure Crew
EGC210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 2022-12-05 08:00 | 2022-12-14 16:00 |  |  | 8 | 0 | 8 | 4 |  | Light Cut/Fill Earthwork Crew
DEMO1640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Demo / Grade - Hillsborough Ramp C2 - Ph1-S1 | 2023-04-17 08:00 | 2023-04-18 16:00 |  |  | 2 | 0 | 2 | 66 |  | Demolition Crews
SUBS1030 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-06-20 08:00 | 2022-07-15 16:00 | 2022-06-20 08:00 | 2022-07-15 16:00 | 10 | 19 | 0 |  |  | Substructure Crew
STAB330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 2023-04-17 08:00 | 2023-05-02 16:00 |  |  | 12 | 0 | 12 | 20 |  | Cement Subgrade Crew
TCC140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.1 | Construction: Phase 1: Stage 1: Traffic Control | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | 2022-10-17 21:00 | 2022-10-24 01:00 | 2022-10-17 21:00 | 2022-10-24 01:00 | 5 | 5 | 0 |  |  | Traffic Control Crews
BASE470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Black Base - SB: 815+20-839+61 - Ph1-S1 | 2023-06-12 08:00 | 2023-06-28 16:00 |  |  | 13 | 0 | 13 | 16 |  | Agg Base Crew
SUBS1290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-09-09 08:00 | 2022-09-23 16:00 | 2022-09-09 08:00 | 2022-09-23 16:00 | 6 | 11 | 0 |  |  | Substructure Crew
TCC110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.1 | Construction: Phase 1: Stage 1: Traffic Control | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | 2022-01-09 21:00 | 2022-05-15 06:00 | 2022-01-09 21:00 | 2022-05-15 06:00 | 1 | 100 | 0 |  |  | Traffic Control Crews
CP330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | 2023-08-15 08:00 | 2023-08-31 16:00 |  |  | 13 | 0 | 13 | 14 |  | Concrete Paving Crews
CP310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | 2023-07-12 08:00 | 2023-07-24 16:00 |  |  | 9 | 0 | 9 | 16 |  | Concrete Paving Crews
DRG1450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | 2022-12-15 08:00 | 2022-12-16 16:00 |  |  | 2 | 0 | 2 | 4 |  | Drainage Crew - Combo
SUBS1090 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-11-14 08:00 | 2022-11-30 16:00 |  |  | 10 | 0 | 10 | 142 |  | Substructure Crew
DEMO1650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 | Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | 2023-05-03 08:00 | 2023-05-05 16:00 |  |  | 3 | 0 | 3 | 48 |  | Demolition Crews
SUBS1130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-02-15 08:00 | 2023-02-28 16:00 |  |  | 10 | 0 | 10 | 94 |  | Substructure Crew
EGC400 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Backfill & Grade - NB & SB Median: 714+00-721+43 - Ph2 | 2024-04-24 08:00 | 2024-05-02 16:00 |  |  | 7 | 0 | 7 | -1 |  | Light Cut/Fill Earthwork Crew
EGC390 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 2024-01-09 08:00 | 2024-01-19 16:00 |  |  | 8 | 0 | 8 | -1 | 19 | Light Cut/Fill Earthwork Crew
BBM180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-05-10 05:00 | 2023-05-15 02:00 |  |  | 3 | 0 | 3 | 57 |  | Erection Crew
SUPR620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Overhang 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-05-15 02:00 | 2023-05-19 06:00 |  |  | 5 | 0 | 5 | 57 |  | Super-Structure Crew
SIP180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install SIP Deck Pans100206 - SB: over Chelsea St. - Ph1-S1 | 2023-05-15 02:00 | 2023-05-19 06:00 |  |  | 5 | 0 | 5 | 57 |  | Deck Crew
EGC500 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.1 | Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Excavate / Grade - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 2023-10-11 08:00 | 2023-11-03 16:00 |  |  | 18 | 0 | 18 | 13 |  | Light Cut/Fill Earthwork Crew
STAB540 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Stabilization - NB & SB Median: 714+00-721+43 - Ph2 | 2024-05-03 08:00 | 2024-05-14 16:00 |  |  | 8 | 0 | 8 | -1 |  | Cement Subgrade Crew
STAB510 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Stabilization - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 2024-02-07 08:00 | 2024-02-16 16:00 |  |  | 8 | 0 | 8 | 5 |  | Cement Subgrade Crew
BASE780 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Black Base - NB & SB Median: 714+00-721+43 - Ph2 | 2024-05-30 08:00 | 2024-06-06 16:00 |  |  | 6 | 0 | 6 | -1 |  | Agg Base Crew
SUPR660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-05-19 08:00 | 2023-05-26 16:00 |  |  | 6 | 0 | 6 | 51 |  | Super-Structure Crew
BW1160 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Form / Reinforce / Pour Barrier Wall Footing - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 2024-01-22 08:00 | 2024-01-29 16:00 |  |  | 6 | 0 | 6 | 5 |  | Concrete Barrier Crew
PAV500 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | 2024-09-13 08:00 | 2024-09-19 16:00 |  |  | 5 | 0 | 5 | -4 | 4 | Sub - Asphalt Paving Crew
SUPR720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set Deck Screed 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-06-08 08:00 | 2023-06-09 16:00 |  |  | 2 | 0 | 2 | 55 |  | Super-Structure Crew
BASE720 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Black Base - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 2024-03-06 08:00 | 2024-03-14 16:00 |  |  | 7 | 0 | 7 | -4 | 5 | Agg Base Crew
CP530 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Concrete Pavement (9") - NB & SB Median: 714+00-721+43 - Ph2 | 2024-06-07 08:00 | 2024-06-25 16:00 |  |  | 13 | 0 | 13 | -1 |  | Concrete Paving Crews
SUPR740 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pour Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-06-11 21:00 | 2023-06-12 05:00 |  |  | 1 | 0 | 1 | 62 |  | Super-Structure Crew
CP470 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Concrete Pavement (14") - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 2024-03-15 08:00 | 2024-03-20 16:00 |  |  | 4 | 0 | 4 | -4 | 5 | Concrete Paving Crews
B2450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-06-12 08:00 | 2023-06-25 16:00 |  |  | 14 | 0 | 14 | 78
BW1180 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 714+00-721+43 - Ph2 | 2024-05-15 08:00 | 2024-05-21 16:00 |  |  | 5 | 0 | 5 | -1 |  | Concrete Barrier Crew
EGC380 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Excavate / Grade - MLK Ramp A - Ph1-S2 | 2024-01-22 08:00 | 2024-02-01 16:00 |  |  | 9 | 0 | 9 | -1 | 19 | Light Cut/Fill Earthwork Crew
SUPR790 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-07-03 08:00 | 2023-07-11 16:00 |  |  | 6 | 0 | 6 | 48 |  | Approach Slab Crew
EGC410 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 2024-06-13 08:00 | 2024-06-26 16:00 |  |  | 10 | 0 | 10 | -4 | 1 | Light Cut/Fill Earthwork Crew
B2470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-07-12 08:00 | 2023-07-25 16:00 |  |  | 14 | 0 | 14 | 70
B2480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-12-08 08:00 | 2023-12-18 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Concrete Barrier Crew
DEMO1430 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-03-14 21:00 | 2022-03-18 01:00 | 2022-03-14 21:00 | 2022-03-18 01:00 | 5 | 4 | 0 |  |  | Demolition Crews
STAB490 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Stabilization - MLK Ramp A - Ph1-S2 | 2024-03-13 08:00 | 2024-03-22 16:00 |  |  | 8 | 0 | 8 | -4 | 6 | Cement Subgrade Crew
DEMO1440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-03-14 21:00 | 2022-03-18 06:00 | 2022-03-14 21:00 | 2022-03-18 06:00 | 9 | 5 | 0 |  |  | Demo Bridge Crew
BW1100 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp A - Ph1-S2 | 2024-02-02 08:00 | 2024-02-13 16:00 |  |  | 8 | 0 | 8 | -1 | 19 | Concrete Barrier Crew
DEMO1460 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-03-14 08:00 | 2022-03-18 16:00 | 2022-03-14 08:00 | 2022-03-18 16:00 | 6 | 5 | 0 |  |  | Demo Bridge Crew
BASE670 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Base Course - MLK Ramp A - Ph1-S2 | 2024-03-28 08:00 | 2024-04-04 16:00 |  |  | 6 | 0 | 6 | 2 |  | Agg Base Crew
PAV450 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Asphalt Paving - MLK Ramp A - Ph1-S2 | 2024-04-15 08:00 | 2024-04-17 16:00 |  |  | 3 | 0 | 3 | -4 | 6 | Sub - Asphalt Paving Crew
EGC530 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Excavate / Grade - MLK Ramp B - Ph1-S2 | 2023-05-08 08:00 | 2023-05-19 16:00 |  |  | 10 | 0 | 10 | -4 | 1 | Light Cut/Fill Earthwork Crew
STAB130 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Stabilization - MLK Ramp B - Ph1-S2 | 2023-06-30 08:00 | 2023-07-12 16:00 |  |  | 8 | 0 | 8 | 4 |  | Cement Subgrade Crew
PILE180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-04-16 08:00 | 2022-04-19 16:00 | 2022-04-16 08:00 | 2022-04-19 16:00 | 4 | 2 | 0 |  |  | Pile Driving Crew
DS140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 10 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
BW150 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp B - Ph1-S2 | 2023-05-22 08:00 | 2023-06-01 16:00 |  |  | 8 | 0 | 8 | -4 | 1 | Concrete Barrier Crew
BASE130 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Base Course - MLK Ramp B - Ph1-S2 | 2023-07-31 08:00 | 2023-08-09 16:00 |  |  | 8 | 0 | 8 | 4 |  | Agg Base Crew
CP540 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | 2024-07-30 08:00 | 2024-08-15 16:00 |  |  | 13 | 0 | 13 | -4 | 1 | Concrete Paving Crews
SUBS640 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-15 08:00 | 2022-09-17 16:00 | 2022-09-15 08:00 | 2022-09-17 16:00 | 6 | 2 | 0 |  |  | Substructure Crew
PAV250 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Asphalt Paving - MLK Ramp B - Ph1-S2 | 2024-02-28 08:00 | 2024-03-01 16:00 |  |  | 3 | 0 | 3 | 2 |  | Sub - Asphalt Paving Crew
BW1200 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | 2024-07-01 08:00 | 2024-07-09 16:00 |  |  | 6 | 0 | 6 | -4 | 1 | Concrete Barrier Crew
SUBS560 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-08-22 08:00 | 2022-08-26 16:00 | 2022-08-22 08:00 | 2022-08-26 16:00 | 8 | 5 | 0 |  |  | Substructure Crew
EGC550 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Excavate / Grade - MLK Ramp C - Ph1-S2 | 2023-05-22 08:00 | 2023-06-05 16:00 |  |  | 10 | 0 | 10 | 3 |  | Light Cut/Fill Earthwork Crew
DRG2000 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 2024-05-14 08:00 | 2024-05-15 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
STAB150 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - MLK Ramp C - Ph1-S2 | 2023-08-10 08:00 | 2023-08-23 16:00 |  |  | 10 | 0 | 10 | 4 |  | Cement Subgrade Crew
SUBS570 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-08-30 08:00 | 2022-09-01 16:00 | 2022-08-30 08:00 | 2022-09-01 16:00 | 8 | 3 | 0 |  |  | Substructure Crew
BW210 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp C - Ph1-S2 | 2023-06-06 08:00 | 2023-06-16 16:00 |  |  | 9 | 0 | 9 | 3 |  | Concrete Barrier Crew
SUBS790 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-12 08:00 | 2022-09-19 16:00 | 2022-09-12 08:00 | 2022-09-19 16:00 | 6 | 6 | 0 |  |  | Substructure Crew
BASE150 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Base Course - MLK Ramp C - Ph1-S2 | 2023-09-19 08:00 | 2023-09-28 16:00 |  |  | 8 | 0 | 8 | 4 |  | Agg Base Crew
STAB550 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 2024-06-20 08:00 | 2024-07-11 16:00 |  |  | 15 | 0 | 15 | -4 | 1 | Cement Subgrade Crew
SUBS620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-08-23 08:00 | 2022-09-01 16:00 | 2022-08-23 08:00 | 2022-09-01 16:00 | 8 | 8 | 0 |  |  | Substructure Crew
PAV270 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Asphalt Paving - MLK Ramp C - Ph1-S2 | 2024-03-04 08:00 | 2024-03-06 16:00 |  |  | 3 | 0 | 3 | 2 |  | Sub - Asphalt Paving Crew
BASE800 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | 2024-07-17 08:00 | 2024-08-09 16:00 |  |  | 18 | 0 | 18 | -4 | 1 | Agg Base Crew
EGC370 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Excavate / Grade - MLK Ramp D - Ph1-S2 | 2024-01-05 08:00 | 2024-01-18 16:00 |  |  | 9 | 0 | 9 | -2 | 10 | Light Cut/Fill Earthwork Crew
SUBS630 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-08-31 08:00 | 2022-09-12 16:00 | 2022-08-31 08:00 | 2022-09-12 16:00 | 8 | 7 | 0 |  |  | Substructure Crew
PAV510 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | 2024-09-20 08:00 | 2024-10-03 16:00 |  |  | 10 | 0 | 10 | -4 | 1 | Sub - Asphalt Paving Crew
BBM140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-10-18 08:00 | 2022-10-18 16:00 | 2022-10-18 08:00 | 2022-10-18 16:00 | 2 | 0 | 0 |  |  | Erection Crew
CP550 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | 2024-08-16 08:00 | 2024-09-05 16:00 |  |  | 13 | 0 | 13 | -4 | 1 | Concrete Paving Crews
SUPR380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Overhang 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-10-19 08:00 | 2022-10-27 16:00 | 2022-10-19 08:00 | 2022-10-27 16:00 | 5 | 7 | 0 |  |  | Super-Structure Crew
STAB480 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Stabilization - MLK Ramp D - Ph1-S2 | 2024-02-28 08:00 | 2024-03-12 16:00 |  |  | 10 | 0 | 10 | -4 | 6 | Cement Subgrade Crew
SIP140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install SIP Deck Pans100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-10-25 21:00 | 2022-11-04 16:00 | 2022-10-25 21:00 | 2022-11-04 16:00 | 5 | 9 | 0 |  |  | Deck Crew
BW1030 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp D - Ph1-S2 | 2024-01-19 08:00 | 2024-01-30 16:00 |  |  | 8 | 0 | 8 | -2 | 10 | Concrete Barrier Crew
DRG2100 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (24") - NB & SB Median: 739-740 - Ph2 | 2024-06-10 08:00 | 2024-06-10 16:00 |  |  | 1 | 0 | 1 | -4 | 1 | Drainage Crew - Combo
EGC420 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Backfill & Grade - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-06-27 08:00 | 2024-07-08 16:00 |  |  | 7 | 0 | 7 | 5 |  | Light Cut/Fill Earthwork Crew
SUPR400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-11-03 08:00 | 2022-11-10 16:00 | 2022-11-03 08:00 | 2022-11-10 16:00 | 6 | 6 | 0 |  |  | Super-Structure Crew
BASE630 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Base Course - MLK Ramp D - Ph1-S2 | 2024-03-18 08:00 | 2024-03-25 16:00 |  |  | 6 | 0 | 6 | 4 |  | Agg Base Crew
PAV440 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S2 | 2024-04-04 08:00 | 2024-04-08 16:00 |  |  | 3 | 0 | 3 | 0 |  | Sub - Asphalt Paving Crew
EGC360 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | 2023-11-09 08:00 | 2023-11-27 16:00 |  |  | 9 | 0 | 9 | 12 |  | Light Cut/Fill Earthwork Crew
STAB400 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp A - Ph1-S2 | 2024-02-08 08:00 | 2024-02-21 16:00 |  |  | 10 | 0 | 10 | -4 | 5 | Cement Subgrade Crew
BW910 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp A - Ph1-S2 | 2023-11-28 08:00 | 2023-12-07 16:00 |  |  | 8 | 0 | 8 | 12 |  | Concrete Barrier Crew
BASE490 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Base Course - Hillsborough Ramp A - Ph1-S2 | 2024-02-27 08:00 | 2024-03-05 16:00 |  |  | 6 | 0 | 6 | -4 | 5 | Agg Base Crew
PAV400 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | 2024-03-28 08:00 | 2024-04-01 16:00 |  |  | 3 | 0 | 3 | 2 |  | Sub - Asphalt Paving Crew
SUPR430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set Deck Screed 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-11-17 08:00 | 2022-11-18 16:00 |  |  | 2 | 0 | 2 | 77 |  | Super-Structure Crew
EGC590 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | 2023-07-20 08:00 | 2023-08-02 16:00 |  |  | 10 | 0 | 10 | 8 |  | Light Cut/Fill Earthwork Crew
SUPR450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pour Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-11-20 21:00 | 2022-11-21 05:00 |  |  | 1 | 0 | 1 | 87 |  | Super-Structure Crew
B2690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-11-21 08:00 | 2022-12-04 16:00 |  |  | 14 | 0 | 14 | 121
SUPR490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2023-03-20 08:00 | 2023-03-27 16:00 |  |  | 6 | 0 | 6 | 12 |  | Approach Slab Crew
STAB160 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Stabilization - Hillsborough Ramp B - Ph1-S2 | 2023-11-08 08:00 | 2023-11-20 16:00 |  |  | 8 | 0 | 8 | -1 | 12 | Cement Subgrade Crew
B2710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2023-03-28 08:00 | 2023-04-10 16:00 |  |  | 14 | 0 | 14 | 16
PAV520 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-10-04 08:00 | 2024-10-10 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sub - Asphalt Paving Crew
CP560 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | 2024-09-06 08:00 | 2024-09-16 16:00 |  |  | 7 | 0 | 7 | -3 | 8 | Concrete Paving Crews
BW320 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp B - Ph1-S2 | 2023-08-03 08:00 | 2023-08-14 16:00 |  |  | 8 | 0 | 8 | 9 |  | Concrete Barrier Crew
B2720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2023-09-07 08:00 | 2023-09-15 16:00 |  |  | 7 | 0 | 7 | 1 |  | Concrete Barrier Crew
DEMO1490 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-08-15 21:00 | 2022-08-16 01:00 | 2022-08-15 21:00 | 2022-08-16 01:00 | 5 | 1 | 0 |  |  | Demolition Crews
BASE160 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Base Course - Hillsborough Ramp B - Ph1-S2 | 2023-11-29 08:00 | 2023-12-06 16:00 |  |  | 6 | 0 | 6 | -1 | 12 | Agg Base Crew
DRG2140 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | 2024-06-17 08:00 | 2024-06-17 16:00 |  |  | 1 | 0 | 1 | 10 |  | Drainage Crew - Combo
PAV290 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | 2024-03-07 08:00 | 2024-03-11 16:00 |  |  | 3 | 0 | 3 | 2 |  | Sub - Asphalt Paving Crew
DEMO1560 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Edge of Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-08-15 21:00 | 2022-08-17 05:00 | 2022-08-15 21:00 | 2022-08-17 05:00 | 10 | 2 | 0 |  |  | Demo Bridge Crew
EGC330 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | 2023-08-15 08:00 | 2023-08-25 16:00 |  |  | 9 | 0 | 9 | 8 |  | Light Cut/Fill Earthwork Crew
DEMO1570 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo End of Existing End Bent 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-08-15 08:00 | 2022-08-17 16:00 | 2022-08-15 08:00 | 2022-08-17 16:00 | 6 | 3 | 0 |  |  | Demo Bridge Crew
STAB560 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Stabilization - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-07-12 08:00 | 2024-07-25 16:00 |  |  | 10 | 0 | 10 | 2 |  | Cement Subgrade Crew
PILE290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-08-17 08:00 | 2022-08-19 16:00 | 2022-08-17 08:00 | 2022-08-19 16:00 | 4 | 3 | 0 |  |  | Pile Driving Crew
BASE810 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Black Base - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-08-12 08:00 | 2024-08-27 16:00 |  |  | 12 | 0 | 12 | 2 |  | Agg Base Crew
DS170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-05-12 08:00 | 2022-05-14 16:00 | 2022-05-12 08:00 | 2022-05-14 16:00 | 10 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
CP570 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 757+10-759+97 - Ph2 | 2024-09-17 08:00 | 2024-09-25 16:00 |  |  | 7 | 0 | 7 | -1 | 16 | Concrete Paving Crews
STAB300 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | 2023-12-22 08:00 | 2024-01-11 16:00 |  |  | 8 | 0 | 8 | 9 |  | Cement Subgrade Crew
BW1220 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-07-26 08:00 | 2024-08-01 16:00 |  |  | 5 | 0 | 5 | 2 |  | Concrete Barrier Crew
SUBS1280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-04-27 08:00 | 2023-05-03 16:00 |  |  | 5 | 0 | 5 | 35 |  | Substructure Crew
SUBS930 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-07-08 08:00 | 2022-07-25 16:00 | 2022-07-08 08:00 | 2022-07-25 16:00 | 8 | 12 | 0 |  |  | Substructure Crew
EGC430 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | 2024-07-09 08:00 | 2024-07-22 16:00 |  |  | 10 | 0 | 10 | 6 |  | Light Cut/Fill Earthwork Crew
BW660 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp C1 - Ph1-S2 | 2023-08-28 08:00 | 2023-09-08 16:00 |  |  | 8 | 0 | 8 | 8 |  | Concrete Barrier Crew
SUBS950 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-07-07 08:00 | 2022-07-21 16:00 | 2022-07-07 08:00 | 2022-07-21 16:00 | 8 | 11 | 0 |  |  | Substructure Crew
BASE370 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp C1 - Ph1-S2 | 2024-01-18 08:00 | 2024-01-30 16:00 |  |  | 9 | 0 | 9 | 9 |  | Agg Base Crew
SUBS1260 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-11-07 08:00 | 2022-11-18 16:00 | 2022-11-07 08:00 |  | 5 | 4 | 5 | 143 |  | Substructure Crew
PAV350 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S2 | 2024-03-19 08:00 | 2024-03-22 16:00 |  |  | 4 | 0 | 4 | 2 |  | Sub - Asphalt Paving Crew
SUBS1000 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-09-06 08:00 | 2022-09-15 16:00 | 2022-09-06 08:00 | 2022-09-15 16:00 | 8 | 8 | 0 |  |  | Substructure Crew
EGC340 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | 2023-08-03 08:00 | 2023-08-14 16:00 |  |  | 8 | 0 | 8 | 8 |  | Light Cut/Fill Earthwork Crew
SUBS1050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-01-25 08:00 | 2023-02-03 16:00 |  |  | 8 | 0 | 8 | 94 |  | Substructure Crew
STAB570 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Stabilization - NB & SB Median: 761+67-773+42 - Ph2 | 2024-07-26 08:00 | 2024-08-12 16:00 |  |  | 12 | 0 | 12 | 3 |  | Cement Subgrade Crew
STAB320 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 2023-11-08 08:00 | 2023-11-27 16:00 |  |  | 10 | 0 | 10 | 13 |  | Cement Subgrade Crew
BBM170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-09 21:00 | 2023-05-12 03:00 |  |  | 3 | 0 | 3 | 39 |  | Erection Crew
BASE820 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Black Base - NB & SB Median: 761+67-773+42 - Ph2 | 2024-08-28 08:00 | 2024-09-12 16:00 |  |  | 10 | 0 | 10 | 13 |  | Agg Base Crew
SG100 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | 2023-08-15 08:00 | 2023-08-24 16:00 |  |  | 8 | 0 | 8 | 9 |  | Concrete Barrier Crew
SUPR590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Overhang 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-12 03:00 | 2023-05-18 22:00 |  |  | 5 | 0 | 5 | 39 |  | Super-Structure Crew
CP580 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | 2024-09-26 08:00 | 2024-10-04 16:00 |  |  | 7 | 0 | 7 | 4 |  | Concrete Paving Crews
BASE410 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | 2023-12-07 08:00 | 2023-12-21 16:00 |  |  | 11 | 0 | 11 | 9 |  | Agg Base Crew
BW1240 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | 2024-08-13 08:00 | 2024-08-20 16:00 |  |  | 6 | 0 | 6 | 11 |  | Concrete Barrier Crew
SIP170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install SIP Deck Pans100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-12 03:00 | 2023-05-18 22:00 |  |  | 5 | 0 | 5 | 39 |  | Deck Crew
PAV370 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S2 | 2024-03-12 08:00 | 2024-03-18 16:00 |  |  | 5 | 0 | 5 | 2 |  | Sub - Asphalt Paving Crew
DRG2160 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | 2024-06-20 08:00 | 2024-06-21 16:00 |  |  | 2 | 0 | 2 | 11 |  | Drainage Crew - Combo
SUPR610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-19 08:00 | 2023-05-26 16:00 |  |  | 6 | 0 | 6 | 34 |  | Super-Structure Crew
EGC350 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | 2023-08-28 08:00 | 2023-09-11 16:00 |  |  | 9 | 0 | 9 | 8 |  | Light Cut/Fill Earthwork Crew
STAB370 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Stabilization - Hillsborough Ramp D - Ph1-S2 | 2023-10-30 08:00 | 2023-11-08 16:00 |  |  | 8 | 0 | 8 | 4 |  | Cement Subgrade Crew
CP590 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | 2024-10-07 08:00 | 2024-10-15 16:00 |  |  | 7 | 0 | 7 | 4 |  | Concrete Paving Crews
SUPR670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set Deck Screed 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-06-02 08:00 | 2023-06-05 16:00 |  |  | 2 | 0 | 2 | 34 |  | Super-Structure Crew
BW820 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp D - Ph1-S2 | 2023-09-12 08:00 | 2023-09-22 16:00 |  |  | 9 | 0 | 9 | 8 |  | Concrete Barrier Crew
BASE450 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Base Course - Hillsborough Ramp D - Ph1-S2 | 2024-01-31 08:00 | 2024-02-07 16:00 |  |  | 6 | 0 | 6 | 9 |  | Agg Base Crew
PAV390 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | 2024-03-25 08:00 | 2024-03-27 16:00 |  |  | 3 | 0 | 3 | 2 |  | Sub - Asphalt Paving Crew
MS330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 2023-04-28 08:00 | 2023-05-11 16:00 |  |  | 10 | 0 | 10 | 46 |  | Concrete Paving Crews
DS10 | Completed | 3462-FDOT-Owner-12.2.1.1.2 | Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Prepare Shop Drawings / Submittals: Structural 48" Drilled Shafts | 2021-08-19 08:00 | 2021-09-24 16:00 | 2021-08-19 08:00 | 2021-09-24 16:00 | 25 | 25 | 0
SUPR690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pour Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-06-05 21:00 | 2023-06-06 05:00 |  |  | 1 | 0 | 1 | 38 |  | Super-Structure Crew
DS30 | Completed | 3462-FDOT-Owner-12.2.1.1.2 | Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Procurement: Structural 48" Drilled Shafts | 2022-01-03 08:00 | 2022-02-19 16:00 | 2022-01-03 08:00 | 2022-02-19 16:00 | 65 | 34 | 0
DRG2180 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: Existing to S-82 to S-86 (18") - NB & SB Median: 768-770 - Ph2 | 2024-06-26 08:00 | 2024-06-28 16:00 |  |  | 3 | 0 | 3 | 11 |  | Drainage Crew - Combo
B2930 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-06-06 08:00 | 2023-06-19 16:00 |  |  | 14 | 0 | 14 | 49
EGC440 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | 2024-07-23 08:00 | 2024-08-01 16:00 |  |  | 8 | 0 | 8 | 10 |  | Light Cut/Fill Earthwork Crew
SUPR780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-06-20 08:00 | 2023-06-27 16:00 |  |  | 6 | 0 | 6 | 34 |  | Approach Slab Crew
B2950 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-06-28 08:00 | 2023-07-11 16:00 |  |  | 14 | 0 | 14 | 49
STAB580 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Stabilization - NB & SB Median: 774+82-786+69 - Ph2 | 2024-08-13 08:00 | 2024-08-28 16:00 |  |  | 12 | 0 | 12 | 3 |  | Cement Subgrade Crew
B2960 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-11-17 08:00 | 2023-11-30 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Concrete Barrier Crew
BASE840 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Black Base - NB & SB Median: 774+82-786+69 - Ph2 | 2024-09-16 08:00 | 2024-09-27 16:00 |  |  | 10 | 0 | 10 | 13 |  | Agg Base Crew
DEMO1450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-03-14 21:00 | 2022-03-18 01:00 | 2022-03-14 21:00 | 2022-03-18 01:00 | 5 | 4 | 0 |  |  | Demolition Crews
CP610 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | 2024-10-16 08:00 | 2024-10-24 16:00 |  |  | 7 | 0 | 7 | 4 |  | Concrete Paving Crews
BW100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | 2022-07-14 08:00 | 2022-08-15 16:00 | 2022-07-14 08:00 | 2022-08-15 16:00 | 7 | 23 | 0 |  |  | Concrete Barrier Crew
BW1260 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | 2024-08-29 08:00 | 2024-09-06 16:00 |  |  | 5 | 0 | 5 | 10 |  | Concrete Barrier Crew
BW270 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | 2022-08-17 08:00 | 2022-08-20 16:00 | 2022-08-17 08:00 | 2022-08-20 16:00 | 6 | 3 | 0 |  |  | Concrete Barrier Crew
DEMO1480 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-03-14 21:00 | 2022-03-19 02:00 | 2022-03-14 21:00 | 2022-03-19 02:00 | 13 | 5 | 0 |  |  | Demo Bridge Crew
BW300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 104+06.12-107+60.00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 20 |  | Concrete Barrier Crew
DRG2190 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | 2024-07-01 08:00 | 2024-07-02 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
DEMO1520 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-03-28 08:00 | 2022-04-10 16:00 | 2022-03-28 08:00 | 2022-04-10 16:00 | 6 | 10 | 0 |  |  | Demo Bridge Crew
BW410 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | 2022-10-03 08:00 | 2022-10-07 16:00 | 2022-10-03 08:00 | 2022-10-07 16:00 | 5 | 5 | 0 |  |  | Concrete Barrier Crew
PILE200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Drive Production H-Piles 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-04-25 08:00 | 2022-05-14 16:00 | 2022-04-25 08:00 | 2022-05-14 16:00 | 4 | 15 | 0 |  |  | Pile Driving Crew
BW470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 150+98.92-155+14.52 - Ph1-S1 | 2022-11-22 08:00 | 2022-12-01 16:00 |  |  | 5 | 0 | 5 | 15 |  | Concrete Barrier Crew
DS150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2022-07-11 08:00 | 2022-07-14 16:00 | 15 | 4 | 0 |  |  | Sub - Drilled Shaft Crew
CP630 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | 2024-10-25 08:00 | 2024-11-04 16:00 |  |  | 7 | 0 | 7 | 4 |  | Concrete Paving Crews
BW500 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 408+39.93-170+00.00 - Ph1-S1 | 2022-11-01 08:00 | 2022-11-18 16:00 | 2022-11-01 08:00 |  | 5 | 8 | 5 | 28 |  | Concrete Barrier Crew
SUBS700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-30 08:00 | 2022-12-09 16:00 |  |  | 8 | 0 | 8 | 69 |  | Substructure Crew
DRG2200 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-105 to S-111 to Existing (18" & 15") - NB & SB Median: 780-782 - Ph2 | 2024-07-03 08:00 | 2024-07-05 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
EGC450 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 2024-08-02 08:00 | 2024-08-13 16:00 |  |  | 8 | 0 | 8 | 14 |  | Light Cut/Fill Earthwork Crew
BW1060 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | 2023-07-07 08:00 | 2023-07-18 16:00 |  |  | 8 | 0 | 8 | 13 |  | Concrete Barrier Crew
SUBS670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 48 |  | Substructure Crew
BW980 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | 2023-06-13 08:00 | 2023-06-21 16:00 |  |  | 7 | 0 | 7 | 13 |  | Concrete Barrier Crew
SUBS680 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-08-23 08:00 | 2022-08-29 16:00 | 2022-08-23 08:00 | 2022-08-29 16:00 | 8 | 5 | 0 |  |  | Substructure Crew
STAB590 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Stabilization - NB & SB Median: 788+09-813+16 - Ph2 | 2024-08-29 08:00 | 2024-09-24 16:00 |  |  | 17 | 0 | 17 | 3 |  | Cement Subgrade Crew
BW940 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 64+06.16-69+52.31 - Ph1-S1 | 2023-06-06 08:00 | 2023-06-12 16:00 |  |  | 5 | 0 | 5 | 13 |  | Concrete Barrier Crew
BASE870 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Black Base - NB & SB Median: 788+09-813+16 - Ph2 | 2024-10-14 08:00 | 2024-11-05 16:00 |  |  | 17 | 0 | 17 | 3 |  | Agg Base Crew
BW770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | 2023-04-18 08:00 | 2023-04-24 16:00 |  |  | 5 | 0 | 5 | 8 |  | Concrete Barrier Crew
SUBS850 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-16 08:00 | 2022-12-22 16:00 |  |  | 5 | 0 | 5 | 60 |  | Substructure Crew
CP650 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | 2024-11-06 08:00 | 2024-11-15 16:00 |  |  | 7 | 0 | 7 | 3 |  | Concrete Paving Crews
BW670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | 2023-03-27 08:00 | 2023-03-31 16:00 |  |  | 5 | 0 | 5 | 6 |  | Concrete Barrier Crew
SUBS720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-06 08:00 | 2022-12-15 16:00 |  |  | 8 | 0 | 8 | 48 |  | Substructure Crew
BW1280 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | 2024-09-25 08:00 | 2024-10-01 16:00 |  |  | 5 | 0 | 5 | 3 |  | Concrete Barrier Crew
BW570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | 2023-02-03 08:00 | 2023-02-14 16:00 |  |  | 8 | 0 | 8 | 4 |  | Concrete Barrier Crew
DRG2230 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 2024-07-10 08:00 | 2024-07-11 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
SUBS760 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-09-07 08:00 | 2022-09-16 16:00 | 2022-09-07 08:00 | 2022-09-16 16:00 | 10 | 8 | 0 |  |  | Substructure Crew
BBM150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-24 21:00 | 2023-01-31 01:00 |  |  | 5 | 0 | 5 | 56 |  | Erection Crew
BW630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 2023-03-13 08:00 | 2023-03-17 16:00 |  |  | 5 | 0 | 5 | 6 |  | Concrete Barrier Crew
SUPR420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Overhang 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-31 01:00 | 2023-02-08 03:00 |  |  | 7 | 0 | 7 | 56 |  | Super-Structure Crew
BW600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 2023-02-24 08:00 | 2023-03-02 16:00 |  |  | 5 | 0 | 5 | 7 |  | Concrete Barrier Crew
SIP150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install SIP Deck Pans100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-31 01:00 | 2023-02-08 03:00 |  |  | 7 | 0 | 7 | 56 |  | Deck Crew
CP670 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | 2024-11-18 08:00 | 2024-11-26 16:00 |  |  | 7 | 0 | 7 | 5 |  | Concrete Paving Crews
MS-SC | Not Started | 3462-FDOT-Owner-12.0 | Project Milestones | Substantial Completion |  | 2025-05-13 16:00 |  |  | 0 | 0 | 0 | -6 | 1
SUPR460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-08 08:00 | 2023-02-17 16:00 |  |  | 8 | 0 | 8 | 49 |  | Super-Structure Crew
DRG2290 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-138 to S-141 (18") - NB & SB Median: 799-801 - Ph2 | 2024-07-25 08:00 | 2024-07-26 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
EGC460 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 2024-09-17 08:00 | 2024-09-24 16:00 |  |  | 6 | 0 | 6 | 8 |  | Light Cut/Fill Earthwork Crew
SUPR480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set Deck Screed 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-23 08:00 | 2023-02-24 16:00 |  |  | 2 | 0 | 2 | 49 |  | Super-Structure Crew
SUPR500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pour Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-26 21:00 | 2023-02-27 05:00 |  |  | 1 | 0 | 1 | 55 |  | Super-Structure Crew
B3170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-27 08:00 | 2023-03-12 16:00 |  |  | 14 | 0 | 14 | 67
STAB600 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Stabilization - NB & SB Median: 815+20-839+61 - Ph2 | 2024-09-25 08:00 | 2024-10-14 16:00 |  |  | 14 | 0 | 14 | 8 |  | Cement Subgrade Crew
BASE910 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Black Base - NB & SB Median: 815+20-839+61 - Ph2 | 2024-11-06 08:00 | 2024-12-06 16:00 |  |  | 19 | 0 | 19 | 4 |  | Agg Base Crew
SUPR510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-04-17 08:00 | 2023-04-25 16:00 |  |  | 7 | 0 | 7 | 24 |  | Approach Slab Crew
CP700 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | 2024-12-03 08:00 | 2024-12-12 16:00 |  |  | 8 | 0 | 8 | 4 |  | Concrete Paving Crews
B3190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Approach Slabs Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-04-26 08:00 | 2023-05-09 16:00 |  |  | 14 | 0 | 14 | 35
BW1300 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 815+20-839+61 - Ph2 | 2024-10-14 08:00 | 2024-10-23 16:00 |  |  | 8 | 0 | 8 | 5 |  | Concrete Barrier Crew
B3200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-09-25 08:00 | 2023-10-04 16:00 |  |  | 8 | 0 | 8 | 1 |  | Concrete Barrier Crew
DRG2360 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 2024-08-07 08:00 | 2024-08-08 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DEMO1470 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-10-03 08:00 | 2022-10-07 16:00 | 2022-10-03 08:00 | 2022-10-07 16:00 | 4 | 5 | 0 |  |  | Demolition Crews
R3500 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | 2025-02-18 08:00 | 2025-03-05 16:00 |  |  | 12 | 0 | 12 | -4 | 1 | Sub - Diamond Grind Pavement Crew
DEMO1530 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Edge of Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-10-10 08:00 | 2022-10-14 16:00 | 2022-10-10 08:00 | 2022-10-14 16:00 | 10 | 5 | 0 |  |  | Demo Bridge Crew
DEMO1550 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-10-03 08:00 | 2022-10-07 16:00 | 2022-10-03 08:00 | 2022-10-07 16:00 | 5 | 5 | 0 |  |  | Demo Bridge Crew
PILE250 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-03-01 08:00 | 2022-03-18 16:00 | 2022-03-01 08:00 | 2022-03-18 16:00 | 4 | 14 | 0 |  |  | Pile Driving Crew
DS160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Install 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-07-11 08:00 | 2022-08-22 16:00 | 2022-07-11 08:00 | 2022-08-22 16:00 | 15 | 31 | 0 |  |  | Sub - Drilled Shaft Crew
SUBS1230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-15 08:00 | 2023-01-03 16:00 |  |  | 8 | 0 | 8 | 72 |  | Substructure Crew
R3510 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | 2025-03-06 08:00 | 2025-03-21 16:00 |  |  | 12 | 0 | 12 | -2 | 15 | Sub - Diamond Grind Pavement Crew
SUBS810 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 57 |  | Substructure Crew
PAV530 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | 2025-02-12 08:00 | 2025-03-04 16:00 |  |  | 15 | 0 | 15 | -4 | 3 | Sub - Asphalt Milling Crew
SUBS820 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-08-22 08:00 | 2022-08-29 16:00 | 2022-08-22 08:00 | 2022-08-29 16:00 | 8 | 6 | 0 |  |  | Substructure Crew
PM220 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | 2025-03-26 08:00 | 2025-04-08 16:00 |  |  | 10 | 0 | 10 | -4 | 2 | Sub - Striping Crew
SUBS1220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-17 08:00 | 2023-01-26 16:00 |  |  | 8 | 0 | 8 | 56 |  | Substructure Crew
R3540 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Install Misc Final Signage Remaining - Project Limits - Ph3 | 2025-03-06 08:00 | 2025-04-01 16:00 |  |  | 19 | 0 | 19 | -4 | 1 | Sub - Signing Crew
SUBS890 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-06 08:00 | 2022-12-15 16:00 |  |  | 8 | 0 | 8 | 56 |  | Substructure Crew
MS-FC | Not Started | 3462-FDOT-Owner-12.0 | Project Milestones | Final Completion (Baseline Date: 24-Apr-25) |  | 2025-06-18 16:00 |  |  | 0 | 0 | 0 | -6 | 1
SUBS910 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-09-07 08:00 | 2022-10-10 16:00 | 2022-09-07 08:00 | 2022-10-10 16:00 | 10 | 24 | 0 |  |  | Substructure Crew
FDOTP | Not Started | 3462-FDOT-Owner-12.0 | Project Milestones | FDOT Develop & Issue Punch List | 2025-05-14 08:00 | 2025-05-20 16:00 |  |  | 7 | 0 | 7 | -6 | 1
BBM160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-31 21:00 | 2023-02-07 01:00 |  |  | 5 | 0 | 5 | 65 |  | Erection Crew
MS-P3F | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | End of Phase 3 |  | 2025-05-13 16:00 |  |  | 0 | 0 | 0 | -6 | 1
SUPR520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Overhang 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-07 08:00 | 2023-02-15 16:00 |  |  | 7 | 0 | 7 | 57 |  | Super-Structure Crew
MS-P3S | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Start of Phase 3 | 2025-02-12 08:00 |  |  |  | 0 | 0 | 0 | -6 | 2
SIP160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install SIP Deck Pans100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-07 08:00 | 2023-02-15 16:00 |  |  | 7 | 0 | 7 | 57 |  | Deck Crew
MS-P2F | Not Started | 3462-FDOT-Owner-12.4.P2.1 | Construction: Phase 2: Milestones | End of Phase 2 |  | 2025-02-11 16:00 |  |  | 0 | 0 | 0 | -6 | 1
MS-P2S | Not Started | 3462-FDOT-Owner-12.4.P2.1 | Construction: Phase 2: Milestones | Start of Phase 2 | 2024-04-18 08:00 |  |  |  | 0 | 0 | 0 | -6 | 1
SUPR540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-16 08:00 | 2023-02-27 16:00 |  |  | 8 | 0 | 8 | 57 |  | Super-Structure Crew
LOE-CD | In Progress | 3462-FDOT-Owner-12.0 | Project Milestones | Construction Duration (1200 Calendar Days + 92 FDOT Holidays = 1292 Calendar Day Contract Duration) | 2021-10-25 08:00 | 2025-06-18 16:00 | 2021-10-25 08:00 |  | 1292 | 384 | 949 | -6
MS-CE | Completed | 3462-FDOT-Owner-12.0 | Project Milestones | Contract Execution | 2021-07-15 08:00 |  | 2021-07-15 08:00 |  | 0 | 0 | 0
SUPR560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set Deck Screed 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-03-03 08:00 | 2023-03-06 16:00 |  |  | 2 | 0 | 2 | 57 |  | Super-Structure Crew
MS-LNTP | Completed | 3462-FDOT-Owner-12.0 | Project Milestones | Notice to Proceed | 2021-10-25 08:00 |  | 2021-10-25 08:00 |  | 0 | 0 | 0
SUPR570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pour Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-03-07 08:00 | 2023-03-07 16:00 |  |  | 1 | 0 | 1 | 57 |  | Super-Structure Crew
MS-NTP | Completed | 3462-FDOT-Owner-12.0 | Project Milestones | Start Construction | 2021-10-25 08:00 |  | 2021-10-25 08:00 |  | 0 | 0 | 0
B3410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-03-08 08:00 | 2023-03-21 16:00 |  |  | 14 | 0 | 14 | 79
SP10 | Completed | 3462-FDOT-Owner-12.4.IP1.2 | Construction: Initial Phase 1: Site Preparation | Mobilization - IPh1 | 2021-10-18 08:00 | 2021-11-15 16:00 | 2021-10-18 08:00 | 2021-11-15 16:00 | 20 | 20 | 0
ENV10 | Completed | 3462-FDOT-Owner-12.2.1.5 | Preconstruction: Procurement: Environmental | Prepare Shop Drawings / Submittals: Environmental Compliance | 2021-08-12 08:00 | 2021-08-18 16:00 | 2021-08-12 08:00 | 2021-08-18 16:00 | 5 | 5 | 0
SUPR580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-05-16 08:00 | 2023-05-25 16:00 |  |  | 8 | 0 | 8 | 17 |  | Approach Slab Crew
RDW10 | Completed | 3462-FDOT-Owner-12.2.1.2.3 | Preconstruction: Procurement: Walls: Temp Critical Walls | Prepare Shop Drawings / Submittals: Temp Critical Walls | 2021-09-13 08:00 | 2022-02-18 16:00 | 2021-09-13 08:00 | 2022-02-18 16:00 | 15 | 104 | 0
B3430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Approach Slabs Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-05-26 08:00 | 2023-06-08 16:00 |  |  | 14 | 0 | 14 | 26
DRG10 | Completed | 3462-FDOT-Owner-12.2.1.3 | Preconstruction: Procurement: Drainage Pipe & Structures | Prepare Shop Drawings / Submittals: Drainage Pipe & Structures | 2021-08-26 08:00 | 2022-01-15 16:00 | 2021-08-26 08:00 | 2022-01-15 16:00 | 25 | 90 | 0
B3440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-10-20 08:00 | 2023-10-31 16:00 |  |  | 8 | 0 | 8 | 1 |  | Concrete Barrier Crew
SUBS800 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-04 08:00 | 2023-01-13 16:00 |  |  | 8 | 0 | 8 | 48 |  | Substructure Crew
FND10 | Completed | 3462-FDOT-Owner-12.2.1.1.1 | Preconstruction: Procurement: Bridges: H-Pile Foundations | Prepare Shop Drawings / Submittals: H-Pile Foundations | 2021-09-08 08:00 | 2021-10-12 16:00 | 2021-09-08 08:00 | 2021-10-12 16:00 | 25 | 25 | 0
SUBS730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-06 08:00 | 2022-12-15 16:00 |  |  | 8 | 0 | 8 | 50 |  | Substructure Crew
SUB30 | Completed | 3462-FDOT-Owner-12.2.1.1.3 | Preconstruction: Procurement: Bridges: Substructure | Procurement: Substructure | 2022-02-14 08:00 | 2022-02-19 16:00 | 2022-02-14 08:00 | 2022-02-19 16:00 | 50 | 5 | 0
SUBS900 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-06 08:00 | 2022-12-15 16:00 |  |  | 8 | 0 | 8 | 59 |  | Substructure Crew
SPS10 | Completed | 3462-FDOT-Owner-12.2.1.1.4 | Preconstruction: Procurement: Bridges: Superstructure | Prepare Shop Drawings / Submittals: Superstructure | 2022-02-14 08:00 | 2022-03-18 16:00 | 2022-02-14 08:00 | 2022-03-18 16:00 | 25 | 25 | 0
SUBS980 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-04 08:00 | 2023-01-13 16:00 |  |  | 8 | 0 | 8 | 56 |  | Substructure Crew
EGC320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | 2023-04-26 08:00 | 2023-05-16 16:00 |  |  | 15 | 0 | 15 | 23 |  | Light Cut/Fill Earthwork Crew
RET10 | Completed | 3462-FDOT-Owner-12.2.1.2.1 | Preconstruction: Procurement: Walls: Anchored Retaining Walls | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | 2022-02-18 08:00 | 2022-02-18 08:00 | 2022-02-18 08:00 | 2022-02-18 08:00 | 0 | 0 | 0
STAB530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 2023-11-07 08:00 | 2023-11-17 16:00 |  |  | 8 | 0 | 8 | -2 | 10 | Cement Subgrade Crew
ITS10 | Completed | 3462-FDOT-Owner-12.2.1.4.3 | Preconstruction: Procurement: Electrical / ITS: ITS | Prepare Shop Drawings / Submittals: ITS | 2021-10-11 08:00 | 2021-11-19 16:00 | 2021-10-11 08:00 | 2021-11-19 16:00 | 40 | 29 | 0
BASE740 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Black Base - SB: 709+50-721+43 - Ph1-S1 | 2023-11-27 08:00 | 2023-12-01 16:00 |  |  | 5 | 0 | 5 | 0 | 13 | Agg Base Crew
PAV490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | 2024-01-10 08:00 | 2024-01-11 16:00 |  |  | 2 | 0 | 2 | 53 |  | Sub - Asphalt Paving Crew
LTG10 | Completed | 3462-FDOT-Owner-12.2.1.4.1 | Preconstruction: Procurement: Electrical / ITS: Lighting | Prepare Shop Drawings / Submittals: Lighting | 2021-10-11 08:00 | 2021-11-15 16:00 | 2021-10-11 08:00 | 2021-11-15 16:00 | 25 | 25 | 0
CP490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | 2023-12-04 08:00 | 2023-12-15 16:00 |  |  | 10 | 0 | 10 | 45 |  | Concrete Paving Crews
SGN10 | Completed | 3462-FDOT-Owner-12.2.1.4.2.1 | Preconstruction: Procurement: Electrical / ITS: Signage | Prepare Shop Drawings / Submittals: Signage | 2021-11-16 08:00 | 2021-12-05 16:00 | 2021-11-16 08:00 | 2021-12-05 16:00 | 25 | 11 | 0
EGC100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | 2022-03-17 08:00 | 2022-03-18 16:00 | 2022-03-17 08:00 | 2022-03-18 16:00 | 2 | 2 | 0 |  |  | Light Cut/Fill Earthwork Crew
DRG30 | Completed | 3462-FDOT-Owner-12.2.1.3 | Preconstruction: Procurement: Drainage Pipe & Structures | Procurement: Drainage Pipe & Structures | 2021-10-25 08:00 | 2022-02-18 16:00 | 2021-10-25 08:00 | 2022-02-18 16:00 | 30 | 74 | 0
STAB170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 2022-12-07 08:00 | 2022-12-16 16:00 |  |  | 8 | 0 | 8 | 0 | 9 | Cement Subgrade Crew
FND30 | Completed | 3462-FDOT-Owner-12.2.1.1.1 | Preconstruction: Procurement: Bridges: H-Pile Foundations | Procurement: Foundations: H-Pile Foundations | 2021-10-13 08:00 | 2021-11-16 16:00 | 2021-10-13 08:00 | 2021-11-16 16:00 | 30 | 24 | 0
BASE170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Black Base - NB: 722+83-735+00 - Ph1-S1 | 2022-12-19 08:00 | 2023-01-10 16:00 |  |  | 11 | 0 | 11 | 10 |  | Agg Base Crew
RDW30 | Completed | 3462-FDOT-Owner-12.2.1.2.3 | Preconstruction: Procurement: Walls: Temp Critical Walls | Procurement: Temp Critical Walls: H Pile | 2021-10-27 08:00 | 2022-02-18 16:00 | 2021-10-27 08:00 | 2022-02-18 16:00 | 20 | 72 | 0
PAV300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | 2023-03-06 08:00 | 2023-03-08 16:00 |  |  | 3 | 0 | 3 | 1 |  | Sub - Asphalt Paving Crew
RET30 | Completed | 3462-FDOT-Owner-12.2.1.2.1 | Preconstruction: Procurement: Walls: Anchored Retaining Walls | Procurement: Anchored Retaining Walls | 2022-02-18 08:00 | 2022-04-16 16:00 | 2022-02-18 08:00 | 2022-04-16 16:00 | 19 | 41 | 0
GRD100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | 2023-02-28 08:00 | 2023-03-06 16:00 |  |  | 5 | 0 | 5 | 3 |  | Sub - Diamond Grind Pavement Crew
ITS30 | Completed | 3462-FDOT-Owner-12.2.1.4.3 | Preconstruction: Procurement: Electrical / ITS: ITS | Procurement: ITS | 2022-02-21 08:00 | 2022-05-15 08:00 | 2022-02-21 08:00 | 2022-05-15 08:00 | 150 | 60 | 0
DRG150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: Existing to S-11 to S-13 (24") - NB: 725-726 - Ph1-S1 | 2022-09-16 08:00 | 2022-09-17 16:00 | 2022-09-16 08:00 | 2022-09-17 16:00 | 2 | 1 | 0 |  |  | Drainage Crew - Combo
LTG30 | Completed | 3462-FDOT-Owner-12.2.1.4.1 | Preconstruction: Procurement: Electrical / ITS: Lighting | Procurement: Lighting | 2022-02-21 08:00 | 2022-05-14 16:00 | 2022-02-21 08:00 | 2022-05-14 16:00 | 80 | 60 | 0
EGC310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | 2023-04-18 08:00 | 2023-04-25 16:00 |  |  | 6 | 0 | 6 | 23 |  | Light Cut/Fill Earthwork Crew
SGN30 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.1 | Preconstruction: Procurement: Electrical / ITS: Signage | Procurement: Signage | 2022-06-20 08:00 | 2023-04-14 16:00 | 2022-06-20 08:00 |  | 130 | 101 | 100 | 46
STAB520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Stabilization - SB: 722+83-735+00 - Ph1-S1 | 2023-10-26 08:00 | 2023-11-06 16:00 |  |  | 8 | 0 | 8 | -2 | 10 | Cement Subgrade Crew
SPS30 | Completed | 3462-FDOT-Owner-12.2.1.1.4 | Preconstruction: Procurement: Bridges: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | 2022-02-21 08:00 | 2022-05-14 16:00 | 2022-02-21 08:00 | 2022-05-14 16:00 | 60 | 60 | 0
BASE710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Black Base - SB: 722+83-735+00 - Ph1-S1 | 2023-11-15 08:00 | 2023-11-21 16:00 |  |  | 5 | 0 | 5 | 0 | 13 | Agg Base Crew
PAV480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | 2023-12-22 08:00 | 2024-01-04 16:00 |  |  | 3 | 0 | 3 | 18 |  | Sub - Asphalt Paving Crew
CP460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | 2023-11-27 08:00 | 2023-12-01 16:00 |  |  | 5 | 0 | 5 | 20 |  | Concrete Paving Crews
WBO-TEC-10 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | Tampa Electric Company - Remaining Pole Procurement - Started 14-Jan-21 | 2021-01-21 12:00 | 2022-02-18 16:00 | 2021-01-21 12:00 | 2022-02-18 16:00 | 87 | 394 | 0 |  |  | Sub - Electrical Installation Crew
EC10 | Completed | 3462-FDOT-Owner-12.4.IP1.2 | Construction: Initial Phase 1: Site Preparation | Erosion Control Installation - Project Limits - IPh1 | 2021-11-01 08:00 | 2021-11-23 16:00 | 2021-11-01 08:00 | 2021-11-23 16:00 | 20 | 16 | 0 |  |  | Sub - Erosion Control Crew
CG100 | Completed | 3462-FDOT-Owner-12.4.IP1.2 | Construction: Initial Phase 1: Site Preparation | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | 2021-10-25 08:00 | 2021-11-29 16:00 | 2021-10-25 08:00 | 2021-11-29 16:00 | 20 | 22 | 0 |  |  | Sub - Clearing & Grubbing Crew
M1900 | Not Started | 3462-FDOT-Owner-12.4.P1.2.1 | Construction: Phase 1: Stage 2: Milestones | Start of Phase 1, Stage 2 | 2023-05-08 08:00 |  |  |  | 0 | 0 | 0 | -4 | 1
M1999 | Not Started | 3462-FDOT-Owner-12.4.P1.2.1 | Construction: Phase 1: Stage 2: Milestones | End of Phase 1, Stage 2 |  | 2024-04-17 16:00 |  |  | 0 | 0 | 0 | -4 | 5
MS-IP1S | Completed | 3462-FDOT-Owner-12.4.IP1.1 | Construction: Initial Phase 1: Milestones | Start of Initial Phase 1 | 2021-10-18 08:00 |  | 2021-10-18 08:00 |  | 0 | 0 | 0
DRGJB20 | Completed | 3462-FDOT-Owner-12.4.IP1.4 | Construction: Initial Phase 1: Jack and Bore | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | 2022-02-21 08:00 | 2022-02-25 16:00 | 2022-02-21 08:00 | 2022-02-25 16:00 | 10 | 5 | 0 |  |  | Sub - Jack and Bore Pipe Crew
DRGJB10 | Completed | 3462-FDOT-Owner-12.4.IP1.4 | Construction: Initial Phase 1: Jack and Bore | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | 2022-02-14 08:00 | 2022-02-18 16:00 | 2022-02-14 08:00 | 2022-02-18 16:00 | 10 | 5 | 0 |  |  | Sub - Jack and Bore Pipe Crew
EGC470 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | 2022-01-12 08:00 | 2022-01-15 08:00 | 2022-01-12 08:00 | 2022-01-15 08:00 | 10 | 3 | 0 |  |  | Light Cut/Fill Earthwork Crew
EGC480 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | 2022-04-25 08:00 | 2022-08-15 16:00 | 2022-04-25 08:00 | 2022-08-15 16:00 | 12 | 79 | 0 |  |  | Light Cut/Fill Earthwork Crew
EGC490 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | 2021-12-12 08:00 | 2022-05-14 16:00 | 2021-12-12 08:00 | 2022-05-14 16:00 | 12 | 103 | 0 |  |  | Light Cut/Fill Earthwork Crew
EGC580 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.6 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | 2023-01-18 08:00 | 2023-01-23 16:00 |  |  | 4 | 0 | 4 | 23 |  | Light Cut/Fill Earthwork Crew
EGC570 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | 2022-12-22 08:00 | 2023-01-17 16:00 |  |  | 12 | 0 | 12 | 23 |  | Light Cut/Fill Earthwork Crew
EGC560 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | 2022-12-06 08:00 | 2022-12-21 16:00 |  |  | 12 | 0 | 12 | 23 |  | Light Cut/Fill Earthwork Crew
EGC540 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | 2022-11-15 08:00 | 2022-12-05 16:00 |  |  | 12 | 0 | 12 | 13 |  | Light Cut/Fill Earthwork Crew
EGC520 | In Progress | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 2022-08-08 08:00 | 2022-11-14 16:00 | 2022-08-08 08:00 |  | 12 | 67 | 1 | 12 |  | Light Cut/Fill Earthwork Crew
EGC510 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | 2022-11-14 08:00 | 2022-12-02 16:00 |  |  | 12 | 0 | 12 | 4 |  | Light Cut/Fill Earthwork Crew
PAV240 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.6 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 2022-12-01 08:00 | 2022-12-06 16:00 |  |  | 4 | 0 | 4 | 64 |  | Sub - Asphalt Paving Crew
PAV230 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 2022-10-04 08:00 | 2022-10-07 16:00 | 2022-10-04 08:00 | 2022-10-07 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
PAV220 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Asphalt Paving: Temporary Diversion: SB: MLK Ramp A - IPh1 | 2022-09-01 08:00 | 2022-09-08 16:00 | 2022-09-01 08:00 | 2022-09-08 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
PAV100 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Asphalt Paving: Temporary Diversion: NB: MLK Ramp B - IPh1 | 2022-05-13 08:00 | 2022-05-14 16:00 | 2022-05-13 08:00 | 2022-05-14 16:00 | 3 | 1 | 0 |  |  | Sub - Asphalt Paving Crew
PAV110 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Asphalt Paving: Temporary Diversion: NB: MLK Ramp C - IPh1 | 2022-06-20 08:00 | 2022-06-30 16:00 | 2022-06-20 08:00 | 2022-06-30 16:00 | 4 | 9 | 0 |  |  | Sub - Asphalt Paving Crew
PAV200 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Asphalt Paving: Temporary Diversion: SB: MLK Ramp D - IPh1 | 2022-10-04 08:00 | 2022-10-07 16:00 | 2022-10-04 08:00 | 2022-10-07 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
PAV190 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 2022-10-10 08:00 | 2022-10-13 16:00 | 2022-10-10 08:00 | 2022-10-13 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
PAV120 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 2022-06-21 08:00 | 2022-07-05 16:00 | 2022-06-21 08:00 | 2022-07-05 16:00 | 4 | 10 | 0 |  |  | Sub - Asphalt Paving Crew
PAV150 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 2022-05-24 08:00 | 2022-05-27 16:00 | 2022-05-24 08:00 | 2022-05-27 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
PAV140 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 2022-04-12 08:00 | 2022-04-15 16:00 | 2022-04-12 08:00 | 2022-04-15 16:00 | 4 | 4 | 0 |  |  | Sub - Asphalt Paving Crew
LOE-P2 | Not Started | 3462-FDOT-Owner-12.1 | MOT Summary | Phase 2 Duration | 2024-04-18 08:00 | 2025-02-11 16:00 |  |  | 300 | 0 | 300 | -6
LOE-IP1 | In Progress | 3462-FDOT-Owner-12.1 | MOT Summary | Initial Phase 1 Duration | 2021-10-18 08:00 | 2023-02-03 16:00 | 2021-10-18 08:00 |  | 402 | 391 | 83 | 87
LOE-P1S1S1 | In Progress | 3462-FDOT-Owner-12.1 | MOT Summary | Phase 1: Stage 1 - Step 1 Duration | 2021-11-08 08:00 | 2022-12-15 16:00 | 2021-11-08 08:00 |  | 147 | 370 | 33 | 874
LOE-P1S1S2 | Not Started | 3462-FDOT-Owner-12.1 | MOT Summary | Phase 1: Stage 1 - Step 2 Duration | 2022-11-16 08:00 | 2023-01-10 16:00 |  |  | 56 | 0 | 56 | 111
LOE-P1S1 | In Progress | 3462-FDOT-Owner-12.1 | MOT Summary | Phase 1: Stage 1 Duration | 2021-12-08 08:00 | 2024-04-11 16:00 | 2021-12-08 08:00 |  | 805 | 340 | 516 | -6
LOE-P1S2 | Not Started | 3462-FDOT-Owner-12.1 | MOT Summary | Phase 1: Stage 2 Duration | 2023-05-08 08:00 | 2024-04-17 16:00 |  |  | 346 | 0 | 346 | -6
LOE-P3 | Not Started | 3462-FDOT-Owner-12.1 | MOT Summary | Phase 3 Duration | 2025-02-12 08:00 | 2025-05-13 16:00 |  |  | 91 | 0 | 91 | -6
FND20 | Completed | 3462-FDOT-Owner-12.2.1.1.1 | Preconstruction: Procurement: Bridges: H-Pile Foundations | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | 2021-10-13 08:00 | 2021-10-13 16:00 | 2021-10-13 08:00 | 2021-10-13 16:00 | 25 | 1 | 0
SUB20 | Completed | 3462-FDOT-Owner-12.2.1.1.3 | Preconstruction: Procurement: Bridges: Substructure | Review & Approve Shop Drawings / Submittals: Substructure (Duration = 25 Calendar Days) | 2022-02-02 08:00 | 2022-02-19 16:00 | 2022-02-02 08:00 | 2022-02-19 16:00 | 25 | 18 | 0
SUB10 | Completed | 3462-FDOT-Owner-12.2.1.1.3 | Preconstruction: Procurement: Bridges: Substructure | Prepare Shop Drawings / Submittals: Substructure | 2022-02-18 08:00 | 2022-02-19 16:00 | 2022-02-18 08:00 | 2022-02-19 16:00 | 25 | 1 | 0
SPS20 | Completed | 3462-FDOT-Owner-12.2.1.1.4 | Preconstruction: Procurement: Bridges: Superstructure | Review & Approve Shop Drawings / Submittals: Superstructure (Duration = 25 Calendar Days) | 2022-02-22 08:00 | 2022-03-18 16:00 | 2022-02-22 08:00 | 2022-03-18 16:00 | 25 | 25 | 0
RET20 | Completed | 3462-FDOT-Owner-12.2.1.2.1 | Preconstruction: Procurement: Walls: Anchored Retaining Walls | Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) (Deleted) | 2022-02-20 08:00 | 2022-02-20 08:00 | 2022-02-20 08:00 | 2022-02-20 08:00 | 0 | 0 | 0
RDW20 | Completed | 3462-FDOT-Owner-12.2.1.2.3 | Preconstruction: Procurement: Walls: Temp Critical Walls | Review & Approve Shop Drawings / Submittals: Temp Critical Walls (Duration = 25 Calendar Days) | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 20 | 18 | 0
DRG20 | Completed | 3462-FDOT-Owner-12.2.1.3 | Preconstruction: Procurement: Drainage Pipe & Structures | Review & Approve Shop Drawings / Submittals: Drainage Pipe & Structures (Duration = 25 Calendar Days) | 2021-09-10 08:00 | 2022-01-15 16:00 | 2021-09-10 08:00 | 2022-01-15 16:00 | 25 | 128 | 0
DS20 | Completed | 3462-FDOT-Owner-12.2.1.1.2 | Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Review & Approve Shop Drawings / Submittals: Structural 48" Drilled Shafts (Duration = 25 Calendar Days) (Criteria) | 2021-09-25 08:00 | 2022-01-15 16:00 | 2021-09-25 08:00 | 2022-01-15 16:00 | 25 | 113 | 0
LTG20 | Completed | 3462-FDOT-Owner-12.2.1.4.1 | Preconstruction: Procurement: Electrical / ITS: Lighting | Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | 2021-11-16 08:00 | 2022-03-18 16:00 | 2021-11-16 08:00 | 2022-03-18 16:00 | 25 | 123 | 0
SGN20 | Completed | 3462-FDOT-Owner-12.2.1.4.2.1 | Preconstruction: Procurement: Electrical / ITS: Signage | Review & Approve Shop Drawings / Submittals: Signage (Duration = 25 Calendar Days) | 2022-06-21 08:00 | 2022-07-04 16:00 | 2022-06-21 08:00 | 2022-07-04 16:00 | 25 | 14 | 0
ITS20 | Completed | 3462-FDOT-Owner-12.2.1.4.3 | Preconstruction: Procurement: Electrical / ITS: ITS | Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | 2021-11-22 08:00 | 2022-02-18 16:00 | 2021-11-22 08:00 | 2022-02-18 16:00 | 25 | 89 | 0
MS-CE10 | Completed | 3462-FDOT-Owner-12.0 | Project Milestones | Start-Up | 2021-08-12 08:00 | 2021-10-25 16:00 | 2021-08-12 08:00 | 2021-10-25 16:00 | 60 | 75 | 0
ENV20 | Completed | 3462-FDOT-Owner-12.2.1.5 | Preconstruction: Procurement: Environmental | Review & Approve Shop Drawings / Submittals: Environmental Compliance (Duration = 25 Calendar Days) | 2021-08-19 08:00 | 2021-09-12 16:00 | 2021-08-19 08:00 | 2021-09-12 16:00 | 25 | 25 | 0
DRG110 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Drainage: CS-1A to CS-1A OUT (18") - NB: 737 - 738 - IPh1 | 2022-02-17 08:00 | 2022-02-18 16:00 | 2022-02-17 08:00 | 2022-02-18 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG120 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Drainage: S-30 to S-30 OUT - Lower (18") - NB: 738 - 739 - IPh1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 1 | 5 | 0 |  |  | Drainage Crew - Combo
DRG130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-31 to Existing (24") - NB: 739-740 - Ph1-S1 | 2022-06-06 08:00 | 2022-06-09 16:00 | 2022-06-06 08:00 | 2022-06-09 16:00 | 1 | 4 | 0 |  |  | Drainage Crew - Combo
DRG140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: Existing to S-34A to S-34 to Existing (15") - NB: 744-745) - Ph1-S1 | 2022-08-08 08:00 | 2022-08-11 16:00 | 2022-08-08 08:00 | 2022-08-11 16:00 | 2 | 4 | 0 |  |  | Drainage Crew - Combo
DRG160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-13 to S-16 (30") - NB: 726-730 - Ph1-S1 | 2022-06-13 08:00 | 2022-07-11 16:00 | 2022-06-13 08:00 | 2022-07-11 16:00 | 1 | 20 | 0 |  |  | Drainage Crew - Combo
DRG170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-16 to S-17 (18") - NB: 729-730 - Ph1-S1 | 2022-06-23 08:00 | 2022-06-24 16:00 | 2022-06-23 08:00 | 2022-06-24 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-17 to S-18 (18") - NB: 729-730 - Ph1-S1 | 2022-09-15 08:00 | 2022-09-15 16:00 | 2022-09-15 08:00 | 2022-09-15 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-18 to S-15 (18") - NB: 728-730 - Ph1-S1 | 2022-09-15 08:00 | 2022-09-15 16:00 | 2022-09-15 08:00 | 2022-09-15 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-16 to S-22 (30") - NB: 729-734 - Ph1-S1 | 2022-05-03 08:00 | 2022-05-12 16:00 | 2022-05-03 08:00 | 2022-05-12 16:00 | 1 | 8 | 0 |  |  | Drainage Crew - Combo
DRG210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-21 OF to S-22 (29"x45") - NB: 733-734 - Ph1-S1 | 2022-02-28 08:00 | 2022-03-02 16:00 | 2022-02-28 08:00 | 2022-03-02 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
DRG220 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | 2022-03-17 08:00 | 2022-03-18 16:00 | 2022-03-17 08:00 | 2022-03-18 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG230 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-22 to Existing (36") - NB: 733-734 - Ph1-S1 | 2022-07-12 08:00 | 2022-07-13 16:00 | 2022-07-12 08:00 | 2022-07-13 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG250 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-41 to S-42 (30") - NB: 751-752 - Ph1-S1 | 2022-08-09 08:00 | 2022-08-11 16:00 | 2022-08-09 08:00 | 2022-08-11 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
DRG260 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-42 to S-45 (24") - NB: 751-754 - Ph1-S1 | 2022-03-09 08:00 | 2022-03-10 16:00 | 2022-03-09 08:00 | 2022-03-10 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG270 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-45 to S-49 (18") - NB: 753-754 - Ph1-S1 | 2022-03-08 08:00 | 2022-03-09 16:00 | 2022-03-08 08:00 | 2022-03-09 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG280 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-45 to S-46 (24") - NB: 753-754 - Ph1-S1 | 2022-02-17 08:00 | 2022-05-14 16:00 | 2022-02-17 08:00 | 2022-05-14 16:00 | 7 | 62 | 0 |  |  | Drainage Crew - Combo
DRG290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | 2022-07-04 08:00 | 2022-07-06 16:00 | 2022-07-04 08:00 | 2022-07-06 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | 2022-07-13 08:00 | 2022-07-15 16:00 | 2022-07-13 08:00 | 2022-07-15 16:00 | 3 | 3 | 0 |  |  | Drainage Crew - Combo
DRG310 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG320 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-60 to S-60A (42") - NB: 764-766 - Ph1-S1 | 2022-08-08 08:00 | 2022-08-10 16:00 | 2022-08-08 08:00 | 2022-08-10 16:00 | 3 | 3 | 0 |  |  | Drainage Crew - Combo
DRG350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-60A to S-78 (42") - NB: 766-768 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 36 |  | Drainage Crew - Combo
DRG360 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-65 to S-66 (18") - NB: 765-766 - Ph1-S1 | 2022-09-16 08:00 | 2022-09-16 16:00 | 2022-09-16 08:00 | 2022-09-16 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-66 to S-73 (18") - NB: 766-767 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 39 |  | Drainage Crew - Combo
DRG390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-78 to Existing (48") - NB: 767-768 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Drainage Crew - Combo
DRG400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-78 to S-80 (18") - NB: 767-768 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Drainage Crew - Combo
DRG410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-80 to S-79 (18") - NB: 767-768 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Drainage Crew - Combo
DRG420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-79 to S-73 (18") - NB: 767-768 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Drainage Crew - Combo
DRG430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-83 OF to S-83 to Existing (18") - NB: 768-769 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 54 |  | Drainage Crew - Combo
DRG460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-115 to S-110 (18") - NB: 781-782 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 74 |  | Drainage Crew - Combo
DRG470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-115 to S-117 (18") - NB: 781-782 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 74 |  | Drainage Crew - Combo
DRG480 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-119 to Existing (15") - NB: 783-784 - Ph1-S1 | 2022-08-10 08:00 | 2022-08-10 16:00 | 2022-08-10 08:00 | 2022-08-10 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG500 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 to S-122 (18") - NB: 795-796 - Ph1-S1 | 2022-07-13 08:00 | 2022-07-15 16:00 | 2022-07-13 08:00 | 2022-07-15 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
DRG510 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-135 OF to S-135 (14"x23") - NB: 798-799 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-13 16:00 | 2022-07-11 08:00 | 2022-07-13 16:00 | 1 | 3 | 0 |  |  | Drainage Crew - Combo
DRG530 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-144 to S-145 (30") - NB: 801 - 802 - IPh1 | 2022-01-24 08:00 | 2022-01-24 16:00 | 2022-01-24 08:00 | 2022-01-24 16:00 | 2 | 1 | 0 |  |  | Drainage Crew - Combo
DRG540 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-145 to S-150 (30") - NB: 801 - 805 - IPh1 | 2022-01-18 08:00 | 2022-01-18 16:00 | 2022-01-18 08:00 | 2022-01-18 16:00 | 6 | 1 | 0 |  |  | Drainage Crew - Combo
DRG550 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-150 to S-151 (30") - NB: 804 - 805 - IPh1 | 2022-01-26 08:00 | 2022-01-26 16:00 | 2022-01-26 08:00 | 2022-01-26 16:00 | 2 | 1 | 0 |  |  | Drainage Crew - Combo
DRG560 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-151 OF to S-151 (30") - NB: 804 - 805 - IPh1 | 2022-01-26 08:00 | 2022-01-26 16:00 | 2022-01-26 08:00 | 2022-01-26 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG570 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: CS-1 to S-151 - Lower (18") - NB: 804 - 805 - IPh1 | 2022-08-08 08:00 | 2022-08-12 16:00 | 2022-08-08 08:00 | 2022-08-12 16:00 | 2 | 5 | 0 |  |  | Drainage Crew - Combo
DRG580 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | 2022-07-25 08:00 | 2022-07-27 16:00 | 2022-07-25 08:00 | 2022-07-27 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
DRG590 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | 2022-07-13 08:00 | 2022-07-14 16:00 | 2022-07-13 08:00 | 2022-07-14 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG600 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-159 OF to S-159 (14"x23") - NB: 806-807 - Ph1-S1 | 2022-09-21 08:00 | 2022-09-22 16:00 | 2022-09-21 08:00 | 2022-09-22 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG610 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | 2022-09-23 08:00 | 2022-09-26 16:00 | 2022-09-23 08:00 | 2022-09-26 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 to S-168 (18") - NB: 807-808 - Ph1-S1 | 2022-09-27 08:00 | 2022-09-27 16:00 | 2022-09-27 08:00 | 2022-09-27 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-168 to S-169 (18") - NB: 807-808 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 16 |  | Drainage Crew - Combo
DRG640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-169 to S-173 (18") - NB: 807-809 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 16 |  | Drainage Crew - Combo
DRG650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 19 |  | Drainage Crew - Combo
DRG660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-177 to S-175 to Existing (15") - NB: 810-812 - Ph1-S1 | 2022-11-18 08:00 | 2022-11-21 16:00 |  |  | 2 | 0 | 2 | 19 |  | Drainage Crew - Combo
DRG680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 19 |  | Drainage Crew - Combo
DRG690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | 2022-11-18 08:00 | 2022-11-21 16:00 |  |  | 2 | 0 | 2 | 19 |  | Drainage Crew - Combo
DRG700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-203 (18") - NB: 819-821 - Ph1-S1 | 2022-11-22 08:00 | 2022-11-29 16:00 |  |  | 3 | 0 | 3 | 19 |  | Drainage Crew - Combo
DRG710 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-220 to S-221 (18") - NB: 823-824 - Ph1-S1 | 2022-08-11 08:00 | 2022-08-11 16:00 | 2022-08-11 08:00 | 2022-08-11 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG720 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | 2022-08-12 08:00 | 2022-08-12 16:00 | 2022-08-12 08:00 | 2022-08-12 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG730 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | 2022-08-12 08:00 | 2022-08-15 16:00 | 2022-08-12 08:00 | 2022-08-15 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG740 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | 2022-11-02 08:00 | 2022-11-14 16:00 | 2022-11-02 08:00 |  | 1 | 7 | 1 | 26 |  | Drainage Crew - Combo
DRG750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: Mitered End to Mitered End (24") - NB: 826-827 - Ph1-S1 | 2022-11-15 08:00 | 2022-11-15 16:00 |  |  | 1 | 0 | 1 | 26 |  | Drainage Crew - Combo
DRG760 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-228 to S-232 (24") - NB: 826-828 - Ph1-S1 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG770 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-232 to S-231 (36") - NB: 827-828 - Ph1-S1 | 2022-11-02 08:00 | 2022-11-14 16:00 | 2022-11-02 08:00 |  | 1 | 7 | 1 | 27 |  | Drainage Crew - Combo
DRG780 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-231 to Existing (36") - NB: 827-828 - Ph1-S1 | 2022-11-02 08:00 | 2022-11-14 16:00 | 2022-11-02 08:00 |  | 1 | 7 | 1 | 27 |  | Drainage Crew - Combo
DRG790 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-234 to S-235 (18") - NB: 828-829 - Ph1-S1 | 2022-11-02 08:00 | 2022-11-03 16:00 | 2022-11-02 08:00 | 2022-11-03 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG800 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | 2022-11-02 08:00 | 2022-11-03 16:00 | 2022-11-02 08:00 | 2022-11-03 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG810 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | 2022-11-02 08:00 | 2022-11-04 16:00 | 2022-11-02 08:00 | 2022-11-04 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
DRG820 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-301 OF to S-301 (18") - NB: 834-835 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 23 |  | Drainage Crew - Combo
DRG1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | 2023-05-03 08:00 | 2023-05-05 16:00 |  |  | 3 | 0 | 3 | 30 |  | Drainage Crew - Combo
DRGS10 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.6 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | 2023-01-24 08:00 | 2023-01-25 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRGS20 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.6 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | 2023-01-26 08:00 | 2023-01-27 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG1030 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | 2023-04-11 08:00 | 2023-04-14 16:00 |  |  | 4 | 0 | 4 | 30 |  | Drainage Crew - Combo
DRG1040 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | 2023-04-17 08:00 | 2023-04-18 16:00 |  |  | 2 | 0 | 2 | 30 |  | Drainage Crew - Combo
DRG1050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | 2023-04-19 08:00 | 2023-04-21 16:00 |  |  | 3 | 0 | 3 | 30 |  | Drainage Crew - Combo
DRG1060 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | 2023-04-24 08:00 | 2023-04-26 16:00 |  |  | 3 | 0 | 3 | 30 |  | Drainage Crew - Combo
DRG1080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | 2023-03-22 08:00 | 2023-03-23 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG1090 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | 2023-03-24 08:00 | 2023-03-28 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG1100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | 2023-02-16 08:00 | 2023-02-22 16:00 |  |  | 5 | 0 | 5 | 25 |  | Drainage Crew - Combo
DRG1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | 2023-02-27 08:00 | 2023-02-28 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG1120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | 2023-03-01 08:00 | 2023-03-03 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG1130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | 2023-03-06 08:00 | 2023-03-07 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | 2023-03-08 08:00 | 2023-03-10 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG1150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | 2023-03-29 08:00 | 2023-03-30 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG1160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | 2023-03-31 08:00 | 2023-04-03 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG1170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | 2023-04-04 08:00 | 2023-04-06 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRGS30 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | 2023-01-09 08:00 | 2023-01-09 16:00 |  |  | 1 | 0 | 1 | 29 |  | Drainage Crew - Combo
DRGS40 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | 2023-01-10 08:00 | 2023-01-10 16:00 |  |  | 1 | 0 | 1 | 29 |  | Drainage Crew - Combo
DRGS50 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | 2023-01-11 08:00 | 2023-01-11 16:00 |  |  | 1 | 0 | 1 | 29 |  | Drainage Crew - Combo
DRGS1180 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | 2023-01-12 08:00 | 2023-01-12 16:00 |  |  | 1 | 0 | 1 | 29 |  | Drainage Crew - Combo
DRG1190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | 2023-03-13 08:00 | 2023-03-14 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRGS60 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | 2022-12-09 08:00 | 2022-12-15 16:00 |  |  | 5 | 0 | 5 | 32 |  | Drainage Crew - Combo
DRGS70 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 2022-12-19 08:00 | 2022-12-19 16:00 |  |  | 1 | 0 | 1 | 32 |  | Drainage Crew - Combo
DRGS80 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 2022-12-20 08:00 | 2022-12-20 16:00 |  |  | 1 | 0 | 1 | 32 |  | Drainage Crew - Combo
DRGS90 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | 2022-12-21 08:00 | 2022-12-21 16:00 |  |  | 1 | 0 | 1 | 32 |  | Drainage Crew - Combo
DRGS100 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | 2022-12-22 08:00 | 2022-12-22 16:00 |  |  | 1 | 0 | 1 | 32 |  | Drainage Crew - Combo
DRGS110 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | 2022-10-11 08:00 | 2022-10-12 16:00 | 2022-10-11 08:00 | 2022-10-12 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRGS120 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | 2022-10-13 08:00 | 2022-10-13 16:00 | 2022-10-13 08:00 | 2022-10-13 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRGS130 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | 2022-12-09 08:00 | 2022-12-09 16:00 |  |  | 1 | 0 | 1 | 40 |  | Drainage Crew - Combo
DRG1210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | 2023-01-30 08:00 | 2023-01-31 16:00 |  |  | 2 | 0 | 2 | 26 |  | Drainage Crew - Combo
DRG1220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | 2023-02-01 08:00 | 2023-02-02 16:00 |  |  | 2 | 0 | 2 | 26 |  | Drainage Crew - Combo
DRGS1230 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | 2022-12-12 08:00 | 2022-12-12 16:00 |  |  | 1 | 0 | 1 | 40 |  | Drainage Crew - Combo
DRG1240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | 2023-02-03 08:00 | 2023-02-06 16:00 |  |  | 2 | 0 | 2 | 26 |  | Drainage Crew - Combo
DRG1250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | 2023-02-07 08:00 | 2023-02-08 16:00 |  |  | 2 | 0 | 2 | 26 |  | Drainage Crew - Combo
DRG1280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | 2023-02-13 08:00 | 2023-02-14 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | 2023-02-15 08:00 | 2023-02-16 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | 2023-02-17 08:00 | 2023-02-21 16:00 |  |  | 3 | 0 | 3 | 6 |  | Drainage Crew - Combo
DRG1310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | 2023-02-22 08:00 | 2023-02-23 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | 2023-02-24 08:00 | 2023-02-28 16:00 |  |  | 3 | 0 | 3 | 6 |  | Drainage Crew - Combo
DRG1330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Mitered End to Mitered End (30") - SB: 799-800 - Ph1-S1 | 2023-03-01 08:00 | 2023-03-03 16:00 |  |  | 3 | 0 | 3 | 6 |  | Drainage Crew - Combo
DRG1350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | 2023-01-09 08:00 | 2023-01-10 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | 2023-01-11 08:00 | 2023-01-12 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | 2023-01-13 08:00 | 2023-01-17 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | 2023-01-18 08:00 | 2023-01-19 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | 2023-01-20 08:00 | 2023-01-23 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | 2023-01-24 08:00 | 2023-01-25 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | 2023-01-26 08:00 | 2023-01-27 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | 2023-01-30 08:00 | 2023-01-31 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | 2023-02-01 08:00 | 2023-02-02 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG1440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | 2023-02-03 08:00 | 2023-02-06 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRGS140 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | 2022-11-18 08:00 | 2022-11-21 16:00 |  |  | 2 | 0 | 2 | 20 |  | Drainage Crew - Combo
DRGS150 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-142 OF to S-142 (30") - SB:801 - 802 - Swale 1A - IPh 1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 25 |  | Drainage Crew - Combo
DRGS160 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-142 to S-143 (30") - SB:801 - 802 - Swale 1A - IPh 1 | 2022-08-22 08:00 | 2022-08-23 16:00 | 2022-08-22 08:00 | 2022-08-23 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRGS170 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | 2022-03-28 08:00 | 2022-04-15 08:00 | 2022-03-28 08:00 | 2022-04-15 08:00 | 7 | 14 | 0 |  |  | Drainage Crew - Combo
DRGS180 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 2022-08-23 08:00 | 2022-08-23 16:00 | 2022-08-23 08:00 | 2022-08-23 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRGS190 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 2022-11-18 08:00 | 2022-11-18 16:00 |  |  | 1 | 0 | 1 | 21 |  | Drainage Crew - Combo
DRGS200 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | 2022-08-23 08:00 | 2022-08-23 16:00 | 2022-08-23 08:00 | 2022-08-23 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRGS210 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | 2022-11-18 08:00 | 2022-11-18 16:00 |  |  | 1 | 0 | 1 | 21 |  | Drainage Crew - Combo
DRGS220 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | 2022-03-24 08:00 | 2022-03-25 16:00 | 2022-03-24 08:00 | 2022-03-25 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRGS230 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | 2022-02-07 08:00 | 2022-02-07 16:00 | 2022-02-07 08:00 | 2022-02-07 16:00 | 2 | 1 | 0 |  |  | Drainage Crew - Combo
DRGS240 | Completed | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | 2022-07-13 08:00 | 2022-07-14 16:00 | 2022-07-13 08:00 | 2022-07-14 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG1460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | 2022-12-19 08:00 | 2022-12-19 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | 2022-12-20 08:00 | 2022-12-21 16:00 |  |  | 2 | 0 | 2 | 4 |  | Drainage Crew - Combo
DRG1480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | 2022-12-22 08:00 | 2022-12-23 16:00 |  |  | 2 | 0 | 2 | 4 |  | Drainage Crew - Combo
DRSG245 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 13 |  | Drainage Crew - Combo
DRG1500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | 2023-01-03 08:00 | 2023-01-03 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | 2023-01-04 08:00 | 2023-01-04 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | 2023-01-05 08:00 | 2023-01-05 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | 2023-01-06 08:00 | 2023-01-09 16:00 |  |  | 2 | 0 | 2 | 4 |  | Drainage Crew - Combo
DRG1540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | 2023-01-10 08:00 | 2023-01-10 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | 2023-01-11 08:00 | 2023-01-11 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | 2023-01-12 08:00 | 2023-01-13 16:00 |  |  | 2 | 0 | 2 | 4 |  | Drainage Crew - Combo
DRG1570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | 2023-01-17 08:00 | 2023-01-17 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRGS295 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | 2022-07-11 08:00 | 2022-07-13 16:00 | 2022-07-11 08:00 | 2022-07-13 16:00 | 2 | 3 | 0 |  |  | Drainage Crew - Combo
DRGS250 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | 2022-11-15 08:00 | 2022-11-16 16:00 |  |  | 2 | 0 | 2 | 13 |  | Drainage Crew - Combo
DRGS260 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRGS270 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 12 |  | Drainage Crew - Combo
DRGS280 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 12 |  | Drainage Crew - Combo
DRG1590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | 2023-01-18 08:00 | 2023-01-18 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRG1600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-305 to Existing (18") - SB: 834-835 - Ph1-S1 | 2023-01-19 08:00 | 2023-01-19 16:00 |  |  | 1 | 0 | 1 | 4 |  | Drainage Crew - Combo
DRGS290 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | 2022-07-13 08:00 | 2022-07-14 16:00 | 2022-07-13 08:00 | 2022-07-14 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRGS300 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | 2022-02-04 08:00 | 2022-05-14 16:00 | 2022-02-04 08:00 | 2022-05-14 16:00 | 2 | 71 | 0 |  |  | Drainage Crew - Combo
DRG2010 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-12 to S-14 (18") - NB & SB Median: 726-728 - Ph2 | 2024-05-16 08:00 | 2024-05-17 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2020 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-14 to S-19 (18") - NB & SB Median: 728-730 - Ph2 | 2024-05-20 08:00 | 2024-05-21 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2030 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-19 to Existing (15") - NB & SB Median: 729-730 - Ph2 | 2024-05-22 08:00 | 2024-05-22 16:00 |  |  | 1 | 0 | 1 | -4 | 1 | Drainage Crew - Combo
DRG2040 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-19 to S-20 (18") - NB & SB Median: 729-733 - Ph2 | 2024-05-23 08:00 | 2024-05-24 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2050 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-20 to S-23 (24") - NB & SB Median: 732-734 - Ph2 | 2024-05-28 08:00 | 2024-05-29 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2060 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-23 to Existing (36") - NB & SB Median: 733-734 - Ph2 | 2024-05-30 08:00 | 2024-05-30 16:00 |  |  | 1 | 0 | 1 | -4 | 1 | Drainage Crew - Combo
DRG2070 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-23 to S-25 (24") - NB & SB Median: 733-734 - Ph2 | 2024-05-31 08:00 | 2024-06-03 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2080 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-25 to S-26 (24") - NB & SB Median: 734-735 - Ph2 | 2024-06-04 08:00 | 2024-06-05 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2090 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-26 to S-27 (18") - NB & SB Median: 734-735 - Ph2 | 2024-06-06 08:00 | 2024-06-07 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Drainage Crew - Combo
DRG2110 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (18") - NB & SB Median: 739-740 - Ph2 | 2024-06-11 08:00 | 2024-06-11 16:00 |  |  | 1 | 0 | 1 | -4 | 1 | Drainage Crew - Combo
DRG2120 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-35 to Existing (15") - NB & SB Median: 744-745 - Ph2 | 2024-06-12 08:00 | 2024-06-12 16:00 |  |  | 1 | 0 | 1 | -4 | 1 | Drainage Crew - Combo
DRG2130 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-35 to S-38 (15") - NB & SB Median: 744-745 - Ph2 | 2024-06-13 08:00 | 2024-06-14 16:00 |  |  | 2 | 0 | 2 | -1 | 21 | Drainage Crew - Combo
DRG2150 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Drainage: S-55 to Existing (15") - NB & SB Median: 755-756 - Ph2 | 2024-06-18 08:00 | 2024-06-19 16:00 |  |  | 2 | 0 | 2 | 10 |  | Drainage Crew - Combo
DRG2170 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-70 to S-72 (18") - NB & SB Median: 766-767 - Ph2 | 2024-06-24 08:00 | 2024-06-25 16:00 |  |  | 2 | 0 | 2 | 11 |  | Drainage Crew - Combo
DRG2210 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-111 to S-116 (18") - NB & SB Median: 781-782 - Ph2 | 2024-07-08 08:00 | 2024-07-08 16:00 |  |  | 1 | 0 | 1 | 18 |  | Drainage Crew - Combo
DRG2220 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-120 to Existing (15") - NB & SB Median: 784-785 - Ph2 | 2024-07-09 08:00 | 2024-07-09 16:00 |  |  | 1 | 0 | 1 | 18 |  | Drainage Crew - Combo
DRG2240 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-127 to S-130 (18") - NB & SB Median: 795-797 - Ph2 | 2024-07-12 08:00 | 2024-07-15 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
DRG2250 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-130 to S-131 (18") - NB & SB Median: 796-798 - Ph2 | 2024-07-16 08:00 | 2024-07-17 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
DRG2260 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-131 to S-134 (18") - NB & SB Median: 797-799 - Ph2 | 2024-07-18 08:00 | 2024-07-19 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
DRG2270 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-134 to S-137 (18") - NB & SB Median: 798-800 - Ph2 | 2024-07-22 08:00 | 2024-07-23 16:00 |  |  | 2 | 0 | 2 | 18 |  | Drainage Crew - Combo
DRG2280 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-137 to S-138 (18") - NB & SB Median: 799-800 - Ph2 | 2024-07-24 08:00 | 2024-07-24 16:00 |  |  | 1 | 0 | 1 | 18 |  | Drainage Crew - Combo
DRG2300 | Completed | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-141 to S-140 (18") - NB & SB Median: 800-801 - Ph2 | 2022-05-23 08:00 | 2022-05-24 16:00 | 2022-05-23 08:00 | 2022-05-24 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG2310 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-140 to S-147 (18") - NB & SB Median: 801-803 - Ph2 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 419 |  | Drainage Crew - Combo
DRG2320 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-147 to S-148 (18") - NB & SB Median: 802-804 - Ph2 | 2022-11-16 08:00 | 2022-11-21 16:00 |  |  | 4 | 0 | 4 | 419 |  | Drainage Crew - Combo
DRG2330 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-148 to S-152 (18") - NB & SB Median: 803-805 - Ph2 | 2022-11-22 08:00 | 2022-11-28 16:00 |  |  | 2 | 0 | 2 | 419 |  | Drainage Crew - Combo
DRG2340 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-152 to S-158 (24") - NB & SB Median: 804-806 - Ph2 | 2022-11-29 08:00 | 2022-12-01 16:00 |  |  | 3 | 0 | 3 | 419 |  | Drainage Crew - Combo
DRG2350 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: Existing to S-160 to S-163 (18") - NB & SB Median: 804-806 - Ph2 | 2022-12-02 08:00 | 2022-12-05 16:00 |  |  | 2 | 0 | 2 | 419 |  | Drainage Crew - Combo
DRG2370 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-212 to S-219 (18") - NB & SB Median: 822-823 - Ph2 | 2024-08-09 08:00 | 2024-08-12 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2380 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-219 to S-222 (18") - NB & SB Median: 823-824 - Ph2 | 2024-08-13 08:00 | 2024-08-14 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2390 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-222 to S-223 (18") - NB & SB Median: 824-825 - Ph2 | 2024-08-15 08:00 | 2024-08-16 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2400 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-223 to S-225 (18") - NB & SB Median: 824-825 - Ph2 | 2024-08-19 08:00 | 2024-08-20 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2410 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-230 to Existing (36") - NB & SB Median: 827-828 - Ph2 | 2024-08-21 08:00 | 2024-08-21 16:00 |  |  | 1 | 0 | 1 | 8 |  | Drainage Crew - Combo
DRG2420 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-227 to S-230 (18") - NB & SB Median: 826-828 - Ph2 | 2024-08-22 08:00 | 2024-08-23 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2430 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-230 to S-233 (18") - NB & SB Median: 827-828 - Ph2 | 2024-08-26 08:00 | 2024-08-27 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2440 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-233 to S-236 (18") - NB & SB Median: 828-829 - Ph2 | 2024-08-28 08:00 | 2024-08-29 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2450 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-236 to S-238 (18") - NB & SB Median: 828-830 - Ph2 | 2024-09-03 08:00 | 2024-09-04 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2460 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-238 to S-241 (18") - NB & SB Median: 829-831 - Ph2 | 2024-09-05 08:00 | 2024-09-06 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2470 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-241 to S-243 (18") - NB & SB Median: 830-832 - Ph2 | 2024-09-09 08:00 | 2024-09-10 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2480 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-243 to S-244 (18") - NB & SB Median: 831-833 - Ph2 | 2024-09-11 08:00 | 2024-09-12 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
DRG2490 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: Existing to S-304 to S-306 (18") - NB & SB Median: 835-838 - Ph2 | 2024-09-13 08:00 | 2024-09-16 16:00 |  |  | 2 | 0 | 2 | 8 |  | Drainage Crew - Combo
PILE120 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.1 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 2022-03-07 08:00 | 2022-03-28 16:00 | 2022-03-07 08:00 | 2022-03-28 16:00 | 3 | 16 | 0 |  |  | Soldier Pile Crew
TCW280 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.2 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 2022-03-14 08:00 | 2022-04-15 16:00 | 2022-03-14 08:00 | 2022-04-15 16:00 | 9 | 25 | 0 |  |  | Wall Crews
PILE350 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 2022-12-06 08:00 | 2022-12-12 16:00 |  |  | 5 | 0 | 5 | 29 |  | Soldier Pile Crew
TCW420 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 2023-01-06 08:00 | 2023-01-18 16:00 |  |  | 8 | 0 | 8 | 23 |  | Wall Crews
PILE140 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.1 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 2022-04-11 08:00 | 2022-04-16 16:00 | 2022-04-11 08:00 | 2022-04-16 16:00 | 3 | 5 | 0 |  |  | Soldier Pile Crew
TCW290 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.2 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 2022-04-11 08:00 | 2022-05-14 16:00 | 2022-04-11 08:00 | 2022-05-14 16:00 | 10 | 25 | 0 |  |  | Wall Crews
PILE330 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 2022-11-22 08:00 | 2022-12-05 16:00 |  |  | 7 | 0 | 7 | 25 |  | Soldier Pile Crew
TCW410 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 2022-12-08 08:00 | 2022-12-21 16:00 |  |  | 10 | 0 | 10 | 23 |  | Wall Crews
PILE170 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.1 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 2022-04-04 08:00 | 2022-05-14 16:00 | 2022-04-04 08:00 | 2022-05-14 16:00 | 5 | 30 | 0 |  |  | Soldier Pile Crew
TCW300 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.2 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 11 | 10 | 0 |  |  | Wall Crews
PILE300 | Completed | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | 2022-06-01 08:00 | 2022-06-03 16:00 | 2022-06-01 08:00 | 2022-06-03 16:00 | 5 | 3 | 0 |  |  | Soldier Pile Crew
TCW390 | Completed | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | 2022-05-25 08:00 | 2022-06-10 16:00 | 2022-05-25 08:00 | 2022-06-10 16:00 | 8 | 12 | 0 |  |  | Wall Crews
PILE310 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 2022-11-14 08:00 | 2022-11-21 16:00 |  |  | 6 | 0 | 6 | 23 |  | Soldier Pile Crew
TCW400 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 2022-11-22 08:00 | 2022-12-07 16:00 |  |  | 9 | 0 | 9 | 23 |  | Wall Crews
PILE280 | Completed | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 2022-09-16 08:00 | 2022-09-23 16:00 | 2022-09-16 08:00 | 2022-09-23 16:00 | 6 | 6 | 0 |  |  | Soldier Pile Crew
TCW380 | Completed | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 2022-09-26 08:00 | 2022-10-14 16:00 | 2022-09-26 08:00 | 2022-10-14 16:00 | 9 | 15 | 0 |  |  | Wall Crews
PILE190 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.1 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 2022-06-01 08:00 | 2022-06-10 16:00 | 2022-06-01 08:00 | 2022-06-10 16:00 | 9 | 8 | 0 |  |  | Soldier Pile Crew
TCW310 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.2 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 2022-07-27 08:00 | 2022-08-25 16:00 | 2022-07-27 08:00 | 2022-08-25 16:00 | 12 | 22 | 0 |  |  | Wall Crews
PILE210 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.1 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 2022-06-01 08:00 | 2022-06-10 16:00 | 2022-06-01 08:00 | 2022-06-10 16:00 | 7 | 8 | 0 |  |  | Soldier Pile Crew
TCW320 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.2 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 2022-07-25 08:00 | 2022-08-15 16:00 | 2022-07-25 08:00 | 2022-08-15 16:00 | 9 | 16 | 0 |  |  | Wall Crews
PILE220 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 42 |  | Soldier Pile Crew
TCW330 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 2022-12-01 08:00 | 2022-12-14 16:00 |  |  | 10 | 0 | 10 | 40 |  | Wall Crews
PILE230 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 2022-11-29 08:00 | 2022-12-07 16:00 |  |  | 7 | 0 | 7 | 57 |  | Soldier Pile Crew
TCW340 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 2022-12-15 08:00 | 2023-01-04 16:00 |  |  | 9 | 0 | 9 | 52 |  | Wall Crews
PILE240 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 2022-12-08 08:00 | 2022-12-14 16:00 |  |  | 5 | 0 | 5 | 62 |  | Soldier Pile Crew
TCW350 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 2023-01-05 08:00 | 2023-01-17 16:00 |  |  | 8 | 0 | 8 | 53 |  | Wall Crews
PILE260 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 2022-12-15 08:00 | 2022-12-21 16:00 |  |  | 5 | 0 | 5 | 68 |  | Soldier Pile Crew
TCW360 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 2023-01-18 08:00 | 2023-01-27 16:00 |  |  | 8 | 0 | 8 | 56 |  | Wall Crews
PILE270 | Completed | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 2022-09-19 08:00 | 2022-09-23 16:00 | 2022-09-19 08:00 | 2022-09-23 16:00 | 7 | 5 | 0 |  |  | Soldier Pile Crew
TCW370 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 2023-01-30 08:00 | 2023-02-09 16:00 |  |  | 9 | 0 | 9 | 56 |  | Wall Crews
PILE360 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 2022-12-13 08:00 | 2022-12-22 16:00 |  |  | 8 | 0 | 8 | 29 |  | Soldier Pile Crew
TCW430 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.2 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 2023-01-19 08:00 | 2023-02-03 16:00 |  |  | 12 | 0 | 12 | 23 |  | Wall Crews
PILE110 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.1 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 2022-02-21 08:00 | 2022-03-24 16:00 | 2022-02-21 08:00 | 2022-03-24 16:00 | 3 | 24 | 0 |  |  | Soldier Pile Crew
TCW270 | Completed | 3462-FDOT-Owner-12.4.IP1.3.1.2 | Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 2022-03-02 08:00 | 2022-03-23 16:00 | 2022-03-02 08:00 | 2022-03-23 16:00 | 13 | 16 | 0 |  |  | Wall Crews
RDW40 | Completed | 3462-FDOT-Owner-12.2.1.2.3 | Preconstruction: Procurement: Walls: Temp Critical Walls | Procurement: Temp Critical Walls: Lagging Wall | 2021-10-27 08:00 | 2022-02-09 16:00 | 2021-10-27 08:00 | 2022-02-09 16:00 | 30 | 65 | 0
DRG120A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-30 to S-30 OUT - Upper (18") - NB: 738-739) - Ph1-S1 | 2022-03-10 08:00 | 2022-03-11 16:00 | 2022-03-10 08:00 | 2022-03-11 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG570A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | 2022-09-28 08:00 | 2022-09-29 16:00 | 2022-09-28 08:00 | 2022-09-29 16:00 | 2 | 2 | 0 |  |  | Drainage Crew - Combo
DRG580A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | 2022-09-29 08:00 | 2022-09-29 16:00 | 2022-09-29 08:00 | 2022-09-29 16:00 | 1 | 1 | 0 |  |  | Drainage Crew - Combo
DRG1260A | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | 2023-02-13 08:00 | 2023-02-14 16:00 |  |  | 2 | 0 | 2 | 26 |  | Drainage Crew - Combo
DRG1230A | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | 2023-02-09 08:00 | 2023-02-10 16:00 |  |  | 2 | 0 | 2 | 26 |  | Drainage Crew - Combo
DRG1180A | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | 2023-03-15 08:00 | 2023-03-16 16:00 |  |  | 2 | 0 | 2 | 23 |  | Drainage Crew - Combo
DRG140A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 OF to S-139 - Upper (18") - SB: 800-802 - Swale 1A - Ph1-S1 | 2022-07-26 08:00 | 2022-09-05 16:00 | 2022-07-26 08:00 | 2022-09-05 16:00 | 2 | 28 | 0 |  |  | Drainage Crew - Combo
DRG210A | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | 2023-02-07 08:00 | 2023-02-08 16:00 |  |  | 2 | 0 | 2 | 6 |  | Drainage Crew - Combo
DRG260A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-227B to S-227A - Upper (18") - SB: 826-827 - Swale 2 - Ph1-S1 | 2022-06-07 08:00 | 2022-07-08 16:00 | 2022-06-07 08:00 | 2022-07-08 16:00 | 2 | 23 | 0 |  |  | Drainage Crew - Combo
DRG1490A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-218 to S-217 - Upper (24") - SB: 823-824 - Ph1-S1 | 2022-07-12 08:00 | 2022-07-13 16:00 | 2022-07-12 08:00 | 2022-07-13 16:00 | 1 | 2 | 0 |  |  | Drainage Crew - Combo
DRG1580A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | 2022-06-27 08:00 | 2022-06-30 16:00 | 2022-06-27 08:00 | 2022-06-30 16:00 | 1 | 4 | 0 |  |  | Drainage Crew - Combo
PM230 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | 2025-04-09 08:00 | 2025-04-22 16:00 |  |  | 10 | 0 | 10 | -4 | 2 | Sub - Striping Crew
PM210 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Final Pavement Markings - Side Roads - Project Limits - Ph3 | 2025-03-12 08:00 | 2025-04-01 16:00 |  |  | 15 | 0 | 15 | -4 | 3 | Sub - Striping Crew
SGN500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Signs - NB: 709+50-735+00 - Ph1-S1 | 2023-04-17 08:00 | 2023-04-19 16:00 |  |  | 3 | 0 | 3 | 46 |  | Sub - Signing Crew
SGN510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Signs - NB: 735+46-746+91 - Ph1-S1 | 2023-04-20 08:00 | 2023-04-26 16:00 |  |  | 5 | 0 | 5 | 46 |  | Sub - Signing Crew
MSE100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 2022-08-08 08:00 | 2022-08-10 16:00 | 2022-08-08 08:00 | 2022-08-10 16:00 | 3 | 3 | 0 |  |  | Sub - MSE Wall Crew
MS100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Form / Reinforce / Pour Moment Slab - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 2022-11-22 08:00 | 2022-12-06 16:00 |  |  | 8 | 0 | 8 | 0 | 9 | Concrete Paving Crews
MSE120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 | Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Leveling Pad - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 2022-04-25 08:00 | 2022-05-04 16:00 | 2022-04-25 08:00 | 2022-05-04 16:00 | 2 | 8 | 0 |  |  | Sub - MSE Wall Crew
MS110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 | Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Form / Reinforce / Pour Moment Slab - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-30 16:00 |  |  | 8 | 0 | 8 | 10 |  | Concrete Paving Crews
MSE150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 | Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Leveling Pad - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 2022-04-25 08:00 | 2022-05-04 16:00 | 2022-04-25 08:00 | 2022-05-04 16:00 | 3 | 8 | 0 |  |  | Sub - MSE Wall Crew
MS120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 | Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Form / Reinforce / Pour Moment Slab - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-29 16:00 |  |  | 9 | 0 | 9 | 11 |  | Concrete Paving Crews
BW180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | 2022-07-18 08:00 | 2022-08-17 16:00 | 2022-07-18 08:00 | 2022-08-17 16:00 | 7 | 23 | 0 |  |  | Concrete Barrier Crew
BW370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | 2022-11-14 08:00 | 2022-11-28 16:00 |  |  | 8 | 0 | 8 | 10 |  | Concrete Barrier Crew
MSE400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Leveling Pad - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 2022-08-12 08:00 | 2022-08-15 16:00 | 2022-08-12 08:00 | 2022-08-15 16:00 | 2 | 2 | 0 |  |  | Sub - MSE Wall Crew
MSE460 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Leveling Pad - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 2022-07-25 08:00 | 2022-07-30 16:00 | 2022-07-25 08:00 | 2022-07-30 16:00 | 2 | 5 | 0 |  |  | Sub - MSE Wall Crew
MS190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 2022-11-28 08:00 | 2022-12-06 16:00 |  |  | 7 | 0 | 7 | 45 |  | Concrete Paving Crews
MS200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 2022-12-07 08:00 | 2022-12-20 16:00 |  |  | 10 | 0 | 10 | 45 |  | Concrete Paving Crews
BW440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 2022-10-13 08:00 | 2022-10-26 16:00 | 2022-10-13 08:00 | 2022-10-26 16:00 | 6 | 10 | 0 |  |  | Concrete Barrier Crew
MSE600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 53 |  | Sub - MSE Wall Crew
MS230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 2023-01-11 08:00 | 2023-01-19 16:00 |  |  | 6 | 0 | 6 | 31 |  | Concrete Paving Crews
BW530 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 170+00.00-177+80.95 - Ph1-S1 | 2022-11-01 08:00 | 2022-11-22 16:00 | 2022-11-01 08:00 |  | 7 | 8 | 7 | 36 |  | Concrete Barrier Crew
MS280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-23 16:00 |  |  | 4 | 0 | 4 | 24 |  | Concrete Paving Crews
MSE860 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 2023-03-22 08:00 | 2023-03-23 16:00 |  |  | 2 | 0 | 2 | 23 |  | Sub - MSE Wall Crew
MS310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 2023-04-12 08:00 | 2023-04-17 16:00 |  |  | 4 | 0 | 4 | 23 |  | Concrete Paving Crews
BW730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | 2023-04-03 08:00 | 2023-04-07 16:00 |  |  | 5 | 0 | 5 | 8 |  | Concrete Barrier Crew
MSE950 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Leveling Pad - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 2022-10-24 08:00 | 2022-10-25 16:00 | 2022-10-24 08:00 | 2022-10-25 16:00 | 2 | 2 | 0 |  |  | Sub - MSE Wall Crew
BW800 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | 2023-05-02 08:00 | 2023-05-05 16:00 |  |  | 4 | 0 | 4 | 8 |  | Concrete Barrier Crew
BW850 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 2023-05-12 08:00 | 2023-05-17 16:00 |  |  | 4 | 0 | 4 | 8 |  | Concrete Barrier Crew
BW890 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 | Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 2023-05-24 08:00 | 2023-05-30 16:00 |  |  | 4 | 0 | 4 | 13 |  | Concrete Barrier Crew
BW1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 2023-06-30 08:00 | 2023-07-06 16:00 |  |  | 4 | 0 | 4 | 13 |  | Concrete Barrier Crew
BW1120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 38+98.75-44+00.00 - Ph1-S1 | 2023-08-01 08:00 | 2023-08-10 16:00 |  |  | 8 | 0 | 8 | 13 |  | Concrete Barrier Crew
R655A | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | 2022-06-06 08:00 | 2022-11-16 16:00 | 2022-06-06 08:00 |  | 12 | 111 | 3 | 160 |  | CIP Wall Crew
R720A | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | 2022-07-19 08:00 | 2022-11-29 16:00 | 2022-07-19 08:00 |  | 12 | 81 | 9 | 69 |  | CIP Wall Crew
R790A | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - West Half - North Side - Ph1-S1-S2 | 2022-07-12 08:00 | 2022-07-22 08:00 | 2022-07-12 08:00 | 2022-07-22 08:00 | 12 | 8 | 0 |  |  | CIP Wall Crew
R850A | In Progress | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - West Half - North Side - Ph1-S1-S2 | 2022-07-18 08:00 | 2022-11-29 16:00 | 2022-07-18 08:00 |  | 12 | 82 | 9 | 72 |  | CIP Wall Crew
DSS100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-101) - NB: 723+54 - Ph1-S1 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2 | 0 | 0 |  |  | Sub - Drilled Shaft Crew
DSS110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-101) - SB: 723+54 - Ph1-S1 | 2022-10-25 08:00 | 2022-11-04 16:00 | 2022-10-25 08:00 | 2022-11-04 16:00 | 2 | 9 | 0 |  |  | Sub - Drilled Shaft Crew
DSS120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 2022-05-12 08:00 | 2022-05-13 16:00 | 2022-05-12 08:00 | 2022-05-13 16:00 | 2 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
DSS130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-102) - SB: 736+00 - Ph1-S1 | 2022-08-22 08:00 | 2022-08-30 16:00 | 2022-08-22 08:00 | 2022-08-30 16:00 | 2 | 7 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 2022-03-10 08:00 | 2022-03-11 16:00 | 2022-03-10 08:00 | 2022-03-11 16:00 | 5 | 2 | 0 |  |  | Demolition Crews
BW110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 2022-05-23 08:00 | 2022-05-25 16:00 | 2022-05-23 08:00 | 2022-05-25 16:00 | 3 | 3 | 0 |  |  | Concrete Barrier Crew
DSS150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-101) - NB: 739+29 - Ph1-S1 | 2022-08-18 08:00 | 2022-08-19 16:00 | 2022-08-18 08:00 | 2022-08-19 16:00 | 2 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
DSS160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-102) - SB: 745+96 - Ph1-S1 | 2022-08-17 08:00 | 2022-08-19 16:00 | 2022-08-17 08:00 | 2022-08-19 16:00 | 2 | 3 | 0 |  |  | Sub - Drilled Shaft Crew
DSS170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 2022-05-10 08:00 | 2022-05-11 16:00 | 2022-05-10 08:00 | 2022-05-11 16:00 | 2 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 2022-03-09 08:00 | 2022-03-10 16:00 | 2022-03-09 08:00 | 2022-03-10 16:00 | 5 | 2 | 0 |  |  | Demolition Crews
BW130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 2022-05-13 08:00 | 2022-05-14 16:00 | 2022-05-13 08:00 | 2022-05-14 16:00 | 5 | 1 | 0 |  |  | Concrete Barrier Crew
DSS190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2 | 0 | 0 |  |  | Sub - Drilled Shaft Crew
DSS200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-103) - SB: 758+73 - Ph1-S1 | 2022-08-22 08:00 | 2022-08-26 16:00 | 2022-08-22 08:00 | 2022-08-26 16:00 | 2 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DSS210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 2022-04-15 08:00 | 2022-04-16 16:00 | 2022-04-15 08:00 | 2022-04-16 16:00 | 2 | 1 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO480 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 2022-03-08 08:00 | 2022-03-09 16:00 | 2022-03-08 08:00 | 2022-03-09 16:00 | 5 | 2 | 0 |  |  | Demolition Crews
BW140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 2022-05-13 08:00 | 2022-05-14 16:00 | 2022-05-13 08:00 | 2022-05-14 16:00 | 5 | 1 | 0 |  |  | Concrete Barrier Crew
DSS230 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | 2022-06-14 08:00 | 2022-07-15 16:00 | 2022-06-14 08:00 | 2022-07-15 16:00 | 3 | 23 | 0 |  |  | Sub - Drilled Shaft Crew
DSS240 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 2022-04-15 08:00 | 2022-04-16 16:00 | 2022-04-15 08:00 | 2022-04-16 16:00 | 3 | 1 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO530 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 2022-03-08 08:00 | 2022-03-09 16:00 | 2022-03-08 08:00 | 2022-03-09 16:00 | 6 | 2 | 0 |  |  | Demolition Crews
BW240 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 2022-05-12 08:00 | 2022-05-14 16:00 | 2022-05-12 08:00 | 2022-05-14 16:00 | 7 | 2 | 0 |  |  | Concrete Barrier Crew
DSS260 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | 2022-06-17 08:00 | 2022-07-15 16:00 | 2022-06-17 08:00 | 2022-07-15 16:00 | 3 | 20 | 0 |  |  | Sub - Drilled Shaft Crew
DSS270 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 2022-04-20 08:00 | 2022-04-22 16:00 | 2022-04-20 08:00 | 2022-04-22 16:00 | 3 | 3 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO590 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 2022-03-07 08:00 | 2022-03-08 16:00 | 2022-03-07 08:00 | 2022-03-08 16:00 | 6 | 2 | 0 |  |  | Demolition Crews
BW260 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 2022-05-11 08:00 | 2022-05-14 16:00 | 2022-05-11 08:00 | 2022-05-14 16:00 | 6 | 3 | 0 |  |  | Concrete Barrier Crew
DSS290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | 2022-06-07 08:00 | 2022-07-11 16:00 | 2022-06-07 08:00 | 2022-07-11 16:00 | 3 | 24 | 0 |  |  | Sub - Drilled Shaft Crew
DSS300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-104) - SB: 792+45 - Ph1-S1 | 2022-08-22 08:00 | 2022-08-26 16:00 | 2022-08-22 08:00 | 2022-08-26 16:00 | 3 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DSS310 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 2022-04-12 08:00 | 2022-04-14 16:00 | 2022-04-12 08:00 | 2022-04-14 16:00 | 2 | 3 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO670 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 2022-03-07 08:00 | 2022-03-08 16:00 | 2022-03-07 08:00 | 2022-03-08 16:00 | 7 | 2 | 0 |  |  | Demolition Crews
BW310 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 2022-05-09 08:00 | 2022-05-12 16:00 | 2022-05-09 08:00 | 2022-05-12 16:00 | 5 | 4 | 0 |  |  | Concrete Barrier Crew
DSS330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 800+70 - Ph1-S1 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2 | 0 | 0 |  |  | Sub - Drilled Shaft Crew
DSS340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-105) - SB: 808+47 - Ph1-S1 | 2022-06-06 08:00 | 2022-06-08 16:00 | 2022-06-06 08:00 | 2022-06-08 16:00 | 3 | 3 | 0 |  |  | Sub - Drilled Shaft Crew
DSS350 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-106) - NB: 811+90 - Ph1-S1 | 2022-06-17 08:00 | 2022-06-27 16:00 | 2022-06-17 08:00 | 2022-06-27 16:00 | 2 | 7 | 0 |  |  | Sub - Drilled Shaft Crew
DSS360 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHB-101) - SB: 818+78 - Ph1-S1 | 2022-09-05 08:00 | 2022-09-09 16:00 | 2022-09-05 08:00 | 2022-09-09 16:00 | 3 | 4 | 0 |  |  | Sub - Drilled Shaft Crew
DSS370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 2022-04-10 08:00 | 2022-04-12 16:00 | 2022-04-10 08:00 | 2022-04-12 16:00 | 3 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
DEMO730 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 2022-03-06 08:00 | 2022-03-07 16:00 | 2022-03-06 08:00 | 2022-03-07 16:00 | 9 | 1 | 0 |  |  | Demolition Crews
BW340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 2022-05-09 08:00 | 2022-05-12 16:00 | 2022-05-09 08:00 | 2022-05-12 16:00 | 8 | 4 | 0 |  |  | Concrete Barrier Crew
DSS390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 3 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DSS400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 833+46 - Ph1-S1 | 2022-05-20 08:00 | 2022-05-20 16:00 | 2022-05-20 08:00 | 2022-05-20 16:00 | 3 | 1 | 0 |  |  | Sub - Drilled Shaft Crew
SGN60 | Completed | 3462-FDOT-Owner-12.2.1.4.2.2 | Preconstruction: Procurement: Electrical / ITS: Foundations | Procurement: Sign Foundations (Drilled Shafts) | 2022-02-01 08:00 | 2022-04-15 16:00 | 2022-02-01 08:00 | 2022-04-15 16:00 | 30 | 54 | 0
SGN70 | Not Started | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-101 / 723+54 | 2022-11-14 08:00 | 2023-05-12 16:00 |  |  | 120 | 0 | 120 | 37
SGN80 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-102 / 736+00 | 2022-09-15 08:00 | 2023-04-12 16:00 | 2022-09-15 08:00 |  | 120 | 41 | 98 | 190
SGN90 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-101 / 739+29 | 2022-09-05 08:00 | 2023-04-03 16:00 | 2022-09-05 08:00 |  | 120 | 48 | 91 | 69
SGN100 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-102 / 745+96 | 2022-09-05 08:00 | 2023-04-03 16:00 | 2022-09-05 08:00 |  | 120 | 48 | 91 | 200
SGN110 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-103 / 750+92 | 2022-06-20 08:00 | 2023-01-18 16:00 | 2022-06-20 08:00 |  | 120 | 101 | 38 | 120
SGN120 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-103 / 758+73 | 2022-09-05 08:00 | 2023-04-03 16:00 | 2022-09-05 08:00 |  | 120 | 48 | 91 | 193
SGN130 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-104 / 771+34 | 2022-06-20 08:00 | 2023-01-18 16:00 | 2022-06-20 08:00 |  | 120 | 101 | 38 | 223
SGN140 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-105 / 775+55 | 2022-06-20 08:00 | 2023-01-18 16:00 | 2022-06-20 08:00 |  | 120 | 101 | 38 | 148
SGN150 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-106 / 783+35 | 2022-07-25 08:00 | 2023-02-21 16:00 | 2022-07-25 08:00 |  | 120 | 77 | 62 | 184
SGN160 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-104 / 792+45 | 2022-09-12 08:00 | 2023-03-10 16:00 | 2022-09-12 08:00 |  | 120 | 44 | 75 | 167
SGN170 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-107 / 800+70 | 2022-07-25 08:00 | 2023-02-21 16:00 | 2022-07-25 08:00 |  | 120 | 77 | 62 | 143
SGN180 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-105 / 808+47 | 2022-07-27 08:00 | 2023-02-23 16:00 | 2022-07-27 08:00 |  | 120 | 75 | 64 | 171
SGN190 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-106 / 811+90 | 2022-07-28 08:00 | 2023-02-24 16:00 | 2022-07-28 08:00 |  | 120 | 74 | 65 | 144
SGN200 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHB-01 / 818+78 | 2022-09-12 08:00 | 2023-04-07 16:00 | 2022-09-12 08:00 |  | 120 | 44 | 95 | 127
SGN210 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHS-108 / 825+75 | 2022-07-26 08:00 | 2023-02-22 16:00 | 2022-07-26 08:00 |  | 120 | 76 | 63 | 161
SGN220 | In Progress | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Procurement: Sign Posts / Gantry - OHC-107 / 833+46 | 2022-07-22 08:00 | 2023-02-20 16:00 | 2022-07-22 08:00 |  | 120 | 78 | 61 | 155
SGN520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Signs - NB: 748+30-757+10 - Ph1-S1 | 2023-04-27 08:00 | 2023-05-05 16:00 |  |  | 7 | 0 | 7 | 46 |  | Sub - Signing Crew
SGN530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 2023-05-19 08:00 | 2023-05-30 16:00 |  |  | 7 | 0 | 7 | 37 |  | Sub - Signing Crew
SGN540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Signs - NB: 761+67-767+00 - Ph1-S1 | 2023-06-29 08:00 | 2023-07-10 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Signs - NB: 767+00-773+42 - Ph1-S1 | 2023-07-11 08:00 | 2023-07-19 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Signs - NB: 774+82-780+00 - Ph1-S1 | 2023-07-20 08:00 | 2023-07-28 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Signs - NB: 780+00-786+69 - Ph1-S1 | 2023-07-31 08:00 | 2023-08-08 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Signs - NB: 788+09-800+00 - Ph1-S1 | 2023-08-09 08:00 | 2023-08-17 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Signs - NB: 800+00-813+16 - Ph1-S1 | 2023-08-18 08:00 | 2023-08-28 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 2023-08-29 08:00 | 2023-09-08 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 2023-09-11 08:00 | 2023-09-19 16:00 |  |  | 7 | 0 | 7 | 21 |  | Sub - Signing Crew
SGN620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 2023-09-20 08:00 | 2023-09-28 16:00 |  |  | 7 | 0 | 7 | 21 |  | Sub - Signing Crew
SGN630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Signs - SB: 788+09-800+00 - Ph1-S1 | 2023-10-06 08:00 | 2023-10-16 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Signing Crew
SGN640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Signs - SB: 780+00-786+69 - Ph1-S1 | 2023-10-24 08:00 | 2023-11-01 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Signs - SB: 774+82-780+00 - Ph1-S1 | 2023-11-02 08:00 | 2023-11-13 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Signs - SB: 767+00-773+42 - Ph1-S1 | 2023-11-14 08:00 | 2023-11-27 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Signs - SB: 761+67-767+00 - Ph1-S1 | 2023-11-28 08:00 | 2023-12-06 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Signs - SB: 757+10-759+97 - Ph1-S1 | 2023-12-07 08:00 | 2023-12-15 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Signs - SB: 748+30-757+10 - Ph1-S1 | 2023-12-18 08:00 | 2024-01-04 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Signs - SB: 735+46-746+91 - Ph1-S1 | 2024-01-05 08:00 | 2024-01-16 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 2024-01-17 08:00 | 2024-01-25 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sub - Signing Crew
SGN720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | 2024-01-26 08:00 | 2024-02-05 16:00 |  |  | 7 | 0 | 7 | 44 |  | Sub - Signing Crew
EL100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 12 |  | Sub - Electrical Installation Crew
EL120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 2022-08-15 08:00 | 2022-09-16 16:00 | 2022-08-15 08:00 | 2022-09-16 16:00 | 4 | 23 | 0 |  |  | Sub - Electrical Installation Crew
EL130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 757+10-759+97 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 29 |  | Sub - Electrical Installation Crew
EL140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-21 16:00 |  |  | 6 | 0 | 6 | 35 |  | Sub - Electrical Installation Crew
EL150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-21 16:00 |  |  | 4 | 0 | 4 | 9 |  | Sub - Electrical Installation Crew
EL180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 2022-11-22 08:00 | 2022-11-29 16:00 |  |  | 3 | 0 | 3 | 9 |  | Sub - Electrical Installation Crew
EL190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 2022-11-30 08:00 | 2022-12-13 16:00 |  |  | 10 | 0 | 10 | 9 |  | Sub - Electrical Installation Crew
EL200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 2022-12-14 08:00 | 2023-01-11 16:00 |  |  | 15 | 0 | 15 | 9 |  | Sub - Electrical Installation Crew
EL210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 2023-01-20 08:00 | 2023-02-02 16:00 |  |  | 10 | 0 | 10 | 4 |  | Sub - Electrical Installation Crew
EL220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 2023-02-09 08:00 | 2023-02-20 16:00 |  |  | 8 | 0 | 8 | 15 |  | Sub - Electrical Installation Crew
EL230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 2023-03-06 08:00 | 2023-03-10 16:00 |  |  | 5 | 0 | 5 | 6 |  | Sub - Electrical Installation Crew
EL240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 2023-03-13 08:00 | 2023-03-15 16:00 |  |  | 3 | 0 | 3 | 31 |  | Sub - Electrical Installation Crew
EL260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 2023-03-17 08:00 | 2023-03-20 16:00 |  |  | 2 | 0 | 2 | 36 |  | Sub - Electrical Installation Crew
EL270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-20 16:00 |  |  | 10 | 0 | 10 | 23 |  | Sub - Electrical Installation Crew
EL280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | 2023-04-21 08:00 | 2023-04-28 16:00 |  |  | 6 | 0 | 6 | 34 |  | Sub - Electrical Installation Crew
EL290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 2023-05-01 08:00 | 2023-05-08 16:00 |  |  | 6 | 0 | 6 | 34 |  | Sub - Electrical Installation Crew
EL300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | 2023-05-09 08:00 | 2023-05-16 16:00 |  |  | 6 | 0 | 6 | 34 |  | Sub - Electrical Installation Crew
EL310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | 2023-05-17 08:00 | 2023-05-26 16:00 |  |  | 8 | 0 | 8 | 34 |  | Sub - Electrical Installation Crew
EL320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 2023-06-14 08:00 | 2023-06-21 16:00 |  |  | 6 | 0 | 6 | 23 |  | Sub - Electrical Installation Crew
CP350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | 2023-08-15 08:00 | 2023-09-05 16:00 |  |  | 14 | 0 | 14 | 13 |  | Concrete Paving Crews
CP280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | 2023-06-26 08:00 | 2023-07-11 16:00 |  |  | 11 | 0 | 11 | 13 |  | Concrete Paving Crews
CP300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 2023-07-31 08:00 | 2023-08-14 16:00 |  |  | 11 | 0 | 11 | 13 |  | Concrete Paving Crews
DEMO1700 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Remove Light Poles / Demo - NB & SB Median: 714+00-721+43 - Ph2 | 2024-04-18 08:00 | 2024-04-23 16:00 |  |  | 4 | 0 | 4 | -4 | 1 | Demolition Crews
DEMO1710 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | 2024-04-24 08:00 | 2024-04-29 16:00 |  |  | 4 | 0 | 4 | -4 | 1 | Demolition Crews
DEMO1730 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-04-30 08:00 | 2024-05-06 16:00 |  |  | 5 | 0 | 5 | 8 |  | Demolition Crews
DEMO1790 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | 2024-05-07 08:00 | 2024-05-13 16:00 |  |  | 5 | 0 | 5 | 8 |  | Demolition Crews
DEMO1820 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | 2024-05-14 08:00 | 2024-05-22 16:00 |  |  | 7 | 0 | 7 | 8 |  | Demolition Crews
DEMO1850 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | 2024-05-23 08:00 | 2024-06-03 16:00 |  |  | 7 | 0 | 7 | 8 |  | Demolition Crews
DEMO1880 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | 2024-06-24 08:00 | 2024-07-08 16:00 |  |  | 10 | 0 | 10 | 8 |  | Demolition Crews
UDR440 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Install Edgedrain - NB & SB Median: 714+00-721+43 - Ph2 | 2024-06-26 08:00 | 2024-07-02 16:00 |  |  | 5 | 0 | 5 | -1 |  | Underdrain Crew
BASE790 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Shoulder Base - NB & SB Median: 714+00-721+43 - Ph2 | 2024-07-03 08:00 | 2024-07-11 16:00 |  |  | 6 | 0 | 6 | -1 |  | Agg Base Crew
UDR450 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Install Edgedrain - NB & SB Median: 722+83-746+91 - Ph2 | 2024-08-16 08:00 | 2024-08-29 16:00 |  |  | 10 | 0 | 10 | -1 |  | Underdrain Crew
BASE830 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Shoulder Base - NB & SB Median: 722+83-746+91 - Ph2 | 2024-09-06 08:00 | 2024-09-19 16:00 |  |  | 10 | 0 | 10 | -4 | 1 | Agg Base Crew
UDR460 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Install Edgedrain - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-09-17 08:00 | 2024-09-23 16:00 |  |  | 5 | 0 | 5 | -3 | 8 | Underdrain Crew
BASE850 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Shoulder Base - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-09-24 08:00 | 2024-10-01 16:00 |  |  | 6 | 0 | 6 | -3 | 8 | Agg Base Crew
SGN2000 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Install Signs - NB & SB Median: 714+00-721+43 - Ph2 | 2024-10-29 08:00 | 2024-11-07 16:00 |  |  | 8 | 0 | 8 | -4 | 1 | Sub - Signing Crew
SGN2010 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Install Signs - NB & SB Median: 722+83-746+91 - Ph2 | 2024-11-08 08:00 | 2024-11-20 16:00 |  |  | 8 | 0 | 8 | -1 | 25 | Sub - Signing Crew
SGN2020 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Install Signs - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-11-21 08:00 | 2024-12-05 16:00 |  |  | 8 | 0 | 8 | -1 | 25 | Sub - Signing Crew
SGN2030 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | 2024-12-06 08:00 | 2024-12-17 16:00 |  |  | 8 | 0 | 8 | -1 | 25 | Sub - Signing Crew
SGN2040 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | 2024-12-18 08:00 | 2025-01-08 16:00 |  |  | 8 | 0 | 8 | -1 | 25 | Sub - Signing Crew
SGN2050 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | 2025-01-09 08:00 | 2025-01-21 16:00 |  |  | 8 | 0 | 8 | -1 | 25 | Sub - Signing Crew
SGN2060 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Install Signs - NB & SB Median: 815+20-839+61 - Ph2 | 2025-01-22 08:00 | 2025-01-31 16:00 |  |  | 8 | 0 | 8 | 3 |  | Sub - Signing Crew
TCC170 | Not Started | 3462-FDOT-Owner-12.4.P2.1 | Construction: Phase 2: Milestones | Remove MOT Construction Barriers | 2025-02-11 21:00 | 2025-02-24 05:00 |  |  | 10 | 0 | 10 | -4 | 1 | Traffic Control Crews
TCC160 | Not Started | 3462-FDOT-Owner-12.4.P2.1 | Construction: Phase 2: Milestones | Relocate MOT Construction Barriers to Median | 2024-04-11 21:00 | 2024-04-18 01:00 |  |  | 5 | 0 | 5 | -4 | 1 | Traffic Control Crews
TCC100 | Completed | 3462-FDOT-Owner-12.4.IP1.2 | Construction: Initial Phase 1: Site Preparation | Install MOT Construction Barriers I-275 NB - IPh1 | 2022-01-03 21:00 | 2022-02-18 04:00 | 2022-01-03 21:00 | 2022-02-18 04:00 | 12 | 37 | 0 |  |  | Traffic Control Crews
TCC130 | Completed | 3462-FDOT-Owner-12.4.IP1.2 | Construction: Initial Phase 1: Site Preparation | Install MOT Construction Barriers I-275 SB - IPh1 | 2022-03-21 21:00 | 2022-04-15 03:00 | 2022-03-21 21:00 | 2022-04-15 03:00 | 12 | 21 | 0 |  |  | Traffic Control Crews
CP100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | 2023-01-30 08:00 | 2023-02-13 16:00 |  |  | 11 | 0 | 11 | 1 |  | Concrete Paving Crews
GRD110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | 2023-03-09 08:00 | 2023-03-15 16:00 |  |  | 5 | 0 | 5 | 7 |  | Sub - Diamond Grind Pavement Crew
GRD120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | 2023-03-23 08:00 | 2023-03-29 16:00 |  |  | 5 | 0 | 5 | 8 |  | Sub - Diamond Grind Pavement Crew
GRD130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | 2023-04-24 08:00 | 2023-04-28 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sub - Diamond Grind Pavement Crew
GRD140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | 2023-05-12 08:00 | 2023-05-23 16:00 |  |  | 8 | 0 | 8 | 16 |  | Sub - Diamond Grind Pavement Crew
GRD150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | 2023-05-24 08:00 | 2023-06-05 16:00 |  |  | 8 | 0 | 8 | 16 |  | Sub - Diamond Grind Pavement Crew
GRD160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | 2023-06-06 08:00 | 2023-06-13 16:00 |  |  | 6 | 0 | 6 | 16 |  | Sub - Diamond Grind Pavement Crew
GRD170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | 2023-06-14 08:00 | 2023-06-21 16:00 |  |  | 6 | 0 | 6 | 16 |  | Sub - Diamond Grind Pavement Crew
GRD180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | 2023-06-29 08:00 | 2023-07-07 16:00 |  |  | 6 | 0 | 6 | 11 |  | Sub - Diamond Grind Pavement Crew
GRD190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | 2023-07-10 08:00 | 2023-07-17 16:00 |  |  | 6 | 0 | 6 | 11 |  | Sub - Diamond Grind Pavement Crew
GRD200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 2023-08-29 08:00 | 2023-09-13 16:00 |  |  | 10 | 0 | 10 | 13 |  | Sub - Diamond Grind Pavement Crew
GRD210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | 2023-09-20 08:00 | 2023-09-26 16:00 |  |  | 5 | 0 | 5 | 22 |  | Sub - Diamond Grind Pavement Crew
GRD220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | 2023-10-03 08:00 | 2023-10-10 16:00 |  |  | 6 | 0 | 6 | 24 |  | Sub - Diamond Grind Pavement Crew
GRD230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | 2023-10-20 08:00 | 2023-10-27 16:00 |  |  | 6 | 0 | 6 | 19 |  | Sub - Diamond Grind Pavement Crew
GRD240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | 2023-11-07 08:00 | 2023-11-15 16:00 |  |  | 6 | 0 | 6 | 13 |  | Sub - Diamond Grind Pavement Crew
GRD250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | 2023-11-16 08:00 | 2023-11-28 16:00 |  |  | 6 | 0 | 6 | 13 |  | Sub - Diamond Grind Pavement Crew
GRD260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | 2023-11-29 08:00 | 2023-12-05 16:00 |  |  | 5 | 0 | 5 | 13 |  | Sub - Diamond Grind Pavement Crew
GRD270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | 2023-12-06 08:00 | 2023-12-12 16:00 |  |  | 5 | 0 | 5 | 13 |  | Sub - Diamond Grind Pavement Crew
GRD280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | 2023-12-14 08:00 | 2023-12-20 16:00 |  |  | 5 | 0 | 5 | 12 |  | Sub - Diamond Grind Pavement Crew
GRD290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | 2023-12-21 08:00 | 2024-01-05 16:00 |  |  | 5 | 0 | 5 | 12 |  | Sub - Diamond Grind Pavement Crew
GRD300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | 2024-01-08 08:00 | 2024-01-12 16:00 |  |  | 5 | 0 | 5 | 14 |  | Sub - Diamond Grind Pavement Crew
GRD310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | 2024-01-16 08:00 | 2024-01-22 16:00 |  |  | 5 | 0 | 5 | 14 |  | Sub - Diamond Grind Pavement Crew
GRD320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | 2024-01-23 08:00 | 2024-01-29 16:00 |  |  | 5 | 0 | 5 | 37 |  | Sub - Diamond Grind Pavement Crew
GRD330 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Grind Concrete Pavement - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 2024-04-04 08:00 | 2024-04-10 16:00 |  |  | 5 | 0 | 5 | -4 | 5 | Sub - Diamond Grind Pavement Crew
GRD340 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | 2024-10-21 08:00 | 2024-10-28 16:00 |  |  | 6 | 0 | 6 | -4 | 1 | Sub - Diamond Grind Pavement Crew
GRD350 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | 2024-10-29 08:00 | 2024-11-07 16:00 |  |  | 8 | 0 | 8 | 7 |  | Sub - Diamond Grind Pavement Crew
GRD360 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-11-08 08:00 | 2024-11-20 16:00 |  |  | 8 | 0 | 8 | 7 |  | Sub - Diamond Grind Pavement Crew
GRD370 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 2024-11-22 08:00 | 2024-12-04 16:00 |  |  | 6 | 0 | 6 | 8 |  | Sub - Diamond Grind Pavement Crew
GRD380 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 2024-12-05 08:00 | 2024-12-12 16:00 |  |  | 6 | 0 | 6 | 10 |  | Sub - Diamond Grind Pavement Crew
GRD390 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 2025-01-03 08:00 | 2025-01-10 16:00 |  |  | 6 | 0 | 6 | 5 |  | Sub - Diamond Grind Pavement Crew
GRD400 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | 2025-01-16 08:00 | 2025-01-23 16:00 |  |  | 5 | 0 | 5 | 4 |  | Sub - Diamond Grind Pavement Crew
CLK100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | 2023-03-29 08:00 | 2023-04-04 16:00 |  |  | 5 | 0 | 5 | 9 |  | Conc Pvmt Sawcut Crew
CLK110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | 2023-04-10 08:00 | 2023-04-14 16:00 |  |  | 5 | 0 | 5 | 6 |  | Conc Pvmt Sawcut Crew
CLK120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | 2023-04-24 08:00 | 2023-04-28 16:00 |  |  | 5 | 0 | 5 | 1 |  | Conc Pvmt Sawcut Crew
CLK130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | 2023-05-01 08:00 | 2023-05-05 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Conc Pvmt Sawcut Crew
CLK140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | 2023-11-01 08:00 | 2023-11-07 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | 2023-11-08 08:00 | 2023-11-15 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | 2023-11-16 08:00 | 2023-11-27 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | 2023-11-28 08:00 | 2023-12-04 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | 2023-12-05 08:00 | 2023-12-11 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | 2023-12-12 08:00 | 2023-12-18 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | 2023-12-19 08:00 | 2024-01-03 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | 2024-01-04 08:00 | 2024-01-10 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | 2024-01-11 08:00 | 2024-01-18 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | 2024-01-19 08:00 | 2024-01-25 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | 2024-01-26 08:00 | 2024-02-01 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | 2024-02-02 08:00 | 2024-02-08 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | 2024-02-09 08:00 | 2024-02-15 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | 2024-02-16 08:00 | 2024-02-22 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | 2024-02-23 08:00 | 2024-02-29 16:00 |  |  | 5 | 0 | 5 | -1 |  | Conc Pvmt Sawcut Crew
CLK290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | 2024-03-06 08:00 | 2024-03-12 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Conc Pvmt Sawcut Crew
CLK300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | 2024-03-13 08:00 | 2024-03-19 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Conc Pvmt Sawcut Crew
CLK310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | 2024-03-20 08:00 | 2024-03-26 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Conc Pvmt Sawcut Crew
CLK320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | 2024-03-27 08:00 | 2024-04-02 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Conc Pvmt Sawcut Crew
CLK330 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Caulk & Seal Joints - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 2024-04-11 08:00 | 2024-04-17 16:00 |  |  | 5 | 0 | 5 | -4 | 5 | Conc Pvmt Sawcut Crew
CLK340 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Caulk & Seal Joints - NB & SB Median: 714+00-721+43 - Ph2 | 2024-11-08 08:00 | 2024-11-20 16:00 |  |  | 8 | 0 | 8 | -4 | 1 | Conc Pvmt Sawcut Crew
CLK350 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Caulk & Seal Joints - NB & SB Median: 722+83-746+91 - Ph2 | 2024-11-21 08:00 | 2024-12-05 16:00 |  |  | 8 | 0 | 8 | -1 | 24 | Conc Pvmt Sawcut Crew
CLK360 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Caulk & Seal Joints - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-12-06 08:00 | 2024-12-17 16:00 |  |  | 8 | 0 | 8 | -1 | 24 | Conc Pvmt Sawcut Crew
CLK370 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Caulk & Seal Joints - NB & SB Median: 761+67-773+42 - Ph2 | 2024-12-18 08:00 | 2025-01-08 16:00 |  |  | 8 | 0 | 8 | -1 | 24 | Conc Pvmt Sawcut Crew
CLK380 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Caulk & Seal Joints - NB & SB Median: 774+82-786+69 - Ph2 | 2025-01-09 08:00 | 2025-01-21 16:00 |  |  | 8 | 0 | 8 | -1 | 24 | Conc Pvmt Sawcut Crew
CLK390 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Caulk & Seal Joints - NB & SB Median: 788+09-813+16 - Ph2 | 2025-01-22 08:00 | 2025-01-30 16:00 |  |  | 7 | 0 | 7 | -1 | 24 | Conc Pvmt Sawcut Crew
CLK400 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Caulk & Seal Joints - NB & SB Median: 815+20-839+61 - Ph2 | 2025-01-31 08:00 | 2025-02-06 16:00 |  |  | 5 | 0 | 5 | -1 | 24 | Conc Pvmt Sawcut Crew
CP1440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Cure Concrete - NB: 722+83-735+00 - Ph1-S1 | 2023-02-14 08:00 | 2023-02-27 16:00 |  |  | 14 | 0 | 14 | 3
CP1450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Cure Concrete - NB: 735+46-746+91 - Ph1-S1 | 2023-02-23 08:00 | 2023-03-08 16:00 |  |  | 14 | 0 | 14 | 11
CP1460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Cure Concrete - NB: 748+30-757+10 - Ph1-S1 | 2023-03-09 08:00 | 2023-03-22 16:00 |  |  | 14 | 0 | 14 | 12
CP1470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Cure Concrete - NB: 757+10-759+97 - Ph1-S1 | 2023-04-12 08:00 | 2023-04-21 16:00 |  |  | 10 | 0 | 10 | -4 | 1
CP1480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Cure Concrete - NB: 761+67-767+00 - Ph1-S1 | 2023-04-28 08:00 | 2023-05-11 16:00 |  |  | 14 | 0 | 14 | 25
CP1490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Cure Concrete - NB: 767+00-773+42 - Ph1-S1 | 2023-05-09 08:00 | 2023-05-22 16:00 |  |  | 14 | 0 | 14 | 24
CP1500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Cure Concrete - NB: 774+82-780+00 - Ph1-S1 | 2023-05-16 08:00 | 2023-05-29 16:00 |  |  | 14 | 0 | 14 | 29
CP1510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Cure Concrete - NB: 780+00-786+69 - Ph1-S1 | 2023-05-25 08:00 | 2023-06-07 16:00 |  |  | 14 | 0 | 14 | 29
CP1520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Cure Concrete - NB: 788+09-800+00 - Ph1-S1 | 2023-06-15 08:00 | 2023-06-28 16:00 |  |  | 14 | 0 | 14 | 18
CP1530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Cure Concrete - NB: 800+00-813+16 - Ph1-S1 | 2023-05-31 08:00 | 2023-06-13 16:00 |  |  | 14 | 0 | 14 | 41
CP1540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Cure Concrete - NB: 815+20-839+61 - Ph1-S1 | 2023-08-15 08:00 | 2023-08-28 16:00 |  |  | 14 | 0 | 14 | 21
CP1550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Cure Concrete - SB: 827+00-839+61 - Ph1-S1 | 2023-09-06 08:00 | 2023-09-19 16:00 |  |  | 14 | 0 | 14 | 30
CP1560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Cure Concrete - SB: 800+00-813+16 - Ph1-S1 | 2023-09-19 08:00 | 2023-10-02 16:00 |  |  | 14 | 0 | 14 | 34
CP1570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Cure Concrete - SB: 788+09-800+00 - Ph1-S1 | 2023-10-06 08:00 | 2023-10-19 16:00 |  |  | 14 | 0 | 14 | 28
CP1580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Cure Concrete - SB: 780+00-786+69 - Ph1-S1 | 2023-10-24 08:00 | 2023-11-06 16:00 |  |  | 14 | 0 | 14 | 23
CP1590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Cure Concrete - SB: 774+82-780+00 - Ph1-S1 | 2023-10-31 08:00 | 2023-11-13 16:00 |  |  | 14 | 0 | 14 | 24
CP1600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Cure Concrete - SB: 767+00-773+42 - Ph1-S1 | 2023-11-07 08:00 | 2023-11-20 16:00 |  |  | 14 | 0 | 14 | 27
CP1610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Cure Concrete - SB: 761+67-767+00 - Ph1-S1 | 2023-11-18 08:00 | 2023-12-01 16:00 |  |  | 14 | 0 | 14 | 32
CP1620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Cure Concrete - SB: 757+10-759+97 - Ph1-S1 | 2023-11-30 08:00 | 2023-12-13 16:00 |  |  | 14 | 0 | 14 | 27
CP1630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Cure Concrete - SB: 748+30-757+10 - Ph1-S1 | 2023-11-09 08:00 | 2023-11-22 16:00 |  |  | 14 | 0 | 14 | 56
CP1640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Cure Concrete - SB: 735+46-746+91 - Ph1-S1 | 2023-11-22 08:00 | 2023-12-05 16:00 |  |  | 14 | 0 | 14 | 54
CP1650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Cure Concrete - SB: 722+83-735+00 - Ph1-S1 | 2023-12-02 08:00 | 2023-12-15 16:00 |  |  | 14 | 0 | 14 | 51
CP1660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Cure Concrete - SB: 709+50-721+43 - Ph1-S1 | 2023-12-16 08:00 | 2023-12-29 16:00 |  |  | 14 | 0 | 14 | 75
CP1670 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Cure Concrete - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 2024-03-21 08:00 | 2024-04-03 16:00 |  |  | 14 | 0 | 14 | -6 | 5
CP1680 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Cure Concrete - NB & SB Median: 714+00-721+43 - Ph2 | 2024-06-26 08:00 | 2024-07-09 16:00 |  |  | 14 | 0 | 14 | 97
CP1690 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Cure Concrete - NB & SB Median: 735+00-746+91 - Ph2 | 2024-09-06 08:00 | 2024-09-19 16:00 |  |  | 14 | 0 | 14 | 48
CP1700 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Cure Concrete - NB & SB Median: 757+10-759+97 - Ph2 | 2024-10-19 08:00 | 2024-11-01 16:00 |  |  | 14 | 0 | 14 | 18
CP1710 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Cure Concrete - NB & SB Median: 767+00-773+42 - Ph2 | 2024-11-08 08:00 | 2024-11-21 16:00 |  |  | 14 | 0 | 14 | 17
CP1720 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Cure Concrete - NB & SB Median: 780+00-786+69 - Ph2 | 2024-11-20 08:00 | 2024-12-03 16:00 |  |  | 14 | 0 | 14 | 15
CP1730 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Cure Concrete - NB & SB Median: 800+00-813+16 - Ph2 | 2024-12-14 08:00 | 2024-12-27 16:00 |  |  | 14 | 0 | 14 | 13
CP1740 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Cure Concrete - NB & SB Median: 815+20-839+61 - Ph2 | 2024-12-13 08:00 | 2024-12-26 16:00 |  |  | 14 | 0 | 14 | 27
DRG2500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | 2023-05-17 08:00 | 2023-05-19 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG2510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | 2023-05-22 08:00 | 2023-05-25 16:00 |  |  | 4 | 0 | 4 | 23 |  | Drainage Crew - Combo
DRG2520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | 2023-05-26 08:00 | 2023-05-31 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG2530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | 2023-06-01 08:00 | 2023-06-05 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG2540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | 2023-06-06 08:00 | 2023-06-08 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG2550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to S-1 (18") - SB: 715-717 - Ph1-S1 | 2023-06-09 08:00 | 2023-06-13 16:00 |  |  | 3 | 0 | 3 | 23 |  | Drainage Crew - Combo
DRG2560 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Drainage: S-9 to S-8 (24") - Floribraska - Ph1-S1-S1 | 2022-02-17 08:00 | 2022-02-19 16:00 | 2022-02-17 08:00 | 2022-02-19 16:00 | 5 | 2 | 0 |  |  | Drainage Crew - Combo
DRG2570 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Drainage: S-8 to S-7 (24") - Floribraska - Ph1-S1-S1 | 2022-02-08 08:00 | 2022-02-18 16:00 | 2022-02-08 08:00 | 2022-02-18 16:00 | 4 | 9 | 0 |  |  | Drainage Crew - Combo
UDR130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Edgedrain - NB: 722+83-735+00 - Ph1-S1 | 2023-02-14 08:00 | 2023-02-22 16:00 |  |  | 7 | 0 | 7 | 1 |  | Underdrain Crew
BASE210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Shoulder Base - NB: 722+83-735+00 - Ph1-S1 | 2023-02-23 08:00 | 2023-03-03 16:00 |  |  | 7 | 0 | 7 | 1 |  | Agg Base Crew
UDR140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Edgedrain - NB: 735+46-746+91 - Ph1-S1 | 2023-02-23 08:00 | 2023-02-28 16:00 |  |  | 4 | 0 | 4 | 4 |  | Underdrain Crew
BASE250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Shoulder Base - NB: 735+46-746+91 - Ph1-S1 | 2023-03-01 08:00 | 2023-03-09 16:00 |  |  | 7 | 0 | 7 | 8 |  | Agg Base Crew
UDR150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Edgedrain - NB: 748+30-757+10 - Ph1-S1 | 2023-03-09 08:00 | 2023-03-17 16:00 |  |  | 7 | 0 | 7 | -2 | 1 | Underdrain Crew
BASE270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Shoulder Base - NB: 748+30-757+10 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-24 16:00 |  |  | 5 | 0 | 5 | 8 |  | Agg Base Crew
UDR390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Edgedrain - SB: 748+30-757+10 - Ph1-S1 | 2023-11-09 08:00 | 2023-11-17 16:00 |  |  | 6 | 0 | 6 | 4 |  | Underdrain Crew
BASE730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Shoulder Base - SB: 748+30-757+10 - Ph1-S1 | 2023-11-20 08:00 | 2023-11-29 16:00 |  |  | 5 | 0 | 5 | 4 |  | Agg Base Crew
UDR410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Edgedrain - SB: 735+46-746+91 - Ph1-S1 | 2023-11-27 08:00 | 2023-12-04 16:00 |  |  | 6 | 0 | 6 | 19 |  | Underdrain Crew
BASE750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Shoulder Base - SB: 735+46-746+91 - Ph1-S1 | 2023-12-05 08:00 | 2023-12-11 16:00 |  |  | 5 | 0 | 5 | 19 |  | Agg Base Crew
UDR420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Edgedrain - SB: 722+83-735+00 - Ph1-S1 | 2023-12-05 08:00 | 2023-12-12 16:00 |  |  | 6 | 0 | 6 | 19 |  | Underdrain Crew
BASE760 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Shoulder Base - SB: 722+83-735+00 - Ph1-S1 | 2023-12-13 08:00 | 2023-12-20 16:00 |  |  | 6 | 0 | 6 | 19 |  | Agg Base Crew
UDR430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Edgedrain - SB: 709+50-721+43 - Ph1-S1 | 2023-12-18 08:00 | 2023-12-22 16:00 |  |  | 5 | 0 | 5 | 53 |  | Underdrain Crew
BASE770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Shoulder Base - SB: 709+50-721+43 - Ph1-S1 | 2024-01-03 08:00 | 2024-01-09 16:00 |  |  | 5 | 0 | 5 | 53 |  | Agg Base Crew
GRD410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | 2023-03-17 08:00 | 2023-03-23 16:00 |  |  | 5 | 0 | 5 | 9 |  | Sub - Diamond Grind Pavement Crew
CLK410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | 2023-03-24 08:00 | 2023-03-28 16:00 |  |  | 3 | 0 | 3 | 9 |  | Conc Pvmt Sawcut Crew
GRD420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | 2023-04-12 08:00 | 2023-04-18 16:00 |  |  | 5 | 0 | 5 | 27 |  | Sub - Diamond Grind Pavement Crew
CLK420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Caulk & Seal Joints 100207 - NB: over East Lake - Ph1-S1 | 2023-04-19 08:00 | 2023-04-21 16:00 |  |  | 3 | 0 | 3 | 46 |  | Conc Pvmt Sawcut Crew
GRD430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-05-01 08:00 | 2023-05-08 16:00 |  |  | 6 | 0 | 6 | 19 |  | Sub - Diamond Grind Pavement Crew
CLK430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-06-06 08:00 | 2023-06-12 16:00 |  |  | 5 | 0 | 5 | 16 |  | Conc Pvmt Sawcut Crew
GRD440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-05-26 08:00 | 2023-06-05 16:00 |  |  | 6 | 0 | 6 | 16 |  | Sub - Diamond Grind Pavement Crew
CLK440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Caulk & Seal Joints 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-06-13 08:00 | 2023-06-22 16:00 |  |  | 8 | 0 | 8 | 83 |  | Conc Pvmt Sawcut Crew
GRD450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2023-09-25 08:00 | 2023-09-29 16:00 |  |  | 5 | 0 | 5 | 13 |  | Sub - Diamond Grind Pavement Crew
CLK450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2023-10-02 08:00 | 2023-10-04 16:00 |  |  | 3 | 0 | 3 | 15 |  | Conc Pvmt Sawcut Crew
GRD460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-10-20 08:00 | 2023-10-26 16:00 |  |  | 5 | 0 | 5 | -1 |  | Sub - Diamond Grind Pavement Crew
CLK460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-10-27 08:00 | 2023-10-31 16:00 |  |  | 3 | 0 | 3 | -1 |  | Conc Pvmt Sawcut Crew
GRD470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-11-17 08:00 | 2023-11-28 16:00 |  |  | 5 | 0 | 5 | 15 |  | Sub - Diamond Grind Pavement Crew
CLK470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-11-29 08:00 | 2023-12-01 16:00 |  |  | 3 | 0 | 3 | 15 |  | Conc Pvmt Sawcut Crew
GRD480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-12-08 08:00 | 2023-12-14 16:00 |  |  | 5 | 0 | 5 | 13 |  | Sub - Diamond Grind Pavement Crew
CLK480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-12-15 08:00 | 2023-12-19 16:00 |  |  | 3 | 0 | 3 | 15 |  | Conc Pvmt Sawcut Crew
GRD490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | 2024-01-04 08:00 | 2024-01-10 16:00 |  |  | 5 | 0 | 5 | 6 |  | Sub - Diamond Grind Pavement Crew
CLK490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | 2024-01-11 08:00 | 2024-01-16 16:00 |  |  | 3 | 0 | 3 | 6 |  | Conc Pvmt Sawcut Crew
GRD500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | 2024-01-24 08:00 | 2024-01-30 16:00 |  |  | 5 | 0 | 5 | 2 |  | Sub - Diamond Grind Pavement Crew
CLK500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | 2024-01-31 08:00 | 2024-02-05 16:00 |  |  | 4 | 0 | 4 | 2 |  | Conc Pvmt Sawcut Crew
GRD510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | 2024-02-15 08:00 | 2024-02-22 16:00 |  |  | 6 | 0 | 6 | -4 | 1 | Sub - Diamond Grind Pavement Crew
CLK510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | 2024-02-23 08:00 | 2024-03-05 16:00 |  |  | 8 | 0 | 8 | -4 | 1 | Conc Pvmt Sawcut Crew
SGN2070 | Completed | 3462-FDOT-Owner-12.2.1.4.2.2 | Preconstruction: Procurement: Electrical / ITS: Foundations | Prepare Shop Drawings / Submittals: Sign Foundations (Drilled Shafts) | 2021-08-26 08:00 | 2021-10-01 16:00 | 2021-08-26 08:00 | 2021-10-01 16:00 | 25 | 25 | 0
SGN2080 | Completed | 3462-FDOT-Owner-12.2.1.4.2.2 | Preconstruction: Procurement: Electrical / ITS: Foundations | Review & Approve Shop Drawings / Submittals: Sign Foundations (Drilled Shafts) (Duration = 25 Calendar Days) | 2022-01-13 08:00 | 2022-01-15 16:00 | 2022-01-13 08:00 | 2022-01-15 16:00 | 25 | 3 | 0
EL330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | 2023-03-09 08:00 | 2023-03-23 16:00 |  |  | 11 | 0 | 11 | 1 |  | Sub - Electrical Installation Crew
EL340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | 2023-03-24 08:00 | 2023-04-07 16:00 |  |  | 11 | 0 | 11 | 1 |  | Sub - Electrical Installation Crew
EL350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | 2023-04-10 08:00 | 2023-04-21 16:00 |  |  | 10 | 0 | 10 | 1 |  | Sub - Electrical Installation Crew
EL360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | 2023-04-12 08:00 | 2023-04-25 16:00 |  |  | 10 | 0 | 10 | -1 |  | Sub - Electrical Installation Crew
EL370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 2023-06-13 08:00 | 2023-06-28 16:00 |  |  | 12 | 0 | 12 | 16 |  | Sub - Electrical Installation Crew
EL380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | 2023-06-29 08:00 | 2023-07-17 16:00 |  |  | 12 | 0 | 12 | 71 |  | Sub - Electrical Installation Crew
EL390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | 2023-07-18 08:00 | 2023-08-02 16:00 |  |  | 12 | 0 | 12 | 71 |  | Sub - Electrical Installation Crew
EL400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | 2023-06-22 08:00 | 2023-07-10 16:00 |  |  | 12 | 0 | 12 | 37 |  | Sub - Electrical Installation Crew
EL410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | 2023-07-11 08:00 | 2023-07-26 16:00 |  |  | 12 | 0 | 12 | 37 |  | Sub - Electrical Installation Crew
EL420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | 2023-07-27 08:00 | 2023-08-11 16:00 |  |  | 12 | 0 | 12 | 37 |  | Sub - Electrical Installation Crew
EL430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 2023-09-14 08:00 | 2023-10-04 16:00 |  |  | 15 | 0 | 15 | 16 |  | Sub - Electrical Installation Crew
EL440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 2023-10-05 08:00 | 2023-10-20 16:00 |  |  | 12 | 0 | 12 | 16 |  | Sub - Electrical Installation Crew
EL450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | 2023-10-23 08:00 | 2023-11-03 16:00 |  |  | 10 | 0 | 10 | 16 |  | Sub - Electrical Installation Crew
EL460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | 2023-11-06 08:00 | 2023-11-16 16:00 |  |  | 8 | 0 | 8 | 16 |  | Sub - Electrical Installation Crew
EL470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | 2023-11-17 08:00 | 2023-11-30 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Electrical Installation Crew
EL480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | 2023-12-01 08:00 | 2023-12-11 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Electrical Installation Crew
EL490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | 2023-12-12 08:00 | 2023-12-21 16:00 |  |  | 8 | 0 | 8 | 16 |  | Sub - Electrical Installation Crew
EL500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | 2023-12-22 08:00 | 2024-01-10 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Electrical Installation Crew
EL510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | 2024-01-11 08:00 | 2024-01-19 16:00 |  |  | 6 | 0 | 6 | 16 |  | Sub - Electrical Installation Crew
EL520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | 2024-01-22 08:00 | 2024-02-01 16:00 |  |  | 9 | 0 | 9 | 16 |  | Sub - Electrical Installation Crew
EL530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | 2024-02-02 08:00 | 2024-02-09 16:00 |  |  | 6 | 0 | 6 | 16 |  | Sub - Electrical Installation Crew
EL540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | 2024-02-12 08:00 | 2024-02-20 16:00 |  |  | 7 | 0 | 7 | 16 |  | Sub - Electrical Installation Crew
EL550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 2024-04-03 08:00 | 2024-04-11 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Electrical Installation Crew
B3450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 2022-04-12 08:00 | 2022-04-16 16:00 | 2022-04-12 08:00 | 2022-04-16 16:00 | 3 | 5 | 0
SUBS150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 2022-04-16 08:00 | 2022-04-16 16:00 | 2022-04-16 08:00 | 2022-04-16 16:00 | 1 | 0 | 0 |  |  | Substructure Crew
B3470 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 2022-04-12 08:00 | 2022-04-16 16:00 | 2022-04-12 08:00 | 2022-04-16 16:00 | 3 | 5 | 0
SUBS160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 2022-04-16 08:00 | 2022-04-16 16:00 | 2022-04-16 08:00 | 2022-04-16 16:00 | 1 | 0 | 0 |  |  | Substructure Crew
B3490 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-11 08:00 | 2022-07-12 16:00 | 2022-07-11 08:00 | 2022-07-12 16:00 | 7 | 2 | 0
SUBS250 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-01 08:00 | 2022-07-01 16:00 | 2022-07-01 08:00 | 2022-07-01 16:00 | 1 | 1 | 0 |  |  | Substructure Crew
B3510 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-06-08 08:00 | 2022-06-11 16:00 | 2022-06-08 08:00 | 2022-06-11 16:00 | 7 | 4 | 0
SUBS260 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-06-14 08:00 | 2022-06-17 16:00 | 2022-06-14 08:00 | 2022-06-17 16:00 | 1 | 4 | 0 |  |  | Substructure Crew
B3530 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 2022-10-27 08:00 | 2022-10-29 16:00 | 2022-10-27 08:00 | 2022-10-29 16:00 | 3 | 3 | 0
SUBS140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
B3550 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 3 | 2 | 0
SUBS170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 2022-07-15 08:00 | 2022-10-26 16:00 | 2022-07-15 08:00 | 2022-10-26 16:00 | 2 | 72 | 0 |  |  | Substructure Crew
B3570 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 2022-06-08 08:00 | 2022-06-11 08:00 | 2022-06-08 08:00 | 2022-06-11 08:00 | 3 | 3 | 0
SUBS270 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 2022-05-14 08:00 | 2022-06-08 16:00 | 2022-05-14 08:00 | 2022-06-08 16:00 | 2 | 17 | 0 |  |  | Substructure Crew
B3590 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 2022-06-09 08:00 | 2022-06-11 16:00 | 2022-06-09 08:00 | 2022-06-11 16:00 | 3 | 3 | 0
SUBS280 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 2022-06-10 08:00 | 2022-06-10 16:00 | 2022-06-10 08:00 | 2022-06-10 16:00 | 2 | 1 | 0 |  |  | Substructure Crew
B3610 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | 2022-06-08 08:00 | 2022-06-11 16:00 | 2022-06-08 08:00 | 2022-06-11 16:00 | 7 | 4 | 0
B3620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 2022-07-07 08:00 | 2022-07-08 16:00 | 2022-07-07 08:00 | 2022-07-08 16:00 | 7 | 2 | 0
SUBS350 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | 2022-06-08 08:00 | 2022-06-09 16:00 | 2022-06-08 08:00 | 2022-06-09 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS360 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 2022-07-11 08:00 | 2022-07-12 16:00 | 2022-07-11 08:00 | 2022-07-12 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
B3650 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 2022-07-27 08:00 | 2022-07-29 16:00 | 2022-07-27 08:00 | 2022-07-29 16:00 | 3 | 3 | 0
SUBS230 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 2022-08-01 08:00 | 2022-08-02 16:00 | 2022-08-01 08:00 | 2022-08-02 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
B3670 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 2022-07-15 08:00 | 2022-07-15 16:00 | 2022-07-15 08:00 | 2022-07-15 16:00 | 3 | 1 | 0
SUBS370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 2022-07-18 08:00 | 2022-07-19 16:00 | 2022-07-18 08:00 | 2022-07-19 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
B3690 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-15 08:00 | 2022-09-23 16:00 | 2022-09-15 08:00 | 2022-09-23 16:00 | 3 | 9 | 0
B3700 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-15 08:00 | 2022-09-23 16:00 | 2022-09-15 08:00 | 2022-09-23 16:00 | 3 | 9 | 0
B3710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-11-13 08:00 | 2022-11-14 16:00 |  |  | 2 | 0 | 2 | 36
SUBS380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Substructure Crew
SUBS390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-12 08:00 | 2022-10-04 16:00 | 2022-09-12 08:00 | 2022-10-04 16:00 | 2 | 17 | 0 |  |  | Substructure Crew
SUBS320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-11-15 08:00 | 2022-11-16 16:00 |  |  | 2 | 0 | 2 | 23 |  | Substructure Crew
B3750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-01 08:00 | 2022-12-07 16:00 |  |  | 7 | 0 | 7 | 13
B3760 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-10-14 08:00 | 2022-11-17 16:00 | 2022-10-14 08:00 |  | 7 | 30 | 5 | 33
B3770 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-07-15 08:00 | 2022-07-15 16:00 | 2022-07-15 08:00 | 2022-07-15 16:00 | 3 | 1 | 0
SUBS480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-08 08:00 | 2022-12-09 16:00 |  |  | 2 | 0 | 2 | 9 |  | Substructure Crew
SUBS490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-11-18 08:00 | 2022-11-21 16:00 |  |  | 2 | 0 | 2 | 20 |  | Substructure Crew
SUBS440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-05 08:00 | 2022-09-08 16:00 | 2022-09-05 08:00 | 2022-09-08 16:00 | 2 | 3 | 0 |  |  | Substructure Crew
B3810 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2022-05-14 08:00 | 2022-05-14 16:00 | 3 | 1 | 0
B3820 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-06-13 08:00 | 2022-06-14 16:00 | 2022-06-13 08:00 | 2022-06-14 16:00 | 3 | 2 | 0
B3830 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-11-13 08:00 | 2022-11-15 16:00 |  |  | 3 | 0 | 3 | 77
SUBS510 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-05-16 08:00 | 2022-05-18 16:00 | 2022-05-16 08:00 | 2022-05-18 16:00 | 2 | 3 | 0 |  |  | Substructure Crew
SUBS520 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 45 |  | Substructure Crew
B3870 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-12-22 08:00 | 2022-12-28 16:00 |  |  | 7 | 0 | 7 | 34
B3880 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-12-02 08:00 | 2022-12-08 16:00 |  |  | 7 | 0 | 7 | 54
B3890 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-11-13 08:00 | 2022-11-15 16:00 |  |  | 3 | 0 | 3 | 77
SUBS580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-03 08:00 | 2023-01-04 16:00 |  |  | 2 | 0 | 2 | 20 |  | Substructure Crew
SUBS590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-12-09 08:00 | 2022-12-12 16:00 |  |  | 2 | 0 | 2 | 31 |  | Substructure Crew
SUBS530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 45 |  | Substructure Crew
B3930 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-08-26 08:00 | 2022-08-28 16:00 | 2022-08-26 08:00 | 2022-08-28 16:00 | 3 | 3 | 0
B3940 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-02 08:00 | 2022-09-04 16:00 | 2022-09-02 08:00 | 2022-09-04 16:00 | 3 | 3 | 0
B3950 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-18 08:00 | 2022-09-20 16:00 | 2022-09-18 08:00 | 2022-09-20 16:00 | 3 | 3 | 0
SUBS600 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-08-29 08:00 | 2022-08-30 16:00 | 2022-08-29 08:00 | 2022-08-30 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS610 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-06 08:00 | 2022-09-07 16:00 | 2022-09-06 08:00 | 2022-09-07 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS690 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-21 08:00 | 2022-09-22 16:00 | 2022-09-21 08:00 | 2022-09-22 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
B3990 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-03 08:00 | 2022-09-09 16:00 | 2022-09-03 08:00 | 2022-09-09 16:00 | 7 | 7 | 0
B4000 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-13 08:00 | 2022-09-19 16:00 | 2022-09-13 08:00 | 2022-09-19 16:00 | 7 | 7 | 0
B4010 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-20 08:00 | 2022-09-22 16:00 | 2022-09-20 08:00 | 2022-09-22 16:00 | 3 | 3 | 0
SUBS650 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-12 08:00 | 2022-09-13 16:00 | 2022-09-12 08:00 | 2022-09-13 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS660 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-20 08:00 | 2022-09-22 16:00 | 2022-09-20 08:00 | 2022-09-22 16:00 | 2 | 3 | 0 |  |  | Substructure Crew
SUBS840 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-09-23 08:00 | 2022-09-26 16:00 | 2022-09-23 08:00 | 2022-09-26 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
B4050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-29 08:00 | 2022-12-01 16:00 |  |  | 3 | 0 | 3 | 77
B4060 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-08-30 08:00 | 2022-09-01 16:00 | 2022-08-30 08:00 | 2022-09-01 16:00 | 3 | 3 | 0
B4070 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-16 08:00 | 2022-12-18 16:00 |  |  | 3 | 0 | 3 | 81
B4080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-10 08:00 | 2022-12-12 16:00 |  |  | 3 | 0 | 3 | 108
SUBS710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-02 08:00 | 2022-12-05 16:00 |  |  | 2 | 0 | 2 | 48 |  | Substructure Crew
SUBS740 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-09-02 08:00 | 2022-09-02 16:00 | 2022-09-02 08:00 | 2022-09-02 16:00 | 2 | 0 | 0 |  |  | Substructure Crew
SUBS770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-19 08:00 | 2022-12-20 16:00 |  |  | 2 | 0 | 2 | 52 |  | Substructure Crew
SUBS750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-13 08:00 | 2022-12-14 16:00 |  |  | 2 | 0 | 2 | 71 |  | Substructure Crew
B4130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-16 08:00 | 2022-12-22 16:00 |  |  | 7 | 0 | 7 | 77
B4140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-13 08:00 | 2022-11-19 16:00 |  |  | 7 | 0 | 7 | 101
B4150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-14 08:00 | 2023-01-20 16:00 |  |  | 7 | 0 | 7 | 69
B4160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-23 08:00 | 2022-12-25 16:00 |  |  | 3 | 0 | 3 | 95
SUBS780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-23 08:00 | 2023-01-03 16:00 |  |  | 2 | 0 | 2 | 48 |  | Substructure Crew
SUBS830 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-21 08:00 | 2022-11-22 16:00 |  |  | 2 | 0 | 2 | 62 |  | Substructure Crew
SUBS870 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-23 08:00 | 2023-01-24 16:00 |  |  | 2 | 0 | 2 | 49 |  | Substructure Crew
SUBS920 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-03 08:00 | 2023-01-04 16:00 |  |  | 2 | 0 | 2 | 62 |  | Substructure Crew
B4210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-29 08:00 | 2022-12-01 16:00 |  |  | 3 | 0 | 3 | 89
B4220 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-08-30 08:00 | 2022-09-01 16:00 | 2022-08-30 08:00 | 2022-09-01 16:00 | 3 | 3 | 0
B4230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-16 08:00 | 2022-12-18 16:00 |  |  | 3 | 0 | 3 | 93
B4240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-04 08:00 | 2023-01-06 16:00 |  |  | 3 | 0 | 3 | 102
SUBS860 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-02 08:00 | 2022-12-05 16:00 |  |  | 2 | 0 | 2 | 56 |  | Substructure Crew
SUBS880 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-09-01 08:00 | 2022-09-02 16:00 | 2022-09-01 08:00 | 2022-09-02 16:00 | 2 | 1 | 0 |  |  | Substructure Crew
SUBS940 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-19 08:00 | 2022-12-20 16:00 |  |  | 2 | 0 | 2 | 60 |  | Substructure Crew
SUBS1250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-09 08:00 | 2023-01-10 16:00 |  |  | 2 | 0 | 2 | 71 |  | Substructure Crew
B4290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-16 08:00 | 2022-12-22 16:00 |  |  | 7 | 0 | 7 | 89
B4300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-10-10 08:00 | 2022-10-15 16:00 | 2022-10-10 08:00 | 2022-10-15 16:00 | 7 | 6 | 0
B4310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-14 08:00 | 2023-01-20 16:00 |  |  | 7 | 0 | 7 | 88
B4320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-27 08:00 | 2023-01-29 16:00 |  |  | 3 | 0 | 3 | 79
SUBS960 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-12-23 08:00 | 2023-01-03 16:00 |  |  | 2 | 0 | 2 | 56 |  | Substructure Crew
SUBS990 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 102 |  | Substructure Crew
SUBS1040 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-23 08:00 | 2023-01-24 16:00 |  |  | 2 | 0 | 2 | 62 |  | Substructure Crew
SUBS1240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-30 08:00 | 2023-01-31 16:00 |  |  | 2 | 0 | 2 | 57 |  | Substructure Crew
B4370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-07-25 08:00 | 2022-07-27 16:00 | 2022-07-25 08:00 | 2022-07-27 16:00 | 3 | 3 | 0
B4380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-07-22 08:00 | 2022-07-25 16:00 | 2022-07-22 08:00 | 2022-07-25 16:00 | 3 | 4 | 0
B4390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-04 08:00 | 2023-05-06 16:00 |  |  | 3 | 0 | 3 | 50
SUBS970 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-07-27 08:00 | 2022-07-28 16:00 | 2022-07-27 08:00 | 2022-07-28 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 134 |  | Substructure Crew
SUBS1300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-08 08:00 | 2023-05-09 16:00 |  |  | 2 | 0 | 2 | 34 |  | Substructure Crew
B4430 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-09-15 08:00 | 2022-09-21 16:00 | 2022-09-15 08:00 | 2022-09-21 16:00 | 7 | 7 | 0
B4440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-02-04 08:00 | 2023-02-10 16:00 |  |  | 7 | 0 | 7 | 135
B4450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-11-19 08:00 | 2022-11-21 16:00 |  |  | 3 | 0 | 3 | 216
SUBS1060 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-09-22 08:00 | 2022-09-23 16:00 | 2022-09-22 08:00 | 2022-09-23 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS1100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-02-13 08:00 | 2023-02-14 16:00 |  |  | 2 | 0 | 2 | 94 |  | Substructure Crew
SUBS1270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-04-24 08:00 | 2023-04-25 16:00 |  |  | 2 | 0 | 2 | 44 |  | Substructure Crew
B4490 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-06-11 08:00 | 2022-06-11 16:00 | 2022-06-11 08:00 | 2022-06-11 16:00 | 3 | 1 | 0
B4500 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-07-11 08:00 | 2022-07-13 16:00 | 2022-07-11 08:00 | 2022-07-13 16:00 | 3 | 3 | 0
B4510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-11-13 08:00 | 2022-11-15 16:00 |  |  | 3 | 0 | 3 | 239
SUBS1070 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-06-09 08:00 | 2022-06-11 16:00 | 2022-06-09 08:00 | 2022-06-11 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS1080 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-06-09 08:00 | 2022-06-13 16:00 | 2022-06-09 08:00 | 2022-06-13 16:00 | 2 | 3 | 0 |  |  | Substructure Crew
SUBS1350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 159 |  | Substructure Crew
B4550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-12-01 08:00 | 2022-12-07 16:00 |  |  | 7 | 0 | 7 | 210
B4560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-03-01 08:00 | 2023-03-07 16:00 |  |  | 7 | 0 | 7 | 134
B4570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-11-13 08:00 | 2022-11-15 16:00 |  |  | 3 | 0 | 3 | 246
SUBS1160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-12-08 08:00 | 2022-12-09 16:00 |  |  | 2 | 0 | 2 | 141 |  | Substructure Crew
SUBS1180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-03-08 08:00 | 2023-03-09 16:00 |  |  | 2 | 0 | 2 | 94 |  | Substructure Crew
SUBS1310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 164 |  | Substructure Crew
B4610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 2022-12-01 08:00 | 2022-12-03 16:00 |  |  | 3 | 0 | 3 | 214
B4620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 2022-10-14 08:00 | 2022-10-16 16:00 | 2022-10-14 08:00 | 2022-10-16 16:00 | 3 | 3 | 0
B4630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 2022-11-30 08:00 | 2022-12-02 16:00 |  |  | 3 | 0 | 3 | 236
SUBS1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 2022-12-05 08:00 | 2022-12-06 16:00 |  |  | 2 | 0 | 2 | 144 |  | Substructure Crew
SUBS1150 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 2022-10-17 08:00 | 2022-10-17 16:00 | 2022-10-17 08:00 | 2022-10-17 16:00 | 2 | 1 | 0 |  |  | Substructure Crew
SUBS1370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 2022-12-05 08:00 | 2022-12-06 16:00 |  |  | 2 | 0 | 2 | 159 |  | Substructure Crew
B4670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 2022-12-22 08:00 | 2022-12-28 16:00 |  |  | 7 | 0 | 7 | 210
B4680 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | 2022-10-22 08:00 | 2022-10-28 16:00 | 2022-10-22 08:00 | 2022-10-28 16:00 | 7 | 7 | 0
B4690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 2022-11-14 08:00 | 2022-11-16 16:00 |  |  | 3 | 0 | 3 | 252
SUBS1200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 2023-01-03 08:00 | 2023-01-04 16:00 |  |  | 2 | 0 | 2 | 144 |  | Substructure Crew
SUBS1210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2 | 2 | 0 |  |  | Substructure Crew
SUBS1340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 2022-11-17 08:00 | 2022-11-18 16:00 |  |  | 2 | 0 | 2 | 168 |  | Substructure Crew
UDR160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Edgedrain - NB: 757+10-759+97 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-28 16:00 |  |  | 7 | 0 | 7 | -2 | 1 | Underdrain Crew
BASE280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Shoulder Base - NB: 757+10-759+97 - Ph1-S1 | 2023-03-29 08:00 | 2023-04-06 16:00 |  |  | 7 | 0 | 7 | -2 | 1 | Agg Base Crew
UDR170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Edgedrain - NB: 761+67-767+00 - Ph1-S1 | 2023-03-29 08:00 | 2023-04-06 16:00 |  |  | 7 | 0 | 7 | 9 |  | Underdrain Crew
BASE290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Shoulder Base - NB: 761+67-767+00 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-18 16:00 |  |  | 8 | 0 | 8 | 9 |  | Agg Base Crew
UDR180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Edgedrain - NB: 767+00-773+42 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-17 16:00 |  |  | 7 | 0 | 7 | 9 |  | Underdrain Crew
BASE300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Shoulder Base - NB: 767+00-773+42 - Ph1-S1 | 2023-04-18 08:00 | 2023-04-27 16:00 |  |  | 8 | 0 | 8 | 9 |  | Agg Base Crew
UDR190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Edgedrain - NB: 774+82-780+00 - Ph1-S1 | 2023-04-18 08:00 | 2023-04-26 16:00 |  |  | 7 | 0 | 7 | 15 |  | Underdrain Crew
BASE330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Shoulder Base - NB: 774+82-780+00 - Ph1-S1 | 2023-04-27 08:00 | 2023-05-05 16:00 |  |  | 7 | 0 | 7 | 17 |  | Agg Base Crew
UDR200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Edgedrain - NB: 780+00-786+69 - Ph1-S1 | 2023-04-27 08:00 | 2023-05-05 16:00 |  |  | 7 | 0 | 7 | 15 |  | Underdrain Crew
BASE360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Shoulder Base - NB: 780+00-786+69 - Ph1-S1 | 2023-05-08 08:00 | 2023-05-16 16:00 |  |  | 7 | 0 | 7 | 15 |  | Agg Base Crew
UDR220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Edgedrain - NB: 788+09-800+00 - Ph1-S1 | 2023-05-15 08:00 | 2023-05-18 16:00 |  |  | 4 | 0 | 4 | 12 |  | Underdrain Crew
BASE380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Shoulder Base - NB: 788+09-800+00 - Ph1-S1 | 2023-05-19 08:00 | 2023-05-30 16:00 |  |  | 7 | 0 | 7 | 12 |  | Agg Base Crew
UDR240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Edgedrain - NB: 800+00-813+16 - Ph1-S1 | 2023-05-31 08:00 | 2023-06-08 16:00 |  |  | 7 | 0 | 7 | 12 |  | Underdrain Crew
BASE420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Shoulder Base - NB: 800+00-813+16 - Ph1-S1 | 2023-06-09 08:00 | 2023-06-19 16:00 |  |  | 7 | 0 | 7 | 12 |  | Agg Base Crew
UDR250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 815+20-827+00 - Ph1-S1 | 2023-06-26 08:00 | 2023-07-05 16:00 |  |  | 7 | 0 | 7 | 14 |  | Underdrain Crew
BASE440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Shoulder Base - NB: 815+20-827+00 - Ph1-S1 | 2023-07-06 08:00 | 2023-07-13 16:00 |  |  | 6 | 0 | 6 | 14 |  | Agg Base Crew
UDR270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 827+00-839+61 - Ph1-S1 | 2023-07-12 08:00 | 2023-07-20 16:00 |  |  | 7 | 0 | 7 | 13 |  | Underdrain Crew
BASE460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Shoulder Base - NB: 827+00-839+61 - Ph1-S1 | 2023-07-21 08:00 | 2023-07-28 16:00 |  |  | 6 | 0 | 6 | 13 |  | Agg Base Crew
UDR290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - SB: 815+20-839+61 - Ph1-S1 | 2023-07-25 08:00 | 2023-08-02 16:00 |  |  | 7 | 0 | 7 | 16 |  | Underdrain Crew
BASE510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Shoulder Base - SB: 815+20-839+61 - Ph1-S1 | 2023-08-03 08:00 | 2023-08-10 16:00 |  |  | 6 | 0 | 6 | 16 |  | Agg Base Crew
UDR300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Edgedrain - SB: 800+00-813+16 - Ph1-S1 | 2023-08-09 08:00 | 2023-08-17 16:00 |  |  | 7 | 0 | 7 | 19 |  | Underdrain Crew
BASE520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Shoulder Base - SB: 800+00-813+16 - Ph1-S1 | 2023-08-18 08:00 | 2023-08-24 16:00 |  |  | 5 | 0 | 5 | 19 |  | Agg Base Crew
UDR310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Edgedrain - SB: 788+09-800+00 - Ph1-S1 | 2023-08-21 08:00 | 2023-08-29 16:00 |  |  | 7 | 0 | 7 | 20 |  | Underdrain Crew
BASE590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Shoulder Base - SB: 788+09-800+00 - Ph1-S1 | 2023-08-30 08:00 | 2023-09-07 16:00 |  |  | 5 | 0 | 5 | 20 |  | Agg Base Crew
UDR320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Edgedrain - SB: 780+00-786+69 - Ph1-S1 | 2023-09-25 08:00 | 2023-10-02 16:00 |  |  | 6 | 0 | 6 | 11 |  | Underdrain Crew
BASE600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Shoulder Base - SB: 780+00-786+69 - Ph1-S1 | 2023-10-03 08:00 | 2023-10-09 16:00 |  |  | 5 | 0 | 5 | 11 |  | Agg Base Crew
UDR330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Edgedrain - SB: 774+82-780+00 - Ph1-S1 | 2023-10-03 08:00 | 2023-10-10 16:00 |  |  | 6 | 0 | 6 | 17 |  | Underdrain Crew
BASE620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Shoulder Base - SB: 774+82-780+00 - Ph1-S1 | 2023-10-11 08:00 | 2023-10-17 16:00 |  |  | 5 | 0 | 5 | 17 |  | Agg Base Crew
UDR350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Edgedrain - SB: 767+00-773+42 - Ph1-S1 | 2023-10-11 08:00 | 2023-10-18 16:00 |  |  | 6 | 0 | 6 | 18 |  | Underdrain Crew
BASE650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Shoulder Base - SB: 767+00-773+42 - Ph1-S1 | 2023-10-19 08:00 | 2023-10-25 16:00 |  |  | 5 | 0 | 5 | 18 |  | Agg Base Crew
UDR360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Edgedrain - SB: 761+67-767+00 - Ph1-S1 | 2023-10-26 08:00 | 2023-11-02 16:00 |  |  | 6 | 0 | 6 | 14 |  | Underdrain Crew
BASE680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Shoulder Base - SB: 761+67-767+00 - Ph1-S1 | 2023-11-03 08:00 | 2023-11-09 16:00 |  |  | 5 | 0 | 5 | 14 |  | Agg Base Crew
UDR380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Edgedrain - SB: 757+10-759+97 - Ph1-S1 | 2023-10-30 08:00 | 2023-11-06 16:00 |  |  | 6 | 0 | 6 | 6 |  | Underdrain Crew
BASE690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Shoulder Base - SB: 757+10-759+97 - Ph1-S1 | 2023-11-07 08:00 | 2023-11-14 16:00 |  |  | 5 | 0 | 5 | 7 |  | Agg Base Crew
CP600 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | 2024-10-11 08:00 | 2024-10-18 16:00 |  |  | 6 | 0 | 6 | -4 | 1 | Concrete Paving Crews
UDR470 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Install Edgedrain - NB & SB Median: 757+10-759+97 - Ph2 | 2024-09-26 08:00 | 2024-09-27 16:00 |  |  | 2 | 0 | 2 | -1 | 16 | Underdrain Crew
BASE860 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Shoulder Base - NB & SB Median: 757+10-759+97 - Ph2 | 2024-10-02 08:00 | 2024-10-09 16:00 |  |  | 6 | 0 | 6 | -3 | 8 | Agg Base Crew
CP620 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | 2024-10-22 08:00 | 2024-10-29 16:00 |  |  | 6 | 0 | 6 | 8 |  | Concrete Paving Crews
CP640 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | 2024-10-31 08:00 | 2024-11-07 16:00 |  |  | 6 | 0 | 6 | 7 |  | Concrete Paving Crews
CP660 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | 2024-11-12 08:00 | 2024-11-19 16:00 |  |  | 6 | 0 | 6 | 6 |  | Concrete Paving Crews
CP680 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 780+00-786+69 - Ph2 | 2024-11-21 08:00 | 2024-12-03 16:00 |  |  | 6 | 0 | 6 | 5 |  | Concrete Paving Crews
CP690 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | 2024-12-06 08:00 | 2024-12-13 16:00 |  |  | 6 | 0 | 6 | 3 |  | Concrete Paving Crews
CP710 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 800+00-813+16 - Ph2 | 2024-12-16 08:00 | 2024-12-23 16:00 |  |  | 6 | 0 | 6 | 3 |  | Concrete Paving Crews
CP720 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Shoulder - NB & SB Median: 815+20-839+61 - Ph2 | 2025-01-08 08:00 | 2025-01-15 16:00 |  |  | 6 | 0 | 6 | 4 |  | Concrete Paving Crews
UDR480 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Edgedrain - NB & SB Median: 761+67-767+00 - Ph2 | 2024-10-07 08:00 | 2024-10-11 16:00 |  |  | 5 | 0 | 5 | 8 |  | Underdrain Crew
BASE880 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Shoulder Base - NB & SB Median: 761+67-767+00 - Ph2 | 2024-10-14 08:00 | 2024-10-21 16:00 |  |  | 6 | 0 | 6 | 8 |  | Agg Base Crew
UDR490 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Edgedrain - NB & SB Median: 767+00-773+42 - Ph2 | 2024-10-16 08:00 | 2024-10-22 16:00 |  |  | 5 | 0 | 5 | 7 |  | Underdrain Crew
BASE890 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Shoulder Base - NB & SB Median: 767+00-773+42 - Ph2 | 2024-10-23 08:00 | 2024-10-30 16:00 |  |  | 6 | 0 | 6 | 7 |  | Agg Base Crew
UDR500 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Edgedrain - NB & SB Median: 774+82-780+00 - Ph2 | 2024-10-25 08:00 | 2024-10-31 16:00 |  |  | 5 | 0 | 5 | 6 |  | Underdrain Crew
BASE900 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Shoulder Base - NB & SB Median: 774+82-780+00 - Ph2 | 2024-11-01 08:00 | 2024-11-08 16:00 |  |  | 6 | 0 | 6 | 6 |  | Agg Base Crew
UDR510 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Edgedrain - NB & SB Median: 780+00-786+69 - Ph2 | 2024-11-05 08:00 | 2024-11-12 16:00 |  |  | 5 | 0 | 5 | 5 |  | Underdrain Crew
BASE920 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Shoulder Base - NB & SB Median: 780+00-786+69 - Ph2 | 2024-11-13 08:00 | 2024-11-20 16:00 |  |  | 6 | 0 | 6 | 5 |  | Agg Base Crew
UDR520 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Edgedrain - NB & SB Median: 788+09-800+00 - Ph2 | 2024-11-18 08:00 | 2024-11-22 16:00 |  |  | 5 | 0 | 5 | 3 |  | Underdrain Crew
BASE930 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Shoulder Base - NB & SB Median: 788+09-800+00 - Ph2 | 2024-11-25 08:00 | 2024-12-05 16:00 |  |  | 6 | 0 | 6 | 3 |  | Agg Base Crew
UDR530 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Edgedrain - NB & SB Median: 800+00-813+16 - Ph2 | 2024-12-02 08:00 | 2024-12-03 16:00 |  |  | 2 | 0 | 2 | 5 |  | Underdrain Crew
BASE940 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Shoulder Base - NB & SB Median: 800+00-813+16 - Ph2 | 2024-12-04 08:00 | 2024-12-11 16:00 |  |  | 6 | 0 | 6 | 5 |  | Agg Base Crew
UDR540 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Install Edgedrain - NB & SB Median: 815+20-839+61 - Ph2 | 2024-12-13 08:00 | 2024-12-19 16:00 |  |  | 5 | 0 | 5 | 4 |  | Underdrain Crew
BASE950 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Shoulder Base - NB & SB Median: 815+20-839+61 - Ph2 | 2024-12-20 08:00 | 2025-01-07 16:00 |  |  | 5 | 0 | 5 | 4 |  | Agg Base Crew
EPM100 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Erosion Protection Mat - NB: 737 - 739 - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 36 |  | Sub - Landscape Crew
LSP100 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Grassing - NB: 737 - 739 - IPh1 | 2022-11-15 08:00 | 2022-11-15 16:00 |  |  | 1 | 0 | 1 | 37 |  | Sub - Landscape Crew
EPM110 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 2022-11-15 08:00 | 2022-11-16 16:00 |  |  | 2 | 0 | 2 | 36 |  | Sub - Landscape Crew
LSP110 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Grassing - NB: 801 - 805 - IPh1 | 2022-11-17 08:00 | 2022-11-28 16:00 |  |  | 5 | 0 | 5 | 36 |  | Sub - Landscape Crew
EPM120 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | 2022-11-17 08:00 | 2022-11-18 16:00 |  |  | 2 | 0 | 2 | 39 |  | Sub - Landscape Crew
LSP120 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Grassing: NB - NB: 815 - 818 - IPh1 | 2022-11-29 08:00 | 2022-12-05 16:00 |  |  | 5 | 0 | 5 | 36 |  | Sub - Landscape Crew
EPM130 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | 2022-12-05 08:00 | 2022-12-06 16:00 |  |  | 2 | 0 | 2 | 35 |  | Sub - Landscape Crew
LSP130 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Grassing - SB: 835 - 840 - IPh1 | 2022-12-07 08:00 | 2022-12-13 16:00 |  |  | 5 | 0 | 5 | 35 |  | Sub - Landscape Crew
EPM140 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 2022-12-07 08:00 | 2022-12-08 16:00 |  |  | 2 | 0 | 2 | 38 |  | Sub - Landscape Crew
LSP140 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Grassing - SB: 823 - 827 - IPh1 | 2022-12-14 08:00 | 2022-12-20 16:00 |  |  | 5 | 0 | 5 | 35 |  | Sub - Landscape Crew
EPM150 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 2022-12-09 08:00 | 2022-12-12 16:00 |  |  | 2 | 0 | 2 | 41 |  | Sub - Landscape Crew
LSP150 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Grassing - SB: 801 - 805 - IPh 1 | 2022-12-21 08:00 | 2023-01-04 16:00 |  |  | 5 | 0 | 5 | 35 |  | Sub - Landscape Crew
EPM160 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 2022-12-23 08:00 | 2022-12-23 16:00 |  |  | 1 | 0 | 1 | 37 |  | Sub - Landscape Crew
LSP160 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Grassing - SB: 777 - 781 - IPh1 | 2023-01-05 08:00 | 2023-01-09 16:00 |  |  | 3 | 0 | 3 | 35 |  | Sub - Landscape Crew
EPM170 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 2023-01-18 08:00 | 2023-01-18 16:00 |  |  | 1 | 0 | 1 | 29 |  | Sub - Landscape Crew
LSP170 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Grassing - SB: 769 - 772 - IPh1 | 2023-01-19 08:00 | 2023-01-23 16:00 |  |  | 3 | 0 | 3 | 29 |  | Sub - Landscape Crew
EPM180 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.6 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Erosion Protection Mat - SB: 748 - 751 - IPh1 | 2023-01-30 08:00 | 2023-01-31 16:00 |  |  | 2 | 0 | 2 | 23 |  | Sub - Landscape Crew
LSP180 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.6 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Grassing - SB: 748 - 751 - IPh1 | 2023-02-01 08:00 | 2023-02-07 16:00 |  |  | 5 | 0 | 5 | 23 |  | Sub - Landscape Crew
DEMO130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Roadway - NB: 722+83-735+00 - Ph1-S1 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 5 | 14 | 0 |  |  | Demolition Crews
DEMO210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | 2022-02-22 08:00 | 2022-03-18 16:00 | 2022-02-22 08:00 | 2022-03-18 16:00 | 3 | 19 | 0 |  |  | Demolition Crews
DEMO290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - NB: 748+30-757+10 - Ph1-S1 | 2022-02-17 08:00 | 2022-05-14 16:00 | 2022-02-17 08:00 | 2022-05-14 16:00 | 5 | 62 | 0 |  |  | Demolition Crews
DEMO320 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Demo Roadway - NB: 757+10-759+97 - Ph1-S1 | 2022-05-09 08:00 | 2022-05-13 16:00 | 2022-05-09 08:00 | 2022-05-13 16:00 | 5 | 5 | 0 |  |  | Demolition Crews
DEMO360 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | 2022-03-09 08:00 | 2022-03-11 16:00 | 2022-03-09 08:00 | 2022-03-11 16:00 | 5 | 3 | 0 |  |  | Demolition Crews
DEMO420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | 2022-03-17 08:00 | 2022-03-18 16:00 | 2022-03-17 08:00 | 2022-03-18 16:00 | 5 | 2 | 0 |  |  | Demolition Crews
DEMO470 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - NB: 774+82-780+00 - Ph1-S1 | 2022-03-16 08:00 | 2022-05-14 16:00 | 2022-03-16 08:00 | 2022-05-14 16:00 | 5 | 43 | 0 |  |  | Demolition Crews
DEMO520 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - NB: 780+00-786+69 - Ph1-S1 | 2022-03-14 08:00 | 2022-03-18 16:00 | 2022-03-14 08:00 | 2022-03-18 16:00 | 5 | 5 | 0 |  |  | Demolition Crews
DEMO580 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Roadway - NB: 788+09-800+00 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2022-07-11 08:00 | 2022-07-14 16:00 | 5 | 4 | 0 |  |  | Demolition Crews
DEMO630 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-13 16:00 | 2022-07-11 08:00 | 2022-07-13 16:00 | 5 | 3 | 0 |  |  | Demolition Crews
DEMO660 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2022-07-11 08:00 | 2022-07-14 16:00 | 7 | 4 | 0 |  |  | Demolition Crews
DEMO720 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | 2022-08-01 08:00 | 2022-08-12 16:00 | 2022-08-01 08:00 | 2022-08-12 16:00 | 7 | 10 | 0 |  |  | Demolition Crews
DEMO790 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | 2022-11-01 08:00 | 2022-11-09 16:00 | 2022-11-01 08:00 | 2022-11-09 16:00 | 7 | 7 | 0 |  |  | Demolition Crews
DEMO850 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Roadway - SB: 788+09-800+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-22 16:00 |  |  | 7 | 0 | 7 | 39 |  | Demolition Crews
DEMO910 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - SB: 780+00-786+69 - Ph1-S1 | 2022-08-03 08:00 | 2022-08-09 16:00 | 2022-08-03 08:00 | 2022-08-09 16:00 | 5 | 5 | 0 |  |  | Demolition Crews
DEMO960 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - SB: 774+82-780+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 54 |  | Demolition Crews
DEMO1040 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | 2022-12-12 08:00 | 2022-12-16 16:00 |  |  | 5 | 0 | 5 | 42 |  | Demolition Crews
DEMO1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - SB: 761+67-767+00 - Ph1-S1 | 2022-12-19 08:00 | 2022-12-23 16:00 |  |  | 5 | 0 | 5 | 43 |  | Demolition Crews
DEMO1180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Demo Roadway - SB: 757+10-759+97 - Ph1-S1 | 2023-02-08 08:00 | 2023-02-14 16:00 |  |  | 5 | 0 | 5 | 23 |  | Demolition Crews
DEMO1220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | 2023-02-15 08:00 | 2023-02-21 16:00 |  |  | 5 | 0 | 5 | 23 |  | Demolition Crews
DEMO1250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | 2023-02-22 08:00 | 2023-03-01 16:00 |  |  | 6 | 0 | 6 | 23 |  | Demolition Crews
DEMO1300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Demo Roadway - SB: 722+83-735+00 - Ph1-S1 | 2023-03-02 08:00 | 2023-03-21 16:00 |  |  | 14 | 0 | 14 | 23 |  | Demolition Crews
DEMO1320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Demo Roadway - SB: 709+50-721+43 - Ph1-S1 | 2023-03-22 08:00 | 2023-04-07 16:00 |  |  | 13 | 0 | 13 | 23 |  | Demolition Crews
REINF100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Rebar 100201 - NB: over Floribraska - Ph1-S1 | 2022-12-01 08:00 | 2022-12-05 16:00 |  |  | 3 | 0 | 3 | -2 | 1 | Sub - Rebar Placement Crew
REINF110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Rebar 100207 - NB: over East Lake - Ph1-S1 | 2022-12-07 08:00 | 2022-12-12 16:00 |  |  | 4 | 0 | 4 | 5 |  | Sub - Rebar Placement Crew
REINF120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-01-06 08:00 | 2023-01-11 16:00 |  |  | 4 | 0 | 4 | 9 |  | Sub - Rebar Placement Crew
REINF130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-24 08:00 | 2023-01-27 16:00 |  |  | 4 | 0 | 4 | 20 |  | Sub - Rebar Placement Crew
REINF140 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-11-07 08:00 | 2022-11-17 16:00 | 2022-11-07 08:00 |  | 4 | 4 | 4 | 77 |  | Sub - Rebar Placement Crew
REINF150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-20 08:00 | 2023-02-23 16:00 |  |  | 4 | 0 | 4 | 49 |  | Sub - Rebar Placement Crew
REINF160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-02-28 08:00 | 2023-03-03 16:00 |  |  | 4 | 0 | 4 | 57 |  | Sub - Rebar Placement Crew
REINF170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-30 08:00 | 2023-06-02 16:00 |  |  | 4 | 0 | 4 | 34 |  | Sub - Rebar Placement Crew
REINF180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-06-05 08:00 | 2023-06-08 16:00 |  |  | 4 | 0 | 4 | 47 |  | Sub - Rebar Placement Crew
REINF190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100204 - SB: over MLK - Ph1-S1 | 2023-06-09 08:00 | 2023-06-14 16:00 |  |  | 4 | 0 | 4 | 47 |  | Sub - Rebar Placement Crew
PNT100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Paint 100201 - NB: over Floribraska - Ph1-S1 | 2024-04-18 21:00 | 2024-04-25 01:00 |  |  | 5 | 0 | 5 | 86 |  | Sub - Structure Painting Crew
PNT110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Paint 100207 - NB: over East Lake - Ph1-S1 | 2024-04-25 01:00 | 2024-05-01 05:00 |  |  | 5 | 0 | 5 | 86 |  | Sub - Structure Painting Crew
PNT120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | 2024-05-01 05:00 | 2024-05-08 |  |  | 5 | 0 | 5 | 86 |  | Sub - Structure Painting Crew
PNT130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | 2024-05-08 | 2024-05-14 04:00 |  |  | 5 | 0 | 5 | 86 |  | Sub - Structure Painting Crew
PNT140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2024-05-14 04:00 | 2024-05-20 23:00 |  |  | 5 | 0 | 5 | 86 |  | Sub - Structure Painting Crew
PNT150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2024-05-20 23:00 | 2024-05-31 |  |  | 8 | 0 | 8 | 86 |  | Sub - Structure Painting Crew
PNT160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2024-05-31 08:00 | 2024-06-11 16:00 |  |  | 8 | 0 | 8 | 76 |  | Sub - Structure Painting Crew
PNT170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2024-06-11 21:00 | 2024-06-20 22:00 |  |  | 8 | 0 | 8 | 86 |  | Sub - Structure Painting Crew
PNT180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 2024-06-20 22:00 | 2024-07-01 23:00 |  |  | 8 | 0 | 8 | 86 |  | Sub - Structure Painting Crew
PNT190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Paint 100204 - SB: over MLK - Ph1-S1 | 2024-07-01 23:00 | 2024-07-12 |  |  | 8 | 0 | 8 | 86 |  | Sub - Structure Painting Crew
PNT200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Paint 100207 - SB: over East Lake - Ph1-S1 | 2024-07-12 08:00 | 2024-07-23 16:00 |  |  | 8 | 0 | 8 | 76 |  | Sub - Structure Painting Crew
BW120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | 2022-09-09 08:00 | 2022-09-09 16:00 | 2022-09-09 08:00 | 2022-09-09 16:00 | 7 | 1 | 0 |  |  | Concrete Barrier Crew
NW100 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour 14' Noise Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | 2022-07-13 08:00 | 2022-11-17 16:00 | 2022-07-13 08:00 |  | 12 | 85 | 4 | 10 |  | Sound Wall Crew
BW200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | 2022-09-12 08:00 | 2022-10-14 16:00 | 2022-09-12 08:00 | 2022-10-14 16:00 | 8 | 25 | 0 |  |  | Concrete Barrier Crew
NW120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour 14' Noise Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | 2022-07-13 08:00 | 2022-08-19 16:00 | 2022-07-13 08:00 | 2022-08-19 16:00 | 12 | 28 | 0 |  |  | Sound Wall Crew
BW280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 7 |  | Concrete Barrier Crew
NW140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | 2022-11-21 08:00 | 2022-12-09 16:00 |  |  | 12 | 0 | 12 | 7 |  | Sound Wall Crew
BW330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | 2022-11-29 08:00 | 2022-12-05 16:00 |  |  | 5 | 0 | 5 | 20 |  | Concrete Barrier Crew
NW150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | 2022-12-06 08:00 | 2022-12-15 16:00 |  |  | 8 | 0 | 8 | 20 |  | Sound Wall Crew
BW390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | 2022-11-29 08:00 | 2022-12-06 16:00 |  |  | 6 | 0 | 6 | 10 |  | Concrete Barrier Crew
NW170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | 2022-12-07 08:00 | 2023-01-06 16:00 |  |  | 17 | 0 | 17 | 10 |  | Sound Wall Crew
BW420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | 2022-10-10 08:00 | 2022-10-14 16:00 | 2022-10-10 08:00 | 2022-10-14 16:00 | 4 | 5 | 0 |  |  | Concrete Barrier Crew
NW200 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | 2022-11-07 08:00 | 2022-11-30 16:00 | 2022-11-07 08:00 |  | 13 | 4 | 10 | 11 |  | Sound Wall Crew
BW450 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 2022-10-13 08:00 | 2022-11-21 16:00 | 2022-10-13 08:00 |  | 6 | 21 | 6 | 15 |  | Concrete Barrier Crew
NW230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 2022-12-01 08:00 | 2022-12-14 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sound Wall Crew
BW480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | 2022-12-02 08:00 | 2022-12-08 16:00 |  |  | 5 | 0 | 5 | 15 |  | Concrete Barrier Crew
NW260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | 2022-12-15 08:00 | 2022-12-23 16:00 |  |  | 7 | 0 | 7 | 11 |  | Sound Wall Crew
BW510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 2022-12-09 08:00 | 2022-12-15 16:00 |  |  | 5 | 0 | 5 | 17 |  | Concrete Barrier Crew
NW290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 2023-01-03 08:00 | 2023-01-17 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sound Wall Crew
BW550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | 2022-12-16 08:00 | 2022-12-22 16:00 |  |  | 5 | 0 | 5 | 22 |  | Concrete Barrier Crew
NW320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | 2023-01-18 08:00 | 2023-02-07 16:00 |  |  | 15 | 0 | 15 | 11 |  | Sound Wall Crew
BW580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 2023-02-15 08:00 | 2023-02-23 16:00 |  |  | 7 | 0 | 7 | 7 |  | Concrete Barrier Crew
NW340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 2023-02-17 08:00 | 2023-03-09 16:00 |  |  | 15 | 0 | 15 | 4 |  | Sound Wall Crew
BW610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 2023-03-03 08:00 | 2023-03-09 16:00 |  |  | 5 | 0 | 5 | 7 |  | Concrete Barrier Crew
NW360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 2023-03-17 08:00 | 2023-03-28 16:00 |  |  | 8 | 0 | 8 | 4 |  | Sound Wall Crew
BW640 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-24 16:00 |  |  | 5 | 0 | 5 | 6 |  | Concrete Barrier Crew
NW380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | 2023-03-29 08:00 | 2023-04-06 16:00 |  |  | 7 | 0 | 7 | 4 |  | Sound Wall Crew
BW690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 2023-04-03 08:00 | 2023-04-07 16:00 |  |  | 5 | 0 | 5 | 6 |  | Concrete Barrier Crew
NW410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 2023-04-12 08:00 | 2023-04-21 16:00 |  |  | 8 | 0 | 8 | 4 |  | Sound Wall Crew
BW750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 2023-04-10 08:00 | 2023-04-17 16:00 |  |  | 6 | 0 | 6 | 8 |  | Concrete Barrier Crew
NW450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 2023-04-24 08:00 | 2023-05-05 16:00 |  |  | 10 | 0 | 10 | 4 |  | Sound Wall Crew
BW780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 2023-04-25 08:00 | 2023-05-01 16:00 |  |  | 5 | 0 | 5 | 8 |  | Concrete Barrier Crew
NW470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 2023-05-08 08:00 | 2023-05-19 16:00 |  |  | 10 | 0 | 10 | 4 |  | Sound Wall Crew
BW810 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 2023-05-08 08:00 | 2023-05-11 16:00 |  |  | 4 | 0 | 4 | 8 |  | Concrete Barrier Crew
NW490 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 2023-05-22 08:00 | 2023-05-30 16:00 |  |  | 6 | 0 | 6 | 4 |  | Sound Wall Crew
BW870 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 2023-05-18 08:00 | 2023-05-23 16:00 |  |  | 4 | 0 | 4 | 8 |  | Concrete Barrier Crew
NW500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 2023-05-31 08:00 | 2023-06-02 16:00 |  |  | 3 | 0 | 3 | 4 |  | Sound Wall Crew
BW900 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 | Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 2023-05-31 08:00 | 2023-06-05 16:00 |  |  | 4 | 0 | 4 | 13 |  | Concrete Barrier Crew
NW540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 | Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 2023-06-30 08:00 | 2023-07-12 16:00 |  |  | 8 | 0 | 8 | -4 | 1 | Sound Wall Crew
BW960 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 2023-06-13 08:00 | 2023-06-19 16:00 |  |  | 5 | 0 | 5 | 27 |  | Concrete Barrier Crew
NW560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 2023-08-03 08:00 | 2023-08-17 16:00 |  |  | 11 | 0 | 11 | -4 | 1 | Sound Wall Crew
BW990 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 2023-06-22 08:00 | 2023-06-29 16:00 |  |  | 6 | 0 | 6 | 13 |  | Concrete Barrier Crew
NW600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 2023-08-18 08:00 | 2023-09-06 16:00 |  |  | 12 | 0 | 12 | -4 | 1 | Sound Wall Crew
BW1020 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 2023-07-07 08:00 | 2023-07-12 16:00 |  |  | 4 | 0 | 4 | 17 |  | Concrete Barrier Crew
NW630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 2023-09-07 08:00 | 2023-09-15 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sound Wall Crew
BW1080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | 2023-07-19 08:00 | 2023-07-31 16:00 |  |  | 9 | 0 | 9 | 13 |  | Concrete Barrier Crew
NW650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | 2023-09-18 08:00 | 2023-09-28 16:00 |  |  | 9 | 0 | 9 | -4 | 1 | Sound Wall Crew
BW1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | 2023-08-11 08:00 | 2023-08-23 16:00 |  |  | 9 | 0 | 9 | 13 |  | Concrete Barrier Crew
NW680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | 2023-09-29 08:00 | 2023-10-11 16:00 |  |  | 9 | 0 | 9 | -4 | 1 | Sound Wall Crew
BW170 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall - MLK Ramp B - Ph1-S2 | 2023-06-02 08:00 | 2023-06-14 16:00 |  |  | 9 | 0 | 9 | -4 | 1 | Concrete Barrier Crew
NW110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp B (NB: 250+88.27-256+15.55) - Ph1-S2 | 2023-06-15 08:00 | 2023-06-29 16:00 |  |  | 11 | 0 | 11 | -4 | 1 | Sound Wall Crew
BW220 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | 2023-06-19 08:00 | 2023-06-30 16:00 |  |  | 10 | 0 | 10 | 3 |  | Concrete Barrier Crew
NW130 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | 2023-07-13 08:00 | 2023-08-02 16:00 |  |  | 15 | 0 | 15 | -4 | 1 | Sound Wall Crew
BW360 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | 2023-08-15 08:00 | 2023-08-25 16:00 |  |  | 9 | 0 | 9 | 16 |  | Concrete Barrier Crew
NW180 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | 2023-10-20 08:00 | 2023-11-07 16:00 |  |  | 13 | 0 | 13 | -4 | 1 | Sound Wall Crew
BW680 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | 2023-09-11 08:00 | 2023-09-22 16:00 |  |  | 10 | 0 | 10 | 8 |  | Concrete Barrier Crew
NW530 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp C1 - Ph1-S2 | 2023-09-29 08:00 | 2023-10-12 16:00 |  |  | 10 | 0 | 10 | 4 |  | Sound Wall Crew
BW840 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | 2023-09-25 08:00 | 2023-10-06 16:00 |  |  | 10 | 0 | 10 | 8 |  | Concrete Barrier Crew
NW640 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp D - Ph1-S2 | 2023-10-13 08:00 | 2023-10-27 16:00 |  |  | 11 | 0 | 11 | 4 |  | Sound Wall Crew
BW930 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | 2023-12-08 08:00 | 2023-12-20 16:00 |  |  | 9 | 0 | 9 | 12 |  | Concrete Barrier Crew
NW690 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp A - Ph1-S2 | 2024-01-24 08:00 | 2024-02-07 16:00 |  |  | 11 | 0 | 11 | -4 | 1 | Sound Wall Crew
BW1050 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | 2024-01-31 08:00 | 2024-02-12 16:00 |  |  | 9 | 0 | 9 | -2 | 10 | Concrete Barrier Crew
NW750 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | 2024-02-15 08:00 | 2024-02-27 16:00 |  |  | 9 | 0 | 9 | -4 | 6 | Sound Wall Crew
BW1110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | 2024-02-14 08:00 | 2024-02-26 16:00 |  |  | 9 | 0 | 9 | -1 | 19 | Concrete Barrier Crew
NW770 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp A (SB: 107+11.78-104+50.80) - Ph1-S2 | 2024-02-28 08:00 | 2024-03-08 16:00 |  |  | 8 | 0 | 8 | -2 | 18 | Sound Wall Crew
BW1170 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Form / Reinforce / Pour Barrier Wall - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 2024-01-30 08:00 | 2024-02-06 16:00 |  |  | 6 | 0 | 6 | 5 |  | Concrete Barrier Crew
BW1190 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 714+00-721+43 - Ph2 | 2024-05-22 08:00 | 2024-05-29 16:00 |  |  | 5 | 0 | 5 | -1 |  | Concrete Barrier Crew
BW1210 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | 2024-07-10 08:00 | 2024-07-16 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Concrete Barrier Crew
BW1230 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-08-02 08:00 | 2024-08-09 16:00 |  |  | 6 | 0 | 6 | 2 |  | Concrete Barrier Crew
BW1250 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | 2024-08-21 08:00 | 2024-08-27 16:00 |  |  | 5 | 0 | 5 | 11 |  | Concrete Barrier Crew
BW1270 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | 2024-09-09 08:00 | 2024-09-13 16:00 |  |  | 5 | 0 | 5 | 10 |  | Concrete Barrier Crew
BW1290 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | 2024-10-02 08:00 | 2024-10-11 16:00 |  |  | 8 | 0 | 8 | 3 |  | Concrete Barrier Crew
BW1310 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall - NB & SB Median: 815+20-839+61 - Ph2 | 2024-10-24 08:00 | 2024-11-04 16:00 |  |  | 8 | 0 | 8 | 5 |  | Concrete Barrier Crew
R3930 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.1 | Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Erosion Protection Mat - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 2023-11-06 08:00 | 2023-11-09 16:00 |  |  | 4 | 0 | 4 | 13 |  | Sub - Landscape Crew
R3940 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.1 | Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Grassing - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 2023-11-13 08:00 | 2023-11-16 16:00 |  |  | 4 | 0 | 4 | 13 |  | Sub - Landscape Crew
PNT1000 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - NB: 709+50-735+00 - Ph1-S1 | 2024-08-22 08:00 | 2024-08-28 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - NB: 735+46-746+91 - Ph1-S1 | 2024-08-29 08:00 | 2024-09-06 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1020 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - NB: 748+30-757+10 - Ph1-S1 | 2024-09-09 08:00 | 2024-09-16 16:00 |  |  | 6 | 0 | 6 | 55 |  | Sub - Structure Painting Crew
PNT1030 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - NB: 757+10-759+97 - Ph1-S1 | 2024-09-17 08:00 | 2024-09-23 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1040 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - NB: 761+67-767+00 - Ph1-S1 | 2024-09-24 08:00 | 2024-09-30 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - NB: 767+00-773+42 - Ph1-S1 | 2024-10-01 08:00 | 2024-10-07 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1060 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - NB: 774+82-780+00 - Ph1-S1 | 2024-10-08 08:00 | 2024-10-15 16:00 |  |  | 6 | 0 | 6 | 55 |  | Sub - Structure Painting Crew
PNT1070 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - NB: 780+00-786+69 - Ph1-S1 | 2024-10-16 08:00 | 2024-10-22 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - NB: 788+09-800+00 - Ph1-S1 | 2024-10-23 08:00 | 2024-10-29 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1090 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - NB: 800+00-813+16 - Ph1-S1 | 2024-10-30 08:00 | 2024-11-05 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Paint - NB: 815+20-839+61 - Ph1-S1 | 2024-11-06 08:00 | 2024-11-14 16:00 |  |  | 6 | 0 | 6 | 55 |  | Sub - Structure Painting Crew
PNT1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Paint - SB: 815+20-839+61 - Ph1-S1 | 2024-11-15 08:00 | 2024-11-21 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - SB: 800+00-813+16 - Ph1-S1 | 2024-11-22 08:00 | 2024-12-03 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - SB: 788+09-800+00 - Ph1-S1 | 2024-12-04 08:00 | 2024-12-10 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - SB: 780+00-786+69 - Ph1-S1 | 2024-12-11 08:00 | 2024-12-17 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - SB: 774+82-780+00 - Ph1-S1 | 2024-12-18 08:00 | 2025-01-03 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - SB: 767+00-773+42 - Ph1-S1 | 2025-01-06 08:00 | 2025-01-10 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - SB: 761+67-767+00 - Ph1-S1 | 2025-01-13 08:00 | 2025-01-17 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - SB: 757+10-759+97 - Ph1-S1 | 2025-01-21 08:00 | 2025-01-27 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - SB: 748+30-757+10 - Ph1-S1 | 2025-01-28 08:00 | 2025-02-03 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - SB: 735+46-746+91 - Ph1-S1 | 2025-02-04 08:00 | 2025-02-07 16:00 |  |  | 4 | 0 | 4 | 55 |  | Sub - Structure Painting Crew
PNT1210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - SB: 722+83-735+00 - Ph1-S1 | 2025-02-10 08:00 | 2025-02-13 16:00 |  |  | 4 | 0 | 4 | 55 |  | Sub - Structure Painting Crew
PNT1220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - SB: 709+50-721+43 - Ph1-S1 | 2025-02-14 08:00 | 2025-02-19 16:00 |  |  | 4 | 0 | 4 | 55 |  | Sub - Structure Painting Crew
PNT1230 | Not Started | 3462-FDOT-Owner-12.4.P2.2 | Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Paint - NB & SB Median: 714+00-721+43 - Ph2 | 2024-11-21 08:00 | 2024-12-04 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Structure Painting Crew
PNT1240 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Paint - MLK Ramp B - Ph1-S2 | 2024-06-12 08:00 | 2024-06-18 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1250 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Paint - MLK Ramp C - Ph1-S2 | 2024-06-19 08:00 | 2024-06-25 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1260 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Paint - Hillsborough Ramp B - Ph1-S2 | 2024-06-26 08:00 | 2024-07-02 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1270 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Paint - Hillsborough Ramp C2 - Ph1-S2 | 2024-07-03 08:00 | 2024-07-10 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1280 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Paint - Hillsborough Ramp C1 - Ph1-S2 | 2024-07-11 08:00 | 2024-07-17 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1290 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Paint - Hillsborough Ramp D - Ph1-S2 | 2024-07-18 08:00 | 2024-07-24 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1300 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Paint - Hillsborough Ramp A - Ph1-S2 | 2024-07-25 08:00 | 2024-07-31 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1310 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Paint - MLK Ramp D - Ph1-S2 | 2024-08-01 08:00 | 2024-08-07 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1320 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Paint - MLK Ramp A - Ph1-S2 | 2024-08-08 08:00 | 2024-08-14 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1330 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Paint - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 2024-08-15 08:00 | 2024-08-21 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Structure Painting Crew
PNT1360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Paint @ Floribraska - South Side - Ph1-S1-S1 | 2024-04-18 08:00 | 2024-04-22 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Paint @ East Lake Ave. - South Side - Ph1-S1-S1 | 2024-04-23 08:00 | 2024-04-25 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Paint @ MLK Blvd.- South Side - Ph1-S1-S1 | 2024-04-26 08:00 | 2024-04-30 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Paint @ Chelsea St.- South Side - Ph1-S1-S1 | 2024-05-01 08:00 | 2024-05-03 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Paint @ E. Osborne Ave - South Side - Ph1-S1-S1 | 2024-05-06 08:00 | 2024-05-08 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Paint @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 2024-05-09 08:00 | 2024-05-14 16:00 |  |  | 4 | 0 | 4 | 55 |  | Sub - Structure Painting Crew
PNT1420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Paint @ Floribraska - North Side - Ph1-S1-S2 | 2024-05-15 08:00 | 2024-05-17 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Paint @ East Lake Ave. - North Side - Ph1-S1-S2 | 2024-05-20 08:00 | 2024-05-22 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Paint @ MLK Blvd.- North Side - Ph1-S1-S2 | 2024-05-23 08:00 | 2024-05-28 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Paint @ Chelsea St.- North Side - Ph1-S1-S2 | 2024-05-29 08:00 | 2024-05-31 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Paint @ E. Osborne Ave - North Side - Ph1-S1-S2 | 2024-06-03 08:00 | 2024-06-05 16:00 |  |  | 3 | 0 | 3 | 55 |  | Sub - Structure Painting Crew
PNT1470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Paint @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 2024-06-06 08:00 | 2024-06-11 16:00 |  |  | 4 | 0 | 4 | 55 |  | Sub - Structure Painting Crew
PNT1480 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Paint - NB & SB Median: 722+83-746+91 - Ph2 | 2024-12-05 08:00 | 2024-12-13 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Structure Painting Crew
PNT1490 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Paint - NB & SB Median: 748+30-759+97 - Ph 2 | 2024-12-16 08:00 | 2025-01-03 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Structure Painting Crew
PNT1500 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Paint - NB & SB Median: 761+67-773+42 - Ph2 | 2025-01-06 08:00 | 2025-01-14 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Structure Painting Crew
PNT1510 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Paint - NB & SB Median: 774+82-786+69 - Ph2 | 2025-01-15 08:00 | 2025-01-24 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Structure Painting Crew
PNT1520 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Paint - NB & SB Median: 788+09-813+16 - Ph2 | 2025-01-27 08:00 | 2025-02-04 16:00 |  |  | 7 | 0 | 7 | -4 | 1 | Sub - Structure Painting Crew
PNT1530 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Paint - NB & SB Median: 815+20-839+61 - Ph2 | 2025-02-05 08:00 | 2025-02-11 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sub - Structure Painting Crew
ITS100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 2023-04-20 08:00 | 2023-05-03 16:00 |  |  | 10 | 0 | 10 | 131 |  | Sub - ITS Installation Crew
ITS120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 2023-05-19 08:00 | 2023-06-02 16:00 |  |  | 10 | 0 | 10 | 120 |  | Sub - ITS Installation Crew
ITS200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 2023-09-14 08:00 | 2023-10-04 16:00 |  |  | 15 | 0 | 15 | 13 |  | Sub - ITS Installation Crew
ITS220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | 2023-10-11 08:00 | 2023-10-31 16:00 |  |  | 15 | 0 | 15 | 34 |  | Sub - ITS Installation Crew
ITS230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | 2023-10-30 08:00 | 2023-11-13 16:00 |  |  | 10 | 0 | 10 | 27 |  | Sub - ITS Installation Crew
ITS240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 2023-11-16 08:00 | 2023-12-11 16:00 |  |  | 15 | 0 | 15 | 21 |  | Sub - ITS Installation Crew
ITS260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | 2023-12-06 08:00 | 2023-12-19 16:00 |  |  | 10 | 0 | 10 | 15 |  | Sub - ITS Installation Crew
ITS290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | 2024-01-08 08:00 | 2024-01-24 16:00 |  |  | 12 | 0 | 12 | 12 |  | Sub - ITS Installation Crew
ITS310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 2024-01-26 08:00 | 2024-02-01 16:00 |  |  | 5 | 0 | 5 | 11 |  | Sub - ITS Installation Crew
MSE110 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 2022-08-01 08:00 | 2022-08-19 08:00 | 2022-08-01 08:00 | 2022-08-19 08:00 | 9 | 14 | 0 |  |  | Sub - MSE Wall Crew
MSE130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Coping - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-21 16:00 |  |  | 6 | 0 | 6 | 0 | 9 | Sub - MSE Wall Crew
NW160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 2022-11-28 08:00 | 2022-12-12 16:00 |  |  | 11 | 0 | 11 | 472 |  | Sound Wall Crew
MSE140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 | Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 2022-05-11 08:00 | 2022-06-27 16:00 | 2022-05-11 08:00 | 2022-06-27 16:00 | 5 | 33 | 0 |  |  | Sub - MSE Wall Crew
MSE160 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 | Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Coping - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 2022-06-14 08:00 | 2022-06-17 16:00 | 2022-06-14 08:00 | 2022-06-17 16:00 | 6 | 4 | 0 |  |  | Sub - MSE Wall Crew
NW190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 | Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 2022-12-01 08:00 | 2022-12-14 16:00 |  |  | 10 | 0 | 10 | 18 |  | Sound Wall Crew
MSE170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 | Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 2022-05-09 08:00 | 2022-06-03 16:00 | 2022-05-09 08:00 | 2022-06-03 16:00 | 15 | 19 | 0 |  |  | Sub - MSE Wall Crew
MSE200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 | Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Coping - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 2022-06-09 08:00 | 2022-06-20 16:00 | 2022-06-09 08:00 | 2022-06-20 16:00 | 6 | 8 | 0 |  |  | Sub - MSE Wall Crew
NW210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 | Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 2022-12-15 08:00 | 2023-01-04 16:00 |  |  | 9 | 0 | 9 | 18 |  | Sound Wall Crew
MSE220 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-07-04 08:00 | 2022-07-11 16:00 | 2022-07-04 08:00 | 2022-07-11 16:00 | 4 | 5 | 0 |  |  | Sub - MSE Wall Crew
MSE240 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Coping - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-07-27 08:00 | 2022-11-14 16:00 | 2022-07-27 08:00 |  | 5 | 75 | 1 | 7 |  | Sub - MSE Wall Crew
NW220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-11-28 08:00 | 2022-12-07 16:00 |  |  | 8 | 0 | 8 | 475 |  | Sound Wall Crew
MSE250 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-06-01 08:00 | 2022-06-01 16:00 | 2022-06-01 08:00 | 2022-06-01 16:00 | 3 | 1 | 0 |  |  | Sub - MSE Wall Crew
MSE280 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Coping - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-07-27 08:00 | 2022-09-17 16:00 | 2022-07-27 08:00 | 2022-09-17 16:00 | 6 | 36 | 0 |  |  | Sub - MSE Wall Crew
NW240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-22 16:00 |  |  | 7 | 0 | 7 | 7 |  | Sound Wall Crew
MSE290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 | Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 2022-07-04 08:00 | 2022-07-07 16:00 | 2022-07-04 08:00 | 2022-07-07 16:00 | 5 | 3 | 0 |  |  | Sub - MSE Wall Crew
MSE320 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 | Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Coping - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 2022-07-25 08:00 | 2022-07-28 16:00 | 2022-07-25 08:00 | 2022-07-28 16:00 | 6 | 4 | 0 |  |  | Sub - MSE Wall Crew
NW250 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 | Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 2022-10-21 08:00 | 2022-11-28 16:00 | 2022-10-21 08:00 |  | 8 | 15 | 8 | 20 |  | Sound Wall Crew
MSE330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2022-07-13 08:00 | 2022-08-15 16:00 | 2022-07-13 08:00 | 2022-08-15 16:00 | 3 | 24 | 0 |  |  | Sub - MSE Wall Crew
MSE350 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install Coping - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2022-09-12 08:00 | 2022-09-16 16:00 | 2022-09-12 08:00 | 2022-09-16 16:00 | 3 | 5 | 0 |  |  | Sub - MSE Wall Crew
NW270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2023-01-05 08:00 | 2023-01-17 16:00 |  |  | 8 | 0 | 8 | 18 |  | Sound Wall Crew
MSE370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-08-16 08:00 | 2022-08-19 16:00 | 2022-08-16 08:00 | 2022-08-19 16:00 | 10 | 4 | 0 |  |  | Sub - MSE Wall Crew
MSE420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Coping - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-08-09 08:00 | 2022-09-05 16:00 | 2022-08-09 08:00 | 2022-09-05 16:00 | 5 | 18 | 0 |  |  | Sub - MSE Wall Crew
NW280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 2023-01-18 08:00 | 2023-01-27 16:00 |  |  | 8 | 0 | 8 | 18 |  | Sound Wall Crew
MSE410 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2022-08-15 08:00 | 2022-08-18 16:00 | 2022-08-15 08:00 | 2022-08-18 16:00 | 4 | 4 | 0 |  |  | Sub - MSE Wall Crew
MSE430 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Coping - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2022-08-19 08:00 | 2022-08-24 16:00 | 2022-08-19 08:00 | 2022-08-24 16:00 | 4 | 4 | 0 |  |  | Sub - MSE Wall Crew
NW300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2023-01-30 08:00 | 2023-02-07 16:00 |  |  | 7 | 0 | 7 | 441 |  | Sound Wall Crew
MSE440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 2022-08-15 08:00 | 2022-08-29 16:00 | 2022-08-15 08:00 | 2022-08-29 16:00 | 11 | 11 | 0 |  |  | Sub - MSE Wall Crew
MSE470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Coping - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 32 |  | Sub - MSE Wall Crew
NW310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 2023-02-08 08:00 | 2023-02-17 16:00 |  |  | 8 | 0 | 8 | 441 |  | Sound Wall Crew
MSE480 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 2022-08-01 08:00 | 2022-08-12 16:00 | 2022-08-01 08:00 | 2022-08-12 16:00 | 10 | 10 | 0 |  |  | Sub - MSE Wall Crew
MSE520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Coping - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 2022-11-21 08:00 | 2022-11-30 16:00 |  |  | 5 | 0 | 5 | 32 |  | Sub - MSE Wall Crew
NW330 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 2023-02-20 08:00 | 2023-03-01 16:00 |  |  | 8 | 0 | 8 | 441 |  | Sound Wall Crew
MSE530 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | 2022-11-14 08:00 | 2022-12-01 16:00 |  |  | 11 | 0 | 11 | 31 |  | Sub - MSE Wall Crew
MSE570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 2022-12-02 08:00 | 2022-12-12 16:00 |  |  | 7 | 0 | 7 | 31 |  | Sub - MSE Wall Crew
NW350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 2023-03-02 08:00 | 2023-03-17 16:00 |  |  | 12 | 0 | 12 | 441 |  | Sound Wall Crew
MSE580 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | 2022-09-20 08:00 | 2022-09-29 16:00 | 2022-09-20 08:00 | 2022-09-29 16:00 | 15 | 8 | 0 |  |  | Sub - MSE Wall Crew
MSE630 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 2022-12-13 08:00 | 2022-12-21 16:00 |  |  | 7 | 0 | 7 | 31 |  | Sub - MSE Wall Crew
NW400 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 2023-01-11 08:00 | 2023-01-27 16:00 |  |  | 12 | 0 | 12 | 487 |  | Sound Wall Crew
MSE620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 2022-11-15 08:00 | 2022-11-22 16:00 |  |  | 6 | 0 | 6 | 53 |  | Sub - MSE Wall Crew
MSE650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install Coping - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 2022-12-22 08:00 | 2023-01-04 16:00 |  |  | 4 | 0 | 4 | 35 |  | Sub - MSE Wall Crew
NW420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 2023-01-20 08:00 | 2023-01-31 16:00 |  |  | 8 | 0 | 8 | 485 |  | Sound Wall Crew
MSE640 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 2022-10-31 08:00 | 2022-11-01 16:00 | 2022-10-31 08:00 | 2022-11-01 16:00 | 4 | 2 | 0 |  |  | Sub - MSE Wall Crew
MSE680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Coping - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 2023-01-05 08:00 | 2023-01-12 16:00 |  |  | 6 | 0 | 6 | 35 |  | Sub - MSE Wall Crew
NW440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 2023-02-03 08:00 | 2023-02-20 16:00 |  |  | 12 | 0 | 12 | 481 |  | Sound Wall Crew
MSE690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2022-11-29 08:00 | 2022-12-19 16:00 |  |  | 15 | 0 | 15 | 40 |  | Sub - MSE Wall Crew
MSE720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Coping - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2023-01-13 08:00 | 2023-01-20 16:00 |  |  | 5 | 0 | 5 | 40 |  | Sub - MSE Wall Crew
NW460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2023-02-16 08:00 | 2023-03-03 16:00 |  |  | 12 | 0 | 12 | 38 |  | Sound Wall Crew
MSE740 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | 2023-01-12 08:00 | 2023-01-26 16:00 |  |  | 10 | 0 | 10 | 29 |  | Sub - MSE Wall Crew
MSE770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 2023-02-13 08:00 | 2023-02-17 16:00 |  |  | 5 | 0 | 5 | 29 |  | Sub - MSE Wall Crew
NW520 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 2023-03-06 08:00 | 2023-03-21 16:00 |  |  | 12 | 0 | 12 | 40 |  | Sound Wall Crew
MSE780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 2023-02-21 08:00 | 2023-03-02 16:00 |  |  | 8 | 0 | 8 | 23 |  | Sub - MSE Wall Crew
MSE800 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 2023-03-03 08:00 | 2023-03-09 16:00 |  |  | 5 | 0 | 5 | 24 |  | Sub - MSE Wall Crew
NW550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 2023-03-24 08:00 | 2023-04-10 16:00 |  |  | 12 | 0 | 12 | 38 |  | Sound Wall Crew
MSE810 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2023-03-03 08:00 | 2023-03-17 16:00 |  |  | 11 | 0 | 11 | 23 |  | Sub - MSE Wall Crew
MSE840 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Coping - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-24 16:00 |  |  | 5 | 0 | 5 | 23 |  | Sub - MSE Wall Crew
NW570 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2023-04-11 08:00 | 2023-04-25 16:00 |  |  | 11 | 0 | 11 | 38 |  | Sound Wall Crew
MSE850 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-23 16:00 |  |  | 4 | 0 | 4 | 23 |  | Sub - MSE Wall Crew
MSE870 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install Coping - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2023-03-27 08:00 | 2023-03-29 16:00 |  |  | 3 | 0 | 3 | 28 |  | Sub - MSE Wall Crew
NW580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2023-04-26 08:00 | 2023-05-09 16:00 |  |  | 10 | 0 | 10 | 38 |  | Sound Wall Crew
MSE880 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 2023-03-24 08:00 | 2023-03-31 16:00 |  |  | 6 | 0 | 6 | 23 |  | Sub - MSE Wall Crew
MSE910 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 2023-04-03 08:00 | 2023-04-05 16:00 |  |  | 3 | 0 | 3 | 27 |  | Sub - MSE Wall Crew
NW590 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 2023-05-10 08:00 | 2023-05-23 16:00 |  |  | 10 | 0 | 10 | 38 |  | Sound Wall Crew
MSE920 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 2023-04-03 08:00 | 2023-04-11 16:00 |  |  | 7 | 0 | 7 | 23 |  | Sub - MSE Wall Crew
MSE940 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Coping - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 2023-04-12 08:00 | 2023-04-17 16:00 |  |  | 4 | 0 | 4 | 23 |  | Sub - MSE Wall Crew
NW620 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 2023-05-24 08:00 | 2023-06-09 16:00 |  |  | 12 | 0 | 12 | 38 |  | Sound Wall Crew
MSE970 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 2022-10-26 08:00 | 2022-11-30 16:00 | 2022-10-26 08:00 |  | 10 | 12 | 10 | 126 |  | Sub - MSE Wall Crew
MSE1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 2023-04-18 08:00 | 2023-04-21 16:00 |  |  | 4 | 0 | 4 | 35 |  | Sub - MSE Wall Crew
NW660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 2023-06-12 08:00 | 2023-06-27 16:00 |  |  | 12 | 0 | 12 | 38 |  | Sound Wall Crew
MSE1020 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 2022-11-09 08:00 | 2022-11-22 16:00 | 2022-11-09 08:00 |  | 7 | 2 | 7 | 133 |  | Sub - MSE Wall Crew
MSE1040 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 2023-04-24 08:00 | 2023-04-26 16:00 |  |  | 3 | 0 | 3 | 35 |  | Sub - MSE Wall Crew
NW670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 2023-06-28 08:00 | 2023-07-11 16:00 |  |  | 9 | 0 | 9 | 38 |  | Sound Wall Crew
MSE1050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 2023-02-10 08:00 | 2023-03-01 16:00 |  |  | 14 | 0 | 14 | 87 |  | Sub - MSE Wall Crew
MSE1080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 2023-04-27 08:00 | 2023-05-04 16:00 |  |  | 6 | 0 | 6 | 58 |  | Sub - MSE Wall Crew
MSE1090 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 2023-03-02 08:00 | 2023-03-23 16:00 |  |  | 16 | 0 | 16 | 87 |  | Sub - MSE Wall Crew
MSE1120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Coping - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 2023-05-05 08:00 | 2023-05-11 16:00 |  |  | 5 | 0 | 5 | 62 |  | Sub - MSE Wall Crew
NW710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 2023-07-12 08:00 | 2023-07-27 16:00 |  |  | 12 | 0 | 12 | 38 |  | Sound Wall Crew
MSE1130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2023-03-24 08:00 | 2023-04-06 16:00 |  |  | 10 | 0 | 10 | 87 |  | Sub - MSE Wall Crew
MSE1150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2023-05-12 08:00 | 2023-05-18 16:00 |  |  | 5 | 0 | 5 | 62 |  | Sub - MSE Wall Crew
NW720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2023-07-28 08:00 | 2023-08-14 16:00 |  |  | 12 | 0 | 12 | 38 |  | Sound Wall Crew
MSE1160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2023-05-19 08:00 | 2023-06-14 16:00 |  |  | 18 | 0 | 18 | 62 |  | Sub - MSE Wall Crew
MSE1190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Coping - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2023-08-24 08:00 | 2023-08-31 16:00 |  |  | 6 | 0 | 6 | 13 |  | Sub - MSE Wall Crew
NW740 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2023-09-21 08:00 | 2023-10-10 16:00 |  |  | 14 | 0 | 14 | 13 |  | Sound Wall Crew
ITS330 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | ITS Testing - NB | 2024-01-25 08:00 | 2024-02-07 16:00 |  |  | 10 | 0 | 10 | 17 |  | Sub - ITS Installation Crew
ITS340 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | ITS Testing - SB | 2024-02-16 08:00 | 2024-02-29 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sub - ITS Installation Crew
ITS350 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | ITS: Field Acceptance Testing | 2024-03-01 08:00 | 2024-03-14 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sub - ITS Installation Crew
ITS360 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | ITS: System Integration & Acceptance Testing | 2024-03-15 08:00 | 2024-03-21 16:00 |  |  | 5 | 0 | 5 | 11 |  | Sub - ITS Installation Crew
STAB100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Stabilization - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-09-15 08:00 | 2022-09-17 16:00 | 2022-09-15 08:00 | 2022-09-17 16:00 | 10 | 3 | 0 |  |  | Subgrade Stabilization Crew
BASE100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Base - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-09-25 08:00 | 2022-09-26 16:00 | 2022-09-25 08:00 | 2022-09-26 16:00 | 10 | 2 | 0 |  |  | Agg Base Crew
PAV130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Asphalt Paving - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-10-20 08:00 | 2022-10-24 16:00 | 2022-10-20 08:00 | 2022-10-24 16:00 | 5 | 5 | 0 |  |  | Sub - Asphalt Paving Crew
PM100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Pavement Markings - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-10-25 08:00 | 2022-10-26 16:00 | 2022-10-25 08:00 | 2022-10-26 16:00 | 2 | 2 | 0 |  |  | Sub - Striping Crew
LOE-FLOR-C | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | **Floribraska Ramp C - 45 Calendar Day Duration (SUMMARY) | 2022-09-12 08:00 | 2022-09-16 16:00 | 2022-09-12 08:00 | 2022-09-16 16:00 | 71 | 5 | 0
STAB110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Stabilization - MLK Ramp B - Ph1-S1 | 2023-01-18 08:00 | 2023-01-30 16:00 |  |  | 9 | 0 | 9 | 10 |  | Subgrade Stabilization Crew
BASE110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Base Course - MLK Ramp B - Ph1-S1 | 2023-02-27 08:00 | 2023-03-07 16:00 |  |  | 7 | 0 | 7 | 12 |  | Agg Base Crew
PAV180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Asphalt Paving - MLK Ramp B - Ph1-S1 | 2023-03-30 08:00 | 2023-04-03 16:00 |  |  | 3 | 0 | 3 | 13 |  | Sub - Asphalt Paving Crew
PM110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Pavement Markings - MLK Ramp B - Ph1-S1 | 2023-04-04 08:00 | 2023-04-05 16:00 |  |  | 2 | 0 | 2 | 13 |  | Sub - Striping Crew
STAB120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Stabilization - MLK Ramp C - Ph1-S1 | 2023-02-13 08:00 | 2023-02-17 16:00 |  |  | 5 | 0 | 5 | 10 |  | Subgrade Stabilization Crew
BASE120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Base Course - MLK Ramp C - Ph1-S1 | 2023-02-20 08:00 | 2023-03-01 16:00 |  |  | 8 | 0 | 8 | 24 |  | Agg Base Crew
PAV210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Asphalt Paving - MLK Ramp C - Ph1-S1 | 2023-05-09 08:00 | 2023-05-10 16:00 |  |  | 2 | 0 | 2 | 9 |  | Sub - Asphalt Paving Crew
PM120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 | Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Pavement Parkings - MLK Ramp C - Ph1-S1 | 2023-05-11 08:00 | 2023-05-11 16:00 |  |  | 1 | 0 | 1 | 9 |  | Sub - Striping Crew
STAB140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Stabilization - Hillsborough Ramp B - Ph1-S1 | 2023-04-27 08:00 | 2023-05-11 16:00 |  |  | 11 | 0 | 11 | 13 |  | Subgrade Stabilization Crew
BASE140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Base Course - Hillsborough Ramp B - Ph1-S1 | 2023-05-12 08:00 | 2023-05-24 16:00 |  |  | 9 | 0 | 9 | 13 |  | Agg Base Crew
PAV260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | 2023-07-18 08:00 | 2023-07-21 16:00 |  |  | 4 | 0 | 4 | 11 |  | Sub - Asphalt Paving Crew
PM130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Pavement Markings - Hillsborough Ramp B - Ph1-S1 | 2023-07-24 08:00 | 2023-07-25 16:00 |  |  | 2 | 0 | 2 | 12 |  | Sub - Striping Crew
STAB270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Stabilization - Hillsborough Ramp C1 - Ph1-S1 | 2023-04-17 08:00 | 2023-04-27 16:00 |  |  | 9 | 0 | 9 | 59 |  | Subgrade Stabilization Crew
BASE260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp C1 - Ph1-S1 | 2023-07-07 08:00 | 2023-07-12 16:00 |  |  | 4 | 0 | 4 | 16 |  | Agg Base Crew
PAV320 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | 2023-07-24 08:00 | 2023-07-25 16:00 |  |  | 2 | 0 | 2 | 11 |  | Sub - Asphalt Paving Crew
PM140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Pavement Markings - Hillsborough Ramp C1 - Ph1-S1 | 2023-07-26 08:00 | 2023-07-26 16:00 |  |  | 1 | 0 | 1 | 12 |  | Sub - Striping Crew
STAB280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp C2 - Ph1-S1 | 2023-04-28 08:00 | 2023-05-10 16:00 |  |  | 9 | 0 | 9 | 59 |  | Subgrade Stabilization Crew
BASE310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp C2 - Ph1-S1 | 2023-07-13 08:00 | 2023-07-18 16:00 |  |  | 4 | 0 | 4 | 16 |  | Agg Base Crew
PAV340 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | 2023-07-26 08:00 | 2023-07-27 16:00 |  |  | 2 | 0 | 2 | 11 |  | Sub - Asphalt Paving Crew
PM150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Pavement Markings - Hillsborough Ramp C2 - Ph1-S1 | 2023-07-28 08:00 | 2023-07-28 16:00 |  |  | 1 | 0 | 1 | 11 |  | Sub - Striping Crew
STAB310 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 | Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Stabilization - Hillsborough Ramp D - Ph1-S1 | 2023-06-22 08:00 | 2023-06-28 16:00 |  |  | 5 | 0 | 5 | 16 |  | Subgrade Stabilization Crew
BASE390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 | Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Base Course - Hillsborough Ramp D - Ph1-S1 | 2023-06-29 08:00 | 2023-07-06 16:00 |  |  | 5 | 0 | 5 | 16 |  | Agg Base Crew
PAV360 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 | Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | 2023-07-28 08:00 | 2023-08-01 16:00 |  |  | 3 | 0 | 3 | 24 |  | Sub - Asphalt Paving Crew
PM160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 | Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | 2023-08-07 08:00 | 2023-08-08 16:00 |  |  | 2 | 0 | 2 | 21 |  | Sub - Striping Crew
STAB350 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 | Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Stabilization - Hillsborough Ramp A - Ph1-S1 | 2023-08-24 08:00 | 2023-09-07 16:00 |  |  | 9 | 0 | 9 | 10 |  | Subgrade Stabilization Crew
BASE430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 | Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Base Course - Hillsborough Ramp A - Ph1-S1 | 2023-09-08 08:00 | 2023-09-12 16:00 |  |  | 3 | 0 | 3 | 10 |  | Agg Base Crew
PAV380 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 | Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | 2023-10-06 08:00 | 2023-10-09 16:00 |  |  | 2 | 0 | 2 | 33 |  | Sub - Asphalt Paving Crew
PM170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 | Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Pavement Markings - Hillsborough Ramp A - Ph1-S1 | 2023-10-10 08:00 | 2023-10-10 16:00 |  |  | 1 | 0 | 1 | 33 |  | Sub - Striping Crew
STAB420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Stabilization - MLK Ramp D - Ph1-S1 | 2023-08-29 08:00 | 2023-09-14 16:00 |  |  | 11 | 0 | 11 | 25 |  | Subgrade Stabilization Crew
BASE500 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Base Course - MLK Ramp D - Ph1-S1 | 2023-12-08 08:00 | 2023-12-14 16:00 |  |  | 5 | 0 | 5 | -2 | 10 | Agg Base Crew
PAV410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S1 | 2023-12-15 08:00 | 2023-12-18 16:00 |  |  | 2 | 0 | 2 | -2 | 10 | Sub - Asphalt Paving Crew
PM180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Pavement Markings - MLK Ramp D - Ph1-S1 | 2024-01-04 08:00 | 2024-01-04 16:00 |  |  | 1 | 0 | 1 | -2 | 10 | Sub - Striping Crew
STAB440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Stabilization - MLK Ramp A - Ph1-S1 | 2023-10-09 08:00 | 2023-10-19 16:00 |  |  | 9 | 0 | 9 | 9 |  | Subgrade Stabilization Crew
BASE540 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Base Course - MLK Ramp A - Ph1-S1 | 2023-11-02 08:00 | 2023-11-03 16:00 |  |  | 2 | 0 | 2 | 0 | 13 | Agg Base Crew
PAV420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Asphalt Paving - MLK Ramp A - Ph1-S1 | 2023-12-05 08:00 | 2023-12-06 16:00 |  |  | 2 | 0 | 2 | 4 |  | Sub - Asphalt Paving Crew
PM190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Pavement Markings - MLK Ramp A - Ph1-S1 | 2024-01-05 08:00 | 2024-01-05 16:00 |  |  | 1 | 0 | 1 | -1 | 19 | Sub - Striping Crew
STAB460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 | Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Stabilization - Floribraska Ramp NE - Ph1-S1 | 2023-11-20 08:00 | 2023-12-05 16:00 |  |  | 9 | 0 | 9 | -2 | 10 | Subgrade Stabilization Crew
BASE580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 | Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Base Course - Floribraska Ramp NE - Ph1-S1 | 2023-12-06 08:00 | 2023-12-07 16:00 |  |  | 2 | 0 | 2 | -2 | 10 | Agg Base Crew
PAV430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 | Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Asphalt Paving - Floribraska Ramp NE - Ph1-S1 | 2023-12-08 08:00 | 2023-12-11 16:00 |  |  | 2 | 0 | 2 | 11 |  | Sub - Asphalt Paving Crew
PM200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 | Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Pavement Markings - Floribraska Ramp NE - Ph1-S1 | 2024-01-08 08:00 | 2024-01-08 16:00 |  |  | 1 | 0 | 1 | -1 | 19 | Sub - Striping Crew
UDR100 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Install Edgedrain - MLK Ramp B - Ph1-S2 | 2023-07-13 08:00 | 2023-07-17 16:00 |  |  | 3 | 0 | 3 | 9 |  | Underdrain Crew
UDR110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Install Edgedrain - MLK Ramp C - Ph1-S2 | 2023-08-24 08:00 | 2023-08-28 16:00 |  |  | 3 | 0 | 3 | 4 |  | Underdrain Crew
UDR120 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Edgedrain - Hillsborough Ramp B - Ph1-S2 | 2023-11-21 08:00 | 2023-11-28 16:00 |  |  | 3 | 0 | 3 | -1 | 12 | Underdrain Crew
UDR230 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Install Edgedrain - Hillsborough Ramp C2 - Ph1-S2 | 2023-11-29 08:00 | 2023-12-01 16:00 |  |  | 3 | 0 | 3 | 12 |  | Underdrain Crew
UDR210 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.6 | Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Install Edgedrain - Hillsborough Ramp C1 - Ph1-S2 | 2024-01-12 08:00 | 2024-01-17 16:00 |  |  | 3 | 0 | 3 | 9 |  | Underdrain Crew
UDR260 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Edgedrain - Hillsborough Ramp D - Ph1-S2 | 2024-01-18 08:00 | 2024-01-22 16:00 |  |  | 3 | 0 | 3 | 15 |  | Underdrain Crew
UDR280 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | 2024-02-22 08:00 | 2024-02-26 16:00 |  |  | 3 | 0 | 3 | -4 | 5 | Underdrain Crew
UDR340 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Install Edgedrain - MLK Ramp D - Ph1-S2 | 2024-03-13 08:00 | 2024-03-15 16:00 |  |  | 3 | 0 | 3 | 3 |  | Underdrain Crew
UDR370 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Install Edgedrain - MLK Ramp A - Ph1-S2 | 2024-03-25 08:00 | 2024-03-27 16:00 |  |  | 3 | 0 | 3 | 1 |  | Underdrain Crew
UDR400 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.11 | Construction: Phase 1: Stage 2: Floribraska Ramp NE | Install Edgedrain - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 2024-02-27 08:00 | 2024-02-29 16:00 |  |  | 3 | 0 | 3 | -1 |  | Underdrain Crew
DEMO100 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - NB: 815 - 818 - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 43 |  | Demolition Crews
DEMO140 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - SB: 835 - 840 - IPh1 | 2022-11-01 08:00 | 2022-11-01 16:00 | 2022-11-01 08:00 | 2022-11-01 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO170 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 2 Structures - SB: 835 - 840 - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 419 |  | Demolition Crews
DEMO200 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Demo Existing Drainage: 1 Structure - SB: 835 - 840 - IPh1 | 2022-02-04 08:00 | 2022-02-04 16:00 | 2022-02-04 08:00 | 2022-02-04 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO230 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Demo Existing Drainage: End U Wall, 20' of 24" Pipe, 1 Structure - SB: 823 - 827 - IPh1 | 2022-07-26 08:00 | 2022-07-27 16:00 | 2022-07-26 08:00 | 2022-07-27 16:00 | 1 | 2 | 0 |  |  | Demolition Crews
DEMO260 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.4 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 777 - 781 - IPh1 | 2022-03-09 08:00 | 2022-03-10 16:00 | 2022-03-09 08:00 | 2022-03-10 16:00 | 1 | 2 | 0 |  |  | Demolition Crews
DEMO280 | Completed | 3462-FDOT-Owner-12.4.IP1.6.2.5 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 769 - 772 - IPh1 | 2022-02-15 08:00 | 2022-03-18 16:00 | 2022-02-15 08:00 | 2022-03-18 16:00 | 1 | 24 | 0 |  |  | Demolition Crews
DEMO310 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.6 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 748 - 751 - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 59 |  | Demolition Crews
DEMO400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Existing Drainage: S-31 Remove to Existing - NB: 739+00-740+00 - Ph1-S1 | 2022-10-07 08:00 | 2022-10-07 16:00 | 2022-10-07 08:00 | 2022-10-07 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO410 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Existing Drainage: S-34 Remove 35' of 18" Pipe & 2 Structures - NB: 744+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 514 |  | Demolition Crews
DEMO190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove S-11 Structure - NB: 725+00-726+00 - Ph1-S1 | 2022-04-05 08:00 | 2022-04-07 16:00 | 2022-04-05 08:00 | 2022-04-07 16:00 | 1 | 3 | 0 |  |  | Demolition Crews
DEMO240 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 619' of 30" Pipe & 5 Structures - NB: 726+00-734+00 - Ph1-S1 | 2022-02-28 08:00 | 2022-03-09 16:00 | 2022-02-28 08:00 | 2022-03-09 16:00 | 5 | 8 | 0 |  |  | Demolition Crews
DEMO340 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 84' of 15" Pipe - NB: 726+00-730+00 - Ph1-S1 | 2022-09-07 08:00 | 2022-09-07 16:00 | 2022-09-07 08:00 | 2022-09-07 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO350 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 36' of 15" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | 2022-09-08 08:00 | 2022-09-08 16:00 | 2022-09-08 08:00 | 2022-09-08 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 12' of 24" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | 2022-10-03 08:00 | 2022-10-05 16:00 | 2022-10-03 08:00 | 2022-10-05 16:00 | 1 | 3 | 0 |  |  | Demolition Crews
DEMO390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 730+00-745+00 - Ph1-S1 | 2022-10-06 08:00 | 2022-10-06 16:00 | 2022-10-06 08:00 | 2022-10-06 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - NB: 751+00-752+00 - Ph1-S1 | 2022-11-15 08:00 | 2022-11-15 16:00 |  |  | 1 | 0 | 1 | 514 |  | Demolition Crews
DEMO440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 12' of 18" Pipe & 1 Structure - NB: 752+00-753+00 - Ph1-S1 | 2022-03-09 08:00 | 2022-03-15 16:00 | 2022-03-09 08:00 | 2022-03-15 16:00 | 1 | 5 | 0 |  |  | Demolition Crews
DEMO450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 40' of 18" Pipe & 2 Structures - NB: 752+00-756+00 - Ph1-S1 | 2022-07-27 08:00 | 2022-07-28 16:00 | 2022-07-27 08:00 | 2022-07-28 16:00 | 1 | 2 | 0 |  |  | Demolition Crews
DEMO460 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 30' of 15" Pipe & 1 Structure - NB: 755+00-756+00 - Ph1-S1 | 2022-07-29 08:00 | 2022-07-30 16:00 | 2022-07-29 08:00 | 2022-07-30 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO490 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 2 Structures - NB: 755+00-756+00 - Ph1-S1 | 2022-08-01 08:00 | 2022-08-02 16:00 | 2022-08-01 08:00 | 2022-08-02 16:00 | 1 | 2 | 0 |  |  | Demolition Crews
DEMO500 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 97' of 36" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | 2022-05-13 08:00 | 2022-05-17 16:00 | 2022-05-13 08:00 | 2022-05-17 16:00 | 2 | 3 | 0 |  |  | Demolition Crews
DEMO540 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 15' of 15" Pipe & 3 Structures - NB: 768+00-769+00 - Ph1-S1 | 2022-05-20 08:00 | 2022-05-21 16:00 | 2022-05-20 08:00 | 2022-05-21 16:00 | 2 | 1 | 0 |  |  | Demolition Crews
DEMO550 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 769+00-770+00 - Ph1-S1 | 2022-05-22 08:00 | 2022-05-23 16:00 | 2022-05-22 08:00 | 2022-05-23 16:00 | 2 | 1 | 0 |  |  | Demolition Crews
DEMO510 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 252' of 42" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | 2022-05-15 08:00 | 2022-05-17 16:00 | 2022-05-15 08:00 | 2022-05-17 16:00 | 3 | 2 | 0 |  |  | Demolition Crews
DEMO560 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 28' of 18" Pipe & 3 Structures - NB: 778+00-779+00 - Ph1-S1 | 2022-05-24 08:00 | 2022-05-27 16:00 | 2022-05-24 08:00 | 2022-05-27 16:00 | 2 | 4 | 0 |  |  | Demolition Crews
DEMO600 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 1 Structure - NB: 778+00-779+00 - Ph1-S1 | 2022-05-28 08:00 | 2022-05-29 16:00 | 2022-05-28 08:00 | 2022-05-29 16:00 | 2 | 0 | 0 |  |  | Demolition Crews
DEMO610 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - NB: 784+00-785+00 - Ph1-S1 | 2022-05-23 08:00 | 2022-05-25 16:00 | 2022-05-23 08:00 | 2022-05-25 16:00 | 2 | 3 | 0 |  |  | Demolition Crews
DEMO620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 792+00-793+00 - Ph1-S1 | 2022-10-18 08:00 | 2022-10-20 16:00 | 2022-10-18 08:00 | 2022-10-20 16:00 | 3 | 3 | 0 |  |  | Demolition Crews
DEMO640 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 793+00-795+00 - Ph1-S1 | 2022-09-06 08:00 | 2022-09-08 16:00 | 2022-09-06 08:00 | 2022-09-08 16:00 | 3 | 3 | 0 |  |  | Demolition Crews
DEMO650 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 805+00-806+00 - Ph1-S1 | 2022-08-17 08:00 | 2022-08-17 16:00 | 2022-08-17 08:00 | 2022-08-17 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO680 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 806+00-807+00 - Ph1-S1 | 2022-08-16 08:00 | 2022-08-16 16:00 | 2022-08-16 08:00 | 2022-08-16 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO690 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 42' of 18" Pipe & 2 Structures - NB: 807+00-808+00 - Ph1-S1 | 2022-09-15 08:00 | 2022-09-16 16:00 | 2022-09-15 08:00 | 2022-09-16 16:00 | 2 | 2 | 0 |  |  | Demolition Crews
DEMO700 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 13' of 23"x14" Pipe & 1 Structure - NB: 807+00-808+00 - Ph1-S1 | 2022-08-18 08:00 | 2022-08-18 16:00 | 2022-08-18 08:00 | 2022-08-18 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO710 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove End Wall - NB: 808+00-809+00 - Ph1-S1 | 2022-08-18 08:00 | 2022-08-18 16:00 | 2022-08-18 08:00 | 2022-08-18 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO740 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove Inlet - NB: 809+00-810+00 - Ph1-S1 | 2022-08-18 08:00 | 2022-08-18 16:00 | 2022-08-18 08:00 | 2022-08-18 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO760 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 41' of 15" Pipe & 2 Structures - NB: 810+00-811+00 - Ph1-S1 | 2022-09-16 08:00 | 2022-09-16 16:00 | 2022-09-16 08:00 | 2022-09-16 16:00 | 2 | 1 | 0 |  |  | Demolition Crews
DEMO770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 32' of 15" Pipe & 1 Structure - NB: 810+00-811+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 254 |  | Demolition Crews
DEMO780 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 816+00-817+00 - Ph1-S2 | 2022-11-15 08:00 | 2022-11-15 16:00 |  |  | 1 | 0 | 1 | 254 |  | Demolition Crews
DEMO800 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 47' of 15" Pipe & 2 Structures - NB: 819+00-820+00 - Ph1-S2 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 255 |  | Demolition Crews
DEMO810 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 64' of 18" Pipe & 1 Structure - NB: 819+00-821+00 - Ph1-S2 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 255 |  | Demolition Crews
DEMO820 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 27' of 14"x23" Pipe & 2 Structures - NB: 820+00-822+00 - Ph1-S2 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 252 |  | Demolition Crews
DEMO830 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 41' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | 2022-11-15 08:00 | 2022-11-15 16:00 |  |  | 1 | 0 | 1 | 252 |  | Demolition Crews
DEMO840 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | 2022-11-16 08:00 | 2022-11-16 16:00 |  |  | 1 | 0 | 1 | 252 |  | Demolition Crews
DEMO860 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 10' of 15" Pipe & 2 Structures - NB: 822+00-823+00 - Ph1-S2 | 2022-11-17 08:00 | 2022-11-17 16:00 |  |  | 1 | 0 | 1 | 252 |  | Demolition Crews
DEMO870 | Completed | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 17' of 24" Pipe & 2 Structures - NB: 826+00-828+00 - Ph1-S2 | 2022-11-03 08:00 | 2022-11-03 16:00 | 2022-11-03 08:00 | 2022-11-03 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO880 | Completed | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 2 Structures - NB: 835+00-836+00 - Ph1-S2 | 2022-11-04 08:00 | 2022-11-04 16:00 | 2022-11-04 08:00 | 2022-11-04 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO890 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 839+00-840+00 - Ph1-S1 | 2022-02-17 08:00 | 2022-02-19 16:00 | 2022-02-17 08:00 | 2022-02-19 16:00 | 1 | 2 | 0 |  |  | Demolition Crews
DEMO900 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 836+00-837+00 - Ph1-S1 | 2022-08-11 08:00 | 2022-08-12 16:00 | 2022-08-11 08:00 | 2022-08-12 16:00 | 2 | 2 | 0 |  |  | Demolition Crews
DEMO920 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 30' of 15" Pipe & 3 Structures - SB: 835+00-836+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 14 |  | Demolition Crews
DEMO930 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 20' of 24" Pipe & 2 Structures - SB: 826+00-828+00 - Ph1-S1 | 2022-11-03 08:00 | 2022-11-04 16:00 | 2022-11-03 08:00 | 2022-11-04 16:00 | 1 | 2 | 0 |  |  | Demolition Crews
DEMO940 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 823+00-824+00 - Ph1-S1 | 2022-10-19 08:00 | 2022-10-19 16:00 | 2022-10-19 08:00 | 2022-10-19 16:00 | 1 | 1 | 0 |  |  | Demolition Crews
DEMO950 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 823+00-824+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 15 |  | Demolition Crews
DEMO980 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - SB: 808+00-809+00 - Ph1-S1 | 2022-11-09 08:00 | 2022-11-10 16:00 | 2022-11-09 08:00 | 2022-11-10 16:00 | 2 | 2 | 0 |  |  | Demolition Crews
DEMO990 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 16 |  | Demolition Crews
DEMO1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 16' of 36" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | 2022-11-16 08:00 | 2022-11-17 16:00 |  |  | 2 | 0 | 2 | 16 |  | Demolition Crews
DEMO1020 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 806+00-807+00 - Ph1-S1 | 2022-11-18 08:00 | 2022-11-21 16:00 |  |  | 2 | 0 | 2 | 16 |  | Demolition Crews
DEMO1050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 70' of 15" Pipe & 2 Structures - SB: 806+00-807+00 - Ph1-S1 | 2022-11-22 08:00 | 2022-11-28 16:00 |  |  | 2 | 0 | 2 | 16 |  | Demolition Crews
DEMO1070 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove End Wall - SB: 806+00-807+00 - Ph1-S1 | 2022-11-29 08:00 | 2022-11-30 16:00 |  |  | 2 | 0 | 2 | 16 |  | Demolition Crews
DEMO1080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 7' of 23"x14" Pipe & 2 Structures - SB: 794+00-795+00 - Ph1-S1 | 2022-12-01 08:00 | 2022-12-02 16:00 |  |  | 2 | 0 | 2 | 36 |  | Demolition Crews
DEMO1100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 28' of 18" Pipe & 1 Structure - SB: 794+00-795+00 - Ph1-S1 | 2022-12-05 08:00 | 2022-12-06 16:00 |  |  | 2 | 0 | 2 | 36 |  | Demolition Crews
DEMO1120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 791+00-792+00 - Ph1-S1 | 2022-12-07 08:00 | 2022-12-08 16:00 |  |  | 2 | 0 | 2 | 36 |  | Demolition Crews
DEMO1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 784+00-785+00 - Ph1-S1 | 2022-12-09 08:00 | 2022-12-12 16:00 |  |  | 2 | 0 | 2 | 38 |  | Demolition Crews
DEMO1150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 781+00-782+00 - Ph1-S1 | 2022-12-13 08:00 | 2022-12-14 16:00 |  |  | 2 | 0 | 2 | 38 |  | Demolition Crews
DEMO1160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - SB: 778+00-779+00 - Ph1-S1 | 2022-12-15 08:00 | 2022-12-16 16:00 |  |  | 2 | 0 | 2 | 42 |  | Demolition Crews
DEMO1170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 769+00-770+00 - Ph1-S1 | 2022-12-19 08:00 | 2022-12-20 16:00 |  |  | 2 | 0 | 2 | 42 |  | Demolition Crews
DEMO1190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 94' of 30" Pipe & 1 Structure - SB: 767+00-768+00 - Ph1-S1 | 2022-12-21 08:00 | 2022-12-22 16:00 |  |  | 2 | 0 | 2 | 42 |  | Demolition Crews
DEMO1200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 766+00-768+00 - Ph1-S1 | 2022-12-23 08:00 | 2023-01-03 16:00 |  |  | 2 | 0 | 2 | 42 |  | Demolition Crews
DEMO1210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 178' of 30" Pipe & 1 Structure - SB: 765+00-767+00 - Ph1-S1 | 2023-01-04 08:00 | 2023-01-05 16:00 |  |  | 2 | 0 | 2 | 42 |  | Demolition Crews
DEMO1230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 40' of 30" Pipe - SB: 765+00-767+00 - Ph1-S1 | 2023-01-06 08:00 | 2023-01-09 16:00 |  |  | 2 | 0 | 2 | 42 |  | Demolition Crews
DEMO1240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 1 Structure - SB: 756+00-757+00 - Ph1-S1 | 2023-02-22 08:00 | 2023-02-23 16:00 |  |  | 2 | 0 | 2 | 43 |  | Demolition Crews
DEMO1260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 37' of 18" Pipe & 2 Structures - SB: 753+00-755+00 - Ph1-S1 | 2023-02-24 08:00 | 2023-02-27 16:00 |  |  | 2 | 0 | 2 | 43 |  | Demolition Crews
DEMO1270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 753+00-754+00 - Ph1-S1 | 2023-02-28 08:00 | 2023-03-01 16:00 |  |  | 2 | 0 | 2 | 43 |  | Demolition Crews
DEMO1290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Existing Drainage: Remove 5' of 23"x1" Pipe & 2 Structures - SB: 744+00-745+00 - Ph1-S1 | 2023-03-02 08:00 | 2023-03-03 16:00 |  |  | 2 | 0 | 2 | 48 |  | Demolition Crews
DEMO1720 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 729+00-730+00 - Ph2 | 2024-04-30 08:00 | 2024-05-01 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Demolition Crews
DEMO150 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Demo Existing Drainage: Remove 25' of 24" Pipe - Floribraska: 721+00-722+00 - Ph1-S1 | 2021-12-07 08:00 | 2021-12-10 16:00 | 2021-12-07 08:00 | 2021-12-10 16:00 | 3 | 4 | 0 |  |  | Demolition Crews
DEMO1740 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 733+00-734+00 - Ph2 | 2024-05-02 08:00 | 2024-05-03 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Demolition Crews
DEMO1750 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 75' of 15" Pipe & 2 Structures - NB & SB Median: 734+00-735+00 - Ph2 | 2024-05-06 08:00 | 2024-05-07 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Demolition Crews
DEMO1760 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 739+00-740+00 - Ph2 | 2024-05-08 08:00 | 2024-05-09 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Demolition Crews
DEMO1770 | Not Started | 3462-FDOT-Owner-12.4.P2.3 | Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 744+00-745+00 - Ph2 | 2024-05-10 08:00 | 2024-05-13 16:00 |  |  | 2 | 0 | 2 | -4 | 1 | Demolition Crews
DEMO1780 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Demo Existing Drainage: Remove 12' of 15" Pipe & 2 Structures - NB & SB Median: 753+00-754+00 - Ph2 | 2024-05-14 08:00 | 2024-05-15 16:00 |  |  | 2 | 0 | 2 | 9 |  | Demolition Crews
DEMO1800 | Not Started | 3462-FDOT-Owner-12.4.P2.4 | Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 756+00-757+00 - Ph2 | 2024-05-16 08:00 | 2024-05-17 16:00 |  |  | 2 | 0 | 2 | 9 |  | Demolition Crews
DEMO1810 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 766+00-767+00 - Ph2 | 2024-05-20 08:00 | 2024-05-21 16:00 |  |  | 2 | 0 | 2 | 9 |  | Demolition Crews
DEMO1830 | Not Started | 3462-FDOT-Owner-12.4.P2.5 | Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 768+00-769+00 - Ph2 | 2024-05-22 08:00 | 2024-05-24 16:00 |  |  | 3 | 0 | 3 | 9 |  | Demolition Crews
DEMO1840 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | 2024-05-28 08:00 | 2024-05-29 16:00 |  |  | 2 | 0 | 2 | 9 |  | Demolition Crews
DEMO1860 | Not Started | 3462-FDOT-Owner-12.4.P2.6 | Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | 2024-05-30 08:00 | 2024-05-31 16:00 |  |  | 2 | 0 | 2 | 9 |  | Demolition Crews
DEMO1870 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 794+00-795+00 - Ph2 | 2024-06-04 08:00 | 2024-06-06 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1890 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 800+00-801+00 - Ph2 | 2024-06-07 08:00 | 2024-06-11 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1900 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | 2024-06-12 08:00 | 2024-06-14 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1910 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 96' of 18" Pipe - NB & SB Median: 800+00-802+00 - Ph2 | 2024-06-17 08:00 | 2024-06-19 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1920 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | 2024-06-20 08:00 | 2024-06-24 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1930 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 96' of 18" Pipe & 1 Structure - NB & SB Median: 805+00-806+00 - Ph2 | 2024-06-25 08:00 | 2024-06-27 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1940 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 27' of 18" Pipe & 1 Structure - NB & SB Median: 806+00-807+00 - Ph2 | 2024-06-28 08:00 | 2024-07-02 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1950 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 44' of 18" Pipe & 2 Structures - NB & SB Median: 807+00-808+00 - Ph2 | 2024-07-03 08:00 | 2024-07-08 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1960 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 60' of 18" Pipe & 2 Structures - NB & SB Median: 822+00-823+00 - Ph2 | 2024-07-09 08:00 | 2024-07-11 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1970 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 34' of 18" Pipe & 1 Structure - NB & SB Median: 823+00-824+00 - Ph2 | 2024-07-12 08:00 | 2024-07-16 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1980 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 827+00-828+00 - Ph2 | 2024-07-17 08:00 | 2024-07-19 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO1990 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 76' of 18" Pipe - NB & SB Median: 828+00-830+00 - Ph2 | 2024-07-22 08:00 | 2024-07-24 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO2000 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 829+00-830+00 - Ph2 | 2024-07-25 08:00 | 2024-07-29 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO2010 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 835+00-836+00 - Ph2 | 2024-07-30 08:00 | 2024-08-01 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
DEMO2020 | Not Started | 3462-FDOT-Owner-12.4.P2.8 | Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - NB & SB Median: 836+00-837+00 - Ph2 | 2024-08-02 08:00 | 2024-08-06 16:00 |  |  | 3 | 0 | 3 | 8 |  | Demolition Crews
NW370 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | 2023-03-10 08:00 | 2023-03-16 16:00 |  |  | 5 | 0 | 5 | 4 |  | Sound Wall Crew
NW390 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | 2023-04-07 08:00 | 2023-04-11 16:00 |  |  | 3 | 0 | 3 | 4 |  | Sound Wall Crew
NW430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - NB: over MLK Blvd - Ph1-S1 | 2023-04-24 08:00 | 2023-04-28 16:00 |  |  | 5 | 0 | 5 | 19 |  | Sound Wall Crew
NW480 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-05-22 08:00 | 2023-05-25 16:00 |  |  | 4 | 0 | 4 | 16 |  | Sound Wall Crew
NW510 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2023-09-18 08:00 | 2023-09-22 16:00 |  |  | 5 | 0 | 5 | 1 |  | Sound Wall Crew
NW610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-10-12 08:00 | 2023-10-19 16:00 |  |  | 6 | 0 | 6 | -4 | 1 | Sound Wall Crew
NW700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-11-08 08:00 | 2023-11-16 16:00 |  |  | 6 | 0 | 6 | -4 | 1 | Sound Wall Crew
NW730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-12-01 08:00 | 2023-12-07 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sound Wall Crew
NW760 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-12-19 08:00 | 2024-01-03 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sound Wall Crew
NW780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | 2024-01-17 08:00 | 2024-01-23 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sound Wall Crew
NW790 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - SB: over East Lake - Ph1-S1 | 2024-02-08 08:00 | 2024-02-14 16:00 |  |  | 5 | 0 | 5 | -4 | 1 | Sound Wall Crew
MSE530A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | 2022-08-15 08:00 | 2022-09-06 16:00 | 2022-08-15 08:00 | 2022-09-06 16:00 | 15 | 15 | 0 |  |  | Sub - MSE Wall Crew
MSE580A | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | 2022-09-30 08:00 | 2022-10-14 16:00 | 2022-09-30 08:00 | 2022-10-14 16:00 | 11 | 11 | 0 |  |  | Sub - MSE Wall Crew
MSE740A | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | 2023-01-27 08:00 | 2023-02-10 16:00 |  |  | 11 | 0 | 11 | 29 |  | Sub - MSE Wall Crew
GRD1000 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Earthwork: Temporary Diversion: NB: MLK Ramp B - IPh1 | 2021-11-29 08:00 | 2021-12-01 16:00 | 2021-11-29 08:00 | 2021-12-01 16:00 | 2 | 3 | 0 |  |  | Earthwork Grade Crew - Combo
DRG900 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Temp Drainage: Temporary Diversion: NB: MLK Ramp B - IPh1 | 2022-02-18 08:00 | 2022-02-18 16:00 | 2022-02-18 08:00 | 2022-02-18 16:00 | 1 | 1 | 0 |  |  | Storm Drain Crew
BASE1000 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Limerock: Temporary Diversion: NB: MLK Ramp B - IPh1 | 2022-02-18 08:00 | 2022-03-04 16:00 | 2022-02-18 08:00 | 2022-03-04 16:00 | 2 | 11 | 0 |  |  | Agg Base Crew
PM1000 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.1.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Pavement Marking: Temporary Diversion: NB: MLK Ramp B - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 109 |  | Sub - Striping Crew
LTG1000 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | 2022-02-15 08:00 | 2022-02-17 16:00 | 2022-02-15 08:00 | 2022-02-17 16:00 | 2 | 3 | 0 |  |  | Sub - Electrical Installation Crew
GRD1010 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Earthwork: Temporary Diversion: NB: MLK Ramp C - IPh1 | 2021-11-29 08:00 | 2022-03-19 16:00 | 2021-11-29 08:00 | 2022-03-19 16:00 | 2 | 73 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2580 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Temp Drainage: Temporary Diversion: NB: MLK Ramp C - IPh1 | 2022-02-18 08:00 | 2022-02-18 16:00 | 2022-02-18 08:00 | 2022-02-18 16:00 | 2 | 1 | 0 |  |  | Storm Drain Crew
BASE1010 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Limerock: Temporary Diversion: NB: MLK Ramp C - IPh1 | 2022-03-29 08:00 | 2022-03-30 16:00 | 2022-03-29 08:00 | 2022-03-30 16:00 | 2 | 2 | 0 |  |  | Agg Base Crew
PM1010 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.1.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Pavement Marking: Temporary Diversion: NB: MLK Ramp C - IPh1 | 2022-11-15 08:00 | 2022-11-15 16:00 |  |  | 1 | 0 | 1 | 109 |  | Sub - Striping Crew
LTG1010 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp C - IPh1 | 2022-02-16 08:00 | 2022-02-19 16:00 | 2022-02-16 08:00 | 2022-02-19 16:00 | 3 | 3 | 0 |  |  | Sub - Electrical Installation Crew
GRD1020 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Earthwork: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 2022-04-11 08:00 | 2022-05-14 16:00 | 2022-04-11 08:00 | 2022-05-14 16:00 | 3 | 25 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2590 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 2022-02-18 08:00 | 2022-02-18 16:00 | 2022-02-18 08:00 | 2022-02-18 16:00 | 2 | 1 | 0 |  |  | Storm Drain Crew
BASE1020 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Limerock: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 2022-07-04 08:00 | 2022-07-06 16:00 | 2022-07-04 08:00 | 2022-07-06 16:00 | 3 | 2 | 0 |  |  | Agg Base Crew
PM1020 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2 | 4 | 0 |  |  | Sub - Striping Crew
LTG1020 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.1.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 106 |  | Sub - Electrical Installation Crew
GRD1030 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2 | 14 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2600 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 2022-02-15 08:00 | 2022-02-18 16:00 | 2022-02-15 08:00 | 2022-02-18 16:00 | 2 | 4 | 0 |  |  | Storm Drain Crew
BASE1030 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 2022-02-18 08:00 | 2022-02-18 16:00 | 2022-02-18 08:00 | 2022-02-18 16:00 | 4 | 1 | 0 |  |  | Agg Base Crew
PM1030 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 2022-04-11 08:00 | 2022-04-12 16:00 | 2022-04-11 08:00 | 2022-04-12 16:00 | 2 | 2 | 0 |  |  | Sub - Striping Crew
LTG1030 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 2022-04-11 08:00 | 2022-04-15 16:00 | 2022-04-11 08:00 | 2022-04-15 16:00 | 5 | 5 | 0 |  |  | Sub - Electrical Installation Crew
GRD1040 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2 | 14 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2610 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 2022-02-18 08:00 | 2022-02-19 16:00 | 2022-02-18 08:00 | 2022-02-19 16:00 | 1 | 1 | 0 |  |  | Storm Drain Crew
BASE1040 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 2022-02-18 08:00 | 2022-02-19 16:00 | 2022-02-18 08:00 | 2022-02-19 16:00 | 4 | 1 | 0 |  |  | Agg Base Crew
PM1040 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 2022-06-01 08:00 | 2022-06-02 16:00 | 2022-06-01 08:00 | 2022-06-02 16:00 | 2 | 2 | 0 |  |  | Sub - Striping Crew
LTG1040 | Completed | 3462-FDOT-Owner-12.4.IP1.5.1.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 5 | 5 | 0 |  |  | Sub - Electrical Installation Crew
GRD1050 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Earthwork: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 2022-08-29 08:00 | 2022-09-01 16:00 | 2022-08-29 08:00 | 2022-09-01 16:00 | 1 | 4 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2620 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 2022-09-02 08:00 | 2022-09-02 16:00 | 2022-09-02 08:00 | 2022-09-02 16:00 | 1 | 0 | 0 |  |  | Storm Drain Crew
BASE1050 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Limerock: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 2022-09-01 08:00 | 2022-09-02 16:00 | 2022-09-01 08:00 | 2022-09-02 16:00 | 6 | 1 | 0 |  |  | Agg Base Crew
PM1050 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 42 |  | Sub - Striping Crew
LTG1050 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.1 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 2022-11-16 08:00 | 2022-11-22 16:00 |  |  | 5 | 0 | 5 | 42 |  | Sub - Electrical Installation Crew
GRD1060 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Earthwork: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 2022-09-06 08:00 | 2022-09-06 16:00 | 2022-09-06 08:00 | 2022-09-06 16:00 | 1 | 1 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2630 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 2022-09-07 08:00 | 2022-09-08 16:00 | 2022-09-07 08:00 | 2022-09-08 16:00 | 3 | 2 | 0 |  |  | Storm Drain Crew
BASE1060 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Limerock: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 2022-09-12 08:00 | 2022-09-19 16:00 | 2022-09-12 08:00 | 2022-09-19 16:00 | 6 | 6 | 0 |  |  | Agg Base Crew
PM1060 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 47 |  | Sub - Striping Crew
LTG1060 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.2 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 2022-11-28 08:00 | 2022-12-02 16:00 |  |  | 5 | 0 | 5 | 42 |  | Sub - Electrical Installation Crew
GRD1070 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Earthwork: Temporary Diversion: SB: MLK Ramp D - IPh1 | 2022-03-20 08:00 | 2022-03-21 16:00 | 2022-03-20 08:00 | 2022-03-21 16:00 | 1 | 1 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2640 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Temp Drainage: Temporary Diversion: SB: MLK Ramp D - IPh1 | 2022-04-11 08:00 | 2022-04-15 16:00 | 2022-04-11 08:00 | 2022-04-15 16:00 | 4 | 5 | 0 |  |  | Storm Drain Crew
BASE1070 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Limerock: Temporary Diversion: SB: MLK Ramp D - IPh1 | 2022-03-22 08:00 | 2022-03-23 16:00 | 2022-03-22 08:00 | 2022-03-23 16:00 | 6 | 2 | 0 |  |  | Agg Base Crew
PM1070 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Pavement Marking: Temporary Diversion: SB: MLK Ramp D - IPh1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 52 |  | Sub - Striping Crew
LTG1070 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.3 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp D - IPh1 | 2022-12-05 08:00 | 2022-12-09 16:00 |  |  | 5 | 0 | 5 | 42 |  | Sub - Electrical Installation Crew
GRD1080 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Earthwork: Temporary Diversion: SB: MLK Ramp A - IPh1 | 2021-12-03 08:00 | 2021-12-03 16:00 | 2021-12-03 08:00 | 2021-12-03 16:00 | 2 | 1 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2650 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Temp Drainage: Temporary Diversion: SB: MLK Ramp A - IPh1 | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 4 | 14 | 0 |  |  | Storm Drain Crew
BASE1080 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Limerock: Temporary Diversion: SB: MLK Ramp A - IPh1 | 2022-02-01 08:00 | 2022-05-14 16:00 | 2022-02-01 08:00 | 2022-05-14 16:00 | 6 | 74 | 0 |  |  | Agg Base Crew
PM1080 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Pavement Marking: Temporary Diversion: SB: MLK Ramp A - IPh1 | 2022-09-01 08:00 | 2022-09-06 16:00 | 2022-09-01 08:00 | 2022-09-06 16:00 | 2 | 2 | 0 |  |  | Sub - Striping Crew
LTG1080 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.4 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp A - IPh1 | 2022-09-01 08:00 | 2022-09-09 16:00 | 2022-09-01 08:00 | 2022-09-09 16:00 | 5 | 5 | 0 |  |  | Sub - Electrical Installation Crew
GRD1090 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 2022-09-22 08:00 | 2022-09-22 16:00 | 2022-09-22 08:00 | 2022-09-22 16:00 | 1 | 1 | 0 |  |  | Earthwork Grade Crew - Combo
DRG2660 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 2022-09-26 08:00 | 2022-09-28 16:00 | 2022-09-26 08:00 | 2022-09-28 16:00 | 3 | 3 | 0 |  |  | Storm Drain Crew
BASE1090 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Limerock: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 2022-09-27 08:00 | 2022-10-04 16:00 | 2022-09-27 08:00 | 2022-10-04 16:00 | 6 | 6 | 0 |  |  | Agg Base Crew
PM1090 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 2022-10-07 08:00 | 2022-10-10 16:00 | 2022-10-07 08:00 | 2022-10-10 16:00 | 2 | 2 | 0 |  |  | Sub - Striping Crew
LTG1090 | Completed | 3462-FDOT-Owner-12.4.IP1.5.2.5 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 2022-10-10 08:00 | 2022-10-14 16:00 | 2022-10-10 08:00 | 2022-10-14 16:00 | 5 | 5 | 0 |  |  | Sub - Electrical Installation Crew
GRD1100 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.6 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Earthwork: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 64 |  | Earthwork Grade Crew - Combo
DRG2670 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.6 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 2022-11-15 08:00 | 2022-11-17 16:00 |  |  | 3 | 0 | 3 | 64 |  | Storm Drain Crew
BASE1100 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.6 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Limerock: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 2022-11-18 08:00 | 2022-11-30 16:00 |  |  | 6 | 0 | 6 | 64 |  | Agg Base Crew
PM1100 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.6 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 2022-12-07 08:00 | 2022-12-08 16:00 |  |  | 2 | 0 | 2 | 64 |  | Sub - Striping Crew
LTG1100 | Not Started | 3462-FDOT-Owner-12.4.IP1.5.2.6 | Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 2022-12-09 08:00 | 2022-12-15 16:00 |  |  | 5 | 0 | 5 | 64 |  | Sub - Electrical Installation Crew
PILE370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | H Pile Install - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-02-01 08:00 | 2022-02-04 16:00 | 2022-02-01 08:00 | 2022-02-04 16:00 | 6 | 4 | 0 |  |  | Pile Driving Crew
PILE380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-02-09 08:00 | 2022-02-11 16:00 | 2022-02-09 08:00 | 2022-02-11 16:00 | 6 | 3 | 0 |  |  | Pile Driving Crew
PILE390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | H Pile Install - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2022-02-17 08:00 | 2022-02-18 16:00 | 2022-02-17 08:00 | 2022-02-18 16:00 | 6 | 2 | 0 |  |  | Pile Driving Crew
PILE400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | H Pile Install - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-02-24 08:00 | 2022-02-28 16:00 | 2022-02-24 08:00 | 2022-02-28 16:00 | 6 | 3 | 0 |  |  | Pile Driving Crew
PILE410 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2022-04-11 08:00 | 2022-04-15 16:00 | 2022-04-11 08:00 | 2022-04-15 16:00 | 5 | 5 | 0 |  |  | Pile Driving Crew
PILE420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | H Pile Install - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2022-05-23 08:00 | 2022-05-25 16:00 | 2022-05-23 08:00 | 2022-05-25 16:00 | 5 | 3 | 0 |  |  | Pile Driving Crew
PILE430 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | H Pile Install - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | 2022-05-25 08:00 | 2022-06-01 16:00 | 2022-05-25 08:00 | 2022-06-01 16:00 | 5 | 5 | 0 |  |  | Pile Driving Crew
PILE440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | H Pile Install - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2022-06-20 08:00 | 2022-07-15 16:00 | 2022-06-20 08:00 | 2022-07-15 16:00 | 5 | 19 | 0 |  |  | Pile Driving Crew
PILE450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | H Pile Install - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2022-06-20 08:00 | 2022-07-15 16:00 | 2022-06-20 08:00 | 2022-07-15 16:00 | 5 | 19 | 0 |  |  | Pile Driving Crew
PILE460 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | H Pile Install - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2022-05-14 08:00 | 2022-05-14 16:00 | 2022-05-14 08:00 | 2022-05-14 16:00 | 5 | 0 | 0 |  |  | Pile Driving Crew
PILE470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | H Pile Install - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2022-12-23 08:00 | 2023-01-06 16:00 |  |  | 5 | 0 | 5 | 29 |  | Pile Driving Crew
DS200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Cure 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | 2022-03-20 08:00 | 2022-03-26 16:00 | 2022-03-20 08:00 | 2022-03-26 16:00 | 7 | 7 | 0 |  |  | Sub - Drilled Shaft Crew
DS210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Cure 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | 2022-03-29 08:00 | 2022-04-17 08:00 | 2022-03-29 08:00 | 2022-04-17 08:00 | 7 | 19 | 0 |  |  | Sub - Drilled Shaft Crew
DS220 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Cure 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-09-26 08:00 | 2022-09-30 16:00 | 2022-09-26 08:00 | 2022-09-30 16:00 | 7 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DS230 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Cure 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-04-12 08:00 | 2022-05-14 16:00 | 2022-04-12 08:00 | 2022-05-14 16:00 | 7 | 33 | 0 |  |  | Sub - Drilled Shaft Crew
DS240 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Cure 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-10-03 08:00 | 2022-10-07 16:00 | 2022-10-03 08:00 | 2022-10-07 16:00 | 6 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DS250 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Cure 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2022-09-26 08:00 | 2022-09-30 16:00 | 2022-09-26 08:00 | 2022-09-30 16:00 | 7 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DS260 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Cure 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2022-08-21 08:00 | 2022-08-22 16:00 | 2022-08-21 08:00 | 2022-08-22 16:00 | 7 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
DS270 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Cure 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2022-05-13 08:00 | 2022-05-14 16:00 | 2022-05-13 08:00 | 2022-05-14 16:00 | 7 | 2 | 0 |  |  | Sub - Drilled Shaft Crew
DS280 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Cure 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-05-11 08:00 | 2022-05-14 16:00 | 2022-05-11 08:00 | 2022-05-14 16:00 | 7 | 4 | 0 |  |  | Sub - Drilled Shaft Crew
DS290 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Cure 48" Drilled Shafts 100204 - SB: over MLK - Ph1-S1 | 2022-10-01 08:00 | 2022-10-07 16:00 | 2022-10-01 08:00 | 2022-10-07 16:00 | 7 | 7 | 0 |  |  | Sub - Drilled Shaft Crew
CB100 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Floribraska | 2021-11-01 08:00 | 2021-11-06 16:00 | 2021-11-01 08:00 | 2021-11-06 16:00 | 3 | 5 | 0
CB110 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - E. Lake | 2021-10-28 08:00 | 2021-10-29 16:00 | 2021-10-28 08:00 | 2021-10-29 16:00 | 3 | 2 | 0
CB120 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - MLK | 2021-11-15 08:00 | 2021-12-07 16:00 | 2021-11-15 08:00 | 2021-12-07 16:00 | 6 | 14 | 0
CB130 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Chelsea | 2021-11-08 08:00 | 2021-11-12 16:00 | 2021-11-08 08:00 | 2021-11-12 16:00 | 6 | 4 | 0
CB140 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Osborne | 2021-11-24 08:00 | 2021-12-08 16:00 | 2021-11-24 08:00 | 2021-12-08 16:00 | 6 | 8 | 0
CB150 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Hillsborough | 2022-02-01 08:00 | 2022-02-11 16:00 | 2022-02-01 08:00 | 2022-02-11 16:00 | 9 | 9 | 0
GW10 | Completed | 3462-FDOT-Owner-12.2.1.2.2 | Preconstruction: Procurement: Walls: Gravity Walls | Prepare Shop Drawings / Submittals: Gravity Walls | 2021-09-13 08:00 | 2021-10-05 16:00 | 2021-09-13 08:00 | 2021-10-05 16:00 | 25 | 17 | 0
GW30 | Completed | 3462-FDOT-Owner-12.2.1.2.2 | Preconstruction: Procurement: Walls: Gravity Walls | Procurement: Gravity Walls | 2021-10-21 08:00 | 2021-11-04 16:00 | 2021-10-21 08:00 | 2021-11-04 16:00 | 30 | 11 | 0
GW20 | Completed | 3462-FDOT-Owner-12.2.1.2.2 | Preconstruction: Procurement: Walls: Gravity Walls | Review & Approve Shop Drawings / Submittals: Gravity Walls (Duration = 25 Calendar Days) | 2021-10-06 08:00 | 2021-10-20 16:00 | 2021-10-06 08:00 | 2021-10-20 16:00 | 25 | 15 | 0
MSE10 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls (Delete) | 2022-02-21 08:00 | 2022-02-23 08:00 | 2022-02-21 08:00 | 2022-02-23 08:00 | 0 | 2 | 0
MSE30 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls (Delete) | 2022-04-15 08:00 | 2022-04-16 08:00 | 2022-04-15 08:00 | 2022-04-16 08:00 | 0 | 1 | 0
MSE20 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | 2022-02-21 08:00 | 2022-02-23 08:00 | 2022-02-21 08:00 | 2022-02-23 08:00 | 0 | 2 | 0
PM1110 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | 2025-04-02 08:00 | 2025-04-22 16:00 |  |  | 15 | 0 | 15 | -4 | 1 | Sub - Striping Crew
PM1120 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | 2025-04-23 08:00 | 2025-05-13 16:00 |  |  | 15 | 0 | 15 | -4 | 1 | Sub - Striping Crew
PUNCH10 | Not Started | 3462-FDOT-Owner-12.0 | Project Milestones | Punch-out Items | 2025-05-21 08:00 | 2025-06-18 16:00 |  |  | 20 | 0 | 20 | -4 | 1
PAV540 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Cure Friction Course - Project Limits - Ph3 | 2025-03-02 08:00 | 2025-03-11 16:00 |  |  | 10 | 0 | 10 | -6 | 3 | Sub - Asphalt Milling Crew
SGN90A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-101 / 739+29 | 2022-08-23 08:00 | 2022-09-16 16:00 | 2022-08-23 08:00 | 2022-09-16 16:00 | 15 | 17 | 0
SGN110A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-103 / 750+92 | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 15 | 10 | 0
SGN140A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-105 / 775+55 | 2022-06-20 08:00 | 2022-07-11 16:00 | 2022-06-20 08:00 | 2022-07-11 16:00 | 15 | 15 | 0
SGN190A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-106 / 811+90 | 2022-07-25 08:00 | 2022-07-27 16:00 | 2022-07-25 08:00 | 2022-07-27 16:00 | 15 | 3 | 0
SGN170A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-107 / 800+70 | 2022-06-18 08:00 | 2022-07-05 16:00 | 2022-06-18 08:00 | 2022-07-05 16:00 | 15 | 11 | 0
SGN220A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-107 / 833+46 | 2022-06-18 08:00 | 2022-07-05 16:00 | 2022-06-18 08:00 | 2022-07-05 16:00 | 15 | 11 | 0
SGN210A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-108 / 825+75 | 2022-06-18 08:00 | 2022-07-05 16:00 | 2022-06-18 08:00 | 2022-07-05 16:00 | 15 | 11 | 0
SGN200A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHB-01 / 818+78 | 2022-08-22 08:00 | 2022-09-16 16:00 | 2022-08-22 08:00 | 2022-09-16 16:00 | 15 | 18 | 0
SGN180A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-105 / 808+47 | 2022-07-25 08:00 | 2022-08-01 16:00 | 2022-07-25 08:00 | 2022-08-01 16:00 | 15 | 6 | 0
SGN160A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-104 / 792+45 | 2022-08-19 08:00 | 2022-09-16 16:00 | 2022-08-19 08:00 | 2022-09-16 16:00 | 15 | 19 | 0
SGN150A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-106 / 783+35 | 2022-06-18 08:00 | 2022-07-11 16:00 | 2022-06-18 08:00 | 2022-07-11 16:00 | 15 | 15 | 0
SGN130A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-104 / 771+34 | 2022-06-19 08:00 | 2022-07-15 16:00 | 2022-06-19 08:00 | 2022-07-15 16:00 | 15 | 19 | 0
SGN120A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-103 / 758+73 | 2022-08-25 08:00 | 2022-09-16 16:00 | 2022-08-25 08:00 | 2022-09-16 16:00 | 15 | 15 | 0
SGN100A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-102 / 745+96 | 2022-08-24 08:00 | 2022-09-16 16:00 | 2022-08-24 08:00 | 2022-09-16 16:00 | 15 | 16 | 0
SGN80A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-102 / 736+00 | 2022-08-26 08:00 | 2022-09-16 16:00 | 2022-08-26 08:00 | 2022-09-16 16:00 | 15 | 14 | 0
SGN70A | Completed | 3462-FDOT-Owner-12.2.1.4.2.3 | Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-101 / 723+54 | 2022-03-21 08:00 | 2022-05-14 16:00 | 2022-03-21 08:00 | 2022-05-14 16:00 | 15 | 40 | 0
WL370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Wall Lagging & Tie-Backs - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-02-18 08:00 | 2022-05-14 16:00 | 2022-02-18 08:00 | 2022-05-14 16:00 | 8 | 61 | 0 |  |  | Pile Driving Crew
WL380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Wall Lagging & Tie-Backs - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-02-18 08:00 | 2022-05-14 16:00 | 2022-02-18 08:00 | 2022-05-14 16:00 | 8 | 61 | 0 |  |  | Pile Driving Crew
WL390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Wall Lagging & Tie-Backs - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 2022-02-21 08:00 | 2022-04-15 16:00 | 2022-02-21 08:00 | 2022-04-15 16:00 | 8 | 40 | 0 |  |  | Pile Driving Crew
WL400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Wall Lagging & Tie-Backs - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-03-02 08:00 | 2022-05-14 16:00 | 2022-03-02 08:00 | 2022-05-14 16:00 | 8 | 53 | 0 |  |  | Pile Driving Crew
WL410 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Wall Lagging & Tie-Backs - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 2022-06-01 08:00 | 2022-06-10 16:00 | 2022-06-01 08:00 | 2022-06-10 16:00 | 5 | 8 | 0 |  |  | Pile Driving Crew
WL420 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Wall Lagging & Tie-Backs - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 40 |  | Pile Driving Crew
WL430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Wall Lagging & Tie-Backs - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | 2022-11-21 08:00 | 2022-11-30 16:00 |  |  | 5 | 0 | 5 | 40 |  | Pile Driving Crew
WL440 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Wall Lagging & Tie-Backs - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2022-07-15 08:00 | 2022-07-28 16:00 | 2022-07-15 08:00 | 2022-07-28 16:00 | 5 | 10 | 0 |  |  | Pile Driving Crew
WL450 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 | Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Wall Lagging & Tie-Backs - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-28 16:00 | 2022-07-11 08:00 | 2022-07-28 16:00 | 5 | 14 | 0 |  |  | Pile Driving Crew
WL460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Wall Lagging & Tie-Backs - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2022-12-22 08:00 | 2023-01-05 16:00 |  |  | 5 | 0 | 5 | 23 |  | Pile Driving Crew
WL470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2023-02-06 08:00 | 2023-02-15 16:00 |  |  | 8 | 0 | 8 | 23 |  | Pile Driving Crew
WBO-TECO-01 | Not Started | 3462-FDOT-Owner-12.3.3.1 | TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #1) 4" Coated Steel GM & 8" Coated Steel Casing (807+21 - 136' RT) - To be retired and removed where accessible | 2022-11-13 08:00 | 2022-11-14 16:00 |  |  | 2 | 0 | 2 | 508
WBO-TECO-02 | Not Started | 3462-FDOT-Owner-12.3.3.1 | TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #2) 4" Coated Steel GM & 8" Coated Steel Casing (807+25 - 127' LT) - To be retired and removed where accessible | 2023-01-13 08:00 | 2023-01-14 16:00 |  |  | 2 | 0 | 2 | 447
WBO-TECO-03 | Not Started | 3462-FDOT-Owner-12.3.3.1 | TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #3) Retired 4" Coated Steel GM (826+93 - 114' LT) - To remove where accessible | 2022-11-16 08:00 | 2022-11-16 16:00 |  |  | 1 | 0 | 1 | 506
WBO-TECO-04 | Not Started | 3462-FDOT-Owner-12.3.3.1 | TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #4) Unknown 1" Facility (826+93 - 114' LT) - To investigate & remove where accessible if determined to be Teco | 2022-11-16 08:00 | 2022-11-16 16:00 |  |  | 1 | 0 | 1 | 506
WBO-TECO-05 | Not Started | 3462-FDOT-Owner-12.3.3.1 | TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #5) Retired 4" Coated Steel GM (827+05 102' RT) - To remove where accessible | 2022-11-16 08:00 | 2022-11-16 16:00 |  |  | 1 | 0 | 1 | 506
WBO-TECO-06 | Not Started | 3462-FDOT-Owner-12.3.3.1 | TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | TECO Project ID: 431821-2-52-01 Work Complete |  | 2023-01-14 16:00 |  |  | 0 | 0 | 0 | 447
WBO-TECO-10 | Not Started | 3462-FDOT-Owner-12.3.3.2 | TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #1) 6" Polyethylene GM x 10" Steel Casing & 2" Steel Casing Vent (728+20 - 124.0' RT) - Offset 18" below 30" storm | 2022-11-13 08:00 | 2022-11-17 16:00 |  |  | 5 | 0 | 5 | 505
WBO-TECO-11 | Not Started | 3462-FDOT-Owner-12.3.3.2 | TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #2) Retired 2" Coated Steel GM x 6" Coated Steel Casing (776+57 - 94' RT) - Remove where accessible | 2022-11-13 08:00 | 2022-11-13 16:00 |  |  | 1 | 0 | 1 | 509
WBO-TECO-12 | Not Started | 3462-FDOT-Owner-12.3.3.2 | TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #3) Retired 2" Coated Steel GM (777+54 - 117' LT) - Remove where accessible | 2023-02-15 08:00 | 2023-02-15 16:00 |  |  | 1 | 0 | 1 | 415
WBO-TECO-13 | Not Started | 3462-FDOT-Owner-12.3.3.2 | TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #4) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+13 - 102' RT) - Remove where accessible | 2022-11-13 08:00 | 2022-11-13 16:00 |  |  | 1 | 0 | 1 | 509
WBO-TECO-14 | Not Started | 3462-FDOT-Owner-12.3.3.2 | TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #5) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+15 - 119' LT) - Remove where accessible | 2023-01-13 08:00 | 2023-01-13 16:00 |  |  | 1 | 0 | 1 | 448
WBO-TECO-15 | Not Started | 3462-FDOT-Owner-12.3.3.2 | TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | TECO Project ID: 443770-1-52-01 Work Complete |  | 2023-02-15 16:00 |  |  | 0 | 0 | 0 | 415
WBO-TEC-11 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #1) Overhead 230KV Pole Foundation (37+15-R64) - Pouring of Foundation & Cure Time | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 30 | 15 | 0
WBO-TEC-12 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #2) Overhead 230KV Pole (37+15-R64) - Install Transmission Pole | 2022-02-22 08:00 | 2022-03-10 16:00 | 2022-02-22 08:00 | 2022-03-10 16:00 | 6 | 17 | 0
WBO-TEC-13 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #3) Overhead 230KV Conductor (37+15-64R to 36+51-R310) - Install Overhead 230KV Conductor | 2022-03-16 08:00 | 2022-03-18 16:00 | 2022-03-16 08:00 | 2022-03-18 16:00 | 5 | 3 | 0
WBO-TEC-14 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #4) Overhead 230KV Conductor (33+85-49R to 37+15-64R) - Install Overhead 230KV Conductor | 2022-03-18 08:00 | 2022-03-18 16:00 | 2022-03-18 08:00 | 2022-03-18 16:00 | 5 | 1 | 0
WBO-TEC-15 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #5) Overhead 230KV Conductor (33+85-49R to 37+15+64R) - Remove 230KV Conductor | 2022-03-14 08:00 | 2022-03-18 16:00 | 2022-03-14 08:00 | 2022-03-18 16:00 | 2 | 5 | 0
WBO-TEC-16 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #6) Stub Pole/Span Guys/Anchors (37+07-40L) - Removal | 2022-09-05 08:00 | 2022-09-06 16:00 | 2022-09-05 08:00 | 2022-09-06 16:00 | 2 | 2 | 0
WBO-TEC-17 | Completed | 3462-FDOT-Owner-12.3.2.1 | Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #7) Steel Transmission Pole/Guys/Anchors (37+9-53R) - Removal | 2022-09-19 08:00 | 2022-09-21 16:00 | 2022-09-19 08:00 | 2022-09-21 16:00 | 3 | 3 | 0
WBO-TEC-20 | Completed | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #1) 13.2 KV Underground (8100+73+208L to 810+73-230R) - Install UG conduit & conductor | 2022-02-21 08:00 | 2022-05-14 16:00 | 2022-02-21 08:00 | 2022-05-14 16:00 | 30 | 83 | 0
WBO-TEC-21 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #2) 13.2 KV Underground (820+50-217L to 820+50-230R) - Install UG conduit & conductor | 2022-11-13 08:00 | 2022-12-12 16:00 |  |  | 30 | 0 | 30 | 470
WBO-TEC-22 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #3) OH to UG Pole & 13.2KV Conductor (810+73-208L) - Install terminal pole & conductor | 2022-12-13 08:00 | 2022-12-14 16:00 |  |  | 2 | 0 | 2 | 470
WBO-TEC-23 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #4) OH to UG Pole & 13.2KV Conductor (820+50-217L) - Install terminal pole & conductor | 2022-12-15 08:00 | 2022-12-16 16:00 |  |  | 2 | 0 | 2 | 470
WBO-TEC-24 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #5) OH to UG Pole & 13.2KV Conductor (810+73-230R) - Install terminal pole & conductor | 2022-12-17 08:00 | 2022-12-18 16:00 |  |  | 2 | 0 | 2 | 470
WBO-TEC-25 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #6) OH to UG Pole & 13.2KV Conductor (810+50-230R) - Install terminal pole & conductor | 2022-12-19 08:00 | 2022-12-20 16:00 |  |  | 2 | 0 | 2 | 470
WBO-TEC-26 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #7) Overhead 13.2KV Poles & Conductors (810+73-178L to 810+73-198R) - Remove OH conductors & poles | 2022-12-21 08:00 | 2022-12-21 16:00 |  |  | 1 | 0 | 1 | 470
WBO-TEC-27 | Not Started | 3462-FDOT-Owner-12.3.2.2 | Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #8) Overhead 13.2KV Poles & Conductors (820+50-187L to 820+50-20R) - Remove OH conductors & poles | 2022-12-22 08:00 | 2022-12-22 16:00 |  |  | 1 | 0 | 1 | 470
WBO-CTWD-10 | Not Started | 3462-FDOT-Owner-12.3.1.1 | City of Tampa Wastewater Department Project ID: 431821-02-52-01 (Prior to starting work) | (Act #1) Ex. 12" Concrete Wastewater (815+14.86-174' RT to 815+39.86-173.71' RT) - COT Identified Line to Remain | 2022-11-13 08:00 | 2022-11-13 08:00 |  |  | 0 | 0 | 0 | 943
BP100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | 2022-11-07 08:00 | 2022-11-08 08:00 | 2022-11-07 08:00 | 2022-11-08 08:00 | 1 | 1 | 0 |  |  | Erection Crew
BP110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | 2022-11-13 21:00 | 2022-11-14 05:00 |  |  | 1 | 0 | 1 | 8 |  | Erection Crew
BP120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | 2022-12-11 21:00 | 2022-12-12 05:00 |  |  | 1 | 0 | 1 | 11 |  | Erection Crew
BP130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-01-04 21:00 | 2023-01-05 05:00 |  |  | 1 | 0 | 1 | 23 |  | Erection Crew
BP140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-10-14 08:00 | 2022-10-15 16:00 | 2022-10-14 08:00 | 2022-10-15 16:00 | 1 | 0 | 0 |  |  | Erection Crew
BP150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-24 21:00 | 2023-01-25 05:00 |  |  | 1 | 0 | 1 | 56 |  | Erection Crew
BP160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 2023-01-31 21:00 | 2023-02-01 05:00 |  |  | 1 | 0 | 1 | 65 |  | Erection Crew
BP170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 2023-05-09 21:00 | 2023-05-10 05:00 |  |  | 1 | 0 | 1 | 39 |  | Erection Crew
BP180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-05-10 05:00 | 2023-05-11 04:00 |  |  | 1 | 0 | 1 | 57 |  | Erection Crew
BP190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | 2023-05-11 04:00 | 2023-05-12 03:00 |  |  | 1 | 0 | 1 | 62 |  | Erection Crew
EC100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Lighting Conduit at Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | 2023-01-24 08:00 | 2023-01-25 16:00 |  |  | 2 | 0 | 2 | 35 |  | Sub - Electrical Installation Crew
EC130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 2023-05-03 08:00 | 2023-05-04 16:00 |  |  | 2 | 0 | 2 | 27 |  | Concrete Barrier Crew
EC180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 2023-12-12 08:00 | 2023-12-13 16:00 |  |  | 2 | 0 | 2 | -1 | 22 | Sub - Electrical Installation Crew
PILE700 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Install H-Pile for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 2022-02-15 08:00 | 2022-02-18 16:00 | 2022-02-15 08:00 | 2022-02-18 16:00 | 10 | 4 | 0 |  |  | CIP Wall Crew
LAG700 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Install Lagging & Anchors for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 2022-01-31 08:00 | 2022-05-11 16:00 | 2022-01-31 08:00 | 2022-05-11 16:00 | 10 | 73 | 0 |  |  | CIP Wall Crew
PILE710 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Install H-Pile for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 2022-02-01 08:00 | 2022-03-18 16:00 | 2022-02-01 08:00 | 2022-03-18 16:00 | 10 | 34 | 0 |  |  | CIP Wall Crew
LAG710 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Install Lagging & Anchors for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 2022-04-12 08:00 | 2022-05-14 16:00 | 2022-04-12 08:00 | 2022-05-14 16:00 | 10 | 24 | 0 |  |  | CIP Wall Crew
PILE720 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Install H-Pile for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 2022-03-14 08:00 | 2022-04-15 16:00 | 2022-03-14 08:00 | 2022-04-15 16:00 | 10 | 25 | 0 |  |  | CIP Wall Crew
LAG720 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.3 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Install Lagging & Anchors for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 2022-04-14 08:00 | 2022-06-11 16:00 | 2022-04-14 08:00 | 2022-06-11 16:00 | 10 | 41 | 0 |  |  | CIP Wall Crew
PILE730 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Install H-Pile for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 2022-02-25 08:00 | 2022-03-18 16:00 | 2022-02-25 08:00 | 2022-03-18 16:00 | 10 | 16 | 0 |  |  | CIP Wall Crew
LAG730 | Completed | 3462-FDOT-Owner-12.4.P1.1.3.2.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Install Lagging & Anchors for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 2022-04-15 08:00 | 2022-08-18 16:00 | 2022-04-15 08:00 | 2022-08-18 16:00 | 10 | 88 | 0 |  |  | CIP Wall Crew
CURB100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Install Curb & Gutter Type E & F - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-10-14 08:00 | 2022-10-20 16:00 | 2022-10-14 08:00 | 2022-10-20 16:00 | 5 | 7 | 0 |  |  | Concrete Paving Crews
GR100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Install Guardrail - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 2022-11-01 08:00 | 2022-11-02 16:00 | 2022-11-01 08:00 | 2022-11-02 16:00 | 3 | 2 | 0 |  |  | Sub - Guardrail Crew
CURB110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Install Curb & Gutter Type F - MLK Ramp B - Ph1-S2 | 2023-07-25 08:00 | 2023-07-28 16:00 |  |  | 4 | 0 | 4 | 4 |  | Concrete Paving Crews
CC100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Crash Cushions - NB: 748+30-757+10 - Ph1-S1 | 2023-05-01 08:00 | 2023-05-05 16:00 |  |  | 5 | 0 | 5 | 351 |  | Sub - Guardrail Crew
CURB120 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | 2023-09-12 08:00 | 2023-09-18 16:00 |  |  | 5 | 0 | 5 | 4 |  | Concrete Paving Crews
GR110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Install Guardrail - MLK Ramp C - Ph1-S2 | 2023-09-29 08:00 | 2023-10-03 16:00 |  |  | 3 | 0 | 3 | 98 |  | Sub - Guardrail Crew
BW170B | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.2 | Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall (NB: 96+36.16 to C&G Type F) - MLK Ramp B - Ph1-S2 | 2023-07-13 08:00 | 2023-07-24 16:00 |  |  | 8 | 0 | 8 | 4 |  | Concrete Barrier Crew
BW220B | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall (NB: 364+63.60 to 110+00.83) - MLK Ramp B - Ph1-S2 | 2023-08-29 08:00 | 2023-09-11 16:00 |  |  | 8 | 0 | 8 | 4 |  | Concrete Barrier Crew
CAP100 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.3 | Construction: Phase 1: Stage 2: MLK Ramp C | Install Concrete Cap - MLK Ramp C - Ph1-S2 | 2023-09-19 08:00 | 2023-09-21 16:00 |  |  | 3 | 0 | 3 | 106 |  | Concrete Paving Crews
BW360B | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | 2023-11-21 08:00 | 2023-12-05 16:00 |  |  | 8 | 0 | 8 | 50 |  | Concrete Barrier Crew
CURB130 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Curb & Gutter Type F - Hillsborough Ramp B - Ph1-S2 | 2023-12-06 08:00 | 2023-12-14 16:00 |  |  | 7 | 0 | 7 | 50 |  | Concrete Paving Crews
CAP110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Concrete Cap - Hillsborough Ramp B - Ph1-S2 | 2023-12-15 08:00 | 2023-12-19 16:00 |  |  | 3 | 0 | 3 | 50 |  | Concrete Paving Crews
CC110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.4 | Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Crash Cushion - Hillsborough Ramp B - Ph1-S2 | 2024-03-12 08:00 | 2024-03-13 16:00 |  |  | 2 | 0 | 2 | 128 |  | Sub - Guardrail Crew
GR120 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.5 | Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Install Guardrail - Hillsborough Ramp C2 - Ph1-S2 | 2023-12-22 08:00 | 2024-01-10 16:00 |  |  | 7 | 0 | 7 | 177 |  | Sub - Guardrail Crew
GR130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Guardrail - NB: 159+48.98-163+10.72 - Ph1-S1 | 2023-09-14 08:00 | 2023-09-21 16:00 |  |  | 6 | 0 | 6 | 332 |  | Sub - Guardrail Crew
TBW100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Set Temp Concrete Barrier Wall - Type K - NB: 177+89.06-181+78.62 - Ph1-S1 | 2024-01-04 08:00 | 2024-01-05 16:00 |  |  | 2 | 0 | 2 | 267 |  | Concrete Barrier Crew
BW840B | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | 2023-11-09 08:00 | 2023-11-27 16:00 |  |  | 9 | 0 | 9 | 58 |  | Concrete Barrier Crew
CURB140 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Curb & Gutter Type F - Hillsborough Ramp D - Ph1-S2 | 2024-01-23 08:00 | 2024-01-31 16:00 |  |  | 7 | 0 | 7 | 26 |  | Concrete Paving Crews
CAP120 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Concrete Cap - Hillsborough Ramp D - Ph1-S2 | 2024-02-01 08:00 | 2024-02-05 16:00 |  |  | 3 | 0 | 3 | 31 |  | Concrete Paving Crews
GC100 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | 2024-02-06 08:00 | 2024-02-12 16:00 |  |  | 5 | 0 | 5 | 31 |  | Concrete Paving Crews
CC120 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.7 | Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Crash Cushion - Hillsborough Ramp D - Ph1-S2 | 2024-03-28 08:00 | 2024-03-29 16:00 |  |  | 2 | 0 | 2 | 131 |  | Sub - Guardrail Crew
BW930A | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | 2024-02-22 08:00 | 2024-02-29 16:00 |  |  | 6 | 0 | 6 | 5 |  | Concrete Barrier Crew
CURB150 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | 2024-03-01 08:00 | 2024-03-13 16:00 |  |  | 9 | 0 | 9 | 5 |  | Concrete Paving Crews
CAP130 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Concrete Cap - Hillsborough Ramp A - Ph1-S2 | 2024-03-14 08:00 | 2024-03-18 16:00 |  |  | 3 | 0 | 3 | 9 |  | Concrete Paving Crews
GR140 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.8 | Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Guardrail - Hillsborough Ramp A - Ph1-S2 | 2024-03-14 08:00 | 2024-03-20 16:00 |  |  | 5 | 0 | 5 | 7 |  | Sub - Guardrail Crew
GR150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Reset Guardrail (South of Swale 1A) - SB: 788+09-800+00 - Ph1-S1 | 2023-10-30 08:00 | 2023-11-03 16:00 |  |  | 5 | 0 | 5 | 317 |  | Sub - Guardrail Crew
BW1050A | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | 2024-03-13 08:00 | 2024-03-20 16:00 |  |  | 6 | 0 | 6 | 0 |  | Concrete Barrier Crew
CURB160 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Install Curb & Gutter Type F (?) - MLK Ramp D - Ph1-S2 | 2024-03-21 08:00 | 2024-03-28 16:00 |  |  | 6 | 0 | 6 | 0 |  | Concrete Paving Crews
CAP140 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Install Concrete Cap - MLK Ramp D - Ph1-S2 | 2024-03-29 08:00 | 2024-04-02 16:00 |  |  | 3 | 0 | 3 | 1 |  | Concrete Paving Crews
CC130 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Install Crash Cushion - MLK Ramp D - Ph1-S2 | 2024-04-09 08:00 | 2024-04-10 16:00 |  |  | 2 | 0 | 2 | 133 |  | Sub - Guardrail Crew
GC110 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.9 | Construction: Phase 1: Stage 2: MLK Ramp D | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | 2024-03-29 08:00 | 2024-04-03 16:00 |  |  | 4 | 0 | 4 | 0 |  | Concrete Paving Crews
BW1110A | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | 2024-03-25 08:00 | 2024-04-03 16:00 |  |  | 8 | 0 | 8 | -4 | 6 | Concrete Barrier Crew
CURB170 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Install Curb & Gutter Type F & D - MLK Ramp A - Ph1-S2 | 2024-04-04 08:00 | 2024-04-09 16:00 |  |  | 4 | 0 | 4 | -4 | 6 | Concrete Paving Crews
CAP150 | Not Started | 3462-FDOT-Owner-12.4.P1.2.2.10 | Construction: Phase 1: Stage 2: MLK Ramp A | Install Concrete Cap - MLK Ramp A - Ph1-S2 | 2024-04-10 08:00 | 2024-04-12 16:00 |  |  | 3 | 0 | 3 | -4 | 6 | Concrete Paving Crews
GR160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | 2024-01-17 08:00 | 2024-01-22 16:00 |  |  | 4 | 0 | 4 | 32 |  | Sub - Guardrail Crew
CC140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Crash Cushion - SB: 709+50-721+43 - Ph1-S1 | 2024-04-03 08:00 | 2024-04-09 16:00 |  |  | 5 | 0 | 5 | -2 | 17 | Sub - Guardrail Crew
TBW110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Set Temp Concrete Barrier Wall - Type K - SB: 709+50-721+43 - Ph1-S1 | 2024-04-03 08:00 | 2024-04-04 16:00 |  |  | 2 | 0 | 2 | 1 |  | Concrete Barrier Crew
MOW | In Progress | 3462-FDOT-Owner-12.1 | MOT Summary | Mowing | 2021-10-25 08:00 | 2025-06-18 16:00 | 2021-10-25 08:00 |  | 1292 | 384 | 949 | -6
LITTER | In Progress | 3462-FDOT-Owner-12.1 | MOT Summary | Litter Clean Up | 2021-10-25 08:00 | 2025-06-18 16:00 | 2021-10-25 08:00 |  | 1292 | 384 | 949 | -6
FEN100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | 2024-03-08 08:00 | 2024-03-21 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sub - Fence Installation Crew
FEN110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Install Fencing @ East Lake Ave. - South Side - Ph1-S1-S1 | 2022-11-16 08:00 | 2022-11-18 16:00 |  |  | 3 | 0 | 3 | 400 |  | Sub - Fence Installation Crew
FEN130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Install Fencing @ Chelsea St.- South Side - Ph1-S1-S1 | 2022-11-15 08:00 | 2022-11-17 16:00 |  |  | 3 | 0 | 3 | 407 |  | Sub - Fence Installation Crew
FEN140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Install Fencing @ E. Osborne Ave - South Side - Ph1-S1-S1 | 2022-11-15 08:00 | 2022-11-17 16:00 |  |  | 3 | 0 | 3 | 410 |  | Sub - Fence Installation Crew
FEN160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Install 4' Mesh Fencing & Gate @ Floribraska - North Side - Ph1-S1-S2 | 2022-12-16 08:00 | 2022-12-20 16:00 |  |  | 3 | 0 | 3 | 87 |  | Sub - Fence Installation Crew
FEN170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.2 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Install Fencing @ East Lake Ave. - North Side - Ph1-S1-S2 | 2022-12-01 08:00 | 2022-12-05 16:00 |  |  | 3 | 0 | 3 | 98 |  | Sub - Fence Installation Crew
FEN190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.4 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Install Fencing @ Chelsea St.- North Side - Ph1-S1-S2 | 2022-12-19 08:00 | 2022-12-21 16:00 |  |  | 3 | 0 | 3 | 86 |  | Sub - Fence Installation Crew
FEN200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.5 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Install Fencing @ E. Osborne Ave - North Side - Ph1-S1-S2 | 2023-01-04 08:00 | 2023-01-06 16:00 |  |  | 3 | 0 | 3 | 80 |  | Sub - Fence Installation Crew
DP100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form & Pour Ditch Pavement - NB: 722+83-735+00 - Ph1-S1 | 2023-03-09 08:00 | 2023-03-17 16:00 |  |  | 7 | 0 | 7 | 410 |  | Concrete Paving Crews
DP110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form & Pour Ditch Pavement - NB: 735+46-746+91 - Ph1-S1 | 2023-03-15 08:00 | 2023-03-20 16:00 |  |  | 4 | 0 | 4 | 414 |  | Concrete Paving Crews
RR100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Rip-Rap - NB: 751-752 - Ph1-S1 | 2023-03-30 08:00 | 2023-03-31 16:00 |  |  | 2 | 0 | 2 | 410 |  | DRAINAGE CREWS
DP120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form & Pour Ditch Pavement - NB: 761+67-767+00 - Ph1-S1 | 2023-04-28 08:00 | 2023-05-03 16:00 |  |  | 4 | 0 | 4 | 398 |  | Concrete Paving Crews
DP130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form & Pour Ditch Pavement - NB: 788+09-800+00 - Ph1-S1 | 2023-06-15 08:00 | 2023-06-26 16:00 |  |  | 8 | 0 | 8 | 382 |  | Concrete Paving Crews
FENCE10 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | 2024-01-26 08:00 | 2024-01-31 16:00 |  |  | 4 | 0 | 4 | 228 |  | Sub - Fence Installation Crew
RR110 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.1.2 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Install Rip-Rap - NB: 801 - 802 - IPh1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 37 |  | DRAINAGE CREWS
FENCE20 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Repair Fence / Install 6' Black Vinyl Fence & Gate at Ramp HILLSC1 - NB: 815+20-839+61 - Ph1-S1 | 2024-02-01 08:00 | 2024-02-06 16:00 |  |  | 4 | 0 | 4 | 228 |  | Sub - Fence Installation Crew
FENCE30 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - NB: 827+13.67-832+53.77 - Ph1-S1 | 2024-02-07 08:00 | 2024-02-13 16:00 |  |  | 5 | 0 | 5 | 228 |  | Sub - Fence Installation Crew
DP140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Form & Pour Ditch Pavement (3 Locations) - NB: 815+20-839+61 - Ph1-S1 | 2023-08-15 08:00 | 2023-08-23 16:00 |  |  | 7 | 0 | 7 | 351 |  | Concrete Paving Crews
RR120 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.1 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Install Rip-Rap - SB: 834 - 836 - Swale 3B - IPh1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 47 |  | DRAINAGE CREWS
FENCE40 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 815+20-839+61 - Ph1-S1 | 2024-02-09 08:00 | 2024-02-16 16:00 |  |  | 6 | 0 | 6 | 233 |  | Sub - Fence Installation Crew
RR130 | Not Started | 3462-FDOT-Owner-12.4.IP1.6.2.3 | Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Install Rip-Rap (2 Locations) - SB:805 - 806 - Swale 1A - IPh 1 | 2022-11-22 08:00 | 2022-11-29 16:00 |  |  | 3 | 0 | 3 | 50 |  | DRAINAGE CREWS
DP150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form & Pour Ditch Pavement - SB: 800+00-813+16 - Ph1-S1 | 2023-09-19 08:00 | 2023-09-22 16:00 |  |  | 4 | 0 | 4 | 316 |  | Concrete Paving Crews
FENCE50 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | 2024-02-23 08:00 | 2024-02-27 16:00 |  |  | 3 | 0 | 3 | 229 |  | Sub - Fence Installation Crew
FENCE60 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | 2024-02-28 08:00 | 2024-03-01 16:00 |  |  | 3 | 0 | 3 | 229 |  | Sub - Fence Installation Crew
FENCE70 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 790+73.28-791+94.03 - Ph1-S1 | 2024-03-04 08:00 | 2024-03-05 16:00 |  |  | 2 | 0 | 2 | 229 |  | Sub - Fence Installation Crew
DP160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Form & Pour Ditch Pavement - SB: 774+82-780+00 - Ph1-S1 | 2023-10-31 08:00 | 2023-11-02 16:00 |  |  | 3 | 0 | 3 | 328 |  | Concrete Paving Crews
FENCE80 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | 2024-03-08 08:00 | 2024-03-13 16:00 |  |  | 4 | 0 | 4 | 233 |  | Sub - Fence Installation Crew
FENCE90 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 748+30-757+10 - Ph1-S1 | 2024-04-05 08:00 | 2024-04-10 16:00 |  |  | 4 | 0 | 4 | 233 |  | Sub - Fence Installation Crew
FENCE100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 739+739+79.12-739+81.53 - Ph1-S1 | 2024-04-26 08:00 | 2024-04-26 16:00 |  |  | 1 | 0 | 1 | 227 |  | Sub - Fence Installation Crew
FENCE110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 727+93.05-736+99.11 - Ph1-S1 | 2024-04-29 08:00 | 2024-05-02 16:00 |  |  | 4 | 0 | 4 | 227 |  | Sub - Fence Installation Crew
RBS120 | Not Started | 3462-FDOT-Owner-12.4.P2.1 | Construction: Phase 2: Milestones | Ground-In Rumble Strips - Median | 2025-01-16 08:00 | 2025-01-24 16:00 |  |  | 6 | 0 | 6 | 8 |  | Sub - Rumble Strip Crew
RBS100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Ground-In Rumble Strips - NB | 2023-12-12 08:00 | 2023-12-18 16:00 |  |  | 5 | 0 | 5 | 66 |  | Sub - Rumble Strip Crew
RBS110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Ground-In Rumble Strips - SB | 2024-01-12 08:00 | 2024-01-19 16:00 |  |  | 5 | 0 | 5 | 55 |  | Sub - Rumble Strip Crew
R3950 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Form / Pour Slope Pavement Leave-Outs @ Floribraska - South & North Sides - Ph1-S1 | 2023-07-18 08:00 | 2023-07-24 16:00 |  |  | 5 | 0 | 5 | 97 |  | Concrete Flatwork Crew
R3960 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | 2023-07-11 08:00 | 2023-07-17 16:00 |  |  | 5 | 0 | 5 | 54 |  | Concrete Flatwork Crew
R3970 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | 2023-06-13 08:00 | 2023-06-19 16:00 |  |  | 5 | 0 | 5 | 57 |  | Concrete Flatwork Crew
R3980 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ MLK - South & North Sides - Ph1-S1 | 2023-06-20 08:00 | 2023-06-26 16:00 |  |  | 5 | 0 | 5 | 62 |  | Concrete Flatwork Crew
R3990 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Osbourne Ave - South & North Sides - Ph1-S1 | 2023-06-06 08:00 | 2023-06-12 16:00 |  |  | 5 | 0 | 5 | 39 |  | Concrete Flatwork Crew
R4000 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Hillsborough - South & North Sides - Ph1-S1 | 2023-03-08 08:00 | 2023-03-14 16:00 |  |  | 5 | 0 | 5 | 61 |  | Concrete Flatwork Crew
FEN210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install 6' Black Vinyl & 6' Mesh Fencing @ E. Hillsborough Ave. - South & North Sides - Ph1-S1 | 2023-11-29 08:00 | 2023-12-04 16:00 |  |  | 4 | 0 | 4 | 41 |  | Sub - Fence Installation Crew
FEN220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install 6' Black Vinyl & 4' & 6' & 8' Mesh Fencing & Gates @ E. Osborne Ave. - South & North Sides - Ph1-S1 | 2023-12-15 08:00 | 2024-01-08 16:00 |  |  | 10 | 0 | 10 | 33 |  | Sub - Fence Installation Crew
FEN230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install 6' Black Vinyl & 4' & 8' Mesh Fencing & Gates @ Chelsea St. - South & North Sides - Ph1-S1 | 2024-01-11 08:00 | 2024-01-25 16:00 |  |  | 10 | 0 | 10 | 31 |  | Sub - Fence Installation Crew
FEN240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install 4' & 6' & 8' Mesh Fencing & Gates @ East Lake - South & North Sides - Ph1-S1 | 2024-02-23 08:00 | 2024-03-07 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sub - Fence Installation Crew
DW100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Detectable Warnings - Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | 2022-11-22 08:00 | 2022-11-22 16:00 |  |  | 1 | 0 | 1 | 598 |  | Concrete Flatwork Crew
DW150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.1.6 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Detectable Warnings - Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 2022-12-15 08:00 | 2022-12-15 16:00 |  |  | 1 | 0 | 1 | 584 |  | Concrete Flatwork Crew
DW160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.3.2.1 | Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Detectable Warnings - Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | 2022-11-21 08:00 | 2022-11-21 16:00 |  |  | 1 | 0 | 1 | 105 |  | Concrete Flatwork Crew
PAV550 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 | Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Architectural Pavers - Hillsborough Ramp D - Ph1-S1 | 2023-07-28 08:00 | 2023-08-04 16:00 |  |  | 6 | 0 | 6 | 21 |  | Sub - Asphalt Paving Crew
PAV560 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 | Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Architectural Pavers - MLK Ramp D - Ph1-S1 | 2023-12-19 08:00 | 2024-01-03 16:00 |  |  | 5 | 0 | 5 | -2 | 10 | Sub - Asphalt Paving Crew
TMS100 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 718+11.00 - Ph 3 | 2025-02-12 08:00 | 2025-02-25 16:00 |  |  | 10 | 0 | 10 | -4 | 2 | Sub - ITS Installation Crew
TMS110 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 743+77.00 & 745+39.00 - Ph 3 | 2025-02-26 08:00 | 2025-03-11 16:00 |  |  | 10 | 0 | 10 | -4 | 2 | Sub - ITS Installation Crew
TMS120 | Not Started | 3462-FDOT-Owner-12.4.3 | Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 795+22.00 & 796+67.00 - Ph 3 | 2025-03-12 08:00 | 2025-03-25 16:00 |  |  | 10 | 0 | 10 | -4 | 2 | Sub - ITS Installation Crew
TMS130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Traffic Montoring Site Conduit - 718+11.00 - Ph 3 | 2023-03-08 21:00 | 2023-03-13 03:00 |  |  | 3 | 0 | 3 | 24 |  | Sub - ITS Installation Crew
TMS140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Traffic Montoring Site Conduit - 743+77.00 & 745+39.00 - Ph 3 | 2023-03-14 21:00 | 2023-03-20 02:00 |  |  | 4 | 0 | 4 | 24 |  | Sub - ITS Installation Crew
TMS150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Traffic Montoring Site Conduit - 795+22.00 & 796+67.00 - Ph 3 | 2023-06-14 21:00 | 2023-06-20 02:00 |  |  | 4 | 0 | 4 | 127 |  | Sub - ITS Installation Crew
SUPR810 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100207 - SB: over East Lake - Ph1-S1 | 2023-10-04 08:00 | 2023-10-11 16:00 |  |  | 6 | 0 | 6 | 0 | 13 | Approach Slab Crew
B4700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Approach Slabs Cure 100207 - SB: over East Lake - Ph1-S1 | 2023-10-12 08:00 | 2023-10-25 16:00 |  |  | 14 | 0 | 14 | 0 | 13
FG100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Fine Grade - NB: 709+50 - Ph1-S1 | 2023-05-24 08:00 | 2023-06-07 16:00 |  |  | 10 | 0 | 10 | 329 |  | Finegrade Crew
SOD100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - NB: 709+50 - Ph1-S1 | 2023-06-08 08:00 | 2023-06-19 16:00 |  |  | 8 | 0 | 8 | 345 |  | Sub - Landscape Crew
EL560 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 2022-07-04 08:00 | 2022-07-08 16:00 | 2022-07-04 08:00 | 2022-07-08 16:00 | 1 | 4 | 0 |  |  | Sub - Electrical Installation Crew
EL570 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 2022-06-27 08:00 | 2022-07-01 16:00 | 2022-06-27 08:00 | 2022-07-01 16:00 | 1 | 5 | 0 |  |  | Sub - Electrical Installation Crew
EL580 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 4 |  | Sub - Electrical Installation Crew
EL590 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 | Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2022-07-11 08:00 | 2022-07-14 16:00 | 2 | 4 | 0 |  |  | Sub - Electrical Installation Crew
EL600 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 | Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 10 |  | Sub - Electrical Installation Crew
EL610 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 | Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-16 16:00 |  |  | 3 | 0 | 3 | 82 |  | Sub - Electrical Installation Crew
EL620 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 606+52.91-610+36.08 - Ph1-S1 | 2022-09-07 08:00 | 2022-09-08 16:00 | 2022-09-07 08:00 | 2022-09-08 16:00 | 2 | 2 | 0 |  |  | Sub - Electrical Installation Crew
EL630 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 610+36.08-81+47.63 - Ph1-S1 | 2022-09-09 08:00 | 2022-09-12 16:00 | 2022-09-09 08:00 | 2022-09-12 16:00 | 2 | 2 | 0 |  |  | Sub - Electrical Installation Crew
EL640 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 2022-09-12 08:00 | 2022-09-16 16:00 | 2022-09-12 08:00 | 2022-09-16 16:00 | 3 | 5 | 0 |  |  | Sub - Electrical Installation Crew
EL650 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 104+06.12-107+60.00 - Ph1-S1 | 2022-11-29 08:00 | 2022-11-30 16:00 |  |  | 2 | 0 | 2 | 21 |  | Sub - Electrical Installation Crew
EL660 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 35 |  | Sub - Electrical Installation Crew
EL670 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 40 |  | Sub - Electrical Installation Crew
EL680 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 2022-12-02 08:00 | 2022-12-07 16:00 |  |  | 4 | 0 | 4 | 34 |  | Sub - Electrical Installation Crew
EL690 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-17 16:00 |  |  | 4 | 0 | 4 | 52 |  | Sub - Electrical Installation Crew
EL700 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-15 16:00 |  |  | 2 | 0 | 2 | 68 |  | Sub - Electrical Installation Crew
EL710 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 408+39.93-170+00.00 - Ph1-S1 | 2022-11-21 08:00 | 2022-11-22 16:00 |  |  | 2 | 0 | 2 | 29 |  | Sub - Electrical Installation Crew
EL720 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 | Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 2022-12-20 08:00 | 2022-12-22 16:00 |  |  | 3 | 0 | 3 | 54 |  | Sub - Electrical Installation Crew
EL730 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Conduit & Pull Boxes: Lighting - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 2023-02-13 08:00 | 2023-02-15 16:00 |  |  | 3 | 0 | 3 | 31 |  | Sub - Electrical Installation Crew
EL740 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 129+29.53-136+98.62 - Ph1-S1 | 2023-02-15 08:00 | 2023-02-16 16:00 |  |  | 2 | 0 | 2 | 4 |  | Sub - Electrical Installation Crew
EL750 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 2023-03-03 08:00 | 2023-03-07 16:00 |  |  | 3 | 0 | 3 | 26 |  | Sub - Electrical Installation Crew
EL760 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Install Conduit & Pull Boxes: Lighting - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 2023-03-03 08:00 | 2023-03-06 16:00 |  |  | 2 | 0 | 2 | 8 |  | Sub - Electrical Installation Crew
EL770 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 2023-03-20 08:00 | 2023-03-21 16:00 |  |  | 2 | 0 | 2 | 26 |  | Sub - Electrical Installation Crew
EL780 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 2023-04-03 08:00 | 2023-04-04 16:00 |  |  | 2 | 0 | 2 | 28 |  | Sub - Electrical Installation Crew
EL790 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 2023-04-12 08:00 | 2023-04-13 16:00 |  |  | 2 | 0 | 2 | 25 |  | Sub - Electrical Installation Crew
EL800 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 92+99.11-98+00.00 - Ph1-S1 | 2023-04-10 08:00 | 2023-04-11 16:00 |  |  | 2 | 0 | 2 | 10 |  | Sub - Electrical Installation Crew
EL810 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 | Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 2022-12-01 08:00 | 2022-12-02 16:00 |  |  | 2 | 0 | 2 | 128 |  | Sub - Electrical Installation Crew
EL820 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 2022-11-28 08:00 | 2022-11-29 16:00 |  |  | 2 | 0 | 2 | 134 |  | Sub - Electrical Installation Crew
EL830 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 82+99.07-87+69.07 - Ph1-S1 | 2023-04-25 08:00 | 2023-04-26 16:00 |  |  | 2 | 0 | 2 | 9 |  | Sub - Electrical Installation Crew
EL840 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 2023-03-02 08:00 | 2023-03-03 16:00 |  |  | 2 | 0 | 2 | 102 |  | Sub - Electrical Installation Crew
EL850 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 77+25.61-79+58.07 - Ph1-S1 | 2023-05-08 08:00 | 2023-05-09 16:00 |  |  | 2 | 0 | 2 | 8 |  | Sub - Electrical Installation Crew
EL860 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 | Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 2023-03-24 08:00 | 2023-03-28 16:00 |  |  | 3 | 0 | 3 | 94 |  | Sub - Electrical Installation Crew
EL870 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 472+02.74-473+19.41 - Ph1-S1 | 2023-05-18 08:00 | 2023-05-18 16:00 |  |  | 1 | 0 | 1 | 10 |  | Sub - Electrical Installation Crew
EL880 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 | Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Install Conduit & Pull Boxes: Lighting - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 2023-05-31 08:00 | 2023-05-31 16:00 |  |  | 1 | 0 | 1 | 15 |  | Sub - Electrical Installation Crew
EL890 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 | Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 2023-04-07 08:00 | 2023-04-10 16:00 |  |  | 2 | 0 | 2 | 90 |  | Sub - Electrical Installation Crew
EL900 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 | Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 54+85.63-61+96.16 - Ph1-S1 | 2023-06-22 08:00 | 2023-06-23 16:00 |  |  | 2 | 0 | 2 | 15 |  | Sub - Electrical Installation Crew
EL910 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Install Conduit & Pull Boxes: Lighting - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 2023-07-07 08:00 | 2023-07-07 16:00 |  |  | 1 | 0 | 1 | 18 |  | Sub - Electrical Installation Crew
EL920 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 | Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 2023-06-15 08:00 | 2023-06-19 16:00 |  |  | 3 | 0 | 3 | 65 |  | Sub - Electrical Installation Crew
EC190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | 2023-01-26 08:00 | 2023-01-31 16:00 |  |  | 4 | 0 | 4 | 41 |  | Sub - Electrical Installation Crew
EC200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | 2023-02-01 08:00 | 2023-02-07 16:00 |  |  | 5 | 0 | 5 | 41 |  | Sub - Electrical Installation Crew
EC210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 2024-02-02 08:00 | 2024-02-08 16:00 |  |  | 5 | 0 | 5 | 1 |  | Sub - Electrical Installation Crew
EC220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 2024-02-09 08:00 | 2024-02-15 16:00 |  |  | 5 | 0 | 5 | 1 |  | Sub - Electrical Installation Crew
EC230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | 2024-01-17 08:00 | 2024-01-23 16:00 |  |  | 5 | 0 | 5 | 2 |  | Sub - Electrical Installation Crew
EC240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | 2024-01-24 08:00 | 2024-01-30 16:00 |  |  | 5 | 0 | 5 | 2 |  | Sub - Electrical Installation Crew
EC250 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | 2023-12-14 08:00 | 2023-12-20 16:00 |  |  | 5 | 0 | 5 | 9 |  | Sub - Electrical Installation Crew
EC260 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | 2023-12-21 08:00 | 2024-01-05 16:00 |  |  | 5 | 0 | 5 | 9 |  | Sub - Electrical Installation Crew
EC270 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | 2023-12-01 08:00 | 2023-12-07 16:00 |  |  | 5 | 0 | 5 | 15 |  | Sub - Electrical Installation Crew
EC280 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | 2023-12-08 08:00 | 2023-12-14 16:00 |  |  | 5 | 0 | 5 | 15 |  | Sub - Electrical Installation Crew
EC290 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-11-01 08:00 | 2023-11-07 16:00 |  |  | 5 | 0 | 5 | 21 |  | Sub - Electrical Installation Crew
EC300 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | 2023-11-08 08:00 | 2023-11-15 16:00 |  |  | 5 | 0 | 5 | 21 |  | Sub - Electrical Installation Crew
EL930 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 2022-11-14 08:00 | 2022-12-07 16:00 |  |  | 15 | 0 | 15 | 76 |  | Sub - ITS Installation Crew
EL940 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 2022-12-08 08:00 | 2022-12-16 16:00 |  |  | 7 | 0 | 7 | 76 |  | Sub - ITS Installation Crew
EL950 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 2022-12-19 08:00 | 2022-12-23 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL960 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 761+67-767+00 - Ph1-S1 | 2023-01-03 08:00 | 2023-01-09 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL970 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 2023-01-10 08:00 | 2023-01-17 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL980 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 774+82-780+00 - Ph1-S1 | 2023-01-18 08:00 | 2023-01-24 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL990 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 2023-01-25 08:00 | 2023-01-31 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL1000 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 | Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 2023-02-01 08:00 | 2023-02-07 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL1010 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 2023-02-08 08:00 | 2023-02-17 16:00 |  |  | 8 | 0 | 8 | 76 |  | Sub - ITS Installation Crew
EL1020 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 2023-02-20 08:00 | 2023-03-09 16:00 |  |  | 14 | 0 | 14 | 76 |  | Sub - ITS Installation Crew
EL1030 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 2023-03-10 08:00 | 2023-03-16 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL1040 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 2023-03-17 08:00 | 2023-03-28 16:00 |  |  | 8 | 0 | 8 | 76 |  | Sub - ITS Installation Crew
EL1050 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 2023-03-29 08:00 | 2023-04-05 16:00 |  |  | 6 | 0 | 6 | 76 |  | Sub - ITS Installation Crew
EL1060 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 2023-04-06 08:00 | 2023-04-13 16:00 |  |  | 6 | 0 | 6 | 76 |  | Sub - ITS Installation Crew
EL1070 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 774+82-780+00 - Ph1-S1 | 2023-04-14 08:00 | 2023-04-20 16:00 |  |  | 5 | 0 | 5 | 76 |  | Sub - ITS Installation Crew
EL1080 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 2023-04-21 08:00 | 2023-04-28 16:00 |  |  | 6 | 0 | 6 | 76 |  | Sub - ITS Installation Crew
EL1090 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 2023-05-01 08:00 | 2023-05-08 16:00 |  |  | 6 | 0 | 6 | 76 |  | Sub - ITS Installation Crew
EL1100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 757+10-759+97 - Ph1-S1 | 2023-05-09 08:00 | 2023-05-12 16:00 |  |  | 4 | 0 | 4 | 76 |  | Sub - ITS Installation Crew
EL1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 2023-05-15 08:00 | 2023-05-26 16:00 |  |  | 10 | 0 | 10 | 76 |  | Sub - ITS Installation Crew
EL1120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | 2023-05-30 08:00 | 2023-06-08 16:00 |  |  | 8 | 0 | 8 | 76 |  | Sub - ITS Installation Crew
EL1130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 2023-06-09 08:00 | 2023-06-22 16:00 |  |  | 10 | 0 | 10 | 76 |  | Sub - ITS Installation Crew
EL1140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 2023-06-23 08:00 | 2023-07-07 16:00 |  |  | 10 | 0 | 10 | 76 |  | Sub - ITS Installation Crew
ITS370 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Main Lines - NB | 2023-10-09 08:00 | 2023-10-20 16:00 |  |  | 10 | 0 | 10 | 13 |  | Sub - ITS Installation Crew
ITS380 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Main Lines - SB | 2023-10-23 08:00 | 2023-11-03 16:00 |  |  | 10 | 0 | 10 | 13 |  | Sub - ITS Installation Crew
ITS390 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | 2023-11-06 08:00 | 2023-11-30 16:00 |  |  | 15 | 0 | 15 | 13 |  | Sub - ITS Installation Crew
ITS400 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - NB: MLK to North End | 2023-12-01 08:00 | 2023-12-21 16:00 |  |  | 15 | 0 | 15 | 13 |  | Sub - ITS Installation Crew
ITS410 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - SB: South End to MLK | 2024-01-26 08:00 | 2024-02-15 16:00 |  |  | 15 | 0 | 15 | 11 |  | Sub - ITS Installation Crew
ITS420 | Not Started | 3462-FDOT-Owner-12.4.P1.3 | Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 2023-12-22 08:00 | 2024-01-23 16:00 |  |  | 15 | 0 | 15 | 13 |  | Sub - ITS Installation Crew
ITS430 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 2023-05-04 08:00 | 2023-05-17 16:00 |  |  | 10 | 0 | 10 | 131 |  | Sub - ITS Installation Crew
ITS440 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 2023-10-05 08:00 | 2023-10-20 16:00 |  |  | 12 | 0 | 12 | 13 |  | Sub - ITS Installation Crew
ITS450 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | 2023-10-30 08:00 | 2023-11-13 16:00 |  |  | 10 | 0 | 10 | 27 |  | Sub - ITS Installation Crew
ITS460 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 2024-01-26 08:00 | 2024-02-08 16:00 |  |  | 10 | 0 | 10 | 11 |  | Sub - ITS Installation Crew
ITS470 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | 2023-05-17 08:00 | 2023-05-23 16:00 |  |  | 5 | 0 | 5 | 127 |  | Sub - ITS Installation Crew
SGN2090 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | 2023-05-14 21:00 | 2023-05-17 03:00 |  |  | 3 | 0 | 3 | 42 |  | Sub - Signing Crew
SGN2100 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 2023-05-17 03:00 | 2023-05-19 01:00 |  |  | 2 | 0 | 2 | 42 |  | Sub - Signing Crew
SGN2110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | 2023-04-26 21:00 | 2023-05-02 02:00 |  |  | 4 | 0 | 4 | 57 |  | Sub - Signing Crew
SGN2120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | 2023-07-19 21:00 | 2023-07-25 02:00 |  |  | 4 | 0 | 4 | 23 |  | Sub - Signing Crew
SGN2130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | 2023-08-17 21:00 | 2023-08-23 02:00 |  |  | 4 | 0 | 4 | 21 |  | Sub - Signing Crew
SGN2140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 | Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | 2023-08-23 02:00 | 2023-08-25 |  |  | 2 | 0 | 2 | 21 |  | Sub - Signing Crew
SGN2150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 | Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 2023-08-28 21:00 | 2023-08-30 04:00 |  |  | 2 | 0 | 2 | 25 |  | Sub - Signing Crew
SGN2160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 2023-09-10 21:00 | 2023-09-14 02:00 |  |  | 4 | 0 | 4 | 26 |  | Sub - Signing Crew
SGN2170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 2023-09-14 08:00 | 2023-09-15 16:00 |  |  | 2 | 0 | 2 | 23 |  | Sub - Signing Crew
SGN2180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 2023-09-19 21:00 | 2023-09-21 04:00 |  |  | 2 | 0 | 2 | 31 |  | Sub - Signing Crew
SGN2190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | 2023-10-05 21:00 | 2023-10-09 04:00 |  |  | 2 | 0 | 2 | 25 |  | Sub - Signing Crew
SGN2200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | 2023-10-23 21:00 | 2023-10-30 01:00 |  |  | 5 | 0 | 5 | 16 |  | Sub - Signing Crew
SGN2210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | 2023-11-13 21:00 | 2023-11-17 02:00 |  |  | 4 | 0 | 4 | 17 |  | Sub - Signing Crew
SGN2220 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 | Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | 2023-12-04 21:00 | 2023-12-06 04:00 |  |  | 2 | 0 | 2 | 30 |  | Sub - Signing Crew
SGN2230 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | 2024-01-04 21:00 | 2024-01-08 04:00 |  |  | 2 | 0 | 2 | 19 |  | Sub - Signing Crew
SGN2240 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 | Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | 2024-01-05 08:00 | 2024-01-10 16:00 |  |  | 4 | 0 | 4 | 14 |  | Sub - Signing Crew
FG110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 2023-06-08 08:00 | 2023-06-21 16:00 |  |  | 10 | 0 | 10 | 329 |  | Finegrade Crew
SOD110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - NB: 748+30-759+97 - Ph1-S1 | 2023-06-22 08:00 | 2023-07-03 16:00 |  |  | 8 | 0 | 8 | 345 |  | Sub - Landscape Crew
FG120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 2023-11-16 08:00 | 2023-12-04 16:00 |  |  | 10 | 0 | 10 | 228 |  | Finegrade Crew
SOD120 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - NB: 761+67-773+42 - Ph1-S1 | 2023-12-05 08:00 | 2023-12-14 16:00 |  |  | 8 | 0 | 8 | 245 |  | Sub - Landscape Crew
FG130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | 2023-12-05 08:00 | 2023-12-18 16:00 |  |  | 10 | 0 | 10 | 228 |  | Finegrade Crew
SOD130 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - NB: 774+82-786+69 - Ph1-S1 | 2023-12-19 08:00 | 2024-01-08 16:00 |  |  | 8 | 0 | 8 | 245 |  | Sub - Landscape Crew
FG140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 2023-12-19 08:00 | 2024-01-10 16:00 |  |  | 10 | 0 | 10 | 228 |  | Finegrade Crew
SOD140 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - NB: 788+09-813+16 - Ph1-S1 | 2024-01-11 08:00 | 2024-01-23 16:00 |  |  | 8 | 0 | 8 | 243 |  | Sub - Landscape Crew
FG150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 2024-01-11 08:00 | 2024-01-25 16:00 |  |  | 10 | 0 | 10 | 228 |  | Finegrade Crew
SOD150 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | 2024-02-14 08:00 | 2024-02-23 16:00 |  |  | 8 | 0 | 8 | 228 |  | Sub - Landscape Crew
FG160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 2024-01-26 08:00 | 2024-02-08 16:00 |  |  | 10 | 0 | 10 | 229 |  | Finegrade Crew
SOD160 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 2024-02-26 08:00 | 2024-03-06 16:00 |  |  | 8 | 0 | 8 | 228 |  | Sub - Landscape Crew
FG170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 2024-02-09 08:00 | 2024-02-22 16:00 |  |  | 10 | 0 | 10 | 229 |  | Finegrade Crew
SOD170 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 2024-03-07 08:00 | 2024-03-18 16:00 |  |  | 8 | 0 | 8 | 228 |  | Sub - Landscape Crew
FG180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 2024-02-23 08:00 | 2024-03-07 16:00 |  |  | 10 | 0 | 10 | 232 |  | Finegrade Crew
SOD180 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 2024-03-19 08:00 | 2024-03-28 16:00 |  |  | 8 | 0 | 8 | 230 |  | Sub - Landscape Crew
FG190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 2024-03-08 08:00 | 2024-03-21 16:00 |  |  | 10 | 0 | 10 | 232 |  | Finegrade Crew
SOD190 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 2024-03-29 08:00 | 2024-04-09 16:00 |  |  | 8 | 0 | 8 | 232 |  | Sub - Landscape Crew
FG200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 2024-03-22 08:00 | 2024-04-04 16:00 |  |  | 10 | 0 | 10 | 232 |  | Finegrade Crew
SOD200 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 | Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 2024-04-11 08:00 | 2024-04-22 16:00 |  |  | 8 | 0 | 8 | 233 |  | Sub - Landscape Crew
FG210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 2024-04-12 08:00 | 2024-04-25 16:00 |  |  | 10 | 0 | 10 | 227 |  | Finegrade Crew
SOD210 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 | Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 2024-05-03 08:00 | 2024-05-14 16:00 |  |  | 8 | 0 | 8 | 227 |  | Sub - Landscape Crew
MS-P1S1S1S10 | Completed | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Impact - Shoulder Work per RFI 54 & RFI 55 (Notification, Procurement, etc.) | 2021-11-04 08:00 | 2021-12-08 16:00 | 2021-11-04 08:00 | 2021-12-08 16:00 | 5 | 21 | 0
MS-P1S1F10 | Completed | 3462-FDOT-Owner-12.4.P1.1.1 | Construction: Phase 1: Stage 1: Milestones | Impact - Added Temporary Pavement per RFI 54 & RFI 55 (Start of Work) | 2022-01-15 08:00 | 2022-01-15 16:00 | 2022-01-15 08:00 | 2022-01-15 16:00 | 6 | 0 | 0
MSE40 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls 6A, 6B | 2022-06-19 08:00 | 2022-07-01 16:00 | 2022-06-19 08:00 | 2022-07-01 16:00 | 30 | 10 | 0
MSE50 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls 6A, 6B | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1200 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls 6A, 6B | 2022-02-23 08:00 | 2022-03-18 16:00 | 2022-02-23 08:00 | 2022-03-18 16:00 | 25 | 18 | 0
MSE60 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-3C | 2022-03-31 08:00 | 2022-04-15 16:00 | 2022-03-31 08:00 | 2022-04-15 16:00 | 30 | 12 | 0
MSE70 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-11A, 11B, 11C | 2022-06-19 08:00 | 2022-07-04 16:00 | 2022-06-19 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE80 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-14A, 14B | 2022-06-27 08:00 | 2022-07-04 16:00 | 2022-06-27 08:00 | 2022-07-04 16:00 | 30 | 5 | 0
MSE90 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE WallsW-13G | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE180 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-1A, 1B, 1C | 2022-04-01 08:00 | 2022-06-10 16:00 | 2022-04-01 08:00 | 2022-06-10 16:00 | 30 | 50 | 0
MSE210 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-5A | 2022-03-07 08:00 | 2022-04-15 16:00 | 2022-03-07 08:00 | 2022-04-15 16:00 | 30 | 30 | 0
MSE270 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-5B | 2022-03-07 08:00 | 2022-04-01 16:00 | 2022-03-07 08:00 | 2022-04-01 16:00 | 30 | 20 | 0
MSE310 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-2A, 2B | 2022-03-07 08:00 | 2022-04-15 16:00 | 2022-03-07 08:00 | 2022-04-15 16:00 | 20 | 30 | 0
MSE360 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-3B | 2022-03-07 08:00 | 2022-04-15 16:00 | 2022-03-07 08:00 | 2022-04-15 16:00 | 30 | 30 | 0
MSE380 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-4A, 4B | 2022-03-21 08:00 | 2022-04-16 16:00 | 2022-03-21 08:00 | 2022-04-16 16:00 | 30 | 20 | 0
MSE450 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-5C | 2022-03-07 08:00 | 2022-04-13 16:00 | 2022-03-07 08:00 | 2022-04-13 16:00 | 30 | 28 | 0
MSE490 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-7B, 7C | 2022-05-02 08:00 | 2022-05-14 16:00 | 2022-05-02 08:00 | 2022-05-14 16:00 | 30 | 10 | 0
MSE510 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-13B | 2022-05-02 08:00 | 2022-05-14 16:00 | 2022-05-02 08:00 | 2022-05-14 16:00 | 30 | 10 | 0
MSE540 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-13C | 2022-05-09 08:00 | 2022-05-14 16:00 | 2022-05-09 08:00 | 2022-05-14 16:00 | 30 | 5 | 0
MSE560 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-13D | 2022-05-09 08:00 | 2022-05-14 16:00 | 2022-05-09 08:00 | 2022-05-14 16:00 | 30 | 5 | 0
MSE590 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-13E | 2022-05-14 08:00 | 2022-05-14 16:00 | 2022-05-14 08:00 | 2022-05-14 16:00 | 30 | 0 | 0
MSE670 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-15C | 2022-05-09 08:00 | 2022-05-14 16:00 | 2022-05-09 08:00 | 2022-05-14 16:00 | 30 | 5 | 0
MSE700 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-15D | 2022-05-09 08:00 | 2022-05-14 16:00 | 2022-05-09 08:00 | 2022-05-14 16:00 | 30 | 5 | 0
MSE730 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-19A | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE760 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-22A, W-22B, W-22C | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE820 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-21C, 21D | 2022-06-18 08:00 | 2022-07-15 16:00 | 2022-06-18 08:00 | 2022-07-15 16:00 | 30 | 19 | 0
MSE900 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-21A, 21B | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE930 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-20A, 20B | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE960 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-18A, 18B | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE980 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-17B | 2022-05-09 08:00 | 2022-05-14 16:00 | 2022-05-09 08:00 | 2022-05-14 16:00 | 30 | 5 | 0
MSE1000 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-17C | 2022-06-20 08:00 | 2022-07-04 16:00 | 2022-06-20 08:00 | 2022-07-04 16:00 | 30 | 10 | 0
MSE1060 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-16A, 16B | 2022-06-18 08:00 | 2022-07-01 16:00 | 2022-06-18 08:00 | 2022-07-01 16:00 | 30 | 10 | 0
MSE1100 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Procurement: MSE Walls W-15A | 2022-05-09 08:00 | 2022-05-14 16:00 | 2022-05-09 08:00 | 2022-05-14 16:00 | 30 | 5 | 0
MSE1170 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-3C | 2022-02-07 08:00 | 2022-02-18 16:00 | 2022-02-07 08:00 | 2022-02-18 16:00 | 10 | 10 | 0
MSE1180 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-11A, 11B, 11C | 2022-02-22 08:00 | 2022-03-18 16:00 | 2022-02-22 08:00 | 2022-03-18 16:00 | 25 | 19 | 0
MSE1210 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-14A, 14B | 2022-02-22 08:00 | 2022-03-18 16:00 | 2022-02-22 08:00 | 2022-03-18 16:00 | 25 | 19 | 0
MSE1220 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W- 5A | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 25 | 14 | 0
MSE1230 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13G | 2022-02-21 08:00 | 2022-03-18 16:00 | 2022-02-21 08:00 | 2022-03-18 16:00 | 25 | 20 | 0
MSE1240 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-1A, 1B, 1C | 2022-02-21 08:00 | 2022-03-18 16:00 | 2022-02-21 08:00 | 2022-03-18 16:00 | 25 | 20 | 0
MSE1250 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-5B | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 25 | 14 | 0
MSE1260 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-2A, 2B | 2022-01-14 08:00 | 2022-01-15 16:00 | 2022-01-14 08:00 | 2022-01-15 16:00 | 16 | 1 | 0
MSE1270 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-3B | 2022-01-15 08:00 | 2022-01-15 16:00 | 2022-01-15 08:00 | 2022-01-15 16:00 | 10 | 0 | 0
MSE1280 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-4A, 4B | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 25 | 14 | 0
MSE1290 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-5C | 2022-02-01 08:00 | 2022-02-18 16:00 | 2022-02-01 08:00 | 2022-02-18 16:00 | 25 | 14 | 0
MSE1300 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-7B, 7C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1310 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1320 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1330 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13D | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1340 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13E | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1350 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-15C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1360 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-15D | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1370 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-19A | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1380 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-22A, 22B, 22C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1390 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-21C, 21D | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1400 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-21A, 21B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1410 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-20A, 20B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1420 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-18A, 18B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1430 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-17B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1440 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-17C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1450 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-16A, 16B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1460 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-15A | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1470 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-3C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1480 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-11A, 11B, 11C | 2022-06-06 08:00 | 2022-07-04 16:00 | 2022-06-06 08:00 | 2022-07-04 16:00 | 25 | 20 | 0
MSE1490 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13G | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1500 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-14A, 14B | 2022-06-06 08:00 | 2022-07-04 16:00 | 2022-06-06 08:00 | 2022-07-04 16:00 | 25 | 20 | 0
MSE1510 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-1A, 1B, 1C | 2022-03-28 08:00 | 2022-04-01 16:00 | 2022-03-28 08:00 | 2022-04-01 16:00 | 25 | 5 | 0
MSE1520 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-5A | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1530 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-5B | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1540 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-5C | 2022-02-04 08:00 | 2022-02-18 16:00 | 2022-02-04 08:00 | 2022-02-18 16:00 | 25 | 11 | 0
MSE1550 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-2A, 2B | 2022-01-15 08:00 | 2022-02-18 16:00 | 2022-01-15 08:00 | 2022-02-18 16:00 | 25 | 24 | 0
MSE1560 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-3B | 2022-01-15 08:00 | 2022-02-18 16:00 | 2022-01-15 08:00 | 2022-02-18 16:00 | 25 | 24 | 0
MSE1570 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-4A, 4B | 2022-02-21 08:00 | 2022-03-18 16:00 | 2022-02-21 08:00 | 2022-03-18 16:00 | 25 | 20 | 0
MSE1580 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-7B, 7C | 2022-05-02 08:00 | 2022-05-14 16:00 | 2022-05-02 08:00 | 2022-05-14 16:00 | 25 | 10 | 0
MSE1590 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13B | 2022-05-02 08:00 | 2022-05-14 16:00 | 2022-05-02 08:00 | 2022-05-14 16:00 | 25 | 10 | 0
MSE1600 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13C | 2022-03-21 08:00 | 2022-03-31 16:00 | 2022-03-21 08:00 | 2022-03-31 16:00 | 25 | 9 | 0
MSE1610 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13D | 2022-03-21 08:00 | 2022-03-31 16:00 | 2022-03-21 08:00 | 2022-03-31 16:00 | 25 | 9 | 0
MSE1620 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13E | 2022-03-31 08:00 | 2022-04-01 16:00 | 2022-03-31 08:00 | 2022-04-01 16:00 | 25 | 2 | 0
MSE1630 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-15C | 2022-03-21 08:00 | 2022-04-01 08:00 | 2022-03-21 08:00 | 2022-04-01 08:00 | 25 | 9 | 0
MSE1640 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-15D | 2022-03-21 08:00 | 2022-04-01 16:00 | 2022-03-21 08:00 | 2022-04-01 16:00 | 25 | 10 | 0
MSE1650 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-19A | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1660 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-22A, W-22B, W-22C | 2022-06-06 08:00 | 2022-07-04 16:00 | 2022-06-06 08:00 | 2022-07-04 16:00 | 25 | 20 | 0
MSE1670 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-21C, 21D | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1680 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-21A, 21B | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1690 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-20A, 20B | 2022-06-06 08:00 | 2022-07-04 16:00 | 2022-06-06 08:00 | 2022-07-04 16:00 | 25 | 20 | 0
MSE1700 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-18A, 18B | 2022-06-06 08:00 | 2022-07-04 16:00 | 2022-06-06 08:00 | 2022-07-04 16:00 | 25 | 20 | 0
MSE1710 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-17B | 2022-05-13 08:00 | 2022-05-14 16:00 | 2022-05-13 08:00 | 2022-05-14 16:00 | 25 | 1 | 0
MSE1720 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-17C | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1730 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-16A, 16B | 2022-06-06 08:00 | 2022-07-01 16:00 | 2022-06-06 08:00 | 2022-07-01 16:00 | 25 | 20 | 0
MSE1740 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls 15A | 2022-03-28 08:00 | 2022-04-01 16:00 | 2022-03-28 08:00 | 2022-04-01 16:00 | 25 | 5 | 0
DS300 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Utility Conflict At NB over MLK Blvd Ph1-S1 | 2022-07-04 08:00 | 2022-07-06 16:00 | 2022-07-04 08:00 | 2022-07-06 16:00 | 5 | 2 | 0
DS310 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Utility Conflict at MLK NB Pier 3 Drilled Shaft (RFI#126) See Notes | 2022-07-06 08:00 | 2022-07-08 16:00 | 2022-07-06 08:00 | 2022-07-08 16:00 | 7 | 3 | 0
DS320 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Utility Conflict at MLK SB Pier 3 Drilled Shaft (RFI#131) See Notes | 2022-07-07 08:00 | 2022-07-08 16:00 | 2022-07-07 08:00 | 2022-07-08 16:00 | 5 | 2 | 0
DS330 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Utility Conflict at Hillsborough NB Pier 2 Drilled Shaft (RFI#134) See Notes | 2022-07-08 08:00 | 2022-07-09 16:00 | 2022-07-08 08:00 | 2022-07-09 16:00 | 5 | 1 | 0
DS340 | Not Started | 3462-FDOT-Owner-12.4.P2.7 | Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Utility Conflict Issue at Jack and Bore Drainage Structure S-158 (RFI#114) See Notes | 2022-11-14 08:00 | 2022-11-18 16:00 |  |  | 5 | 0 | 5 | 422
CB160 | Completed | 3462-FDOT-Owner-12.4.P1.1.2 | Construction: Phase 1: Stage 1: Site Investigations | Additional Core Bores Needed @ Osborne Pier 3 | 2022-04-17 08:00 | 2022-06-01 16:00 | 2022-04-17 08:00 | 2022-06-01 16:00 | 5 | 32 | 0
DS350 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Utility Conflict at MLK SB Pier 3 (RFI# 132) | 2022-07-04 08:00 | 2022-07-15 16:00 | 2022-07-04 08:00 | 2022-07-15 16:00 | 5 | 9 | 0
MSE1750 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1 | Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 746+91.13 (S.End to Floribraska to E Lake) | Concrete Readymix needed- Material Shortage in Tampa FL. | 2022-05-14 08:00 | 2022-05-23 16:00 | 2022-05-14 08:00 | 2022-05-23 16:00 | 0 | 6 | 0
ITS210 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 | Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Relocate Existing ITS Poles and Camera SB MLK | 2022-08-18 08:00 | 2022-08-19 16:00 | 2022-08-18 08:00 | 2022-08-19 16:00 | 1 | 2 | 0
ITS250 | Not Started | 3462-FDOT-Owner-12.4.IP1.3.2.1 | Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Relocate Existing ITS Hillsborough SB | 2022-11-14 08:00 | 2022-11-14 16:00 |  |  | 1 | 0 | 1 | 76
DS360 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | PIER 2 NB Bridge Osborne Waiting on EAR Results | 2022-06-09 08:00 | 2022-07-08 16:00 | 2022-06-09 08:00 | 2022-07-08 16:00 | 28 | 21 | 0
DS370 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | PIER 3 NB Redesign Osborne Drilled shaft issued by owner to a spread footer. | 2022-06-09 08:00 | 2022-07-15 16:00 | 2022-06-09 08:00 | 2022-07-15 16:00 | 5 | 26 | 0
DS380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | PIER 2 SB Bridge Osborne Waiting on EAR Results | 2022-06-09 08:00 | 2022-07-07 16:00 | 2022-06-09 08:00 | 2022-07-07 16:00 | 28 | 20 | 0
DS390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | PIER 3 SB Bridge Osborne Waiting on EAR Results | 2022-06-09 08:00 | 2022-07-08 16:00 | 2022-06-09 08:00 | 2022-07-08 16:00 | 28 | 21 | 0
MSE1760 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | DELAY- Waiting on Soil Nail Anchor Owner Review/Approval @ Wall 2 (Sent Data 5-25-2022) | 2022-05-25 08:00 | 2022-06-20 16:00 | 2022-05-25 08:00 | 2022-06-20 16:00 | 5 | 18 | 0
DEMO1280 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 | Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Waiting on Owner Lane Closure Approval to Ensure Floribraska Ramp C can begin on 7/31 | 2022-09-11 08:00 | 2022-09-12 16:00 | 2022-09-11 08:00 | 2022-09-12 16:00 | 5 | 1 | 0
BBM200 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | DELAY - Preferred Concrete - Floribraska EAR (NB Pier 3 cap) | 2022-06-08 21:00 | 2022-09-16 16:00 | 2022-06-08 21:00 | 2022-09-16 16:00 | 30 | 69 | 0 |  |  | Erection Crew
BBM210 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | DELAY - Preferred Concrete - East Lake EAR (NB Pier 2 Cap - NB Pier 3 Cap - NB Pier 3 Column) | 2022-06-08 21:00 | 2022-11-14 08:00 | 2022-06-08 21:00 |  | 30 | 108 | 0 | 6 |  | Erection Crew
BBM220 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | DELAY - Preferred Concrete - Chelsea EAR (NB Pier 3 Column) | 2022-06-13 21:00 | 2022-11-14 08:00 | 2022-06-13 21:00 |  | 30 | 105 | 0 | 49 |  | Erection Crew
BBM230 | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | DELAY - Preferred Concrete - Chelsea EAR (SB Pier 3 Column - SB Pier 2 Column) | 2022-06-09 21:00 | 2022-11-14 08:00 | 2022-06-09 21:00 |  | 30 | 107 | 0 | 49 |  | Erection Crew
DS400 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Driving Pile | 2022-07-11 08:00 | 2022-07-15 16:00 | 2022-07-11 08:00 | 2022-07-15 16:00 | 10 | 5 | 0
DW170 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Form/Reinforce/Place | 2022-09-05 08:00 | 2022-09-09 16:00 | 2022-09-05 08:00 | 2022-09-09 16:00 | 14 | 4 | 0
DW180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Cure | 2022-09-10 08:00 | 2022-09-13 16:00 | 2022-09-10 08:00 | 2022-09-13 16:00 | 14 | 2 | 0
DW190 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Strip | 2022-09-14 08:00 | 2022-09-14 16:00 | 2022-09-14 08:00 | 2022-09-14 16:00 | 3 | 1 | 0
DS410 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Development for EAR For Installed 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 2022-06-06 08:00 | 2022-06-10 16:00 | 2022-06-06 08:00 | 2022-06-10 16:00 | 10 | 5 | 0 |  |  | Sub - Drilled Shaft Crew
DS420 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Development for EAR for Installed NB Pier 3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 2022-03-03 08:00 | 2022-03-18 16:00 | 2022-03-03 08:00 | 2022-03-18 16:00 | 10 | 12 | 0 |  |  | Sub - Drilled Shaft Crew
DS430 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Development for EAR for Installed NB Pier 2 Cap & NB Pier 3 Cap & Column Pier 3- NB: over East Lake - Ph1-S1 | 2022-03-03 08:00 | 2022-03-18 16:00 | 2022-03-03 08:00 | 2022-03-18 16:00 | 10 | 12 | 0 |  |  | Sub - Drilled Shaft Crew
SUBS1380 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Development for EAR for Installed NB Pier 3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 2022-06-10 08:00 | 2022-06-13 16:00 | 2022-06-10 08:00 | 2022-06-13 16:00 | 8 | 2 | 0 |  |  | Substructure Crew
SUBS1390 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Development for EAR for Installed SB Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 2022-06-06 08:00 | 2022-06-09 16:00 | 2022-06-06 08:00 | 2022-06-09 16:00 | 10 | 4 | 0 |  |  | Substructure Crew
RET40 | Completed | 3462-FDOT-Owner-12.2.1.2.1 | Preconstruction: Procurement: Walls: Anchored Retaining Walls | (R&R)Revision 1. Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) | 2022-02-20 08:00 | 2022-02-20 08:00 | 2022-02-20 08:00 | 2022-02-20 08:00 | 0 | 0 | 0
SGN2250 | Completed | 3462-FDOT-Owner-12.2.1.4.2.1 | Preconstruction: Procurement: Electrical / ITS: Signage | (R&R) Revision 1. Review & Approve Shop Drawings/ Submittals: Signage | 2022-06-20 08:00 | 2022-06-30 16:00 | 2022-06-20 08:00 | 2022-06-30 16:00 | 130 | 9 | 0
ITS480 | Completed | 3462-FDOT-Owner-12.2.1.4.3 | Preconstruction: Procurement: Electrical / ITS: ITS | (R&R) Revision 1. Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | 2021-11-22 08:00 | 2022-02-18 16:00 | 2021-11-22 08:00 | 2022-02-18 16:00 | 25 | 89 | 0
MSE1770 | Completed | 3462-FDOT-Owner-12.2.1.2.4 | Preconstruction: Procurement: Walls: MSE Walls | (R&R) Revision 1.Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | 2022-02-21 08:00 | 2022-02-23 08:00 | 2022-02-21 08:00 | 2022-02-23 08:00 | 0 | 2 | 0
LTG1110 | Completed | 3462-FDOT-Owner-12.2.1.4.1 | Preconstruction: Procurement: Electrical / ITS: Lighting | (R&R) Revision 1. Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | 2021-11-16 08:00 | 2022-03-18 16:00 | 2021-11-16 08:00 | 2022-03-18 16:00 | 25 | 123 | 0
DEL-A1000 | Completed | 3462-FDOT-Owner-12.4 | Construction | DELAY - Preferred Concrete - EAR Review and Response | 2022-06-14 08:00 | 2022-09-16 16:00 | 2022-06-14 08:00 | 2022-09-16 16:00 | 5 | 66 | 0
DEL-A1010 | Completed | 3462-FDOT-Owner-12.4 | Construction | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | 2022-09-16 08:00 | 2022-10-12 16:00 | 2022-09-16 08:00 | 2022-10-12 16:00 | 18 | 19 | 0
DEL-A1030 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #2 Cap | 2022-10-12 08:00 | 2022-10-14 16:00 | 2022-10-12 08:00 | 2022-10-14 16:00 | 6 | 3 | 0
DEL-A1040 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #3 Column & Cap | 2022-10-20 08:00 | 2022-10-21 16:00 | 2022-10-20 08:00 | 2022-10-21 16:00 | 3 | 2 | 0
DEL-A1050 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - Chelsea Pier #3 Column | 2022-10-26 08:00 | 2022-10-28 16:00 | 2022-10-26 08:00 | 2022-10-28 16:00 | 3 | 3 | 0
DEL-A1060 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #3 Column & Cap | 2022-10-24 08:00 | 2022-10-25 16:00 | 2022-10-24 08:00 | 2022-10-25 16:00 | 3 | 2 | 0
DEL-A1070 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #2 Column | 2022-10-25 08:00 | 2022-10-26 16:00 | 2022-10-25 08:00 | 2022-10-26 16:00 | 3 | 2 | 0
TCC180 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | MOT Shift Traffic to Install (OHS-101) - SB: 723+54 | 2022-10-05 21:00 | 2022-10-06 05:00 | 2022-10-05 21:00 | 2022-10-06 05:00 | 10 | 1 | 0 |  |  | Traffic Control Crews
DEMO2030 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 | Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Demo Roadway - SB: 723+54 Create Access to install (OHS-101) | 2022-10-13 08:00 | 2022-10-15 16:00 | 2022-10-13 08:00 | 2022-10-15 16:00 | 16 | 2 | 0 |  |  | Demolition Crews
DEL-A1080 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - NB - Floribraska Pier #3 Cap | 2022-10-18 08:00 | 2022-10-26 16:00 | 2022-10-18 08:00 | 2022-10-26 16:00 | 5 | 7 | 0
DEL-A1090 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Replace - NB - East Lake Pier #2 Cap | 2022-10-17 08:00 | 2022-11-01 16:00 | 2022-10-17 08:00 | 2022-11-01 16:00 | 5 | 12 | 0
DEL-A1100 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - NB - East Lake Pier #3 Column & Cap | 2022-10-24 08:00 | 2022-11-04 16:00 | 2022-10-24 08:00 | 2022-11-04 16:00 | 8 | 10 | 0
DEL-A1110 | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - NB - Chelsea Pier #3 Column | 2022-11-14 08:00 | 2022-11-16 16:00 |  |  | 3 | 0 | 3 | 31
DEL-A1120 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - SB - Chelsea Pier #3 Column & Cap | 2022-10-26 08:00 | 2022-11-08 16:00 | 2022-10-26 08:00 | 2022-11-08 16:00 | 8 | 10 | 0
DEL-A1130 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Replace - SB - Chelsea Pier #2 Column | 2022-10-27 08:00 | 2022-11-08 16:00 | 2022-10-27 08:00 | 2022-11-08 16:00 | 3 | 9 | 0
DEL-A1140 | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - Floribraska Pier #3 Cap | 2022-10-12 08:00 | 2022-10-17 16:00 | 2022-10-12 08:00 | 2022-10-17 16:00 | 6 | 4 | 0
DEL-A1090S | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Cure and Strip - NB - East Lake Pier #2 Cap | 2022-11-02 08:00 | 2022-11-08 16:00 | 2022-11-02 08:00 | 2022-11-08 16:00 | 7 | 7 | 0
DEL-A1080S | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Cure and Strip - NB - Floribraska Pier #3 Cap | 2022-10-27 08:00 | 2022-11-04 16:00 | 2022-10-27 08:00 | 2022-11-04 16:00 | 7 | 9 | 0
DEL-A1100S | Completed | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 | Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Cure and Strip - NB - East Lake Pier #3 Cap | 2022-11-05 08:00 | 2022-11-11 16:00 | 2022-11-05 08:00 | 2022-11-11 16:00 | 7 | 7 | 0
DEL-A1120S | In Progress | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 | Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Cure and Strip - SB - Chelsea Pier #3 Cap | 2022-11-09 08:00 | 2022-11-13 16:00 | 2022-11-09 08:00 |  | 7 | 4 | 1 | 252
MSE110A | Not Started | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 | Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3C (Sign Leaveout) - NB: 725+50 - Ph1-S1 | 2022-11-14 08:00 | 2022-11-17 16:00 |  |  | 4 | 0 | 4 | 2 | 20 | Sub - MSE Wall Crew

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | comments | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(d) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Comments | Delete This Row
NW110 | NW540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp B (NB: 250+88.27-256+15.55) - Ph1-S2 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW130 | NW560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW530 | NW640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp D - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
MSE110A | MS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3C (Sign Leaveout) - NB: 725+50 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE110 | MSE110A | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Install MSE Wall W-3C (Sign Leaveout) - NB: 725+50 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
DEMO100 | LSP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - NB: 815 - 818 - IPh1 | Grassing: NB - NB: 815 - 818 - IPh1 | 0 | DEMO | SUB-LANDSC
MS-P1S1S | DEMO910 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Start of Phase 1, Stage 1 | Demo Roadway - SB: 780+00-786+69 - Ph1-S1 | 0 |  | DEMO
LOE-P1S1 | MS-P1S1F | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Phase 1: Stage 1 Duration | End of Phase 1, Stage 1 | 0
DEMO840 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO830 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 41' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO820 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 27' of 14"x23" Pipe & 2 Structures - NB: 820+00-822+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO810 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 64' of 18" Pipe & 1 Structure - NB: 819+00-821+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO800 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 47' of 15" Pipe & 2 Structures - NB: 819+00-820+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO780 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 816+00-817+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO880 | STAB320 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 2 Structures - NB: 835+00-836+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO870 | STAB320 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 17' of 24" Pipe & 2 Structures - NB: 826+00-828+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEMO860 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 10' of 15" Pipe & 2 Structures - NB: 822+00-823+00 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | DEMO | EW-CEM
DEL-A1120 | DEL-A1120S | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - SB - Chelsea Pier #3 Column & Cap | DELAY - Preferred Concrete - Cure and Strip - SB - Chelsea Pier #3 Cap | 0
DEL-A1120S | BBM180 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | DELAY - Preferred Concrete - Cure and Strip - SB - Chelsea Pier #3 Cap | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BEAM
DEL-A1100S | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | DELAY - Preferred Concrete - Cure and Strip - NB - East Lake Pier #3 Cap | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BEAM
DEL-A1100 | DEL-A1100S | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - NB - East Lake Pier #3 Column & Cap | DELAY - Preferred Concrete - Cure and Strip - NB - East Lake Pier #3 Cap | 0
DEL-A1080 | DEL-A1080S | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - NB - Floribraska Pier #3 Cap | DELAY - Preferred Concrete - Cure and Strip - NB - Floribraska Pier #3 Cap | 0
DEL-A1080S | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | DELAY - Preferred Concrete - Cure and Strip - NB - Floribraska Pier #3 Cap | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BEAM
DEL-A1090 | DEL-A1090S | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Replace - NB - East Lake Pier #2 Cap | DELAY - Preferred Concrete - Cure and Strip - NB - East Lake Pier #2 Cap | 0
DEL-A1090S | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | DELAY - Preferred Concrete - Cure and Strip - NB - East Lake Pier #2 Cap | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BEAM
DEL-A1110 | SUBS550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Replace - NB - Chelsea Pier #3 Column | Form / Reinforce / Pour Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DEL-A1050 | DEL-A1070 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Remove - NB - Chelsea Pier #3 Column | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #2 Column | 0
DEL-A1040 | DEL-A1050 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #3 Column & Cap | DELAY - Preferred Concrete - Remove - NB - Chelsea Pier #3 Column | 0
DEL-A1030 | DEL-A1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #2 Cap | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #3 Column & Cap | 0
TCC110 | DEMO1540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Demo Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 0 | TRAFFIC | DEMO
DEL-A1010 | DEL-A1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #3 Column & Cap | 0
DEL-A1010 | DEL-A1070 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #2 Column | 0
DEL-A1010 | DEL-A1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #3 Column & Cap | 0
DEL-A1010 | DEL-A1050 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | DELAY - Preferred Concrete - Remove - NB - Chelsea Pier #3 Column | 0
DEL-A1010 | DEL-A1140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | DELAY - Preferred Concrete - Remove - NB - Floribraska Pier #3 Cap | 0
DEL-A1010 | DEL-A1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #2 Cap | 0
DEL-A1140 | DEL-A1080 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - Floribraska Pier #3 Cap | DELAY - Preferred Concrete - Replace - NB - Floribraska Pier #3 Cap | 0
DEL-A1070 | DEL-A1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #2 Column | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #3 Column & Cap | 0
DEL-A1130 | SUBS1090 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Replace - SB - Chelsea Pier #2 Column | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DEL-A1070 | DEL-A1130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #2 Column | DELAY - Preferred Concrete - Replace - SB - Chelsea Pier #2 Column | 0
DEL-A1060 | DEL-A1120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - SB - Chelsea Pier #3 Column & Cap | DELAY - Preferred Concrete - Replace - SB - Chelsea Pier #3 Column & Cap | 0
DEL-A1050 | DEL-A1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - Chelsea Pier #3 Column | DELAY - Preferred Concrete - Replace - NB - Chelsea Pier #3 Column | 0
DEL-A1040 | DEL-A1100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #3 Column & Cap | DELAY - Preferred Concrete - Replace - NB - East Lake Pier #3 Column & Cap | 0
DEL-A1030 | DEL-A1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | DELAY - Preferred Concrete - Remove - NB - East Lake Pier #2 Cap | DELAY - Preferred Concrete - Replace - NB - East Lake Pier #2 Cap | 0
MS-LNTP | NW240 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Notice to Proceed | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 |  | ST-SOUND
MS-LNTP | DRG140A | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Notice to Proceed | Drainage: S-139 OF to S-139 - Upper (18") - SB: 800-802 - Swale 1A - Ph1-S1 | 0 |  | DRAIN
DEMO2030 | DSS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Demo Roadway - SB: 723+54 Create Access to install (OHS-101) | Install Sign Drilled Shaft Foundation (OHS-101) - SB: 723+54 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
TCC180 | DEMO2030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | MOT Shift Traffic to Install (OHS-101) - SB: 723+54 | Demo Roadway - SB: 723+54 Create Access to install (OHS-101) | 0 | TRAFFIC | DEMO
TCC110 | TCC180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | MOT Shift Traffic to Install (OHS-101) - SB: 723+54 | 0 | TRAFFIC | TRAFFIC
SGN60 | DSS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-101) - SB: 723+54 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DEL-A1000 | DEL-A1010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4 Construction | 3462-FDOT-Owner-12.4 Construction | DELAY - Preferred Concrete - EAR Review and Response | DELAY - Preferred Concrete - Develop Repair Procedure & Obtain approval for use / Procure Subs & Materials | 0
SUBS1380 | DEL-A1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4 Construction | Development for EAR for Installed NB Pier 3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - EAR Review and Response | 0 | ST-BRIDGE-SUB
SUBS1390 | DEL-A1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4 Construction | Development for EAR for Installed SB Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - EAR Review and Response | 0 | ST-BRIDGE-SUB
DS430 | DEL-A1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4 Construction | Development for EAR for Installed NB Pier 2 Cap & NB Pier 3 Cap & Column Pier 3- NB: over East Lake - Ph1-S1 | DELAY - Preferred Concrete - EAR Review and Response | 0 | SUB-ST-DRSFT
DS420 | DEL-A1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4 Construction | Development for EAR for Installed NB Pier 3 Cap 100201 - NB: over Floribraska - Ph1-S1 | DELAY - Preferred Concrete - EAR Review and Response | 0 | SUB-ST-DRSFT
LTG1110 | LTG30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | (R&R) Revision 1. Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | Procurement: Lighting | 0
LTG20 | LTG1110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | (R&R) Revision 1. Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | 0
MSE1770 | MSE30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | (R&R) Revision 1.Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | Procurement: MSE Walls (Delete) | 0
MSE20 | MSE1770 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | (R&R) Revision 1.Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | 0
ITS480 | ITS30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | (R&R) Revision 1. Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | Procurement: ITS | 0
ITS20 | ITS480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | (R&R) Revision 1. Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | 0
SGN2250 | SGN30 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | (R&R) Revision 1. Review & Approve Shop Drawings/ Submittals: Signage | Procurement: Signage | 0
SGN20 | SGN2250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | Review & Approve Shop Drawings / Submittals: Signage (Duration = 25 Calendar Days) | (R&R) Revision 1. Review & Approve Shop Drawings/ Submittals: Signage | 0
RET40 | RET30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | (R&R)Revision 1. Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) | Procurement: Anchored Retaining Walls | 0
RET20 | RET40 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) (Deleted) | (R&R)Revision 1. Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) | 0
DEMO1470 | DEMO1530 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Demo Edge of Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DEMO | DM-BRIDGE
SUBS1020 | SUBS1390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Development for EAR for Installed SB Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1390 | BBM230 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Development for EAR for Installed SB Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - Chelsea EAR (SB Pier 3 Column - SB Pier 2 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS460 | SUBS1380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Development for EAR for Installed NB Pier 3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1380 | BBM220 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Development for EAR for Installed NB Pier 3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - Chelsea EAR (NB Pier 3 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS290 | DS430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Form / Reinforce / Pour Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | Development for EAR for Installed NB Pier 2 Cap & NB Pier 3 Cap & Column Pier 3- NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | SUB-ST-DRSFT
SUBS300 | DS430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Form / Reinforce / Pour Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | Development for EAR for Installed NB Pier 2 Cap & NB Pier 3 Cap & Column Pier 3- NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | SUB-ST-DRSFT
SUBS220 | DS430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | Development for EAR for Installed NB Pier 2 Cap & NB Pier 3 Cap & Column Pier 3- NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | SUB-ST-DRSFT
DS430 | BBM210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Development for EAR for Installed NB Pier 2 Cap & NB Pier 3 Cap & Column Pier 3- NB: over East Lake - Ph1-S1 | DELAY - Preferred Concrete - East Lake EAR (NB Pier 2 Cap - NB Pier 3 Cap - NB Pier 3 Column) | 0 | SUB-ST-DRSFT | ST-BEAM
SUBS190 | DS420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Form / Reinforce / Pour Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | Development for EAR for Installed NB Pier 3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | SUB-ST-DRSFT
DS420 | BBM200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Development for EAR for Installed NB Pier 3 Cap 100201 - NB: over Floribraska - Ph1-S1 | DELAY - Preferred Concrete - Floribraska EAR (NB Pier 3 cap) | 0 | SUB-ST-DRSFT | ST-BEAM
DS410 | DS360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Development for EAR For Installed 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | PIER 2 NB Bridge Osborne Waiting on EAR Results | 0 | SUB-ST-DRSFT
DS140 | DS410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Development for EAR For Installed 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
MS-LNTP | DEMO1280 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Notice to Proceed | Waiting on Owner Lane Closure Approval to Ensure Floribraska Ramp C can begin on 7/31 | 0
TCC130 | DEMO1490 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | Install MOT Construction Barriers I-275 SB - IPh1 | Demo Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | TRAFFIC | DEMO
DW190 | SUBS570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Strip | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DW180 | DW190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Cure | Design-Osborne Footer Strip | 0
DS370 | DS400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | PIER 3 NB Redesign Osborne Drilled shaft issued by owner to a spread footer. | Design-Osborne Footer Driving Pile | 0
DW170 | DW180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Form/Reinforce/Place | Design-Osborne Footer Cure | 0
DW180 | SUBS570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Cure | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DS400 | DW170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Design-Osborne Footer Driving Pile | Design-Osborne Footer Form/Reinforce/Place | 0
MS-LNTP | TCC150 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.3.2.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Traffic Control | Notice to Proceed | Detour North Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S2 | 0 |  | TC-Maint.
MS-P1S1S1F | MS-SC | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.0 Project Milestones | End of Phase 1, Stage 1, Step 1 | Substantial Completion | 0
PM1010 | MS-P1S1S2S | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Pavement Marking: Temporary Diversion: NB: MLK Ramp C - IPh1 | Start of Phase 1, Stage 1, Step 2 | 0 | SUB-STRIP
PM1010 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Pavement Marking: Temporary Diversion: NB: MLK Ramp C - IPh1 | End of Initial Phase 1 | 0 | SUB-STRIP
MS-LNTP | NW120 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Notice to Proceed | Form / Reinforce / Pour 14' Noise Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | 0 |  | ST-SOUND
EGC100 | NW100 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Form / Reinforce / Pour 14' Noise Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | 0 | EW-SML | ST-SOUND
EL610 | EL340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
MS-LNTP | DRG490 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Notice to Proceed | Drainage: S-128 OF to S-128 (18") - NB: 795-796 - Ph1-S1 | 0 |  | DRAIN
BBM230 | BBM130 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | DELAY - Preferred Concrete - Chelsea EAR (SB Pier 3 Column - SB Pier 2 Column) | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
DRG340 | DRG350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-60 to S-60A (42") - NB: 764-766 - Ph1-S1 | Drainage: S-60A to S-78 (42") - NB: 766-768 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG300 | DRG310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | 0 | DRAIN | DRAIN
MS-P3F | MS-SC | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.0 Project Milestones | End of Phase 3 | Substantial Completion | 0
BBM230 | BBM180 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | DELAY - Preferred Concrete - Chelsea EAR (SB Pier 3 Column - SB Pier 2 Column) | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
SUBS1080 | BBM230 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - Chelsea EAR (SB Pier 3 Column - SB Pier 2 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1070 | BBM230 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - Chelsea EAR (SB Pier 3 Column - SB Pier 2 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
BBM220 | BBM130 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | DELAY - Preferred Concrete - Chelsea EAR (NB Pier 3 Column) | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
SUBS520 | BBM220 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | DELAY - Preferred Concrete - Chelsea EAR (NB Pier 3 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
BBM210 | BBM110 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | DELAY - Preferred Concrete - East Lake EAR (NB Pier 2 Cap - NB Pier 3 Cap - NB Pier 3 Column) | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
SUBS360 | BBM210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | DELAY - Preferred Concrete - East Lake EAR (NB Pier 2 Cap - NB Pier 3 Cap - NB Pier 3 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS280 | BBM210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | DELAY - Preferred Concrete - East Lake EAR (NB Pier 2 Cap - NB Pier 3 Cap - NB Pier 3 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS350 | BBM210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | DELAY - Preferred Concrete - East Lake EAR (NB Pier 2 Cap - NB Pier 3 Cap - NB Pier 3 Column) | 0 | ST-BRIDGE-SUB | ST-BEAM
BBM200 | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | DELAY - Preferred Concrete - Floribraska EAR (NB Pier 3 cap) | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
SUBS260 | BBM200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | DELAY - Preferred Concrete - Floribraska EAR (NB Pier 3 cap) | 0 | ST-BRIDGE-SUB | ST-BEAM
DEMO620 | MS-SC | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.0 Project Milestones | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 792+00-793+00 - Ph1-S1 | Substantial Completion | 0 | DEMO
CP110 | CP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | CONCRETE
DS370 | SUBS570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | PIER 3 NB Redesign Osborne Drilled shaft issued by owner to a spread footer. | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DS140 | DS370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | PIER 3 NB Redesign Osborne Drilled shaft issued by owner to a spread footer. | 0 | SUB-ST-DRSFT
DEMO1280 | DEMO110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Waiting on Owner Lane Closure Approval to Ensure Floribraska Ramp C can begin on 7/31 | Demo / Grade - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 |  | DEMO
LOE-FLOR-C | DEMO1280 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | **Floribraska Ramp C - 45 Calendar Day Duration (SUMMARY) | Waiting on Owner Lane Closure Approval to Ensure Floribraska Ramp C can begin on 7/31 | 0
MS-LNTP | DEMO110 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Notice to Proceed | Demo / Grade - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 |  | DEMO
DS140 | DS360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | PIER 2 NB Bridge Osborne Waiting on EAR Results | 0 | SUB-ST-DRSFT
DS360 | SUBS560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | PIER 2 NB Bridge Osborne Waiting on EAR Results | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DS170 | DS380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | PIER 2 SB Bridge Osborne Waiting on EAR Results | 0 | SUB-ST-DRSFT
DS380 | SUBS930 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | PIER 2 SB Bridge Osborne Waiting on EAR Results | Form / Reinforce / Pour Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
DS170 | DS390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | PIER 3 SB Bridge Osborne Waiting on EAR Results | 0 | SUB-ST-DRSFT
DS390 | SUBS950 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | PIER 3 SB Bridge Osborne Waiting on EAR Results | Form / Reinforce / Pour Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
MSE1760 | MSE220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | DELAY- Waiting on Soil Nail Anchor Owner Review/Approval @ Wall 2 (Sent Data 5-25-2022) | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE1760 | MSE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | DELAY- Waiting on Soil Nail Anchor Owner Review/Approval @ Wall 2 (Sent Data 5-25-2022) | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 |  | SUB-ST-MSE
WL370 | MSE1760 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Wall Lagging & Tie-Backs - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | DELAY- Waiting on Soil Nail Anchor Owner Review/Approval @ Wall 2 (Sent Data 5-25-2022) | 0 | ST-PILE
ITS250 | PILE240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Relocate Existing ITS Hillsborough SB | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 0 |  | ST-SOLDIER
MS-LNTP | ITS250 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Notice to Proceed | Relocate Existing ITS Hillsborough SB | 0
ITS210 | DEMO1040 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Relocate Existing ITS Poles and Camera SB MLK | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | 0 |  | DEMO
MS-LNTP | ITS210 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Notice to Proceed | Relocate Existing ITS Poles and Camera SB MLK | 0
MS-LNTP | DRG2300 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Notice to Proceed | Drainage: S-141 to S-140 (18") - NB & SB Median: 800-801 - Ph2 | 0 |  | DRAIN
MS-LNTP | PILE430 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Notice to Proceed | H Pile Install - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 |  | ST-PILE
MS-LNTP | PILE460 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Notice to Proceed | H Pile Install - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 |  | ST-PILE
DEMO490 | EGC520 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 2 Structures - NB: 755+00-756+00 - Ph1-S1 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 0 | DEMO | EW-SML
DEMO460 | EGC520 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Demo Existing Drainage: Remove 30' of 15" Pipe & 1 Structure - NB: 755+00-756+00 - Ph1-S1 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 0 | DEMO | EW-SML
DEMO450 | EGC520 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Demo Existing Drainage: Remove 40' of 18" Pipe & 2 Structures - NB: 752+00-756+00 - Ph1-S1 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 0 | DEMO | EW-SML
MS-LNTP | DEMO490 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Notice to Proceed | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 2 Structures - NB: 755+00-756+00 - Ph1-S1 | 0 |  | DEMO
MS-LNTP | DEMO460 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Notice to Proceed | Demo Existing Drainage: Remove 30' of 15" Pipe & 1 Structure - NB: 755+00-756+00 - Ph1-S1 | 0 |  | DEMO
MSE1750 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 746+91.13 (S.End to Floribraska to E Lake) | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Concrete Readymix needed- Material Shortage in Tampa FL. | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE1750 | MSE260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 746+91.13 (S.End to Floribraska to E Lake) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Concrete Readymix needed- Material Shortage in Tampa FL. | Install Leveling Pad - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE1750 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 746+91.13 (S.End to Floribraska to E Lake) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Concrete Readymix needed- Material Shortage in Tampa FL. | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE1750 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 746+91.13 (S.End to Floribraska to E Lake) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Concrete Readymix needed- Material Shortage in Tampa FL. | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 |  | SUB-ST-MSE
MS-LNTP | MSE1750 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 746+91.13 (S.End to Floribraska to E Lake) | Notice to Proceed | Concrete Readymix needed- Material Shortage in Tampa FL. | 0
DS350 | DS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Utility Conflict at MLK SB Pier 3 (RFI# 132) | Cure 48" Drilled Shafts 100204 - SB: over MLK - Ph1-S1 | 0 |  | SUB-ST-DRSFT
MS-LNTP | DS350 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Notice to Proceed | Utility Conflict at MLK SB Pier 3 (RFI# 132) | 0
PM100 | MS-P3S | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Pavement Markings - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Start of Phase 3 | 0 | SUB-STRIP
PNT1360 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ Floribraska - South Side - Ph1-S1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1370 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ East Lake Ave. - South Side - Ph1-S1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1380 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ MLK Blvd.- South Side - Ph1-S1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1390 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ Chelsea St.- South Side - Ph1-S1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1400 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ E. Osborne Ave - South Side - Ph1-S1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1410 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1420 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ Floribraska - North Side - Ph1-S1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1430 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ East Lake Ave. - North Side - Ph1-S1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1440 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ MLK Blvd.- North Side - Ph1-S1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1450 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ Chelsea St.- North Side - Ph1-S1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1460 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ E. Osborne Ave - North Side - Ph1-S1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1470 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1240 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - MLK Ramp B - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1250 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - MLK Ramp C - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1260 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - Hillsborough Ramp B - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1270 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - Hillsborough Ramp C2 - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1280 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - Hillsborough Ramp C1 - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1290 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - Hillsborough Ramp D - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1300 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - Hillsborough Ramp A - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1310 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - MLK Ramp D - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1320 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - MLK Ramp A - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1330 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - I-275 SB / Floribraska Ramp NE - Ph1-S2 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1000 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 709+50-735+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1010 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 735+46-746+91 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1020 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 748+30-757+10 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1030 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 757+10-759+97 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1040 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 761+67-767+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1050 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 767+00-773+42 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1060 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 774+82-780+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1070 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 780+00-786+69 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1080 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 788+09-800+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1090 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 800+00-813+16 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1100 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - NB: 815+20-839+61 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1110 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 815+20-839+61 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1120 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 800+00-813+16 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1130 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 788+09-800+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1140 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 780+00-786+69 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1150 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 774+82-780+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1160 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 767+00-773+42 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1170 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 761+67-767+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1180 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 757+10-759+97 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1190 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 748+30-757+10 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1200 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 735+46-746+91 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1210 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 722+83-735+00 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
PNT1220 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Paint - SB: 709+50-721+43 - Ph1-S1 | End of Phase 3 | 0 | SUB-ST-PNT
MS-LNTP | CB160 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Notice to Proceed | Additional Core Bores Needed @ Osborne Pier 3 | 0
CB160 | DS140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Additional Core Bores Needed @ Osborne Pier 3 | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DEMO430 | FENCE10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Demo Existing Drainage: Remove 1 Structure - NB: 751+00-752+00 - Ph1-S1 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | SUB-FENCE
DEMO310 | FENCE10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 748 - 751 - IPh1 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | SUB-FENCE
DS340 | DRG2340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Utility Conflict Issue at Jack and Bore Drainage Structure S-158 (RFI#114) See Notes | Drainage: S-152 to S-158 (24") - NB & SB Median: 804-806 - Ph2 | 0 |  | DRAIN
MS-LNTP | DS340 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Notice to Proceed | Utility Conflict Issue at Jack and Bore Drainage Structure S-158 (RFI#114) See Notes | 0
MS-LNTP | DS330 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Notice to Proceed | Utility Conflict at Hillsborough NB Pier 2 Drilled Shaft (RFI#134) See Notes | 0
DS330 | DS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Utility Conflict at Hillsborough NB Pier 2 Drilled Shaft (RFI#134) See Notes | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
MS-LNTP | DS320 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Notice to Proceed | Utility Conflict at MLK SB Pier 3 Drilled Shaft (RFI#131) See Notes | 0
DS320 | DS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Utility Conflict at MLK SB Pier 3 Drilled Shaft (RFI#131) See Notes | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS310 | DS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Utility Conflict at MLK NB Pier 3 Drilled Shaft (RFI#126) See Notes | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
MS-LNTP | DS310 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Notice to Proceed | Utility Conflict at MLK NB Pier 3 Drilled Shaft (RFI#126) See Notes | 0
MS-LNTP | DS300 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Notice to Proceed | Utility Conflict At NB over MLK Blvd Ph1-S1 | 0
DS300 | DS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Utility Conflict At NB over MLK Blvd Ph1-S1 | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
MS-LNTP | PILE320 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Notice to Proceed | Drive Production H-Piles 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-PILE
MS-LNTP | SGN70A | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Notice to Proceed | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-101 / 723+54 | 0
MS-LNTP | DRG120A | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Notice to Proceed | Drainage: S-30 to S-30 OUT - Upper (18") - NB: 738-739) - Ph1-S1 | 0 |  | DRAIN
MS-LNTP | DEMO520 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Notice to Proceed | Demo Roadway - NB: 780+00-786+69 - Ph1-S1 | 0 |  | DEMO
MS-LNTP | WL400 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Notice to Proceed | Wall Lagging & Tie-Backs - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 |  | ST-PILE
MS-LNTP | PILE340 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Notice to Proceed | Drive Production H-Piles 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-PILE
MS-LNTP | PILE250 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Notice to Proceed | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-PILE
DEMO190 | WL390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Demo Existing Drainage: Remove S-11 Structure - NB: 725+00-726+00 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | DEMO | ST-PILE
MS-LNTP | DEMO440 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Notice to Proceed | Demo Existing Drainage: Remove 12' of 18" Pipe & 1 Structure - NB: 752+00-753+00 - Ph1-S1 | 0 |  | DEMO
TCC130 | TCC140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | Install MOT Construction Barriers I-275 SB - IPh1 | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | 0 | TRAFFIC | TRAFFIC
MS-LNTP | LTG1000 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Notice to Proceed | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 |  | SUB-UT-ELEC
MS-LNTP | DRG520 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Notice to Proceed | Drainage: S-144 OF to S-144 (30") - NB: 801 - 802 - IPh1 | 0 |  | DRAIN
GRD1020 | PNT1530 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Paint - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW- ALL EW | SUB-ST-PNT
TCC150 | GRD400 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Traffic Control | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Detour North Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S2 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | 0 | TC-Maint. | SUB-DGRIND
MS-LNTP | DEMO970 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Notice to Proceed | Demo Existing Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | 0 |  | DEMO
DEMO170 | DEMO1990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 2 Structures - SB: 835 - 840 - IPh1 | Demo Existing Drainage: Remove 76' of 18" Pipe - NB & SB Median: 828+00-830+00 - Ph2 | 0 | DEMO | DEMO
MS-LNTP | DEMO890 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Notice to Proceed | Demo Existing Drainage: Remove 1 Structure - SB: 839+00-840+00 - Ph1-S1 | 0 |  | DEMO
MS-LNTP | DEMO130 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Notice to Proceed | Demo Roadway - NB: 722+83-735+00 - Ph1-S1 | 0 |  | DEMO
MS-LNTP | DEMO | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | Notice to Proceed | Demo Traffic Railing 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | DEMO
MS-LNTP | DEMO1090 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Notice to Proceed | Demo Existing Slope Pavement @ E. Osborne Ave.- North Side - Ph1-S1-S2 | 0 |  | DEMO
WBO-CTWD-10 | MS-FC | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.1.1 City of Tampa Wastewater Department Project ID: 431821-02-52-01 (Prior to starting work) | 3462-FDOT-Owner-12.0 Project Milestones | (Act #1) Ex. 12" Concrete Wastewater (815+14.86-174' RT to 815+39.86-173.71' RT) - COT Identified Line to Remain | Final Completion (Baseline Date: 24-Apr-25) | 0
MSE1600 | MSE540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13C | Procurement: MSE Walls W-13C | 0
MS-LNTP | MSE1170 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-3C | 0
MS-LNTP | MSE1180 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-11A, 11B, 11C | 0
MS-LNTP | MSE1210 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-14A, 14B | 0
MS-LNTP | MSE1220 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W- 5A | 0
MS-LNTP | MSE1230 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-13G | 0
MS-LNTP | MSE1240 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-1A, 1B, 1C | 0
MS-LNTP | MSE1250 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-5B | 0
MS-LNTP | MSE1260 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-2A, 2B | 0
MS-LNTP | MSE1270 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-3B | 0
MS-LNTP | MSE1280 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-4A, 4B | 0
MS-LNTP | MSE1290 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-5C | 0
MS-LNTP | MSE1300 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-7B, 7C | 0
MS-LNTP | MSE1310 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-13B | 0
MS-LNTP | MSE1320 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-13C | 0
MS-LNTP | MSE1330 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-13D | 0
MS-LNTP | MSE1340 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-13E | 0
MS-LNTP | MSE1350 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-15C | 0
MS-LNTP | MSE1360 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-15D | 0
MS-LNTP | MSE1370 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-19A | 0
MS-LNTP | MSE1380 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-22A, 22B, 22C | 0
MS-LNTP | MSE1390 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-21C, 21D | 0
MS-LNTP | MSE1400 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-21A, 21B | 0
MS-LNTP | MSE1410 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-20A, 20B | 0
MS-LNTP | MSE1420 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-18A, 18B | 0
MS-LNTP | MSE1430 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-17B | 0
MS-LNTP | MSE1440 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-17C | 0
MS-LNTP | MSE1450 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-16A, 16B | 0
MS-LNTP | MSE1460 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls W-15A | 0
MSE1740 | MSE1100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls 15A | Procurement: MSE Walls W-15A | 0
MSE1460 | MSE1740 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-15A | Review & Approve Shop Drawings / Submittals: MSE Walls 15A | 0
MSE1730 | MSE1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-16A, 16B | Procurement: MSE Walls W-16A, 16B | 0
MSE1450 | MSE1730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-16A, 16B | Review & Approve Shop Drawings / Submittals: MSE Walls W-16A, 16B | 0
MSE1720 | MSE1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-17C | Procurement: MSE Walls W-17C | 0
MSE1440 | MSE1720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-17C | Review & Approve Shop Drawings / Submittals: MSE Walls W-17C | 0
MSE1710 | MSE980 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-17B | Procurement: MSE Walls W-17B | 0
MSE1430 | MSE1710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-17B | Review & Approve Shop Drawings / Submittals: MSE Walls W-17B | 0
MSE1700 | MSE960 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-18A, 18B | Procurement: MSE Walls W-18A, 18B | 0
MSE1420 | MSE1700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-18A, 18B | Review & Approve Shop Drawings / Submittals: MSE Walls W-18A, 18B | 0
MSE1690 | MSE930 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-20A, 20B | Procurement: MSE Walls W-20A, 20B | 0
MSE1410 | MSE1690 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-20A, 20B | Review & Approve Shop Drawings / Submittals: MSE Walls W-20A, 20B | 0
MSE1680 | MSE900 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-21A, 21B | Procurement: MSE Walls W-21A, 21B | 0
MSE1400 | MSE1680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-21A, 21B | Review & Approve Shop Drawings / Submittals: MSE Walls W-21A, 21B | 0
MSE1670 | MSE820 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-21C, 21D | Procurement: MSE Walls W-21C, 21D | 0
MSE1390 | MSE1670 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-21C, 21D | Review & Approve Shop Drawings / Submittals: MSE Walls W-21C, 21D | 0
MSE1660 | MSE760 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-22A, W-22B, W-22C | Procurement: MSE Walls W-22A, W-22B, W-22C | 0
MSE1380 | MSE1660 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-22A, 22B, 22C | Review & Approve Shop Drawings / Submittals: MSE Walls W-22A, W-22B, W-22C | 0
MSE1650 | MSE730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-19A | Procurement: MSE Walls W-19A | 0
MSE1370 | MSE1650 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-19A | Review & Approve Shop Drawings / Submittals: MSE Walls W-19A | 0
MSE1640 | MSE700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-15D | Procurement: MSE Walls W-15D | 0
MSE1360 | MSE1640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-15D | Review & Approve Shop Drawings / Submittals: MSE Walls W-15D | 0
MSE1630 | MSE670 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-15C | Procurement: MSE Walls W-15C | 0
MSE1350 | MSE1630 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-15C | Review & Approve Shop Drawings / Submittals: MSE Walls W-15C | 0
MSE1620 | MSE590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13E | Procurement: MSE Walls W-13E | 0
MSE1340 | MSE1620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13E | Review & Approve Shop Drawings / Submittals: MSE Walls W-13E | 0
MSE1610 | MSE560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13D | Procurement: MSE Walls W-13D | 0
MSE1330 | MSE1610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13D | Review & Approve Shop Drawings / Submittals: MSE Walls W-13D | 0
MSE1320 | MSE1600 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13C | Review & Approve Shop Drawings / Submittals: MSE Walls W-13C | 0
MSE1320 | MSE1600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13C | Review & Approve Shop Drawings / Submittals: MSE Walls W-13C | 0
MSE1590 | MSE510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13B | Procurement: MSE Walls W-13B | 0
MSE1310 | MSE1590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13B | Review & Approve Shop Drawings / Submittals: MSE Walls W-13B | 0
MSE1580 | MSE490 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-7B, 7C | Procurement: MSE Walls W-7B, 7C | 0
MSE1300 | MSE1580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-7B, 7C | Review & Approve Shop Drawings / Submittals: MSE Walls W-7B, 7C | 0
MSE1570 | MSE380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-4A, 4B | Procurement: MSE Walls W-4A, 4B | 0
MSE1280 | MSE1570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-4A, 4B | Review & Approve Shop Drawings / Submittals: MSE Walls W-4A, 4B | 0
MSE1560 | MSE360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-3B | Procurement: MSE Walls W-3B | 0
MSE1270 | MSE1560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-3B | Review & Approve Shop Drawings / Submittals: MSE Walls W-3B | 0
MSE1550 | MSE310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-2A, 2B | Procurement: MSE Walls W-2A, 2B | 0
MSE1260 | MSE1550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-2A, 2B | Review & Approve Shop Drawings / Submittals: MSE Walls W-2A, 2B | 0
MSE1540 | MSE450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-5C | Procurement: MSE Walls W-5C | 0
MSE1290 | MSE1540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-5C | Review & Approve Shop Drawings / Submittals: MSE Walls W-5C | 0
MSE1530 | MSE270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-5B | Procurement: MSE Walls W-5B | 0
MSE1250 | MSE1530 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-5B | Review & Approve Shop Drawings / Submittals: MSE Walls W-5B | 0
MSE1520 | MSE210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-5A | Procurement: MSE Walls W-5A | 0
MSE1220 | MSE1520 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W- 5A | Review & Approve Shop Drawings / Submittals: MSE Walls W-5A | 0
MSE1510 | MSE180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-1A, 1B, 1C | Procurement: MSE Walls W-1A, 1B, 1C | 0
MSE1240 | MSE1510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-1A, 1B, 1C | Review & Approve Shop Drawings / Submittals: MSE Walls W-1A, 1B, 1C | 0
MSE1500 | MSE80 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-14A, 14B | Procurement: MSE Walls W-14A, 14B | 0
MSE1210 | MSE1500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-14A, 14B | Review & Approve Shop Drawings / Submittals: MSE Walls W-14A, 14B | 0
MSE1490 | MSE90 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-13G | Procurement: MSE WallsW-13G | 0
MSE1230 | MSE1490 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-13G | Review & Approve Shop Drawings / Submittals: MSE Walls W-13G | 0
MSE1480 | MSE70 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-11A, 11B, 11C | Procurement: MSE Walls W-11A, 11B, 11C | 0
MSE1180 | MSE1480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-11A, 11B, 11C | Review & Approve Shop Drawings / Submittals: MSE Walls W-11A, 11B, 11C | 0
MSE1470 | MSE60 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls W-3C | Procurement: MSE Walls W-3C | 0
MSE1170 | MSE1470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls W-3C | Review & Approve Shop Drawings / Submittals: MSE Walls W-3C | 0
MSE1100 | MSE970 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Procurement: MSE Walls W-15A | Install MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE1060 | MSE920 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Procurement: MSE Walls W-16A, 16B | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE1000 | MSE880 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Procurement: MSE Walls W-17C | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE980 | MSE850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Procurement: MSE Walls W-17B | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE960 | MSE810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Procurement: MSE Walls W-18A, 18B | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE900 | MSE740A | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Procurement: MSE Walls W-21A, 21B | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE930 | MSE780 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Procurement: MSE Walls W-20A, 20B | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE820 | MSE740 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Procurement: MSE Walls W-21C, 21D | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE760 | MSE690 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Procurement: MSE Walls W-22A, W-22B, W-22C | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE730 | MSE640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Procurement: MSE Walls W-19A | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE700 | MSE620 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Procurement: MSE Walls W-15D | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE670 | MSE580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Procurement: MSE Walls W-15C | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE670 | MSE580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Procurement: MSE Walls W-15C | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE590 | MSE530A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Procurement: MSE Walls W-13E | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE590 | MSE530 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Procurement: MSE Walls W-13E | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | 0 |  | SUB-ST-MSE
MSE560 | MSE480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Procurement: MSE Walls W-13D | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE540 | MSE440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Procurement: MSE Walls W-13C | Install MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE510 | MSE410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Procurement: MSE Walls W-13B | Install MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE490 | MSE370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Procurement: MSE Walls W-7B, 7C | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE450 | MSE330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Procurement: MSE Walls W-5C | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE380 | MSE290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Procurement: MSE Walls W-4A, 4B | Install MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE360 | MSE250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Procurement: MSE Walls W-3B | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE310 | MSE220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Procurement: MSE Walls W-2A, 2B | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE270 | MSE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Procurement: MSE Walls W-5B | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE210 | MSE140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Procurement: MSE Walls W-5A | Install MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE180 | MSE1160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Procurement: MSE Walls W-1A, 1B, 1C | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE90 | MSE1020 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Procurement: MSE WallsW-13G | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE80 | MSE1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Procurement: MSE Walls W-14A, 14B | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE70 | MSE1090 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Procurement: MSE Walls W-11A, 11B, 11C | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE60 | MSE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Procurement: MSE Walls W-3C | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE50 | MSE40 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls 6A, 6B | Procurement: MSE Walls 6A, 6B | 0
MSE1200 | MSE50 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls 6A, 6B | Review & Approve Shop Drawings / Submittals: MSE Walls 6A, 6B | 0
MS-LNTP | MSE1200 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls 6A, 6B | 0
MSE40 | MSE1130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Procurement: MSE Walls 6A, 6B | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 |  | SUB-ST-MSE
MS-P1S1F10 | TCC110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | Impact - Added Temporary Pavement per RFI 54 & RFI 55 (Start of Work) | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | 0 |  | TRAFFIC
MS-P1S1S | MS-P1S1S1S10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Start of Phase 1, Stage 1 | Impact - Shoulder Work per RFI 54 & RFI 55 (Notification, Procurement, etc.) | 0
MS-P1S1S1S10 | MS-P1S1F10 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Impact - Shoulder Work per RFI 54 & RFI 55 (Notification, Procurement, etc.) | Impact - Added Temporary Pavement per RFI 54 & RFI 55 (Start of Work) | 0
RDW20 | TCW270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Review & Approve Shop Drawings / Submittals: Temp Critical Walls (Duration = 25 Calendar Days) | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 |  | ST-WALL
RDW20 | PILE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Review & Approve Shop Drawings / Submittals: Temp Critical Walls (Duration = 25 Calendar Days) | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 |  | ST-SOLDIER
RDW10 | RDW40 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | Prepare Shop Drawings / Submittals: Temp Critical Walls | Procurement: Temp Critical Walls: Lagging Wall | 0
RDW10 | RDW30 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | Prepare Shop Drawings / Submittals: Temp Critical Walls | Procurement: Temp Critical Walls: H Pile | 0
R610 | R700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
MS-LNTP | RDW40 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | Notice to Proceed | Procurement: Temp Critical Walls: Lagging Wall | 0
MS-LNTP | RDW30 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | Notice to Proceed | Procurement: Temp Critical Walls: H Pile | 0
GRD1070 | GRD1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Earthwork: Temporary Diversion: SB: MLK Ramp D - IPh1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | EW- ALL EW | EW- ALL EW
FND20 | R720A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND20 | R655A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND20 | R720 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND20 | R655 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND10 | FND30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | Prepare Shop Drawings / Submittals: H-Pile Foundations | Procurement: Foundations: H-Pile Foundations | 0
TCC120 | DRG2570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Drainage: S-8 to S-7 (24") - Floribraska - Ph1-S1-S1 | 0 | TC-Maint. | DRAIN
MS-LNTP | DRG30 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | Notice to Proceed | Procurement: Drainage Pipe & Structures | 0
MS-LNTP | DRG20 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | Notice to Proceed | Review & Approve Shop Drawings / Submittals: Drainage Pipe & Structures (Duration = 25 Calendar Days) | 0
TCC120 | DEMO150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Drainage: Remove 25' of 24" Pipe - Floribraska: 721+00-722+00 - Ph1-S1 | 0 | TC-Maint. | DEMO
MS-P3S | PAV540 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Start of Phase 3 | Cure Friction Course - Project Limits - Ph3 | 0 |  | SUB-MILL
PAV530 | PAV540 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Cure Friction Course - Project Limits - Ph3 | 5 | SUB-MILL | SUB-MILL
FENCE110 | SOD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 727+93.05-736+99.11 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE100 | SOD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 739+739+79.12-739+81.53 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE90 | SOD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 748+30-757+10 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE80 | SOD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE70 | SOD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 790+73.28-791+94.03 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE60 | SOD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE50 | SOD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE40 | SOD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE30 | SOD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - NB: 827+13.67-832+53.77 - Ph1-S1 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE20 | SOD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Repair Fence / Install 6' Black Vinyl Fence & Gate at Ramp HILLSC1 - NB: 815+20-839+61 - Ph1-S1 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FENCE10 | SOD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-LANDSC
FG210 | FENCE100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 739+739+79.12-739+81.53 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG200 | FENCE90 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG180 | FENCE80 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG170 | FENCE70 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 790+73.28-791+94.03 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG170 | FENCE60 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG170 | FENCE50 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG160 | FENCE40 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
FG150 | FENCE10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-FENCE
SGN2180 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
DP150 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - SB: 800+00-813+16 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | EW-FINE
SGN620 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
ITS220 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
EL450 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK220 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN2190 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN630 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Signs - SB: 788+09-800+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL460 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK230 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM170 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Pavement Markings - Hillsborough Ramp A - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SGN2200 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN640 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Signs - SB: 780+00-786+69 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL470 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
ITS240 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
CLK240 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN650 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Signs - SB: 774+82-780+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL480 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK250 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN2210 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN660 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Signs - SB: 767+00-773+42 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
ITS260 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
EL490 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK260 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN670 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Signs - SB: 761+67-767+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL500 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK270 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM180 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Pavement Markings - MLK Ramp D - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SGN680 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Signs - SB: 757+10-759+97 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL510 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK280 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN2220 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN690 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Signs - SB: 748+30-757+10 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
ITS290 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
EL520 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK290 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM190 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Pavement Markings - MLK Ramp A - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SGN700 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Signs - SB: 735+46-746+91 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL530 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK300 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN710 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Signs - SB: 722+83-735+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
ITS310 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
ITS460 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
EL540 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK310 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN720 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
CLK320 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
CC140 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Crash Cushion - SB: 709+50-721+43 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-GRAIL | EW-FINE
EL550 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
PM200 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Pavement Markings - Floribraska Ramp NE - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SOD210 | PNT1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD210 | PNT1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD210 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD200 | PNT1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD200 | PNT1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD190 | PNT1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD190 | PNT1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD180 | PNT1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD180 | PNT1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD170 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD170 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD200 | SOD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD190 | SOD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD180 | SOD190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD170 | SOD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD160 | SOD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
FG200 | FG210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG190 | FG200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG180 | FG190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG170 | FG180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG160 | FG170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG210 | SOD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG200 | SOD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG190 | SOD190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG180 | SOD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG170 | SOD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
SGN2160 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN610 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN2170 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL440 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK210 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM160 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SOD150 | SOD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
FG150 | FG160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
SOD160 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
FG160 | SOD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Fine Grade - SB: 815+20-839+61 - Ph1-S1 | Install Grassing - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
SGN2150 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN600 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
ITS200 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
ITS440 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
CLK200 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM140 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Pavement Markings - Hillsborough Ramp C1 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
PM150 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Pavement Markings - Hillsborough Ramp C2 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SGN580 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Signs - NB: 788+09-800+00 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL410 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK180 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN2130 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN590 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Signs - NB: 800+00-813+16 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
SGN2140 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
EL420 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-FINE
CLK190 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM130 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Pavement Markings - Hillsborough Ramp B - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SGN560 | FG130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Signs - NB: 774+82-780+00 - Ph1-S1 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
CLK160 | FG130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN570 | FG130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Signs - NB: 780+00-786+69 - Ph1-S1 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
CLK170 | FG130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN540 | FG120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Signs - NB: 761+67-767+00 - Ph1-S1 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
CLK140 | FG120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN550 | FG120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Signs - NB: 767+00-773+42 - Ph1-S1 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
CLK150 | FG120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 0 | CP-SAW | EW-FINE
PM120 | FG120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Pavement Parkings - MLK Ramp C - Ph1-S1 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
SOD150 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD140 | PNT1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - NB: 788+09-813+16 - Ph1-S1 | Paint - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD130 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - NB: 774+82-786+69 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD120 | PNT1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - NB: 761+67-773+42 - Ph1-S1 | Paint - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD110 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - NB: 748+30-759+97 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD100 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Grassing - NB: 709+50 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-LANDSC | SUB-ST-PNT
SOD140 | SOD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install Grassing - NB: 788+09-813+16 - Ph1-S1 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD130 | SOD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Grassing - NB: 774+82-786+69 - Ph1-S1 | Install Grassing - NB: 788+09-813+16 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD120 | SOD130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Grassing - NB: 761+67-773+42 - Ph1-S1 | Install Grassing - NB: 774+82-786+69 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
SOD110 | SOD120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Install Grassing - NB: 748+30-759+97 - Ph1-S1 | Install Grassing - NB: 761+67-773+42 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
FG140 | FG150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG130 | FG140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG120 | FG130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG110 | FG120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | 0 | EW-FINE | EW-FINE
FG150 | SOD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Fine Grade - NB: 815+20-839+61 - Ph1-S1 | Install Grassing - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG140 | SOD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Fine Grade - NB: 788+09-813+16 - Ph1-S1 | Install Grassing - NB: 788+09-813+16 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG130 | SOD130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Fine Grade - NB: 774+82-786+69 - Ph1-S1 | Install Grassing - NB: 774+82-786+69 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
FG120 | SOD120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Fine Grade - NB: 761+67-773+42 - Ph1-S1 | Install Grassing - NB: 761+67-773+42 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
SOD100 | SOD110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Grassing - NB: 709+50 - Ph1-S1 | Install Grassing - NB: 748+30-759+97 - Ph1-S1 | 0 | SUB-LANDSC | SUB-LANDSC
FG100 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - NB: 709+50 - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | EW-FINE | EW-FINE
CC100 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Crash Cushions - NB: 748+30-757+10 - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | SUB-GRAIL | EW-FINE
CLK120 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | CP-SAW | EW-FINE
ITS120 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
CLK130 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN530 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
PM110 | FG110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Pavement Markings - MLK Ramp B - Ph1-S1 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | 0 | SUB-STRIP | EW-FINE
FG110 | SOD110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Fine Grade - NB: 748+30-759+97 - Ph1-S1 | Install Grassing - NB: 748+30-759+97 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
CLK110 | FG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | Fine Grade - NB: 709+50 - Ph1-S1 | 0 | CP-SAW | EW-FINE
ITS470 | FG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | Fine Grade - NB: 709+50 - Ph1-S1 | 0 | SUB-UT-ITS | EW-FINE
SGN2090 | FG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | Fine Grade - NB: 709+50 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
CLK100 | FG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | Fine Grade - NB: 709+50 - Ph1-S1 | 0 | CP-SAW | EW-FINE
SGN2100 | FG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | Fine Grade - NB: 709+50 - Ph1-S1 | 0 | SUB-SIGN | EW-FINE
FG100 | SOD100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Fine Grade - NB: 709+50 - Ph1-S1 | Install Grassing - NB: 709+50 - Ph1-S1 | 0 | EW-FINE | SUB-LANDSC
ITS440 | ITS370 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
SGN2220 | SGN2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2240 | GR160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-SIGN | SUB-GRAIL
SGN80 | SGN2240 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Procurement: Sign Posts / Gantry - OHS-102 / 736+00 | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | 0 |  | SUB-SIGN
PAV470 | SGN2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP440 | SGN2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2240 | SGN710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN690 | SGN2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Signs - SB: 748+30-757+10 - Ph1-S1 | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2240 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-102 Structure & Sign - SB: 736+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2220 | SGN2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2230 | GR160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-SIGN | SUB-GRAIL
SGN100 | SGN2230 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Procurement: Sign Posts / Gantry - OHC-102 / 745+96 | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | 0 |  | SUB-SIGN
PAV470 | SGN2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP440 | SGN2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2230 | SGN710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN690 | SGN2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Signs - SB: 748+30-757+10 - Ph1-S1 | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2230 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-102 Structure & Sign - SB: 745+96 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2220 | SGN700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | Install Signs - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2220 | ITS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
PAV460 | SGN2220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP430 | SGN2220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN120 | SGN2220 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Procurement: Sign Posts / Gantry - OHC-103 / 758+73 | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2210 | SGN2220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN650 | SGN2220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Signs - SB: 774+82-780+00 - Ph1-S1 | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2220 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-103 Structure & Sign - SB: 758+73 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2210 | ITS260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN130 | SGN2210 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Procurement: Sign Posts / Gantry - OHS-104 / 771+34 | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | 0 |  | SUB-SIGN
CP500 | SGN2210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP380 | SGN2210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2210 | SGN670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | Install Signs - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN650 | SGN2210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Signs - SB: 774+82-780+00 - Ph1-S1 | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2210 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-104 Structure & Sign - SB: 771+34 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2190 | SGN2200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2200 | FENCE80 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-FENCE
SGN2200 | ITS240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN150 | SGN2200 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Procurement: Sign Posts / Gantry - OHS-106 / 783+35 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | 0 |  | SUB-SIGN
CP450 | SGN2200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP360 | SGN2200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2200 | SGN650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | Install Signs - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN630 | SGN2200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Signs - SB: 788+09-800+00 - Ph1-S1 | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2200 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-106 DMS Structure & Sign - SB: 783+35 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2180 | SGN2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2190 | ITS450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN2190 | ITS230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN160 | SGN2190 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Procurement: Sign Posts / Gantry - OHC-104 / 792+45 | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2190 | SGN640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | Install Signs - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP420 | SGN2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP340 | SGN2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN620 | SGN2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Signs - SB: 800+00-813+16 - Ph1-S1 | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2190 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-104 Structure & Sign - SB: 792+45 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2170 | SGN2180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2160 | SGN2180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2180 | FENCE50 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | 0 | SUB-SIGN | SUB-FENCE
SGN2180 | ITS220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN180 | SGN2180 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Procurement: Sign Posts / Gantry - OHC-105 / 808+47 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 0 |  | SUB-SIGN
CP390 | SGN2180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP320 | SGN2180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2180 | SGN630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | Install Signs - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN610 | SGN2180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Signs - SB: 815+20-839+61 - Ph1-S1 | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2180 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-105 Structure & Sign - SB: 808+47 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2160 | SGN2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2150 | SGN2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP350 | SGN2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN200 | SGN2170 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Procurement: Sign Posts / Gantry - OHB-01 / 818+78 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 |  | SUB-SIGN
CP330 | SGN2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP310 | SGN2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2170 | SGN620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN600 | SGN2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2170 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHB-01 Structure & Sign - SB: 818+78 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2150 | SGN2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP350 | SGN2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN210 | SGN2160 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Procurement: Sign Posts / Gantry - OHS-108 / 825+75 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 0 |  | SUB-SIGN
CP330 | SGN2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP310 | SGN2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2160 | SGN620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN600 | SGN2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2160 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-108 Structure & Sign - SB: 825+75 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2140 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2130 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2150 | ITS440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN2150 | GR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Install Guardrail - NB: 159+48.98-163+10.72 - Ph1-S1 | 0 | SUB-SIGN | SUB-GRAIL
SGN2150 | ITS200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
CP300 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP280 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN220 | SGN2150 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Procurement: Sign Posts / Gantry - OHC-107 / 833+46 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2150 | SGN610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP290 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP260 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN590 | SGN2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 800+00-813+16 - Ph1-S1 | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2150 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-107 Structure & Sign - NB: 833+46 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2130 | SGN2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN190 | SGN2140 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Procurement: Sign Posts / Gantry - OHC-106 / 811+90 | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2140 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP270 | SGN2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP240 | SGN2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN580 | SGN2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Signs - NB: 788+09-800+00 - Ph1-S1 | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2140 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-106 Structure & Sign - NB: 811+90 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN170 | SGN2130 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Procurement: Sign Posts / Gantry - OHS-107 / 800+70 | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2130 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP270 | SGN2130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP240 | SGN2130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN580 | SGN2130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Signs - NB: 788+09-800+00 - Ph1-S1 | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2130 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-107 Structure & Sign - NB: 800+70 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN140 | SGN2120 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Procurement: Sign Posts / Gantry - OHS-105 / 775+55 | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | 0 |  | SUB-SIGN
CP210 | SGN2120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP160 | SGN2120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN2120 | SGN570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | Install Signs - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN550 | SGN2120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Signs - NB: 767+00-773+42 - Ph1-S1 | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2120 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-105 Structure & Sign - NB: 775+55 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN2110 | ITS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN110 | SGN2110 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Procurement: Sign Posts / Gantry - OHS-103 / 750+92 | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2110 | SGN530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
PAV330 | SGN2110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
SGN510 | SGN2110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Signs - NB: 735+46-746+91 - Ph1-S1 | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2110 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-103 Structure & Sign - NB: 750+92 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN90 | SGN2100 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Procurement: Sign Posts / Gantry - OHC-101 / 739+29 | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 0 |  | SUB-SIGN
SGN70 | SGN2090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: Sign Posts / Gantry - OHS-101 / 723+54 | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | 0 |  | SUB-SIGN
SGN500 | ITS470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Signs - NB: 709+50-735+00 - Ph1-S1 | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
PAV300 | ITS470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
GRD100 | ITS470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
PAV300 | SGN2100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
PAV300 | SGN2090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
SGN2090 | SGN2100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2100 | ITS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN2100 | SGN530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
PAV330 | SGN2100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
SGN510 | SGN2100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Signs - NB: 735+46-746+91 - Ph1-S1 | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2100 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN2100 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Procurement: Signage | Install OHC-101 Structure & Signs - NB: 739+29+54 - Ph1-S1 | 0 |  | SUB-SIGN
SGN2090 | ITS470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN2090 | ITS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN2090 | SGN530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN2090 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN2090 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: Signage | Install OHS-101 DMS Structure & Signs - NB: 723+54 - Ph1-S1 | 0 |  | SUB-SIGN
ITS100 | ITS430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS200 | FENCE10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-FENCE
ITS440 | FENCE10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-FENCE
ITS470 | ITS390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS470 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS30 | ITS470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: ITS | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS470 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install DMS-NB-1 & Equipment - NB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS460 | ITS410 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: South End to MLK | 5 | SUB-UT-ITS | SUB-UT-ITS
SGN710 | ITS460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Signs - SB: 722+83-735+00 - Ph1-S1 | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
ITS460 | ITS340 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | ITS Testing - SB | 5 | SUB-UT-ITS | SUB-UT-ITS
ITS30 | ITS460 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Procurement: ITS | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-UT-ITS
PAV480 | ITS460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
GRD310 | ITS460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
ITS460 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install WWVDS SB-1, SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS310 | ITS410 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: South End to MLK | 10 | SUB-UT-ITS | SUB-UT-ITS
ITS290 | ITS410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS260 | ITS420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS240 | ITS420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS450 | ITS420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS230 | ITS420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
SGN630 | ITS450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Signs - SB: 788+09-800+00 - Ph1-S1 | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
ITS450 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS30 | ITS450 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Procurement: ITS | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-UT-ITS
GRD230 | ITS450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
ITS450 | ITS240 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 6 | SUB-UT-ITS | SUB-UT-ITS
ITS220 | ITS450 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | 6 | SUB-UT-ITS | SUB-UT-ITS
ITS450 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Generator & Equipment - SB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS220 | ITS420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS120 | ITS390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS440 | ITS400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - NB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS200 | ITS400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - NB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS200 | ITS440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
SGN600 | ITS440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
ITS440 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS30 | ITS440 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Procurement: ITS | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-UT-ITS
GRD200 | ITS440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
ITS440 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CAB-SB-2 & MVDS SB-7 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS430 | ITS390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
SGN500 | ITS430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Signs - NB: 709+50-735+00 - Ph1-S1 | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
ITS430 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS30 | ITS430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: ITS | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-UT-ITS
GRD100 | ITS430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
PAV300 | ITS430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
ITS430 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CAB-NB-2 & MVDS-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS100 | ITS390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1140 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1140 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1130 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1120 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1110 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1100 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 757+10-759+97 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1090 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1080 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1070 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 774+82-780+00 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1060 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1050 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1040 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1030 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1020 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL960 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL950 | EL960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1010 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL1000 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL990 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL980 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 774+82-780+00 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL970 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL960 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 761+67-767+00 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL950 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL940 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
EL930 | ITS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | Pull Fiber Main Lines - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS420 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS410 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - SB: South End to MLK | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS380 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Main Lines - SB | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS400 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - NB: MLK to North End | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS390 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS370 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Main Lines - NB | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS420 | ITS410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | Pull Fiber Branch Lines & Wire Drops - SB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS400 | ITS420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - NB: MLK to North End | Pull Fiber Branch Lines & Wire Drops - SB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS390 | ITS400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | Pull Fiber Branch Lines & Wire Drops - NB: MLK to North End | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS380 | ITS390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Main Lines - SB | Pull Fiber Branch Lines & Wire Drops - NB: South End to MLK | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS370 | ITS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Pull Fiber Main Lines - NB | Pull Fiber Main Lines - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG2550 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to S-1 (18") - SB: 715-717 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG2540 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG2520 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG2530 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG2510 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG2500 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC320 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL320 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL1130 | EL1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EGC310 | EL1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL310 | EL1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL1120 | EL1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG1010 | EL1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC300 | EL1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
DRG1000 | EL1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EL1110 | EL1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL300 | EL1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG1060 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1050 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1030 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1040 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1020 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC290 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL290 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL1100 | EL1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 757+10-759+97 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EGC280 | EL1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL280 | EL1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL1090 | EL1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG1170 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1160 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1150 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1090 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1080 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1070 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC260 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL1080 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL270 | EL1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG1190 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1140 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1130 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1120 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1110 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1100 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1180A | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC270 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL260 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL1070 | EL1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 774+82-780+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EGC250 | EL1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
DRG1260A | EL1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EL1060 | EL1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG1240 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1250 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1220 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1210 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1230A | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1200 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC240 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL1050 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL240 | EL1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG1330 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Mitered End to Mitered End (30") - SB: 799-800 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1320 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1310 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1300 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1290 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1280 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG140A | EL1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 OF to S-139 - Upper (18") - SB: 800-802 - Swale 1A - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1270 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC230 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL1040 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL230 | EL1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG1440 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1430 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1420 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1410 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1400 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1390 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1380 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1370 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1360 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1350 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG210A | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1340 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC220 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL220 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL1030 | EL1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG1520 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1510 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1500 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1480 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1470 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1460 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1600 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-305 to Existing (18") - SB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1590 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1570 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1560 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1550 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1540 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1530 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1580A | EL1030 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1490A | EL1030 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-218 to S-217 - Upper (24") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG260A | EL1030 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-227B to S-227A - Upper (18") - SB: 826-827 - Swale 2 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG1450 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC210 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL1020 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL210 | EL1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG820 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-301 OF to S-301 (18") - NB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG810 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG800 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG790 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-234 to S-235 (18") - NB: 828-829 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG780 | EL1020 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-231 to Existing (36") - NB: 827-828 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG770 | EL1020 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-232 to S-231 (36") - NB: 827-828 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG760 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-228 to S-232 (24") - NB: 826-828 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG750 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: Mitered End to Mitered End (24") - NB: 826-827 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG740 | EL1020 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG730 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG720 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG710 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-220 to S-221 (18") - NB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG700 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-203 (18") - NB: 819-821 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG690 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG680 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG670 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC200 | EL1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL1010 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL200 | EL1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG600 | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-159 OF to S-159 (14"x23") - NB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG590 | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG660 | EL1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-177 to S-175 to Existing (15") - NB: 810-812 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG650 | EL1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG640 | EL1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-169 to S-173 (18") - NB: 807-809 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG630 | EL1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-168 to S-169 (18") - NB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG620 | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 to S-168 (18") - NB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG610 | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG580A | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG570A | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC190 | EL1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL1000 | EL1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EL190 | EL1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL180 | EL1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG510 | EL1000 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-135 OF to S-135 (14"x23") - NB: 798-799 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG500 | EL1000 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 to S-122 (18") - NB: 795-796 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG490 | EL1000 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 OF to S-128 (18") - NB: 795-796 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC180 | EL1000 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL990 | EL1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG480 | EL990 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-119 to Existing (15") - NB: 783-784 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG470 | EL990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-115 to S-117 (18") - NB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG460 | EL990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-115 to S-110 (18") - NB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG450 | EL990 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-114 to S-115 (18") - NB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EL980 | EL990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 774+82-780+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EGC170 | EL990 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EGC160 | EL980 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL970 | EL980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
DRG440 | EL980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-106 to S-110 (18") - NB: 779-781 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG430 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-83 OF to S-83 to Existing (18") - NB: 768-769 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG420 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-79 to S-73 (18") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG410 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-80 to S-79 (18") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG400 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-78 to S-80 (18") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG390 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-78 to Existing (48") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG380 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: CD-3 to S-78 (48") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC150 | EL970 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL150 | EL970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG360 | EL960 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-65 to S-66 (18") - NB: 765-766 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EL140 | EL960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
DRG290 | EL950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG300 | EL950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG310 | EL950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG320 | EL950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EL120 | EL950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ITS
EL940 | EL950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EGC110 | EL940 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
DRG100 | EL940 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: Existing to S-28 to S-29 to Existing (36") - NB: 736-737 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG120A | EL940 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-30 to S-30 OUT - Upper (18") - NB: 738-739) - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG130 | EL940 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-31 to Existing (24") - NB: 739-740 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG140 | EL940 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: Existing to S-34A to S-34 to Existing (15") - NB: 744-745) - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG230 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-22 to Existing (36") - NB: 733-734 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG220 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG210 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-21 OF to S-22 (29"x45") - NB: 733-734 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG200 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-16 to S-22 (30") - NB: 729-734 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG190 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-18 to S-15 (18") - NB: 728-730 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG180 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-17 to S-18 (18") - NB: 729-730 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG170 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-16 to S-17 (18") - NB: 729-730 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
DRG160 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-13 to S-16 (30") - NB: 726-730 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ITS
EGC100 | EL930 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ITS
EL930 | EL940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Conduit & Pull Boxes: ITS - NB: 709+50-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: ITS - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ITS | SUB-UT-ITS
EC300 | CLK470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
B3440 | EC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-UT-ELEC
B3410 | EC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC290 | EC300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | Pull Wire / Install Underdeck Lighting 100211 - SB & NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EC280 | CLK480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
B2960 | EC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-UT-ELEC
B2930 | EC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC270 | EC280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | Pull Wire / Install Underdeck Lighting 100209 - SB & NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EC260 | CLK490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EC180 | EC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
B2450 | EC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC250 | EC260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | Pull Wire / Install Underdeck Lighting 100206 - SB & NB: over Chelsea St. - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EC240 | CLK500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
B2000 | EC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - SB: over MLK - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | 0 |  | SUB-UT-ELEC
B1970 | EC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - SB: over MLK - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC230 | EC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | Pull Wire / Install Underdeck Lighting 100204 - SB & NB: over MLK - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
B1520 | EC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC220 | CLK510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
B1510 | EC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - SB: over East Lake - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 0 |  | SUB-UT-ELEC
B1470 | EC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 0 |  | SUB-UT-ELEC
B1440 | EC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - NB: over East Lake - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC210 | EC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | Pull Wire / Install Underdeck Lighting 100207 - SB & NB: over East Lake - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EC200 | CLK410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Pull Wire / Install Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EC190 | EC200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | Pull Wire / Install Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EC190 | CLK410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Lighting Conduit for Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EC100 | EC190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Lighting Conduit at Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
B1200 | EC190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Deck Cure 100201 - NB: over Floribraska - Ph1-S1 | Install Lighting Conduit for Underdeck Lighting 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC130 | EC180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit at Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-UT-ELEC
EC100 | EC130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Install Lighting Conduit at Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-UT-ELEC
EL150 | EL180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL920 | MS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-1A, 1B, 1C - RAMP NE: 714+80.00-717+20.23 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL920 | MSE1190 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Coping - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE1160 | EL920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
BW1010 | BW1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | BARRIER
EL910 | BW1020 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Install Conduit & Pull Boxes: Lighting - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL910 | NW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Install Conduit & Pull Boxes: Lighting - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW1010 | EL910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL900 | BW990 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL900 | NW600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW980 | EL900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL890 | MS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL890 | MSE1150 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE1130 | EL890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL880 | BW900 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Install Conduit & Pull Boxes: Lighting - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 1 | SUB-UT-ELEC | BARRIER
EL880 | NW540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Install Conduit & Pull Boxes: Lighting - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW890 | EL880 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL870 | BW870 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 1 | SUB-UT-ELEC | BARRIER
EL870 | NW500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW850 | EL870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL860 | MS360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL860 | MSE1120 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install Coping - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE1090 | EL860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL240 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL850 | BW810 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL850 | NW490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW800 | EL850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL840 | MS350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL840 | MSE1080 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE1050 | EL840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL830 | BW780 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL830 | NW470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW770 | EL830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL820 | MS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL820 | MSE1040 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE1020 | EL820 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL810 | MS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL810 | MSE1010 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE970 | EL810 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL800 | NW450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
EL800 | BW750 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
BW730 | EL800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL790 | MS320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL790 | MSE940 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Install Coping - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE920 | EL790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL780 | MS310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL780 | MSE910 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE880 | EL780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL770 | MS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL770 | MSE840 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Coping - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE810 | EL770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL760 | BW610 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Install Conduit & Pull Boxes: Lighting - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL760 | NW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Install Conduit & Pull Boxes: Lighting - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW600 | EL760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL750 | MS280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL750 | MS270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL750 | MSE800 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE780 | EL750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL740 | BW580 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL740 | NW340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW570 | EL740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL730 | MS260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Conduit & Pull Boxes: Lighting - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE740A | EL730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL730 | MSE770 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Conduit & Pull Boxes: Lighting - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE740 | EL730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL720 | MS250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL720 | MSE720 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Coping - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE690 | EL720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL710 | NW290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 408+39.93-170+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
EL710 | BW510 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 408+39.93-170+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
BW500 | EL710 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 408+39.93-170+00.00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL700 | MSE680 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install Coping - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
EL700 | MS240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE640 | EL700 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL690 | MS220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE580A | EL690 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL690 | MSE630 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE580 | EL690 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL680 | MS210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE530A | EL680 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL680 | MSE570 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE530 | EL680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL670 | MSE520 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install Coping - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
EL670 | MS200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE480 | EL670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL660 | MSE470 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Install Coping - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
EL660 | MS190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE440 | EL660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL650 | BW330 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 104+06.12-107+60.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
EL650 | NW150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 104+06.12-107+60.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
BW300 | EL650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 104+06.12-107+60.00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 104+06.12-107+60.00 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL640 | MSE420 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Coping - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
EL640 | MS170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE370 | EL640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL630 | BW200 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 610+36.08-81+47.63 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
BW180 | EL630 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 610+36.08-81+47.63 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
EL620 | BW120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Install Conduit & Pull Boxes: Lighting - NB: 606+52.91-610+36.08 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | 2 | SUB-UT-ELEC | BARRIER
BW100 | EL620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 606+52.91-610+36.08 - Ph1-S1 | 0 | BARRIER | SUB-UT-ELEC
MSE170 | EL610 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL590 | EL600 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Conduit & Pull Boxes: Lighting - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL570 | EL580 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL560 | EL570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL600 | MS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
MSE140 | EL600 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL590 | MS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-4A, W-4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL590 | MSE320 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Conduit & Pull Boxes: Lighting - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Install Coping - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE290 | EL590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL580 | MS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL580 | MSE130 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Install Coping - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE110 | EL580 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL570 | MS140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL570 | MSE280 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Coping - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE250 | EL570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
EL560 | MS130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | SUB-UT-ELEC | CONCRETE
EL560 | MSE240 | FF | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Conduit & Pull Boxes: Lighting - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install Coping - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-MSE
MSE220 | EL560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-UT-ELEC
B4700 | GRD510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Approach Slabs Cure 100207 - SB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | 0 |  | SUB-DGRIND
B4700 | BASE660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Approach Slabs Cure 100207 - SB: over East Lake - Ph1-S1 | Black Base - SB: 748+30-757+10 - Ph1-S1 | 0 |  | EW-ABC
B4700 | B1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Approach Slabs Cure 100207 - SB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 0
R3960 | SUPR810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - SB: over East Lake - Ph1-S1 | 0 | FLATWORK | ST-APPR
SUPR800 | SUPR810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-APPR | ST-APPR
B1510 | SUPR810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - SB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - SB: over East Lake - Ph1-S1 | 0 |  | ST-APPR
SUPR810 | B4700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100207 - SB: over East Lake - Ph1-S1 | Approach Slabs Cure 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-APPR
PAV300 | TMS130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install Traffic Montoring Site Conduit - 718+11.00 - Ph 3 | 0 | SUB-ASPH | SUB-UT-ITS
PAV310 | TMS140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Install Traffic Montoring Site Conduit - 743+77.00 & 745+39.00 - Ph 3 | 0 | SUB-ASPH | SUB-UT-ITS
CP250 | TMS150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Install Traffic Montoring Site Conduit - 795+22.00 & 796+67.00 - Ph 3 | 0 | CONCRETE | SUB-UT-ITS
TMS150 | CLK180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Traffic Montoring Site Conduit - 795+22.00 & 796+67.00 - Ph 3 | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ITS | CP-SAW
CP220 | TMS150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Install Traffic Montoring Site Conduit - 795+22.00 & 796+67.00 - Ph 3 | 0 | CONCRETE | SUB-UT-ITS
TMS140 | CLK110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Traffic Montoring Site Conduit - 743+77.00 & 745+39.00 - Ph 3 | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ITS | CP-SAW
CP110 | TMS140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | Install Traffic Montoring Site Conduit - 743+77.00 & 745+39.00 - Ph 3 | 0 | CONCRETE | SUB-UT-ITS
TMS130 | CLK100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Traffic Montoring Site Conduit - 718+11.00 - Ph 3 | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ITS | CP-SAW
CP100 | TMS130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | Install Traffic Montoring Site Conduit - 718+11.00 - Ph 3 | 0 | CONCRETE | SUB-UT-ITS
TMS120 | PM220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 795+22.00 & 796+67.00 - Ph 3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-UT-ITS | SUB-STRIP
TMS120 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 795+22.00 & 796+67.00 - Ph 3 | End of Phase 3 | 0 | SUB-UT-ITS
TMS110 | TMS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 743+77.00 & 745+39.00 - Ph 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 795+22.00 & 796+67.00 - Ph 3 | 0 | SUB-UT-ITS | SUB-UT-ITS
TMS100 | TMS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 718+11.00 - Ph 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 743+77.00 & 745+39.00 - Ph 3 | 0 | SUB-UT-ITS | SUB-UT-ITS
MS-P3S | TMS100 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Start of Phase 3 | Install Traffic Montoring Site (Wiring/Sensors/Inductive Loop/Cabinets) - 718+11.00 - Ph 3 | 0 |  | SUB-UT-ITS
PAV410 | PAV560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S1 | Architectural Pavers - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV420 | PAV560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - MLK Ramp A - Ph1-S1 | Architectural Pavers - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV380 | PAV560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | Architectural Pavers - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV560 | PM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Architectural Pavers - MLK Ramp D - Ph1-S1 | Pavement Markings - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
PAV340 | PAV550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | Architectural Pavers - Hillsborough Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV550 | PM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Architectural Pavers - Hillsborough Ramp D - Ph1-S1 | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
PAV550 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Architectural Pavers - Hillsborough Ramp D - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-ASPH
DW160 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Detectable Warnings - Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
R755 | DW160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Pour Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | Detectable Warnings - Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R750 | DW160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Pour Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | Detectable Warnings - Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R730 | DW150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | Detectable Warnings - Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R725 | DW150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Slope Pavement @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | Detectable Warnings - Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
DW150 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Detectable Warnings - Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
DW100 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Detectable Warnings - Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
R620 | DW100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Pour Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | Detectable Warnings - Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R615 | DW100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Pour Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | Detectable Warnings - Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
FEN100 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
FEN240 | FEN100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Install 4' & 6' & 8' Mesh Fencing & Gates @ East Lake - South & North Sides - Ph1-S1 | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
R3960 | FEN240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | Install 4' & 6' & 8' Mesh Fencing & Gates @ East Lake - South & North Sides - Ph1-S1 | 0 | FLATWORK | SUB-FENCE
GRD510 | FEN240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | Install 4' & 6' & 8' Mesh Fencing & Gates @ East Lake - South & North Sides - Ph1-S1 | 0 | SUB-DGRIND | SUB-FENCE
FEN240 | PNT200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install 4' & 6' & 8' Mesh Fencing & Gates @ East Lake - South & North Sides - Ph1-S1 | Paint 100207 - SB: over East Lake - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
FEN230 | FEN240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install 6' Black Vinyl & 4' & 8' Mesh Fencing & Gates @ Chelsea St. - South & North Sides - Ph1-S1 | Install 4' & 6' & 8' Mesh Fencing & Gates @ East Lake - South & North Sides - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
R3970 | FEN230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | Install 6' Black Vinyl & 4' & 8' Mesh Fencing & Gates @ Chelsea St. - South & North Sides - Ph1-S1 | 0 | FLATWORK | SUB-FENCE
FEN230 | PNT180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install 6' Black Vinyl & 4' & 8' Mesh Fencing & Gates @ Chelsea St. - South & North Sides - Ph1-S1 | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
GRD490 | FEN230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | Install 6' Black Vinyl & 4' & 8' Mesh Fencing & Gates @ Chelsea St. - South & North Sides - Ph1-S1 | 0 | SUB-DGRIND | SUB-FENCE
FEN220 | FEN230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install 6' Black Vinyl & 4' & 6' & 8' Mesh Fencing & Gates @ E. Osborne Ave. - South & North Sides - Ph1-S1 | Install 6' Black Vinyl & 4' & 8' Mesh Fencing & Gates @ Chelsea St. - South & North Sides - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
FEN220 | PNT170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install 6' Black Vinyl & 4' & 6' & 8' Mesh Fencing & Gates @ E. Osborne Ave. - South & North Sides - Ph1-S1 | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
GRD480 | FEN220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install 6' Black Vinyl & 4' & 6' & 8' Mesh Fencing & Gates @ E. Osborne Ave. - South & North Sides - Ph1-S1 | 0 | SUB-DGRIND | SUB-FENCE
FEN210 | FEN220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install 6' Black Vinyl & 6' Mesh Fencing @ E. Hillsborough Ave. - South & North Sides - Ph1-S1 | Install 6' Black Vinyl & 4' & 6' & 8' Mesh Fencing & Gates @ E. Osborne Ave. - South & North Sides - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
FEN210 | PNT160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install 6' Black Vinyl & 6' Mesh Fencing @ E. Hillsborough Ave. - South & North Sides - Ph1-S1 | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
GRD470 | FEN210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install 6' Black Vinyl & 6' Mesh Fencing @ E. Hillsborough Ave. - South & North Sides - Ph1-S1 | 0 | SUB-DGRIND | SUB-FENCE
R4000 | FEN210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Hillsborough - South & North Sides - Ph1-S1 | Install 6' Black Vinyl & 6' Mesh Fencing @ E. Hillsborough Ave. - South & North Sides - Ph1-S1 | 0 | FLATWORK | SUB-FENCE
R3950 | FEN100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Form / Pour Slope Pavement Leave-Outs @ Floribraska - South & North Sides - Ph1-S1 | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | 0 | FLATWORK | SUB-FENCE
R3950 | CP440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Form / Pour Slope Pavement Leave-Outs @ Floribraska - South & North Sides - Ph1-S1 | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | 0 | FLATWORK | CONCRETE
R3960 | B1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 0 | FLATWORK
SUPR770 | R3960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / SIP / Reinforce / Pour Replacement Deck 100207 - SB: over East Lake - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
SUPR240 | R3960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Pour Deck 100207 - NB: over East Lake - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
R3980 | SUPR800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ MLK - South & North Sides - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | 0 | FLATWORK | ST-APPR
SUPR760 | R3980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pour Deck 100204 - SB: over MLK - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ MLK - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
SUPR320 | R3980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pour Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ MLK - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
R3970 | SUPR790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | FLATWORK | ST-APPR
SUPR740 | R3970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pour Deck 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
SUPR350 | R3970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pour Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
R3990 | SUPR780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Osbourne Ave - South & North Sides - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | FLATWORK | ST-APPR
SUPR450 | R3990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pour Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Osbourne Ave - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
SUPR690 | R3990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pour Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Osbourne Ave - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
R3960 | R3950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Floribraska - South & North Sides - Ph1-S1 | 0 | FLATWORK | FLATWORK
R3980 | R3960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ MLK - South & North Sides - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ East Lake - South & North Sides - Ph1-S1 | 0 | FLATWORK | FLATWORK
R3970 | R3980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ MLK - South & North Sides - Ph1-S1 | 0 | FLATWORK | FLATWORK
R3990 | R3970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Osbourne Ave - South & North Sides - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Chelsea St - South & North Sides - Ph1-S1 | 0 | FLATWORK | FLATWORK
R4000 | R3990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Hillsborough - South & North Sides - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Osbourne Ave - South & North Sides - Ph1-S1 | 0 | FLATWORK | FLATWORK
R4000 | SUPR580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Pour Slope Pavement Leave-Outs @ Hillsborough - South & North Sides - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | FLATWORK | ST-APPR
SUPR570 | R4000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pour Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Hillsborough - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
SUPR450 | R4000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pour Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Hillsborough - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
SUPR170 | R3950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Pour Deck 100201 - NB: over Floribraska - Ph1-S1 | Form / Pour Slope Pavement Leave-Outs @ Floribraska - South & North Sides - Ph1-S1 | 0 | ST-BRIDGE-SUP | FLATWORK
FEN100 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-FENCE
FEN100 | PNT100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | Paint 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
CLK410 | FEN100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | 0 | CP-SAW | SUB-FENCE
PAV430 | RBS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Floribraska Ramp NE - Ph1-S1 | Ground-In Rumble Strips - NB | 0 | SUB-ASPH | SUB-RUMBLE
PAV430 | RBS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Floribraska Ramp NE - Ph1-S1 | Ground-In Rumble Strips - SB | 0 | SUB-ASPH | SUB-RUMBLE
PAV490 | RBS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | Ground-In Rumble Strips - SB | 0 | SUB-ASPH | SUB-RUMBLE
PAV480 | RBS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | Ground-In Rumble Strips - SB | 0 | SUB-ASPH | SUB-RUMBLE
PAV470 | RBS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | Ground-In Rumble Strips - SB | 0 | SUB-ASPH | SUB-RUMBLE
PAV460 | RBS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Ground-In Rumble Strips - SB | 0 | SUB-ASPH | SUB-RUMBLE
PAV330 | RBS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Ground-In Rumble Strips - NB | 0 | SUB-ASPH | SUB-RUMBLE
PAV130 | RBS100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Ground-In Rumble Strips - NB | 0 | SUB-ASPH | SUB-RUMBLE
PAV310 | RBS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Ground-In Rumble Strips - NB | 0 | SUB-ASPH | SUB-RUMBLE
PAV300 | RBS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Ground-In Rumble Strips - NB | 0 | SUB-ASPH | SUB-RUMBLE
RBS100 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Ground-In Rumble Strips - NB | End of Phase 1, Stage 1 | 0 | SUB-RUMBLE
RBS110 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Ground-In Rumble Strips - SB | End of Phase 1, Stage 1 | 0 | SUB-RUMBLE
RBS100 | RBS110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Ground-In Rumble Strips - NB | Ground-In Rumble Strips - SB | 0 | SUB-RUMBLE | SUB-RUMBLE
CP720 | RBS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Concrete Shoulder - NB & SB Median: 815+20-839+61 - Ph2 | Ground-In Rumble Strips - Median | 0 | CONCRETE | SUB-RUMBLE
PAV520 | RBS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | Ground-In Rumble Strips - Median | 0 | SUB-ASPH | SUB-RUMBLE
PAV510 | RBS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | Ground-In Rumble Strips - Median | 0 | SUB-ASPH | SUB-RUMBLE
PAV500 | RBS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | Ground-In Rumble Strips - Median | 0 | SUB-ASPH | SUB-RUMBLE
RBS120 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Ground-In Rumble Strips - Median | End of Phase 2 | 0 | SUB-RUMBLE
FENCE110 | PNT1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 727+93.05-736+99.11 - Ph1-S1 | Paint - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
EL540 | FENCE110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 727+93.05-736+99.11 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-FENCE
FENCE100 | FENCE110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 739+739+79.12-739+81.53 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 727+93.05-736+99.11 - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
FENCE100 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 739+739+79.12-739+81.53 - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
EL530 | FENCE100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 739+739+79.12-739+81.53 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-FENCE
FENCE90 | PNT1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 748+30-757+10 - Ph1-S1 | Paint - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
EL520 | FENCE90 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-FENCE
EL470 | FENCE80 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-FENCE
FENCE80 | PNT1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | Paint - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
SGN640 | FENCE80 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Install Signs - SB: 780+00-786+69 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-FENCE
DP160 | PNT1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - SB: 774+82-780+00 - Ph1-S1 | Paint - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
CP480 | DP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | Form & Pour Ditch Pavement - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
FENCE70 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - SB: 790+73.28-791+94.03 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
EL460 | FENCE70 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 790+73.28-791+94.03 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-FENCE
FENCE60 | FENCE70 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | Install 6' Black Vinyl Fence - SB: 790+73.28-791+94.03 - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
FENCE60 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
EL460 | FENCE60 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-FENCE
FENCE50 | FENCE60 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | Install 6' Black Vinyl Fence & Double Gate - SB: 797+25.37-801+23.47 - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
FENCE50 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
SGN620 | FENCE50 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 807+15.32-808+41.87 - Ph1-S1 | 0 | SUB-SIGN | SUB-FENCE
DP150 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - SB: 800+00-813+16 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
CP390 | DP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Form & Pour Ditch Pavement - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
DRGS140 | RR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | Install Rip-Rap (2 Locations) - SB:805 - 806 - Swale 1A - IPh 1 | 0 | DRAIN | DRAINAGE
RR130 | LSP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Install Rip-Rap (2 Locations) - SB:805 - 806 - Swale 1A - IPh 1 | Grassing - SB: 801 - 805 - IPh 1 | 0 | DRAINAGE | SUB-LANDSC
DRGS190 | RR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Install Rip-Rap (2 Locations) - SB:805 - 806 - Swale 1A - IPh 1 | 0 | DRAIN | DRAINAGE
FENCE40 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Install 6' Black Vinyl Fence & Gate - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
CP330 | FENCE40 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-FENCE
CP350 | FENCE40 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence & Gate - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-FENCE
RR110 | LSP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Install Rip-Rap - NB: 801 - 802 - IPh1 | Grassing - NB: 801 - 805 - IPh1 | 0 | DRAINAGE | SUB-LANDSC
DRG580 | RR110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | Install Rip-Rap - NB: 801 - 802 - IPh1 | 0 | DRAIN | DRAINAGE
RR120 | LSP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Install Rip-Rap - SB: 834 - 836 - Swale 3B - IPh1 | Grassing - SB: 835 - 840 - IPh1 | 0 | DRAINAGE | SUB-LANDSC
DRGS290 | RR120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | Install Rip-Rap - SB: 834 - 836 - Swale 3B - IPh1 | 0 | DRAIN | DRAINAGE
DP140 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement (3 Locations) - NB: 815+20-839+61 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
CP300 | DP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Form & Pour Ditch Pavement (3 Locations) - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
FENCE30 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install 6' Black Vinyl Fence - NB: 827+13.67-832+53.77 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
FENCE20 | FENCE30 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Repair Fence / Install 6' Black Vinyl Fence & Gate at Ramp HILLSC1 - NB: 815+20-839+61 - Ph1-S1 | Install 6' Black Vinyl Fence - NB: 827+13.67-832+53.77 - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
FENCE10 | FENCE20 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install 6' Black Mesh Fence at Pond 2 - NB: 815+20-839+61 - Ph1-S1 | Repair Fence / Install 6' Black Vinyl Fence & Gate at Ramp HILLSC1 - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-FENCE | SUB-FENCE
DP130 | PNT1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - NB: 788+09-800+00 - Ph1-S1 | Paint - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
CP250 | DP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Form & Pour Ditch Pavement - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
DP120 | PNT1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - NB: 761+67-767+00 - Ph1-S1 | Paint - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
CP180 | DP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | Form & Pour Ditch Pavement - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
RR100 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Rip-Rap - NB: 751-752 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAINAGE | SUB-ST-PNT
PAV330 | RR100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Install Rip-Rap - NB: 751-752 - Ph1-S1 | 0 | SUB-ASPH | DRAINAGE
EGC120 | RR100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Install Rip-Rap - NB: 751-752 - Ph1-S1 | 0 | EW-SML | DRAINAGE
DRG240 | RR100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | Install Rip-Rap - NB: 751-752 - Ph1-S1 | 0 | DRAIN | DRAINAGE
DP110 | PNT1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - NB: 735+46-746+91 - Ph1-S1 | Paint - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
PAV310 | DP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Form & Pour Ditch Pavement - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | CONCRETE
DP100 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form & Pour Ditch Pavement - NB: 722+83-735+00 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | CONCRETE | SUB-ST-PNT
PAV300 | DP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Form & Pour Ditch Pavement - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | CONCRETE
FEN140 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Fencing @ E. Osborne Ave - South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | SUB-FENCE
FEN130 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Fencing @ Chelsea St.- South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | SUB-FENCE
FEN110 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Fencing @ East Lake Ave. - South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | SUB-FENCE
FEN160 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install 4' Mesh Fencing & Gate @ Floribraska - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | SUB-FENCE
FEN170 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Fencing @ East Lake Ave. - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | SUB-FENCE
FEN190 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Fencing @ Chelsea St.- North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | SUB-FENCE
FEN200 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Fencing @ E. Osborne Ave - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | SUB-FENCE
FEN200 | PNT1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Install Fencing @ E. Osborne Ave - North Side - Ph1-S1-S2 | Paint @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | SUB-FENCE | SUB-ST-PNT
R840 | FEN200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | Install Fencing @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-FENCE
FEN190 | PNT1450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Install Fencing @ Chelsea St.- North Side - Ph1-S1-S2 | Paint @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | SUB-FENCE | SUB-ST-PNT
R820 | FEN190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | Install Fencing @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-FENCE
FEN170 | PNT1430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Install Fencing @ East Lake Ave. - North Side - Ph1-S1-S2 | Paint @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | SUB-FENCE | SUB-ST-PNT
R780 | FEN170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | Install Fencing @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-FENCE
FEN160 | PNT1420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Install 4' Mesh Fencing & Gate @ Floribraska - North Side - Ph1-S1-S2 | Paint @ Floribraska - North Side - Ph1-S1-S2 | 0 | SUB-FENCE | SUB-ST-PNT
PAV280 | FEN160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Miscellaneous Asphalt Paving @ Floribraska - North Side - Ph1-S1-S2 | Install 4' Mesh Fencing & Gate @ Floribraska - North Side - Ph1-S1-S2 | 0 | SUB-ASPH | SUB-FENCE
FEN140 | PNT1400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Install Fencing @ E. Osborne Ave - South Side - Ph1-S1-S1 | Paint @ E. Osborne Ave - South Side - Ph1-S1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
R710 | FEN140 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Pour Sidewalk @ E. Osborne Ave - South Side - Ph1-S1-S1 | Install Fencing @ E. Osborne Ave - South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-FENCE
FEN130 | PNT1390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Install Fencing @ Chelsea St.- South Side - Ph1-S1-S1 | Paint @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
R690 | FEN130 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Pour Sidewalk @ Chelsea St.- South Side - Ph1-S1-S1 | Install Fencing @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-FENCE
FEN110 | PNT1370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Install Fencing @ East Lake Ave. - South Side - Ph1-S1-S1 | Paint @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
R645 | FEN110 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Pour Sidewalk @ East Lake Ave. - South Side - Ph1-S1-S1 | Install Fencing @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-FENCE
FEN100 | PNT1360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | Paint @ Floribraska - South Side - Ph1-S1-S1 | 0 | SUB-FENCE | SUB-ST-PNT
PAV160 | FEN100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.1.3 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 722+83.00: Bridge: Over Floribraska | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | Install 6' Black Vinyl Fencing & 4' & 8' Mesh & Gates @ Floribraska - South & North Sides - Ph1-S1 | 0 | SUB-ASPH | SUB-FENCE
LITTER | MS-FC | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.0 Project Milestones | Litter Clean Up | Final Completion (Baseline Date: 24-Apr-25) | 0
MS-NTP | LITTER | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start Construction | Litter Clean Up | 0
MOW | MS-FC | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.0 Project Milestones | Mowing | Final Completion (Baseline Date: 24-Apr-25) | 0
MS-NTP | MOW | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start Construction | Mowing | 0
GR160 | CLK300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-GRAIL | CP-SAW
CC140 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Crash Cushion - SB: 709+50-721+43 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-GRAIL
TBW110 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Set Temp Concrete Barrier Wall - Type K - SB: 709+50-721+43 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | BARRIER
TBW110 | PNT1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Set Temp Concrete Barrier Wall - Type K - SB: 709+50-721+43 - Ph1-S1 | Paint - SB: 709+50-721+43 - Ph1-S1 | 0 | BARRIER | SUB-ST-PNT
CLK320 | TBW110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | Set Temp Concrete Barrier Wall - Type K - SB: 709+50-721+43 - Ph1-S1 | 0 | CP-SAW | BARRIER
CC140 | PNT1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Crash Cushion - SB: 709+50-721+43 - Ph1-S1 | Paint - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-GRAIL | SUB-ST-PNT
CLK320 | CC140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | Install Crash Cushion - SB: 709+50-721+43 - Ph1-S1 | 0 | CP-SAW | SUB-GRAIL
SGN700 | GR160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Signs - SB: 735+46-746+91 - Ph1-S1 | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-SIGN | SUB-GRAIL
GR160 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-GRAIL | SUB-ST-PNT
GRD300 | GR160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | Install Guardrail - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-GRAIL
CURB170 | PAV450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Install Curb & Gutter Type F & D - MLK Ramp A - Ph1-S2 | Asphalt Paving - MLK Ramp A - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CAP150 | PAV450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Install Concrete Cap - MLK Ramp A - Ph1-S2 | Asphalt Paving - MLK Ramp A - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
BW1110A | CURB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | Install Curb & Gutter Type F & D - MLK Ramp A - Ph1-S2 | 0 | BARRIER | CONCRETE
UDR370 | CURB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Install Edgedrain - MLK Ramp A - Ph1-S2 | Install Curb & Gutter Type F & D - MLK Ramp A - Ph1-S2 | 0 | UNDR | CONCRETE
BW1110A | CAP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | Install Concrete Cap - MLK Ramp A - Ph1-S2 | 0 | BARRIER | CONCRETE
CURB170 | CAP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Install Curb & Gutter Type F & D - MLK Ramp A - Ph1-S2 | Install Concrete Cap - MLK Ramp A - Ph1-S2 | 0 | CONCRETE | CONCRETE
STAB490 | BW1110A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Stabilization - MLK Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | 0 | EW-CEM | BARRIER
CURB160 | GC110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Curb & Gutter Type F (?) - MLK Ramp D - Ph1-S2 | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | CONCRETE
GC110 | PAV440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | Asphalt Paving - MLK Ramp D - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CC120 | CC130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Crash Cushion - Hillsborough Ramp D - Ph1-S2 | Install Crash Cushion - MLK Ramp D - Ph1-S2 | 0 | SUB-GRAIL | SUB-GRAIL
CC130 | PNT1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Crash Cushion - MLK Ramp D - Ph1-S2 | Paint - MLK Ramp D - Ph1-S2 | 0 | SUB-GRAIL | SUB-ST-PNT
PAV440 | CC130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S2 | Install Crash Cushion - MLK Ramp D - Ph1-S2 | 0 | SUB-ASPH | SUB-GRAIL
CAP140 | PAV440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Concrete Cap - MLK Ramp D - Ph1-S2 | Asphalt Paving - MLK Ramp D - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CAP130 | CAP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Concrete Cap - Hillsborough Ramp A - Ph1-S2 | Install Concrete Cap - MLK Ramp D - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW1050A | CAP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | Install Concrete Cap - MLK Ramp D - Ph1-S2 | 0 | BARRIER | CONCRETE
CURB160 | CAP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Curb & Gutter Type F (?) - MLK Ramp D - Ph1-S2 | Install Concrete Cap - MLK Ramp D - Ph1-S2 | 0 | CONCRETE | CONCRETE
UDR340 | CURB160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Edgedrain - MLK Ramp D - Ph1-S2 | Install Curb & Gutter Type F (?) - MLK Ramp D - Ph1-S2 | 0 | UNDR | CONCRETE
CURB150 | CURB160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | Install Curb & Gutter Type F (?) - MLK Ramp D - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW1050A | CURB160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | Install Curb & Gutter Type F (?) - MLK Ramp D - Ph1-S2 | 0 | BARRIER | CONCRETE
STAB480 | BW1050A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Stabilization - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | 0 | EW-CEM | BARRIER
GR150 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Reset Guardrail (South of Swale 1A) - SB: 788+09-800+00 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-GRAIL | SUB-ST-PNT
GRD230 | GR150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Reset Guardrail (South of Swale 1A) - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-GRAIL
GR140 | PAV400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Guardrail - Hillsborough Ramp A - Ph1-S2 | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | 0 | SUB-GRAIL | SUB-ASPH
CURB150 | GR140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | Install Guardrail - Hillsborough Ramp A - Ph1-S2 | 0 | CONCRETE | SUB-GRAIL
CAP120 | CAP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Concrete Cap - Hillsborough Ramp D - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp A - Ph1-S2 | 0 | CONCRETE | CONCRETE
CAP130 | PAV400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Concrete Cap - Hillsborough Ramp A - Ph1-S2 | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CURB150 | CAP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp A - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW930A | CAP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp A - Ph1-S2 | 0 | BARRIER | CONCRETE
CURB140 | PAV390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Curb & Gutter Type F - Hillsborough Ramp D - Ph1-S2 | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CURB140 | CURB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Curb & Gutter Type F - Hillsborough Ramp D - Ph1-S2 | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | 0 | CONCRETE | CONCRETE
UDR280 | CURB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | 0 | UNDR | CONCRETE
CURB150 | PAV400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
BW930A | CURB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | Install Curb & Gutter Type F (?) - Hillsborough Ramp A - Ph1-S2 | 0 | BARRIER | CONCRETE
STAB400 | BW930A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | 0 | EW-CEM | BARRIER
CC110 | CC120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Crash Cushion - Hillsborough Ramp B - Ph1-S2 | Install Crash Cushion - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-GRAIL | SUB-GRAIL
CC120 | PNT1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Crash Cushion - Hillsborough Ramp D - Ph1-S2 | Paint - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-GRAIL | SUB-ST-PNT
PAV390 | CC120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | Install Crash Cushion - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-ASPH | SUB-GRAIL
GC100 | PAV390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
GC100 | PNT1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | Paint - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | SUB-ST-PNT
CAP120 | GC100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Concrete Cap - Hillsborough Ramp D - Ph1-S2 | Reset Granite Curb - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW840B | CAP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp D - Ph1-S2 | 0 | BARRIER | CONCRETE
CAP120 | PAV390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Concrete Cap - Hillsborough Ramp D - Ph1-S2 | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CURB140 | CAP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Curb & Gutter Type F - Hillsborough Ramp D - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp D - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW840B | CURB140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | Install Curb & Gutter Type F - Hillsborough Ramp D - Ph1-S2 | 0 | BARRIER | CONCRETE
UDR260 | CURB140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Edgedrain - Hillsborough Ramp D - Ph1-S2 | Install Curb & Gutter Type F - Hillsborough Ramp D - Ph1-S2 | 0 | UNDR | CONCRETE
STAB370 | BW840B | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Stabilization - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | 0 | EW-CEM | BARRIER
TBW100 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Set Temp Concrete Barrier Wall - Type K - NB: 177+89.06-181+78.62 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | BARRIER | SUB-ST-PNT
CLK200 | TBW100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | Set Temp Concrete Barrier Wall - Type K - NB: 177+89.06-181+78.62 - Ph1-S1 | 0 | CP-SAW | BARRIER
SGN600 | GR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Install Guardrail - NB: 159+48.98-163+10.72 - Ph1-S1 | 0 | SUB-SIGN | SUB-GRAIL
GR130 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Install Guardrail - NB: 159+48.98-163+10.72 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-GRAIL | SUB-ST-PNT
GRD200 | GR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Install Guardrail - NB: 159+48.98-163+10.72 - Ph1-S1 | 0 | SUB-DGRIND | SUB-GRAIL
BASE410 | GR120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | Install Guardrail - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-ABC | SUB-GRAIL
GR120 | PNT1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Install Guardrail - Hillsborough Ramp C2 - Ph1-S2 | Paint - Hillsborough Ramp C2 - Ph1-S2 | 0 | SUB-GRAIL | SUB-ST-PNT
SG100 | GR120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | Install Guardrail - Hillsborough Ramp C2 - Ph1-S2 | 0 |  | SUB-GRAIL
BW360 | BW680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | 0
SG100 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 |  | EW-CEM
SG100 | BW680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | 0
CC110 | PNT1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Crash Cushion - Hillsborough Ramp B - Ph1-S2 | Paint - Hillsborough Ramp B - Ph1-S2 | 0 | SUB-GRAIL | SUB-ST-PNT
PAV290 | CC110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | Install Crash Cushion - Hillsborough Ramp B - Ph1-S2 | 0 | SUB-ASPH | SUB-GRAIL
CAP110 | PAV290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Concrete Cap - Hillsborough Ramp B - Ph1-S2 | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CURB130 | CAP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Curb & Gutter Type F - Hillsborough Ramp B - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp B - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW360B | CAP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | Install Concrete Cap - Hillsborough Ramp B - Ph1-S2 | 0 | BARRIER | CONCRETE
CURB130 | PAV290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Curb & Gutter Type F - Hillsborough Ramp B - Ph1-S2 | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
UDR120 | CURB130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Edgedrain - Hillsborough Ramp B - Ph1-S2 | Install Curb & Gutter Type F - Hillsborough Ramp B - Ph1-S2 | 0 | UNDR | CONCRETE
BW360B | CURB130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | Install Curb & Gutter Type F - Hillsborough Ramp B - Ph1-S2 | 0 | BARRIER | CONCRETE
STAB160 | BW360B | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Stabilization - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | 0 | EW-CEM | BARRIER
CAP100 | PAV270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Concrete Cap - MLK Ramp C - Ph1-S2 | Asphalt Paving - MLK Ramp C - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
CURB120 | CAP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | Install Concrete Cap - MLK Ramp C - Ph1-S2 | 0 | CONCRETE | CONCRETE
BW220B | CAP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall (NB: 364+63.60 to 110+00.83) - MLK Ramp B - Ph1-S2 | Install Concrete Cap - MLK Ramp C - Ph1-S2 | 0 | BARRIER | CONCRETE
BW220B | PAV270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall (NB: 364+63.60 to 110+00.83) - MLK Ramp B - Ph1-S2 | Asphalt Paving - MLK Ramp C - Ph1-S2 | 0 | BARRIER | SUB-ASPH
BW220B | CURB120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall (NB: 364+63.60 to 110+00.83) - MLK Ramp B - Ph1-S2 | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | 0 | BARRIER | CONCRETE
UDR110 | BW220B | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Edgedrain - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall (NB: 364+63.60 to 110+00.83) - MLK Ramp B - Ph1-S2 | 0 | UNDR | BARRIER
STAB150 | BW220B | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall (NB: 364+63.60 to 110+00.83) - MLK Ramp B - Ph1-S2 | 0 | EW-CEM | BARRIER
BW170B | CURB110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall (NB: 96+36.16 to C&G Type F) - MLK Ramp B - Ph1-S2 | Install Curb & Gutter Type F - MLK Ramp B - Ph1-S2 | 0 | BARRIER | CONCRETE
BW170B | PAV250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall (NB: 96+36.16 to C&G Type F) - MLK Ramp B - Ph1-S2 | Asphalt Paving - MLK Ramp B - Ph1-S2 | 0 | BARRIER | SUB-ASPH
STAB130 | BW170B | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Stabilization - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall (NB: 96+36.16 to C&G Type F) - MLK Ramp B - Ph1-S2 | 0 | EW-CEM | BARRIER
CURB110 | BASE130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Install Curb & Gutter Type F - MLK Ramp B - Ph1-S2 | Base Course - MLK Ramp B - Ph1-S2 | 0 | CONCRETE | EW-ABC
UDR100 | CURB110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Install Edgedrain - MLK Ramp B - Ph1-S2 | Install Curb & Gutter Type F - MLK Ramp B - Ph1-S2 | 0 | UNDR | CONCRETE
BASE150 | GR110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Base Course - MLK Ramp C - Ph1-S2 | Install Guardrail - MLK Ramp C - Ph1-S2 | 0 | EW-ABC | SUB-GRAIL
CURB120 | BASE150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | Base Course - MLK Ramp C - Ph1-S2 | 0 | CONCRETE | EW-ABC
GR110 | PAV270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Guardrail - MLK Ramp C - Ph1-S2 | Asphalt Paving - MLK Ramp C - Ph1-S2 | 0 | SUB-GRAIL | SUB-ASPH
GR110 | PNT1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Guardrail - MLK Ramp C - Ph1-S2 | Paint - MLK Ramp C - Ph1-S2 | 0 | SUB-GRAIL | SUB-ST-PNT
CURB120 | GR110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | Install Guardrail - MLK Ramp C - Ph1-S2 | 0 | CONCRETE | SUB-GRAIL
CURB120 | PAV270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | Asphalt Paving - MLK Ramp C - Ph1-S2 | 0 | CONCRETE | SUB-ASPH
UDR110 | CURB120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Edgedrain - MLK Ramp C - Ph1-S2 | Install Curb & Gutter Type E & F - MLK Ramp C - Ph1-S2 | 0 | UNDR | CONCRETE
CC100 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Install Crash Cushions - NB: 748+30-757+10 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-GRAIL | SUB-ST-PNT
CLK120 | CC100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | Install Crash Cushions - NB: 748+30-757+10 - Ph1-S1 | 0 | CP-SAW | SUB-GRAIL
GR100 | PM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Install Guardrail - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Pavement Markings - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | SUB-GRAIL | SUB-STRIP
CURB100 | GR100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Install Curb & Gutter Type E & F - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Install Guardrail - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | CONCRETE | SUB-GRAIL
CURB100 | PAV130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Install Curb & Gutter Type E & F - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Asphalt Paving - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
STAB100 | CURB100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Stabilization - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Install Curb & Gutter Type E & F - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | EW-STAB | CONCRETE
LAG730 | R850 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Install Lagging & Anchors for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - East Half - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
PILE730 | LAG730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Install H-Pile for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | Install Lagging & Anchors for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
DEMO1130 | LAG730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | Install Lagging & Anchors for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
DEMO1130 | PILE730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | Install H-Pile for Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
LAG720 | R790 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Install Lagging & Anchors for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - East Half - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
PILE720 | LAG720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Install H-Pile for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | Install Lagging & Anchors for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
RET10 | LAG720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Install Lagging & Anchors for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 0 |  | ST-CIP
DEMO1030 | LAG720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | Install Lagging & Anchors for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
PILE710 | PILE720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Install H-Pile for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Install H-Pile for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
RET10 | PILE720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Install H-Pile for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 0 |  | ST-CIP
DEMO1030 | PILE720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | Install H-Pile for Anchored Retaining Wall W-9A @ MLK Blvd. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
LAG710 | R720 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Install Lagging & Anchors for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
PILE710 | LAG710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Install H-Pile for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Install Lagging & Anchors for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
RET10 | LAG710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Install Lagging & Anchors for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
DEMO270 | LAG710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Install Lagging & Anchors for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
PILE700 | PILE710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Install H-Pile for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | Install H-Pile for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
RET10 | PILE710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Install H-Pile for Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
LAG700 | R655 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Install Lagging & Anchors for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
PILE700 | LAG700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Install H-Pile for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | Install Lagging & Anchors for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
RET10 | LAG700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Install Lagging & Anchors for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
RET10 | PILE700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Install H-Pile for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
DEMO180 | LAG700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | Install Lagging & Anchors for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
DEMO180 | PILE700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | Install H-Pile for Retaining Wall W-8A @ MLK Blvd. - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
BP180 | BP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP170 | BP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP160 | BP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP150 | BP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP140 | BP150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP120 | BP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP110 | BP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP100 | BP110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
B2480 | EC180 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit at Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 2 |  | SUB-UT-ELEC
EC180 | NW760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
B2470 | EC180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit at Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-UT-ELEC
B2240 | EC130 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit at Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 2
EC130 | NW480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Lighting Conduit at Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-SOUND
B2230 | EC130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Install Lighting Conduit at Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 0
BW540 | EC100 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Install Lighting Conduit at Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | 2 |  | SUB-UT-ELEC
EC100 | NW370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Lighting Conduit at Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-UT-ELEC | ST-SOUND
B1220 | EC100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Approach Slabs Cure 100201 - NB: over Floribraska - Ph1-S1 | Install Lighting Conduit at Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-UT-ELEC
BP190 | BBM190 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP190 | SUPR700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | Form Deck 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP190 | SIP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | Install SIP Deck Pans100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BP190 | SUPR640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | Overhang 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUBS1340 | BP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1210 | BP190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1200 | BP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1370 | BP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | Install Bearing Pads 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP180 | BBM180 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP180 | SUPR660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP180 | SIP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | Install SIP Deck Pans100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BP180 | SUPR620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | Overhang 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUBS1310 | BP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1180 | BP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1160 | BP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1350 | BP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP170 | BBM170 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP170 | SUPR610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP170 | SIP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install SIP Deck Pans100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BP170 | SUPR590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Overhang 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUBS1270 | BP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1100 | BP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1060 | BP170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1300 | BP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP160 | BBM160 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP160 | SUPR540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP160 | SIP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install SIP Deck Pans100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BP160 | SUPR520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Overhang 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUBS1240 | BP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1040 | BP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS990 | BP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS960 | BP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1250 | BP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP150 | BBM150 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP150 | SUPR460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP150 | SIP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install SIP Deck Pans100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUBS920 | BP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS870 | BP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS830 | BP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS780 | BP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS750 | BP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP150 | SUPR420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install Bearing Pads 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Overhang 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP140 | BBM140 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP140 | SUPR400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP140 | SIP140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install SIP Deck Pans100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUBS650 | BP140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS840 | BP140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS660 | BP140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS690 | BP140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP140 | SUPR380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install Bearing Pads 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Overhang 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP130 | BBM130 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP130 | SUPR290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP130 | SIP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | Install SIP Deck Pans100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUBS530 | BP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS590 | BP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS580 | BP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS500 | BP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP130 | SUPR260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install Bearing Pads 100206 - NB: over Chelsea St. - Ph1-S1 | Overhang 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP120 | BBM120 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP120 | SUPR250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP120 | SIP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | Install SIP Deck Pans100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUBS440 | BP120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS490 | BP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS480 | BP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS320 | BP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP120 | SUPR190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install Bearing Pads 100204 - NB: over MLK Blvd - Ph1-S1 | Overhang 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP110 | BBM110 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
BP110 | SUPR180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | Form Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP110 | SIP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | Install SIP Deck Pans100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUBS370 | BP110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS230 | BP110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS360 | BP110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS350 | BP110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP110 | SUPR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install Bearing Pads 100207 - NB: over East Lake - Ph1-S1 | Overhang 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUBS170 | BP100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS140 | BP100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS260 | BP100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS250 | BP100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
BP100 | SUPR110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP100 | SUPR100 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | Overhang 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BP100 | BBM100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install Bearing Pads 100201 - NB: over Floribraska - Ph1-S1 | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-BEAM
REINF180 | SUPR740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100206 - SB: over Chelsea St. - Ph1-S1 | Pour Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF170 | SUPR690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Pour Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF160 | SUPR570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Pour Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF150 | SUPR500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Pour Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF140 | SUPR450 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Pour Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF130 | SUPR350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100206 - NB: over Chelsea St. - Ph1-S1 | Pour Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF120 | SUPR320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100204 - NB: over MLK Blvd - Ph1-S1 | Pour Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF110 | SUPR240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Rebar 100207 - NB: over East Lake - Ph1-S1 | Pour Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF190 | SUPR760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100204 - SB: over MLK - Ph1-S1 | Pour Deck 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
BBM190 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR700 | REINF190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form Deck 100204 - SB: over MLK - Ph1-S1 | Rebar 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP190 | SUPR700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install SIP Deck Pans100204 - SB: over MLK - Ph1-S1 | Form Deck 100204 - SB: over MLK - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
BBM180 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR660 | REINF180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | Rebar 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP180 | SUPR660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install SIP Deck Pans100206 - SB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
SUPR610 | REINF170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Rebar 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP170 | SUPR610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install SIP Deck Pans100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
SIP160 | SUPR540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install SIP Deck Pans100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
SUPR540 | REINF160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Rebar 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SUPR520 | SUPR540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Overhang 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM160 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR420 | SUPR460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Overhang 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR460 | REINF150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Rebar 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP150 | SUPR460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Install SIP Deck Pans100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
BBM150 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR400 | REINF140 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Rebar 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP140 | SUPR400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Install SIP Deck Pans100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
BBM140 | SUPR400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM140 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR290 | REINF130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Rebar 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP130 | SUPR290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Install SIP Deck Pans100206 - NB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
BBM130 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR250 | REINF120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Rebar 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP120 | SUPR250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Install SIP Deck Pans100204 - NB: over MLK Blvd - Ph1-S1 | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
BBM120 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUPR180 | REINF110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form Deck 100207 - NB: over East Lake - Ph1-S1 | Rebar 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP110 | SUPR180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Install SIP Deck Pans100207 - NB: over East Lake - Ph1-S1 | Form Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
BBM110 | SUPR180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | Form Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM110 | STAB190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
BBM100 | SUPR110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
REINF100 | SUPR120 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Rebar 100201 - NB: over Floribraska - Ph1-S1 | Set Deck Screed 100201 - NB: over Floribraska - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF100 | SUPR170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Rebar 100201 - NB: over Floribraska - Ph1-S1 | Pour Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-ST-REBAR | ST-BRIDGE-SUP
SUPR110 | SUPR120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | Set Deck Screed 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR110 | REINF100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | Rebar 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP100 | SUPR110 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install SIP Deck Pans 100201 - NB: over Floribraska - Ph1-S1 | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-DECK | ST-BRIDGE-SUP
SUPR100 | REINF100 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Overhang 100201 - NB: over Floribraska - Ph1-S1 | Rebar 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUP | SUB-ST-REBAR
SIP100 | REINF100 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Install SIP Deck Pans 100201 - NB: over Floribraska - Ph1-S1 | Rebar 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-DECK | SUB-ST-REBAR
MS-CE | WBO-CTWD-10 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.3.1.1 City of Tampa Wastewater Department Project ID: 431821-02-52-01 (Prior to starting work) | Contract Execution | (Act #1) Ex. 12" Concrete Wastewater (815+14.86-174' RT to 815+39.86-173.71' RT) - COT Identified Line to Remain | 0
WBO-TEC-27 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #8) Overhead 13.2KV Poles & Conductors (820+50-187L to 820+50-20R) - Remove OH conductors & poles | End of Phase 1, Stage 1 | 0
MS-P1S1S | WBO-TEC-20 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | Start of Phase 1, Stage 1 | (Act #1) 13.2 KV Underground (8100+73+208L to 810+73-230R) - Install UG conduit & conductor | 0
WBO-TEC-26 | WBO-TEC-27 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #7) Overhead 13.2KV Poles & Conductors (810+73-178L to 810+73-198R) - Remove OH conductors & poles | (Act #8) Overhead 13.2KV Poles & Conductors (820+50-187L to 820+50-20R) - Remove OH conductors & poles | 0
WBO-TEC-25 | WBO-TEC-26 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #6) OH to UG Pole & 13.2KV Conductor (810+50-230R) - Install terminal pole & conductor | (Act #7) Overhead 13.2KV Poles & Conductors (810+73-178L to 810+73-198R) - Remove OH conductors & poles | 0
WBO-TEC-24 | WBO-TEC-25 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #5) OH to UG Pole & 13.2KV Conductor (810+73-230R) - Install terminal pole & conductor | (Act #6) OH to UG Pole & 13.2KV Conductor (810+50-230R) - Install terminal pole & conductor | 0
WBO-TEC-23 | WBO-TEC-24 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #4) OH to UG Pole & 13.2KV Conductor (820+50-217L) - Install terminal pole & conductor | (Act #5) OH to UG Pole & 13.2KV Conductor (810+73-230R) - Install terminal pole & conductor | 0
WBO-TEC-22 | WBO-TEC-23 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #3) OH to UG Pole & 13.2KV Conductor (810+73-208L) - Install terminal pole & conductor | (Act #4) OH to UG Pole & 13.2KV Conductor (820+50-217L) - Install terminal pole & conductor | 0
WBO-TEC-21 | WBO-TEC-22 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #2) 13.2 KV Underground (820+50-217L to 820+50-230R) - Install UG conduit & conductor | (Act #3) OH to UG Pole & 13.2KV Conductor (810+73-208L) - Install terminal pole & conductor | 0
WBO-TEC-20 | WBO-TEC-21 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.2 Tampa Electric Co. Project ID: 431821-2-52-01 (Coordination of work w/TEC pending) | (Act #1) 13.2 KV Underground (8100+73+208L to 810+73-230R) - Install UG conduit & conductor | (Act #2) 13.2 KV Underground (820+50-217L to 820+50-230R) - Install UG conduit & conductor | 0
WBO-TEC-17 | SUBS1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | (Act #7) Steel Transmission Pole/Guys/Anchors (37+9-53R) - Removal | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
WBO-TEC-17 | DS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | (Act #7) Steel Transmission Pole/Guys/Anchors (37+9-53R) - Removal | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
WBO-TEC-16 | WBO-TEC-17 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #6) Stub Pole/Span Guys/Anchors (37+07-40L) - Removal | (Act #7) Steel Transmission Pole/Guys/Anchors (37+9-53R) - Removal | 0
WBO-TEC-15 | WBO-TEC-16 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #5) Overhead 230KV Conductor (33+85-49R to 37+15+64R) - Remove 230KV Conductor | (Act #6) Stub Pole/Span Guys/Anchors (37+07-40L) - Removal | 0
WBO-TEC-14 | WBO-TEC-15 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #4) Overhead 230KV Conductor (33+85-49R to 37+15-64R) - Install Overhead 230KV Conductor | (Act #5) Overhead 230KV Conductor (33+85-49R to 37+15+64R) - Remove 230KV Conductor | 0
WBO-TEC-13 | WBO-TEC-14 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #3) Overhead 230KV Conductor (37+15-64R to 36+51-R310) - Install Overhead 230KV Conductor | (Act #4) Overhead 230KV Conductor (33+85-49R to 37+15-64R) - Install Overhead 230KV Conductor | 0
WBO-TEC-12 | WBO-TEC-13 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #2) Overhead 230KV Pole (37+15-R64) - Install Transmission Pole | (Act #3) Overhead 230KV Conductor (37+15-64R to 36+51-R310) - Install Overhead 230KV Conductor | 0
WBO-TEC-11 | WBO-TEC-12 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | (Act #1) Overhead 230KV Pole Foundation (37+15-R64) - Pouring of Foundation & Cure Time | (Act #2) Overhead 230KV Pole (37+15-R64) - Install Transmission Pole | 0
WBO-TEC-10 | WBO-TEC-11 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | Tampa Electric Company - Remaining Pole Procurement - Started 14-Jan-21 | (Act #1) Overhead 230KV Pole Foundation (37+15-R64) - Pouring of Foundation & Cure Time | 0 | SUB-UT-ELEC
WBO-TECO-02 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #2) 4" Coated Steel GM & 8" Coated Steel Casing (807+25 - 127' LT) - To be retired and removed where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-01 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #1) 4" Coated Steel GM & 8" Coated Steel Casing (807+21 - 136' RT) - To be retired and removed where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-05 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #5) Retired 4" Coated Steel GM (827+05 102' RT) - To remove where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-04 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #4) Unknown 1" Facility (826+93 - 114' LT) - To investigate & remove where accessible if determined to be Teco | End of Phase 1, Stage 1 | 0
WBO-TECO-03 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #3) Retired 4" Coated Steel GM (826+93 - 114' LT) - To remove where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-12 | WBO-TECO-15 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #3) Retired 2" Coated Steel GM (777+54 - 117' LT) - Remove where accessible | TECO Project ID: 443770-1-52-01 Work Complete | 0
WBO-TECO-14 | WBO-TECO-15 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #5) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+15 - 119' LT) - Remove where accessible | TECO Project ID: 443770-1-52-01 Work Complete | 0
WBO-TECO-13 | WBO-TECO-15 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #4) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+13 - 102' RT) - Remove where accessible | TECO Project ID: 443770-1-52-01 Work Complete | 0
WBO-TECO-11 | WBO-TECO-15 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #2) Retired 2" Coated Steel GM x 6" Coated Steel Casing (776+57 - 94' RT) - Remove where accessible | TECO Project ID: 443770-1-52-01 Work Complete | 0
WBO-TECO-10 | WBO-TECO-15 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | (Act #1) 6" Polyethylene GM x 10" Steel Casing & 2" Steel Casing Vent (728+20 - 124.0' RT) - Offset 18" below 30" storm | TECO Project ID: 443770-1-52-01 Work Complete | 0
WBO-TECO-15 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | TECO Project ID: 443770-1-52-01 Work Complete | End of Phase 1, Stage 1 | 0
WBO-TECO-14 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #5) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+15 - 119' LT) - Remove where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-13 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #4) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+13 - 102' RT) - Remove where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-12 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #3) Retired 2" Coated Steel GM (777+54 - 117' LT) - Remove where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-11 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #2) Retired 2" Coated Steel GM x 6" Coated Steel Casing (776+57 - 94' RT) - Remove where accessible | End of Phase 1, Stage 1 | 0
WBO-TECO-10 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | (Act #1) 6" Polyethylene GM x 10" Steel Casing & 2" Steel Casing Vent (728+20 - 124.0' RT) - Offset 18" below 30" storm | End of Phase 1, Stage 1 | 0
EGC230 | WBO-TECO-14 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | (Act #5) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+15 - 119' LT) - Remove where accessible | 0 | EW-SML
EGC180 | WBO-TECO-13 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | (Act #4) Retired 2" Coated Steel GM x 6" Coated Steel Casing (790+13 - 102' RT) - Remove where accessible | 0 | EW-SML
DRG1260A | WBO-TECO-12 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | (Act #3) Retired 2" Coated Steel GM (777+54 - 117' LT) - Remove where accessible | 0 | DRAIN
EGC160 | WBO-TECO-11 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | (Act #2) Retired 2" Coated Steel GM x 6" Coated Steel Casing (776+57 - 94' RT) - Remove where accessible | 0 | EW-SML
DRG160 | WBO-TECO-10 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.3.3.2 TECO Project ID: 443770-1-52-01 (Coordination of work with TECO pending) | Drainage: S-13 to S-16 (30") - NB: 726-730 - Ph1-S1 | (Act #1) 6" Polyethylene GM x 10" Steel Casing & 2" Steel Casing Vent (728+20 - 124.0' RT) - Offset 18" below 30" storm | 0 | DRAIN
WBO-TECO-06 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | TECO Project ID: 431821-2-52-01 Work Complete | End of Phase 1, Stage 1 | 0
WBO-TECO-02 | WBO-TECO-06 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #2) 4" Coated Steel GM & 8" Coated Steel Casing (807+25 - 127' LT) - To be retired and removed where accessible | TECO Project ID: 431821-2-52-01 Work Complete | 0
WBO-TECO-01 | WBO-TECO-06 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #1) 4" Coated Steel GM & 8" Coated Steel Casing (807+21 - 136' RT) - To be retired and removed where accessible | TECO Project ID: 431821-2-52-01 Work Complete | 0
WBO-TECO-05 | WBO-TECO-06 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #5) Retired 4" Coated Steel GM (827+05 102' RT) - To remove where accessible | TECO Project ID: 431821-2-52-01 Work Complete | 0
WBO-TECO-04 | WBO-TECO-06 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #4) Unknown 1" Facility (826+93 - 114' LT) - To investigate & remove where accessible if determined to be Teco | TECO Project ID: 431821-2-52-01 Work Complete | 0
WBO-TECO-03 | WBO-TECO-06 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | (Act #3) Retired 4" Coated Steel GM (826+93 - 114' LT) - To remove where accessible | TECO Project ID: 431821-2-52-01 Work Complete | 0
DRGS270 | WBO-TECO-05 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | (Act #5) Retired 4" Coated Steel GM (827+05 102' RT) - To remove where accessible | 0 | DRAIN
DRGS270 | WBO-TECO-04 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | (Act #4) Unknown 1" Facility (826+93 - 114' LT) - To investigate & remove where accessible if determined to be Teco | 0 | DRAIN
DRGS270 | WBO-TECO-03 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | (Act #3) Retired 4" Coated Steel GM (826+93 - 114' LT) - To remove where accessible | 0 | DRAIN
DRG1360 | WBO-TECO-02 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | (Act #2) 4" Coated Steel GM & 8" Coated Steel Casing (807+25 - 127' LT) - To be retired and removed where accessible | 0 | DRAIN
DRG610 | WBO-TECO-01 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.3.3.1 TECO Project ID: 431821-2-52-01 (Coordination of work with TECO pending) | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | (Act #1) 4" Coated Steel GM & 8" Coated Steel Casing (807+21 - 136' RT) - To be retired and removed where accessible | 0 | DRAIN
LTG10 | SGN10 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | Prepare Shop Drawings / Submittals: Lighting | Prepare Shop Drawings / Submittals: Signage | 0
SGN500 | SGN510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Signs - NB: 709+50-735+00 - Ph1-S1 | Install Signs - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
DEMO1570 | BW630 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Demo End of Existing End Bent 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | DM-BRIDGE | BARRIER
DEMO1590 | BW770 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | DM-BRIDGE | BARRIER
DEMO1610 | BW850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Demo End of Existing End Bent 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | DM-BRIDGE | BARRIER
SUBS1080 | SUBS1090 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1070 | SUBS1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1060 | SUBS1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1000 | SUBS1280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS980 | SUBS1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS910 | SUBS1230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS760 | SUBS700 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS720 | SUBS850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
GRD190 | PAV260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | 0 | SUB-DGRIND | SUB-ASPH
BASE120 | BASE230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Base Course - MLK Ramp C - Ph1-S1 | Black Base - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | EW-ABC
CP200 | PAV210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | Asphalt Paving - MLK Ramp C - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
LTG1000 | TCC130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | Install MOT Construction Barriers I-275 SB - IPh1 | 0 | SUB-UT-ELEC | TRAFFIC
DEMO1550 | SUBS900 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1550 | SUBS810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1370 | SUBS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1370 | SUBS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1400 | SUBS340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1420 | SUBS460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1520 | SUBS730 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1520 | SUBS680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1520 | SUBS670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
GRD180 | GRD450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
NW630 | B2720 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND
DEMO1460 | SUBS560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
GRD440 | GRD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
DEMO1420 | SUBS450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
CLK430 | EL370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | CP-SAW | SUB-UT-ELEC
EL370 | SGN540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | Install Signs - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-SIGN
GRD150 | CLK430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
GRD140 | CLK430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
GRD430 | GRD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
DEMO1400 | SUBS330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
BW540 | CP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | 0 |  | CONCRETE
BW540 | GRD100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-DGRIND
B1220 | CP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Approach Slabs Cure 100201 - NB: over Floribraska - Ph1-S1 | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | 0 |  | CONCRETE
BBM100 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | ST-BEAM | EW-CEM
SUBS1090 | SUBS1110 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
CLK510 | CLK290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | 0 | CP-SAW | CP-SAW
DEMO1950 | DEMO1880 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 44' of 18" Pipe & 2 Structures - NB & SB Median: 807+00-808+00 - Ph2 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DEMO | DEMO
GRD320 | EL550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD310 | EL540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD300 | EL530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD290 | EL520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD280 | EL510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD270 | EL500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD260 | EL490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD250 | EL480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD240 | EL470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD230 | EL460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD220 | EL450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD210 | EL440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD200 | EL430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD190 | EL420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD180 | EL410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD170 | EL400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD160 | EL390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD120 | EL350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD100 | EL330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD110 | EL340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
PM110 | CLK130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Pavement Markings - MLK Ramp B - Ph1-S1 | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-STRIP | CP-SAW
BW140 | EGC150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 0 |  | EW-SML
GRD150 | EL380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
GRD140 | EL370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ELEC
STAB220 | DEMO570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Stabilization - NB: 767+00-773+42 - Ph1-S1 | Demo / Grade - MLK Ramp C - Ph1-S1 | 0 | EW-CEM | DEMO
BW240 | DRG440 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Drainage: S-106 to S-110 (18") - NB: 779-781 - Ph1-S1 | 0 |  | DRAIN
BW260 | DRG450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Drainage: S-114 to S-115 (18") - NB: 781-782 - Ph1-S1 | 0 |  | DRAIN
DEMO670 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
BASE350 | STAB140 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Black Base - NB: 800+00-813+16 - Ph1-S1 | Stabilization - Hillsborough Ramp B - Ph1-S1 | 0 | EW-ABC | EW-STAB
BW340 | DRG670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | 0 |  | DRAIN
DSS360 | DRG1450 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHB-101) - SB: 818+78 - Ph1-S1 | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | 0 | SUB-ST-DRSFT | DRAIN
BASE470 | STAB310 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Black Base - SB: 815+20-839+61 - Ph1-S1 | Stabilization - Hillsborough Ramp D - Ph1-S1 | 0 | EW-ABC | EW-STAB
DSS300 | DRG1270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-104) - SB: 792+45 - Ph1-S1 | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | 0 | SUB-ST-DRSFT | DRAIN
DSS340 | DRG1340 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-105) - SB: 808+47 - Ph1-S1 | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | 0 | SUB-ST-DRSFT | DRAIN
DSS290 | DRG1200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | 0 | SUB-ST-DRSFT | DRAIN
NW370 | GRD410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
NW390 | GRD420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
BW140 | DRG380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Drainage: CD-3 to S-78 (48") - NB: 767-768 - Ph1-S1 | 0 |  | DRAIN
NW430 | GRD430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - NB: over MLK Blvd - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
NW480 | GRD440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
BW310 | DRG590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | 0 |  | DRAIN
NW510 | GRD450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
NW460 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW610 | GRD460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
NW700 | GRD470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
STAB330 | DEMO1650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Stabilization - SB: 815+20-839+61 - Ph1-S1 | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | 0 | EW-CEM | DEMO
NW730 | GRD480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
STAB150 | DEMO1660 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Stabilization - MLK Ramp C - Ph1-S2 | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 0 | EW-CEM | DEMO
STAB360 | DEMO1660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Stabilization - SB: 788+09-800+00 - Ph1-S1 | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 0 | EW-CEM | DEMO
STAB350 | BASE430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Stabilization - Hillsborough Ramp A - Ph1-S1 | Base Course - Hillsborough Ramp A - Ph1-S1 | 0 | EW-STAB | EW-ABC
CP420 | PAV380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
NW760 | GRD490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
BASE680 | BASE500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Shoulder Base - SB: 761+67-767+00 - Ph1-S1 | Base Course - MLK Ramp D - Ph1-S1 | 0 | EW-ABC | EW-ABC
MS-NTP | ITS10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | Start Construction | Prepare Shop Drawings / Submittals: ITS | 0
MS-NTP | SGN10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | Start Construction | Prepare Shop Drawings / Submittals: Signage | 0
MS-NTP | LTG10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | Start Construction | Prepare Shop Drawings / Submittals: Lighting | 0
MS-NTP | SPS10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | Start Construction | Prepare Shop Drawings / Submittals: Superstructure | 0
MS-NTP | SUB10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | Start Construction | Prepare Shop Drawings / Submittals: Substructure | 0
CB150 | DS30 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Core Bore @ 48" Drilled Shafts - Hillsborough | Procurement: Structural 48" Drilled Shafts | 40
DS190 | EL270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS190 | EL260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS180 | EL240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS170 | EL230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS170 | EL220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS160 | EL210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS150 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS140 | EL190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS140 | EL180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS120 | EL150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS110 | EL130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
DS110 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-UT-ELEC
NW780 | GRD500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
BASE650 | BASE680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Shoulder Base - SB: 767+00-773+42 - Ph1-S1 | Shoulder Base - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
NW790 | GRD510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - SB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-SOUND | SUB-DGRIND
SUPR770 | STAB450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Form / SIP / Reinforce / Pour Replacement Deck 100207 - SB: over East Lake - Ph1-S1 | Stabilization - SB: 757+10-759+97 - Ph1-S1 | 0 | ST-BRIDGE-SUP | EW-CEM
WL470 | EGC320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | 0 | ST-PILE | EW-SML
WL470 | DRG2500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | 0 | ST-PILE | DRAIN
BW1140 | MSE1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | Install Coping - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | BARRIER | SUB-ST-MSE
PILE470 | MSE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | H Pile Install - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
WL470 | MSE750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
DEMO1320 | EGC300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Roadway - SB: 709+50-721+43 - Ph1-S1 | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | 0 | DEMO | EW-SML
BASE690 | BASE730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Shoulder Base - SB: 757+10-759+97 - Ph1-S1 | Shoulder Base - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | EW-ABC
NW240 | STAB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW130 | EGC130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | 0 |  | EW-SML
R3940 | PAV420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Grassing - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | Asphalt Paving - MLK Ramp A - Ph1-S1 | 0 | SUB-LANDSC | SUB-ASPH
BASE150 | NW530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Base Course - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-ABC | ST-SOUND
NW130 | EGC590 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | 0 | ST-SOUND | EW-SML
BW220 | EGC590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | 0 |  | EW-SML
NW180 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | ST-SOUND | EW-CEM
BASE410 | STAB300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-ABC | EW-CEM
BASE150 | STAB160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Base Course - MLK Ramp C - Ph1-S2 | Stabilization - Hillsborough Ramp B - Ph1-S2 | 0 | EW-ABC | EW-CEM
BASE130 | STAB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Base Course - MLK Ramp B - Ph1-S2 | Stabilization - MLK Ramp C - Ph1-S2 | 0 | EW-ABC | EW-CEM
NW750 | PAV250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | Asphalt Paving - MLK Ramp B - Ph1-S2 | 0 | ST-SOUND | SUB-ASPH
STAB370 | EGC360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp D - Ph1-S2 | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | 0 | EW-CEM | EW-SML
CLK460 | CLK140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK320 | EL550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | CP-SAW | SUB-UT-ELEC
EL540 | CLK310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL530 | CLK300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL520 | CLK290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL510 | CLK280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL500 | CLK270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL490 | CLK260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK500 | CLK260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL480 | CLK250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL470 | CLK240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK490 | CLK240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL460 | CLK230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL450 | CLK220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL440 | CLK210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK470 | CLK210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL430 | CLK200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK460 | CLK200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL420 | CLK190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL410 | CLK180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK450 | CLK180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL400 | CLK170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL390 | CLK160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK440 | CLK160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Caulk & Seal Joints 100206 - NB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK430 | CLK140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL380 | CLK150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL370 | CLK140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL350 | CLK120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL340 | CLK110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
EL330 | CLK100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK410 | CLK100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
EL360 | CLK130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | CP-SAW
CLK130 | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | Start of Phase 1, Stage 2 | 0 | CP-SAW
NW390 | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | Start of Phase 1, Stage 2 | 0 | ST-SOUND
EL350 | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | Start of Phase 1, Stage 2 | 0 | SUB-UT-ELEC
CLK120 | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | Start of Phase 1, Stage 2 | 0 | CP-SAW
PAV330 | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Start of Phase 1, Stage 2 | 0 | SUB-ASPH
BW1050 | BW1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | 0 | BARRIER | BARRIER
BW930 | BW1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | 0 | BARRIER | BARRIER
BW840 | BW930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | 0 | BARRIER | BARRIER
BW680 | BW840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | 0 |  | BARRIER
BW220 | BW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | 0
BW170 | BW220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | 0
BW1030 | BW1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp A - Ph1-S2 | 0 | BARRIER | BARRIER
BW910 | BW1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp D - Ph1-S2 | 0 | BARRIER | BARRIER
BW820 | BW910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp A - Ph1-S2 | 0 | BARRIER | BARRIER
BW660 | BW820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp D - Ph1-S2 | 0 |  | BARRIER
SG100 | BW660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp C1 - Ph1-S2 | 0
BW320 | SG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | 0
BW210 | BW320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp B - Ph1-S2 | 0
BW150 | BW210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp C - Ph1-S2 | 0
EGC390 | EGC380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Excavate / Grade - MLK Ramp A - Ph1-S2 | 0 | EW-SML | EW-SML
EGC370 | EGC380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Excavate / Grade - MLK Ramp D - Ph1-S2 | Excavate / Grade - MLK Ramp A - Ph1-S2 | 0 | EW-SML | EW-SML
EGC360 | EGC370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | Excavate / Grade - MLK Ramp D - Ph1-S2 | 0 | EW-SML | EW-SML
EGC350 | EGC360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | 0 | EW-SML | EW-SML
EGC330 | EGC350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | 0 | EW-SML | EW-SML
EGC340 | EGC330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-SML | EW-SML
EGC590 | EGC340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-SML | EW-SML
EGC550 | EGC590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Excavate / Grade - MLK Ramp C - Ph1-S2 | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | 0 | EW-SML | EW-SML
EGC530 | EGC550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Excavate / Grade - MLK Ramp B - Ph1-S2 | Excavate / Grade - MLK Ramp C - Ph1-S2 | 0 | EW-SML | EW-SML
PNT200 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint 100207 - SB: over East Lake - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT100 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint 100201 - NB: over Floribraska - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PAV440 | PAV450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Asphalt Paving - MLK Ramp D - Ph1-S2 | Asphalt Paving - MLK Ramp A - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV400 | PAV440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | Asphalt Paving - MLK Ramp D - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV390 | PAV400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV350 | PAV390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S2 | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV370 | PAV350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S2 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV290 | PAV370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV270 | PAV290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Asphalt Paving - MLK Ramp C - Ph1-S2 | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV250 | PAV270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Asphalt Paving - MLK Ramp B - Ph1-S2 | Asphalt Paving - MLK Ramp C - Ph1-S2 | 0 | SUB-ASPH | SUB-ASPH
PAV410 | PAV470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - MLK Ramp D - Ph1-S1 | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV420 | PAV410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - MLK Ramp A - Ph1-S1 | Asphalt Paving - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV380 | PAV460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV380 | PAV410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | Asphalt Paving - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV360 | PAV380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV340 | PAV360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV260 | PAV320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV210 | PAV260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Asphalt Paving - MLK Ramp C - Ph1-S1 | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV180 | PAV210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Asphalt Paving - MLK Ramp B - Ph1-S1 | Asphalt Paving - MLK Ramp C - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV330 | PAV180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - MLK Ramp B - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV240 | PAV160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV160 | PAV280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | Miscellaneous Asphalt Paving @ Floribraska - North Side - Ph1-S1-S2 | 0 | SUB-ASPH | SUB-ASPH
BASE580 | BASE500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Base Course - Floribraska Ramp NE - Ph1-S1 | Base Course - MLK Ramp D - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE310 | BASE480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Base Course - Hillsborough Ramp C2 - Ph1-S1 | Black Base - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE390 | BASE260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp D - Ph1-S1 | Base Course - Hillsborough Ramp C1 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE140 | BASE400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Base Course - Hillsborough Ramp B - Ph1-S1 | Black Base - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE120 | BASE240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Base Course - MLK Ramp C - Ph1-S1 | Black Base - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE110 | BASE220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Base Course - MLK Ramp B - Ph1-S1 | Black Base - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE390 | BASE480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Base Course - Hillsborough Ramp D - Ph1-S1 | Black Base - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE430 | BASE550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Base Course - Hillsborough Ramp A - Ph1-S1 | Black Base - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE540 | BASE700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Base Course - MLK Ramp A - Ph1-S1 | Black Base - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE720 | BASE630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Black Base - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Base Course - MLK Ramp D - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE490 | BASE720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Base Course - Hillsborough Ramp A - Ph1-S2 | Black Base - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE630 | BASE670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Base Course - MLK Ramp D - Ph1-S2 | Base Course - MLK Ramp A - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE490 | BASE630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Base Course - Hillsborough Ramp A - Ph1-S2 | Base Course - MLK Ramp D - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE450 | BASE490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Base Course - Hillsborough Ramp D - Ph1-S2 | Base Course - Hillsborough Ramp A - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE370 | BASE450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Base Course - Hillsborough Ramp C1 - Ph1-S2 | Base Course - Hillsborough Ramp D - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE410 | BASE370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | Base Course - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE160 | BASE410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp B - Ph1-S2 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE150 | BASE160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Base Course - MLK Ramp C - Ph1-S2 | Base Course - Hillsborough Ramp B - Ph1-S2 | 0 | EW-ABC | EW-ABC
BASE130 | BASE150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Base Course - MLK Ramp B - Ph1-S2 | Base Course - MLK Ramp C - Ph1-S2 | 0 | EW-ABC | EW-ABC
STAB160 | STAB400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp B - Ph1-S2 | Stabilization - Hillsborough Ramp A - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB150 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Stabilization - MLK Ramp C - Ph1-S2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB480 | STAB490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Stabilization - MLK Ramp D - Ph1-S2 | Stabilization - MLK Ramp A - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB400 | STAB480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Stabilization - Hillsborough Ramp A - Ph1-S2 | Stabilization - MLK Ramp D - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB370 | STAB400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp D - Ph1-S2 | Stabilization - Hillsborough Ramp A - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB320 | STAB300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB150 | STAB160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Stabilization - MLK Ramp C - Ph1-S2 | Stabilization - Hillsborough Ramp B - Ph1-S2 | 0 | EW-CEM | EW-CEM
STAB130 | STAB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - MLK Ramp B - Ph1-S2 | Stabilization - MLK Ramp C - Ph1-S2 | 0 | EW-CEM | EW-CEM
UDR400 | UDR340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Edgedrain - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Install Edgedrain - MLK Ramp D - Ph1-S2 | 0 | UNDR | UNDR
UDR280 | UDR400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | Install Edgedrain - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | UNDR | UNDR
UDR340 | UDR370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Install Edgedrain - MLK Ramp D - Ph1-S2 | Install Edgedrain - MLK Ramp A - Ph1-S2 | 0 | UNDR | UNDR
UDR280 | UDR340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | Install Edgedrain - MLK Ramp D - Ph1-S2 | 0 | UNDR | UNDR
UDR260 | UDR280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Edgedrain - Hillsborough Ramp D - Ph1-S2 | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | 0 | UNDR | UNDR
UDR210 | UDR260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Edgedrain - Hillsborough Ramp C1 - Ph1-S2 | Install Edgedrain - Hillsborough Ramp D - Ph1-S2 | 0 | UNDR | UNDR
UDR230 | UDR210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Install Edgedrain - Hillsborough Ramp C2 - Ph1-S2 | Install Edgedrain - Hillsborough Ramp C1 - Ph1-S2 | 0 | UNDR | UNDR
UDR120 | UDR230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Install Edgedrain - Hillsborough Ramp B - Ph1-S2 | Install Edgedrain - Hillsborough Ramp C2 - Ph1-S2 | 0 | UNDR | UNDR
UDR110 | UDR120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Edgedrain - MLK Ramp C - Ph1-S2 | Install Edgedrain - Hillsborough Ramp B - Ph1-S2 | 0 | UNDR | UNDR
UDR100 | UDR110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Edgedrain - MLK Ramp B - Ph1-S2 | Install Edgedrain - MLK Ramp C - Ph1-S2 | 0 | UNDR | UNDR
UDR420 | UDR430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Edgedrain - SB: 722+83-735+00 - Ph1-S1 | Install Edgedrain - SB: 709+50-721+43 - Ph1-S1 | 0 | UNDR | UNDR
UDR410 | UDR420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Edgedrain - SB: 735+46-746+91 - Ph1-S1 | Install Edgedrain - SB: 722+83-735+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR390 | UDR410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Edgedrain - SB: 748+30-757+10 - Ph1-S1 | Install Edgedrain - SB: 735+46-746+91 - Ph1-S1 | 0 | UNDR | UNDR
UDR380 | UDR390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Edgedrain - SB: 757+10-759+97 - Ph1-S1 | Install Edgedrain - SB: 748+30-757+10 - Ph1-S1 | 0 | UNDR | UNDR
UDR350 | UDR360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Edgedrain - SB: 767+00-773+42 - Ph1-S1 | Install Edgedrain - SB: 761+67-767+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR330 | UDR350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Edgedrain - SB: 774+82-780+00 - Ph1-S1 | Install Edgedrain - SB: 767+00-773+42 - Ph1-S1 | 0 | UNDR | UNDR
UDR320 | UDR330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Edgedrain - SB: 780+00-786+69 - Ph1-S1 | Install Edgedrain - SB: 774+82-780+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR310 | UDR320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Edgedrain - SB: 788+09-800+00 - Ph1-S1 | Install Edgedrain - SB: 780+00-786+69 - Ph1-S1 | 0 | UNDR | UNDR
UDR300 | UDR310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Edgedrain - SB: 800+00-813+16 - Ph1-S1 | Install Edgedrain - SB: 788+09-800+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR290 | UDR300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Edgedrain - SB: 815+20-839+61 - Ph1-S1 | Install Edgedrain - SB: 800+00-813+16 - Ph1-S1 | 0 | UNDR | UNDR
UDR270 | UDR290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 827+00-839+61 - Ph1-S1 | Install Edgedrain - SB: 815+20-839+61 - Ph1-S1 | 0 | UNDR | UNDR
UDR250 | UDR270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 815+20-827+00 - Ph1-S1 | Install Edgedrain - NB: 827+00-839+61 - Ph1-S1 | 0 | UNDR | UNDR
UDR240 | UDR250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 800+00-813+16 - Ph1-S1 | Install Edgedrain - NB: 815+20-827+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR220 | UDR240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Edgedrain - NB: 788+09-800+00 - Ph1-S1 | Install Edgedrain - NB: 800+00-813+16 - Ph1-S1 | 0 | UNDR | UNDR
UDR200 | UDR220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Edgedrain - NB: 780+00-786+69 - Ph1-S1 | Install Edgedrain - NB: 788+09-800+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR190 | UDR200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Edgedrain - NB: 774+82-780+00 - Ph1-S1 | Install Edgedrain - NB: 780+00-786+69 - Ph1-S1 | 0 | UNDR | UNDR
UDR180 | UDR190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Edgedrain - NB: 767+00-773+42 - Ph1-S1 | Install Edgedrain - NB: 774+82-780+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR170 | UDR180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Edgedrain - NB: 761+67-767+00 - Ph1-S1 | Install Edgedrain - NB: 767+00-773+42 - Ph1-S1 | 0 | UNDR | UNDR
UDR160 | UDR170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Edgedrain - NB: 757+10-759+97 - Ph1-S1 | Install Edgedrain - NB: 761+67-767+00 - Ph1-S1 | 0 | UNDR | UNDR
UDR150 | UDR160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Edgedrain - NB: 748+30-757+10 - Ph1-S1 | Install Edgedrain - NB: 757+10-759+97 - Ph1-S1 | 0 | UNDR | UNDR
UDR140 | UDR150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Edgedrain - NB: 735+46-746+91 - Ph1-S1 | Install Edgedrain - NB: 748+30-757+10 - Ph1-S1 | 0 | UNDR | UNDR
UDR130 | UDR140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Edgedrain - NB: 722+83-735+00 - Ph1-S1 | Install Edgedrain - NB: 735+46-746+91 - Ph1-S1 | 0 | UNDR | UNDR
PAV500 | PAV510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-ASPH | SUB-ASPH
BASE830 | PAV500 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Shoulder Base - NB & SB Median: 722+83-746+91 - Ph2 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | 0 | EW-ABC | SUB-ASPH
CP600 | GRD340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | 0 | CONCRETE | SUB-DGRIND
SGN2000 | CLK340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Install Signs - NB & SB Median: 714+00-721+43 - Ph2 | Caulk & Seal Joints - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-SIGN | CP-SAW
GRD340 | SGN2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | Install Signs - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-DGRIND | SUB-SIGN
CLK340 | PNT1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Caulk & Seal Joints - NB & SB Median: 714+00-721+43 - Ph2 | Paint - NB & SB Median: 714+00-721+43 - Ph2 | 0 | CP-SAW | SUB-ST-PNT
PAV500 | GRD340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-ASPH | SUB-DGRIND
PAV520 | CP600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | 0 | SUB-ASPH | CONCRETE
BASE850 | BASE860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Shoulder Base - NB & SB Median: 748+30-759+97 - Ph 2 | Shoulder Base - NB & SB Median: 757+10-759+97 - Ph2 | 0 | EW-ABC | EW-ABC
SGN2030 | CLK370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | Caulk & Seal Joints - NB & SB Median: 761+67-773+42 - Ph2 | 0 | SUB-SIGN | CP-SAW
SGN2040 | CLK380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | Caulk & Seal Joints - NB & SB Median: 774+82-786+69 - Ph2 | 0 | SUB-SIGN | CP-SAW
SGN2050 | CLK390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | Caulk & Seal Joints - NB & SB Median: 788+09-813+16 - Ph2 | 0 | SUB-SIGN | CP-SAW
BASE910 | UDR540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Black Base - NB & SB Median: 815+20-839+61 - Ph2 | Install Edgedrain - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-ABC | UNDR
SGN500 | ITS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Signs - NB: 709+50-735+00 - Ph1-S1 | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN520 | ITS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Signs - NB: 748+30-757+10 - Ph1-S1 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN600 | ITS200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
EL210 | BW570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
EL220 | BW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
EL230 | BW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
SGN620 | ITS220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Signs - SB: 800+00-813+16 - Ph1-S1 | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
SGN630 | ITS230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Signs - SB: 788+09-800+00 - Ph1-S1 | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
EL240 | BW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
SGN640 | ITS240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Signs - SB: 780+00-786+69 - Ph1-S1 | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
EL260 | BW850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
EL270 | BW850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
SGN660 | ITS260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Signs - SB: 767+00-773+42 - Ph1-S1 | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
EL290 | BW980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
EL280 | BW980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
SGN690 | ITS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Signs - SB: 748+30-757+10 - Ph1-S1 | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
EL300 | BW1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
EL320 | BW1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
EL310 | BW1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | SUB-UT-ELEC | BARRIER
SGN710 | ITS310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Signs - SB: 722+83-735+00 - Ph1-S1 | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-UT-ITS
LTG1000 | DRGJB10 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | 0 | SUB-UT-ELEC | SUB-JB
LSP180 | DEMO1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Grassing - SB: 748 - 751 - IPh1 | Demo Roadway - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-LANDSC | DEMO
LTG1100 | DEMO1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1090 | DEMO1250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1080 | DEMO1180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp A - IPh1 | Demo Roadway - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1070 | DEMO1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp D - IPh1 | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1010 | DEMO360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp C - IPh1 | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1000 | DEMO290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | Demo Roadway - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
TCW430 | WL470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-WALL | ST-PILE
WL460 | TCW420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall Lagging & Tie-Backs - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 | ST-PILE | ST-WALL
TCW410 | WL460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | Wall Lagging & Tie-Backs - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | ST-WALL | ST-PILE
WL450 | TCW360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall Lagging & Tie-Backs - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 | ST-PILE | ST-WALL
WL440 | WL450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Wall Lagging & Tie-Backs - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL430 | TCW330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall Lagging & Tie-Backs - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 | ST-PILE | ST-WALL
WL420 | WL430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Wall Lagging & Tie-Backs - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-PILE | ST-PILE
TCW320 | WL420 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Wall & Lagging Crew - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | Wall Lagging & Tie-Backs - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | ST-WALL | ST-PILE
WL410 | TCW300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall Lagging & Tie-Backs - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 | ST-PILE | ST-WALL
TCW290 | WL410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | Wall Lagging & Tie-Backs - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-WALL | ST-PILE
WL390 | TCW280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall Lagging & Tie-Backs - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 0 | ST-PILE | ST-WALL
TCW270 | WL390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | Wall Lagging & Tie-Backs - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-WALL | ST-PILE
WL470 | MSE1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE470 | WL470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | H Pile Install - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL460 | MSE1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Wall Lagging & Tie-Backs - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE460 | WL460 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | H Pile Install - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL450 | MSE830 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Wall Lagging & Tie-Backs - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE450 | WL450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | H Pile Install - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL440 | MSE790 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Wall Lagging & Tie-Backs - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE440 | WL440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | H Pile Install - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL430 | MSE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Wall Lagging & Tie-Backs - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE430 | WL430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | H Pile Install - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL420 | MSE660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Wall Lagging & Tie-Backs - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE420 | WL420 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | H Pile Install - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL410 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Wall Lagging & Tie-Backs - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE410 | WL410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL400 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Wall Lagging & Tie-Backs - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
WL390 | MSE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Wall Lagging & Tie-Backs - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE390 | WL390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | H Pile Install - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL380 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Wall Lagging & Tie-Backs - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE380 | WL380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-PILE | ST-PILE
WL370 | MSE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Wall Lagging & Tie-Backs - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE370 | WL370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | H Pile Install - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Wall Lagging & Tie-Backs - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | ST-PILE | ST-PILE
DEMO1540 | DEMO380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Demo Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | Demo / Grade - MLK Ramp B - Ph1-S1 | 0 | DEMO | DEMO
DEMO270 | DEMO300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO150 | DEMO170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Demo Existing Drainage: Remove 25' of 24" Pipe - Floribraska: 721+00-722+00 - Ph1-S1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 2 Structures - SB: 835 - 840 - IPh1 | 0 | DEMO | DEMO
SGN70A | SGN70 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-101 / 723+54 | Procurement: Sign Posts / Gantry - OHS-101 / 723+54 | 0
SGN80A | SGN80 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-102 / 736+00 | Procurement: Sign Posts / Gantry - OHS-102 / 736+00 | 0
SGN100A | SGN100 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-102 / 745+96 | Procurement: Sign Posts / Gantry - OHC-102 / 745+96 | 0
SGN120A | SGN120 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-103 / 758+73 | Procurement: Sign Posts / Gantry - OHC-103 / 758+73 | 0
DSS130 | SGN80A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-102) - SB: 736+00 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-102 / 736+00 | 0 | SUB-ST-DRSFT
BW110 | SGN80A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-102 / 736+00 | 0
DSS120 | SGN80A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-102 / 736+00 | 0 | SUB-ST-DRSFT
DSS160 | SGN100A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-102) - SB: 745+96 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-102 / 745+96 | 0 | SUB-ST-DRSFT
DSS200 | SGN120A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-103) - SB: 758+73 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-103 / 758+73 | 0 | SUB-ST-DRSFT
SGN130A | SGN130 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-104 / 771+34 | Procurement: Sign Posts / Gantry - OHS-104 / 771+34 | 0
DSS230 | SGN130A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-104 / 771+34 | 0 | SUB-ST-DRSFT
BW140 | SGN130A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-104 / 771+34 | 0
DSS210 | SGN130A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-104 / 771+34 | 0 | SUB-ST-DRSFT
SGN150A | SGN150 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-106 / 783+35 | Procurement: Sign Posts / Gantry - OHS-106 / 783+35 | 0
DSS290 | SGN150A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-106 / 783+35 | 0 | SUB-ST-DRSFT
BW260 | SGN150A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-106 / 783+35 | 0
DSS270 | SGN150A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-106 / 783+35 | 0 | SUB-ST-DRSFT
SGN160A | SGN160 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-104 / 792+45 | Procurement: Sign Posts / Gantry - OHC-104 / 792+45 | 0
DSS300 | SGN160A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-104) - SB: 792+45 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-104 / 792+45 | 0 | SUB-ST-DRSFT
SGN180A | SGN180 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-105 / 808+47 | Procurement: Sign Posts / Gantry - OHC-105 / 808+47 | 0
DSS340 | SGN180A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-105) - SB: 808+47 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-105 / 808+47 | 0 | SUB-ST-DRSFT
SGN200A | SGN200 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHB-01 / 818+78 | Procurement: Sign Posts / Gantry - OHB-01 / 818+78 | 0
DSS360 | SGN200A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHB-101) - SB: 818+78 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHB-01 / 818+78 | 0 | SUB-ST-DRSFT
SGN210A | SGN210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-108 / 825+75 | Procurement: Sign Posts / Gantry - OHS-108 / 825+75 | 0
DSS390 | SGN210A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-108 / 825+75 | 0 | SUB-ST-DRSFT
BW340 | SGN210A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-108 / 825+75 | 0
DSS370 | SGN210A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-108 / 825+75 | 0 | SUB-ST-DRSFT
SGN220A | SGN220 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-107 / 833+46 | Procurement: Sign Posts / Gantry - OHC-107 / 833+46 | 0
DSS400 | SGN220A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 833+46 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-107 / 833+46 | 0 | SUB-ST-DRSFT
SGN170A | SGN170 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-107 / 800+70 | Procurement: Sign Posts / Gantry - OHS-107 / 800+70 | 0
BW310 | SGN170A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-107 / 800+70 | 0
DSS310 | SGN170A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-107 / 800+70 | 0 | SUB-ST-DRSFT
DSS330 | SGN170A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 800+70 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-107 / 800+70 | 0 | SUB-ST-DRSFT
SGN190A | SGN190 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-106 / 811+90 | Procurement: Sign Posts / Gantry - OHC-106 / 811+90 | 0
DSS350 | SGN190A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-106) - NB: 811+90 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-106 / 811+90 | 0 | SUB-ST-DRSFT
SGN140A | SGN140 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-105 / 775+55 | Procurement: Sign Posts / Gantry - OHS-105 / 775+55 | 0
BW240 | SGN140A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-105 / 775+55 | 0
DSS240 | SGN140A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-105 / 775+55 | 0 | SUB-ST-DRSFT
DSS260 | SGN140A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-105 / 775+55 | 0 | SUB-ST-DRSFT
SGN110A | SGN110 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-103 / 750+92 | Procurement: Sign Posts / Gantry - OHS-103 / 750+92 | 0
BW130 | SGN110A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-103 / 750+92 | 0
DSS170 | SGN110A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-103 / 750+92 | 0 | SUB-ST-DRSFT
DSS190 | SGN110A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHS-103 / 750+92 | 0 | SUB-ST-DRSFT
SGN90A | SGN90 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-101 / 739+29 | Procurement: Sign Posts / Gantry - OHC-101 / 739+29 | 0
DSS150 | SGN90A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-101) - NB: 739+29 - Ph1-S1 | Shop Drawing & As-Built Review: Sign Posts / Gantry - OHC-101 / 739+29 | 0 | SUB-ST-DRSFT
STAB460 | STAB400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Floribraska Ramp NE - Ph1-S1 | Stabilization - Hillsborough Ramp A - Ph1-S2 | 0 | EW-STAB | EW-CEM
STAB370 | STAB460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Stabilization - Hillsborough Ramp D - Ph1-S2 | Stabilization - Floribraska Ramp NE - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB440 | STAB300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Stabilization - MLK Ramp A - Ph1-S1 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-STAB | EW-CEM
STAB420 | STAB440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Stabilization - MLK Ramp D - Ph1-S1 | Stabilization - MLK Ramp A - Ph1-S1 | 0 | EW-STAB | EW-STAB
STAB350 | STAB320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp A - Ph1-S1 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-STAB | EW-CEM
STAB150 | STAB350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Stabilization - MLK Ramp C - Ph1-S2 | Stabilization - Hillsborough Ramp A - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB310 | STAB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - Hillsborough Ramp D - Ph1-S1 | Stabilization - MLK Ramp C - Ph1-S2 | 0 | EW-STAB | EW-CEM
STAB280 | STAB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - Hillsborough Ramp C2 - Ph1-S1 | Stabilization - MLK Ramp C - Ph1-S2 | 0 | EW-STAB | EW-CEM
BASE160 | BASE500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Base Course - Hillsborough Ramp B - Ph1-S2 | Base Course - MLK Ramp D - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE790 | BASE800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Shoulder Base - NB & SB Median: 714+00-721+43 - Ph2 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-ABC | EW-ABC
STAB120 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Stabilization - MLK Ramp C - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-STAB | EW-CEM
STAB110 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Stabilization - MLK Ramp B - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-STAB | EW-CEM
STAB210 | STAB110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Stabilization - NB: 761+67-767+00 - Ph1-S1 | Stabilization - MLK Ramp B - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB200 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Stabilization - NB: 757+10-759+97 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
NW750 | NW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp A (SB: 107+11.78-104+50.80) - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
NW790 | NW750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Noise Wall 100207 - SB: over East Lake - Ph1-S1 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
NW690 | NW790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Noise Wall 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW780 | NW690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp A - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
NW760 | NW780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW730 | NW760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW640 | NW730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW180 | NW700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Noise Wall 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW610 | NW180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
NW680 | NW610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW630 | NW510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW540 | NW130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
NW500 | NW110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp B (NB: 250+88.27-256+15.55) - Ph1-S2 | 0 | ST-SOUND | ST-SOUND
NW470 | NW480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW410 | NW430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW380 | NW390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW340 | NW370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW390 | NW410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW370 | NW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS-P1S1S2F | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | End of Phase 1, Stage 1, Step 2 | Start of Phase 1, Stage 2 | 0
MS-IP1F | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | End of Initial Phase 1 | Start of Phase 1, Stage 2 | 0
PM110 | M1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Pavement Markings - MLK Ramp B - Ph1-S1 | Start of Phase 1, Stage 2 | 0 | SUB-STRIP
NW740 | EGC500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Excavate / Grade - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 0 | ST-SOUND | EW-SML
R3540 | PM1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Install Misc Final Signage Remaining - Project Limits - Ph3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-SIGN | SUB-STRIP
PAV530 | PAV540 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Cure Friction Course - Project Limits - Ph3 | 10 | SUB-MILL | SUB-MILL
PAV540 | PM1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Cure Friction Course - Project Limits - Ph3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PAV540 | PM1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Cure Friction Course - Project Limits - Ph3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PAV540 | PM210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Cure Friction Course - Project Limits - Ph3 | Final Pavement Markings - Side Roads - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PAV540 | PM230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Cure Friction Course - Project Limits - Ph3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PAV540 | PM220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Cure Friction Course - Project Limits - Ph3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
FDOTP | PUNCH10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | FDOT Develop & Issue Punch List | Punch-out Items | 0
PUNCH10 | MS-FC | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Punch-out Items | Final Completion (Baseline Date: 24-Apr-25) | 0
PM230 | PM1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-STRIP | SUB-STRIP
PM210 | PM1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Final Pavement Markings - Side Roads - Project Limits - Ph3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-STRIP | SUB-STRIP
R3500 | PM1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-DGRIND | SUB-STRIP
PAV530 | PM1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PAV530 | PM1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PM1110 | PM1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Thermoplastic - I-275 NB & Ramps - Project Limits - Ph3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-STRIP | SUB-STRIP
R3510 | PM1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-DGRIND | SUB-STRIP
PM1120 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Thermoplastic - I-275 SB & Ramps - Project Limits - Ph3 | End of Phase 3 | 0 | SUB-STRIP
MSE30 | MSE1160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Procurement: MSE Walls (Delete) | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE1130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Procurement: MSE Walls (Delete) | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE1090 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Procurement: MSE Walls (Delete) | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Procurement: MSE Walls (Delete) | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE1020 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Procurement: MSE Walls (Delete) | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE970 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Procurement: MSE Walls (Delete) | Install MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE920 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Procurement: MSE Walls (Delete) | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE880 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Procurement: MSE Walls (Delete) | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Procurement: MSE Walls (Delete) | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Procurement: MSE Walls (Delete) | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE780 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Procurement: MSE Walls (Delete) | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE740A | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Procurement: MSE Walls (Delete) | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE740 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Procurement: MSE Walls (Delete) | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE690 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Procurement: MSE Walls (Delete) | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Procurement: MSE Walls (Delete) | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE620 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Procurement: MSE Walls (Delete) | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Procurement: MSE Walls (Delete) | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE530 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Procurement: MSE Walls (Delete) | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | 0 |  | SUB-ST-MSE
MSE30 | MSE480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Procurement: MSE Walls (Delete) | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Procurement: MSE Walls (Delete) | Install MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Procurement: MSE Walls (Delete) | Install MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Procurement: MSE Walls (Delete) | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Procurement: MSE Walls (Delete) | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Procurement: MSE Walls (Delete) | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Procurement: MSE Walls (Delete) | Install MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Procurement: MSE Walls (Delete) | Install MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Procurement: MSE Walls (Delete) | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Procurement: MSE Walls (Delete) | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE30 | MSE220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Procurement: MSE Walls (Delete) | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 |  | SUB-ST-MSE
MSE20 | MSE30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | Procurement: MSE Walls (Delete) | 0
MSE10 | MSE20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Prepare Shop Drawings / Submittals: MSE Walls (Delete) | Review & Approve Shop Drawings / Submittals: MSE Walls (Duration = 25 Calendar Days) (Delete) | 0
MS-LNTP | MSE10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.4 Preconstruction: Procurement: Walls: MSE Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: MSE Walls (Delete) | 10
GW30 | R830 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | 0 |  | ST-CIP
GW30 | R810 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | 0 |  | ST-CIP
GW30 | R770 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-7A @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 |  | ST-CIP
GW30 | R745 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-3A @ Floribraska - North Side - Ph1-S1-S2 | 0 |  | ST-CIP
GW30 | R700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
GW30 | R675 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
GW30 | R635 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-5D @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
GW30 | R610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Procurement: Gravity Walls | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
GW20 | GW30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | Review & Approve Shop Drawings / Submittals: Gravity Walls (Duration = 25 Calendar Days) | Procurement: Gravity Walls | 0
GW10 | GW20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | Prepare Shop Drawings / Submittals: Gravity Walls | Review & Approve Shop Drawings / Submittals: Gravity Walls (Duration = 25 Calendar Days) | 0
MS-LNTP | GW10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.2 Preconstruction: Procurement: Walls: Gravity Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: Gravity Walls | 20
PILE360 | PILE470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | H Pile Install - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-SOLDIER | ST-PILE
PILE460 | PILE360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE450 | PILE260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE250 | PILE450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | H Pile Install - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE430 | PILE220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE410 | PILE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE160 | PILE410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE130 | PILE400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | H Pile Install - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE390 | PILE130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | H Pile Install - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE380 | PILE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE100 | PILE380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE370 | PILE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | H Pile Install - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-PILE | ST-PILE
TCC100 | PILE370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install MOT Construction Barriers I-275 NB - IPh1 | H Pile Install - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | TRAFFIC | ST-PILE
DSS230 | MSE1070 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-MSE
DSS290 | MSE1030 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-MSE
DSS390 | MSE750 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-MSE
DSS260 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-MSE
DSS190 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-MSE
DSS100 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Sign Drilled Shaft Foundation (OHS-101) - NB: 723+54 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-MSE
CB150 | DS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Core Bore @ 48" Drilled Shafts - Hillsborough | Install 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB140 | DS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Core Bore @ 48" Drilled Shafts - Osborne | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB130 | DS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Core Bore @ 48" Drilled Shafts - Chelsea | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB120 | DS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Core Bore @ 48" Drilled Shafts - MLK | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS170 | DS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS180 | DS140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS130 | DS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Install 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS120 | DS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DEMO1600 | SUBS1120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1600 | SUBS1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1530 | SUBS900 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Demo Edge of Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1530 | SUBS810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Demo Edge of Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1480 | SUBS730 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1480 | SUBS680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1480 | SUBS670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1440 | SUBS570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1440 | SUBS560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1410 | SUBS460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1410 | SUBS450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1380 | SUBS340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Demo Edge of Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1380 | SUBS330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Demo Edge of Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1350 | SUBS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Demo Edge of Deck 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1350 | SUBS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Demo Edge of Deck 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1310 | SUBS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Demo Edge of Deck 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1310 | SUBS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Demo Edge of Deck 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
CB150 | DS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Core Bore @ 48" Drilled Shafts - Hillsborough | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB140 | DS140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Core Bore @ 48" Drilled Shafts - Osborne | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB130 | DS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Core Bore @ 48" Drilled Shafts - Chelsea | Install 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB120 | DS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Core Bore @ 48" Drilled Shafts - MLK | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB110 | DS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Core Bore @ 48" Drilled Shafts - E. Lake | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | 0 |  | SUB-ST-DRSFT
CB100 | DS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Core Bore @ 48" Drilled Shafts - Floribraska | Install 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SP10 | CB100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Mobilization - IPh1 | Core Bore @ 48" Drilled Shafts - Floribraska | 5
CB140 | CB150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Osborne | Core Bore @ 48" Drilled Shafts - Hillsborough | 0
CB130 | CB140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Chelsea | Core Bore @ 48" Drilled Shafts - Osborne | 0
CB120 | CB130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - MLK | Core Bore @ 48" Drilled Shafts - Chelsea | 0
CB110 | CB120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - E. Lake | Core Bore @ 48" Drilled Shafts - MLK | 0
CB100 | CB110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | 3462-FDOT-Owner-12.4.P1.1.2 Construction: Phase 1: Stage 1: Site Investigations | Core Bore @ 48" Drilled Shafts - Floribraska | Core Bore @ 48" Drilled Shafts - E. Lake | 0
MS-CE | WBO-TEC-10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | Contract Execution | Tampa Electric Company - Remaining Pole Procurement - Started 14-Jan-21 | 0 |  | SUB-UT-ELEC
DS190 | DS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | Cure 48" Drilled Shafts 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS290 | SUBS1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS290 | SUBS1120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS180 | DS280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | Cure 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS280 | SUBS1020 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS280 | SUBS1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS170 | DS270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS270 | SUBS930 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS270 | SUBS950 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS160 | DS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Install 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS260 | SUBS900 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS260 | SUBS810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS260 | SUBS820 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS150 | DS250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS250 | SUBS670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS250 | SUBS730 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS140 | DS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS240 | SUBS560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS240 | SUBS570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS130 | DS230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Install 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | Cure 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS230 | SUBS450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS230 | SUBS460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS120 | DS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | Cure 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS220 | SUBS330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS220 | SUBS340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS110 | DS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | Cure 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS210 | SUBS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS210 | SUBS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS100 | DS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Install 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | Cure 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS200 | SUBS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Cure 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
DS200 | SUBS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Cure 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-ST-DRSFT | ST-BRIDGE-SUB
PILE470 | MSE1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | H Pile Install - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE460 | PILE470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | H Pile Install - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | H Pile Install - MSE Wall W-1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE460 | MSE1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | H Pile Install - MSE Wall W-6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE450 | MSE830 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | H Pile Install - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE440 | PILE450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | H Pile Install - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | H Pile Install - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE440 | MSE790 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | H Pile Install - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE430 | PILE440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | H Pile Install - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | H Pile Install - MSE Wall W-18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE430 | MSE710 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | H Pile Install - MSE Wall W-21A - SB: 834+76.00-839+49.92 - Ph1-S1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE420 | MSE660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | H Pile Install - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE410 | PILE420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | H Pile Install - MSE Wall W-22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE410 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE400 | PILE410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | H Pile Install - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | H Pile Install - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE400 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | H Pile Install - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE390 | PILE400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | H Pile Install - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | H Pile Install - MSE Wall W-7B - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE380 | PILE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | H Pile Install - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE390 | MSE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | H Pile Install - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE370 | PILE380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | H Pile Install - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE380 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | H Pile Install - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE370 | MSE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | H Pile Install - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
MSE250 | MSE100 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW210 | NW270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW250 | NW190 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW240 | NW160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MSE200 | MSE350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install Coping - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install Coping - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE280 | MSE130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Coping - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Coping - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE170 | MSE330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE250 | MSE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE150 | MSE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install Leveling Pad - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE120 | MSE150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Leveling Pad - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE230 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
BASE740 | BASE580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Black Base - SB: 709+50-721+43 - Ph1-S1 | Base Course - Floribraska Ramp NE - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB530 | STAB460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Stabilization - SB: 709+50-721+43 - Ph1-S1 | Stabilization - Floribraska Ramp NE - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB530 | DEMO1690 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Stabilization - SB: 709+50-721+43 - Ph1-S1 | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | 0 | EW-CEM | DEMO
PAV460 | PAV420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - MLK Ramp A - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
BASE660 | BASE540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Black Base - SB: 748+30-757+10 - Ph1-S1 | Base Course - MLK Ramp A - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB470 | STAB440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Stabilization - SB: 748+30-757+10 - Ph1-S1 | Stabilization - MLK Ramp A - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB470 | DEMO1680 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Stabilization - SB: 748+30-757+10 - Ph1-S1 | Demo / Grade - MLK Ramp A - Ph1-S1 | 0 | EW-CEM | DEMO
DEMO1680 | DEMO1690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Demo / Grade - MLK Ramp A - Ph1-S1 | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | 0 | DEMO | DEMO
CP400 | PAV410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Asphalt Paving - MLK Ramp D - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE610 | BASE500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Black Base - SB: 761+67-767+00 - Ph1-S1 | Base Course - MLK Ramp D - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB430 | STAB420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Stabilization - SB: 761+67-767+00 - Ph1-S1 | Stabilization - MLK Ramp D - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB430 | DEMO1670 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Stabilization - SB: 761+67-767+00 - Ph1-S1 | Demo / Grade - MLK Ramp D - Ph1-S1 | 0 | EW-CEM | DEMO
DEMO1670 | DEMO1680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Demo / Grade - MLK Ramp D - Ph1-S1 | Demo / Grade - MLK Ramp A - Ph1-S1 | 0 | DEMO | DEMO
CP340 | PAV380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE530 | BASE430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Black Base - SB: 788+09-800+00 - Ph1-S1 | Base Course - Hillsborough Ramp A - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB360 | STAB350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Stabilization - SB: 788+09-800+00 - Ph1-S1 | Stabilization - Hillsborough Ramp A - Ph1-S1 | 0 | EW-CEM | EW-STAB
DEMO1660 | DEMO1670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | Demo / Grade - MLK Ramp D - Ph1-S1 | 0 | DEMO | DEMO
DEMO1650 | DEMO1660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 0 | DEMO | DEMO
CP310 | PAV360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE470 | BASE390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Black Base - SB: 815+20-839+61 - Ph1-S1 | Base Course - Hillsborough Ramp D - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB330 | STAB310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Stabilization - SB: 815+20-839+61 - Ph1-S1 | Stabilization - Hillsborough Ramp D - Ph1-S1 | 0 | EW-CEM | EW-STAB
PAV320 | PAV340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
BASE260 | BASE310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp C1 - Ph1-S1 | Base Course - Hillsborough Ramp C2 - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB270 | STAB280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp C1 - Ph1-S1 | Stabilization - Hillsborough Ramp C2 - Ph1-S1 | 0 | EW-STAB | EW-STAB
CP280 | PAV320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE400 | BASE260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Black Base - NB: 815+20-839+61 - Ph1-S1 | Base Course - Hillsborough Ramp C1 - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB290 | STAB270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | Stabilization - Hillsborough Ramp C1 - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB290 | DEMO1630 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | 0 | EW-CEM | DEMO
DEMO750 | DEMO1630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | 0 | DEMO | DEMO
CP240 | PAV260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE350 | BASE140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Black Base - NB: 800+00-813+16 - Ph1-S1 | Base Course - Hillsborough Ramp B - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB260 | STAB140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Stabilization - NB: 800+00-813+16 - Ph1-S1 | Stabilization - Hillsborough Ramp B - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB260 | DEMO750 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Stabilization - NB: 800+00-813+16 - Ph1-S1 | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | 0 | EW-CEM | DEMO
DEMO570 | DEMO750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Demo / Grade - MLK Ramp C - Ph1-S1 | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | 0 | DEMO | DEMO
DEMO380 | DEMO570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Demo / Grade - MLK Ramp B - Ph1-S1 | Demo / Grade - MLK Ramp C - Ph1-S1 | 0 | DEMO | DEMO
CP150 | PAV210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Asphalt Paving - MLK Ramp C - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
STAB220 | STAB120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Stabilization - NB: 767+00-773+42 - Ph1-S1 | Stabilization - MLK Ramp C - Ph1-S1 | 0 | EW-CEM | EW-STAB
CP130 | PAV180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Asphalt Paving - MLK Ramp B - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE200 | BASE110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Black Base - NB: 757+10-759+97 - Ph1-S1 | Base Course - MLK Ramp B - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB200 | STAB110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Stabilization - NB: 757+10-759+97 - Ph1-S1 | Stabilization - MLK Ramp B - Ph1-S1 | 0 | EW-CEM | EW-STAB
STAB200 | DEMO380 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Stabilization - NB: 757+10-759+97 - Ph1-S1 | Demo / Grade - MLK Ramp B - Ph1-S1 | 0 | EW-CEM | DEMO
NW140 | DEMO570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | Demo / Grade - MLK Ramp C - Ph1-S1 | 0 | ST-SOUND | DEMO
NW280 | DEMO570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Demo / Grade - MLK Ramp C - Ph1-S1 | 0 | ST-SOUND | DEMO
LTG1100 | DEMO1690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1080 | DEMO1680 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp A - IPh1 | Demo / Grade - MLK Ramp A - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1070 | DEMO1670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp D - IPh1 | Demo / Grade - MLK Ramp D - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1060 | DEMO1660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1050 | DEMO1650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1030 | DEMO1640 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Demo / Grade - Hillsborough Ramp C2 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1040 | DEMO1630 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1020 | DEMO750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1010 | DEMO570 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp C - IPh1 | Demo / Grade - MLK Ramp C - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
LTG1000 | DEMO380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | Demo / Grade - MLK Ramp B - Ph1-S1 | 0 | SUB-UT-ELEC | DEMO
BASE1040 | PAV100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Limerock: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Asphalt Paving: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 | EW-ABC | SUB-ASPH
MS-IP1S | GRD1100 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Start of Initial Phase 1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1090 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Start of Initial Phase 1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1080 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Start of Initial Phase 1 | Earthwork: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1070 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Start of Initial Phase 1 | Earthwork: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1060 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Start of Initial Phase 1 | Earthwork: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1050 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Start of Initial Phase 1 | Earthwork: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 |  | EW- ALL EW
CG100 | GRD1100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1080 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1070 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1050 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
LTG1100 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1090 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1080 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp A - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1070 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp D - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1060 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1050 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1090 | LTG1100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
LTG1080 | LTG1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp A - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
LTG1060 | LTG1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
LTG1050 | LTG1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
LTG1040 | LTG1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
PM1090 | PM1100 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PM1080 | PM1090 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Pavement Marking: Temporary Diversion: SB: MLK Ramp A - IPh1 | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PM1060 | PM1070 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Pavement Marking: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PM1050 | PM1060 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PM1040 | PM1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PAV150 | PAV170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV170 | PM1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1050 | PAV170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Limerock: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | EW-ABC | SUB-ASPH
PAV190 | PM1060 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1060 | PAV190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Limerock: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | EW-ABC | SUB-ASPH
PAV200 | PM1070 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Asphalt Paving: Temporary Diversion: SB: MLK Ramp D - IPh1 | Pavement Marking: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1070 | PAV200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Limerock: Temporary Diversion: SB: MLK Ramp D - IPh1 | Asphalt Paving: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | EW-ABC | SUB-ASPH
PAV220 | PM1080 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Asphalt Paving: Temporary Diversion: SB: MLK Ramp A - IPh1 | Pavement Marking: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1080 | PAV220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Limerock: Temporary Diversion: SB: MLK Ramp A - IPh1 | Asphalt Paving: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 | EW-ABC | SUB-ASPH
PAV230 | PM1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1090 | PAV230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Limerock: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | EW-ABC | SUB-ASPH
PAV240 | PM1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1100 | PAV240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Limerock: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | EW-ABC | SUB-ASPH
BASE1080 | BASE1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Limerock: Temporary Diversion: SB: MLK Ramp A - IPh1 | Limerock: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | EW-ABC | EW-ABC
BASE1050 | BASE1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Limerock: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Limerock: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | EW-ABC | EW-ABC
BASE1040 | BASE1050 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Limerock: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Limerock: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | EW-ABC | EW-ABC
DRG2660 | DRG2670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | PIPE | PIPE
DRG2650 | DRG2660 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Temp Drainage: Temporary Diversion: SB: MLK Ramp A - IPh1 | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | PIPE | PIPE
DRG2620 | DRG2630 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | PIPE | PIPE
DRG2610 | DRG2620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | PIPE | PIPE
GRD1090 | GRD1100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | EW- ALL EW | EW- ALL EW
GRD1080 | GRD1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Earthwork: Temporary Diversion: SB: MLK Ramp A - IPh1 | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | EW- ALL EW | EW- ALL EW
GRD1040 | GRD1050 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Earthwork: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | EW- ALL EW | EW- ALL EW
PM1100 | LTG1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2670 | BASE1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Limerock: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | PIPE | EW-ABC
GRD1100 | DRG2670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Earthwork: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | EW- ALL EW | PIPE
PM1090 | LTG1090 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Pavement Marking: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2660 | BASE1090 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Limerock: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | PIPE | EW-ABC
GRD1090 | DRG2660 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Earthwork: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Temp Drainage: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | EW- ALL EW | PIPE
PM1080 | LTG1080 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Pavement Marking: Temporary Diversion: SB: MLK Ramp A - IPh1 | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2650 | BASE1080 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Temp Drainage: Temporary Diversion: SB: MLK Ramp A - IPh1 | Limerock: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 | PIPE | EW-ABC
GRD1080 | DRG2650 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | Earthwork: Temporary Diversion: SB: MLK Ramp A - IPh1 | Temp Drainage: Temporary Diversion: SB: MLK Ramp A - IPh1 | 0 | EW- ALL EW | PIPE
PM1070 | LTG1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Pavement Marking: Temporary Diversion: SB: MLK Ramp D - IPh1 | Install Temp Lighting: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2640 | BASE1070 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Temp Drainage: Temporary Diversion: SB: MLK Ramp D - IPh1 | Limerock: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | PIPE | EW-ABC
GRD1070 | DRG2640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Earthwork: Temporary Diversion: SB: MLK Ramp D - IPh1 | Temp Drainage: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | EW- ALL EW | PIPE
PM1060 | LTG1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2630 | BASE1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Limerock: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | PIPE | EW-ABC
GRD1060 | DRG2630 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Earthwork: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | EW- ALL EW | PIPE
PM1050 | LTG1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Pavement Marking: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Install Temp Lighting: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2620 | BASE1050 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Limerock: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | PIPE | EW-ABC
GRD1050 | DRG2620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | Earthwork: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Temp Drainage: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | 0 | EW- ALL EW | PIPE
LTG1040 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1030 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
LTG1020 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
MS-IP1S | GRD1040 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Start of Initial Phase 1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1030 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Start of Initial Phase 1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 |  | EW- ALL EW
MS-IP1S | GRD1020 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Start of Initial Phase 1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 |  | EW- ALL EW
CG100 | GRD1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
CG100 | GRD1020 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
LTG1030 | LTG1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
PAV140 | PM1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | SUB-ASPH | SUB-STRIP
PAV150 | PM1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | SUB-ASPH | SUB-STRIP
PM1030 | PM1040 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PM1020 | PM1030 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | SUB-STRIP | SUB-STRIP
BASE1040 | PAV150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | EW-ABC | SUB-ASPH
BASE1030 | PAV140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | EW-ABC | SUB-ASPH
BASE1030 | BASE1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | EW-ABC | EW-ABC
DRG2600 | DRG2610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | PIPE | PIPE
DRG2590 | DRG2600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | PIPE | PIPE
GRD1030 | GRD1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | EW- ALL EW | EW- ALL EW
PM1040 | LTG1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2610 | BASE1040 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | PIPE | EW-ABC
GRD1040 | DRG2610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | EW- ALL EW | PIPE
PM1030 | LTG1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2600 | BASE1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | PIPE | EW-ABC
GRD1030 | DRG2600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | EW- ALL EW | PIPE
LTG1010 | LTG1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp C - IPh1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
PAV120 | PM1020 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1020 | PAV120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Limerock: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | EW-ABC | SUB-ASPH
BASE1010 | BASE1020 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Limerock: Temporary Diversion: NB: MLK Ramp C - IPh1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | EW-ABC | EW-ABC
DRG2580 | DRG2590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Temp Drainage: Temporary Diversion: NB: MLK Ramp C - IPh1 | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | PIPE | PIPE
GRD1010 | GRD1020 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Earthwork: Temporary Diversion: NB: MLK Ramp C - IPh1 | Earthwork: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | EW- ALL EW | EW- ALL EW
PM1020 | LTG1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Pavement Marking: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Install Temp Lighting: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | SUB-STRIP | SUB-UT-ELEC
DRG2590 | BASE1020 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Temp Drainage: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Limerock: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | PIPE | EW-ABC
PAV110 | PM1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Asphalt Paving: Temporary Diversion: NB: MLK Ramp C - IPh1 | Pavement Marking: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | SUB-ASPH | SUB-STRIP
LTG1000 | LTG1010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
PM1000 | PM1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Pavement Marking: Temporary Diversion: NB: MLK Ramp B - IPh1 | Pavement Marking: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | SUB-STRIP | SUB-STRIP
PAV100 | PAV110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Asphalt Paving: Temporary Diversion: NB: MLK Ramp B - IPh1 | Asphalt Paving: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | SUB-ASPH | SUB-ASPH
BASE1000 | BASE1010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Limerock: Temporary Diversion: NB: MLK Ramp B - IPh1 | Limerock: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | EW-ABC | EW-ABC
DRG900 | DRG2580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Temp Drainage: Temporary Diversion: NB: MLK Ramp B - IPh1 | Temp Drainage: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | PIPE | PIPE
GRD1000 | GRD1010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Earthwork: Temporary Diversion: NB: MLK Ramp B - IPh1 | Earthwork: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | EW- ALL EW | EW- ALL EW
DRG2580 | BASE1010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Temp Drainage: Temporary Diversion: NB: MLK Ramp C - IPh1 | Limerock: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | PIPE | EW-ABC
LTG1010 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp C - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
BASE1010 | PAV110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Limerock: Temporary Diversion: NB: MLK Ramp C - IPh1 | Asphalt Paving: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | EW-ABC | SUB-ASPH
MS-IP1S | GRD1010 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Start of Initial Phase 1 | Earthwork: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 |  | EW- ALL EW
CG100 | GRD1010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: NB: MLK Ramp C - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
PAV100 | PM1000 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Asphalt Paving: Temporary Diversion: NB: MLK Ramp B - IPh1 | Pavement Marking: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 | SUB-ASPH | SUB-STRIP
BASE1000 | PAV100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Limerock: Temporary Diversion: NB: MLK Ramp B - IPh1 | Asphalt Paving: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 | EW-ABC | SUB-ASPH
DRG900 | BASE1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Temp Drainage: Temporary Diversion: NB: MLK Ramp B - IPh1 | Limerock: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 | PIPE | EW-ABC
GRD1000 | DRG900 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Earthwork: Temporary Diversion: NB: MLK Ramp B - IPh1 | Temp Drainage: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 | EW- ALL EW | PIPE
LTG1000 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Install Temp Lighting: Temporary Diversion: NB: MLK Ramp B - IPh1 | End of Initial Phase 1 | 0 | SUB-UT-ELEC
MS-IP1S | GRD1000 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Start of Initial Phase 1 | Earthwork: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 |  | EW- ALL EW
CG100 | GRD1000 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.5.1.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp B | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Earthwork: Temporary Diversion: NB: MLK Ramp B - IPh1 | 0 | SUB-EW-C&G | EW- ALL EW
MSE740 | MSE740A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE740A | MSE750 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE740A | MSE780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE740A | MSE770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE710 | MSE740A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE690 | MSE740A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install MSE Wall W-21A, 21B - SB: 837+68.62-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE580 | MSE580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE530A | MSE580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE580A | MSE600 | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE580A | MSE620 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE580A | MSE630 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE550 | MSE580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Install MSE Wall W-15C - NB: 790+49.71-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE530A | MSE570 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE500 | MSE530A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE480 | MSE530A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install MSE Wall W-13E - NB: 783+00.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
PNT1330 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - I-275 SB / Floribraska Ramp NE - Ph1-S2 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
MS-P2S | PNT1000 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Start of Phase 2 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 |  | SUB-ST-PNT
MS-P2S | PNT100 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Start of Phase 2 | Paint 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-ST-PNT
MS-P2S | PNT1360 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Start of Phase 2 | Paint @ Floribraska - South Side - Ph1-S1-S1 | 0 |  | SUB-ST-PNT
PNT200 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100207 - SB: over East Lake - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT190 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100204 - SB: over MLK - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT180 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT170 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT160 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT150 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT140 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT130 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT120 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT110 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100207 - NB: over East Lake - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT100 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint 100201 - NB: over Floribraska - Ph1-S1 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1470 | PNT1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Paint @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | Paint - MLK Ramp B - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
NW780 | B1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-SOUND
B1520 | NW790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100207 - SB: over East Lake - Ph1-S1 | 0 |  | ST-SOUND
NW790 | PNT200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - SB: over East Lake - Ph1-S1 | Paint 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW760 | B2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100204 - SB: over MLK - Ph1-S1 | 0 | ST-SOUND
B2000 | NW780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-SOUND
NW780 | PNT190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - SB: over MLK - Ph1-S1 | Paint 100204 - SB: over MLK - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW730 | B2480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND
B2480 | NW760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-SOUND
NW760 | PNT180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - SB: over Chelsea St. - Ph1-S1 | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW700 | B2960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND
B2960 | NW730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-SOUND
NW730 | PNT170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW610 | B3440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND
B3440 | NW700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-SOUND
NW700 | PNT160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW510 | B3200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND
B3200 | NW610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-SOUND
NW610 | PNT150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW480 | B2720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND
B2720 | NW510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-SOUND
NW510 | PNT140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
B2710 | NW510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-SOUND
NW430 | B2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND
B2240 | NW480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-SOUND
NW480 | PNT130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100206 - NB: over Chelsea St. - Ph1-S1 | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW390 | B1760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-SOUND
B1760 | NW430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-SOUND
NW430 | PNT120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100204 - NB: over MLK Blvd - Ph1-S1 | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW370 | B1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-SOUND
B1470 | NW390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-SOUND
NW390 | PNT110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100207 - NB: over East Lake - Ph1-S1 | Paint 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
BW540 | NW370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-SOUND
NW370 | PNT100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Noise Wall 100201 - NB: over Floribraska - Ph1-S1 | Paint 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
MSE1130 | MSE1140 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1090 | MSE1110 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1050 | MSE1070 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1020 | MSE1030 | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE880 | MSE890 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE850 | MSE860 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE810 | MSE830 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE780 | MSE790 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE740 | MSE750 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE690 | MSE710 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE580 | MSE600 | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE480 | MSE500 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE370 | MSE390 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE330 | MSE340 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
EGC320 | DRG2550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Drainage: S-4 to S-1 (18") - SB: 715-717 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC320 | DRG2540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC320 | DRG2530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC320 | DRG2520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC320 | DRG2510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | 0 | EW-SML | DRAIN
SUPR640 | SUPR700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Overhang 100204 - SB: over MLK - Ph1-S1 | Form Deck 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM190 | SUPR700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | Form Deck 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM190 | SIP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | Install SIP Deck Pans100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BBM190 | SUPR640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | Overhang 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUPR620 | SUPR660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Overhang 100206 - SB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM180 | SUPR660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM180 | SIP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | Install SIP Deck Pans100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BBM180 | SUPR620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | Overhang 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUPR590 | SUPR610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Overhang 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM170 | SUPR610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM170 | SIP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install SIP Deck Pans100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BBM170 | SUPR590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Overhang 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM160 | SUPR540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM160 | SIP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install SIP Deck Pans100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
BBM160 | SUPR520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Overhang 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM150 | SUPR460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM150 | SIP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install SIP Deck Pans100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUPR380 | SUPR400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Overhang 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM140 | SIP140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install SIP Deck Pans100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUPR260 | SUPR290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Overhang 100206 - NB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM130 | SUPR290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM130 | SIP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | Install SIP Deck Pans100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-DECK
DEMO520 | DEMO590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - NB: 780+00-786+69 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0 | DEMO | DEMO
SUPR190 | SUPR250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Overhang 100204 - NB: over MLK Blvd - Ph1-S1 | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM120 | SUPR250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
BBM120 | SIP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | Install SIP Deck Pans100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-DECK
DEMO420 | DEMO480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0 | DEMO | DEMO
SUPR130 | SUPR180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Overhang 100207 - NB: over East Lake - Ph1-S1 | Form Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
BBM110 | SIP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | Install SIP Deck Pans100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-DECK
DEMO210 | DEMO300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 0 | DEMO | DEMO
BBM100 | SIP100 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | Install SIP Deck Pans 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-DECK
SUPR100 | SUPR110 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Overhang 100201 - NB: over Floribraska - Ph1-S1 | Form Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
DRG2540 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG2530 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG2520 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG2510 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG2500 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1000 | EL300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1060 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1050 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1040 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1030 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1020 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1170 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1160 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1150 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1090 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1080 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1070 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1180A | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1190 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1140 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1130 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1120 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1110 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1100 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1230A | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1250 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1240 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1220 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1210 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1200 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1330 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Mitered End to Mitered End (30") - SB: 799-800 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1320 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1310 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1300 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1290 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1280 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1270 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG210A | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1440 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1430 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1420 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1410 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1400 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1390 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1380 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1370 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1360 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1350 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1340 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1580A | EL210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1490A | EL210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-218 to S-217 - Upper (24") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG260A | EL210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-227B to S-227A - Upper (18") - SB: 826-827 - Swale 2 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1600 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-305 to Existing (18") - SB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1590 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1570 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1560 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1550 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1540 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1530 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1520 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1510 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1500 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1480 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1470 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1460 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1450 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG810 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG800 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG790 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-234 to S-235 (18") - NB: 828-829 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG780 | EL200 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-231 to Existing (36") - NB: 827-828 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG770 | EL200 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-232 to S-231 (36") - NB: 827-828 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG760 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-228 to S-232 (24") - NB: 826-828 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG750 | EL200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: Mitered End to Mitered End (24") - NB: 826-827 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG740 | EL200 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG730 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG720 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG710 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-220 to S-221 (18") - NB: 823-824 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG700 | EL200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-203 (18") - NB: 819-821 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG690 | EL200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG680 | EL200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG670 | EL200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG580A | EL190 | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 3 | DRAIN | SUB-UT-ELEC
DRG570A | EL190 | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 3 | DRAIN | SUB-UT-ELEC
DRG660 | EL190 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-177 to S-175 to Existing (15") - NB: 810-812 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 3 | DRAIN | SUB-UT-ELEC
DRG650 | EL190 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 3 | DRAIN | SUB-UT-ELEC
DRG640 | EL190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-169 to S-173 (18") - NB: 807-809 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG630 | EL190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-168 to S-169 (18") - NB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG620 | EL190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 to S-168 (18") - NB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG610 | EL190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG600 | EL190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-159 OF to S-159 (14"x23") - NB: 806-807 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG590 | EL190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG510 | EL180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-135 OF to S-135 (14"x23") - NB: 798-799 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG500 | EL180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 to S-122 (18") - NB: 795-796 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG490 | EL180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 OF to S-128 (18") - NB: 795-796 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG420 | EL150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-79 to S-73 (18") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG410 | EL150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-80 to S-79 (18") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG400 | EL150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-78 to S-80 (18") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG390 | EL150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-78 to Existing (48") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG380 | EL150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: CD-3 to S-78 (48") - NB: 767-768 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG340 | EL140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-60 to S-60A (42") - NB: 764-766 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG330 | EL140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-59 to S-60 (36") - NB: 764-765 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG320 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG310 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG300 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG290 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG280 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-45 to S-46 (24") - NB: 753-754 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG270 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-45 to S-49 (18") - NB: 753-754 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG260 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-42 to S-45 (24") - NB: 751-754 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG250 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-41 to S-42 (30") - NB: 751-752 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG240 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG200 | EL100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-16 to S-22 (30") - NB: 729-734 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG210 | EL100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-21 OF to S-22 (29"x45") - NB: 733-734 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG220 | EL100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DEMO2020 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - NB & SB Median: 836+00-837+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO2020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - NB & SB Median: 836+00-837+00 - Ph2 | 0 | DEMO | DEMO
DEMO2010 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 835+00-836+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO2010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 835+00-836+00 - Ph2 | 0 | DEMO | DEMO
DEMO2000 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 829+00-830+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 829+00-830+00 - Ph2 | 0 | DEMO | DEMO
DEMO1990 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 76' of 18" Pipe - NB & SB Median: 828+00-830+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO1990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 76' of 18" Pipe - NB & SB Median: 828+00-830+00 - Ph2 | 0 | DEMO | DEMO
DEMO1980 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 827+00-828+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO1980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 827+00-828+00 - Ph2 | 0 | DEMO | DEMO
DEMO1970 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 34' of 18" Pipe & 1 Structure - NB & SB Median: 823+00-824+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO1970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 34' of 18" Pipe & 1 Structure - NB & SB Median: 823+00-824+00 - Ph2 | 0 | DEMO | DEMO
DEMO2010 | DEMO2020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 835+00-836+00 - Ph2 | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - NB & SB Median: 836+00-837+00 - Ph2 | 0 | DEMO | DEMO
DEMO2000 | DEMO2010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 829+00-830+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 835+00-836+00 - Ph2 | 0 | DEMO | DEMO
DEMO1990 | DEMO2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 76' of 18" Pipe - NB & SB Median: 828+00-830+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 829+00-830+00 - Ph2 | 0 | DEMO | DEMO
DEMO1980 | DEMO1990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 827+00-828+00 - Ph2 | Demo Existing Drainage: Remove 76' of 18" Pipe - NB & SB Median: 828+00-830+00 - Ph2 | 0 | DEMO | DEMO
DEMO1970 | DEMO1980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 34' of 18" Pipe & 1 Structure - NB & SB Median: 823+00-824+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 827+00-828+00 - Ph2 | 0 | DEMO | DEMO
DEMO1960 | DEMO1970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 60' of 18" Pipe & 2 Structures - NB & SB Median: 822+00-823+00 - Ph2 | Demo Existing Drainage: Remove 34' of 18" Pipe & 1 Structure - NB & SB Median: 823+00-824+00 - Ph2 | 0 | DEMO | DEMO
DEMO1960 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 60' of 18" Pipe & 2 Structures - NB & SB Median: 822+00-823+00 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DEMO1960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Demo Existing Drainage: Remove 60' of 18" Pipe & 2 Structures - NB & SB Median: 822+00-823+00 - Ph2 | 0 | DEMO | DEMO
DEMO1950 | DEMO1960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Demo Existing Drainage: Remove 44' of 18" Pipe & 2 Structures - NB & SB Median: 807+00-808+00 - Ph2 | Demo Existing Drainage: Remove 60' of 18" Pipe & 2 Structures - NB & SB Median: 822+00-823+00 - Ph2 | 0 | DEMO | DEMO
DEMO1950 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 44' of 18" Pipe & 2 Structures - NB & SB Median: 807+00-808+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 44' of 18" Pipe & 2 Structures - NB & SB Median: 807+00-808+00 - Ph2 | 0 | DEMO | DEMO
DEMO1940 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 27' of 18" Pipe & 1 Structure - NB & SB Median: 806+00-807+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 27' of 18" Pipe & 1 Structure - NB & SB Median: 806+00-807+00 - Ph2 | 0 | DEMO | DEMO
DEMO1930 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 96' of 18" Pipe & 1 Structure - NB & SB Median: 805+00-806+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 96' of 18" Pipe & 1 Structure - NB & SB Median: 805+00-806+00 - Ph2 | 0 | DEMO | DEMO
DEMO1920 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | 0 | DEMO | DEMO
DEMO1910 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 96' of 18" Pipe - NB & SB Median: 800+00-802+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 96' of 18" Pipe - NB & SB Median: 800+00-802+00 - Ph2 | 0 | DEMO | DEMO
DEMO1900 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | 0 | DEMO | DEMO
DEMO1890 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 800+00-801+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 800+00-801+00 - Ph2 | 0 | DEMO | DEMO
DEMO1940 | DEMO1950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 27' of 18" Pipe & 1 Structure - NB & SB Median: 806+00-807+00 - Ph2 | Demo Existing Drainage: Remove 44' of 18" Pipe & 2 Structures - NB & SB Median: 807+00-808+00 - Ph2 | 0 | DEMO | DEMO
DEMO1930 | DEMO1940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 96' of 18" Pipe & 1 Structure - NB & SB Median: 805+00-806+00 - Ph2 | Demo Existing Drainage: Remove 27' of 18" Pipe & 1 Structure - NB & SB Median: 806+00-807+00 - Ph2 | 0 | DEMO | DEMO
DEMO1920 | DEMO1930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | Demo Existing Drainage: Remove 96' of 18" Pipe & 1 Structure - NB & SB Median: 805+00-806+00 - Ph2 | 0 | DEMO | DEMO
DEMO1910 | DEMO1920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 96' of 18" Pipe - NB & SB Median: 800+00-802+00 - Ph2 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | 0 | DEMO | DEMO
DEMO1900 | DEMO1910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | Demo Existing Drainage: Remove 96' of 18" Pipe - NB & SB Median: 800+00-802+00 - Ph2 | 0 | DEMO | DEMO
DEMO1890 | DEMO1900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 800+00-801+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 801+00-802+00 - Ph2 | 0 | DEMO | DEMO
DEMO1870 | DEMO1890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 794+00-795+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 800+00-801+00 - Ph2 | 0 | DEMO | DEMO
DEMO1870 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 794+00-795+00 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 794+00-795+00 - Ph2 | 0 | DEMO | DEMO
DEMO1860 | DEMO1870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 794+00-795+00 - Ph2 | 0 | DEMO | DEMO
DEMO1860 | DRG2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | 0 | DEMO | DRAIN
DEMO1820 | DEMO1860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | 0 | DEMO | DEMO
DEMO1840 | DEMO1860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | 0 | DEMO | DEMO
DEMO1840 | DRG2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | 0 | DEMO | DRAIN
DEMO1820 | DEMO1840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | 0 | DEMO | DEMO
DEMO1830 | DEMO1840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 768+00-769+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 781+00-782+00 - Ph2 | 0 | DEMO | DEMO
DEMO1830 | DRG2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 768+00-769+00 - Ph2 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | 0 | DEMO | DRAIN
DEMO1790 | DEMO1830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 768+00-769+00 - Ph2 | 0 | DEMO | DEMO
DEMO1810 | DRG2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 766+00-767+00 - Ph2 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | 0 | DEMO | DRAIN
DEMO1790 | DEMO1810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 766+00-767+00 - Ph2 | 0 | DEMO | DEMO
DEMO1810 | DEMO1830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 766+00-767+00 - Ph2 | Demo Existing Drainage: Remove 5' of 18" Pipe & 1 Structure - NB & SB Median: 768+00-769+00 - Ph2 | 0 | DEMO | DEMO
DEMO1800 | DEMO1810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 756+00-757+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 766+00-767+00 - Ph2 | 0 | DEMO | DEMO
DEMO1800 | DRG2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 756+00-757+00 - Ph2 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | 0 | DEMO | DRAIN
DEMO1730 | DEMO1800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 756+00-757+00 - Ph2 | 0 | DEMO | DEMO
DEMO1780 | DRG2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Demo Existing Drainage: Remove 12' of 15" Pipe & 2 Structures - NB & SB Median: 753+00-754+00 - Ph2 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | 0 | DEMO | DRAIN
DEMO1730 | DEMO1780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | Demo Existing Drainage: Remove 12' of 15" Pipe & 2 Structures - NB & SB Median: 753+00-754+00 - Ph2 | 0 | DEMO | DEMO
DEMO1770 | DEMO1780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 744+00-745+00 - Ph2 | Demo Existing Drainage: Remove 12' of 15" Pipe & 2 Structures - NB & SB Median: 753+00-754+00 - Ph2 | 0 | DEMO | DEMO
DEMO1780 | DEMO1800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Demo Existing Drainage: Remove 12' of 15" Pipe & 2 Structures - NB & SB Median: 753+00-754+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 756+00-757+00 - Ph2 | 0 | DEMO | DEMO
DEMO1710 | DEMO1770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 744+00-745+00 - Ph2 | 0 | DEMO | DEMO
DEMO1770 | DRG2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 744+00-745+00 - Ph2 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 0 | DEMO | DRAIN
DEMO1760 | DEMO1770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 739+00-740+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 744+00-745+00 - Ph2 | 0 | DEMO | DEMO
DEMO1760 | DRG2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 739+00-740+00 - Ph2 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DEMO1760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 739+00-740+00 - Ph2 | 0 | DEMO | DEMO
DEMO1750 | DRG2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 75' of 15" Pipe & 2 Structures - NB & SB Median: 734+00-735+00 - Ph2 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DEMO1750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Demo Existing Drainage: Remove 75' of 15" Pipe & 2 Structures - NB & SB Median: 734+00-735+00 - Ph2 | 0 | DEMO | DEMO
DEMO1740 | DRG2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 733+00-734+00 - Ph2 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DEMO1740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 733+00-734+00 - Ph2 | 0 | DEMO | DEMO
DEMO1750 | DEMO1760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 75' of 15" Pipe & 2 Structures - NB & SB Median: 734+00-735+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 739+00-740+00 - Ph2 | 0 | DEMO | DEMO
DEMO1740 | DEMO1750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 733+00-734+00 - Ph2 | Demo Existing Drainage: Remove 75' of 15" Pipe & 2 Structures - NB & SB Median: 734+00-735+00 - Ph2 | 0 | DEMO | DEMO
DEMO1720 | DEMO1740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 729+00-730+00 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 733+00-734+00 - Ph2 | 0 | DEMO | DEMO
DEMO1720 | DRG2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 729+00-730+00 - Ph2 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DEMO1720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Demo Existing Drainage: Remove 1 Structure - NB & SB Median: 729+00-730+00 - Ph2 | 0 | DEMO | DEMO
DEMO150 | DRG2560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Demo Existing Drainage: Remove 25' of 24" Pipe - Floribraska: 721+00-722+00 - Ph1-S1 | Drainage: S-9 to S-8 (24") - Floribraska - Ph1-S1-S1 | 0 | DEMO | DRAIN
DEMO120 | DEMO150 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Demo Existing Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | Demo Existing Drainage: Remove 25' of 24" Pipe - Floribraska: 721+00-722+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1270 | DEMO1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 753+00-754+00 - Ph1-S1 | Demo Existing Drainage: Remove 5' of 23"x1" Pipe & 2 Structures - SB: 744+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1290 | EGC300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Existing Drainage: Remove 5' of 23"x1" Pipe & 2 Structures - SB: 744+00-745+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1250 | DEMO1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | Demo Existing Drainage: Remove 5' of 23"x1" Pipe & 2 Structures - SB: 744+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1270 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 753+00-754+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1220 | DEMO1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 753+00-754+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1260 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 37' of 18" Pipe & 2 Structures - SB: 753+00-755+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1220 | DEMO1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | Demo Existing Drainage: Remove 37' of 18" Pipe & 2 Structures - SB: 753+00-755+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1260 | DEMO1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 37' of 18" Pipe & 2 Structures - SB: 753+00-755+00 - Ph1-S1 | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 753+00-754+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1240 | DEMO1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 1 Structure - SB: 756+00-757+00 - Ph1-S1 | Demo Existing Drainage: Remove 37' of 18" Pipe & 2 Structures - SB: 753+00-755+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1220 | DEMO1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 1 Structure - SB: 756+00-757+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1240 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 1 Structure - SB: 756+00-757+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1230 | DEMO1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 40' of 30" Pipe - SB: 765+00-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 5' of 23"x14" Pipe & 1 Structure - SB: 756+00-757+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1230 | EGC260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 40' of 30" Pipe - SB: 765+00-767+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1110 | DEMO1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - SB: 761+67-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 40' of 30" Pipe - SB: 765+00-767+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1210 | EGC260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 178' of 30" Pipe & 1 Structure - SB: 765+00-767+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1110 | DEMO1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - SB: 761+67-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 178' of 30" Pipe & 1 Structure - SB: 765+00-767+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1210 | DEMO1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 178' of 30" Pipe & 1 Structure - SB: 765+00-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 40' of 30" Pipe - SB: 765+00-767+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1200 | DEMO1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 766+00-768+00 - Ph1-S1 | Demo Existing Drainage: Remove 178' of 30" Pipe & 1 Structure - SB: 765+00-767+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1190 | DEMO1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 94' of 30" Pipe & 1 Structure - SB: 767+00-768+00 - Ph1-S1 | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 766+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1170 | DEMO1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 769+00-770+00 - Ph1-S1 | Demo Existing Drainage: Remove 94' of 30" Pipe & 1 Structure - SB: 767+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1200 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 766+00-768+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1040 | DEMO1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 766+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1190 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 94' of 30" Pipe & 1 Structure - SB: 767+00-768+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1040 | DEMO1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | Demo Existing Drainage: Remove 94' of 30" Pipe & 1 Structure - SB: 767+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1170 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 769+00-770+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1040 | DEMO1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 769+00-770+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1160 | DEMO1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - SB: 778+00-779+00 - Ph1-S1 | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 769+00-770+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1160 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - SB: 778+00-779+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO960 | DEMO1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - SB: 774+82-780+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - SB: 778+00-779+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1150 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 781+00-782+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO910 | DEMO1150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - SB: 780+00-786+69 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - SB: 781+00-782+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1140 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 784+00-785+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO910 | DEMO1140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - SB: 780+00-786+69 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - SB: 784+00-785+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1150 | DEMO1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 781+00-782+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - SB: 778+00-779+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1140 | DEMO1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 784+00-785+00 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - SB: 781+00-782+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1120 | DEMO1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 791+00-792+00 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - SB: 784+00-785+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1100 | DEMO1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 28' of 18" Pipe & 1 Structure - SB: 794+00-795+00 - Ph1-S1 | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 791+00-792+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1080 | DEMO1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 7' of 23"x14" Pipe & 2 Structures - SB: 794+00-795+00 - Ph1-S1 | Demo Existing Drainage: Remove 28' of 18" Pipe & 1 Structure - SB: 794+00-795+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1120 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 791+00-792+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO850 | DEMO1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Roadway - SB: 788+09-800+00 - Ph1-S1 | Demo Existing Drainage: Remove 18' of 15" Pipe & 2 Structures - SB: 791+00-792+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1100 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 28' of 18" Pipe & 1 Structure - SB: 794+00-795+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO850 | DEMO1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Roadway - SB: 788+09-800+00 - Ph1-S1 | Demo Existing Drainage: Remove 28' of 18" Pipe & 1 Structure - SB: 794+00-795+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1070 | DEMO1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove End Wall - SB: 806+00-807+00 - Ph1-S1 | Demo Existing Drainage: Remove 7' of 23"x14" Pipe & 2 Structures - SB: 794+00-795+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1080 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 7' of 23"x14" Pipe & 2 Structures - SB: 794+00-795+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO850 | DEMO1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Roadway - SB: 788+09-800+00 - Ph1-S1 | Demo Existing Drainage: Remove 7' of 23"x14" Pipe & 2 Structures - SB: 794+00-795+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1050 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 70' of 15" Pipe & 2 Structures - SB: 806+00-807+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO790 | DEMO1050 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 70' of 15" Pipe & 2 Structures - SB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1020 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 806+00-807+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO790 | DEMO1020 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1010 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 16' of 36" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO790 | DEMO1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 16' of 36" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO990 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO790 | DEMO990 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO790 | DEMO1070 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove End Wall - SB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1070 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove End Wall - SB: 806+00-807+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1050 | DEMO1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 70' of 15" Pipe & 2 Structures - SB: 806+00-807+00 - Ph1-S1 | Demo Existing Drainage: Remove End Wall - SB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1020 | DEMO1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 806+00-807+00 - Ph1-S1 | Demo Existing Drainage: Remove 70' of 15" Pipe & 2 Structures - SB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1010 | DEMO1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 16' of 36" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO990 | DEMO1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | Demo Existing Drainage: Remove 16' of 36" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO980 | DEMO990 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - SB: 808+00-809+00 - Ph1-S1 | Demo Existing Drainage: Remove 48' of 15" Pipe & 1 Structure - SB: 808+00-809+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO980 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - SB: 808+00-809+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO790 | DEMO980 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 10' of 18" Pipe & 2 Structures - SB: 808+00-809+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO940 | DEMO950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 823+00-824+00 - Ph1-S1 | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 823+00-824+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO930 | DEMO940 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 20' of 24" Pipe & 2 Structures - SB: 826+00-828+00 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - SB: 823+00-824+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO950 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 823+00-824+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO720 | DEMO950 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 10' of 18" Pipe & 1 Structure - SB: 823+00-824+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO940 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 823+00-824+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO720 | DEMO940 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - SB: 823+00-824+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO920 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 30' of 15" Pipe & 3 Structures - SB: 835+00-836+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO720 | DEMO920 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 30' of 15" Pipe & 3 Structures - SB: 835+00-836+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO900 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 836+00-837+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO720 | DEMO900 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 836+00-837+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO720 | DEMO930 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 24" Pipe & 2 Structures - SB: 826+00-828+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO890 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 839+00-840+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO930 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 20' of 24" Pipe & 2 Structures - SB: 826+00-828+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO900 | DEMO920 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 836+00-837+00 - Ph1-S1 | Demo Existing Drainage: Remove 30' of 15" Pipe & 3 Structures - SB: 835+00-836+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO890 | DEMO900 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - SB: 839+00-840+00 - Ph1-S1 | Demo Existing Drainage: Remove 25' of 15" Pipe & 2 Structures - SB: 836+00-837+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO660 | DEMO880 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 40' of 15" Pipe & 2 Structures - NB: 835+00-836+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO870 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 17' of 24" Pipe & 2 Structures - NB: 826+00-828+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO870 | DEMO880 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 17' of 24" Pipe & 2 Structures - NB: 826+00-828+00 - Ph1-S2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 2 Structures - NB: 835+00-836+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO860 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 10' of 15" Pipe & 2 Structures - NB: 822+00-823+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO840 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 40' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO830 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 41' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO820 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 27' of 14"x23" Pipe & 2 Structures - NB: 820+00-822+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 64' of 18" Pipe & 1 Structure - NB: 819+00-821+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO800 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 47' of 15" Pipe & 2 Structures - NB: 819+00-820+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO840 | DEMO860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | Demo Existing Drainage: Remove 10' of 15" Pipe & 2 Structures - NB: 822+00-823+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO830 | DEMO840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 41' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | Demo Existing Drainage: Remove 40' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO820 | DEMO830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 27' of 14"x23" Pipe & 2 Structures - NB: 820+00-822+00 - Ph1-S2 | Demo Existing Drainage: Remove 41' of 15" Pipe & 1 Structure - NB: 821+00-822+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO660 | DEMO780 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 816+00-817+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO770 | DEMO780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Demo Existing Drainage: Remove 32' of 15" Pipe & 1 Structure - NB: 810+00-811+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 816+00-817+00 - Ph1-S2 | 0 | DEMO | DEMO
DEMO630 | DEMO770 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 32' of 15" Pipe & 1 Structure - NB: 810+00-811+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO650 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 805+00-806+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO760 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 41' of 15" Pipe & 2 Structures - NB: 810+00-811+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO760 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 41' of 15" Pipe & 2 Structures - NB: 810+00-811+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO740 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove Inlet - NB: 809+00-810+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO740 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove Inlet - NB: 809+00-810+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO710 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove End Wall - NB: 808+00-809+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove End Wall - NB: 808+00-809+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO700 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 13' of 23"x14" Pipe & 1 Structure - NB: 807+00-808+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 13' of 23"x14" Pipe & 1 Structure - NB: 807+00-808+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO690 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 42' of 18" Pipe & 2 Structures - NB: 807+00-808+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO690 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 42' of 18" Pipe & 2 Structures - NB: 807+00-808+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO680 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 806+00-807+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 806+00-807+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO630 | DEMO650 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 805+00-806+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO610 | DEMO620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - NB: 784+00-785+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 792+00-793+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO640 | EGC180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 793+00-795+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO580 | DEMO640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Roadway - NB: 788+09-800+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 18" Pipe & 2 Structures - NB: 793+00-795+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO580 | DEMO620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Roadway - NB: 788+09-800+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 2 Structures - NB: 792+00-793+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO600 | DEMO610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 1 Structure - NB: 778+00-779+00 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - NB: 784+00-785+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO610 | EGC170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Existing Drainage: Remove 1 Structure - NB: 784+00-785+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO520 | DEMO610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - NB: 780+00-786+69 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - NB: 784+00-785+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO550 | DEMO560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 769+00-770+00 - Ph1-S1 | Demo Existing Drainage: Remove 28' of 18" Pipe & 3 Structures - NB: 778+00-779+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO560 | DEMO600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 28' of 18" Pipe & 3 Structures - NB: 778+00-779+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 1 Structure - NB: 778+00-779+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO600 | EGC160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 20' of 15" Pipe & 1 Structure - NB: 778+00-779+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO470 | DEMO600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - NB: 774+82-780+00 - Ph1-S1 | Demo Existing Drainage: Remove 20' of 15" Pipe & 1 Structure - NB: 778+00-779+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO560 | EGC160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Existing Drainage: Remove 28' of 18" Pipe & 3 Structures - NB: 778+00-779+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO470 | DEMO560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - NB: 774+82-780+00 - Ph1-S1 | Demo Existing Drainage: Remove 28' of 18" Pipe & 3 Structures - NB: 778+00-779+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO510 | DEMO540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 252' of 42" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | Demo Existing Drainage: Remove 15' of 15" Pipe & 3 Structures - NB: 768+00-769+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO500 | DEMO510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Existing Drainage: Remove 97' of 36" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | Demo Existing Drainage: Remove 252' of 42" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO360 | DEMO510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 252' of 42" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO550 | EGC150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 769+00-770+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO420 | DEMO550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 769+00-770+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO540 | EGC150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Existing Drainage: Remove 15' of 15" Pipe & 3 Structures - NB: 768+00-769+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO420 | DEMO540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | Demo Existing Drainage: Remove 15' of 15" Pipe & 3 Structures - NB: 768+00-769+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO360 | DEMO550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 769+00-770+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO360 | DEMO540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 15' of 15" Pipe & 3 Structures - NB: 768+00-769+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO360 | DEMO500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | Demo Existing Drainage: Remove 97' of 36" Pipe & 2 Structures - NB: 764+00-768+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO440 | DEMO450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 12' of 18" Pipe & 1 Structure - NB: 752+00-753+00 - Ph1-S1 | Demo Existing Drainage: Remove 40' of 18" Pipe & 2 Structures - NB: 752+00-756+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO440 | EGC120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: Remove 12' of 18" Pipe & 1 Structure - NB: 752+00-753+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO290 | DEMO430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - NB: 748+30-757+10 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - NB: 751+00-752+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO410 | DEMO430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Existing Drainage: S-34 Remove 35' of 18" Pipe & 2 Structures - NB: 744+00 - Ph1-S1 | Demo Existing Drainage: Remove 1 Structure - NB: 751+00-752+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO390 | DEMO400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 730+00-745+00 - Ph1-S1 | Demo Existing Drainage: S-31 Remove to Existing - NB: 739+00-740+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO210 | DEMO390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 730+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO210 | DEMO370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | Demo Existing Drainage: Remove 12' of 24" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO370 | DEMO390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 12' of 24" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | Demo Existing Drainage: Remove 23' of 15" Pipe & 2 Structures - NB: 730+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO350 | DEMO370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 36' of 15" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | Demo Existing Drainage: Remove 12' of 24" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO340 | DEMO350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 84' of 15" Pipe - NB: 726+00-730+00 - Ph1-S1 | Demo Existing Drainage: Remove 36' of 15" Pipe & 1 Structure - NB: 730+00-745+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO240 | DEMO340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 619' of 30" Pipe & 5 Structures - NB: 726+00-734+00 - Ph1-S1 | Demo Existing Drainage: Remove 84' of 15" Pipe - NB: 726+00-730+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO240 | DEMO400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Existing Drainage: Remove 619' of 30" Pipe & 5 Structures - NB: 726+00-734+00 - Ph1-S1 | Demo Existing Drainage: S-31 Remove to Existing - NB: 739+00-740+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO240 | EGC100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Existing Drainage: Remove 619' of 30" Pipe & 5 Structures - NB: 726+00-734+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO130 | DEMO240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Roadway - NB: 722+83-735+00 - Ph1-S1 | Demo Existing Drainage: Remove 619' of 30" Pipe & 5 Structures - NB: 726+00-734+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO130 | DEMO190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Roadway - NB: 722+83-735+00 - Ph1-S1 | Demo Existing Drainage: Remove S-11 Structure - NB: 725+00-726+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO210 | DEMO410 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | Demo Existing Drainage: S-34 Remove 35' of 18" Pipe & 2 Structures - NB: 744+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO400 | DEMO410 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Existing Drainage: S-31 Remove to Existing - NB: 739+00-740+00 - Ph1-S1 | Demo Existing Drainage: S-34 Remove 35' of 18" Pipe & 2 Structures - NB: 744+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO210 | DEMO400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | Demo Existing Drainage: S-31 Remove to Existing - NB: 739+00-740+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO310 | EGC580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 748 - 751 - IPh1 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | 0 | DEMO | EW-SML
DEMO280 | DEMO310 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 769 - 772 - IPh1 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 748 - 751 - IPh1 | 0 | DEMO | DEMO
SP10 | DEMO280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Mobilization - IPh1 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 769 - 772 - IPh1 | 0 |  | DEMO
CG100 | DEMO280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 769 - 772 - IPh1 | 0 | SUB-EW-C&G | DEMO
DEMO280 | EGC570 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 769 - 772 - IPh1 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | 0 | DEMO | EW-SML
DEMO260 | DEMO280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 777 - 781 - IPh1 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 769 - 772 - IPh1 | 0 | DEMO | DEMO
CG100 | DEMO260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 777 - 781 - IPh1 | 0 | SUB-EW-C&G | DEMO
SP10 | DEMO260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Mobilization - IPh1 | Demo Existing Drainage: End U Wall, 15' of 15" Pipe, 1 Structure - SB: 777 - 781 - IPh1 | 0 |  | DEMO
CG100 | DEMO230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: End U Wall, 20' of 24" Pipe, 1 Structure - SB: 823 - 827 - IPh1 | 0 | SUB-EW-C&G | DEMO
SP10 | DEMO230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Mobilization - IPh1 | Demo Existing Drainage: End U Wall, 20' of 24" Pipe, 1 Structure - SB: 823 - 827 - IPh1 | 0 |  | DEMO
DEMO230 | EGC520 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Demo Existing Drainage: End U Wall, 20' of 24" Pipe, 1 Structure - SB: 823 - 827 - IPh1 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 0 | DEMO | EW-SML
DEMO200 | DEMO230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Demo Existing Drainage: 1 Structure - SB: 835 - 840 - IPh1 | Demo Existing Drainage: End U Wall, 20' of 24" Pipe, 1 Structure - SB: 823 - 827 - IPh1 | 0 | DEMO | DEMO
CG100 | DEMO200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: 1 Structure - SB: 835 - 840 - IPh1 | 0 | SUB-EW-C&G | DEMO
CG100 | DEMO170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 2 Structures - SB: 835 - 840 - IPh1 | 0 | SUB-EW-C&G | DEMO
CG100 | DEMO140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - SB: 835 - 840 - IPh1 | 0 | SUB-EW-C&G | DEMO
SP10 | DEMO200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Mobilization - IPh1 | Demo Existing Drainage: 1 Structure - SB: 835 - 840 - IPh1 | 0 |  | DEMO
SP10 | DEMO170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Mobilization - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 2 Structures - SB: 835 - 840 - IPh1 | 0 |  | DEMO
SP10 | DEMO140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Mobilization - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - SB: 835 - 840 - IPh1 | 0 |  | DEMO
DEMO200 | EGC510 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Demo Existing Drainage: 1 Structure - SB: 835 - 840 - IPh1 | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | 0 | DEMO | EW-SML
DEMO140 | DEMO170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - SB: 835 - 840 - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 2 Structures - SB: 835 - 840 - IPh1 | 0 | DEMO | DEMO
CG100 | DEMO100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - NB: 815 - 818 - IPh1 | 0 | SUB-EW-C&G | DEMO
SP10 | DEMO100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Mobilization - IPh1 | Demo Existing Drainage: End U Wall, 20' of 15" Pipe, 1 Structure - NB: 815 - 818 - IPh1 | 0 |  | DEMO
UDR400 | BASE720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Install Edgedrain - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Black Base - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | UNDR | EW-ABC
STAB510 | UDR400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Stabilization - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Install Edgedrain - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-CEM | UNDR
UDR370 | BASE670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Install Edgedrain - MLK Ramp A - Ph1-S2 | Base Course - MLK Ramp A - Ph1-S2 | 0 | UNDR | EW-ABC
STAB490 | UDR370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Stabilization - MLK Ramp A - Ph1-S2 | Install Edgedrain - MLK Ramp A - Ph1-S2 | 0 | EW-CEM | UNDR
UDR340 | BASE630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Install Edgedrain - MLK Ramp D - Ph1-S2 | Base Course - MLK Ramp D - Ph1-S2 | 0 | UNDR | EW-ABC
STAB480 | UDR340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Stabilization - MLK Ramp D - Ph1-S2 | Install Edgedrain - MLK Ramp D - Ph1-S2 | 0 | EW-CEM | UNDR
UDR280 | BASE490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | Base Course - Hillsborough Ramp A - Ph1-S2 | 0 | UNDR | EW-ABC
STAB400 | UDR280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp A - Ph1-S2 | Install Edgedrain - Hillsborough Ramp A - Ph1-S2 | 0 | EW-CEM | UNDR
UDR260 | BASE450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Install Edgedrain - Hillsborough Ramp D - Ph1-S2 | Base Course - Hillsborough Ramp D - Ph1-S2 | 0 | UNDR | EW-ABC
STAB370 | UDR260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Stabilization - Hillsborough Ramp D - Ph1-S2 | Install Edgedrain - Hillsborough Ramp D - Ph1-S2 | 0 | EW-CEM | UNDR
UDR210 | BASE370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Install Edgedrain - Hillsborough Ramp C1 - Ph1-S2 | Base Course - Hillsborough Ramp C1 - Ph1-S2 | 0 | UNDR | EW-ABC
STAB300 | UDR210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | Install Edgedrain - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-CEM | UNDR
UDR230 | BASE410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Install Edgedrain - Hillsborough Ramp C2 - Ph1-S2 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | 0 | UNDR | EW-ABC
STAB320 | UDR230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | Install Edgedrain - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-CEM | UNDR
UDR120 | BASE160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Install Edgedrain - Hillsborough Ramp B - Ph1-S2 | Base Course - Hillsborough Ramp B - Ph1-S2 | 0 | UNDR | EW-ABC
STAB160 | UDR120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Stabilization - Hillsborough Ramp B - Ph1-S2 | Install Edgedrain - Hillsborough Ramp B - Ph1-S2 | 0 | EW-CEM | UNDR
UDR110 | BASE150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Install Edgedrain - MLK Ramp C - Ph1-S2 | Base Course - MLK Ramp C - Ph1-S2 | 0 | UNDR | EW-ABC
STAB150 | UDR110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - MLK Ramp C - Ph1-S2 | Install Edgedrain - MLK Ramp C - Ph1-S2 | 0 | EW-CEM | UNDR
UDR100 | BASE130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Install Edgedrain - MLK Ramp B - Ph1-S2 | Base Course - MLK Ramp B - Ph1-S2 | 0 | UNDR | EW-ABC
STAB130 | UDR100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Stabilization - MLK Ramp B - Ph1-S2 | Install Edgedrain - MLK Ramp B - Ph1-S2 | 0 | EW-CEM | UNDR
PAV430 | PM200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Asphalt Paving - Floribraska Ramp NE - Ph1-S1 | Pavement Markings - Floribraska Ramp NE - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE580 | PAV430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Base Course - Floribraska Ramp NE - Ph1-S1 | Asphalt Paving - Floribraska Ramp NE - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB460 | BASE580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Stabilization - Floribraska Ramp NE - Ph1-S1 | Base Course - Floribraska Ramp NE - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO1690 | STAB460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | Stabilization - Floribraska Ramp NE - Ph1-S1 | 0 | DEMO | EW-STAB
PM190 | PM200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Pavement Markings - MLK Ramp A - Ph1-S1 | Pavement Markings - Floribraska Ramp NE - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM200 | EGC390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Pavement Markings - Floribraska Ramp NE - Ph1-S1 | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV420 | PM190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Asphalt Paving - MLK Ramp A - Ph1-S1 | Pavement Markings - MLK Ramp A - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE540 | PAV420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Base Course - MLK Ramp A - Ph1-S1 | Asphalt Paving - MLK Ramp A - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB440 | BASE540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Stabilization - MLK Ramp A - Ph1-S1 | Base Course - MLK Ramp A - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO1680 | STAB440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Demo / Grade - MLK Ramp A - Ph1-S1 | Stabilization - MLK Ramp A - Ph1-S1 | 0 | DEMO | EW-STAB
PM180 | PM190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Pavement Markings - MLK Ramp D - Ph1-S1 | Pavement Markings - MLK Ramp A - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM190 | EGC380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Pavement Markings - MLK Ramp A - Ph1-S1 | Excavate / Grade - MLK Ramp A - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV420 | EGC380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Asphalt Paving - MLK Ramp A - Ph1-S1 | Excavate / Grade - MLK Ramp A - Ph1-S2 | 0 | SUB-ASPH | EW-SML
PAV410 | PM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S1 | Pavement Markings - MLK Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE500 | PAV410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Base Course - MLK Ramp D - Ph1-S1 | Asphalt Paving - MLK Ramp D - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB420 | BASE500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Stabilization - MLK Ramp D - Ph1-S1 | Base Course - MLK Ramp D - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO1670 | STAB420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Demo / Grade - MLK Ramp D - Ph1-S1 | Stabilization - MLK Ramp D - Ph1-S1 | 0 | DEMO | EW-STAB
PM170 | PM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Pavement Markings - Hillsborough Ramp A - Ph1-S1 | Pavement Markings - MLK Ramp D - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM180 | EGC370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Pavement Markings - MLK Ramp D - Ph1-S1 | Excavate / Grade - MLK Ramp D - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV410 | EGC370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S1 | Excavate / Grade - MLK Ramp D - Ph1-S2 | 0 | SUB-ASPH | EW-SML
PAV380 | PM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | Pavement Markings - Hillsborough Ramp A - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE430 | PAV380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Base Course - Hillsborough Ramp A - Ph1-S1 | Asphalt Paving - Hillsborough Ramp A - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
DEMO1660 | STAB350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | Stabilization - Hillsborough Ramp A - Ph1-S1 | 0 | DEMO | EW-STAB
PM160 | PM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | Pavement Markings - Hillsborough Ramp A - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM170 | EGC360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Pavement Markings - Hillsborough Ramp A - Ph1-S1 | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV360 | PM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE390 | PAV360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Base Course - Hillsborough Ramp D - Ph1-S1 | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB310 | BASE390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Stabilization - Hillsborough Ramp D - Ph1-S1 | Base Course - Hillsborough Ramp D - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO1650 | STAB310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | Stabilization - Hillsborough Ramp D - Ph1-S1 | 0 | DEMO | EW-STAB
PM160 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-STRIP
PM160 | EGC350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Pavement Markings - Hillsborough Ramp D - Ph1-S1 | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV360 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-ASPH
PAV360 | EGC350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp D - Ph1-S1 | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-ASPH | EW-SML
PAV340 | PM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | Pavement Markings - Hillsborough Ramp C2 - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE310 | PAV340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp C2 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB280 | BASE310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp C2 - Ph1-S1 | Base Course - Hillsborough Ramp C2 - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO1640 | STAB280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Demo / Grade - Hillsborough Ramp C2 - Ph1-S1 | Stabilization - Hillsborough Ramp C2 - Ph1-S1 | 0 | DEMO | EW-STAB
PM140 | PM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Pavement Markings - Hillsborough Ramp C1 - Ph1-S1 | Pavement Markings - Hillsborough Ramp C2 - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM150 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Pavement Markings - Hillsborough Ramp C2 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-STRIP
PM150 | EGC340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Pavement Markings - Hillsborough Ramp C2 - Ph1-S1 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV340 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-ASPH
PAV340 | EGC340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S1 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | 0 | SUB-ASPH | EW-SML
PAV320 | PM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | Pavement Markings - Hillsborough Ramp C1 - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE260 | PAV320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp C1 - Ph1-S1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB270 | BASE260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Stabilization - Hillsborough Ramp C1 - Ph1-S1 | Base Course - Hillsborough Ramp C1 - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO1630 | STAB270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | Stabilization - Hillsborough Ramp C1 - Ph1-S1 | 0 | DEMO | EW-STAB
PM130 | PM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Pavement Markings - Hillsborough Ramp B - Ph1-S1 | Pavement Markings - Hillsborough Ramp C1 - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM140 | EGC330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Pavement Markings - Hillsborough Ramp C1 - Ph1-S1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV320 | EGC330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | 0 | SUB-ASPH | EW-SML
PAV260 | PM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | Pavement Markings - Hillsborough Ramp B - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE140 | PAV260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Base Course - Hillsborough Ramp B - Ph1-S1 | Asphalt Paving - Hillsborough Ramp B - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB140 | BASE140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Stabilization - Hillsborough Ramp B - Ph1-S1 | Base Course - Hillsborough Ramp B - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO750 | STAB140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | Stabilization - Hillsborough Ramp B - Ph1-S1 | 0 | DEMO | EW-STAB
PM120 | PM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Pavement Parkings - MLK Ramp C - Ph1-S1 | Pavement Markings - Hillsborough Ramp B - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PAV210 | PM120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Asphalt Paving - MLK Ramp C - Ph1-S1 | Pavement Parkings - MLK Ramp C - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE120 | PAV210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Base Course - MLK Ramp C - Ph1-S1 | Asphalt Paving - MLK Ramp C - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB120 | BASE120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Stabilization - MLK Ramp C - Ph1-S1 | Base Course - MLK Ramp C - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO570 | STAB120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Demo / Grade - MLK Ramp C - Ph1-S1 | Stabilization - MLK Ramp C - Ph1-S1 | 0 | DEMO | EW-STAB
PM110 | PM120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Pavement Markings - MLK Ramp B - Ph1-S1 | Pavement Parkings - MLK Ramp C - Ph1-S1 | 0 | SUB-STRIP | SUB-STRIP
PM120 | EGC550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Pavement Parkings - MLK Ramp C - Ph1-S1 | Excavate / Grade - MLK Ramp C - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV210 | EGC550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Asphalt Paving - MLK Ramp C - Ph1-S1 | Excavate / Grade - MLK Ramp C - Ph1-S2 | 0 | SUB-ASPH | EW-SML
MS-P1S1S | STAB120 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Start of Phase 1, Stage 1 | Stabilization - MLK Ramp C - Ph1-S1 | 0 |  | EW-STAB
PAV180 | PM110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Asphalt Paving - MLK Ramp B - Ph1-S1 | Pavement Markings - MLK Ramp B - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE110 | PAV180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Base Course - MLK Ramp B - Ph1-S1 | Asphalt Paving - MLK Ramp B - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB110 | BASE110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Stabilization - MLK Ramp B - Ph1-S1 | Base Course - MLK Ramp B - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO380 | STAB110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Demo / Grade - MLK Ramp B - Ph1-S1 | Stabilization - MLK Ramp B - Ph1-S1 | 0 | DEMO | EW-STAB
PM110 | EGC530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Pavement Markings - MLK Ramp B - Ph1-S1 | Excavate / Grade - MLK Ramp B - Ph1-S2 | 0 | SUB-STRIP | EW-SML
PAV180 | EGC530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Asphalt Paving - MLK Ramp B - Ph1-S1 | Excavate / Grade - MLK Ramp B - Ph1-S2 | 0 | SUB-ASPH | EW-SML
PAV130 | PM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Asphalt Paving - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Pavement Markings - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | SUB-ASPH | SUB-STRIP
BASE100 | PAV130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Base - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Asphalt Paving - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB100 | BASE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Stabilization - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Base - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | EW-STAB | EW-ABC
DEMO110 | STAB100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Demo / Grade - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Stabilization - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 | DEMO | EW-STAB
LOE-FLOR-C | PM100 | FF | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | **Floribraska Ramp C - 45 Calendar Day Duration (SUMMARY) | Pavement Markings - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 |  | SUB-STRIP
DEMO110 | LOE-FLOR-C | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Demo / Grade - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | **Floribraska Ramp C - 45 Calendar Day Duration (SUMMARY) | 0 | DEMO
PAV130 | DEMO380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Asphalt Paving - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | Demo / Grade - MLK Ramp B - Ph1-S1 | 0 | SUB-ASPH | DEMO
ITS290 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS360 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | ITS: System Integration & Acceptance Testing | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS330 | ITS350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | ITS Testing - NB | ITS: Field Acceptance Testing | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS350 | ITS360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | ITS: Field Acceptance Testing | ITS: System Integration & Acceptance Testing | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS340 | ITS350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | ITS Testing - SB | ITS: Field Acceptance Testing | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS330 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | ITS Testing - NB | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS310 | ITS340 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | ITS Testing - SB | 5 | SUB-UT-ITS | SUB-UT-ITS
ITS290 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS260 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS240 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS230 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS220 | ITS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | ITS Testing - SB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS200 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS120 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS100 | ITS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.3 Construction: Phase 1: ITS Fiber Installation & Testing | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | ITS Testing - NB | 0 | SUB-UT-ITS | SUB-UT-ITS
ITS30 | ITS310 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Procurement: ITS | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Procurement: ITS | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Procurement: ITS | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Procurement: ITS | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Procurement: ITS | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Procurement: ITS | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Procurement: ITS | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: ITS | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-UT-ITS
ITS30 | ITS200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Procurement: ITS | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-UT-ITS
PILE340 | PILE350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Drive Production H-Piles 100204 - SB: over MLK - Ph1-S1 | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE320 | PILE330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Drive Production H-Piles 100206 - SB: over Chelsea St. - Ph1-S1 | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE250 | PILE260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE200 | PILE210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Drive Production H-Piles 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE180 | PILE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE160 | PILE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE130 | PILE140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 0 | ST-PILE | ST-SOLDIER
PILE100 | PILE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 | ST-PILE | ST-SOLDIER
TCC100 | PILE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Install MOT Construction Barriers I-275 NB - IPh1 | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | 0 | TRAFFIC | ST-PILE
NW250 | PNT1000 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW240 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW220 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW210 | PNT1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Paint - NB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW190 | PNT1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Paint - NB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW160 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW280 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW270 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW350 | PNT1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Paint - NB: 780+00-786+69 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW350 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW330 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW310 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW300 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW420 | PNT1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Paint - NB: 788+09-800+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW400 | PNT1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Paint - NB: 788+09-800+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW460 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW440 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW580 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW570 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW550 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW520 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW660 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW620 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW590 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW670 | PNT1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Paint - SB: 780+00-786+69 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW710 | PNT1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Paint - SB: 761+67-767+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW710 | PNT1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Paint - SB: 767+00-773+42 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW720 | PNT1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Paint - SB: 748+30-757+10 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW720 | PNT1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Paint - SB: 757+10-759+97 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW740 | PNT1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Paint - SB: 709+50-721+43 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW740 | PNT1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Paint - SB: 722+83-735+00 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW740 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | SUB-ST-PNT
NW720 | NW740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS380 | NW740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Form / Reinforce / Pour Moment Slab - MSE Wall W-1A, 1B, 1C - RAMP NE: 714+80.00-717+20.23 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE1160 | MSE1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install Coping - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1140 | MSE1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1150 | MSE1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Coping - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1190 | MS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Coping - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-1A, 1B, 1C - RAMP NE: 714+80.00-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE1150 | MSE1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW710 | NW720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS360 | MS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS370 | NW720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE1130 | MSE1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1110 | MSE1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1120 | MSE1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Coping - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1150 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
MSE1150 | MS370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Coping - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE1090 | MSE1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW670 | NW710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS360 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS360 | NW710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE1090 | MSE1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install Coping - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1070 | MSE1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1080 | MSE1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install Coping - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1120 | MS360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Coping - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE1050 | MSE1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1050 | MSE1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1030 | MSE1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1040 | MSE1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1080 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
MSE1080 | MS350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Coping - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE1020 | MSE1050 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW660 | NW670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS340 | NW670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE1020 | MSE1040 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE990 | MSE1020 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Leveling Pad - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1010 | MSE1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1040 | SUBS1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-MSE | ST-BRIDGE-SUB
MSE1040 | MS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE1040 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Coping - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
NW620 | NW660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS320 | MS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS330 | NW660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE970 | MSE1010 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE950 | MSE970 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Leveling Pad - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Install MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE940 | MSE1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Coping - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE1010 | SUBS1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-MSE | ST-BRIDGE-SUB
MSE1010 | MS330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Install Coping - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MS320 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | EW-CEM
NW590 | NW620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS320 | NW620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE920 | MSE940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Install Coping - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE890 | MSE920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE910 | MSE940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install Coping - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE940 | MS320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Coping - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE880 | MSE920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW580 | NW590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS310 | NW590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE880 | MSE910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE860 | MSE880 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE870 | MSE910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Coping - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE910 | MS310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE910 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Coping - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
MSE850 | MSE880 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW570 | NW580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS300 | NW580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Form / Reinforce / Pour Moment Slab - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE850 | MSE870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install Coping - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE830 | MSE850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE840 | MSE870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install Coping - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Coping - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE870 | MS300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install Coping - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE870 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Coping - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
MSE810 | MSE850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE750 | MSE790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS290 | NW570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
NW550 | NW570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MSE810 | MSE840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Coping - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE790 | MSE810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE800 | MSE840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install Coping - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE840 | MS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install Coping - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE780 | MSE810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW520 | NW550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS280 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS270 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MSE770 | MSE800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE710 | MSE750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE780 | MSE800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE750 | MSE780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS280 | NW550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MS270 | NW550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE800 | MS280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE800 | MS270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install Coping - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE740 | MSE780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | Install MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE770 | MS260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
NW460 | NW520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS260 | NW520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE740 | MSE770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE710 | MSE740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS250 | MS260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS260 | MS270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MSE720 | MSE770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Coping - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Coping - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE690 | MSE740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install MSE Wall W-21C, 21D - SB: 834+76.00-837+68.62 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE720 | MS250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Coping - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MS250 | NW460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE690 | MSE720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Coping - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE660 | MSE690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE680 | MSE720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Coping - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install Coping - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE640 | MSE690 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS240 | NW440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE640 | MSE680 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install Coping - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE610 | MSE640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Leveling Pad - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE650 | MSE680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Coping - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Install Coping - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE680 | MS240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Install Coping - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE640 | MSE660 | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS220 | MS230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Form / Reinforce / Pour Moment Slab - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MSE620 | MSE650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Install Coping - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE600 | MSE620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS230 | NW420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE630 | MSE650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Install Coping - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE650 | MS230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install Coping - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE580 | MSE620 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | Install MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS220 | NW400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Form / Reinforce / Pour Moment Slab - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE580 | MSE630 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE550 | MSE580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Install MSE Wall W-15C - NB: 787+88.29-790+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE570 | MSE630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE630 | MS220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Coping - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE550 | MSE600 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS200 | MS210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | CONCRETE | CONCRETE
NW330 | NW350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS210 | NW350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Form / Reinforce / Pour Moment Slab - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE530 | MSE570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE500 | MSE530 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE520 | MSE570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Coping - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE570 | MS210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Coping - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE480 | MSE530 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install MSE Wall W-13E - NB: 779+33.94-783+00.00 - Ph1-S1 (Leaveout) | 0 | SUB-ST-MSE | SUB-ST-MSE
NW310 | NW330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS200 | NW330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE480 | MSE520 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install Coping - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE460 | MSE480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Leveling Pad - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE470 | MSE520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Coping - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Install Coping - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE520 | MS200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Install Coping - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
NW300 | NW310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MSE440 | MSE470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Install Coping - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE400 | MSE440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Leveling Pad - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Install MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS190 | NW310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE430 | MSE470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Coping - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Install Coping - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE470 | MS190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Coping - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
NW280 | NW300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS180 | NW300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Form / Reinforce / Pour Moment Slab - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE410 | MSE430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Install Coping - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE390 | MSE410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Install MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE420 | MSE430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Coping - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Coping - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE430 | MS180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Coping - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE430 | STAB230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Coping - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
MSE370 | MSE420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Coping - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE340 | MSE370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
NW270 | NW280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MS170 | NW280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Form / Reinforce / Pour Moment Slab - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE350 | MSE420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Coping - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install Coping - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE420 | MS170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Coping - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE330 | MSE370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE330 | MSE350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install Coping - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE300 | MSE330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS160 | NW270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Form / Reinforce / Pour Moment Slab - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE350 | MS160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Install Coping - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE290 | MSE320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Install Coping - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE260 | MSE290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Leveling Pad - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Install MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS150 | NW250 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Form / Reinforce / Pour Moment Slab - MSE Wall W-4A, W-4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE320 | MS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | Install Coping - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-4A, W-4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE250 | MSE280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install Coping - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE230 | MSE250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Install MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE280 | MS140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Install Coping - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MS130 | NW220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Form / Reinforce / Pour Moment Slab - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE220 | MSE240 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install Coping - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE190 | MSE220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Install MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE240 | MS130 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Install Coping - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
NW190 | NW210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
MSE170 | MSE200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install Coping - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE150 | MSE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Leveling Pad - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Install MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS120 | NW210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Form / Reinforce / Pour Moment Slab - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE160 | MSE200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Coping - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Install Coping - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE200 | MS120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Install Coping - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MS110 | NW190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Form / Reinforce / Pour Moment Slab - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Form / Reinforce / Pour 8' Noise Wall - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | CONCRETE | ST-SOUND
MSE140 | MSE160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Install Coping - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE120 | MSE140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Leveling Pad - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Install MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE160 | MS110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Install Coping - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
MSE110 | MSE130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Install Coping - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE100 | MSE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE130 | MS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Install Coping - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | SUB-ST-MSE | CONCRETE
PILE110 | MSE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | ST-SOLDIER | SUB-ST-MSE
MSE110 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ST-MSE | EW-CEM
PAV480 | ITS310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
GRD310 | ITS310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
PAV460 | ITS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
GRD290 | ITS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
GRD260 | ITS260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
GRD240 | ITS240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
GRD230 | ITS230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
GRD220 | ITS220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
GRD200 | ITS200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
GRD120 | ITS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
PAV330 | ITS120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
GRD100 | ITS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-UT-ITS
PAV300 | ITS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ITS
ITS230 | ITS240 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | 6 | SUB-UT-ITS | SUB-UT-ITS
ITS220 | ITS230 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | 6 | SUB-UT-ITS | SUB-UT-ITS
ITS310 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install MVDS SB-2 Pole & Equipment - SB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS290 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CAB-NB-3 & MVDS NB-2, SB-3 Pole & Equipment - SB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS260 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CAB-SB-1 & MVDS-SB-4 Pole & Equipment - SB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS240 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CAB-NB-4, MVDSNB-3 & SB-5, & DMS SB-1 Poles & Equipment - SB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS230 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CCTV-3, CCTV-2 (Verification) Poles & Equipment - SB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS220 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CAB-NB-5 & MVDS NB-4, SB-6 Poles & Equipment - SB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS200 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CCTV-4 & MVDS NB-5 Poles & Equipment - NB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS120 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Generator & Equipment - NB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
ITS100 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install CCTV-1 Pole & Cabinet / Equipment - NB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ITS
GRD320 | PNT1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | Paint - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD310 | PNT1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | Paint - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD300 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD290 | PNT1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | Paint - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD280 | PNT1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | Paint - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD270 | PNT1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | Paint - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD260 | PNT1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | Paint - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD250 | PNT1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | Paint - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD240 | PNT1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | Paint - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD230 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD220 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD210 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD200 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD190 | PNT1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | Paint - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD180 | PNT1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | Paint - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD170 | PNT1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | Paint - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD160 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD150 | PNT1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | Paint - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD140 | PNT1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | Paint - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD130 | PNT1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | Paint - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PAV330 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-ST-PNT
GRD120 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PAV310 | PNT1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Paint - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-ST-PNT
GRD110 | PNT1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | Paint - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT1210 | PNT1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - SB: 722+83-735+00 - Ph1-S1 | Paint - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1200 | PNT1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - SB: 735+46-746+91 - Ph1-S1 | Paint - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1190 | PNT1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.5 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - SB: 748+30-757+10 - Ph1-S1 | Paint - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1180 | PNT1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - SB: 757+10-759+97 - Ph1-S1 | Paint - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1170 | PNT1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - SB: 761+67-767+00 - Ph1-S1 | Paint - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1160 | PNT1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - SB: 767+00-773+42 - Ph1-S1 | Paint - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1150 | PNT1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - SB: 774+82-780+00 - Ph1-S1 | Paint - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1140 | PNT1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - SB: 780+00-786+69 - Ph1-S1 | Paint - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1130 | PNT1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - SB: 788+09-800+00 - Ph1-S1 | Paint - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1120 | PNT1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - SB: 800+00-813+16 - Ph1-S1 | Paint - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1110 | PNT1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - SB: 815+20-839+61 - Ph1-S1 | Paint - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1100 | PNT1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 839+61.49: Work to Complete Prior to Phase 3 | Paint - NB: 815+20-839+61 - Ph1-S1 | Paint - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1090 | PNT1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 839+61.49: Work To Complete Prior to Phase 3 | Paint - NB: 800+00-813+16 - Ph1-S1 | Paint - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1080 | PNT1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - NB: 788+09-800+00 - Ph1-S1 | Paint - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1070 | PNT1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 813+15.64: Work To Complete Prior to Phase 3 | Paint - NB: 780+00-786+69 - Ph1-S1 | Paint - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1060 | PNT1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - NB: 774+82-780+00 - Ph1-S1 | Paint - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1050 | PNT1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 786+69.29: Work To Complete Prior to Phase 3 | Paint - NB: 767+00-773+42 - Ph1-S1 | Paint - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1040 | PNT1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - NB: 761+67-767+00 - Ph1-S1 | Paint - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1030 | PNT1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 773+41.84: Work To Complete Prior to Phase 3 | Paint - NB: 757+10-759+97 - Ph1-S1 | Paint - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1020 | PNT1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - NB: 748+30-757+10 - Ph1-S1 | Paint - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1010 | PNT1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.4 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 759+97.10: Work To Complete Prior to Phase 3 | Paint - NB: 735+46-746+91 - Ph1-S1 | Paint - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1000 | PNT1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Paint - NB: 709+50-735+00 - Ph1-S1 | Paint - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PAV300 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-ST-PNT
GRD100 | PNT1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 746+91.13: Work To Complete Prior to Phase 3 | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Paint - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
R860 | PNT1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Pour Sidewalk @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | Paint @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-ST-PNT
R840 | PNT1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | Paint @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-ST-PNT
R820 | PNT1450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | Paint @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-ST-PNT
R800 | PNT1440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Pour Sidewalk @ MLK Blvd.- North Side - Ph1-S1-S2 | Paint @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-ST-PNT
R780 | PNT1430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | Paint @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-ST-PNT
PAV280 | PNT1420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Miscellaneous Asphalt Paving @ Floribraska - North Side - Ph1-S1-S2 | Paint @ Floribraska - North Side - Ph1-S1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
R730 | PNT1410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | Paint @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-ST-PNT
R710 | PNT1400 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Pour Sidewalk @ E. Osborne Ave - South Side - Ph1-S1-S1 | Paint @ E. Osborne Ave - South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-ST-PNT
R690 | PNT1390 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Pour Sidewalk @ Chelsea St.- South Side - Ph1-S1-S1 | Paint @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-ST-PNT
R665 | PNT1380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Pour Sidewalk @ MLK Blvd.- South Side - Ph1-S1-S1 | Paint @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-ST-PNT
R645 | PNT1370 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Pour Sidewalk @ East Lake Ave. - South Side - Ph1-S1-S1 | Paint @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-ST-PNT
PAV160 | PNT1360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | Paint @ Floribraska - South Side - Ph1-S1-S1 | 0 | SUB-ASPH | SUB-ST-PNT
PNT1460 | PNT1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Paint @ E. Osborne Ave - North Side - Ph1-S1-S2 | Paint @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1450 | PNT1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Paint @ Chelsea St.- North Side - Ph1-S1-S2 | Paint @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1440 | PNT1450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Paint @ MLK Blvd.- North Side - Ph1-S1-S2 | Paint @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1430 | PNT1440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Paint @ East Lake Ave. - North Side - Ph1-S1-S2 | Paint @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1420 | PNT1430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Paint @ Floribraska - North Side - Ph1-S1-S2 | Paint @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1410 | PNT1420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Paint @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | Paint @ Floribraska - North Side - Ph1-S1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1400 | PNT1410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Paint @ E. Osborne Ave - South Side - Ph1-S1-S1 | Paint @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1390 | PNT1400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Paint @ Chelsea St.- South Side - Ph1-S1-S1 | Paint @ E. Osborne Ave - South Side - Ph1-S1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1380 | PNT1390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Paint @ MLK Blvd.- South Side - Ph1-S1-S1 | Paint @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1370 | PNT1380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Paint @ East Lake Ave. - South Side - Ph1-S1-S1 | Paint @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1360 | PNT1370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Paint @ Floribraska - South Side - Ph1-S1-S1 | Paint @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
GRD330 | PNT1330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Grind Concrete Pavement - I-275 SB / Floribraska Ramp NE - Ph1-S2 | Paint - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 0 | SUB-DGRIND | SUB-ST-PNT
PAV450 | PNT1320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Asphalt Paving - MLK Ramp A - Ph1-S2 | Paint - MLK Ramp A - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV440 | PNT1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Asphalt Paving - MLK Ramp D - Ph1-S2 | Paint - MLK Ramp D - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV400 | PNT1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | Paint - Hillsborough Ramp A - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV390 | PNT1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | Paint - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV350 | PNT1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S2 | Paint - Hillsborough Ramp C1 - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV370 | PNT1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S2 | Paint - Hillsborough Ramp C2 - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV290 | PNT1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | Paint - Hillsborough Ramp B - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV270 | PNT1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Asphalt Paving - MLK Ramp C - Ph1-S2 | Paint - MLK Ramp C - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PAV250 | PNT1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Asphalt Paving - MLK Ramp B - Ph1-S2 | Paint - MLK Ramp B - Ph1-S2 | 0 | SUB-ASPH | SUB-ST-PNT
PNT1320 | PNT1330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Paint - MLK Ramp A - Ph1-S2 | Paint - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1310 | PNT1320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Paint - MLK Ramp D - Ph1-S2 | Paint - MLK Ramp A - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1300 | PNT1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Paint - Hillsborough Ramp A - Ph1-S2 | Paint - MLK Ramp D - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1290 | PNT1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Paint - Hillsborough Ramp D - Ph1-S2 | Paint - Hillsborough Ramp A - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1280 | PNT1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Paint - Hillsborough Ramp C1 - Ph1-S2 | Paint - Hillsborough Ramp D - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1270 | PNT1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Paint - Hillsborough Ramp C2 - Ph1-S2 | Paint - Hillsborough Ramp C1 - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1260 | PNT1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Paint - Hillsborough Ramp B - Ph1-S2 | Paint - Hillsborough Ramp C2 - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1250 | PNT1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Paint - MLK Ramp C - Ph1-S2 | Paint - Hillsborough Ramp B - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1240 | PNT1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Paint - MLK Ramp B - Ph1-S2 | Paint - MLK Ramp C - Ph1-S2 | 0 | SUB-ST-PNT | SUB-ST-PNT
GRD390 | PNT1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | Paint - NB & SB Median: 788+09-813+16 - Ph2 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD380 | PNT1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | Paint - NB & SB Median: 774+82-786+69 - Ph2 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD370 | PNT1500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | Paint - NB & SB Median: 761+67-773+42 - Ph2 | 0 | SUB-DGRIND | SUB-ST-PNT
PAV520 | PNT1490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | Paint - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-ASPH | SUB-ST-PNT
GRD360 | PNT1490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | Paint - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-DGRIND | SUB-ST-PNT
PAV510 | PNT1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | Paint - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-ASPH | SUB-ST-PNT
GRD350 | PNT1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | Paint - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-DGRIND | SUB-ST-PNT
PAV500 | PNT1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | Paint - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-ASPH | SUB-ST-PNT
GRD340 | PNT1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | Paint - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-DGRIND | SUB-ST-PNT
GRD400 | PNT1530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | Paint - NB & SB Median: 815+20-839+61 - Ph2 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT1520 | PNT1530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Paint - NB & SB Median: 788+09-813+16 - Ph2 | Paint - NB & SB Median: 815+20-839+61 - Ph2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1510 | PNT1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Paint - NB & SB Median: 774+82-786+69 - Ph2 | Paint - NB & SB Median: 788+09-813+16 - Ph2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1500 | PNT1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Paint - NB & SB Median: 761+67-773+42 - Ph2 | Paint - NB & SB Median: 774+82-786+69 - Ph2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1490 | PNT1500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Paint - NB & SB Median: 748+30-759+97 - Ph 2 | Paint - NB & SB Median: 761+67-773+42 - Ph2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1480 | PNT1490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Paint - NB & SB Median: 722+83-746+91 - Ph2 | Paint - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1230 | PNT1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Paint - NB & SB Median: 714+00-721+43 - Ph2 | Paint - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-ST-PNT | SUB-ST-PNT
PNT1530 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 815+20-839+61 - Ph2 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1520 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 788+09-813+16 - Ph2 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1510 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 774+82-786+69 - Ph2 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1500 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 761+67-773+42 - Ph2 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1490 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 748+30-759+97 - Ph 2 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1480 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 722+83-746+91 - Ph2 | End of Phase 2 | 0 | SUB-ST-PNT
PNT1230 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Paint - NB & SB Median: 714+00-721+43 - Ph2 | End of Phase 2 | 0 | SUB-ST-PNT
R3940 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Grassing - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-LANDSC
R3930 | R3940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Erosion Protection Mat - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | Grassing - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 0 | SUB-LANDSC | SUB-LANDSC
EGC500 | R3930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Excavate / Grade - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | Erosion Protection Mat - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 0 | EW-SML | SUB-LANDSC
M1900 | R3940 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Start of Phase 1, Stage 2 | Grassing - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 0 |  | SUB-LANDSC
M1900 | R3930 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Start of Phase 1, Stage 2 | Erosion Protection Mat - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 0 |  | SUB-LANDSC
BW1300 | BW1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 815+20-839+61 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | BARRIER
BW1290 | BW1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | BARRIER
BW1280 | BW1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | BARRIER
BW1310 | BASE910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall - NB & SB Median: 815+20-839+61 - Ph2 | Black Base - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | EW-ABC
STAB600 | BW1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Stabilization - NB & SB Median: 815+20-839+61 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-CEM | BARRIER
BW1280 | BW1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | BARRIER
BW1270 | BW1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | BARRIER
BW1290 | BW1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | BARRIER
BW1260 | BW1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | BARRIER
BW1290 | BASE870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | Black Base - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | EW-ABC
STAB590 | BW1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Stabilization - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 788+09-813+16 - Ph2 | 0 | EW-CEM | BARRIER
BW1260 | BW1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | BARRIER
BW1250 | BW1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | BARRIER
BW1270 | BW1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | BARRIER
BW1240 | BW1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | BARRIER
BW1270 | BASE840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | Black Base - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | EW-ABC
STAB580 | BW1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Stabilization - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 774+82-786+69 - Ph2 | 0 | EW-CEM | BARRIER
BW1240 | BW1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | BARRIER
BW1230 | BW1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | BARRIER
BW1250 | BW1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | BARRIER
BW1250 | BASE820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | Black Base - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | EW-ABC
STAB570 | BW1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Stabilization - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | 0 | EW-CEM | BARRIER
BW1220 | BW1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | BARRIER
BW1220 | BW1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | BARRIER
BW1210 | BW1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | BARRIER
BW1200 | BW1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | BARRIER
BW1230 | BASE810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | Black Base - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | EW-ABC
STAB560 | BW1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Stabilization - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-CEM | BARRIER
BW1230 | BW1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | BARRIER
BW1200 | BW1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | 0 | BARRIER | BARRIER
BW1190 | BW1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | 0 | BARRIER | BARRIER
BW1210 | CP540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | 0 | BARRIER | CONCRETE
EGC410 | BW1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-SML | BARRIER
BW1210 | BW1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | BARRIER
BW1180 | BW1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | 0 | BARRIER | BARRIER
BW1210 | BASE800 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | 5 | BARRIER | EW-ABC
STAB550 | BW1210 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 722+83-746+91 - Ph2 | 7 | EW-CEM | BARRIER
BW1180 | BW1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 714+00-721+43 - Ph2 | 0 | BARRIER | BARRIER
BW1190 | BW1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | 0 | BARRIER | BARRIER
BW1190 | BASE780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 714+00-721+43 - Ph2 | Black Base - NB & SB Median: 714+00-721+43 - Ph2 | 0 | BARRIER | EW-ABC
STAB540 | BW1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Stabilization - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall - NB & SB Median: 714+00-721+43 - Ph2 | 0 | EW-CEM | BARRIER
BW1160 | BW1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Form / Reinforce / Pour Barrier Wall Footing - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | BARRIER | BARRIER
EGC390 | BW1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-SML | BARRIER
BW1170 | STAB510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Form / Reinforce / Pour Barrier Wall - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Stabilization - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | BARRIER | EW-CEM
BW1110 | NW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp A (SB: 107+11.78-104+50.80) - Ph1-S2 | 0 | BARRIER | ST-SOUND
BW1100 | BW1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | 0 | BARRIER | BARRIER
EGC380 | NW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Excavate / Grade - MLK Ramp A - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp A (SB: 107+11.78-104+50.80) - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW770 | STAB490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp A (SB: 107+11.78-104+50.80) - Ph1-S2 | Stabilization - MLK Ramp A - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC380 | BW1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Excavate / Grade - MLK Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp A - Ph1-S2 | 0 | EW-SML | BARRIER
BW1050 | NW750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | 0 | BARRIER | ST-SOUND
BW1030 | BW1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | 0 | BARRIER | BARRIER
EGC370 | NW750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Excavate / Grade - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW750 | STAB480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp D - Ph1-S2 | Stabilization - MLK Ramp D - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC370 | BW1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Excavate / Grade - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp D - Ph1-S2 | 0 | EW-SML | BARRIER
BW930 | NW690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp A - Ph1-S2 | 0 | BARRIER | ST-SOUND
BW910 | BW930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | 0 | BARRIER | BARRIER
EGC360 | NW690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp A - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW690 | STAB400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp A - Ph1-S2 | Stabilization - Hillsborough Ramp A - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC360 | BW930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp A - Ph1-S2 | 0 | EW-SML | BARRIER
BW840 | NW640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp D - Ph1-S2 | 0 | BARRIER | ST-SOUND
BW820 | BW840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | 0 | BARRIER | BARRIER
EGC350 | NW640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp D - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW640 | STAB370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp D - Ph1-S2 | Stabilization - Hillsborough Ramp D - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC350 | BW840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp D - Ph1-S2 | 0 | EW-SML | BARRIER
BW680 | NW530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp C1 - Ph1-S2 | 0 |  | ST-SOUND
BW660 | BW680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | 0
EGC330 | NW530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW530 | STAB300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp C1 - Ph1-S2 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC330 | BW680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-SML
BW360 | NW180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | 0 |  | ST-SOUND
BW320 | BW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | 0
EGC590 | NW180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW180 | STAB160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Form / Reinforce / Pour 14' Noise Wall - Hillsborough Ramp B - Ph1-S2 | Stabilization - Hillsborough Ramp B - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC590 | BW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - Hillsborough Ramp B - Ph1-S2 | 0 | EW-SML
BW220 | NW130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | 0 |  | ST-SOUND
BW210 | BW220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | 0
EGC550 | NW130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Excavate / Grade - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW130 | STAB150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp C (NB: 365+01.75-373+45.01) - Ph1-S2 | Stabilization - MLK Ramp C - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC550 | BW220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Excavate / Grade - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp C - Ph1-S2 | 0 | EW-SML
BW170 | NW110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp B (NB: 250+88.27-256+15.55) - Ph1-S2 | 0 |  | ST-SOUND
BW150 | BW170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp B - Ph1-S2 | 0
EGC530 | NW110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Excavate / Grade - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp B (NB: 250+88.27-256+15.55) - Ph1-S2 | 0 | EW-SML | ST-SOUND
NW110 | STAB130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Form / Reinforce / Pour 14' Noise Wall - MLK Ramp B (NB: 250+88.27-256+15.55) - Ph1-S2 | Stabilization - MLK Ramp B - Ph1-S2 | 0 | ST-SOUND | EW-CEM
EGC530 | BW170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Excavate / Grade - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall - MLK Ramp B - Ph1-S2 | 0 | EW-SML
BW1140 | NW680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW1120 | BW1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 38+98.75-44+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
BW1080 | NW650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW1060 | BW1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | BARRIER | BARRIER
NW650 | NW680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW680 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW1080 | BW1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
NW630 | NW650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW650 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW1020 | BW1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | BARRIER | BARRIER
BW1080 | BW1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 44+00.00-48+91.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
BW1020 | NW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW990 | NW600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW980 | BW990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | BARRIER | BARRIER
NW600 | NW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW630 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW630 | STAB450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Stabilization - SB: 757+10-759+97 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW990 | BW1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | BARRIER
BW980 | BW1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | BARRIER
NW560 | NW600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW600 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW600 | STAB450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | Stabilization - SB: 757+10-759+97 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW990 | BW1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | BARRIER
BW960 | NW560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW940 | BW960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 64+06.16-69+52.31 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | BARRIER | BARRIER
BW900 | NW540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW890 | BW900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | BARRIER | BARRIER
BW870 | NW500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW850 | BW870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | BARRIER | BARRIER
NW540 | NW560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW560 | STAB430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW900 | BW960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | BARRIER | BARRIER
NW500 | NW540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW540 | STAB430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW870 | BW900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | BARRIER | BARRIER
BW900 | BW940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | BARRIER | BARRIER
NW490 | NW500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW500 | STAB430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW810 | BW870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | BARRIER | BARRIER
BW870 | BW890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | BARRIER | BARRIER
BW810 | NW490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW800 | BW810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | BARRIER | BARRIER
BW780 | NW470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW770 | BW780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | BARRIER | BARRIER
NW470 | NW490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW490 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 8' Noise Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW780 | BW810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | BARRIER | BARRIER
BW810 | BW850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | BARRIER | BARRIER
BW810 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 77+25.61-79+58.07 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
NW450 | NW470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW470 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW750 | BW780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | BARRIER | BARRIER
BW780 | BW800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | BARRIER | BARRIER
BW780 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 82+99.07-87+69.07 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW750 | NW450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW730 | BW750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
NW410 | NW450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW450 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW690 | BW750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
BW750 | BW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | BARRIER | BARRIER
BW750 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 92+99.11-98+00.00 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW690 | NW410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW670 | BW690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | BARRIER | BARRIER
NW380 | NW410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW410 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW640 | BW690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | BARRIER | BARRIER
BW690 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 98+00.00-103+33.28 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW640 | NW380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW630 | BW640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | BARRIER | BARRIER
NW360 | NW380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW380 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW610 | BW640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | BARRIER | BARRIER
BW640 | BW670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | BARRIER | BARRIER
BW640 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 109+78.31-114+18.91 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW610 | NW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW600 | BW610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | BARRIER | BARRIER
NW340 | NW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW360 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW580 | BW610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | BARRIER | BARRIER
BW610 | BW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | BARRIER | BARRIER
BW570 | BW580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | BARRIER | BARRIER
NW320 | NW340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW340 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW550 | BW580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | BARRIER | BARRIER
BW580 | BW600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Wall - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | BARRIER | BARRIER
BW550 | NW320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW530 | BW550 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 170+00.00-177+80.95 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | 0 | BARRIER | BARRIER
NW290 | NW320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW320 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW510 | BW550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | 0 | BARRIER | BARRIER
BW550 | BW570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 170+00.00-177+80.95 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | BARRIER | BARRIER
BW510 | NW290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW500 | BW510 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 408+39.93-170+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
NW260 | NW290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW290 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW480 | BW510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
BW480 | NW260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW470 | BW480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 150+98.92-155+14.52 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | BARRIER | BARRIER
NW230 | NW260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW260 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW450 | BW480 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | BARRIER | BARRIER
BW480 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 150+98.92-155+14.52 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW450 | NW230 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW440 | BW450 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | BARRIER | BARRIER
NW200 | NW230 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW230 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW230 | STAB250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW420 | BW450 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | BARRIER | BARRIER
BW450 | BW470 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | BARRIER | BARRIER
BW450 | STAB260 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW450 | STAB250 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW420 | NW200 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW410 | BW420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | 0 | BARRIER | BARRIER
NW200 | STAB260 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW200 | STAB250 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW420 | BW440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | BARRIER | BARRIER
BW420 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW420 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 138+14.43-145+55.54 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW390 | NW170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW370 | BW390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | 0 | BARRIER | BARRIER
NW170 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW390 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW330 | NW150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW300 | BW330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 104+06.12-107+60.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | 0 | BARRIER | BARRIER
NW150 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW330 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 104+06.12-107+60.00 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW280 | NW140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | 0 | BARRIER | ST-SOUND
BW270 | BW280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | 0 | BARRIER | BARRIER
NW120 | NW140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour 14' Noise Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | 0 | ST-SOUND | ST-SOUND
NW140 | STAB200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW140 | STAB190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier 14' Noise Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW280 | STAB200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW280 | STAB190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 96+36.16-101+96.12 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW180 | BW200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | 0 | BARRIER | BARRIER
NW120 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour 14' Noise Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW120 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour 14' Noise Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW200 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW200 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 610+36.08-81+47.63 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | BARRIER | EW-CEM
NW100 | STAB170 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour 14' Noise Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
NW100 | STAB180 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour 14' Noise Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | ST-SOUND | EW-CEM
BW120 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW120 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Shoulder Barrier Wall - NB: 606+52.91-610+36.08 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | BARRIER | EW-CEM
B1520 | PNT200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | Paint 100207 - SB: over East Lake - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD510 | PNT200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | Paint 100207 - SB: over East Lake - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
CLK510 | PNT200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | Paint 100207 - SB: over East Lake - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
PNT190 | PNT200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Paint 100204 - SB: over MLK - Ph1-S1 | Paint 100207 - SB: over East Lake - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
CLK500 | PNT190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | Paint 100204 - SB: over MLK - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
B2000 | PNT190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - SB: over MLK - Ph1-S1 | Paint 100204 - SB: over MLK - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD500 | PNT190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | Paint 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT180 | PNT190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | Paint 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
CLK490 | PNT180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
B2480 | PNT180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD490 | PNT180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT170 | PNT180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Paint 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
CLK480 | PNT170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
B2960 | PNT170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD480 | PNT170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT160 | PNT170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
CLK470 | PNT160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
B3440 | PNT160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD470 | PNT160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT150 | PNT160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
GRD460 | PNT150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
B3200 | PNT150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-PNT
CLK460 | PNT150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
PNT140 | PNT150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Paint 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
CLK450 | PNT140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
B2720 | PNT140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD450 | PNT140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT130 | PNT140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | Paint 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
CLK440 | PNT130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Caulk & Seal Joints 100206 - NB: over Chelsea St. - Ph1-S1 | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
B2240 | PNT130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-ST-PNT
GRD440 | PNT130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
PNT120 | PNT130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | Paint 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
GRD430 | PNT120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
B1760 | PNT120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-PNT
CLK430 | PNT120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
PNT110 | PNT120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Paint 100207 - NB: over East Lake - Ph1-S1 | Paint 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
GRD420 | PNT110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | Paint 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
B1470 | PNT110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | Paint 100207 - NB: over East Lake - Ph1-S1 | 0 |  | SUB-ST-PNT
CLK420 | PNT110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Caulk & Seal Joints 100207 - NB: over East Lake - Ph1-S1 | Paint 100207 - NB: over East Lake - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
PNT100 | PNT110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Paint 100201 - NB: over Floribraska - Ph1-S1 | Paint 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-PNT | SUB-ST-PNT
GRD410 | PNT100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | Paint 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-DGRIND | SUB-ST-PNT
BW540 | PNT100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | Paint 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-ST-PNT
CLK410 | PNT100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | Paint 100201 - NB: over Floribraska - Ph1-S1 | 0 | CP-SAW | SUB-ST-PNT
REINF190 | SUPR750 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100204 - SB: over MLK - Ph1-S1 | Set Deck Screed 100204 - SB: over MLK - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF180 | REINF190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100206 - SB: over Chelsea St. - Ph1-S1 | Rebar 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF180 | SUPR720 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100206 - SB: over Chelsea St. - Ph1-S1 | Set Deck Screed 100206 - SB: over Chelsea St. - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF170 | REINF180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Rebar 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF170 | SUPR670 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set Deck Screed 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF160 | REINF170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Rebar 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF160 | SUPR560 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set Deck Screed 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF150 | REINF160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Rebar 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF150 | SUPR480 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set Deck Screed 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF140 | REINF150 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Rebar 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Rebar 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF140 | SUPR430 | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Rebar 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set Deck Screed 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF130 | SUPR340 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100206 - NB: over Chelsea St. - Ph1-S1 | Set Deck Screed 100206 - NB: over Chelsea St. - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF120 | REINF130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Rebar 100204 - NB: over MLK Blvd - Ph1-S1 | Rebar 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF120 | SUPR300 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100204 - NB: over MLK Blvd - Ph1-S1 | Set Deck Screed 100204 - NB: over MLK Blvd - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF110 | REINF120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Rebar 100207 - NB: over East Lake - Ph1-S1 | Rebar 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
REINF110 | SUPR210 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Rebar 100207 - NB: over East Lake - Ph1-S1 | Set Deck Screed 100207 - NB: over East Lake - Ph1-S1 | 1 | SUB-ST-REBAR | ST-BRIDGE-SUP
REINF100 | REINF110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Rebar 100201 - NB: over Floribraska - Ph1-S1 | Rebar 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-REBAR | SUB-ST-REBAR
DEMO1320 | EGC320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Demo Roadway - SB: 709+50-721+43 - Ph1-S1 | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1300 | DEMO1320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Demo Roadway - SB: 722+83-735+00 - Ph1-S1 | Demo Roadway - SB: 709+50-721+43 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1300 | EGC310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Demo Roadway - SB: 722+83-735+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1250 | DEMO1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | Demo Roadway - SB: 722+83-735+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1250 | EGC300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1220 | DEMO1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | Demo Roadway - SB: 735+46-746+91 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1220 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1180 | DEMO1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - SB: 757+10-759+97 - Ph1-S1 | Demo Roadway - SB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1180 | EGC280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Demo Roadway - SB: 757+10-759+97 - Ph1-S1 | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1110 | DEMO1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Demo Roadway - SB: 761+67-767+00 - Ph1-S1 | Demo Roadway - SB: 757+10-759+97 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1110 | EGC260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - SB: 761+67-767+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO1040 | DEMO1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | Demo Roadway - SB: 761+67-767+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO1040 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO960 | DEMO1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - SB: 774+82-780+00 - Ph1-S1 | Demo Roadway - SB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | DEMO
DEMO960 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - SB: 774+82-780+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO910 | DEMO960 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - SB: 780+00-786+69 - Ph1-S1 | Demo Roadway - SB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO910 | EGC240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - SB: 780+00-786+69 - Ph1-S1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO850 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Roadway - SB: 788+09-800+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO790 | DEMO850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Demo Roadway - SB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO790 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO720 | DEMO790 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Demo Roadway - SB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | DEMO
DEMO720 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO660 | DEMO720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Demo Roadway - SB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | DEMO
DEMO660 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO630 | DEMO660 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Demo Roadway - NB: 815+20-839+61 - Ph1-S1 | 0 | DEMO | DEMO
DEMO630 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO580 | DEMO630 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Roadway - NB: 788+09-800+00 - Ph1-S1 | Demo Roadway - NB: 800+00-813+16 - Ph1-S1 | 0 | DEMO | DEMO
DEMO580 | EGC180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Roadway - NB: 788+09-800+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO520 | DEMO580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Demo Roadway - NB: 780+00-786+69 - Ph1-S1 | Demo Roadway - NB: 788+09-800+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO520 | EGC170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Roadway - NB: 780+00-786+69 - Ph1-S1 | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO470 | EGC160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - NB: 774+82-780+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO420 | DEMO470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | Demo Roadway - NB: 774+82-780+00 - Ph1-S1 | 0 | DEMO | DEMO
DEMO420 | EGC150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO360 | DEMO420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | Demo Roadway - NB: 767+00-773+42 - Ph1-S1 | 0 | DEMO | DEMO
DEMO360 | EGC140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Demo Roadway - NB: 761+67-767+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO320 | EGC130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Demo Roadway - NB: 757+10-759+97 - Ph1-S1 | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO290 | DEMO320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Demo Roadway - NB: 748+30-757+10 - Ph1-S1 | Demo Roadway - NB: 757+10-759+97 - Ph1-S1 | 0 | DEMO | DEMO
DEMO290 | EGC120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Roadway - NB: 748+30-757+10 - Ph1-S1 | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO210 | EGC110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | 0 | DEMO | EW-SML
DEMO130 | DEMO210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Roadway - NB: 722+83-735+00 - Ph1-S1 | Demo Roadway - NB: 735+46-746+91 - Ph1-S1 | 0 | DEMO | DEMO
DEMO130 | EGC100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Demo Roadway - NB: 722+83-735+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | 0 | DEMO | EW-SML
LSP170 | LSP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Grassing - SB: 769 - 772 - IPh1 | Grassing - SB: 748 - 751 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP160 | LSP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Grassing - SB: 777 - 781 - IPh1 | Grassing - SB: 769 - 772 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP150 | LSP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Grassing - SB: 801 - 805 - IPh 1 | Grassing - SB: 777 - 781 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP140 | LSP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Grassing - SB: 823 - 827 - IPh1 | Grassing - SB: 801 - 805 - IPh 1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP130 | LSP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Grassing - SB: 835 - 840 - IPh1 | Grassing - SB: 823 - 827 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP120 | LSP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Grassing: NB - NB: 815 - 818 - IPh1 | Grassing - SB: 835 - 840 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP110 | LSP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Grassing - NB: 801 - 805 - IPh1 | Grassing: NB - NB: 815 - 818 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
LSP100 | LSP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Grassing - NB: 737 - 739 - IPh1 | Grassing - NB: 801 - 805 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM170 | EPM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | Erosion Protection Mat - SB: 748 - 751 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM160 | EPM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM150 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM140 | EPM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM130 | EPM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM120 | EPM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM110 | EPM120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EPM100 | EPM110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Erosion Protection Mat - NB: 737 - 739 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
DRGS20 | EPM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | Erosion Protection Mat - SB: 748 - 751 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS10 | EPM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | Erosion Protection Mat - SB: 748 - 751 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM180 | LSP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Erosion Protection Mat - SB: 748 - 751 - IPh1 | Grassing - SB: 748 - 751 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC580 | EPM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | Erosion Protection Mat - SB: 748 - 751 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRGS1180 | EPM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS50 | EPM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS40 | EPM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS30 | EPM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM170 | LSP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | Grassing - SB: 769 - 772 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC570 | EPM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Erosion Protection Mat - SB: 769 - 772 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRGS1230 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS130 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS120 | EPM160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS110 | EPM160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS100 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS90 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS80 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS70 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS65 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS60 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM160 | LSP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | Grassing - SB: 777 - 781 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC560 | EPM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Erosion Protection Mat - SB: 777 - 781 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRGS210 | EPM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS200 | EPM150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS190 | EPM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS180 | EPM150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS170 | EPM150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS160 | EPM150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-142 to S-143 (30") - SB:801 - 802 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS150 | EPM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-142 OF to S-142 (30") - SB:801 - 802 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
DRGS140 | EPM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | DRAIN | SUB-LANDSC
EPM150 | LSP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | Grassing - SB: 801 - 805 - IPh 1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC540 | EPM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Erosion Protection Mat - SB: 801 - 805 - IPh 1 | 0 | EW-SML | SUB-LANDSC
DRGS280 | EPM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS270 | EPM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS260 | EPM140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS250 | EPM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRSG245 | EPM140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM140 | LSP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | Grassing - SB: 823 - 827 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC520 | EPM140 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Erosion Protection Mat - SB: 823 - 827 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRGS300 | EPM130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS295 | EPM130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS290 | EPM130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM130 | LSP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | Grassing - SB: 835 - 840 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC510 | EPM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | Erosion Protection Mat - SB: 835 - 840 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRGS240 | EPM120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS230 | EPM120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRGS220 | EPM120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM120 | LSP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | Grassing: NB - NB: 815 - 818 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC490 | EPM120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | Erosion Protection Mat - NB: 815 - 818 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRG580 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG570 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: CS-1 to S-151 - Lower (18") - NB: 804 - 805 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG560 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-151 OF to S-151 (30") - NB: 804 - 805 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG550 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-150 to S-151 (30") - NB: 804 - 805 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG540 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-145 to S-150 (30") - NB: 801 - 805 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG530 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-144 to S-145 (30") - NB: 801 - 802 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG520 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-144 OF to S-144 (30") - NB: 801 - 802 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM110 | LSP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | Grassing - NB: 801 - 805 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC480 | EPM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | Erosion Protection Mat - NB: 801 - 805 - IPh1 | 0 | EW-SML | SUB-LANDSC
DRG120 | EPM100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Drainage: S-30 to S-30 OUT - Lower (18") - NB: 738 - 739 - IPh1 | Erosion Protection Mat - NB: 737 - 739 - IPh1 | 0 | DRAIN | SUB-LANDSC
DRG110 | EPM100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Drainage: CS-1A to CS-1A OUT (18") - NB: 737 - 738 - IPh1 | Erosion Protection Mat - NB: 737 - 739 - IPh1 | 0 | DRAIN | SUB-LANDSC
EPM100 | LSP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Erosion Protection Mat - NB: 737 - 739 - IPh1 | Grassing - NB: 737 - 739 - IPh1 | 0 | SUB-LANDSC | SUB-LANDSC
EGC470 | EPM100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | Erosion Protection Mat - NB: 737 - 739 - IPh1 | 0 | EW-SML | SUB-LANDSC
BASE950 | CP720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Shoulder Base - NB & SB Median: 815+20-839+61 - Ph2 | Concrete Shoulder - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-ABC | CONCRETE
UDR540 | BASE950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Install Edgedrain - NB & SB Median: 815+20-839+61 - Ph2 | Shoulder Base - NB & SB Median: 815+20-839+61 - Ph2 | 0 | UNDR | EW-ABC
CP700 | UDR540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | Install Edgedrain - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | UNDR
BASE940 | CP710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Shoulder Base - NB & SB Median: 800+00-813+16 - Ph2 | Concrete Shoulder - NB & SB Median: 800+00-813+16 - Ph2 | 0 | EW-ABC | CONCRETE
UDR530 | BASE940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Edgedrain - NB & SB Median: 800+00-813+16 - Ph2 | Shoulder Base - NB & SB Median: 800+00-813+16 - Ph2 | 0 | UNDR | EW-ABC
CP670 | UDR530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | Install Edgedrain - NB & SB Median: 800+00-813+16 - Ph2 | 0 | CONCRETE | UNDR
BASE930 | CP690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Shoulder Base - NB & SB Median: 788+09-800+00 - Ph2 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | 0 | EW-ABC | CONCRETE
UDR520 | BASE930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Edgedrain - NB & SB Median: 788+09-800+00 - Ph2 | Shoulder Base - NB & SB Median: 788+09-800+00 - Ph2 | 0 | UNDR | EW-ABC
CP650 | UDR520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | Install Edgedrain - NB & SB Median: 788+09-800+00 - Ph2 | 0 | CONCRETE | UNDR
BASE920 | CP680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Shoulder Base - NB & SB Median: 780+00-786+69 - Ph2 | Concrete Shoulder - NB & SB Median: 780+00-786+69 - Ph2 | 0 | EW-ABC | CONCRETE
CP630 | UDR510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | Install Edgedrain - NB & SB Median: 780+00-786+69 - Ph2 | 0 | CONCRETE | UNDR
UDR510 | BASE920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Edgedrain - NB & SB Median: 780+00-786+69 - Ph2 | Shoulder Base - NB & SB Median: 780+00-786+69 - Ph2 | 0 | UNDR | EW-ABC
BASE900 | CP660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Shoulder Base - NB & SB Median: 774+82-780+00 - Ph2 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | 0 | EW-ABC | CONCRETE
CP610 | UDR500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | Install Edgedrain - NB & SB Median: 774+82-780+00 - Ph2 | 0 | CONCRETE | UNDR
UDR500 | BASE900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Edgedrain - NB & SB Median: 774+82-780+00 - Ph2 | Shoulder Base - NB & SB Median: 774+82-780+00 - Ph2 | 0 | UNDR | EW-ABC
BASE890 | CP640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Shoulder Base - NB & SB Median: 767+00-773+42 - Ph2 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | 0 | EW-ABC | CONCRETE
CP590 | UDR490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | Install Edgedrain - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE | UNDR
UDR490 | BASE890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Edgedrain - NB & SB Median: 767+00-773+42 - Ph2 | Shoulder Base - NB & SB Median: 767+00-773+42 - Ph2 | 0 | UNDR | EW-ABC
BASE880 | CP620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Shoulder Base - NB & SB Median: 761+67-767+00 - Ph2 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | 0 | EW-ABC | CONCRETE
CP580 | UDR480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | Install Edgedrain - NB & SB Median: 761+67-767+00 - Ph2 | 0 | CONCRETE | UNDR
UDR480 | BASE880 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Edgedrain - NB & SB Median: 761+67-767+00 - Ph2 | Shoulder Base - NB & SB Median: 761+67-767+00 - Ph2 | 0 | UNDR | EW-ABC
CP710 | CP720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Shoulder - NB & SB Median: 800+00-813+16 - Ph2 | Concrete Shoulder - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | CONCRETE
CP720 | GRD400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Shoulder - NB & SB Median: 815+20-839+61 - Ph2 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP720 | SGN2060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Shoulder - NB & SB Median: 815+20-839+61 - Ph2 | Install Signs - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP690 | CP710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | Concrete Shoulder - NB & SB Median: 800+00-813+16 - Ph2 | 0 | CONCRETE | CONCRETE
CP710 | GRD390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 800+00-813+16 - Ph2 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP710 | SGN2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 800+00-813+16 - Ph2 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP680 | CP690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 780+00-786+69 - Ph2 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | 0 | CONCRETE | CONCRETE
CP690 | CP1730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | Cure Concrete - NB & SB Median: 800+00-813+16 - Ph2 | 0 | CONCRETE
CP690 | GRD390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP690 | SGN2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Shoulder - NB & SB Median: 788+09-800+00 - Ph2 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP660 | CP680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | Concrete Shoulder - NB & SB Median: 780+00-786+69 - Ph2 | 0 | CONCRETE | CONCRETE
CP680 | GRD380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 780+00-786+69 - Ph2 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP680 | SGN2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 780+00-786+69 - Ph2 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP640 | CP660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | 0 | CONCRETE | CONCRETE
CP660 | CP1720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | Cure Concrete - NB & SB Median: 780+00-786+69 - Ph2 | 0 | CONCRETE
CP660 | GRD380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP660 | SGN2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Shoulder - NB & SB Median: 774+82-780+00 - Ph2 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP620 | CP640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE | CONCRETE
CP640 | CP1710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | Cure Concrete - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE
CP640 | GRD370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP640 | SGN2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 767+00-773+42 - Ph2 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP600 | CP620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | 0 | CONCRETE | CONCRETE
CP620 | CP1710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | Cure Concrete - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE
CP620 | GRD370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP620 | SGN2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Shoulder - NB & SB Median: 761+67-767+00 - Ph2 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-SIGN
BASE860 | CP600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Shoulder Base - NB & SB Median: 757+10-759+97 - Ph2 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | 0 | EW-ABC | CONCRETE
UDR470 | BASE860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Install Edgedrain - NB & SB Median: 757+10-759+97 - Ph2 | Shoulder Base - NB & SB Median: 757+10-759+97 - Ph2 | 0 | UNDR | EW-ABC
CP570 | UDR470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 757+10-759+97 - Ph2 | Install Edgedrain - NB & SB Median: 757+10-759+97 - Ph2 | 0 | CONCRETE | UNDR
CP600 | CP1700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | Cure Concrete - NB & SB Median: 757+10-759+97 - Ph2 | 0 | CONCRETE
CP600 | GRD360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Shoulder - NB & SB Median: 757+10-759+97 - Ph2 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | CONCRETE | SUB-DGRIND
BASE690 | CP520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Shoulder Base - SB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR380 | BASE690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Edgedrain - SB: 757+10-759+97 - Ph1-S1 | Shoulder Base - SB: 757+10-759+97 - Ph1-S1 | 0 | UNDR | EW-ABC
CP410 | UDR380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | Install Edgedrain - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE680 | CP510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Shoulder Base - SB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR360 | BASE680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Edgedrain - SB: 761+67-767+00 - Ph1-S1 | Shoulder Base - SB: 761+67-767+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP400 | UDR360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Install Edgedrain - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE650 | CP500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Shoulder Base - SB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR350 | BASE650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Edgedrain - SB: 767+00-773+42 - Ph1-S1 | Shoulder Base - SB: 767+00-773+42 - Ph1-S1 | 0 | UNDR | EW-ABC
CP380 | UDR350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Install Edgedrain - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE620 | CP480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Shoulder Base - SB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR330 | BASE620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Edgedrain - SB: 774+82-780+00 - Ph1-S1 | Shoulder Base - SB: 774+82-780+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP370 | UDR330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | Install Edgedrain - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE600 | CP450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Shoulder Base - SB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR320 | BASE600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Edgedrain - SB: 780+00-786+69 - Ph1-S1 | Shoulder Base - SB: 780+00-786+69 - Ph1-S1 | 0 | UNDR | EW-ABC
CP360 | UDR320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Install Edgedrain - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE590 | CP420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Shoulder Base - SB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR310 | BASE590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Edgedrain - SB: 788+09-800+00 - Ph1-S1 | Shoulder Base - SB: 788+09-800+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP340 | UDR310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Install Edgedrain - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE520 | CP390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Shoulder Base - SB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR300 | BASE520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Edgedrain - SB: 800+00-813+16 - Ph1-S1 | Shoulder Base - SB: 800+00-813+16 - Ph1-S1 | 0 | UNDR | EW-ABC
CP320 | UDR300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Install Edgedrain - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE510 | CP330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Shoulder Base - SB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR290 | BASE510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - SB: 815+20-839+61 - Ph1-S1 | Shoulder Base - SB: 815+20-839+61 - Ph1-S1 | 0 | UNDR | EW-ABC
CP310 | UDR290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Install Edgedrain - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE460 | CP300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Shoulder Base - NB: 827+00-839+61 - Ph1-S1 | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR270 | BASE460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 827+00-839+61 - Ph1-S1 | Shoulder Base - NB: 827+00-839+61 - Ph1-S1 | 0 | UNDR | EW-ABC
CP280 | UDR270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Install Edgedrain - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE440 | CP290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Shoulder Base - NB: 815+20-827+00 - Ph1-S1 | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR250 | BASE440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Edgedrain - NB: 815+20-827+00 - Ph1-S1 | Shoulder Base - NB: 815+20-827+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP260 | UDR250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Install Edgedrain - NB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE420 | CP270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Shoulder Base - NB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR240 | BASE420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Edgedrain - NB: 800+00-813+16 - Ph1-S1 | Shoulder Base - NB: 800+00-813+16 - Ph1-S1 | 0 | UNDR | EW-ABC
CP240 | UDR240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Install Edgedrain - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE380 | CP250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Shoulder Base - NB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR220 | BASE380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Edgedrain - NB: 788+09-800+00 - Ph1-S1 | Shoulder Base - NB: 788+09-800+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP220 | UDR220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Install Edgedrain - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE360 | CP230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Shoulder Base - NB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR200 | BASE360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Edgedrain - NB: 780+00-786+69 - Ph1-S1 | Shoulder Base - NB: 780+00-786+69 - Ph1-S1 | 0 | UNDR | EW-ABC
CP190 | UDR200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | Install Edgedrain - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE330 | CP210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Shoulder Base - NB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR190 | BASE330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Edgedrain - NB: 774+82-780+00 - Ph1-S1 | Shoulder Base - NB: 774+82-780+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP160 | UDR190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Install Edgedrain - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE300 | CP200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Shoulder Base - NB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | CONCRETE
UDR180 | BASE300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Edgedrain - NB: 767+00-773+42 - Ph1-S1 | Shoulder Base - NB: 767+00-773+42 - Ph1-S1 | 0 | UNDR | EW-ABC
CP150 | UDR180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Install Edgedrain - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE290 | CP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Shoulder Base - NB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
CP140 | UDR170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | Install Edgedrain - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | UNDR
UDR170 | BASE290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Edgedrain - NB: 761+67-767+00 - Ph1-S1 | Shoulder Base - NB: 761+67-767+00 - Ph1-S1 | 0 | UNDR | EW-ABC
BASE280 | CP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Shoulder Base - NB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | CONCRETE
CP130 | UDR160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Install Edgedrain - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | UNDR
UDR160 | BASE280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Edgedrain - NB: 757+10-759+97 - Ph1-S1 | Shoulder Base - NB: 757+10-759+97 - Ph1-S1 | 0 | UNDR | EW-ABC
B4690 | SUBS1340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | Strip Forms End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1320 | B4690 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | Cure End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4680 | SUBS1210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | Strip Forms Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1190 | B4680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | Cure Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4670 | SUBS1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | Strip Forms Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1170 | B4670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | Cure Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1340 | BBM190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1210 | BBM190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1200 | BBM190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B4630 | SUBS1370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | Strip Forms End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1360 | B4630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | Cure End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4620 | SUBS1150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | Strip Forms Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1120 | B4620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | Cure Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4610 | SUBS1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | Strip Forms Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1110 | B4610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | Cure Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1370 | BBM190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1150 | SUBS1190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1140 | SUBS1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1350 | SUBS1360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1080 | SUBS1120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1160 | SUBS1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1070 | SUBS1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4570 | SUBS1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Strip Forms End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1290 | B4570 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Cure End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4560 | SUBS1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1130 | B4560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Cure Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4550 | SUBS1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1090 | B4550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Cure Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1310 | BBM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1180 | BBM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1160 | BBM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1080 | SUBS1130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1070 | SUBS1090 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4510 | SUBS1350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Strip Forms End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1330 | B4510 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Cure End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4500 | SUBS1080 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1030 | B4500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Cure Pier #3 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4490 | SUBS1070 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1020 | B4490 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | Cure Pier #2 Column 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1350 | BBM180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1100 | SUBS1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1060 | SUBS1090 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4450 | SUBS1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1260 | B4450 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4440 | SUBS1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1050 | B4440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4430 | SUBS1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1000 | B4430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1240 | SUBS1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
R830 | SUBS1270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
SUBS1270 | BBM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
PILE290 | SUBS1270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
SUBS1100 | BBM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1060 | BBM170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1010 | SUBS1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS970 | SUBS1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4390 | SUBS1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1280 | B4390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4380 | SUBS1010 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS950 | B4380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #3 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4370 | SUBS970 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS930 | B4370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #2 Column 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1300 | BBM170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1250 | SUBS1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS1040 | SUBS1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS960 | SUBS980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4320 | SUBS1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1220 | B4320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4310 | SUBS1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS980 | B4310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4300 | SUBS990 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS910 | B4300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4290 | SUBS960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS890 | B4290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1240 | BBM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS1040 | BBM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS990 | BBM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS960 | BBM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS940 | SUBS980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS880 | SUBS910 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS860 | SUBS890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS860 | SUBS900 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4240 | SUBS1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS1230 | B4240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4230 | SUBS940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS900 | B4230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #4 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4220 | SUBS880 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS820 | B4220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #3 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4210 | SUBS860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS810 | B4210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS1250 | BBM160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS750 | SUBS1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS920 | SUBS1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS830 | SUBS890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS740 | SUBS810 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS780 | SUBS800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4160 | SUBS920 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS850 | B4160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4150 | SUBS870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS800 | B4150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4140 | SUBS830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS760 | B4140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4130 | SUBS780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS720 | B4130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS920 | BBM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS870 | BBM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS830 | BBM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS780 | BBM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS770 | SUBS800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS740 | SUBS760 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS710 | SUBS720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS710 | SUBS730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Strip Forms Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B4080 | SUBS750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Cure End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS700 | B4080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4070 | SUBS770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Cure Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS730 | B4070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #4 | Form / Reinforce / Pour Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #4 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4060 | SUBS740 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS680 | B4060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4050 | SUBS710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Strip Forms Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS670 | B4050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Cure Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS750 | BBM150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS650 | SUBS720 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS840 | SUBS850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS690 | SUBS700 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Strip Forms End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS600 | SUBS670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS650 | BBM140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B4010 | SUBS840 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Strip Forms End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS790 | B4010 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B4000 | SUBS660 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS630 | B4000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3990 | SUBS650 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS620 | B3990 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS840 | BBM140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS660 | BBM140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS610 | SUBS630 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS600 | SUBS620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3950 | SUBS690 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Strip Forms End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS640 | B3950 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3940 | SUBS610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS570 | B3940 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3930 | SUBS600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Strip Forms Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS560 | B3930 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Cure Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS690 | BBM140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS520 | SUBS570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS510 | SUBS560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3890 | SUBS530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Strip Forms End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS470 | B3890 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Cure End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3880 | SUBS590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS550 | B3880 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Cure Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3870 | SUBS580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS540 | B3870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Cure Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS530 | BBM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS590 | BBM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS580 | BBM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS520 | SUBS550 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS510 | SUBS540 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3830 | SUBS500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Strip Forms End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
B3820 | SUBS520 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS460 | B3820 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Cure Pier #3 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS430 | B3830 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Cure End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3810 | SUBS510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Strip Forms Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS450 | B3810 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | Cure Pier #2 Column 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS500 | BBM130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS440 | SUBS470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS480 | SUBS540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3770 | SUBS440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Strip Forms End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS400 | B3770 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Cure End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3760 | SUBS490 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Strip Forms Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS420 | B3760 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Cure Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3750 | SUBS480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Strip Forms Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS410 | B3750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Cure Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS440 | BBM120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS490 | BBM120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS480 | BBM120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS390 | SUBS420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS380 | SUBS410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3710 | SUBS320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Strip Forms End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS240 | B3710 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Cure End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3700 | SUBS390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | Strip Forms Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS340 | B3700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | Cure Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3690 | SUBS380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | Strip Forms Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS330 | B3690 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | Cure Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS320 | BBM120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B3670 | SUBS370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | Strip Forms End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS310 | B3670 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | Cure End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS370 | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS360 | SUBS420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS350 | SUBS410 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS270 | SUBS330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS280 | SUBS340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3650 | SUBS230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | Strip Forms End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS200 | B3650 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | Cure End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS230 | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B3620 | SUBS360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | Strip Forms Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS300 | B3620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | Cure Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3610 | SUBS350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | Strip Forms Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS290 | B3610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | Cure Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS360 | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS350 | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Strip Forms Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B3590 | SUBS280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | Strip Forms Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS220 | B3590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | Cure Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB
B3570 | SUBS270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | Strip Forms Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS210 | B3570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | Cure Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS280 | SUBS300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS270 | SUBS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS140 | SUBS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Strip Forms End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3550 | SUBS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Cure End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | Strip Forms End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS130 | B3550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | Cure End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS170 | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B3530 | SUBS140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Cure End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | Strip Forms End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS100 | B3530 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | Cure End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS140 | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS260 | SUBS300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS160 | SUBS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
SUBS150 | SUBS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #2 Column 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3510 | SUBS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Cure Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | Strip Forms Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS190 | B3510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | Cure Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS260 | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
B3490 | SUBS250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Cure Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | Strip Forms Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS180 | B3490 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | Cure Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS250 | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Strip Forms Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BEAM
SUBS150 | SUBS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Strip Forms Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3470 | SUBS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Cure Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | Strip Forms Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS120 | B3470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Form / Reinforce / Pour Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | Cure Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB
SUBS160 | SUBS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Strip Forms Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB | ST-BRIDGE-SUB
B3450 | SUBS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Cure Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | Strip Forms Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUBS110 | B3450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Form / Reinforce / Pour Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | Cure Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUB
LTG30 | EL550 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL540 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL530 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL520 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL510 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Procurement: Lighting | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL500 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL490 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Procurement: Lighting | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL480 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Procurement: Lighting | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL460 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Procurement: Lighting | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL450 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Procurement: Lighting | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL440 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Procurement: Lighting | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Procurement: Lighting | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL420 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Procurement: Lighting | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL410 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Procurement: Lighting | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL400 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Procurement: Lighting | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL390 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Procurement: Lighting | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Procurement: Lighting | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL370 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Procurement: Lighting | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Procurement: Lighting | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Procurement: Lighting | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL340 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Procurement: Lighting | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | 0 |  | SUB-UT-ELEC
LTG30 | EL330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: Lighting | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-UT-ELEC
PAV490 | EL550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
PAV480 | EL540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
PAV470 | EL530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
EL320 | EL550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL310 | EL540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL300 | EL530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
PAV460 | EL520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
CP520 | EL510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL290 | EL520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL280 | EL510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP510 | EL500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP500 | EL490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL270 | EL500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL260 | EL490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP480 | EL480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP450 | EL470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL240 | EL470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP420 | EL460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP390 | EL450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL230 | EL460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL220 | EL450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL210 | EL440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP350 | EL440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP330 | EL440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL440 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL450 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL460 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL470 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL480 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL490 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL500 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL510 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL520 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL530 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL540 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL550 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL540 | EL550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | Install Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL530 | EL540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | Install Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL520 | EL530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | Install Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL510 | EL520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | Install Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL500 | EL510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | Install Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL490 | EL500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | Install Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL480 | EL490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | Install Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL470 | EL480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | Install Lighting - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL460 | EL470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | Install Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL450 | EL460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | Install Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL440 | EL450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | Install Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL430 | EL440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | Install Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL430 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
CP290 | EL430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP300 | EL430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL200 | EL430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL420 | EL430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | Install Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP270 | EL420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP250 | EL410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL190 | EL420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL180 | EL410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL420 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL410 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL410 | EL420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | Install Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL400 | EL410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | Install Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP230 | EL400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP210 | EL390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL400 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL390 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL380 | EL390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | Install Lighting - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL380 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL370 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
CP200 | EL380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
CP180 | EL370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
EL150 | EL380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL140 | EL370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL370 | EL380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | Install Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL360 | EL370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | Install Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL340 | EL350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
CP170 | EL360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-UT-ELEC
PAV330 | EL350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
EL130 | EL360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 757+10-759+97 - Ph1-S1 | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL120 | EL350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL360 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 757+10-759+97 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL350 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL340 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
EL330 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-UT-ELEC
PAV310 | EL340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
EL330 | EL340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | Install Lighting - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
PAV300 | EL330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-UT-ELEC
EL100 | EL330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | Install Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
SGN2080 | SGN60 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | Review & Approve Shop Drawings / Submittals: Sign Foundations (Drilled Shafts) (Duration = 25 Calendar Days) | Procurement: Sign Foundations (Drilled Shafts) | 0
SGN2070 | SGN2080 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | Prepare Shop Drawings / Submittals: Sign Foundations (Drilled Shafts) | Review & Approve Shop Drawings / Submittals: Sign Foundations (Drilled Shafts) (Duration = 25 Calendar Days) | 0
MS-LNTP | SGN2070 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | Notice to Proceed | Prepare Shop Drawings / Submittals: Sign Foundations (Drilled Shafts) | 10
SUPR760 | SUPR770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Pour Deck 100204 - SB: over MLK - Ph1-S1 | Form / SIP / Reinforce / Pour Replacement Deck 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
GRD500 | GRD510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
CLK500 | CLK510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK490 | CLK500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK480 | CLK490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK470 | CLK480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK460 | CLK470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK450 | CLK460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK440 | CLK450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Caulk & Seal Joints 100206 - NB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK430 | CLK440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | Caulk & Seal Joints 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK420 | CLK430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Caulk & Seal Joints 100207 - NB: over East Lake - Ph1-S1 | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK410 | CLK420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | Caulk & Seal Joints 100207 - NB: over East Lake - Ph1-S1 | 0 | CP-SAW | CP-SAW
GRD490 | GRD500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD480 | GRD490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD470 | GRD480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD460 | GRD470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD450 | GRD460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD440 | GRD450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD430 | GRD440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD420 | GRD430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD410 | GRD420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
CLK510 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B1510 | GRD510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - SB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | 0 |  | SUB-DGRIND
GRD510 | CLK510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - SB: over East Lake - Ph1-S1 | Caulk & Seal Joints 100207 - SB: over East Lake - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK500 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B1990 | GRD500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Approach Slabs Cure 100204 - SB: over MLK - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | 0 |  | SUB-DGRIND
B1970 | GRD500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - SB: over MLK - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | 0 |  | SUB-DGRIND
GRD500 | CLK500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - SB: over MLK - Ph1-S1 | Caulk & Seal Joints 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK490 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B2470 | GRD490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-DGRIND
B2450 | GRD490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-DGRIND
GRD490 | CLK490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - SB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK480 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B2950 | GRD480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
B2930 | GRD480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
GRD480 | CLK480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Caulk & Seal Joints 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK470 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B3430 | GRD470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Approach Slabs Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
B3410 | GRD470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
GRD470 | CLK470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK460 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B3190 | GRD460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Approach Slabs Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
B3170 | GRD460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
GRD460 | CLK460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Grind & Grove Concrete Pavement 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Caulk & Seal Joints 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK450 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B2710 | GRD450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
B2690 | GRD450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-DGRIND
GRD450 | CLK450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Grind & Grove Concrete Pavement 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Caulk & Seal Joints 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
B2230 | GRD440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-DGRIND
B2210 | GRD440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-DGRIND
GRD440 | CLK440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Grind & Grove Concrete Pavement 100206 - NB: over Chelsea St. - Ph1-S1 | Caulk & Seal Joints 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK430 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B1750 | GRD430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Approach Slabs Cure 100204 - NB: over MLK Blvd - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-DGRIND
B1730 | GRD430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - NB: over MLK Blvd - Ph1-S1 | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-DGRIND
GRD430 | CLK430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Grind & Grove Concrete Pavement 100204 - NB: over MLK Blvd - Ph1-S1 | Caulk & Seal Joints 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK420 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100207 - NB: over East Lake - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
B1460 | GRD420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Approach Slabs Cure 100207 - NB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | 0 |  | SUB-DGRIND
B1440 | GRD420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - NB: over East Lake - Ph1-S1 | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | 0 |  | SUB-DGRIND
GRD420 | CLK420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Grind & Grove Concrete Pavement 100207 - NB: over East Lake - Ph1-S1 | Caulk & Seal Joints 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CLK410 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
GRD410 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-DGRIND
B1220 | GRD410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Approach Slabs Cure 100201 - NB: over Floribraska - Ph1-S1 | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-DGRIND
B1200 | GRD410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Deck Cure 100201 - NB: over Floribraska - Ph1-S1 | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-DGRIND
GRD410 | CLK410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Grind & Grove Concrete Pavement 100201 - NB: over Floribraska - Ph1-S1 | Caulk & Seal Joints 100201 - NB: over Floribraska - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
BASE770 | PAV490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Shoulder Base - SB: 709+50-721+43 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR430 | BASE770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Edgedrain - SB: 709+50-721+43 - Ph1-S1 | Shoulder Base - SB: 709+50-721+43 - Ph1-S1 | 0 | UNDR | EW-ABC
CP490 | UDR430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | Install Edgedrain - SB: 709+50-721+43 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE760 | PAV480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Shoulder Base - SB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR420 | BASE760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Edgedrain - SB: 722+83-735+00 - Ph1-S1 | Shoulder Base - SB: 722+83-735+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP460 | UDR420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | Install Edgedrain - SB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE750 | PAV470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Shoulder Base - SB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR410 | BASE750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Edgedrain - SB: 735+46-746+91 - Ph1-S1 | Shoulder Base - SB: 735+46-746+91 - Ph1-S1 | 0 | UNDR | EW-ABC
CP440 | UDR410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Install Edgedrain - SB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE730 | PAV460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Shoulder Base - SB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR390 | BASE730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Edgedrain - SB: 748+30-757+10 - Ph1-S1 | Shoulder Base - SB: 748+30-757+10 - Ph1-S1 | 0 | UNDR | EW-ABC
CP430 | UDR390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Install Edgedrain - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE270 | PAV330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Shoulder Base - NB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR150 | BASE270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Edgedrain - NB: 748+30-757+10 - Ph1-S1 | Shoulder Base - NB: 748+30-757+10 - Ph1-S1 | 0 | UNDR | EW-ABC
CP120 | UDR150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | Install Edgedrain - NB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE250 | PAV310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Shoulder Base - NB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR140 | BASE250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Install Edgedrain - NB: 735+46-746+91 - Ph1-S1 | Shoulder Base - NB: 735+46-746+91 - Ph1-S1 | 0 | UNDR | EW-ABC
CP110 | UDR140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | Install Edgedrain - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | UNDR
BASE210 | PAV300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Shoulder Base - NB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
UDR130 | BASE210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Edgedrain - NB: 722+83-735+00 - Ph1-S1 | Shoulder Base - NB: 722+83-735+00 - Ph1-S1 | 0 | UNDR | EW-ABC
CP100 | UDR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | Install Edgedrain - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | UNDR
DRG2570 | R610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Drainage: S-8 to S-7 (24") - Floribraska - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | 0 | DRAIN | ST-CIP
DRG2560 | DRG2570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Drainage: S-9 to S-8 (24") - Floribraska - Ph1-S1-S1 | Drainage: S-8 to S-7 (24") - Floribraska - Ph1-S1-S1 | 0 | DRAIN | DRAIN
DEMO120 | DRG2560 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Demo Existing Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | Drainage: S-9 to S-8 (24") - Floribraska - Ph1-S1-S1 | 0 | DEMO | DRAIN
DRG2550 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to S-1 (18") - SB: 715-717 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG1010 | EL300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | SUB-UT-ELEC
DRG2540 | DRG2550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | Drainage: S-4 to S-1 (18") - SB: 715-717 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG2550 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Drainage: S-4 to S-1 (18") - SB: 715-717 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG2540 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG2530 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG2520 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG2510 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG2500 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC320 | DRG2500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG2530 | DRG2540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | Drainage: S-4 to Existing (18") - SB: 716-718 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG2520 | DRG2530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | Drainage: S-3 to S-2 (14"x23") - SB: 716-717 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG2510 | DRG2520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | Drainage: S-5 to S-3 (14"x23") - SB: 716-718 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG2500 | DRG2510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | Drainage: S-5 to S-6 to Existing (14"x23" & 15") - SB: 717-718 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1010 | DRG2500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | Drainage: S-5 to Existing (24") - SB: 717-718 - Ph1-S1 | 0 | DRAIN | DRAIN
DRGS10 | DRGS20 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | 0 | DRAIN | DRAIN
DRGS1180 | DRGS10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | 0 | DRAIN | DRAIN
DRGS1230 | DRGS30 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | 0 | DRAIN | DRAIN
DRGS210 | DRGS60 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS280 | DRGS140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | 0 | DRAIN | DRAIN
DRGS300 | DRSG245 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | 0 | DRAIN | DRAIN
DRGS240 | DRGS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | 0 | DRAIN | DRAIN
DRG580 | DRGS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | 0 | DRAIN | DRAIN
DRG570 | DRG580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: CS-1 to S-151 - Lower (18") - NB: 804 - 805 - IPh1 | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | 0 | DRAIN | DRAIN
DRG560 | DRG570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-151 OF to S-151 (30") - NB: 804 - 805 - IPh1 | Drainage: CS-1 to S-151 - Lower (18") - NB: 804 - 805 - IPh1 | 0 | DRAIN | DRAIN
DRG550 | DRG560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-150 to S-151 (30") - NB: 804 - 805 - IPh1 | Drainage: S-151 OF to S-151 (30") - NB: 804 - 805 - IPh1 | 0 | DRAIN | DRAIN
DRG540 | DRG550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-145 to S-150 (30") - NB: 801 - 805 - IPh1 | Drainage: S-150 to S-151 (30") - NB: 804 - 805 - IPh1 | 0 | DRAIN | DRAIN
DRG530 | DRG540 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-144 to S-145 (30") - NB: 801 - 802 - IPh1 | Drainage: S-145 to S-150 (30") - NB: 801 - 805 - IPh1 | 0 | DRAIN | DRAIN
DRG520 | DRG530 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Drainage: S-144 OF to S-144 (30") - NB: 801 - 802 - IPh1 | Drainage: S-144 to S-145 (30") - NB: 801 - 802 - IPh1 | 0 | DRAIN | DRAIN
DRG2480 | DRG2490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-243 to S-244 (18") - NB & SB Median: 831-833 - Ph2 | Drainage: Existing to S-304 to S-306 (18") - NB & SB Median: 835-838 - Ph2 | 0 | DRAIN | DRAIN
DRG2470 | DRG2480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-241 to S-243 (18") - NB & SB Median: 830-832 - Ph2 | Drainage: S-243 to S-244 (18") - NB & SB Median: 831-833 - Ph2 | 0 | DRAIN | DRAIN
DRG2460 | DRG2470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-238 to S-241 (18") - NB & SB Median: 829-831 - Ph2 | Drainage: S-241 to S-243 (18") - NB & SB Median: 830-832 - Ph2 | 0 | DRAIN | DRAIN
DRG2450 | DRG2460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-236 to S-238 (18") - NB & SB Median: 828-830 - Ph2 | Drainage: S-238 to S-241 (18") - NB & SB Median: 829-831 - Ph2 | 0 | DRAIN | DRAIN
DRG2440 | DRG2450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-233 to S-236 (18") - NB & SB Median: 828-829 - Ph2 | Drainage: S-236 to S-238 (18") - NB & SB Median: 828-830 - Ph2 | 0 | DRAIN | DRAIN
DRG2430 | DRG2440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-230 to S-233 (18") - NB & SB Median: 827-828 - Ph2 | Drainage: S-233 to S-236 (18") - NB & SB Median: 828-829 - Ph2 | 0 | DRAIN | DRAIN
DRG2420 | DRG2430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-227 to S-230 (18") - NB & SB Median: 826-828 - Ph2 | Drainage: S-230 to S-233 (18") - NB & SB Median: 827-828 - Ph2 | 0 | DRAIN | DRAIN
DRG2410 | DRG2420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-230 to Existing (36") - NB & SB Median: 827-828 - Ph2 | Drainage: S-227 to S-230 (18") - NB & SB Median: 826-828 - Ph2 | 0 | DRAIN | DRAIN
DRG2400 | DRG2410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-223 to S-225 (18") - NB & SB Median: 824-825 - Ph2 | Drainage: S-230 to Existing (36") - NB & SB Median: 827-828 - Ph2 | 0 | DRAIN | DRAIN
DRG2390 | DRG2400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-222 to S-223 (18") - NB & SB Median: 824-825 - Ph2 | Drainage: S-223 to S-225 (18") - NB & SB Median: 824-825 - Ph2 | 0 | DRAIN | DRAIN
DRG2380 | DRG2390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-219 to S-222 (18") - NB & SB Median: 823-824 - Ph2 | Drainage: S-222 to S-223 (18") - NB & SB Median: 824-825 - Ph2 | 0 | DRAIN | DRAIN
DRG2370 | DRG2380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-212 to S-219 (18") - NB & SB Median: 822-823 - Ph2 | Drainage: S-219 to S-222 (18") - NB & SB Median: 823-824 - Ph2 | 0 | DRAIN | DRAIN
DRG2360 | DRG2370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | Drainage: S-212 to S-219 (18") - NB & SB Median: 822-823 - Ph2 | 0 | DRAIN | DRAIN
DRG2350 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: Existing to S-160 to S-163 (18") - NB & SB Median: 804-806 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DRAIN | DRAIN
DRG2340 | DRG2350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-152 to S-158 (24") - NB & SB Median: 804-806 - Ph2 | Drainage: Existing to S-160 to S-163 (18") - NB & SB Median: 804-806 - Ph2 | 0 | DRAIN | DRAIN
DRG2330 | DRG2340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-148 to S-152 (18") - NB & SB Median: 803-805 - Ph2 | Drainage: S-152 to S-158 (24") - NB & SB Median: 804-806 - Ph2 | 0 | DRAIN | DRAIN
DRG2320 | DRG2330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-147 to S-148 (18") - NB & SB Median: 802-804 - Ph2 | Drainage: S-148 to S-152 (18") - NB & SB Median: 803-805 - Ph2 | 0 | DRAIN | DRAIN
DRG2310 | DRG2320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-140 to S-147 (18") - NB & SB Median: 801-803 - Ph2 | Drainage: S-147 to S-148 (18") - NB & SB Median: 802-804 - Ph2 | 0 | DRAIN | DRAIN
DRG2300 | DRG2310 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-141 to S-140 (18") - NB & SB Median: 800-801 - Ph2 | Drainage: S-140 to S-147 (18") - NB & SB Median: 801-803 - Ph2 | 0 | DRAIN | DRAIN
DRG2280 | DRG2290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-137 to S-138 (18") - NB & SB Median: 799-800 - Ph2 | Drainage: S-138 to S-141 (18") - NB & SB Median: 799-801 - Ph2 | 0 | DRAIN | DRAIN
DRG2270 | DRG2280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-134 to S-137 (18") - NB & SB Median: 798-800 - Ph2 | Drainage: S-137 to S-138 (18") - NB & SB Median: 799-800 - Ph2 | 0 | DRAIN | DRAIN
DRG2260 | DRG2270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-131 to S-134 (18") - NB & SB Median: 797-799 - Ph2 | Drainage: S-134 to S-137 (18") - NB & SB Median: 798-800 - Ph2 | 0 | DRAIN | DRAIN
DRG2250 | DRG2260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-130 to S-131 (18") - NB & SB Median: 796-798 - Ph2 | Drainage: S-131 to S-134 (18") - NB & SB Median: 797-799 - Ph2 | 0 | DRAIN | DRAIN
DRG2240 | DRG2250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-127 to S-130 (18") - NB & SB Median: 795-797 - Ph2 | Drainage: S-130 to S-131 (18") - NB & SB Median: 796-798 - Ph2 | 0 | DRAIN | DRAIN
DRG2230 | DRG2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | Drainage: S-127 to S-130 (18") - NB & SB Median: 795-797 - Ph2 | 0 | DRAIN | DRAIN
DRG2220 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-120 to Existing (15") - NB & SB Median: 784-785 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DRAIN | DRAIN
DRG2210 | DRG2220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-111 to S-116 (18") - NB & SB Median: 781-782 - Ph2 | Drainage: S-120 to Existing (15") - NB & SB Median: 784-785 - Ph2 | 0 | DRAIN | DRAIN
DRG2200 | DRG2210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-105 to S-111 to Existing (18" & 15") - NB & SB Median: 780-782 - Ph2 | Drainage: S-111 to S-116 (18") - NB & SB Median: 781-782 - Ph2 | 0 | DRAIN | DRAIN
DRG2190 | EGC440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | 0 | DRAIN | EW-SML
DRG2170 | EGC430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-70 to S-72 (18") - NB & SB Median: 766-767 - Ph2 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | 0 | DRAIN | EW-SML
DRG2160 | EGC430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | 0 | DRAIN | EW-SML
DRG2130 | DRG2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Drainage: S-35 to S-38 (15") - NB & SB Median: 744-745 - Ph2 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | 0 | DRAIN | DRAIN
DRG2120 | DRG2130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-35 to Existing (15") - NB & SB Median: 744-745 - Ph2 | Drainage: S-35 to S-38 (15") - NB & SB Median: 744-745 - Ph2 | 0 | DRAIN | DRAIN
DRG2110 | DRG2120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (18") - NB & SB Median: 739-740 - Ph2 | Drainage: S-35 to Existing (15") - NB & SB Median: 744-745 - Ph2 | 0 | DRAIN | DRAIN
DRG2100 | DRG2110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (24") - NB & SB Median: 739-740 - Ph2 | Drainage: S-32 to Existing (18") - NB & SB Median: 739-740 - Ph2 | 0 | DRAIN | DRAIN
DRG2090 | DRG2100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-26 to S-27 (18") - NB & SB Median: 734-735 - Ph2 | Drainage: S-32 to Existing (24") - NB & SB Median: 739-740 - Ph2 | 0 | DRAIN | DRAIN
DRG2080 | DRG2090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-25 to S-26 (24") - NB & SB Median: 734-735 - Ph2 | Drainage: S-26 to S-27 (18") - NB & SB Median: 734-735 - Ph2 | 0 | DRAIN | DRAIN
DRG2070 | DRG2080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-23 to S-25 (24") - NB & SB Median: 733-734 - Ph2 | Drainage: S-25 to S-26 (24") - NB & SB Median: 734-735 - Ph2 | 0 | DRAIN | DRAIN
DRG2060 | DRG2070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-23 to Existing (36") - NB & SB Median: 733-734 - Ph2 | Drainage: S-23 to S-25 (24") - NB & SB Median: 733-734 - Ph2 | 0 | DRAIN | DRAIN
DRG2050 | DRG2060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-20 to S-23 (24") - NB & SB Median: 732-734 - Ph2 | Drainage: S-23 to Existing (36") - NB & SB Median: 733-734 - Ph2 | 0 | DRAIN | DRAIN
DRG2040 | DRG2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-19 to S-20 (18") - NB & SB Median: 729-733 - Ph2 | Drainage: S-20 to S-23 (24") - NB & SB Median: 732-734 - Ph2 | 0 | DRAIN | DRAIN
DRG2030 | DRG2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-19 to Existing (15") - NB & SB Median: 729-730 - Ph2 | Drainage: S-19 to S-20 (18") - NB & SB Median: 729-733 - Ph2 | 0 | DRAIN | DRAIN
DRG2020 | DRG2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-14 to S-19 (18") - NB & SB Median: 728-730 - Ph2 | Drainage: S-19 to Existing (15") - NB & SB Median: 729-730 - Ph2 | 0 | DRAIN | DRAIN
DRG2010 | DRG2020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-12 to S-14 (18") - NB & SB Median: 726-728 - Ph2 | Drainage: S-14 to S-19 (18") - NB & SB Median: 728-730 - Ph2 | 0 | DRAIN | DRAIN
DRG2000 | DRG2010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | Drainage: S-12 to S-14 (18") - NB & SB Median: 726-728 - Ph2 | 0 | DRAIN | DRAIN
DRG2160 | DRG2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | Drainage: S-70 to S-72 (18") - NB & SB Median: 766-767 - Ph2 | 0 | DRAIN | DRAIN
DRG2140 | DRG2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | Drainage: S-55 to Existing (15") - NB & SB Median: 755-756 - Ph2 | 0 | DRAIN | DRAIN
DRG2150 | DRG2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-55 to Existing (15") - NB & SB Median: 755-756 - Ph2 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | 0 | DRAIN | DRAIN
DRG1000 | DRG1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1060 | DRG1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1050 | DRG1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1040 | DRG1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1030 | DRG1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1020 | DRG1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1170 | DRG1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1160 | DRG1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1150 | DRG1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1090 | DRG1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1080 | DRG1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1070 | DRG1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1180A | DRG1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1190 | DRG1180A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1140 | DRG1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1130 | DRG1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1120 | DRG1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1110 | DRG1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1100 | DRG1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1260A | DRG1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1230A | DRG1260A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1250 | DRG1230A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1240 | DRG1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1220 | DRG1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1210 | DRG1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1200 | DRG1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG140A | DRG1200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-139 OF to S-139 - Upper (18") - SB: 800-802 - Swale 1A - Ph1-S1 | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1320 | DRG1330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | Drainage: Mitered End to Mitered End (30") - SB: 799-800 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1310 | DRG1320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1300 | DRG1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1290 | DRG1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1280 | DRG1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1270 | DRG1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG210A | DRG1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1440 | DRG210A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1430 | DRG1440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1420 | DRG1430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1410 | DRG1420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1400 | DRG1410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1390 | DRG1400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1380 | DRG1390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1370 | DRG1380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1360 | DRG1370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1350 | DRG1360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1340 | DRG1350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1580A | DRG1340 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1490A | DRG1580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-218 to S-217 - Upper (24") - SB: 823-824 - Ph1-S1 | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG260A | DRG1490A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-227B to S-227A - Upper (18") - SB: 826-827 - Swale 2 - Ph1-S1 | Drainage: S-218 to S-217 - Upper (24") - SB: 823-824 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1590 | DRG1600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | Drainage: S-305 to Existing (18") - SB: 834-835 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1570 | DRG1590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1560 | DRG1570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1550 | DRG1560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1540 | DRG1550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1530 | DRG1540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1520 | DRG1530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1510 | DRG1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1500 | DRG1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1480 | DRG1500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1470 | DRG1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1460 | DRG1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1450 | DRG1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG820 | DRG1450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-301 OF to S-301 (18") - NB: 834-835 - Ph1-S1 | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG810 | DRG820 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | Drainage: S-301 OF to S-301 (18") - NB: 834-835 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG800 | DRG810 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG790 | DRG800 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-234 to S-235 (18") - NB: 828-829 - Ph1-S1 | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG760 | DRG770 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-228 to S-232 (24") - NB: 826-828 - Ph1-S1 | Drainage: S-232 to S-231 (36") - NB: 827-828 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG740 | DRG750 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | Drainage: Mitered End to Mitered End (24") - NB: 826-827 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG730 | DRG740 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG720 | DRG730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG710 | DRG720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-220 to S-221 (18") - NB: 823-824 - Ph1-S1 | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG690 | DRG700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | Drainage: S-205 to S-203 (18") - NB: 819-821 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG680 | DRG690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG670 | DRG680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG580A | DRG670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG570A | DRG580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG650 | DRG660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | Drainage: S-177 to S-175 to Existing (15") - NB: 810-812 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG640 | DRG650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-169 to S-173 (18") - NB: 807-809 - Ph1-S1 | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG610 | DRG620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | Drainage: S-167 to S-168 (18") - NB: 807-808 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG600 | DRG610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-159 OF to S-159 (14"x23") - NB: 806-807 - Ph1-S1 | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG590 | DRG600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | Drainage: S-159 OF to S-159 (14"x23") - NB: 806-807 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG510 | DRG590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-135 OF to S-135 (14"x23") - NB: 798-799 - Ph1-S1 | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG500 | DRG510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 to S-122 (18") - NB: 795-796 - Ph1-S1 | Drainage: S-135 OF to S-135 (14"x23") - NB: 798-799 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG490 | DRG500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Drainage: S-128 OF to S-128 (18") - NB: 795-796 - Ph1-S1 | Drainage: S-128 to S-122 (18") - NB: 795-796 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG460 | DRG470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-115 to S-110 (18") - NB: 781-782 - Ph1-S1 | Drainage: S-115 to S-117 (18") - NB: 781-782 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG450 | DRG460 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-114 to S-115 (18") - NB: 781-782 - Ph1-S1 | Drainage: S-115 to S-110 (18") - NB: 781-782 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG430 | DRG440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-83 OF to S-83 to Existing (18") - NB: 768-769 - Ph1-S1 | Drainage: S-106 to S-110 (18") - NB: 779-781 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG330 | DRG340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-59 to S-60 (36") - NB: 764-765 - Ph1-S1 | Drainage: S-60 to S-60A (42") - NB: 764-766 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG320 | DRG330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | Drainage: S-59 to S-60 (36") - NB: 764-765 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG310 | DRG320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG290 | DRG300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG280 | DRG290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-45 to S-46 (24") - NB: 753-754 - Ph1-S1 | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG260 | DRG270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-42 to S-45 (24") - NB: 751-754 - Ph1-S1 | Drainage: S-45 to S-49 (18") - NB: 753-754 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG240 | DRG250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | Drainage: S-41 to S-42 (30") - NB: 751-752 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG140 | DRG240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Existing to S-34A to S-34 to Existing (15") - NB: 744-745) - Ph1-S1 | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG230 | DRG100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-22 to Existing (36") - NB: 733-734 - Ph1-S1 | Drainage: Existing to S-28 to S-29 to Existing (36") - NB: 736-737 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG220 | DRG230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | Drainage: S-22 to Existing (36") - NB: 733-734 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG210 | DRG220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Drainage: S-21 OF to S-22 (29"x45") - NB: 733-734 - Ph1-S1 | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG130 | DRG140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-31 to Existing (24") - NB: 739-740 - Ph1-S1 | Drainage: Existing to S-34A to S-34 to Existing (15") - NB: 744-745) - Ph1-S1 | 0 | DRAIN | DRAIN
DRG120A | DRG130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: S-30 to S-30 OUT - Upper (18") - NB: 738-739) - Ph1-S1 | Drainage: S-31 to Existing (24") - NB: 739-740 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG110 | DRG120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Drainage: CS-1A to CS-1A OUT (18") - NB: 737 - 738 - IPh1 | Drainage: S-30 to S-30 OUT - Lower (18") - NB: 738 - 739 - IPh1 | 0 | DRAIN | DRAIN
DRGS290 | DRGS295 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | 0 | DRAIN | DRAIN
DRGS270 | DRGS280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | 0 | DRAIN | DRAIN
DRGS260 | DRGS270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | 0 | DRAIN | DRAIN
DRSG245 | DRGS250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | 0 | DRAIN | DRAIN
DRGS200 | DRGS210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | 0 | DRAIN | DRAIN
DRGS180 | DRGS190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 0 | DRAIN | DRAIN
DRGS170 | DRGS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 0 | DRAIN | DRAIN
DRGS65 | DRGS70 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS60 | DRGS65 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | 0 | DRAIN | DRAIN
DRGS130 | DRGS1230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS120 | DRGS130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS110 | DRGS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS90 | DRGS100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS80 | DRGS90 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS70 | DRGS80 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | DRAIN | DRAIN
DRGS50 | DRGS1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | 0 | DRAIN | DRAIN
DRGS40 | DRGS50 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | 0 | DRAIN | DRAIN
DRGS30 | DRGS40 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | 0 | DRAIN | DRAIN
DRGS230 | DRGS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | 0 | DRAIN | DRAIN
CP1740 | GRD400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Cure Concrete - NB & SB Median: 815+20-839+61 - Ph2 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | 0 |  | SUB-DGRIND
CP700 | CP1740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | Cure Concrete - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE
CP670 | CP1730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | Cure Concrete - NB & SB Median: 800+00-813+16 - Ph2 | 0 | CONCRETE
CP1730 | GRD390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Cure Concrete - NB & SB Median: 800+00-813+16 - Ph2 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 0 |  | SUB-DGRIND
CP650 | CP1730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | Cure Concrete - NB & SB Median: 800+00-813+16 - Ph2 | 0 | CONCRETE
CP630 | CP1720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | Cure Concrete - NB & SB Median: 780+00-786+69 - Ph2 | 0 | CONCRETE
CP1720 | GRD380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Cure Concrete - NB & SB Median: 780+00-786+69 - Ph2 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 0 |  | SUB-DGRIND
CP610 | CP1720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | Cure Concrete - NB & SB Median: 780+00-786+69 - Ph2 | 0 | CONCRETE
CP590 | CP1710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | Cure Concrete - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE
CP1710 | GRD370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Cure Concrete - NB & SB Median: 767+00-773+42 - Ph2 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 0 |  | SUB-DGRIND
CP580 | CP1710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | Cure Concrete - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE
CP570 | CP1700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 757+10-759+97 - Ph2 | Cure Concrete - NB & SB Median: 757+10-759+97 - Ph2 | 0 | CONCRETE
CP1700 | GRD360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Cure Concrete - NB & SB Median: 757+10-759+97 - Ph2 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | 0 |  | SUB-DGRIND
CP560 | CP1700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | Cure Concrete - NB & SB Median: 757+10-759+97 - Ph2 | 0 | CONCRETE
CP550 | CP1690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | Cure Concrete - NB & SB Median: 735+00-746+91 - Ph2 | 0 | CONCRETE
CP1690 | GRD350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Cure Concrete - NB & SB Median: 735+00-746+91 - Ph2 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | 0 |  | SUB-DGRIND
CP540 | CP1690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | Cure Concrete - NB & SB Median: 735+00-746+91 - Ph2 | 0 | CONCRETE
CP1680 | GRD340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Cure Concrete - NB & SB Median: 714+00-721+43 - Ph2 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | 0 |  | SUB-DGRIND
CP530 | CP1680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Concrete Pavement (9") - NB & SB Median: 714+00-721+43 - Ph2 | Cure Concrete - NB & SB Median: 714+00-721+43 - Ph2 | 0 | CONCRETE
CP1670 | GRD330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Cure Concrete - I-275 SB / Floribraska Ramp NE - Ph1-S2 | Grind Concrete Pavement - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 0 |  | SUB-DGRIND
CP470 | CP1670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Concrete Pavement (14") - I-275 SB / Floribraska Ramp NE - Ph1-S2 | Cure Concrete - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 0 | CONCRETE
CP1660 | GRD320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Cure Concrete - SB: 709+50-721+43 - Ph1-S1 | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | 0 |  | SUB-DGRIND
CP490 | CP1660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | Cure Concrete - SB: 709+50-721+43 - Ph1-S1 | 0 | CONCRETE
CP1650 | GRD310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Cure Concrete - SB: 722+83-735+00 - Ph1-S1 | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP460 | CP1650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | Cure Concrete - SB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE
CP1640 | GRD300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Cure Concrete - SB: 735+46-746+91 - Ph1-S1 | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | 0 |  | SUB-DGRIND
CP440 | CP1640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Cure Concrete - SB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE
CP1630 | GRD290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Cure Concrete - SB: 748+30-757+10 - Ph1-S1 | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-DGRIND
CP430 | CP1630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Cure Concrete - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE
CP520 | CP1620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | Cure Concrete - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE
CP1620 | GRD280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Cure Concrete - SB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | 0 |  | SUB-DGRIND
CP410 | CP1620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | Cure Concrete - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE
CP510 | CP1610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | Cure Concrete - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE
CP1610 | GRD270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Cure Concrete - SB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP400 | CP1610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Cure Concrete - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE
CP500 | CP1600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | Cure Concrete - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE
CP1600 | GRD260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Cure Concrete - SB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-DGRIND
CP380 | CP1600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Cure Concrete - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE
CP480 | CP1590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | Cure Concrete - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE
CP1590 | GRD250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Cure Concrete - SB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP370 | CP1590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | Cure Concrete - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE
CP450 | CP1580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | Cure Concrete - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE
CP1580 | GRD240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Cure Concrete - SB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-DGRIND
CP360 | CP1580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Cure Concrete - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE
CP420 | CP1570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Cure Concrete - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE
CP1570 | GRD230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Cure Concrete - SB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP340 | CP1570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Cure Concrete - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE
CP390 | CP1560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Cure Concrete - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE
CP1560 | GRD220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Cure Concrete - SB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-DGRIND
CP320 | CP1560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Cure Concrete - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE
CP350 | CP1550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Cure Concrete - SB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE
CP330 | CP1550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Cure Concrete - SB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE
CP1550 | GRD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Cure Concrete - SB: 827+00-839+61 - Ph1-S1 | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-DGRIND
CP310 | CP1550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Cure Concrete - SB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE
CP300 | CP1540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Cure Concrete - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE
CP290 | CP1540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Cure Concrete - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE
CP280 | CP1540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Cure Concrete - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE
CP1540 | GRD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Cure Concrete - NB: 815+20-839+61 - Ph1-S1 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-DGRIND
CP260 | CP1540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Cure Concrete - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE
CP1530 | GRD190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Cure Concrete - NB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-DGRIND
CP240 | CP1530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Cure Concrete - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE
CP250 | CP1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Cure Concrete - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE
CP1520 | GRD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Cure Concrete - NB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP220 | CP1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Cure Concrete - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE
CP230 | CP1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | Cure Concrete - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE
CP1510 | GRD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Cure Concrete - NB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-DGRIND
CP190 | CP1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | Cure Concrete - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE
CP160 | CP1500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Cure Concrete - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE
CP1500 | GRD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Cure Concrete - NB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP210 | CP1500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | Cure Concrete - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE
CP200 | CP1490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | Cure Concrete - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE
CP1490 | GRD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Cure Concrete - NB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-DGRIND
CP150 | CP1490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Cure Concrete - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE
CP180 | CP1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | Cure Concrete - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE
CP1480 | GRD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Cure Concrete - NB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP140 | CP1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | Cure Concrete - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE
CP170 | CP1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | Cure Concrete - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE
CP1470 | GRD130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Cure Concrete - NB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | 0 |  | SUB-DGRIND
CP130 | CP1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Cure Concrete - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE
CP1460 | GRD120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Cure Concrete - NB: 748+30-757+10 - Ph1-S1 | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-DGRIND
CP120 | CP1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | Cure Concrete - NB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE
CP1450 | GRD110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Cure Concrete - NB: 735+46-746+91 - Ph1-S1 | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | 0 |  | SUB-DGRIND
CP110 | CP1450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | Cure Concrete - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE
CP1440 | GRD100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Cure Concrete - NB: 722+83-735+00 - Ph1-S1 | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-DGRIND
CP100 | CP1440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | Cure Concrete - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE
CLK390 | CLK400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Caulk & Seal Joints - NB & SB Median: 788+09-813+16 - Ph2 | Caulk & Seal Joints - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CP-SAW | CP-SAW
CLK380 | CLK390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Caulk & Seal Joints - NB & SB Median: 774+82-786+69 - Ph2 | Caulk & Seal Joints - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CP-SAW | CP-SAW
CLK370 | CLK380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Caulk & Seal Joints - NB & SB Median: 761+67-773+42 - Ph2 | Caulk & Seal Joints - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CP-SAW | CP-SAW
CLK360 | CLK370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Caulk & Seal Joints - NB & SB Median: 748+30-759+97 - Ph 2 | Caulk & Seal Joints - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CP-SAW | CP-SAW
CLK350 | CLK360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Caulk & Seal Joints - NB & SB Median: 722+83-746+91 - Ph2 | Caulk & Seal Joints - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | CP-SAW | CP-SAW
CLK340 | CLK350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Caulk & Seal Joints - NB & SB Median: 714+00-721+43 - Ph2 | Caulk & Seal Joints - NB & SB Median: 722+83-746+91 - Ph2 | 0 | CP-SAW | CP-SAW
CLK310 | CLK320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK300 | CLK310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK290 | CLK300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK280 | CLK290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK270 | CLK280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK260 | CLK270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK250 | CLK260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK240 | CLK250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK230 | CLK240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK220 | CLK230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK210 | CLK220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK200 | CLK210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK190 | CLK200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK180 | CLK190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK170 | CLK180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK160 | CLK170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK150 | CLK160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK140 | CLK150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK130 | CLK140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK110 | CLK120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | 0 | CP-SAW | CP-SAW
CLK100 | CLK110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | 0 | CP-SAW | CP-SAW
GRD390 | GRD400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | 0 | SUB-DGRIND | SUB-DGRIND
GRD380 | GRD390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 0 | SUB-DGRIND | SUB-DGRIND
GRD370 | GRD380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 0 | SUB-DGRIND | SUB-DGRIND
GRD360 | GRD370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 0 | SUB-DGRIND | SUB-DGRIND
GRD350 | GRD360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-DGRIND | SUB-DGRIND
GRD340 | GRD350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-DGRIND | SUB-DGRIND
GRD310 | GRD320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD300 | GRD310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD290 | GRD300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD280 | GRD290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD270 | GRD280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD260 | GRD270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD250 | GRD260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD240 | GRD250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD230 | GRD240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD220 | GRD230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD210 | GRD220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD200 | GRD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD190 | GRD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD180 | GRD190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD170 | GRD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD160 | GRD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD150 | GRD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD140 | GRD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD130 | GRD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD120 | GRD130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD110 | GRD120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
GRD100 | GRD110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | SUB-DGRIND
CP100 | PAV300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE170 | CP100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Black Base - NB: 722+83-735+00 - Ph1-S1 | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
GRD330 | CLK330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Grind Concrete Pavement - I-275 SB / Floribraska Ramp NE - Ph1-S2 | Caulk & Seal Joints - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 0 | SUB-DGRIND | CP-SAW
CLK330 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Caulk & Seal Joints - I-275 SB / Floribraska Ramp NE - Ph1-S2 | End of Phase 1, Stage 2 | 0 | CP-SAW
CLK400 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 815+20-839+61 - Ph2 | End of Phase 2 | 0 | CP-SAW
CLK390 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 788+09-813+16 - Ph2 | End of Phase 2 | 0 | CP-SAW
CLK380 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 774+82-786+69 - Ph2 | End of Phase 2 | 0 | CP-SAW
CLK370 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 761+67-773+42 - Ph2 | End of Phase 2 | 0 | CP-SAW
GRD370 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | End of Phase 2 | 0 | SUB-DGRIND
CLK360 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 748+30-759+97 - Ph 2 | End of Phase 2 | 0 | CP-SAW
CLK350 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 722+83-746+91 - Ph2 | End of Phase 2 | 0 | CP-SAW
CLK340 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Caulk & Seal Joints - NB & SB Median: 714+00-721+43 - Ph2 | End of Phase 2 | 0 | CP-SAW
GRD400 | CLK400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | Caulk & Seal Joints - NB & SB Median: 815+20-839+61 - Ph2 | 0 | SUB-DGRIND | CP-SAW
CP700 | GRD400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | Grind Concrete Pavement - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP670 | GRD390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-DGRIND
GRD390 | CLK390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | Caulk & Seal Joints - NB & SB Median: 788+09-813+16 - Ph2 | 0 | SUB-DGRIND | CP-SAW
CP650 | GRD390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP630 | GRD380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-DGRIND
GRD380 | CLK380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | Caulk & Seal Joints - NB & SB Median: 774+82-786+69 - Ph2 | 0 | SUB-DGRIND | CP-SAW
CP610 | GRD380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP590 | GRD370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-DGRIND
GRD370 | CLK370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | Caulk & Seal Joints - NB & SB Median: 761+67-773+42 - Ph2 | 0 | SUB-DGRIND | CP-SAW
CP580 | GRD370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-DGRIND
CP570 | GRD360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 757+10-759+97 - Ph2 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | CONCRETE | SUB-DGRIND
GRD360 | CLK360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | Caulk & Seal Joints - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-DGRIND | CP-SAW
CP560 | GRD360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | Grind Concrete Pavement - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | CONCRETE | SUB-DGRIND
CP550 | GRD350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | 0 | CONCRETE | SUB-DGRIND
GRD350 | CLK350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | Caulk & Seal Joints - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-DGRIND | CP-SAW
CP540 | GRD350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | Grind Concrete Pavement - NB & SB Median: 722+83-746+91 - Ph2 | 0 | CONCRETE | SUB-DGRIND
GRD340 | CLK340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | Caulk & Seal Joints - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-DGRIND | CP-SAW
CP530 | GRD340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Concrete Pavement (9") - NB & SB Median: 714+00-721+43 - Ph2 | Grind Concrete Pavement - NB & SB Median: 714+00-721+43 - Ph2 | 0 | CONCRETE | SUB-DGRIND
GRD320 | CLK320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP490 | GRD320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | Grind Concrete Pavement - SB: 709+50-721+43 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD310 | CLK310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP460 | GRD310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | Grind Concrete Pavement - SB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD300 | CLK300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP440 | GRD300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Grind Concrete Pavement - SB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD290 | CLK290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP430 | GRD290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Grind Concrete Pavement - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP520 | GRD280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD280 | CLK280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP410 | GRD280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP510 | GRD270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD270 | CLK270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP400 | GRD270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP500 | GRD260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD260 | CLK260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP380 | GRD260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP480 | GRD250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD250 | CLK250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP370 | GRD250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP450 | GRD240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD240 | CLK240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP360 | GRD240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP420 | GRD230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD230 | CLK230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP340 | GRD230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP390 | GRD220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD220 | CLK220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP320 | GRD220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP350 | GRD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP330 | GRD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD210 | CLK210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP310 | GRD210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Grind Concrete Pavement - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP300 | GRD200 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 5 | CONCRETE | SUB-DGRIND
CP290 | GRD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP280 | GRD200 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 5 | CONCRETE | SUB-DGRIND
GRD200 | CLK200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP260 | GRD200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Grind Concrete Pavement - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP270 | GRD190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD190 | CLK190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP240 | GRD190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Grind Concrete Pavement - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP250 | GRD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD180 | CLK180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP220 | GRD180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Grind Concrete Pavement - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP230 | GRD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD170 | CLK170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP190 | GRD170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | Grind Concrete Pavement - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP210 | GRD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD160 | CLK160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP160 | GRD160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Grind Concrete Pavement - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP200 | GRD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD150 | CLK150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP150 | GRD150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Grind Concrete Pavement - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP180 | GRD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD140 | CLK140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP140 | GRD140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | Grind Concrete Pavement - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CP170 | GRD130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD130 | CLK130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP130 | GRD130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Grind Concrete Pavement - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD120 | CLK120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP120 | GRD120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | Grind Concrete Pavement - NB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD110 | CLK110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP110 | GRD110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | Grind Concrete Pavement - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
GRD100 | CLK100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-DGRIND | CP-SAW
CP100 | GRD100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Concrete Pavement (9") - NB: 722+83-735+00 - Ph1-S1 | Grind Concrete Pavement - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | SUB-DGRIND
CLK320 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 709+50-721+43 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK310 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK300 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK290 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK280 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 757+10-759+97 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK270 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 761+67-767+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK260 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK250 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 774+82-780+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK240 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK230 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK220 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK210 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - SB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK200 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK190 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK180 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK170 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK160 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 774+82-780+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK150 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK140 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 761+67-767+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK130 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 757+10-759+97 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK120 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK110 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
CLK100 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Caulk & Seal Joints - NB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CP-SAW
MS-LNTP | MS-CE10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Notice to Proceed | Start-Up | 0
DRGJB20 | DRG1340 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | 0 | SUB-JB | DRAIN
DRGJB20 | DRG2340 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | Drainage: S-152 to S-158 (24") - NB & SB Median: 804-806 - Ph2 | 0 | SUB-JB | DRAIN
DRGJB10 | DRGJB20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | 0 | SUB-JB | SUB-JB
MS-IP1S | DRGJB10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | Start of Initial Phase 1 | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | 0 |  | SUB-JB
SP10 | DRGJB10 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | Mobilization - IPh1 | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | 0 |  | SUB-JB
CG100 | TCC130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Install MOT Construction Barriers I-275 SB - IPh1 | 0 | SUB-EW-C&G | TRAFFIC
CG100 | TCC100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Install MOT Construction Barriers I-275 NB - IPh1 | 8 | SUB-EW-C&G | TRAFFIC
TCC100 | PILE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Install MOT Construction Barriers I-275 NB - IPh1 | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 | TRAFFIC | ST-SOLDIER
TCC100 | TCC130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Install MOT Construction Barriers I-275 NB - IPh1 | Install MOT Construction Barriers I-275 SB - IPh1 | 0 | TRAFFIC | TRAFFIC
MS-IP1S | TCC100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Start of Initial Phase 1 | Install MOT Construction Barriers I-275 NB - IPh1 | 0 |  | TRAFFIC
MS-P1S1F | TCC160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | End of Phase 1, Stage 1 | Relocate MOT Construction Barriers to Median | 0 |  | TRAFFIC
TCC160 | MS-P2S | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Relocate MOT Construction Barriers to Median | Start of Phase 2 | 0 | TRAFFIC
MS-P3S | PM210 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Start of Phase 3 | Final Pavement Markings - Side Roads - Project Limits - Ph3 | 0 |  | SUB-STRIP
PAV530 | PM210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Final Pavement Markings - Side Roads - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
R3510 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | End of Phase 3 | 0 | SUB-DGRIND
R3510 | R3540 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | Install Misc Final Signage Remaining - Project Limits - Ph3 | 5 | SUB-DGRIND | SUB-SIGN
R3500 | R3540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | Install Misc Final Signage Remaining - Project Limits - Ph3 | 0 | SUB-DGRIND | SUB-SIGN
R3500 | R3510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | 0 | SUB-DGRIND | SUB-DGRIND
R3500 | PM220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-DGRIND | SUB-STRIP
PAV530 | PM230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
PAV530 | PM220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | 0 | SUB-MILL | SUB-STRIP
TCC170 | R3510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Remove MOT Construction Barriers | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | 0 | TRAFFIC | SUB-DGRIND
TCC170 | R3500 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Remove MOT Construction Barriers | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | 5 | TRAFFIC | SUB-DGRIND
MS-P2F | TCC170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | End of Phase 2 | Remove MOT Construction Barriers | 0 |  | TRAFFIC
SGN2060 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 815+20-839+61 - Ph2 | End of Phase 2 | 0 | SUB-SIGN
SGN2050 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | End of Phase 2 | 0 | SUB-SIGN
SGN2040 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | End of Phase 2 | 0 | SUB-SIGN
SGN2030 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | End of Phase 2 | 0 | SUB-SIGN
SGN2020 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 748+30-759+97 - Ph 2 | End of Phase 2 | 0 | SUB-SIGN
SGN2010 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 722+83-746+91 - Ph2 | End of Phase 2 | 0 | SUB-SIGN
SGN2000 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Install Signs - NB & SB Median: 714+00-721+43 - Ph2 | End of Phase 2 | 0 | SUB-SIGN
SGN2050 | SGN2060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | Install Signs - NB & SB Median: 815+20-839+61 - Ph2 | 0 | SUB-SIGN | SUB-SIGN
SGN2040 | SGN2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | 0 | SUB-SIGN | SUB-SIGN
SGN2030 | SGN2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | 0 | SUB-SIGN | SUB-SIGN
SGN2020 | SGN2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Install Signs - NB & SB Median: 748+30-759+97 - Ph 2 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | 0 | SUB-SIGN | SUB-SIGN
SGN2010 | SGN2020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Install Signs - NB & SB Median: 722+83-746+91 - Ph2 | Install Signs - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-SIGN | SUB-SIGN
SGN2000 | SGN2010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Install Signs - NB & SB Median: 714+00-721+43 - Ph2 | Install Signs - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-SIGN | SUB-SIGN
CP700 | SGN2060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | Install Signs - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP670 | SGN2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP650 | SGN2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | Install Signs - NB & SB Median: 788+09-813+16 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP630 | SGN2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP610 | SGN2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | Install Signs - NB & SB Median: 774+82-786+69 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP580 | SGN2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-SIGN
CP590 | SGN2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | Install Signs - NB & SB Median: 761+67-773+42 - Ph2 | 0 | CONCRETE | SUB-SIGN
PAV520 | SGN2020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | Install Signs - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-ASPH | SUB-SIGN
PAV510 | SGN2010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | Install Signs - NB & SB Median: 722+83-746+91 - Ph2 | 0 | SUB-ASPH | SUB-SIGN
PAV500 | SGN2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | Install Signs - NB & SB Median: 714+00-721+43 - Ph2 | 0 | SUB-ASPH | SUB-SIGN
DRG2180 | DRG2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: Existing to S-82 to S-86 (18") - NB & SB Median: 768-770 - Ph2 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | 0 | DRAIN | DRAIN
PAV510 | PAV520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | SUB-ASPH | SUB-ASPH
CP540 | UDR450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | Install Edgedrain - NB & SB Median: 722+83-746+91 - Ph2 | 0 | CONCRETE | UNDR
CP550 | BASE830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | Shoulder Base - NB & SB Median: 722+83-746+91 - Ph2 | 0 | CONCRETE | EW-ABC
BASE800 | CP550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | 0 | EW-ABC | CONCRETE
BW1200 | CP540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | 0 | BARRIER | CONCRETE
STAB550 | BASE800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-CEM | EW-ABC
EGC410 | BW1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-SML | BARRIER
DRG2130 | STAB550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-35 to S-38 (15") - NB & SB Median: 744-745 - Ph2 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-CEM
DRG2120 | STAB550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-35 to Existing (15") - NB & SB Median: 744-745 - Ph2 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-CEM
DRG2110 | STAB550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (18") - NB & SB Median: 739-740 - Ph2 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-CEM
DRG2100 | STAB550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (24") - NB & SB Median: 739-740 - Ph2 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-CEM
CP670 | CP700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | 0 | CONCRETE | CONCRETE
CP630 | CP650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | 0 | CONCRETE | CONCRETE
CP590 | CP610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | 0 | CONCRETE | CONCRETE
CP570 | CP580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 757+10-759+97 - Ph2 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | 0 | CONCRETE | CONCRETE
CP550 | CP560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | 0 | CONCRETE | CONCRETE
CP530 | CP540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 714+00-721+43 - Ph2 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | 0 | CONCRETE | CONCRETE
BASE870 | BASE910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Black Base - NB & SB Median: 788+09-813+16 - Ph2 | Black Base - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-ABC | EW-ABC
BASE840 | BASE870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Black Base - NB & SB Median: 774+82-786+69 - Ph2 | Black Base - NB & SB Median: 788+09-813+16 - Ph2 | 0 | EW-ABC | EW-ABC
BASE820 | BASE840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Black Base - NB & SB Median: 761+67-773+42 - Ph2 | Black Base - NB & SB Median: 774+82-786+69 - Ph2 | 0 | EW-ABC | EW-ABC
BASE810 | BASE820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Black Base - NB & SB Median: 748+30-759+97 - Ph 2 | Black Base - NB & SB Median: 761+67-773+42 - Ph2 | 0 | EW-ABC | EW-ABC
BASE800 | BASE810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | Black Base - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-ABC | EW-ABC
BASE780 | BASE800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Black Base - NB & SB Median: 714+00-721+43 - Ph2 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-ABC | EW-ABC
BW1280 | BW1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | BARRIER
BW1260 | BW1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | BARRIER
BW1240 | BW1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | BARRIER
BW1200 | BW1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | BARRIER
BW1180 | BW1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | 0 | BARRIER | BARRIER
STAB590 | STAB600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Stabilization - NB & SB Median: 788+09-813+16 - Ph2 | Stabilization - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-CEM | EW-CEM
STAB580 | STAB590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Stabilization - NB & SB Median: 774+82-786+69 - Ph2 | Stabilization - NB & SB Median: 788+09-813+16 - Ph2 | 0 | EW-CEM | EW-CEM
STAB570 | STAB580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Stabilization - NB & SB Median: 761+67-773+42 - Ph2 | Stabilization - NB & SB Median: 774+82-786+69 - Ph2 | 0 | EW-CEM | EW-CEM
STAB560 | STAB570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Stabilization - NB & SB Median: 748+30-759+97 - Ph 2 | Stabilization - NB & SB Median: 761+67-773+42 - Ph2 | 0 | EW-CEM | EW-CEM
STAB550 | STAB560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | Stabilization - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-CEM | EW-CEM
STAB540 | STAB550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Stabilization - NB & SB Median: 714+00-721+43 - Ph2 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-CEM | EW-CEM
EGC450 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-SML | EW-SML
EGC440 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | EW-SML | EW-SML
EGC430 | EGC440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | 0 | EW-SML | EW-SML
EGC420 | EGC430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Backfill & Grade - NB & SB Median: 748+30-759+97 - Ph 2 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | 0 | EW-SML | EW-SML
EGC410 | EGC420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | Backfill & Grade - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-SML | EW-SML
EGC400 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Backfill & Grade - NB & SB Median: 714+00-721+43 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-SML | EW-SML
BASE910 | CP700 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Black Base - NB & SB Median: 815+20-839+61 - Ph2 | Concrete Pavement (9") - NB & SB Median: 815+20-839+61 - Ph2 | 4 | EW-ABC | CONCRETE
BW1300 | BASE910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 815+20-839+61 - Ph2 | Black Base - NB & SB Median: 815+20-839+61 - Ph2 | 0 | BARRIER | EW-ABC
STAB600 | BW1300 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Stabilization - NB & SB Median: 815+20-839+61 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 815+20-839+61 - Ph2 | 4 | EW-CEM | BARRIER
EGC460 | STAB600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | Stabilization - NB & SB Median: 815+20-839+61 - Ph2 | 0 | EW-SML | EW-CEM
DRG2490 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: Existing to S-304 to S-306 (18") - NB & SB Median: 835-838 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2480 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-243 to S-244 (18") - NB & SB Median: 831-833 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2470 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-241 to S-243 (18") - NB & SB Median: 830-832 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2460 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-238 to S-241 (18") - NB & SB Median: 829-831 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2450 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-236 to S-238 (18") - NB & SB Median: 828-830 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2440 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-233 to S-236 (18") - NB & SB Median: 828-829 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2430 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-230 to S-233 (18") - NB & SB Median: 827-828 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2420 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-227 to S-230 (18") - NB & SB Median: 826-828 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2410 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-230 to Existing (36") - NB & SB Median: 827-828 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2400 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-223 to S-225 (18") - NB & SB Median: 824-825 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2390 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-222 to S-223 (18") - NB & SB Median: 824-825 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2380 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-219 to S-222 (18") - NB & SB Median: 823-824 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2370 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-212 to S-219 (18") - NB & SB Median: 822-823 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DRG2360 | EGC460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | Backfill & Grade - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DRAIN | EW-SML
DEMO1880 | DRG2490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: Existing to S-304 to S-306 (18") - NB & SB Median: 835-838 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-243 to S-244 (18") - NB & SB Median: 831-833 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-241 to S-243 (18") - NB & SB Median: 830-832 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-238 to S-241 (18") - NB & SB Median: 829-831 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-236 to S-238 (18") - NB & SB Median: 828-830 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-233 to S-236 (18") - NB & SB Median: 828-829 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-230 to S-233 (18") - NB & SB Median: 827-828 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-227 to S-230 (18") - NB & SB Median: 826-828 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-230 to Existing (36") - NB & SB Median: 827-828 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-223 to S-225 (18") - NB & SB Median: 824-825 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-222 to S-223 (18") - NB & SB Median: 824-825 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-219 to S-222 (18") - NB & SB Median: 823-824 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-212 to S-219 (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1880 | DRG2360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | Drainage: S-211 to S-212 to Existing (18") - NB & SB Median: 822-823 - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DEMO1880 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | 0 | DEMO | DEMO
CP650 | CP670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | Concrete Pavement (9") - NB & SB Median: 800+00-813+16 - Ph2 | 0 | CONCRETE | CONCRETE
BASE870 | CP650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Black Base - NB & SB Median: 788+09-813+16 - Ph2 | Concrete Pavement (9") - NB & SB Median: 788+09-800+00 - Ph2 | 0 | EW-ABC | CONCRETE
BW1280 | BASE870 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | Black Base - NB & SB Median: 788+09-813+16 - Ph2 | 0 | BARRIER | EW-ABC
STAB590 | BW1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Stabilization - NB & SB Median: 788+09-813+16 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 788+09-813+16 - Ph2 | 0 | EW-CEM | BARRIER
EGC450 | STAB590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | Stabilization - NB & SB Median: 788+09-813+16 - Ph2 | 0 | EW-SML | EW-CEM
DRG2350 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: Existing to S-160 to S-163 (18") - NB & SB Median: 804-806 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2340 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-152 to S-158 (24") - NB & SB Median: 804-806 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2330 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-148 to S-152 (18") - NB & SB Median: 803-805 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2320 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-147 to S-148 (18") - NB & SB Median: 802-804 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2310 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-140 to S-147 (18") - NB & SB Median: 801-803 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2300 | EGC450 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-141 to S-140 (18") - NB & SB Median: 800-801 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2290 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-138 to S-141 (18") - NB & SB Median: 799-801 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2280 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-137 to S-138 (18") - NB & SB Median: 799-800 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2270 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-134 to S-137 (18") - NB & SB Median: 798-800 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2260 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-131 to S-134 (18") - NB & SB Median: 797-799 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2250 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-130 to S-131 (18") - NB & SB Median: 796-798 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2240 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-127 to S-130 (18") - NB & SB Median: 795-797 - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DRG2230 | EGC450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | Backfill & Grade - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DRAIN | EW-SML
DEMO1850 | DRG2280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Drainage: S-137 to S-138 (18") - NB & SB Median: 799-800 - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DRG2270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Drainage: S-134 to S-137 (18") - NB & SB Median: 798-800 - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DRG2260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Drainage: S-131 to S-134 (18") - NB & SB Median: 797-799 - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DRG2250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Drainage: S-130 to S-131 (18") - NB & SB Median: 796-798 - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DRG2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Drainage: S-127 to S-130 (18") - NB & SB Median: 795-797 - Ph2 | 0 | DEMO | DRAIN
DEMO1850 | DRG2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | Drainage: S-123 to S-125 to Existing (18" & 15") (MED:793 - 795) - Ph2 | 0 | DEMO | DRAIN
DEMO1820 | DEMO1850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | 0 | DEMO | DEMO
CP560 | UDR460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | Install Edgedrain - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | CONCRETE | UNDR
CP610 | CP630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | Concrete Pavement (9") - NB & SB Median: 780+00-786+69 - Ph2 | 0 | CONCRETE | CONCRETE
BASE840 | CP610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Black Base - NB & SB Median: 774+82-786+69 - Ph2 | Concrete Pavement (9") - NB & SB Median: 774+82-780+00 - Ph2 | 0 | EW-ABC | CONCRETE
BW1260 | BASE840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | Black Base - NB & SB Median: 774+82-786+69 - Ph2 | 0 | BARRIER | EW-ABC
STAB580 | BW1260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Stabilization - NB & SB Median: 774+82-786+69 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 774+82-786+69 - Ph2 | 0 | EW-CEM | BARRIER
EGC440 | STAB580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | Stabilization - NB & SB Median: 774+82-786+69 - Ph2 | 0 | EW-SML | EW-CEM
DRG2220 | EGC440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-120 to Existing (15") - NB & SB Median: 784-785 - Ph2 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | 0 | DRAIN | EW-SML
DRG2210 | EGC440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-111 to S-116 (18") - NB & SB Median: 781-782 - Ph2 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | 0 | DRAIN | EW-SML
DRG2200 | EGC440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-105 to S-111 to Existing (18" & 15") - NB & SB Median: 780-782 - Ph2 | Backfill & Grade - NB & SB Median: 774+82-786+69 - Ph2 | 0 | DRAIN | EW-SML
DRG2190 | DRG2200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | Drainage: S-105 to S-111 to Existing (18" & 15") - NB & SB Median: 780-782 - Ph2 | 0 | DRAIN | DRAIN
DEMO1820 | DRG2190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | Drainage: S-104 to S-105 (18") - NB & SB Median: 778-781 - Ph2 | 0 | DEMO | DRAIN
DEMO1790 | DEMO1820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | 0 | DEMO | DEMO
CP580 | CP590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | Concrete Pavement (9") - NB & SB Median: 767+00-773+42 - Ph2 | 0 | CONCRETE | CONCRETE
BASE820 | CP580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Black Base - NB & SB Median: 761+67-773+42 - Ph2 | Concrete Pavement (9") - NB & SB Median: 761+67-767+00 - Ph2 | 0 | EW-ABC | CONCRETE
BW1240 | BASE820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | Black Base - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | EW-ABC
STAB570 | BW1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Stabilization - NB & SB Median: 761+67-773+42 - Ph2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | 0 | EW-CEM | BARRIER
EGC430 | STAB570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | Stabilization - NB & SB Median: 761+67-773+42 - Ph2 | 0 | EW-SML | EW-CEM
DRG2180 | EGC430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: Existing to S-82 to S-86 (18") - NB & SB Median: 768-770 - Ph2 | Backfill & Grade - NB & SB Median: 761+67-773+42 - Ph2 | 0 | DRAIN | EW-SML
DRG2170 | DRG2180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Drainage: S-70 to S-72 (18") - NB & SB Median: 766-767 - Ph2 | Drainage: Existing to S-82 to S-86 (18") - NB & SB Median: 768-770 - Ph2 | 0 | DRAIN | DRAIN
DEMO1790 | DRG2170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | Drainage: S-70 to S-72 (18") - NB & SB Median: 766-767 - Ph2 | 0 | DEMO | DRAIN
DEMO1790 | DRG2160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | Drainage: S-68 to S-70 to Existing (18" & 15") - NB & SB Median: 766-767 - Ph2 | 0 | DEMO | DRAIN
DEMO1730 | DEMO1790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | 0 | DEMO | DEMO
BASE850 | PAV520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Shoulder Base - NB & SB Median: 748+30-759+97 - Ph 2 | Asphalt Paving - Shoulder - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-ABC | SUB-ASPH
UDR460 | BASE850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Install Edgedrain - NB & SB Median: 748+30-759+97 - Ph 2 | Shoulder Base - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | UNDR | EW-ABC
CP560 | CP570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | Concrete Pavement (9") - NB & SB Median: 757+10-759+97 - Ph2 | 0 | CONCRETE | CONCRETE
BASE810 | CP560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Black Base - NB & SB Median: 748+30-759+97 - Ph 2 | Concrete Pavement (9") - NB & SB Median: 748+30-757+10 - Ph2 | 0 | EW-ABC | CONCRETE
BW1220 | BASE810 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | Black Base - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | BARRIER | EW-ABC
STAB560 | BW1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Stabilization - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-CEM | BARRIER
EGC420 | STAB560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Backfill & Grade - NB & SB Median: 748+30-759+97 - Ph 2 | Stabilization - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | EW-SML | EW-CEM
DRG2150 | EGC420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Drainage: S-55 to Existing (15") - NB & SB Median: 755-756 - Ph2 | Backfill & Grade - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | DRAIN | EW-SML
DRG2140 | EGC420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | Backfill & Grade - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | DRAIN | EW-SML
DEMO1710 | DEMO1730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | 0 | DEMO | DEMO
DEMO1730 | DRG2150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | Drainage: S-55 to Existing (15") - NB & SB Median: 755-756 - Ph2 | 0 | DEMO | DRAIN
DEMO1730 | DRG2140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | Drainage: S-44 to S-47 (18") - NB & SB Median: 753-754 - Ph2 | 0 | DEMO | DRAIN
BASE830 | PAV510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Shoulder Base - NB & SB Median: 722+83-746+91 - Ph2 | Asphalt Paving - Shoulder - NB & SB Median: 722+83-746+91 - Ph2 | 0 | EW-ABC | SUB-ASPH
UDR450 | BASE830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Install Edgedrain - NB & SB Median: 722+83-746+91 - Ph2 | Shoulder Base - NB & SB Median: 722+83-746+91 - Ph2 | 0 | UNDR | EW-ABC
CP540 | CP550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | Concrete Pavement (9") - NB & SB Median: 735+00-746+91 - Ph2 | 0 | CONCRETE | CONCRETE
BASE800 | CP540 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | Concrete Pavement (9") - NB & SB Median: 722+83-735+00 - Ph2 | 9 | EW-ABC | CONCRETE
BW1200 | BASE800 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | Black Base - NB & SB Median: 722+83-746+91 - Ph2 | 5 | BARRIER | EW-ABC
STAB550 | BW1200 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 722+83-746+91 - Ph2 | 7 | EW-CEM | BARRIER
EGC410 | STAB550 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | Stabilization - NB & SB Median: 722+83-746+91 - Ph2 | 5 | EW-SML | EW-CEM
DRG2090 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-26 to S-27 (18") - NB & SB Median: 734-735 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2080 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-25 to S-26 (24") - NB & SB Median: 734-735 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2070 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-23 to S-25 (24") - NB & SB Median: 733-734 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2060 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-23 to Existing (36") - NB & SB Median: 733-734 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2050 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-20 to S-23 (24") - NB & SB Median: 732-734 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2040 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-19 to S-20 (18") - NB & SB Median: 729-733 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2030 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-19 to Existing (15") - NB & SB Median: 729-730 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2020 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-14 to S-19 (18") - NB & SB Median: 728-730 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2010 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-12 to S-14 (18") - NB & SB Median: 726-728 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2000 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DEMO1700 | DEMO1710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 714+00-721+43 - Ph2 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DEMO | DEMO
DRG2120 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-35 to Existing (15") - NB & SB Median: 744-745 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2110 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (18") - NB & SB Median: 739-740 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DRG2100 | EGC410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Drainage: S-32 to Existing (24") - NB & SB Median: 739-740 - Ph2 | Backfill & Grade - NB & SB Median: 722+83-746+91 - Ph2 | 0 | DRAIN | EW-SML
DEMO1710 | DRG2090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-26 to S-27 (18") - NB & SB Median: 734-735 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-25 to S-26 (24") - NB & SB Median: 734-735 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-23 to S-25 (24") - NB & SB Median: 733-734 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-23 to Existing (36") - NB & SB Median: 733-734 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-20 to S-23 (24") - NB & SB Median: 732-734 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-19 to S-20 (18") - NB & SB Median: 729-733 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-19 to Existing (15") - NB & SB Median: 729-730 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-14 to S-19 (18") - NB & SB Median: 728-730 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-12 to S-14 (18") - NB & SB Median: 726-728 - Ph2 | 0 | DEMO | DRAIN
DEMO1710 | DRG2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | Drainage: S-10 to S-12 (18") - NB & SB Median: 724-727 - Ph2 | 0 | DEMO | DRAIN
BASE790 | PAV500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Shoulder Base - NB & SB Median: 714+00-721+43 - Ph2 | Asphalt Paving - Shoulder - NB & SB Median: 714+00-721+43 - Ph2 | 0 | EW-ABC | SUB-ASPH
UDR440 | BASE790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Install Edgedrain - NB & SB Median: 714+00-721+43 - Ph2 | Shoulder Base - NB & SB Median: 714+00-721+43 - Ph2 | 0 | UNDR | EW-ABC
CP530 | UDR440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Concrete Pavement (9") - NB & SB Median: 714+00-721+43 - Ph2 | Install Edgedrain - NB & SB Median: 714+00-721+43 - Ph2 | 0 | CONCRETE | UNDR
BW1180 | BASE780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 714+00-721+43 - Ph2 | Black Base - NB & SB Median: 714+00-721+43 - Ph2 | 0 | BARRIER | EW-ABC
STAB540 | BW1180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Stabilization - NB & SB Median: 714+00-721+43 - Ph2 | Form / Reinforce / Pour Median Barrier Wall Footing - NB & SB Median: 714+00-721+43 - Ph2 | 0 | EW-CEM | BARRIER
EGC400 | STAB540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Backfill & Grade - NB & SB Median: 714+00-721+43 - Ph2 | Stabilization - NB & SB Median: 714+00-721+43 - Ph2 | 0 | EW-SML | EW-CEM
MS-P2S | DEMO1880 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.8 Construction: Phase 2: I-275 Median: NB & SB: Station: 815+20 to 839+61 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 815+20-839+61 - Ph2 | 0 |  | DEMO
MS-P2S | DEMO1850 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.7 Construction: Phase 2: I-275 Median: NB & SB: Station: 788+09 to 813+16 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 788+09-813+16 - Ph2 | 0 |  | DEMO
MS-P2S | DEMO1820 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.6 Construction: Phase 2: I-275 Median: NB & SB: Station: 774+82 to 786+69 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 774+82-786+69 - Ph2 | 0 |  | DEMO
MS-P2S | DEMO1790 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 761+67-773+42 - Ph2 | 0 |  | DEMO
MS-P2S | DEMO1730 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 748+30-759+97 - Ph 2 | 0 |  | DEMO
MS-P2S | DEMO1710 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.3 Construction: Phase 2: I-275 Median: NB & SB: Station: 722+83 to 746+91 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 722+83-746+91 - Ph2 | 0 |  | DEMO
DEMO1700 | EGC400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Remove Light Poles / Demo - NB & SB Median: 714+00-721+43 - Ph2 | Backfill & Grade - NB & SB Median: 714+00-721+43 - Ph2 | 0 | DEMO | EW-SML
MS-P2S | DEMO1700 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Start of Phase 2 | Remove Light Poles / Demo - NB & SB Median: 714+00-721+43 - Ph2 | 0 |  | DEMO
MS-P1S1S | MS-P1S1S1S | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Start of Phase 1, Stage 1 | Start of Phase 1, Stage 1, Step 1 | 0
EC10 | MS-P1S1S | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Erosion Control Installation - Project Limits - IPh1 | Start of Phase 1, Stage 1 | 0 | SUB-EROSION
EC10 | CG100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Erosion Control Installation - Project Limits - IPh1 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | 5 | SUB-EROSION | SUB-EW-C&G
MS-IP1S | EC10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Start of Initial Phase 1 | Erosion Control Installation - Project Limits - IPh1 | 0 |  | SUB-EROSION
CP290 | CP300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP280 | CP300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP300 | CP350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP300 | CP330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP260 | CP300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP300 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
BASE400 | CP300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 0 | EW-ABC | CONCRETE
CP270 | CP300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP260 | CP280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP280 | CP290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP280 | CP310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP240 | CP280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP280 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
BASE400 | CP280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 815+20-839+61 - Ph1-S1 | Concrete Pavement (9") - NB: 827+00-839+61 - Ph1-S1 | 0 | EW-ABC | CONCRETE
CP350 | CP390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP310 | CP350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP350 | SGN610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
BASE470 | CP350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Black Base - SB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - SB: 827+00-839+61 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EL320 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL310 | STAB520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | Stabilization - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL300 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL290 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL280 | STAB450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | Stabilization - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL270 | STAB430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL260 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL240 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL230 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL220 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL210 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL200 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL190 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL180 | STAB250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL150 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL140 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL130 | STAB200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 757+10-759+97 - Ph1-S1 | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL120 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL100 | STAB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | EW-CEM
EL310 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL300 | EL310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL290 | EL300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL280 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL270 | EL280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL260 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL230 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL220 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL210 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL200 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL190 | EL200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL180 | EL190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EL120 | EL130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-UT-ELEC
EGC100 | EL100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC120 | EL120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC130 | EL130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC150 | EL150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC140 | EL140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC180 | EL180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC190 | EL190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC200 | EL200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC210 | EL210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC220 | EL220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC230 | EL230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC240 | EL240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC270 | EL260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC260 | EL270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC280 | EL280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC290 | EL290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Install Conduit & Pull Boxes: Conduit: Lighting - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC310 | EL310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC300 | EL300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Install Conduit: Lighting - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
EGC320 | EL320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | Install Conduit & Pull Boxes: Lighting - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-SML | SUB-UT-ELEC
SGN200 | SGN610 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Procurement: Sign Posts / Gantry - OHB-01 / 818+78 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-SIGN
PILE110 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | ST-SOLDIER | SUB-ST-MSE
SUPR790 | SUPR800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR780 | SUPR790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR580 | SUPR780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR510 | SUPR580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR490 | SUPR510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR370 | SUPR490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR360 | SUPR370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR310 | SUPR360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-APPR | ST-APPR
SUPR230 | SUPR310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-APPR | ST-APPR
CP420 | CP450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP390 | CP420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP290 | CP330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP510 | CP520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP500 | CP510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP480 | CP500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP450 | CP480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP320 | CP390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP340 | CP420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP360 | CP450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP370 | CP480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP380 | CP500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP400 | CP510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP410 | CP520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP330 | CP390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
PAV480 | PAV490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV470 | PAV480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV460 | PAV470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
CP250 | CP270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP230 | CP250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP210 | CP230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP200 | CP210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP180 | CP200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP170 | CP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
PAV310 | PAV330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
PAV300 | PAV310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-ASPH
CP310 | CP330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP260 | CP290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP240 | CP270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP220 | CP250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP190 | CP230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP160 | CP210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP150 | CP200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP140 | CP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP130 | CP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP460 | CP490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP440 | CP460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP430 | CP440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP410 | CP430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP400 | CP410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP380 | CP400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP370 | CP380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP360 | CP370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP340 | CP360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP320 | CP340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP310 | CP320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP260 | CP310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP240 | CP260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP220 | CP240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP190 | CP220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP160 | CP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP150 | CP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP140 | CP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP130 | CP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
CP120 | CP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | CONCRETE
BASE710 | BASE740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Black Base - SB: 722+83-735+00 - Ph1-S1 | Black Base - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE700 | BASE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Black Base - SB: 735+46-746+91 - Ph1-S1 | Black Base - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE660 | BASE700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Black Base - SB: 748+30-757+10 - Ph1-S1 | Black Base - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE640 | BASE660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Black Base - SB: 757+10-759+97 - Ph1-S1 | Black Base - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE400 | BASE470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 815+20-839+61 - Ph1-S1 | Black Base - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE340 | BASE350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Black Base - NB: 788+09-800+00 - Ph1-S1 | Black Base - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE240 | BASE320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Black Base - NB: 774+82-780+00 - Ph1-S1 | Black Base - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE220 | BASE230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Black Base - NB: 761+67-767+00 - Ph1-S1 | Black Base - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE170 | BASE180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Black Base - NB: 722+83-735+00 - Ph1-S1 | Black Base - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | EW-ABC
STAB430 | STAB450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Stabilization - SB: 761+67-767+00 - Ph1-S1 | Stabilization - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB410 | STAB430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Stabilization - SB: 767+00-773+42 - Ph1-S1 | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB390 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Stabilization - SB: 774+82-780+00 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-CEM | EW-CEM
PAV490 | SGN720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP490 | SGN720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
PAV480 | SGN710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP460 | SGN710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
PAV470 | SGN700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | Install Signs - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP440 | SGN700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Install Signs - SB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN710 | SGN720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Install Signs - SB: 722+83-735+00 - Ph1-S1 | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN700 | SGN710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Install Signs - SB: 735+46-746+91 - Ph1-S1 | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN690 | SGN700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Install Signs - SB: 748+30-757+10 - Ph1-S1 | Install Signs - SB: 735+46-746+91 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
PAV460 | SGN690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | Install Signs - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
CP430 | SGN690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Install Signs - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP520 | SGN680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | Install Signs - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP410 | SGN680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | Install Signs - SB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN680 | SGN690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Install Signs - SB: 757+10-759+97 - Ph1-S1 | Install Signs - SB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN670 | SGN680 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Install Signs - SB: 761+67-767+00 - Ph1-S1 | Install Signs - SB: 757+10-759+97 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP510 | SGN670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | Install Signs - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP400 | SGN670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | Install Signs - SB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP500 | SGN660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | Install Signs - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP380 | SGN660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | Install Signs - SB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN660 | SGN670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Install Signs - SB: 767+00-773+42 - Ph1-S1 | Install Signs - SB: 761+67-767+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN650 | SGN660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Install Signs - SB: 774+82-780+00 - Ph1-S1 | Install Signs - SB: 767+00-773+42 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP480 | SGN650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | Install Signs - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP370 | SGN650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | Install Signs - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP450 | SGN640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | Install Signs - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP360 | SGN640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | Install Signs - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN640 | SGN650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Install Signs - SB: 780+00-786+69 - Ph1-S1 | Install Signs - SB: 774+82-780+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN630 | SGN640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Install Signs - SB: 788+09-800+00 - Ph1-S1 | Install Signs - SB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP420 | SGN630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | Install Signs - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP340 | SGN630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | Install Signs - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP390 | SGN620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP320 | SGN620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP330 | SGN610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP310 | SGN610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN620 | SGN630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Install Signs - SB: 800+00-813+16 - Ph1-S1 | Install Signs - SB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN610 | SGN620 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Install Signs - SB: 815+20-839+61 - Ph1-S1 | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN600 | SGN610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 815+20-839+61 - Ph1-S1 | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP290 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP260 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN590 | SGN600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Install Signs - NB: 800+00-813+16 - Ph1-S1 | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP270 | SGN590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Install Signs - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP240 | SGN590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | Install Signs - NB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP250 | SGN580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | Install Signs - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP220 | SGN580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | Install Signs - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN580 | SGN590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Install Signs - NB: 788+09-800+00 - Ph1-S1 | Install Signs - NB: 800+00-813+16 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN570 | SGN580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Install Signs - NB: 780+00-786+69 - Ph1-S1 | Install Signs - NB: 788+09-800+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP230 | SGN570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | Install Signs - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP190 | SGN570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | Install Signs - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP210 | SGN560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | Install Signs - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP160 | SGN560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | Install Signs - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN560 | SGN570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Install Signs - NB: 774+82-780+00 - Ph1-S1 | Install Signs - NB: 780+00-786+69 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN550 | SGN560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Install Signs - NB: 767+00-773+42 - Ph1-S1 | Install Signs - NB: 774+82-780+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP200 | SGN550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | Install Signs - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP150 | SGN550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | Install Signs - NB: 767+00-773+42 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN540 | SGN550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Install Signs - NB: 761+67-767+00 - Ph1-S1 | Install Signs - NB: 767+00-773+42 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP180 | SGN540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | Install Signs - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP140 | SGN540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | Install Signs - NB: 761+67-767+00 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
CP170 | SGN530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN530 | SGN540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Install Signs - NB: 757+10-759+97 - Ph1-S1 | Install Signs - NB: 761+67-767+00 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
CP130 | SGN530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 | CONCRETE | SUB-SIGN
SGN520 | SGN530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Install Signs - NB: 748+30-757+10 - Ph1-S1 | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
PAV330 | SGN520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | Install Signs - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
SGN510 | SGN520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Install Signs - NB: 735+46-746+91 - Ph1-S1 | Install Signs - NB: 748+30-757+10 - Ph1-S1 | 0 | SUB-SIGN | SUB-SIGN
SGN720 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN720 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Procurement: Signage | Install / Remove Signs - SB: 709+50-721+43 - Ph1-S1 | 0 |  | SUB-SIGN
SGN710 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 722+83-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN710 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Procurement: Signage | Install Signs - SB: 722+83-735+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN700 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN700 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Procurement: Signage | Install Signs - SB: 735+46-746+91 - Ph1-S1 | 0 |  | SUB-SIGN
SGN690 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN690 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Procurement: Signage | Install Signs - SB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-SIGN
SGN680 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 757+10-759+97 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN680 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Procurement: Signage | Install Signs - SB: 757+10-759+97 - Ph1-S1 | 0 |  | SUB-SIGN
SGN670 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 761+67-767+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN670 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Procurement: Signage | Install Signs - SB: 761+67-767+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN660 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN660 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Procurement: Signage | Install Signs - SB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-SIGN
SGN650 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 774+82-780+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN650 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Procurement: Signage | Install Signs - SB: 774+82-780+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN640 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN640 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Procurement: Signage | Install Signs - SB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-SIGN
SGN630 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN630 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Procurement: Signage | Install Signs - SB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN620 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN620 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Procurement: Signage | Install Signs - SB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-SIGN
SGN610 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - SB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN610 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Procurement: Signage | Install Signs - SB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-SIGN
SGN600 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 815+20-839+61 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN600 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Procurement: Signage | Install Signs - NB: 815+20-839+61 - Ph1-S1 | 0 |  | SUB-SIGN
SGN590 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 800+00-813+16 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN590 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Procurement: Signage | Install Signs - NB: 800+00-813+16 - Ph1-S1 | 0 |  | SUB-SIGN
SGN580 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 788+09-800+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN580 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Procurement: Signage | Install Signs - NB: 788+09-800+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN570 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 780+00-786+69 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN570 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Procurement: Signage | Install Signs - NB: 780+00-786+69 - Ph1-S1 | 0 |  | SUB-SIGN
SGN560 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 774+82-780+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN560 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Procurement: Signage | Install Signs - NB: 774+82-780+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN550 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 767+00-773+42 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN550 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Procurement: Signage | Install Signs - NB: 767+00-773+42 - Ph1-S1 | 0 |  | SUB-SIGN
SGN540 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 761+67-767+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN540 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Procurement: Signage | Install Signs - NB: 761+67-767+00 - Ph1-S1 | 0 |  | SUB-SIGN
SGN530 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 757+10-759+97 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN530 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Procurement: Signage | Install Signs - NB: 757+10-759+97 - Ph1-S1 | 0 |  | SUB-SIGN
SGN520 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 748+30-757+10 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN520 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Procurement: Signage | Install Signs - NB: 748+30-757+10 - Ph1-S1 | 0 |  | SUB-SIGN
DSS110 | SGN70 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-101) - SB: 723+54 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-101 / 723+54 | 0 | SUB-ST-DRSFT
DSS130 | SGN80 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-102) - SB: 736+00 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-102 / 736+00 | 0 | SUB-ST-DRSFT
DSS160 | SGN100 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-102) - SB: 745+96 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-102 / 745+96 | 0 | SUB-ST-DRSFT
DSS200 | SGN120 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-103) - SB: 758+73 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-103 / 758+73 | 0 | SUB-ST-DRSFT
DSS230 | SGN130 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-104 / 771+34 | 0 | SUB-ST-DRSFT
DSS290 | SGN150 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-106 / 783+35 | 0 | SUB-ST-DRSFT
DSS300 | SGN160 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-104) - SB: 792+45 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-104 / 792+45 | 0 | SUB-ST-DRSFT
DSS340 | SGN180 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-105) - SB: 808+47 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-105 / 808+47 | 0 | SUB-ST-DRSFT
DSS360 | SGN200 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHB-101) - SB: 818+78 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHB-01 / 818+78 | 0 | SUB-ST-DRSFT
DSS390 | SGN210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-108 / 825+75 | 0 | SUB-ST-DRSFT
BW340 | SGN210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-108 / 825+75 | 0
DSS370 | SGN210 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-108 / 825+75 | 0 | SUB-ST-DRSFT
DSS400 | SGN220 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 833+46 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-107 / 833+46 | 0 | SUB-ST-DRSFT
BW310 | SGN170 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-107 / 800+70 | 0
DSS310 | SGN170 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-107 / 800+70 | 0 | SUB-ST-DRSFT
DSS350 | SGN190 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-106) - NB: 811+90 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-106 / 811+90 | 0 | SUB-ST-DRSFT
DSS330 | SGN170 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 800+70 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-107 / 800+70 | 0 | SUB-ST-DRSFT
BW260 | SGN150 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-106 / 783+35 | 0
DSS270 | SGN150 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-106 / 783+35 | 0 | SUB-ST-DRSFT
BW240 | SGN140 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-105 / 775+55 | 0
DSS240 | SGN140 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-105 / 775+55 | 0 | SUB-ST-DRSFT
DSS260 | SGN140 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-105 / 775+55 | 0 | SUB-ST-DRSFT
BW140 | SGN130 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-104 / 771+34 | 0
DSS210 | SGN130 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-104 / 771+34 | 0 | SUB-ST-DRSFT
BW130 | SGN110 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-103 / 750+92 | 0
DSS170 | SGN110 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-103 / 750+92 | 0 | SUB-ST-DRSFT
DSS190 | SGN110 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-103 / 750+92 | 0 | SUB-ST-DRSFT
BW110 | SGN80 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Barrier Wall / Sign Pedestal (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-102 / 736+00 | 0
DSS120 | SGN80 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-102 / 736+00 | 0 | SUB-ST-DRSFT
DSS150 | SGN90 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHC-101) - NB: 739+29 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHC-101 / 739+29 | 0 | SUB-ST-DRSFT
DSS100 | SGN70 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.2.1.4.2.3 Preconstruction: Procurement: Electrical / ITS: Structure / Gantry | Install Sign Drilled Shaft Foundation (OHS-101) - NB: 723+54 - Ph1-S1 | Procurement: Sign Posts / Gantry - OHS-101 / 723+54 | 0 | SUB-ST-DRSFT
SGN60 | DSS400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 833+46 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 0
SGN60 | DSS370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHB-101) - SB: 818+78 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHC-106) - NB: 811+90 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHC-105) - SB: 808+47 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 800+70 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 0
SGN60 | DSS310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHC-104) - SB: 792+45 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0
SGN60 | DSS270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 0
SGN60 | DSS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0
SGN60 | DSS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHC-103) - SB: 758+73 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0
SGN60 | DSS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHC-102) - SB: 745+96 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHC-101) - NB: 739+29 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | BW110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Barrier Wall / Sign Pedestal (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 0
SGN60 | DSS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-102) - SB: 736+00 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
SGN60 | DSS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.2 Preconstruction: Procurement: Electrical / ITS: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Procurement: Sign Foundations (Drilled Shafts) | Install Sign Drilled Shaft Foundation (OHS-101) - NB: 723+54 - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DSS160 | DSS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-102) - SB: 745+96 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-102) - SB: 736+00 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS230 | DSS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHC-103) - SB: 758+73 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS290 | DSS230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-106) - SB: 783+35 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-104) - SB: 771+73 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS340 | DSS300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHC-105) - SB: 808+47 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHC-104) - SB: 792+45 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS390 | DSS360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHB-101) - SB: 818+78 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS370 | DSS390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-108) - SB: 825+75 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
BW310 | BW340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 0
DSS310 | DSS400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 833+46 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DEMO670 | DEMO730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 0 | DEMO | DEMO
BW260 | BW310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 0
DSS270 | DSS330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 800+70 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DEMO590 | DEMO670 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 0 | DEMO | DEMO
BW240 | BW260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0
DSS240 | DSS270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DEMO530 | DEMO590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0 | DEMO | DEMO
BW140 | BW240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 0
DSS210 | DSS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DEMO480 | DEMO530 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 0 | DEMO | DEMO
BW130 | BW140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0
DEMO330 | DEMO480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0 | DEMO | DEMO
DSS120 | DSS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS100 | DSS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-101) - NB: 723+54 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHC-101) - NB: 739+29 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS370 | BW340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO730 | DSS370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-108 - Median) - NB: 825+75 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
DSS330 | DSS350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-107) - NB: 800+70 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHC-106) - NB: 811+90 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS310 | BW310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO670 | DSS310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-107 - Median) - NB: 800+70 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
DSS270 | BW260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO590 | DSS270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-106 - Median) - NB: 783+35 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
EGC160 | DSS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-105) - NB: 775+55 - Ph1-S1 | 0 | EW-SML | SUB-ST-DRSFT
DSS240 | BW240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO530 | DSS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-105 - Median) - NB: 775+55 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
DSS210 | BW140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO480 | DSS210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-104 - Median) - NB: 771+73 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
DSS190 | DSS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DSS190 | BW130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-103) - NB: 750+92 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO300 | DEMO330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Demo Median Barrier Wall for Drilled Shaft (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0 | DEMO | DEMO
DSS170 | BW130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO330 | DSS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-103 - Median) - NB: 750+92 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
DSS120 | BW110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Install Barrier Wall / Sign Pedestal (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 0 | SUB-ST-DRSFT
DEMO300 | DSS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Demo Median Barrier Wall for Drilled Shaft (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-102 - Median) - NB: 736+00 - Ph1-S1 | 0 | DEMO | SUB-ST-DRSFT
EGC100 | DSS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Install Sign Drilled Shaft Foundation (OHS-101) - NB: 723+54 - Ph1-S1 | 0 | EW-SML | SUB-ST-DRSFT
R850A | SUBS1220 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - West Half - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R850A | SUBS850 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - West Half - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
DEMO1130 | R850A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - West Half - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R850A | R855 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - West Half - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R790A | SUBS1320 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - West Half - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
DEMO1030 | R790A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - West Half - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R790A | R795 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - West Half - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R720A | SUBS1230 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R720A | SUBS700 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
DEMO270 | R720A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R720A | R725 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
RET30 | R720A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Procurement: Anchored Retaining Walls | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND30 | R720A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Procurement: Foundations: H-Pile Foundations | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - West Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
R655A | SUBS1360 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
DEMO180 | R655A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R655A | R660 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
RET30 | R655A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Procurement: Anchored Retaining Walls | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND30 | R655A | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Procurement: Foundations: H-Pile Foundations | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - West Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
BASE610 | BASE640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Black Base - SB: 761+67-767+00 - Ph1-S1 | Black Base - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE570 | BASE610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Black Base - SB: 767+00-773+42 - Ph1-S1 | Black Base - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE560 | BASE570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Black Base - SB: 774+82-780+00 - Ph1-S1 | Black Base - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE550 | BASE560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Black Base - SB: 780+00-786+69 - Ph1-S1 | Black Base - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE530 | BASE550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Black Base - SB: 788+09-800+00 - Ph1-S1 | Black Base - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE480 | BASE530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Black Base - SB: 800+00-813+16 - Ph1-S1 | Black Base - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE470 | BASE480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Black Base - SB: 815+20-839+61 - Ph1-S1 | Black Base - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE350 | BASE400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 800+00-813+16 - Ph1-S1 | Black Base - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE230 | BASE240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Black Base - NB: 767+00-773+42 - Ph1-S1 | Black Base - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE200 | BASE220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Black Base - NB: 757+10-759+97 - Ph1-S1 | Black Base - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE190 | BASE200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Black Base - NB: 748+30-757+10 - Ph1-S1 | Black Base - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE180 | BASE190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Black Base - NB: 735+46-746+91 - Ph1-S1 | Black Base - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | EW-ABC
BASE320 | BASE340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Black Base - NB: 780+00-786+69 - Ph1-S1 | Black Base - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | EW-ABC
R655 | SUBS1360 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R790 | SUBS1320 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - East Half - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R675 | SUBS1330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R810 | SUBS1290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R700 | SUBS1280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R830 | SUBS1260 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R720 | SUBS1230 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R850 | SUBS1220 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - East Half - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R850 | SUBS850 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - East Half - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R720 | SUBS700 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R830 | SUBS790 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R700 | SUBS640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R810 | SUBS470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R675 | SUBS430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R770 | SUBS310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-7A @ East Lake Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R635 | SUBS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-5D @ East Lake Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R745 | SUBS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-3A @ Floribraska - North Side - Ph1-S1-S2 | Form / Reinforce / Pour End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
R610 | SUBS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-CIP | ST-BRIDGE-SUB
DEMO1610 | SUBS1320 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1610 | SUBS1360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1590 | SUBS1290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1590 | SUBS1330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1570 | SUBS1280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1570 | SUBS1260 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1550 | SUBS1230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1550 | SUBS1220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1520 | SUBS850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1520 | SUBS700 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1460 | SUBS790 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1460 | SUBS640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1420 | SUBS470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1420 | SUBS430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1400 | SUBS400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1400 | SUBS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1370 | SUBS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1370 | SUBS310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1330 | SUBS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DEMO1330 | SUBS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Demo End of Existing End Bent - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUB
DS150 | DS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Install 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS110 | DS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
DS100 | DS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Install 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | 0 | SUB-ST-DRSFT | SUB-ST-DRSFT
PILE250 | PILE290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE180 | PILE200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Drive Production H-Piles 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE160 | PILE180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE150 | PILE160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Drive Production H-Piles 100204 - NB: over MLK Blvd - Ph1-S1 | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE130 | PILE150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | Drive Production H-Piles 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-PILE | ST-PILE
PILE100 | PILE130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-PILE | ST-PILE
DEMO1600 | DEMO1620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | Demo Existing Deck 100207 - SB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1580 | DEMO1600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Edge of Deck 100206 - SB: over Chelsea St. - Ph1-S1 | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1560 | DEMO1580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Edge of Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Demo Edge of Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1480 | DEMO1530 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Demo Edge of Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1440 | DEMO1480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1410 | DEMO1440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1380 | DEMO1410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Edge of Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1350 | DEMO1380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Edge of Deck 100207 - NB: over East Lake - Ph1-S1 | Demo Edge of Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1310 | DEMO1350 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Edge of Deck 100201 - NB: over Floribraska - Ph1-S1 | Demo Edge of Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1500 | DEMO1510 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Demo Traffic Railing 100204 - SB: over MLK - Ph1-S1 | 0 | DEMO | DEMO
DEMO1490 | DEMO1500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Demo Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DEMO | DEMO
DEMO1450 | DEMO1470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Demo Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DEMO | DEMO
DEMO1430 | DEMO1450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Demo Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DEMO | DEMO
DEMO1390 | DEMO1430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Demo Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DEMO | DEMO
DEMO1360 | DEMO1390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | Demo Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DEMO | DEMO
DEMO1340 | DEMO1360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | Demo Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DEMO | DEMO
DEMO | DEMO1340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Traffic Railing 100201 - NB: over Floribraska - Ph1-S1 | Demo Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | 0 | DEMO | DEMO
DEMO1590 | DEMO1610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | Demo End of Existing End Bent 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1570 | DEMO1590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo End of Existing End Bent 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1520 | DEMO1550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1460 | DEMO1520 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1420 | DEMO1460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1400 | DEMO1420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1370 | DEMO1400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
DEMO1330 | DEMO1370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo End of Existing End Bent - NB: over Floribraska - Ph1-S1 | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
R840 | R860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R820 | R840 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R800 | R820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Pour Sidewalk @ MLK Blvd.- North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R780 | R800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R755 | R780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R835 | R855 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Pour Slope Pavement @ E. Osborne Ave - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R775 | R795 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Pour Slope Pavement @ East Lake Ave. - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R750 | R775 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R810 | R830 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
R770 | R810 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Reinforce / Pour Gravity Wall W-7A @ East Lake Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | 0 | ST-CIP | ST-CIP
DEMO1090 | DEMO1130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Demo Existing Slope Pavement @ E. Osborne Ave.- North Side - Ph1-S1-S2 | Demo Existing Slope Pavement @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | 0 | DEMO | DEMO
DEMO1030 | DEMO1060 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | Demo Existing Slope Pavement @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | DEMO | DEMO
DEMO1000 | DEMO1030 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Demo Existing Slope Pavement @ East Lake Ave.- North Side - Ph1-S1-S2 | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | DEMO | DEMO
DEMO970 | DEMO1000 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Demo Existing Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | Demo Existing Slope Pavement @ East Lake Ave.- North Side - Ph1-S1-S2 | 0 | DEMO | DEMO
MS370 | MS380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-1A, 1B, 1C - RAMP NE: 714+80.00-717+20.23 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS240 | MS250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS230 | MS240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MSE860 | MSE890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE660 | MSE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE500 | MSE550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
BW800 | BW850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | BARRIER | BARRIER
BW730 | BW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | BARRIER | BARRIER
BW600 | BW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | BARRIER | BARRIER
BW530 | BW570 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 170+00.00-177+80.95 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | BARRIER | BARRIER
BW270 | BW300 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 104+06.12-107+60.00 - Ph1-S1 | 0 | BARRIER | BARRIER
BW180 | BW270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | 0 | BARRIER | BARRIER
BW1060 | BW1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
EGC300 | BW1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 38+98.75-44+00.00 - Ph1-S1 | 0 | EW-SML | BARRIER
BW1010 | BW1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | BARRIER | BARRIER
MSE1110 | MSE1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
BW980 | BW1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | BARRIER | BARRIER
EGC290 | BW1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | EW-SML | BARRIER
EGC280 | BW1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.2 Construction: Phase 1: Stage 1: I-275 SB: 104+50.80 to 107+11.78: Barrier Wall (RAMP MLKA) | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 104+50.80-107+11.78 (RAMP MLKA) - Ph1-S1 | 0 | EW-SML | BARRIER
MSE1070 | MSE1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
BW940 | BW980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 64+06.16-69+52.31 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | BARRIER | BARRIER
BW890 | BW940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | BARRIER | BARRIER
BW850 | BW890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | BARRIER | BARRIER
EGC260 | BW890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.2 Construction: Phase 1: Stage 1: I-275 SB: ~465+30 to 468+72.82: Barrier Wall (RAMP MLKD) | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP MLKD: ~465+30-468+72.82 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC260 | BW850 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.1 Construction: Phase 1: Stage 1: I-275 SB: 472+02.74 to 473+19.41: Barrier Wall | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 472+02.74-473+19.41 - Ph1-S1 | 0 | EW-SML | BARRIER
MS350 | MS360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Form / Reinforce / Pour Moment Slab - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MSE1030 | MSE1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
BW770 | BW800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | BARRIER | BARRIER
EGC250 | BW800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | 0 | EW-SML | BARRIER
BW800 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.2 Construction: Phase 1: Stage 1: I-275 SB: 77+25.61 to 79+58.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 77+25.61-79+58.07 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
MS340 | MS350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS330 | MS340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | CONCRETE | CONCRETE
TCW380 | MSE950 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Wall & Lagging Crew - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | Install Leveling Pad - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
PILE290 | MSE950 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
MSE950 | MSE990 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Install Leveling Pad - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS310 | MS320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS300 | MS310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Form / Reinforce / Pour Moment Slab - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS290 | MS300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | CONCRETE | CONCRETE
BW670 | BW730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | BARRIER | BARRIER
EGC220 | BW730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | 0 | EW-SML | BARRIER
BW730 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 92+99.11-98+00.00 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW630 | BW670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | BARRIER | BARRIER
MSE830 | MSE860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
TCW360 | MSE860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC220 | MSE860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
PILE250 | MSE860 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
MS310 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.3 Construction: Phase 1: Stage 1: I-275 SB: 812+00.00 to 812+95.64: MSE Wall W-17C | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-17C - SB: 812+00.00-812+95.64 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS280 | MS290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS270 | MS280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS280 | DEMO1650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Form / Reinforce / Pour Moment Slab - MSE Wall W-20B - RAMP HILLSD: 423+56.61-424+94.59 - Ph1-S1 | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | 0 | CONCRETE | DEMO
BW570 | BW600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | BARRIER | BARRIER
MSE610 | MSE660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Install Leveling Pad - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
EGC200 | BW530 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 170+00.00-177+80.95 - Ph1-S1 | 0 | EW-SML | BARRIER
MS230 | BASE340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Black Base - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | EW-ABC
MS230 | STAB250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
TCW310 | MSE600 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Wall & Lagging Crew - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC180 | MSE600 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
PILE180 | MSE600 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.4 Construction: Phase 1: Stage 1: I-275 NB: 794+49.71 to 795+95.08: MSE Wall W-15D | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-15D - NB: 794+49.71-795+95.08 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
BW410 | BW440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | BARRIER | BARRIER
BW440 | BW470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | BARRIER | BARRIER
EGC190 | BW440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | EW-SML | BARRIER
BW440 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
EGC180 | BW440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | 0 | EW-SML | BARRIER
BW440 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 145+55.54-209+44.37 (RAMP HILLSB) - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
MSE460 | MSE500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Install Leveling Pad - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE340 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MS190 | MS200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS180 | MS190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Form / Reinforce / Pour Moment Slab - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS200 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS190 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MSE390 | MSE400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
TCW300 | MSE460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | Install Leveling Pad - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC160 | MSE460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
PILE160 | MSE460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.3 Construction: Phase 1: Stage 1: I-275 NB: 777+02.51 to 779+33.94: MSE Wall W-13D | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | Install Leveling Pad - MSE Wall W-13D - NB: 777+02.51-779+33.94 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
TCW300 | MSE400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | Install Leveling Pad - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC160 | MSE400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
PILE160 | MSE400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.2 Construction: Phase 1: Stage 1: I-275 NB: 775+09.33 to 777+02.51: MSE Wall W-13C | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | Install Leveling Pad - MSE Wall W-13C - NB: 775+09.33-777+02.51 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
EGC140 | BW370 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | 0 | EW-SML | BARRIER
BW370 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.2 Construction: Phase 1: Stage 1: I-275 NB: 365+01.75 to 373+45.01: Barrier Wall (RAMP MLKC) | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 365+01.75-373+45.01 (RAMP MLKC) - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
MSE300 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
BW100 | BW180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | 0 | BARRIER | BARRIER
EGC110 | BW180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC100 | BW180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | 0 | EW-SML | BARRIER
BW180 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW180 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 610+36.08-81+47.63 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | BARRIER | EW-CEM
TCW280 | MSE150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | Install Leveling Pad - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC110 | MSE150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
MS120 | STAB180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.7 Construction: Phase 1: Stage 1: I-275 NB: 742+25.00 to 746+69.47: MSE Wall W-5B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-5B - NB: 742+25.00-746+69.47 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | EW-CEM
TCW280 | MSE120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | Install Leveling Pad - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC110 | MSE120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
MS110 | STAB180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.6 Construction: Phase 1: Stage 1: I-275 NB: 739+27.00 to 742+25.00: MSE Wall W-5A | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-5A - NB: 739+27.00-742+25.00 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | EW-CEM
TCW270 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
EGC100 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
MS100 | STAB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
TCC110 | MSE100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.4 Construction: Phase 1: Stage 1: I-275 NB: 723+02.10 to 728+32.19: MSE Wall W-3C | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-3C - NB: 723+02.10-728+32.19 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
STAB190 | STAB200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Stabilization - NB: 748+30-757+10 - Ph1-S1 | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-CEM | EW-CEM
PAV310 | SGN510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | Install Signs - NB: 735+46-746+91 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
SGN510 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN510 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Procurement: Signage | Install Signs - NB: 735+46-746+91 - Ph1-S1 | 0 |  | SUB-SIGN
PAV300 | SGN500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Asphalt Paving - Shoulder - NB: 722+83-735+00 - Ph1-S1 | Install Signs - NB: 709+50-735+00 - Ph1-S1 | 0 | SUB-ASPH | SUB-SIGN
SGN500 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Install Signs - NB: 709+50-735+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-SIGN
SGN30 | SGN500 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Procurement: Signage | Install Signs - NB: 709+50-735+00 - Ph1-S1 | 0 |  | SUB-SIGN
PM210 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Final Pavement Markings - Side Roads - Project Limits - Ph3 | End of Phase 3 | 0 | SUB-STRIP
PM220 | PM230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-STRIP | SUB-STRIP
R3510 | PM230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | 0 | SUB-DGRIND | SUB-STRIP
PM230 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Final Pavement Markings - I-275 SB & Ramps - Project Limits - Ph3 | End of Phase 3 | 0 | SUB-STRIP
STAB520 | STAB530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Stabilization - SB: 722+83-735+00 - Ph1-S1 | Stabilization - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB500 | STAB520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Stabilization - SB: 735+46-746+91 - Ph1-S1 | Stabilization - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB470 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Stabilization - SB: 748+30-757+10 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB450 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Stabilization - SB: 757+10-759+97 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB380 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Stabilization - SB: 780+00-786+69 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB360 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Stabilization - SB: 788+09-800+00 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB340 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Stabilization - SB: 800+00-813+16 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB330 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Stabilization - SB: 815+20-839+61 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB290 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Stabilization - NB: 815+20-839+61 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB260 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Stabilization - NB: 800+00-813+16 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB250 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Stabilization - NB: 788+09-800+00 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB240 | STAB250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Stabilization - NB: 780+00-786+69 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB230 | STAB240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Stabilization - NB: 774+82-780+00 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB220 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Stabilization - NB: 767+00-773+42 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB210 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Stabilization - NB: 761+67-767+00 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-CEM | EW-CEM
STAB190 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Stabilization - NB: 748+30-757+10 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-CEM | EW-CEM
EGC310 | EGC320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC300 | EGC310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC290 | EGC300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC280 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC270 | EGC280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC260 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC250 | EGC260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC240 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC230 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC220 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC210 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC200 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC110 | EGC120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC100 | EGC110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | EW-SML
MS-P1S1S | DEMO1640 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Start of Phase 1, Stage 1 | Demo / Grade - Hillsborough Ramp C2 - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO1630 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Start of Phase 1, Stage 1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO750 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp B | Start of Phase 1, Stage 1 | Demo / Grade - Hillsborough Ramp B - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO570 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp C | Start of Phase 1, Stage 1 | Demo / Grade - MLK Ramp C - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO1650 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Start of Phase 1, Stage 1 | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO1660 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Start of Phase 1, Stage 1 | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO1670 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Start of Phase 1, Stage 1 | Demo / Grade - MLK Ramp D - Ph1-S1 | 0 |  | DEMO
MS-P1S1S | DEMO1680 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp A | Start of Phase 1, Stage 1 | Demo / Grade - MLK Ramp A - Ph1-S1 | 0 |  | DEMO
R710 | R730 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Sidewalk @ E. Osborne Ave - South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R645 | R665 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Pour Sidewalk @ East Lake Ave. - South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R705 | R725 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Slope Pavement @ E. Osborne Ave - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R640 | R660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Pour Slope Pavement @ East Lake Ave. - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R675 | R700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
R635 | R675 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Reinforce / Pour Gravity Wall W-5D @ East Lake Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | 0 | ST-CIP | ST-CIP
DEMO250 | DEMO270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Demo Existing Slope Pavement @ E. Osborne Ave.- South Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 | DEMO | DEMO
DEMO220 | DEMO250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Demo Existing Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ E. Osborne Ave.- South Side - Ph1-S1-S1 | 0 | DEMO | DEMO
DEMO160 | DEMO180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Demo Existing Slope Pavement @ East Lake Ave.- South Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | DEMO | DEMO
DEMO120 | DEMO160 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Demo Existing Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ East Lake Ave.- South Side - Ph1-S1-S1 | 0 | DEMO | DEMO
SP10 | MS-P1S1S | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Mobilization - IPh1 | Start of Phase 1, Stage 1 | 0
CG100 | MS-P1S1S1S | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Start of Phase 1, Stage 1, Step 1 | 0 | SUB-EW-C&G
PAV230 | PAV240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.6 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp NE | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp NE - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV220 | PAV230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Floribraska Ramp D | Asphalt Paving: Temporary Diversion: SB: MLK Ramp A - IPh1 | Asphalt Paving: Temporary Diversion: SB: Floribraska Ramp D - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV190 | PAV200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.IP1.5.2.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: MLK Ramp D | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | Asphalt Paving: Temporary Diversion: SB: MLK Ramp D - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV170 | PAV190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.2.1 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.IP1.5.2.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: SB: Hillsborough Ramp A | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp D - IPh1 | Asphalt Paving: Temporary Diversion: SB: Hillsborough Ramp A - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV140 | PAV150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.IP1.5.1.5 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C1 - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV120 | PAV140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.IP1.5.1.4 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp C2 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp C2 - IPh1 | 0 | SUB-ASPH | SUB-ASPH
PAV110 | PAV120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.5.1.2 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: MLK Ramp C | 3462-FDOT-Owner-12.4.IP1.5.1.3 Construction: Initial Phase 1: Temporary Diversion Pavement at Ramps: NB: Hillsborough Ramp B | Asphalt Paving: Temporary Diversion: NB: MLK Ramp C - IPh1 | Asphalt Paving: Temporary Diversion: NB: Hillsborough Ramp B - IPh1 | 0 | SUB-ASPH | SUB-ASPH
EGC570 | EGC580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | 0 | EW-SML | EW-SML
EGC560 | EGC570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | 0 | EW-SML | EW-SML
EGC540 | EGC560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | 0 | EW-SML | EW-SML
EGC520 | EGC540 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | 0 | EW-SML | EW-SML
EGC490 | EGC510 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | 0 | EW-SML | EW-SML
CG100 | DRGS295 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS295 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Procurement: Drainage Pipe & Structures | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | 0 |  | DRAIN
DRGS295 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS295 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS295 | DRG1580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-303 to S-302 - Lower (18") - SB:834 - 835 - IPh1 | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG1580A | STAB330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-303 to S-302 - Upper (18") - SB: 834-835 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRSG245 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRSG245 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
EGC520 | DRGS280 | SS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | 3 | EW-SML | DRAIN
EGC520 | DRGS270 | SS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | 3 | EW-SML | DRAIN
EGC520 | DRGS250 | SS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | 3 | EW-SML | DRAIN
CG100 | DRSG245 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRSG245 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Procurement: Drainage Pipe & Structures | Drainage: S-218 to S-217 - Lower (24") - SB:823 - 824 - IPh1 | 0 |  | DRAIN
DRG1490A | STAB330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-218 to S-217 - Upper (24") - SB: 823-824 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG260A | STAB330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-227B to S-227A - Upper (18") - SB: 826-827 - Swale 2 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGS260 | DRG260A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | Drainage: S-227B to S-227A - Upper (18") - SB: 826-827 - Swale 2 - Ph1-S1 | 0 | DRAIN | DRAIN
DRGS210 | DRG210A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | 0 | DRAIN | DRAIN
EGC220 | DRG210A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | 0 | EW-SML | DRAIN
DRG210A | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-154 to S-153 - Upper (18") - SB: 804-805 - Swale 1A - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG140A | STAB360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: S-139 OF to S-139 - Upper (18") - SB: 800-802 - Swale 1A - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC540 | DRGS210 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | 3 | EW-SML | DRAIN
EGC540 | DRGS190 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 3 | EW-SML | DRAIN
EGC540 | DRGS140 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | 3 | EW-SML | DRAIN
CG100 | DRGS1180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS1180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Procurement: Drainage Pipe & Structures | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | 0 |  | DRAIN
EGC570 | DRGS1180 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | 6 | EW-SML | DRAIN
DRGS1180 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS1180 | DRG1180A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-84 to S-85 (18") - Lower - SB: 768 - 769 - Swale 0A - IPh1 | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | 0 | DRAIN | DRAIN
EGC270 | DRG1180A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1180A | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-84 to S-85 (18") - Upper - SB: 768-769 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
CG100 | DRGS1230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS1230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | 0 |  | DRAIN
EGC560 | DRGS1230 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
DRGS1230 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS1230 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS1230 | DRG1230A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-112 to S-113 (24") - Lower - SB:781 - 782 - Swale 0B - IPh1 | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | 0 | DRAIN | DRAIN
EGC240 | DRG1230A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1230A | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-112 to S-113 (24") - Upper - SB: 781-782 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGS65 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS65 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
EGC560 | DRGS65 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | 3 | EW-SML | DRAIN
DRG30 | DRGS65 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | 0 |  | DRAIN
CG100 | DRGS65 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS65 | DRG1260A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-101 to S-100 - Lower (18" - Swale 0B) - SB:777 - 778 - IPh1 | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | 0 | DRAIN | DRAIN
EGC250 | DRG1260A | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1260A | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Drainage: S-101 to S-100 - Upper (18") - SB: 777-778 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC560 | DRGS90 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
EGC560 | DRGS80 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
EGC560 | DRGS70 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
EGC560 | DRGS60 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
EGC560 | DRGS130 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
EGC560 | DRGS100 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | 3 | EW-SML | DRAIN
DRGS90 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS80 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS70 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS60 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS130 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS120 | EGC240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS110 | EGC240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS100 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS90 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS80 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS70 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS60 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS130 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS120 | EGC250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS110 | EGC250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS100 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-SML
EGC560 | EGC240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC560 | EGC250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | EW-SML
DRGS50 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS40 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS30 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-SML
EGC570 | DRGS50 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | 6 | EW-SML | DRAIN
EGC570 | DRGS40 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | 6 | EW-SML | DRAIN
EGC570 | DRGS30 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | 6 | EW-SML | DRAIN
SP10 | EGC470 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Mobilization - IPh1 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | 5 |  | EW-SML
SP10 | EGC480 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Mobilization - IPh1 | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | 5 |  | EW-SML
SP10 | EGC490 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Mobilization - IPh1 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | 5 |  | EW-SML
SP10 | EGC510 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Mobilization - IPh1 | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | 5 |  | EW-SML
SP10 | EGC520 | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Mobilization - IPh1 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 5 |  | EW-SML
SP10 | EGC540 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Mobilization - IPh1 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | 5 |  | EW-SML
SP10 | EGC560 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Mobilization - IPh1 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | 5 |  | EW-SML
SP10 | EGC570 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Mobilization - IPh1 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | 5 |  | EW-SML
DRGS20 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS10 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-SML
EGC580 | DRGS10 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | 0 | EW-SML | DRAIN
DRGS240 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS230 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS220 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG580 | DRG580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG570 | DRG570A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-1 to S-151 - Lower (18") - NB: 804 - 805 - IPh1 | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | 0 | DRAIN | DRAIN
DRG110 | EGC110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Drainage: CS-1A to CS-1A OUT (18") - NB: 737 - 738 - IPh1 | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG580 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG570 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-1 to S-151 - Lower (18") - NB: 804 - 805 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG560 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-151 OF to S-151 (30") - NB: 804 - 805 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG550 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-150 to S-151 (30") - NB: 804 - 805 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG540 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-145 to S-150 (30") - NB: 801 - 805 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG530 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-144 to S-145 (30") - NB: 801 - 802 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG520 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-144 OF to S-144 (30") - NB: 801 - 802 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
EGC480 | DRG580 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | Drainage: S-146 OF to S-146 - Lower (14"x23") - NB: 801 - 802 - IPh1 | 5 | EW-SML | DRAIN
EGC190 | DRG580A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG580A | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-146 OF to S-146 - Upper (14"x23") - NB: 801-802 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC190 | DRG570A | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG570A | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: CS-1 to S-151 - Upper (18") - NB: 804-805 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC490 | DRGS240 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | 5 | EW-SML | DRAIN
EGC490 | DRGS220 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | 5 | EW-SML | DRAIN
EGC470 | DRG120 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | Drainage: S-30 to S-30 OUT - Lower (18") - NB: 738 - 739 - IPh1 | 5 | EW-SML | DRAIN
EGC470 | DRG110 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | Drainage: CS-1A to CS-1A OUT (18") - NB: 737 - 738 - IPh1 | 5 | EW-SML | DRAIN
DRG120A | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Drainage: S-30 to S-30 OUT - Upper (18") - NB: 738-739) - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-CEM
RDW40 | TCW270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW370 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW340 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW400 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW410 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW420 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 |  | ST-WALL
RDW40 | TCW280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Procurement: Temp Critical Walls: Lagging Wall | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 0 |  | ST-WALL
SP10 | MS-P1S1S1S | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Mobilization - IPh1 | Start of Phase 1, Stage 1, Step 1 | 0
MS-IP1F | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | End of Initial Phase 1 | End of Phase 1, Stage 1 | 0
TCW420 | TCW430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 0 | ST-WALL | ST-WALL
TCW410 | TCW420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 | ST-WALL | ST-WALL
TCW400 | TCW410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 0 | ST-WALL | ST-WALL
TCW390 | TCW400 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 0 | ST-WALL | ST-WALL
TCW360 | TCW370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 0 | ST-WALL | ST-WALL
TCW350 | TCW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 | ST-WALL | ST-WALL
TCW340 | TCW350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 0 | ST-WALL | ST-WALL
TCW330 | TCW340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 0 | ST-WALL | ST-WALL
TCW320 | TCW330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 | ST-WALL | ST-WALL
TCW300 | TCW310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 0 | ST-WALL | ST-WALL
TCW290 | TCW300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 | ST-WALL | ST-WALL
TCW280 | TCW290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 0 | ST-WALL | ST-WALL
TCW270 | TCW280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 0 | ST-WALL | ST-WALL
PILE350 | PILE360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE330 | PILE350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE310 | PILE330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE300 | PILE310 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | H Pile Install - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE270 | PILE280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | H Pile Install - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE240 | PILE260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE230 | PILE240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE220 | PILE230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | H Pile Install - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE210 | PILE220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE190 | PILE210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE170 | PILE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE140 | PILE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE120 | PILE140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
PILE110 | PILE120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | H Pile Install - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 0 | ST-SOLDIER | ST-SOLDIER
SP10 | PILE360 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE270 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE260 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE240 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE230 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE220 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE210 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE190 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE280 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE310 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE300 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE170 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE330 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE140 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE350 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 10 |  | ST-SOLDIER
SP10 | PILE110 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 10 |  | ST-SOLDIER
TCW430 | MS-IP1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | End of Initial Phase 1 | 0 | ST-WALL
SP10 | PILE120 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Mobilization - IPh1 | H Pile Install - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 10 |  | ST-SOLDIER
RDW30 | PILE110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE310 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE330 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 0 |  | ST-SOLDIER
RDW30 | PILE350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 |  | ST-SOLDIER
TCW270 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Wall & Lagging Crew - Temp Critical Wall TW-3 (NB: 723+02.10 to 728+00.00) - IPh1 | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW430 | MSE1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW370 | MSE890 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | Wall & Lagging Crew - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW360 | MSE830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW350 | MSE790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Wall & Lagging Crew - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW340 | MSE750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | Wall & Lagging Crew - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW330 | MSE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW320 | MSE660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Wall & Lagging Crew - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW310 | MSE550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Wall & Lagging Crew - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW400 | MSE1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Wall & Lagging Crew - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW390 | MSE990 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Wall & Lagging Crew - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | Install Leveling Pad - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW300 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW410 | MSE1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW290 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW420 | MSE1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
TCW280 | MSE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-WALL | SUB-ST-MSE
PILE310 | TCW400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-14 (SB: 780+80.00 to 777+38.56) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE280 | TCW380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-15A (SB: 790+80.00 to 788+00.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE190 | TCW310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | H Pile Install - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-15CD (NB: 788+00.00 to 795+98.15) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE210 | TCW320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | H Pile Install - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-22 (NB: 835+65.00 to 839+61.51) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE220 | TCW330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-21 (SB: 839+48.05 to 834+00.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE230 | TCW340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-20 (SB: 827+20.00 to 432+40.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE240 | TCW350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-18 (SB: 817+20.00 to 815+39.64) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE260 | TCW360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-17 (SB: 812+95.64 to 811+80.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE270 | TCW370 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-16 (SB: 202+90.00 to 801+20.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE360 | TCW430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-1 (SB: 717+20.23 to 712+56.03) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE300 | TCW390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-13G (SB: 786+80.00 to 785+40.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE170 | TCW300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | H Pile Install - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-13CDE (NB: 775+11.55 to 786+80.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE330 | TCW410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-11 (SB: 468+60.00 to 472+20.00) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE140 | TCW290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | H Pile Install - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-7 (NB: 247+87.37 to 250+88.27) - IPh1 | 0 | ST-SOLDIER | ST-WALL
PILE350 | TCW420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.2.1 Construction: Initial Phase 1: Temporary Critical Walls: SB: Piles | 3462-FDOT-Owner-12.4.IP1.3.2.2 Construction: Initial Phase 1: Temporary Critical Walls: SB: Lagging | H Pile Install - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-6 (SB: 104+50.80 to 102+55.69) - IPh1 | 0 | ST-SOLDIER | ST-WALL
RDW30 | PILE120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | Procurement: Temp Critical Walls: H Pile | H Pile Install - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 0 |  | ST-SOLDIER
PILE120 | TCW280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.3.1.1 Construction: Initial Phase 1: Temporary Critical Walls: NB: Piles | 3462-FDOT-Owner-12.4.IP1.3.1.2 Construction: Initial Phase 1: Temporary Critical Walls: NB: Lagging | H Pile Install - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | Wall & Lagging Crew - Temp Critical Wall TW-5 (NB: 739+27.00 to 746+69.47) - IPh1 | 0 | ST-SOLDIER | ST-WALL
CG100 | DRGS300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS300 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS300 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Procurement: Drainage Pipe & Structures | Drainage: CS-3B to S-307 (18") - SB: 839 - 840 - Swale 3B - IPh1 | 0 |  | DRAIN
CG100 | DRGS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS290 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS290 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Procurement: Drainage Pipe & Structures | Drainage: S-303 OF to S-303 (18") - SB: 834 - 836 - Swale 3B - IPh1 | 0 |  | DRAIN
EGC210 | DRG1600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-305 to Existing (18") - SB: 834-835 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1600 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-305 to Existing (18") - SB: 834-835 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1590 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1590 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-302 to S-305 (18") - SB: 834-835 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
CG100 | DRGS280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS280 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS280 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Procurement: Drainage Pipe & Structures | Drainage: S-229 to Existing (36") - SB: 826 - 828 - Swale 2 - IPh1 | 0 |  | DRAIN
CG100 | DRGS270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS270 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS270 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Procurement: Drainage Pipe & Structures | Drainage: CS-2B to S-229 (24") - SB: 826 - 828 - Swale 2 - IPh1 | 0 |  | DRAIN
CG100 | DRGS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS260 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS260 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Procurement: Drainage Pipe & Structures | Drainage: S-227B to S-227A - Lower (18") - SB: 826 - 827 - Swale 2 - IPh1 | 0 |  | DRAIN
CG100 | DRGS250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS250 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS250 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Procurement: Drainage Pipe & Structures | Drainage: S-224 to S-218 (30") - SB: 823 - 825 - Swale 2 - IPh1 | 0 |  | DRAIN
EGC210 | DRG1570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1570 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-237 OF to S-237 (18") - SB: 829-830 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1560 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-208 to S-207 (18") - SB: 820-822 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1550 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-209 to S-208 (18") - SB: 821-822 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1540 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-210 to S-209 (18") - SB: 822-823 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1530 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-213 to S-210 (18") - SB: 822-823 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1520 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-213 to Existing (18") - SB: 823-824 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1510 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-215 to S-213 (24") - SB: 823-824 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1500 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-217 to S-215 (24") - SB: 823-824 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1480 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-202 to S-204 (12") - SB: 818-819 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1470 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-200 to S-202 (12") - SB: 817-819 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC210 | DRG1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1460 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-200 to S-201 (18") - SB: 817-818 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
CG100 | DRGS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS240 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Procurement: Drainage Pipe & Structures | Drainage: S-246 to S-247 (18") - NB:817 - 818 - IPh1 | 0 |  | DRAIN
CG100 | DRGS230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRGS230 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Procurement: Drainage Pipe & Structures | Drainage: S-246 OF to S-246 (18") - NB:816 - 818 - IPh1 | 0 |  | DRAIN
CG100 | DRGS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Procurement: Drainage Pipe & Structures | Drainage: CS-2A to S-248 (12") - NB:815 - 816 - IPh1 | 0 |  | DRAIN
CG100 | DRGS210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS210 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS210 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-154 to S-153 - Lower (18") - SB:804 - 805 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS200 | EGC230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS200 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-156 to CS-1A (18") - SB:805 - 806 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS190 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS190 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-156 OF to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS180 | EGC230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS180 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-155 to S-156 (30") - SB:805 - 806 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS170 | EGC230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS170 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-143 to S-155 (30") - SB:801 - 805 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-142 to S-143 (30") - SB:801 - 802 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS160 | EGC230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-142 to S-143 (30") - SB:801 - 802 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS160 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-142 to S-143 (30") - SB:801 - 802 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-142 to S-143 (30") - SB:801 - 802 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-142 OF to S-142 (30") - SB:801 - 802 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS150 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-142 OF to S-142 (30") - SB:801 - 802 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS150 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-142 OF to S-142 (30") - SB:801 - 802 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-142 OF to S-142 (30") - SB:801 - 802 - Swale 1A - IPh 1 | 0 |  | DRAIN
CG100 | DRGS140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | 0 | SUB-EW-C&G | DRAIN
DRGS140 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-SML
DRGS140 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-SML
DRG30 | DRGS140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Drainage: S-139 OF to S-139 - Lower (18") - SB:800 - 802 - Swale 1A - IPh 1 | 0 |  | DRAIN
EGC220 | DRG1440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1440 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-172 to S-174 (18") - SB: 809-810 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1430 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-172 to Existing (36") - SB: 809-810 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1420 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-161 to Existing (18") - SB: 806-807 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1410 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-164 to S-170 to Existing (15") - SB: 807-809 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1400 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-165 to Existing (15") - SB: 808-809 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1390 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-166 to S-165 (18") - SB: 808-809 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1380 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-171 to Existing (36") - SB: 808-809 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1370 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-166 to S-171 (36") - SB: 808-809 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1360 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-166 OF to S-166 (30") - SB: 807-808 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | DRG1350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1350 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-162 OF to S-162 to Existing (18") - SB: 806-807 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC230 | DRG1330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: Mitered End to Mitered End (30") - SB: 799-800 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1330 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: Mitered End to Mitered End (30") - SB: 799-800 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC230 | DRG1320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1320 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: S-132 to S-129 (18") - SB: 796-798 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC230 | DRG1310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1310 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: S-133 to S-132 (18") - SB: 797-798 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC230 | DRG1300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1300 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: S-139 to S-133 (18") - SB: 798-801 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC230 | DRG1290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1290 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: Existing to S-126 (15") - SB: 793-795 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC230 | DRG1280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1280 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: S-126 to S-124 (18") - SB: 793-795 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC240 | DRG1250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1250 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Drainage: Existing to S-121 (15") - SB: 784-785 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC240 | DRG1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1240 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-121 OF to S-121 (18") - SB: 784-785 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC240 | DRG1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1220 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-112 to S-118 (18") - SB: 781-782 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC240 | DRG1210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1210 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-112 to S-109 (18") - SB: 780-782 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
CG100 | DRGS130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-113 OF to S-113 (24") - SB:780 - 781 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-107 to S-108 (18") - SB:780 - 781 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-103 to S-107 (18") - SB:777 - 781 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS100 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-102 to S-103 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS90 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS90 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-102 to S-101 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS80 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS80 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: CS-0B to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS70 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS70 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: S-102 OF to S-102 (18") - SB:777 - 778 - Swale 0B - IPh1 | 0 |  | DRAIN
CG100 | DRGS60 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS60 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Drainage: CD-4 Extension (3'x3') - SB:777 - 778 - Swale 0B - IPh1 | 0 |  | DRAIN
EGC260 | DRG1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC260 | DRG1090 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC260 | DRG1080 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC260 | DRG1070 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC270 | DRG1190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1190 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-81 (Structure Only) - SB: 768-769 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
CG100 | DRGS50 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS50 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Procurement: Drainage Pipe & Structures | Drainage: S-85 OF to S-85 (18") - SB: 768 - 770 - Swale 0A - IPh1 | 0 |  | DRAIN
CG100 | DRGS40 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS40 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Procurement: Drainage Pipe & Structures | Drainage: S-87 OF to S-87 (14"x23") - SB: 769 - 770 - Swale 0A - IPh1 | 0 |  | DRAIN
CG100 | DRGS30 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | 0 | SUB-EW-C&G | DRAIN
DRG30 | DRGS30 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Procurement: Drainage Pipe & Structures | Drainage: CS-0A OF to CS-0A OF (14"x23") - SB: 771 - 772 - Swale 0A - IPh1 | 0 |  | DRAIN
EGC270 | DRG1170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1170 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-71 to S-69 (18") - SB: 765-766 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC270 | DRG1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1160 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-75 to S-71 (18") - SB: 766-767 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC270 | DRG1150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1150 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-74 to Existing (15") - SB: 766-767 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC270 | DRG1140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1140 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-75 to S-74 (18") - SB: 766-768 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC270 | DRG1130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1130 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-76 to S-75 (18") - SB: 766-768 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC270 | DRG1120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1120 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-77 to S-76 (18") - SB: 767-768 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC270 | DRG1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1110 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-77 to Existing (30") - SB: 767-768 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG1100 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-64 to S-77 (30") - SB: 766-768 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG1090 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-62 to S-64 (24") - SB: 764-766 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG1080 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-63 to S-62 (18") - SB: 764-765 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC290 | DRG1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1060 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-56 to S-57 (15") - SB: 756-757 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC290 | DRG1050 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1050 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-43A to S-48 (18") - SB: 752-754 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC290 | DRG1040 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1040 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-43 to S-43A (18") - SB: 752-753 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC290 | DRG1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1030 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-43 to S-51 (18") - SB: 752-755 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
CG100 | DRGS20 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | 0 | SUB-EW-C&G | DRAIN
SP10 | DRGS20 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Mobilization - IPh1 | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | 5 |  | DRAIN
DRG30 | DRGS20 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Procurement: Drainage Pipe & Structures | Drainage: S-40 OF to S-40 (14"x23") - SB: 750 - 751 - Swale 1B - IPh1 | 0 |  | DRAIN
CG100 | DRGS10 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | 0 | SUB-EW-C&G | DRAIN
SP10 | DRGS10 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Mobilization - IPh1 | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | 5 |  | DRAIN
DRG30 | DRGS10 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Procurement: Drainage Pipe & Structures | Drainage: CS-1B to S-39 (18") - SB: 748 - 749 - Swale 1B - IPh1 | 0 |  | DRAIN
EGC300 | DRG1010 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1010 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Drainage: S-36 to S-37 (15") - SB: 744-745 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG820 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-301 OF to S-301 (18") - NB: 834-835 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG820 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-301 OF to S-301 (18") - NB: 834-835 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG810 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG810 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-240 to S-242 (18") - NB: 830-832 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG800 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG800 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-239 to S-240 (18") - NB: 830-831 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG790 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-234 to S-235 (18") - NB: 828-829 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG790 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-234 to S-235 (18") - NB: 828-829 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG780 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-231 to Existing (36") - NB: 827-828 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG780 | STAB290 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-231 to Existing (36") - NB: 827-828 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG770 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-232 to S-231 (36") - NB: 827-828 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG770 | STAB290 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-232 to S-231 (36") - NB: 827-828 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG760 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-228 to S-232 (24") - NB: 826-828 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG760 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-228 to S-232 (24") - NB: 826-828 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG750 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: Mitered End to Mitered End (24") - NB: 826-827 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG750 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: Mitered End to Mitered End (24") - NB: 826-827 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG740 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG740 | STAB290 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-226 OF to S-226 (14"x23") - NB: 825-826 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG730 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG730 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-216 to S-214 (18") - NB: 822-823 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG720 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG720 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-221 to S-216 (18") - NB: 823-824 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG710 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-220 to S-221 (18") - NB: 823-824 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG710 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-220 to S-221 (18") - NB: 823-824 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG700 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-205 to S-203 (18") - NB: 819-821 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG700 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-205 to S-203 (18") - NB: 819-821 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG690 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG690 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-205 to S-206 (18") - NB: 820-821 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC200 | DRG680 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG680 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-245 to S-205 (18") - NB: 820-822 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC190 | DRG660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Drainage: S-177 to S-175 to Existing (15") - NB: 810-812 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG660 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-177 to S-175 to Existing (15") - NB: 810-812 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC190 | DRG650 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG650 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-176 to S-177 (15") - NB: 811-812 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC190 | DRG640 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Drainage: S-169 to S-173 (18") - NB: 807-809 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG640 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-169 to S-173 (18") - NB: 807-809 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC190 | DRG630 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Drainage: S-168 to S-169 (18") - NB: 807-808 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG630 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-168 to S-169 (18") - NB: 807-808 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG620 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-167 to S-168 (18") - NB: 807-808 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG610 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-167 OF to S-167 (18") - NB: 807-808 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG600 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-159 OF to S-159 (14"x23") - NB: 806-807 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG590 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-149 OF to S-149 (14"x23") - NB: 804-805 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG510 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Drainage: S-135 OF to S-135 (14"x23") - NB: 798-799 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRG500 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Drainage: S-128 to S-122 (18") - NB: 795-796 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC170 | DRG480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Drainage: S-119 to Existing (15") - NB: 783-784 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG480 | STAB240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-119 to Existing (15") - NB: 783-784 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC170 | DRG470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Drainage: S-115 to S-117 (18") - NB: 781-782 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG470 | STAB240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-115 to S-117 (18") - NB: 781-782 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC170 | DRG460 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Drainage: S-115 to S-110 (18") - NB: 781-782 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG460 | STAB240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-115 to S-110 (18") - NB: 781-782 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC150 | DRG430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Drainage: S-83 OF to S-83 to Existing (18") - NB: 768-769 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG430 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-83 OF to S-83 to Existing (18") - NB: 768-769 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC150 | DRG420 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Drainage: S-79 to S-73 (18") - NB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG420 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-79 to S-73 (18") - NB: 767-768 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC150 | DRG410 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Drainage: S-80 to S-79 (18") - NB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG410 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-80 to S-79 (18") - NB: 767-768 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC150 | DRG400 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Drainage: S-78 to S-80 (18") - NB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG400 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-78 to S-80 (18") - NB: 767-768 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC150 | DRG390 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Drainage: S-78 to Existing (48") - NB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG390 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-78 to Existing (48") - NB: 767-768 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC140 | DRG370 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Drainage: S-66 to S-73 (18") - NB: 766-767 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG370 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Drainage: S-66 to S-73 (18") - NB: 766-767 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC140 | DRG360 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Drainage: S-65 to S-66 (18") - NB: 765-766 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG360 | STAB210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Drainage: S-65 to S-66 (18") - NB: 765-766 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC140 | DRG350 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Drainage: S-60A to S-78 (42") - NB: 766-768 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG350 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Drainage: S-60A to S-78 (42") - NB: 766-768 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC140 | DRG340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Drainage: S-60 to S-60A (42") - NB: 764-766 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG340 | STAB210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Drainage: S-60 to S-60A (42") - NB: 764-766 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | 0 | SUB-JB | DRAIN
EGC120 | DRG320 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG320 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-54 to Existing (15") - NB: 753-755 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | 0 | SUB-JB | DRAIN
EGC120 | DRG310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG310 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-53 to S-54 (18") - NB: 753-755 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | 0 | SUB-JB | DRAIN
EGC120 | DRG300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG300 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-52 to S-53 (18") - NB: 755-756 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | 0 | SUB-JB | DRAIN
EGC120 | DRG290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG290 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-46 to S-50 (18") - NB: 753-755 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG280 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-45 to S-46 (24") - NB: 753-754 - Ph1-S1 | 0 | SUB-JB | DRAIN
DRG280 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-45 to S-46 (24") - NB: 753-754 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-45 to S-49 (18") - NB: 753-754 - Ph1-S1 | 0 | SUB-JB | DRAIN
DRG270 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-45 to S-49 (18") - NB: 753-754 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
DRGJB10 | DRG260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | Drainage: S-42 to S-45 (24") - NB: 751-754 - Ph1-S1 | 0 | SUB-JB | DRAIN
DRG260 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-42 to S-45 (24") - NB: 751-754 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC120 | DRG250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Drainage: S-41 to S-42 (30") - NB: 751-752 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG250 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-41 to S-42 (30") - NB: 751-752 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-22 to Existing (36") - NB: 733-734 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG230 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-22 to Existing (36") - NB: 733-734 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG220 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-22 to S-24 (18") - NB: 733-734 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG210 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-21 OF to S-22 (29"x45") - NB: 733-734 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG210 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-21 OF to S-22 (29"x45") - NB: 733-734 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-16 to S-22 (30") - NB: 729-734 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG200 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-16 to S-22 (30") - NB: 729-734 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-18 to S-15 (18") - NB: 728-730 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG190 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-18 to S-15 (18") - NB: 728-730 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-17 to S-18 (18") - NB: 729-730 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG180 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-17 to S-18 (18") - NB: 729-730 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-16 to S-17 (18") - NB: 729-730 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG170 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-16 to S-17 (18") - NB: 729-730 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC100 | DRG160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: S-13 to S-16 (30") - NB: 726-730 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG160 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: S-13 to S-16 (30") - NB: 726-730 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC110 | DRG140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Drainage: Existing to S-34A to S-34 to Existing (15") - NB: 744-745) - Ph1-S1 | 0 | EW-SML | DRAIN
DRG140 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Drainage: Existing to S-34A to S-34 to Existing (15") - NB: 744-745) - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC110 | DRG130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Drainage: S-31 to Existing (24") - NB: 739-740 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG130 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Drainage: S-31 to Existing (24") - NB: 739-740 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-CEM
ENV10 | ENV20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.5 Preconstruction: Procurement: Environmental | 3462-FDOT-Owner-12.2.1.5 Preconstruction: Procurement: Environmental | Prepare Shop Drawings / Submittals: Environmental Compliance | Review & Approve Shop Drawings / Submittals: Environmental Compliance (Duration = 25 Calendar Days) | 0
ENV20 | SP10 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.5 Preconstruction: Procurement: Environmental | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Review & Approve Shop Drawings / Submittals: Environmental Compliance (Duration = 25 Calendar Days) | Mobilization - IPh1 | 0
MS-IP1S | CG100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Start of Initial Phase 1 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | 0 |  | SUB-EW-C&G
MS-NTP | LOE-CD | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Start Construction | Construction Duration (1200 Calendar Days + 92 FDOT Holidays = 1292 Calendar Day Contract Duration) | 0
MS-CE10 | MS-NTP | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Start-Up | Start Construction | 0
MS-CE | MS-CE10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Contract Execution | Start-Up | 0
ITS20 | ITS30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | Procurement: ITS | 0
ITS10 | ITS20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | Prepare Shop Drawings / Submittals: ITS | Review & Approve Shop Drawings / Submittals: ITS (Duration = 25 Calendar Days) | 0
SGN20 | SGN30 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | Review & Approve Shop Drawings / Submittals: Signage (Duration = 25 Calendar Days) | Procurement: Signage | 0
SGN10 | SGN20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | Prepare Shop Drawings / Submittals: Signage | Review & Approve Shop Drawings / Submittals: Signage (Duration = 25 Calendar Days) | 0
LTG20 | LTG30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | Procurement: Lighting | 0
LTG10 | LTG20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | Prepare Shop Drawings / Submittals: Lighting | Review & Approve Shop Drawings / Submittals: Lighting (Duration = 25 Calendar Days) | 0
DS20 | DS30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Review & Approve Shop Drawings / Submittals: Structural 48" Drilled Shafts (Duration = 25 Calendar Days) (Criteria) | Procurement: Structural 48" Drilled Shafts | 0
DS10 | DS20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Prepare Shop Drawings / Submittals: Structural 48" Drilled Shafts | Review & Approve Shop Drawings / Submittals: Structural 48" Drilled Shafts (Duration = 25 Calendar Days) (Criteria) | 0
DRG20 | DRG30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | Review & Approve Shop Drawings / Submittals: Drainage Pipe & Structures (Duration = 25 Calendar Days) | Procurement: Drainage Pipe & Structures | 0
DRG10 | DRG20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | Prepare Shop Drawings / Submittals: Drainage Pipe & Structures | Review & Approve Shop Drawings / Submittals: Drainage Pipe & Structures (Duration = 25 Calendar Days) | 0
RDW10 | RDW20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | Prepare Shop Drawings / Submittals: Temp Critical Walls | Review & Approve Shop Drawings / Submittals: Temp Critical Walls (Duration = 25 Calendar Days) | 0
RET20 | RET30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) (Deleted) | Procurement: Anchored Retaining Walls | 0
RET10 | RET20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | Review & Approve Shop Drawings / Submittals: Anchored Retaining Walls (Duration = 25 Calendar Days) (Deleted) | 0
SPS20 | SPS30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | Review & Approve Shop Drawings / Submittals: Superstructure (Duration = 25 Calendar Days) | Procurement: 36" FIB's and Type III ASHHTO Beams | 0
SPS10 | SPS20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | Prepare Shop Drawings / Submittals: Superstructure | Review & Approve Shop Drawings / Submittals: Superstructure (Duration = 25 Calendar Days) | 0
SUB20 | SUB30 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | Review & Approve Shop Drawings / Submittals: Substructure (Duration = 25 Calendar Days) | Procurement: Substructure | 0
SUB10 | SUB20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | Prepare Shop Drawings / Submittals: Substructure | Review & Approve Shop Drawings / Submittals: Substructure (Duration = 25 Calendar Days) | 0
MS-LNTP | SUB10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | Notice to Proceed | Prepare Shop Drawings / Submittals: Substructure | 0
FND20 | FND30 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | Procurement: Foundations: H-Pile Foundations | 0
FND10 | FND20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | Prepare Shop Drawings / Submittals: H-Pile Foundations | Review & Approve Shop Drawings / Submittals: H-Pile Foundations (Duration = 25 Calendar Days) | 0
DRGJB20 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | End of Initial Phase 1 | 0 | SUB-JB
MS-P1S1S1S | TCC120 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | Start of Phase 1, Stage 1, Step 1 | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | 0 |  | TC-Maint.
R710 | MS-P1S1S1F | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ E. Osborne Ave - South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
R690 | MS-P1S1S1F | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ Chelsea St.- South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
R645 | MS-P1S1S1F | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ East Lake Ave. - South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
PAV160 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | SUB-ASPH
R665 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ MLK Blvd.- South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
LOE-P3 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Phase 3 Duration | End of Phase 3 | 0
MS-P3S | LOE-P3 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.1 MOT Summary | Start of Phase 3 | Phase 3 Duration | 0
LOE-P1S2 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Phase 1: Stage 2 Duration | End of Phase 1, Stage 2 | 0
M1900 | LOE-P1S2 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start of Phase 1, Stage 2 | Phase 1: Stage 2 Duration | 0
MS-P1S1S | LOE-P1S1 | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start of Phase 1, Stage 1 | Phase 1: Stage 1 Duration | 0
LOE-P1S1S2 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Phase 1: Stage 1 - Step 2 Duration | End of Phase 1, Stage 1, Step 2 | 0
MS-P1S1S2S | LOE-P1S1S2 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start of Phase 1, Stage 1, Step 2 | Phase 1: Stage 1 - Step 2 Duration | 0
LOE-P1S1S1 | MS-P1S1S1F | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Phase 1: Stage 1 - Step 1 Duration | End of Phase 1, Stage 1, Step 1 | 0
MS-P1S1S1S | LOE-P1S1S1 | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start of Phase 1, Stage 1, Step 1 | Phase 1: Stage 1 - Step 1 Duration | 0
LOE-IP1 | MS-IP1F | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Initial Phase 1 Duration | End of Initial Phase 1 | 0
MS-IP1S | LOE-IP1 | SS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start of Initial Phase 1 | Initial Phase 1 Duration | 0
LOE-P2 | MS-P2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.1 MOT Summary | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | Phase 2 Duration | End of Phase 2 | 0
MS-P2S | LOE-P2 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.1 MOT Summary | Start of Phase 2 | Phase 2 Duration | 0
DEMO | DEMO1310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | Demo Traffic Railing 100201 - NB: over Floribraska - Ph1-S1 | Demo Edge of Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1310 | DEMO1330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Prep Work | Demo Edge of Deck 100201 - NB: over Floribraska - Ph1-S1 | Demo End of Existing End Bent - NB: over Floribraska - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE100 | SUBS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
SUB30 | SUBS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Procurement: Substructure | Form / Reinforce / Pour Pier #2 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
BBM100 | SUPR100 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | Overhang 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUB30 | SUBS310 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Procurement: Substructure | Form / Reinforce / Pour End Bent 4 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUB30 | SUBS470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Procurement: Substructure | Form / Reinforce / Pour End Bent 4 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUB30 | SUBS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Procurement: Substructure | Form / Reinforce / Pour End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUB30 | SUBS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Procurement: Substructure | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUPR120 | SUPR170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Set Deck Screed 100201 - NB: over Floribraska - Ph1-S1 | Pour Deck 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR170 | B1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Pour Deck 100201 - NB: over Floribraska - Ph1-S1 | Deck Cure 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-BRIDGE-SUP
SUB30 | SUBS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Procurement: Substructure | Form / Reinforce / Pour End Bent 1 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
B1200 | SUPR230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Deck Cure 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-APPR
SUPR230 | B1220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100201 - NB: over Floribraska - Ph1-S1 | Approach Slabs Cure 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-APPR
B1220 | BW540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Approach Slabs Cure 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour Traffic Barrier 100201 - NB: over Floribraska - Ph1-S1 | 0
DEMO1350 | DEMO1370 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.1 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Edge of Deck 100207 - NB: over East Lake - Ph1-S1 | Demo End of Existing End Bent 100207 - NB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE130 | SUBS200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
BBM110 | SUPR130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | Overhang 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUPR180 | SUPR210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form Deck 100207 - NB: over East Lake - Ph1-S1 | Set Deck Screed 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR210 | SUPR240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Set Deck Screed 100207 - NB: over East Lake - Ph1-S1 | Pour Deck 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR240 | B1440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Pour Deck 100207 - NB: over East Lake - Ph1-S1 | Deck Cure 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP
B1440 | SUPR310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-APPR
SUPR310 | B1460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | Approach Slabs Cure 100207 - NB: over East Lake - Ph1-S1 | 0 | ST-APPR
B1460 | B1470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Approach Slabs Cure 100207 - NB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100207 - NB: over East Lake - Ph1-S1 | 0
DEMO1540 | DEMO1620 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | Demo Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | Demo Existing Deck 100207 - SB: over East Lake - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1620 | SUPR770 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.1 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Demo Existing Deck 100207 - SB: over East Lake - Ph1-S1 | Form / SIP / Reinforce / Pour Replacement Deck 100207 - SB: over East Lake - Ph1-S1 | 0 | DM-BRIDGE | ST-BRIDGE-SUP
SUPR770 | B1510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Form / SIP / Reinforce / Pour Replacement Deck 100207 - SB: over East Lake - Ph1-S1 | Deck Cure 100207 - SB: over East Lake - Ph1-S1 | 0 | ST-BRIDGE-SUP
B1510 | B1520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.3.4 Construction: Phase 1: Stage 1: I-275 SB: 746+91.13 to 748+29.85: Bridge: Superstructure | Deck Cure 100207 - SB: over East Lake - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100207 - SB: over East Lake - Ph1-S1 | 0
DEMO1380 | DEMO1400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Edge of Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Demo End of Existing End Bent 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE150 | SUBS240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
BBM120 | SUPR190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | Overhang 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
M1900 | EGC380 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Start of Phase 1, Stage 2 | Excavate / Grade - MLK Ramp A - Ph1-S2 | 0 |  | EW-SML
SUPR250 | SUPR300 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Set Deck Screed 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR300 | SUPR320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set Deck Screed 100204 - NB: over MLK Blvd - Ph1-S1 | Pour Deck 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR320 | B1730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pour Deck 100204 - NB: over MLK Blvd - Ph1-S1 | Deck Cure 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-BRIDGE-SUP
B1730 | SUPR360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-APPR
SUPR360 | B1750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | Approach Slabs Cure 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-APPR
B1750 | B1760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Approach Slabs Cure 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100204 - NB: over MLK Blvd - Ph1-S1 | 0
DEMO1510 | DEMO1600 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Traffic Railing 100204 - SB: over MLK - Ph1-S1 | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | 0 | DEMO | DM-BRIDGE
M1900 | EGC590 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Start of Phase 1, Stage 2 | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | 0 |  | EW-SML
DEMO1600 | DEMO1610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Prep Work | Demo Edge of Deck 100204 - SB: over MLK - Ph1-S1 | Demo End of Existing End Bent 100204 - SB: over MLK - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE340 | SUBS1360 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
M1900 | EGC550 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Start of Phase 1, Stage 2 | Excavate / Grade - MLK Ramp C - Ph1-S2 | 0 |  | EW-SML
M1900 | EGC340 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Start of Phase 1, Stage 2 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | 0 |  | EW-SML
M1900 | EGC370 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Start of Phase 1, Stage 2 | Excavate / Grade - MLK Ramp D - Ph1-S2 | 0 |  | EW-SML
M1900 | EGC330 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Start of Phase 1, Stage 2 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | 0 |  | EW-SML
M1900 | EGC360 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Start of Phase 1, Stage 2 | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | 0 |  | EW-SML
SUPR700 | SUPR750 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form Deck 100204 - SB: over MLK - Ph1-S1 | Set Deck Screed 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
M1900 | EGC350 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Start of Phase 1, Stage 2 | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | 0 |  | EW-SML
SUPR750 | SUPR760 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Set Deck Screed 100204 - SB: over MLK - Ph1-S1 | Pour Deck 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR760 | B1970 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Pour Deck 100204 - SB: over MLK - Ph1-S1 | Deck Cure 100204 - SB: over MLK - Ph1-S1 | 0 | ST-BRIDGE-SUP
B1970 | SUPR800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Deck Cure 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-APPR
SUPR800 | B1990 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | Approach Slabs Cure 100204 - SB: over MLK - Ph1-S1 | 0 | ST-APPR
B1990 | B2000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Approach Slabs Cure 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100204 - SB: over MLK - Ph1-S1 | 0
DEMO1390 | DEMO1410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1410 | DEMO1420 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.1 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Edge of Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Demo End of Existing End Bent 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE160 | SUBS430 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
BBM130 | SUPR260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | Overhang 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUPR290 | SUPR340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Set Deck Screed 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR340 | SUPR350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set Deck Screed 100206 - NB: over Chelsea St. - Ph1-S1 | Pour Deck 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR350 | B2210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pour Deck 100206 - NB: over Chelsea St. - Ph1-S1 | Deck Cure 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP
B2210 | SUPR370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-APPR
SUPR370 | B2230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | ST-APPR
PAV250 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - MLK Ramp B - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
B2230 | B2240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100206 - NB: over Chelsea St. - Ph1-S1 | 0
DEMO1500 | DEMO1580 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | Demo Edge of Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1580 | DEMO1590 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.1 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Prep Work | Demo Edge of Deck 100206 - SB: over Chelsea St. - Ph1-S1 | Demo End of Existing End Bent 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PAV270 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - MLK Ramp C - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
PILE320 | SUBS1330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
PAV450 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - MLK Ramp A - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
PAV290 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
PAV440 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - MLK Ramp D - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
PAV370 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
PAV400 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
R755 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
R780 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
R800 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ MLK Blvd.- North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
R820 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
SUPR660 | SUPR720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form Deck 100206 - SB: over Chelsea St. - Ph1-S1 | Set Deck Screed 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
R840 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
SUPR720 | SUPR740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Set Deck Screed 100206 - SB: over Chelsea St. - Ph1-S1 | Pour Deck 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR740 | B2450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Pour Deck 100206 - SB: over Chelsea St. - Ph1-S1 | Deck Cure 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-BRIDGE-SUP
B2450 | SUPR790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Deck Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-APPR
SUPR790 | B2470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-APPR
B2470 | B2480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100206 - SB: over Chelsea St. - Ph1-S1 | 0
DEMO1430 | DEMO1440 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1440 | DEMO1460 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.1 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Edge of Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Demo End of Existing End Bent 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE180 | SUBS640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
BBM140 | SUPR380 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Overhang 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUPR400 | SUPR430 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Set Deck Screed 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR430 | SUPR450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set Deck Screed 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Pour Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR450 | B2690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pour Deck 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Deck Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP
B2690 | SUPR490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-APPR
SUPR490 | B2710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-APPR
B2710 | B2720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0
DEMO1490 | DEMO1560 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Demo Edge of Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1560 | DEMO1570 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.1 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Prep Work | Demo Edge of Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Demo End of Existing End Bent 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE290 | SUBS1280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
SUPR610 | SUPR670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Set Deck Screed 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR670 | SUPR690 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Set Deck Screed 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Pour Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR690 | B2930 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Pour Deck 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Deck Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP
B2930 | SUPR780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Deck Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-APPR
SUPR780 | B2950 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Approach Slabs Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-APPR
B2950 | B2960 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Approach Slabs Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0
DEMO1450 | DEMO1480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DEMO | DM-BRIDGE
DEMO1480 | DEMO1520 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.1 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Edge of Deck & Part of Existing Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Demo End of Existing End Bent 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE200 | SUBS700 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Drive Production H-Piles 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
BBM150 | SUPR420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Overhang 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BEAM | ST-BRIDGE-SUP
SUPR460 | SUPR480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Set Deck Screed 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR480 | SUPR500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set Deck Screed 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Pour Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR500 | B3170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pour Deck 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Deck Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP
B3170 | SUPR510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-APPR
SUPR510 | B3190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Approach Slabs Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-APPR
B3190 | B3200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Approach Slabs Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0
DEMO1530 | DEMO1550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.1 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Prep Work | Demo Edge of Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Demo End of Existing End Bent 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | DM-BRIDGE | DM-BRIDGE
PILE250 | SUBS1230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 1 Extension 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
CG100 | EGC470 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC490 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC580 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC570 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC560 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC540 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC520 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 0 | SUB-EW-C&G | EW-SML
CG100 | EGC510 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | 0 | SUB-EW-C&G | EW-SML
EGC470 | EGC100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC470 | EGC110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC480 | EGC180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC480 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC490 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC490 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Pond 2: 815 - 818 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavate / Grade Pond 2 - NB: 815 - 818 - IPh1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC580 | EGC290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | EW-SML
SUPR540 | SUPR560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Set Deck Screed 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
EGC580 | EGC280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-SML | EW-SML
SUPR560 | SUPR570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Set Deck Screed 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Pour Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP | ST-BRIDGE-SUP
SUPR570 | B3410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Pour Deck 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Deck Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-BRIDGE-SUP
EGC570 | EGC260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC570 | EGC270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | EW-SML
B3410 | SUPR580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Deck Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-APPR
SUPR580 | B3430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Approach Slabs Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-APPR
EGC540 | EGC230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | EW-SML
B3430 | B3440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Approach Slabs Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Traffic Railing 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0
EGC540 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC520 | EGC220 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC520 | EGC210 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC510 | EGC220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC510 | EGC210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-SML
MS-P1S1S | DEMO1690 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Start of Phase 1, Stage 1 | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | 0 |  | DEMO
BASE740 | PAV490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Black Base - SB: 709+50-721+43 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB530 | BASE740 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Stabilization - SB: 709+50-721+43 - Ph1-S1 | Black Base - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE740 | CP490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Black Base - SB: 709+50-721+43 - Ph1-S1 | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC100 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB170 | BASE170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Stabilization - NB: 722+83-735+00 - Ph1-S1 | Black Base - NB: 722+83-735+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
EGC100 | DRG150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Drainage: Existing to S-11 to S-13 (24") - NB: 725-726 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG150 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Drainage: Existing to S-11 to S-13 (24") - NB: 725-726 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
BASE710 | PAV480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Black Base - SB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
STAB520 | BASE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Stabilization - SB: 722+83-735+00 - Ph1-S1 | Black Base - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE710 | CP460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Black Base - SB: 722+83-735+00 - Ph1-S1 | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC110 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB180 | BASE180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Stabilization - NB: 735+46-746+91 - Ph1-S1 | Black Base - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE180 | CP110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Black Base - NB: 735+46-746+91 - Ph1-S1 | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC110 | DRG100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Drainage: Existing to S-28 to S-29 to Existing (36") - NB: 736-737 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG100 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Drainage: Existing to S-28 to S-29 to Existing (36") - NB: 736-737 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-CEM
BASE700 | PAV470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Black Base - SB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
EGC300 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB500 | BASE700 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Stabilization - SB: 735+46-746+91 - Ph1-S1 | Black Base - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE700 | CP440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Black Base - SB: 735+46-746+91 - Ph1-S1 | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC300 | DRG1000 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1000 | STAB500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Drainage: S-33 to Existing (18") - SB: 739-740 - Ph1-S1 | Stabilization - SB: 735+46-746+91 - Ph1-S1 | 0 | DRAIN | EW-CEM
BASE190 | PAV330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Black Base - NB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
EGC120 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB190 | BASE190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Stabilization - NB: 748+30-757+10 - Ph1-S1 | Black Base - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE190 | CP120 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Black Base - NB: 748+30-757+10 - Ph1-S1 | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC120 | DRG240 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | 0 | EW-SML | DRAIN
MS-P1S1S | DEMO380 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.3 Construction: Phase 1: Stage 1: I-275 NB: MLK Ramp B | Start of Phase 1, Stage 1 | Demo / Grade - MLK Ramp B - Ph1-S1 | 0 |  | DEMO
DRG240 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-41 OF to S-41 (30") - NB: 751-752 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
CP110 | PAV310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Concrete Pavement (9") - NB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
CP120 | PAV330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - NB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - NB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
CP490 | PAV490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Roadwork | Concrete Pavement (9") - SB: 709+50-721+43 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 709+50-721+43 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
CP460 | PAV480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Roadwork | Concrete Pavement (9") - SB: 722+83-735+00 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
CP440 | PAV470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Roadwork | Concrete Pavement (9") - SB: 735+46-746+91 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
CP430 | PAV460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | SUB-ASPH
BASE660 | PAV460 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Black Base - SB: 748+30-757+10 - Ph1-S1 | Asphalt Paving - Shoulder - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | SUB-ASPH
EGC290 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB470 | BASE660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Stabilization - SB: 748+30-757+10 - Ph1-S1 | Black Base - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE660 | CP430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Black Base - SB: 748+30-757+10 - Ph1-S1 | Concrete Pavement (9") - SB: 748+30-757+10 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC290 | DRG1020 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | 0 | EW-SML | DRAIN
PAV310 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Asphalt Paving - Shoulder - NB: 735+46-746+91 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | SUB-ASPH
DRG1020 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Drainage: S-43 OF to S-43 (18") - SB: 752-753 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | DRAIN | EW-CEM
BASE200 | CP170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Black Base - NB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC390 | BW1160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-SML | BARRIER
EGC130 | STAB200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB200 | BASE200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Stabilization - NB: 757+10-759+97 - Ph1-S1 | Black Base - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE200 | CP130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Black Base - NB: 757+10-759+97 - Ph1-S1 | Concrete Pavement (9") - NB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | CONCRETE
STAB450 | BASE640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Stabilization - SB: 757+10-759+97 - Ph1-S1 | Black Base - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-CEM | EW-ABC
EGC340 | SG100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Excavate / Grade - Hillsborough Ramp C2 - Ph1-S2 | Form / Reinforce / Pour Shoulder Gutter - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-SML
BASE640 | CP520 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Black Base - SB: 757+10-759+97 - Ph1-S1 | Concrete Shoulder - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC360 | BW910 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Excavate / Grade - Hillsborough Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp A - Ph1-S2 | 0 | EW-SML | BARRIER
BASE640 | CP410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Black Base - SB: 757+10-759+97 - Ph1-S1 | Concrete Pavement (9") - SB: 757+10-759+97 - Ph1-S1 | 0 | EW-ABC | CONCRETE
STAB210 | BASE220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Stabilization - NB: 761+67-767+00 - Ph1-S1 | Black Base - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
EGC590 | BW320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Excavate / Grade - Hillsborough Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp B - Ph1-S2 | 0 | EW-SML
BASE220 | CP180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Black Base - NB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC140 | STAB210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
BASE220 | CP140 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Black Base - NB: 761+67-767+00 - Ph1-S1 | Concrete Pavement (9") - NB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC140 | DRG330 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Drainage: S-59 to S-60 (36") - NB: 764-765 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC330 | BW660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-SML
DRG330 | STAB210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Drainage: S-59 to S-60 (36") - NB: 764-765 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC350 | BW820 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Excavate / Grade - Hillsborough Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - Hillsborough Ramp D - Ph1-S2 | 0 | EW-SML | BARRIER
BASE610 | CP510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Black Base - SB: 761+67-767+00 - Ph1-S1 | Concrete Shoulder - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC260 | STAB430 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Stabilization - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB430 | BASE610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Stabilization - SB: 761+67-767+00 - Ph1-S1 | Black Base - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE610 | CP400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Black Base - SB: 761+67-767+00 - Ph1-S1 | Concrete Pavement (9") - SB: 761+67-767+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC380 | BW1100 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Excavate / Grade - MLK Ramp A - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp A - Ph1-S2 | 0 | EW-SML | BARRIER
BASE230 | CP200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Black Base - NB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC150 | STAB220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB220 | BASE230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Stabilization - NB: 767+00-773+42 - Ph1-S1 | Black Base - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE230 | CP150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Black Base - NB: 767+00-773+42 - Ph1-S1 | Concrete Pavement (9") - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC530 | BW150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Excavate / Grade - MLK Ramp B - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp B - Ph1-S2 | 0 | EW-SML
EGC150 | DRG380 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Drainage: CD-3 to S-78 (48") - NB: 767-768 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC550 | BW210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Excavate / Grade - MLK Ramp C - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp C - Ph1-S2 | 0 | EW-SML
DRG380 | STAB220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Drainage: CD-3 to S-78 (48") - NB: 767-768 - Ph1-S1 | Stabilization - NB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
STAB410 | BASE570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Stabilization - SB: 767+00-773+42 - Ph1-S1 | Black Base - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE570 | CP500 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Black Base - SB: 767+00-773+42 - Ph1-S1 | Concrete Shoulder - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC270 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | EW-CEM
BASE570 | CP380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Black Base - SB: 767+00-773+42 - Ph1-S1 | Concrete Pavement (9") - SB: 767+00-773+42 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC370 | BW1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Excavate / Grade - MLK Ramp D - Ph1-S2 | Form / Reinforce / Pour Barrier Wall Footing - MLK Ramp D - Ph1-S2 | 0 | EW-SML | BARRIER
DRG1070 | STAB410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Drainage: S-61 to S-62 (24") - SB: 764-765 - Ph1-S1 | Stabilization - SB: 767+00-773+42 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC110 | BW100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC100 | BW100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | 0 | EW-SML | BARRIER
BW100 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BW100 | STAB180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.1 Construction: Phase 1: Stage 1: I-275 NB: 606+52.91 to 81+47.63: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 606+52.91-610+36.08 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | BARRIER | EW-CEM
EGC130 | BW270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | 0 | EW-SML | BARRIER
BASE240 | CP210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Black Base - NB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
BW270 | STAB200 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | Stabilization - NB: 757+10-759+97 - Ph1-S1 | 0 | BARRIER | EW-CEM
EGC160 | STAB230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
EGC120 | BW270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | 0 | EW-SML | BARRIER
STAB230 | BASE240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Stabilization - NB: 774+82-780+00 - Ph1-S1 | Black Base - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BW270 | STAB190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.1 Construction: Phase 1: Stage 1: I-275 NB: 96+36.16 to 101+96.12: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 96+36.16-101+96.12 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | BARRIER | EW-CEM
BASE240 | CP160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Black Base - NB: 774+82-780+00 - Ph1-S1 | Concrete Pavement (9") - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC140 | BW300 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 104+06.12-107+60.00 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC160 | DRG440 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Drainage: S-106 to S-110 (18") - NB: 779-781 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG440 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Drainage: S-106 to S-110 (18") - NB: 779-781 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
BW300 | STAB210 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.2.1 Construction: Phase 1: Stage 1: I-275 NB: 104+06.12 to 107+60.00: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 104+06.12-107+60.00 - Ph1-S1 | Stabilization - NB: 761+67-767+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
EGC190 | BW410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | 0 | EW-SML | BARRIER
BW410 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BASE560 | CP480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Black Base - SB: 774+82-780+00 - Ph1-S1 | Concrete Shoulder - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC250 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
EGC180 | BW410 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | 0 | EW-SML | BARRIER
STAB390 | BASE560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Stabilization - SB: 774+82-780+00 - Ph1-S1 | Black Base - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BW410 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.1 Construction: Phase 1: Stage 1: I-275 NB: 138+14.43 to 209+44.37: Barrier Wall (RAMP HILLSB) | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 138+14.43-145+55.54 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | BARRIER | EW-CEM
BASE560 | CP370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Black Base - SB: 774+82-780+00 - Ph1-S1 | Concrete Pavement (9") - SB: 774+82-780+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
BASE320 | CP230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Black Base - NB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC190 | BW470 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 150+98.92-155+14.52 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC170 | STAB240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB240 | BASE320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Stabilization - NB: 780+00-786+69 - Ph1-S1 | Black Base - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE320 | CP190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Black Base - NB: 780+00-786+69 - Ph1-S1 | Concrete Pavement (9") - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | CONCRETE
BW470 | STAB260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.2 Construction: Phase 1: Stage 1: I-275 NB: 150+98.92 to 155+14.52: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 150+98.92-155+14.52 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
EGC170 | DRG450 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Drainage: S-114 to S-115 (18") - NB: 781-782 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC200 | BW500 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.1 Construction: Phase 1: Stage 1: I-275 NB: 408+39.93 to 177+80.95: Barrier Wall | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - NB: 408+39.93-170+00.00 - Ph1-S1 | 0 | EW-SML | BARRIER
DRG450 | STAB240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Drainage: S-114 to S-115 (18") - NB: 781-782 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC300 | BW1060 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.1 Construction: Phase 1: Stage 1: I-275 SB: 38+98.75 to 48+91.82: Barrier Wall | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 44+00.00-48+91.82 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC290 | BW980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | EW-SML | BARRIER
BASE550 | CP450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Black Base - SB: 780+00-786+69 - Ph1-S1 | Concrete Shoulder - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC240 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB380 | BASE550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Stabilization - SB: 780+00-786+69 - Ph1-S1 | Black Base - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE550 | CP360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Black Base - SB: 780+00-786+69 - Ph1-S1 | Concrete Pavement (9") - SB: 780+00-786+69 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC240 | DRG1200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | 0 | EW-SML | DRAIN
EGC280 | BW980 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.1 Construction: Phase 1: Stage 1: I-275 SB: 54+85.63 to 61+96.16: Barrier Wall | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 54+85.63-61+96.16 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC260 | BW940 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.3 Construction: Phase 1: Stage 1: I-275 SB: 64+06.16 to 69+52.31: Barrier Wall | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 64+06.16-69+52.31 - Ph1-S1 | 0 | EW-SML | BARRIER
DRG1200 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Drainage: Existing to S-112 (15") - SB: 781-782 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC240 | BW770 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | 0 | EW-SML | BARRIER
BASE340 | CP250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Black Base - NB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC180 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
BW770 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.1 Construction: Phase 1: Stage 1: I-275 SB: 82+99.07 to 87+69.07: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 82+99.07-87+69.07 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | BARRIER | EW-CEM
STAB250 | BASE340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Stabilization - NB: 788+09-800+00 - Ph1-S1 | Black Base - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
EGC220 | BW670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | 0 | EW-SML | BARRIER
BASE340 | CP220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Black Base - NB: 788+09-800+00 - Ph1-S1 | Concrete Pavement (9") - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
DRG490 | STAB250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Drainage: S-128 OF to S-128 (18") - NB: 795-796 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
BW670 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.2 Construction: Phase 1: Stage 1: I-275 SB: 92+99.11 to 103+33.28: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 98+00.00-103+33.28 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
BASE530 | CP420 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Black Base - SB: 788+09-800+00 - Ph1-S1 | Concrete Shoulder - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC230 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | EW-CEM
EGC210 | BW570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.1 Construction: Phase 1: Stage 1: I-275 SB: 129+29.53 to 136+98.62: Barrier Wall | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 129+29.53-136+98.62 - Ph1-S1 | 0 | EW-SML | BARRIER
STAB360 | BASE530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Stabilization - SB: 788+09-800+00 - Ph1-S1 | Black Base - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE530 | CP340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Black Base - SB: 788+09-800+00 - Ph1-S1 | Concrete Pavement (9") - SB: 788+09-800+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC230 | DRG1270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | 0 | EW-SML | DRAIN
DRG1270 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Drainage: S-126 OF to S-126 (18") - SB: 793-795 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | DRAIN | EW-CEM
EGC220 | BW630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | 0 | EW-SML | BARRIER
BASE350 | CP270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Black Base - NB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | CONCRETE
BW630 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.1 Construction: Phase 1: Stage 1: I-275 SB: 109+78.31 to 114+18.91: Barrier Wall | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Shoulder Barrier Footing - SB: 109+78.31-114+18.91 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | BARRIER | EW-CEM
EGC210 | BW600 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.2 Construction: Phase 1: Stage 1: I-275 SB: 119+18.91 to 423+56.61: Barrier Wall (RAMP HILLSD) | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Shoulder Barrier Footing - RAMP HILLSD: 119+18.91-423+56.61 - Ph1-S1 | 0 | EW-SML | BARRIER
EGC190 | STAB260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Stabilization - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB260 | BASE350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Stabilization - NB: 800+00-813+16 - Ph1-S1 | Black Base - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-CEM | EW-ABC
BASE350 | CP240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | Black Base - NB: 800+00-813+16 - Ph1-S1 | Concrete Pavement (9") - NB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | CONCRETE
STAB490 | BASE670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Stabilization - MLK Ramp A - Ph1-S2 | Base Course - MLK Ramp A - Ph1-S2 | 0 | EW-CEM | EW-ABC
STAB340 | BASE480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Stabilization - SB: 800+00-813+16 - Ph1-S1 | Black Base - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-CEM | EW-ABC
STAB510 | BASE720 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Stabilization - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Black Base - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-CEM | EW-ABC
BASE480 | CP390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Black Base - SB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | CONCRETE
EGC220 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-SML | EW-CEM
BASE480 | CP320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Black Base - SB: 800+00-813+16 - Ph1-S1 | Concrete Pavement (9") - SB: 800+00-813+16 - Ph1-S1 | 0 | EW-ABC | CONCRETE
STAB130 | BASE130 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Stabilization - MLK Ramp B - Ph1-S2 | Base Course - MLK Ramp B - Ph1-S2 | 0 | EW-CEM | EW-ABC
EGC220 | DRG1340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | 0 | EW-SML | DRAIN
STAB150 | BASE150 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Stabilization - MLK Ramp C - Ph1-S2 | Base Course - MLK Ramp C - Ph1-S2 | 0 | EW-CEM | EW-ABC
DRG1340 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Drainage: S-157 OF to S-157 (24") - SB: 806-807 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | DRAIN | EW-CEM
STAB290 | BASE400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Stabilization - NB: 815+20-839+61 - Ph1-S1 | Black Base - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-CEM | EW-ABC
STAB480 | BASE630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Stabilization - MLK Ramp D - Ph1-S2 | Base Course - MLK Ramp D - Ph1-S2 | 0 | EW-CEM | EW-ABC
BASE400 | CP290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
STAB400 | BASE490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Stabilization - Hillsborough Ramp A - Ph1-S2 | Base Course - Hillsborough Ramp A - Ph1-S2 | 0 | EW-CEM | EW-ABC
EGC200 | STAB290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB160 | BASE160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Stabilization - Hillsborough Ramp B - Ph1-S2 | Base Course - Hillsborough Ramp B - Ph1-S2 | 0 | EW-CEM | EW-ABC
BASE400 | CP260 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Black Base - NB: 815+20-839+61 - Ph1-S1 | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
STAB300 | BASE370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Stabilization - Hillsborough Ramp C1 - Ph1-S2 | Base Course - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-CEM | EW-ABC
EGC200 | DRG670 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | 0 | EW-SML | DRAIN
STAB320 | BASE410 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Stabilization - Hillsborough Ramp C2 - Ph1-S2 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-CEM | EW-ABC
DRG670 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-245 OF to S-245 (14"x23") - NB: 821-822 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
STAB370 | BASE450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Stabilization - Hillsborough Ramp D - Ph1-S2 | Base Course - Hillsborough Ramp D - Ph1-S2 | 0 | EW-CEM | EW-ABC
BASE470 | CP330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Black Base - SB: 815+20-839+61 - Ph1-S1 | Concrete Shoulder - SB: 815+20-827+00 - Ph1-S1 | 0 | EW-ABC | CONCRETE
PILE200 | SUBS850 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: EB #1 & 5 | Drive Production H-Piles 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 5 Extension 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
PILE200 | SUBS680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Substructure: Column #3 | Drive Production H-Piles 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Form / Reinforce / Pour Pier #3 Column 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
EGC210 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-CEM
STAB330 | BASE470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Stabilization - SB: 815+20-839+61 - Ph1-S1 | Black Base - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-CEM | EW-ABC
PILE290 | SUBS1260 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
BASE470 | CP310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Black Base - SB: 815+20-839+61 - Ph1-S1 | Concrete Pavement (9") - SB: 815+20-839+61 - Ph1-S1 | 0 | EW-ABC | CONCRETE
PILE320 | SUBS1290 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100206 - SB: over Chelsea St. - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
PILE340 | SUBS1320 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.3 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100204 - SB: over MLK - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100204 - SB: over MLK - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
PILE150 | SUBS400 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100204 - NB: over MLK Blvd - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
PILE100 | SUBS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.3 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: EB #1 & 4 | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | Form / Reinforce / Pour End Bent 4 Extension 100201 - NB: over Floribraska - Ph1-S1 | 0 | ST-PILE | ST-BRIDGE-SUB
EGC210 | DRG1450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | 0 | EW-SML | DRAIN
WBO-TEC-10 | DS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Tampa Electric Company - Remaining Pole Procurement - Started 14-Jan-21 | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 0 | SUB-UT-ELEC | SUB-ST-DRSFT
DRG1450 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Drainage: S-200 to Existing (18") - SB: 817-818 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | DRAIN | EW-CEM
BASE780 | CP530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | 3462-FDOT-Owner-12.4.P2.2 Construction: Phase 2: I-275 Median: NB & SB: Station: 714+00 to 721+43 | Black Base - NB & SB Median: 714+00-721+43 - Ph2 | Concrete Pavement (9") - NB & SB Median: 714+00-721+43 - Ph2 | 0 | EW-ABC | CONCRETE
PAV530 | R3540 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | Install Misc Final Signage Remaining - Project Limits - Ph3 | 0 | SUB-MILL | SUB-SIGN
PM220 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Final Pavement Markings - I-275 NB & Ramps - Project Limits - Ph3 | End of Phase 3 | 0 | SUB-STRIP
R3540 | MS-P3F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Install Misc Final Signage Remaining - Project Limits - Ph3 | End of Phase 3 | 0 | SUB-SIGN
MS-P3S | R3500 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Start of Phase 3 | Misc Grind Concrete Pavement - I-275 NB - Project Limits - Ph3 | 0 |  | SUB-DGRIND
MS-P3S | R3510 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Start of Phase 3 | Misc Grind Concrete Pavement - I-275 SB - Project Limits - Ph3 | 0 |  | SUB-DGRIND
MS-P3S | PAV530 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | Start of Phase 3 | Mill/Resurface Friction Course - Project Limits - Ph3 | 0 |  | SUB-MILL
MS-CE | MS-LNTP | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Contract Execution | Notice to Proceed | 20
MS-LNTP | MS-NTP | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Notice to Proceed | Start Construction | 0
MS-LNTP | ENV10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.5 Preconstruction: Procurement: Environmental | Notice to Proceed | Prepare Shop Drawings / Submittals: Environmental Compliance | 0
MS-LNTP | RDW10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.3 Preconstruction: Procurement: Walls: Temp Critical Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: Temp Critical Walls | 20
MS-LNTP | DRG10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | Notice to Proceed | Prepare Shop Drawings / Submittals: Drainage Pipe & Structures | 10
MS-LNTP | FND10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | Notice to Proceed | Prepare Shop Drawings / Submittals: H-Pile Foundations | 17
MS-LNTP | SPS10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | Notice to Proceed | Prepare Shop Drawings / Submittals: Superstructure | 0
MS-LNTP | RET10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | Notice to Proceed | Prepare Shop Drawings / Submittals: Anchored Retaining Wall (Deleted) | 20
MS-LNTP | ITS10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.3 Preconstruction: Procurement: Electrical / ITS: ITS | Notice to Proceed | Prepare Shop Drawings / Submittals: ITS | 0
MS-LNTP | LTG10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.1 Preconstruction: Procurement: Electrical / ITS: Lighting | Notice to Proceed | Prepare Shop Drawings / Submittals: Lighting | 0
MS-LNTP | SGN10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.4.2.1 Preconstruction: Procurement: Electrical / ITS: Signage | Notice to Proceed | Prepare Shop Drawings / Submittals: Signage | 0
MS180 | STAB230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | Stabilization - NB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS210 | STAB240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | Stabilization - NB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS340 | STAB380 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Stabilization - SB: 780+00-786+69 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS350 | STAB390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | Stabilization - SB: 774+82-780+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
SP10 | EC10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Mobilization - IPh1 | Erosion Control Installation - Project Limits - IPh1 | 0 |  | SUB-EROSION
SP10 | CG100 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Mobilization - IPh1 | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | 5 |  | SUB-EW-C&G
WBO-TEC-10 | SUBS1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.3.2.1 Tampa Electric Co. Project ID: 443770-1-52-01 (Coordination of work w/TEC pending) | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.3.1 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Substructure: Column #2 | Tampa Electric Company - Remaining Pole Procurement - Started 14-Jan-21 | Form / Reinforce / Pour Pier #2 Column 100204 - SB: over MLK - Ph1-S1 | 0 | SUB-UT-ELEC | ST-BRIDGE-SUB
MS-P2F | MS-P3S | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | 3462-FDOT-Owner-12.4.3 Construction: Phase 3 | End of Phase 2 | Start of Phase 3 | 0
M1999 | MS-P2S | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | End of Phase 1, Stage 2 | Start of Phase 2 | 0
MS-IP1S | SP10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | Start of Initial Phase 1 | Mobilization - IPh1 | 0
MS-NTP | MS-IP1S | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Start Construction | Start of Initial Phase 1 | 0
MS-IP1S | DRGJB20 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | Start of Initial Phase 1 | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | 1 |  | SUB-JB
SP10 | DRGJB20 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | Mobilization - IPh1 | Drainage: Jack & Bore: From S-158 to S-157 (24") (NB/SB:806 - 807 - Hillsborough Ramp A) - IPh1 | 0 |  | SUB-JB
DRGJB10 | MS-IP1F | FF | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.4 Construction: Initial Phase 1: Jack and Bore | 3462-FDOT-Owner-12.4.IP1.1 Construction: Initial Phase 1: Milestones | Drainage: Jack & Bore: From S-46 to S-47 (24") (NB: 753 - 754 - MLK Ramp B) - IPh1 | End of Initial Phase 1 | 0 | SUB-JB
TCC120 | DEMO120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | 0 | TC-Maint. | DEMO
DEMO120 | R610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Demo Existing Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R610 | R615 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Reinforce / Pour Gravity Wall W-2C @ Floribraska - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
R615 | R620 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Pour Slope Pavement @ Floribraska - South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
R620 | PAV160 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Floribraska Ave - Southside | Form / Pour Sidewalk @ Floribraska - South Side - Ph1-S1-S1 | Miscellaneous Asphalt Paving @ Floribraska - South Side - Ph1-S1-S1 | 0 | FLATWORK | SUB-ASPH
DEMO160 | R635 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Demo Existing Slope Pavement @ East Lake Ave.- South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-5D @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R635 | R640 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Reinforce / Pour Gravity Wall W-5D @ East Lake Ave. - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
R640 | R645 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Form / Pour Slope Pavement @ East Lake Ave. - South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ East Lake Ave. - South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
DEMO180 | R655 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R655 | R660 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
R660 | R665 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Form / Pour Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
DEMO220 | R675 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Demo Existing Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R675 | R680 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Reinforce / Pour Gravity Wall W-12A @ Chelsea St. - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
R680 | R690 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Form / Pour Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
DEMO250 | R700 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Demo Existing Slope Pavement @ E. Osborne Ave.- South Side - Ph1-S1-S1 | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R700 | R705 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Reinforce / Pour Gravity Wall W-13F @ E. Osborne Ave. - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ E. Osborne Ave - South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
R705 | R710 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Form / Pour Slope Pavement @ E. Osborne Ave - South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ E. Osborne Ave - South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
DEMO270 | R720 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | 0 | DEMO | ST-CIP
R720 | R725 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | Form / Pour Slope Pavement @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | ST-CIP | FLATWORK
R725 | R730 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Form / Pour Slope Pavement @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | Form / Pour Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | 0 | FLATWORK | FLATWORK
TCC120 | DEMO220 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Chelsea Street - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ Chelsea St.- South Side - Ph1-S1-S1 | 0 | TC-Maint. | DEMO
TCC120 | DEMO250 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Osborne Ave - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ E. Osborne Ave.- South Side - Ph1-S1-S1 | 0 | TC-Maint. | DEMO
TCC120 | DEMO160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: East Lake Ave - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ East Lake Ave.- South Side - Ph1-S1-S1 | 0 | TC-Maint. | DEMO
TCC120 | DEMO180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ MLK Blvd.- South Side - Ph1-S1-S1 | 0 | TC-Maint. | DEMO
TCC120 | DEMO270 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.0 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Detour South Side Pedestrian Traffic on Side Streets to North Side - Ph1-S1-S1 | Demo Existing Slope Pavement @ E. Hillsborough Ave. - South Side - Ph1-S1-S1 | 0 | TC-Maint. | DEMO
DEMO970 | R745 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Demo Existing Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Gravity Wall W-3A @ Floribraska - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R745 | R750 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Reinforce / Pour Gravity Wall W-3A @ Floribraska - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R750 | R755 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Pour Slope Pavement @ Floribraska - North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R755 | PAV280 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | Form / Pour Sidewalk @ Floribraska - North Side - Ph1-S1-S2 | Miscellaneous Asphalt Paving @ Floribraska - North Side - Ph1-S1-S2 | 0 | FLATWORK | SUB-ASPH
DEMO1000 | R770 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Demo Existing Slope Pavement @ East Lake Ave.- North Side - Ph1-S1-S2 | Form / Reinforce / Pour Gravity Wall W-7A @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R770 | R775 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Reinforce / Pour Gravity Wall W-7A @ East Lake Ave. - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R775 | R780 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.2 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: East Lake Ave - Northside | Form / Pour Slope Pavement @ East Lake Ave. - North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ East Lake Ave. - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
DEMO1030 | R790 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Demo Existing Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - East Half - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R790 | R795 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-9A @ MLK Blvd. - East Half - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R795 | R800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: MLK Blvd - Northside | Form / Pour Slope Pavement @ MLK Blvd.- North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ MLK Blvd.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
DEMO1060 | R810 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Demo Existing Slope Pavement @ Chelsea St.- North Side - Ph1-S1-S2 | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R810 | R815 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Reinforce / Pour Gravity Wall W-13A @ Chelsea St. - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R815 | R820 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.4 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Chelsea Street - Northside | Form / Pour Slope Pavement @ Chelsea St.- North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ Chelsea St.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
DEMO1090 | R830 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Demo Existing Slope Pavement @ E. Osborne Ave.- North Side - Ph1-S1-S2 | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R830 | R835 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Reinforce / Pour Gravity Wall W-15B @ E. Osborne Ave. - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R835 | R840 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.5 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Osborne Ave - Northside | Form / Pour Slope Pavement @ E. Osborne Ave - North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ E. Osborne Ave - North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
DEMO1130 | R850 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Demo Existing Slope Pavement @ E. Hillsborough Ave. - North Side - Ph1-S1-S2 | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - East Half - North Side - Ph1-S1-S2 | 0 | DEMO | ST-CIP
R850 | R855 | FS | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Reinforce / Pour Anchored Retaining Wall W-18C @ E. Hillsborough Ave. - East Half - North Side - Ph1-S1-S2 | Form / Pour Slope Pavement @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | ST-CIP | FLATWORK
R855 | R860 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | Form / Pour Slope Pavement @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | Form / Pour Sidewalk @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | 0 | FLATWORK | FLATWORK
R860 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Hillsborough Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ E. Hillsborough Ave.- North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | FLATWORK
CP260 | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Concrete Pavement (9") - NB: 815+20-827+00 - Ph1-S1 | End of Phase 1, Stage 1 | 0 | CONCRETE
MS-P1S1F | MS-P2S | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P2.1 Construction: Phase 2: Milestones | End of Phase 1, Stage 1 | Start of Phase 2 | 0
STAB170 | SUPR230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Stabilization - NB: 722+83-735+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100201 - NB: over Floribraska - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB200 | SUPR360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Stabilization - NB: 757+10-759+97 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB210 | SUPR360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Stabilization - NB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - NB: over MLK Blvd - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB450 | SUPR800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Stabilization - SB: 757+10-759+97 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB430 | SUPR800 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Stabilization - SB: 761+67-767+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100204 - SB: over MLK - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB410 | SUPR790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Stabilization - SB: 767+00-773+42 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB390 | SUPR790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Stabilization - SB: 774+82-780+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - SB: over Chelsea St. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB220 | SUPR370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Stabilization - NB: 767+00-773+42 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB230 | SUPR370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Stabilization - NB: 774+82-780+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100206 - NB: over Chelsea St. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB180 | SUPR310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Stabilization - NB: 735+46-746+91 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB190 | SUPR310 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Stabilization - NB: 748+30-757+10 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100207 - NB: over East Lake - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB240 | SUPR490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Stabilization - NB: 780+00-786+69 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB250 | SUPR490 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Stabilization - NB: 788+09-800+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB380 | SUPR780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Stabilization - SB: 780+00-786+69 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB360 | SUPR780 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Stabilization - SB: 788+09-800+00 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB340 | SUPR580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Stabilization - SB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB330 | SUPR580 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Stabilization - SB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB260 | SUPR510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Stabilization - NB: 800+00-813+16 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
STAB290 | SUPR510 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Stabilization - NB: 815+20-839+61 - Ph1-S1 | Form / Reinforce / Pour Approach Slabs 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 | EW-CEM | ST-APPR
B1750 | BASE200 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Roadwork | Approach Slabs Cure 100204 - NB: over MLK Blvd - Ph1-S1 | Black Base - NB: 757+10-759+97 - Ph1-S1 | 0 |  | EW-ABC
B1750 | BASE220 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Roadwork | Approach Slabs Cure 100204 - NB: over MLK Blvd - Ph1-S1 | Black Base - NB: 761+67-767+00 - Ph1-S1 | 0 |  | EW-ABC
B1990 | BASE640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Roadwork | Approach Slabs Cure 100204 - SB: over MLK - Ph1-S1 | Black Base - SB: 757+10-759+97 - Ph1-S1 | 0 |  | EW-ABC
B1990 | BASE610 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Roadwork | Approach Slabs Cure 100204 - SB: over MLK - Ph1-S1 | Black Base - SB: 761+67-767+00 - Ph1-S1 | 0 |  | EW-ABC
B2470 | BASE570 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Roadwork | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Black Base - SB: 767+00-773+42 - Ph1-S1 | 0 |  | EW-ABC
B2470 | BASE560 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Roadwork | Approach Slabs Cure 100206 - SB: over Chelsea St. - Ph1-S1 | Black Base - SB: 774+82-780+00 - Ph1-S1 | 0 |  | EW-ABC
B2230 | BASE230 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.4.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Roadwork | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Black Base - NB: 767+00-773+42 - Ph1-S1 | 0 |  | EW-ABC
B2230 | BASE240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Roadwork | Approach Slabs Cure 100206 - NB: over Chelsea St. - Ph1-S1 | Black Base - NB: 774+82-780+00 - Ph1-S1 | 0 |  | EW-ABC
B1460 | BASE180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Approach Slabs Cure 100207 - NB: over East Lake - Ph1-S1 | Black Base - NB: 735+46-746+91 - Ph1-S1 | 0 |  | EW-ABC
B1460 | BASE190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Approach Slabs Cure 100207 - NB: over East Lake - Ph1-S1 | Black Base - NB: 748+30-757+10 - Ph1-S1 | 0 |  | EW-ABC
B2710 | BASE320 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.4.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Roadwork | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Black Base - NB: 780+00-786+69 - Ph1-S1 | 0 |  | EW-ABC
B2710 | BASE340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Approach Slabs Cure 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Black Base - NB: 788+09-800+00 - Ph1-S1 | 0 |  | EW-ABC
B2950 | BASE550 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.4.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Roadwork | Approach Slabs Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Black Base - SB: 780+00-786+69 - Ph1-S1 | 0 |  | EW-ABC
B2950 | BASE530 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Approach Slabs Cure 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Black Base - SB: 788+09-800+00 - Ph1-S1 | 0 |  | EW-ABC
B3430 | BASE480 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Approach Slabs Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Black Base - SB: 800+00-813+16 - Ph1-S1 | 0 |  | EW-ABC
B3430 | BASE470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Approach Slabs Cure 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Black Base - SB: 815+20-839+61 - Ph1-S1 | 0 |  | EW-ABC
B3190 | BASE400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Approach Slabs Cure 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | Black Base - NB: 815+20-839+61 - Ph1-S1 | 0 |  | EW-ABC
EGC100 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Excavation/Embankment to Grade - NB: 722+83-735+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC110 | MSE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.1.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Excavation/Embankment to Grade - NB: 735+46-746+91 - Ph1-S1 | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC290 | MSE1110 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC120 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC160 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC170 | MSE500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC180 | MSE550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC250 | MSE1030 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC220 | MSE830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC210 | MSE790 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC210 | MSE710 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | Install Leveling Pad - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
EGC200 | MSE660 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | Install Leveling Pad - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | 0 | EW-SML | SUB-ST-MSE
MS-P1S1S1S | TCC140 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | Start of Phase 1, Stage 1, Step 1 | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | 0 |  | TRAFFIC
MS-P1S1S | TCC140 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | Start of Phase 1, Stage 1 | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | 0 |  | TRAFFIC
MS-P1S1S | DEMO110 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.3 Construction: Phase 1: Stage 1: I-275 NB: Floribraska Ramp C (Expedited in 45 Calendar Days) | Start of Phase 1, Stage 1 | Demo / Grade - Floribraska Ramp C (Expedited in 45 Calendar Days) - Ph1-S1 | 0 |  | DEMO
TCC110 | EGC320 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.3 Construction: Phase 1: Stage 1: I-275 SB: 709+50.00 to 721+43.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 709+50-721+43 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC140 | MSE1140 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | Install Leveling Pad - MSE Wall W-1A, 1B, 1C - RAMP NE: 712+54.99-717+20.23 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
DEMO1630 | DEMO1640 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.3 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C2 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | Demo / Grade - Hillsborough Ramp C2 - Ph1-S1 | 0 | DEMO | DEMO
M1900 | EGC390 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Start of Phase 1, Stage 2 | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 |  | EW-SML
LOE-CD | MS-FC | FF | In Progress | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Construction Duration (1200 Calendar Days + 92 FDOT Holidays = 1292 Calendar Day Contract Duration) | Final Completion (Baseline Date: 24-Apr-25) | 0
SP10 | EGC580 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Mobilization - IPh1 | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | 5 |  | EW-SML
BASE720 | CP470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Black Base - I-275/SB / Floribraska Ramp NE - Ph1-S2 | Concrete Pavement (14") - I-275 SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-ABC | CONCRETE
BASE670 | PAV450 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.10 Construction: Phase 1: Stage 2: MLK Ramp A | Base Course - MLK Ramp A - Ph1-S2 | Asphalt Paving - MLK Ramp A - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE130 | PAV250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Base Course - MLK Ramp B - Ph1-S2 | Asphalt Paving - MLK Ramp B - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE150 | PAV270 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | 3462-FDOT-Owner-12.4.P1.2.2.3 Construction: Phase 1: Stage 2: MLK Ramp C | Base Course - MLK Ramp C - Ph1-S2 | Asphalt Paving - MLK Ramp C - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE630 | PAV440 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.9 Construction: Phase 1: Stage 2: MLK Ramp D | Base Course - MLK Ramp D - Ph1-S2 | Asphalt Paving - MLK Ramp D - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE490 | PAV400 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | 3462-FDOT-Owner-12.4.P1.2.2.8 Construction: Phase 1: Stage 2: Hillsborough Ramp A | Base Course - Hillsborough Ramp A - Ph1-S2 | Asphalt Paving - Hillsborough Ramp A - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE160 | PAV290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | 3462-FDOT-Owner-12.4.P1.2.2.4 Construction: Phase 1: Stage 2: Hillsborough Ramp B | Base Course - Hillsborough Ramp B - Ph1-S2 | Asphalt Paving - Hillsborough Ramp B - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE370 | PAV350 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Base Course - Hillsborough Ramp C1 - Ph1-S2 | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE410 | PAV370 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | 3462-FDOT-Owner-12.4.P1.2.2.5 Construction: Phase 1: Stage 2: Hillsborough Ramp C2 | Base Course - Hillsborough Ramp C2 - Ph1-S2 | Asphalt Paving - Hillsborough Ramp C2 - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
BASE450 | PAV390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | Base Course - Hillsborough Ramp D - Ph1-S2 | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | 0 | EW-ABC | SUB-ASPH
PAV350 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - Hillsborough Ramp C1 - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
M1900 | EGC530 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.2 Construction: Phase 1: Stage 2: MLK Ramp B | Start of Phase 1, Stage 2 | Excavate / Grade - MLK Ramp B - Ph1-S2 | 0 |  | EW-SML
PAV390 | M1999 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.7 Construction: Phase 1: Stage 2: Hillsborough Ramp D | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Asphalt Paving - Hillsborough Ramp D - Ph1-S2 | End of Phase 1, Stage 2 | 0 | SUB-ASPH
RET30 | R720 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Procurement: Anchored Retaining Walls | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
RET30 | R655 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.2.1 Preconstruction: Procurement: Walls: Anchored Retaining Walls | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Procurement: Anchored Retaining Walls | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND30 | R720 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | Procurement: Foundations: H-Pile Foundations | Form / Reinforce / Pour Anchored Retaining Wall W-17A @ E. Hillsborough Ave. - East Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
FND30 | R655 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.1 Preconstruction: Procurement: Bridges: H-Pile Foundations | 3462-FDOT-Owner-12.4.P1.1.3.1.3 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: MLK Blvd - Southside | Procurement: Foundations: H-Pile Foundations | Form / Reinforce / Pour Anchored Retaining Wall W-8A @ MLK Blvd. - East Half - South Side - Ph1-S1-S1 | 0 |  | ST-CIP
DRG30 | EGC570 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.5 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0A: 769 - 772 | Procurement: Drainage Pipe & Structures | Excavate / Grade Swale 0A - SB: 769 - 772 - IPh1 | 0 |  | EW-SML
DRG30 | EGC560 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.4 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 0B: 777 - 781 | Procurement: Drainage Pipe & Structures | Excavate / Grade Swale 0B - SB: 777 - 781 - IPh1 | 0 |  | EW-SML
DRG30 | EGC540 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.3 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1A: 801 - 805 | Procurement: Drainage Pipe & Structures | Excavate / Grade Swale 1A - SB: 801 - 805 - IPh 1 | 0 |  | EW-SML
DRG30 | EGC580 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.6 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 1B: 748 - 751 | Procurement: Drainage Pipe & Structures | Excavate / Grade Swale 1B - SB: 748 - 751 - IPh1 | 0 |  | EW-SML
DRG30 | EGC520 | FS | Completed | In Progress | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 2: 823 - 827 | Procurement: Drainage Pipe & Structures | Excavate / Grade Swale 2 - SB: 823 - 827 - IPh1 | 0 |  | EW-SML
DRG30 | EGC510 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.3 Preconstruction: Procurement: Drainage Pipe & Structures | 3462-FDOT-Owner-12.4.IP1.6.2.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: SB: Swale 3B: 835 - 840 | Procurement: Drainage Pipe & Structures | Excavate / Grade Swale 3B - SB: 835 - 840 - IPh1 | 0 |  | EW-SML
SPS30 | BBM100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.4 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM120 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.4 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM190 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.4 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100204 - SB: over MLK - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM130 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.4 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM180 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.4 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.4 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100207 - NB: over East Lake - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.4 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.4 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM150 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.4 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BEAM
SPS30 | BBM160 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.4 Preconstruction: Procurement: Bridges: Superstructure | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.4 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Superstructure | Procurement: 36" FIB's and Type III ASHHTO Beams | Set 36" FL I-Beams 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | ST-BEAM
PAV280 | MS-P1S1S2F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.2.1 Construction: Phase 1: Stage 1: Step 1 & 2: Step 2: North: Floribraska Ave - Northside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Miscellaneous Asphalt Paving @ Floribraska - North Side - Ph1-S1-S2 | End of Phase 1, Stage 1, Step 2 | 0 | SUB-ASPH
PILE100 | MSE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE100 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | Drive Production H-Piles 100201 - NB: over Floribraska - Ph1-S1 | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE130 | MSE300 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | Install Leveling Pad - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE130 | MSE340 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | Drive Production H-Piles 100207 - NB: over East Lake - Ph1-S1 | Install Leveling Pad - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE160 | MSE390 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.1 Construction: Phase 1: Stage 1: I-275 NB: 774+66.55 to 775+09.33: MSE Wall W-13B | Drive Production H-Piles 100206 - NB: over Chelsea St. - Ph1-S1 | Install Leveling Pad - MSE Wall W-13B - NB: 774+66.55-775+09.33 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE180 | MSE500 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.4.2.4 Construction: Phase 1: Stage 1: I-275 NB: 779+33.94 to 786+90.29: MSE Wall W-13E | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-13E - NB: 779+33.94-786+90.29 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE290 | MSE990 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | Drive Production H-Piles 100209 - SB: over E. Osborne Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE180 | MSE550 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | Drive Production H-Piles 100209 - NB: over E. Osborne Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE250 | MSE830 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
PILE250 | MSE790 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | Drive Production H-Piles 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | 0 | ST-PILE | SUB-ST-MSE
DS30 | DS160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.3.6.3.2 Construction: Phase 1: Stage 1: I-275 SB: 813+15.64 to 815+19.64: Bridge: Foundations | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100211 - SB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.2.6.3.2 Construction: Phase 1: Stage 1: I-275 NB: 813+15.64 to 815+19.64: Bridge: Foundation | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100211 - NB: over E. Hillsborough Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.3.5.3.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 788+09.29: Bridge: Foundations | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100209 - SB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.2.5.3.2 Construction: Phase 1: Stage 1: I-275 NB: 786+69.29 to 788+09.29: Bridge: Foundation | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100209 - NB: over E. Osborne Ave. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.2.2.3.2 Construction: Phase 1: Stage 1: I-275 NB: 746+91.13 to 748+29.85: Bridge: Foundation | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100207 - NB: over East Lake - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.3.4.3.2 Construction: Phase 1: Stage 1: I-275 SB: 773+41.84 to 774+86.84: Bridge: Foundations | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100206 - SB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.2.4.3.2 Construction: Phase 1: Stage 1: I-275 NB: 773+41.84 to 774+86.84: Bridge: Foundation | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100206 - NB: over Chelsea St. - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.3.3.3.2 Construction: Phase 1: Stage 1: I-275 SB: 759+97.10 to 761+67.10: Bridge: Foundations | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100204 - SB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.2.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 759+97.10 to 761+67.10: Bridge: Foundation | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100204 - NB: over MLK Blvd - Ph1-S1 | 0 |  | SUB-ST-DRSFT
DS30 | DS100 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Foundation | Procurement: Structural 48" Drilled Shafts | Install 48" Drilled Shafts 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | SUB-ST-DRSFT
MS-LNTP | DS10 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.2.1.1.2 Preconstruction: Procurement: Bridges: 48" Structural Drilled Shafts | Notice to Proceed | Prepare Shop Drawings / Submittals: Structural 48" Drilled Shafts | 5
SUB30 | SUBS120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Procurement: Substructure | Form / Reinforce / Pour Pier #3 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUB30 | SUBS190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.2 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #3 | Procurement: Substructure | Form / Reinforce / Pour Pier #3 Cap 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
SUB30 | SUBS110 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.2.1.1.3 Preconstruction: Procurement: Bridges: Substructure | 3462-FDOT-Owner-12.4.P1.1.4.2.1.3.3.1 Construction: Phase 1: Stage 1: I-275 NB: 721+43.00 to 722+83.00: Bridge: Substructure: Column #2 | Procurement: Substructure | Form / Reinforce / Pour Pier #2 Column 100201 - NB: over Floribraska - Ph1-S1 | 0 |  | ST-BRIDGE-SUB
MS330 | STAB360 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.5 Construction: Phase 1: Stage 1: I-275 SB: 787+88.29 to 790+80.04: MSE Wall W-15A | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-15A - SB: 787+88.29-790+80.04 - Ph1-S1 | Stabilization - SB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS220 | STAB250 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.2.3 Construction: Phase 1: Stage 1: I-275 NB: 787+88.29 to 794+49.71: MSE Wall W-15C | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-15C - NB: 787+88.29-794+49.71 - Ph1-S1 | Stabilization - NB: 788+09-800+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS300 | STAB340 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | Stabilization - SB: 800+00-813+16 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS290 | STAB330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Stabilization - SB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS250 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.3 Construction: Phase 1: Stage 1: I-275 NB: 835+65.00 to 839+61.51 - Ph1-S1: MSE Wall W-22A, 22B, 22C | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-22A, 22B, 22C - NB: 835+65.00-839+61.51 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS380 | DEMO1690 | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.1.2.2 Construction: Phase 1: Stage 1: I-275 SB: 712+54.99 to 717+20.23: MSE Wall W-1A, 1B, 1C | 3462-FDOT-Owner-12.4.P1.1.4.3.1.4.4 Construction: Phase 1: Stage 1: I-275 SB: Floribraska Ramp NE | Form / Reinforce / Pour Moment Slab - MSE Wall W-1A, 1B, 1C - RAMP NE: 714+80.00-717+20.23 - Ph1-S1 | Demo / Grade - Floribraska Ramp NE - Ph1-S1 | 0 | CONCRETE | DEMO
MS140 | STAB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS370 | STAB470 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | 3462-FDOT-Owner-12.4.P1.1.4.3.2.4.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | Stabilization - SB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS170 | STAB190 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.3 Construction: Phase 1: Stage 1: I-275 NB: 247+46.14 to 250+88.27: MSE Wall W-7B, 7C | 3462-FDOT-Owner-12.4.P1.1.4.2.2.4.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-7B, 7C - NB: 247+46.14-250+88.27 - Ph1-S1 | Stabilization - NB: 748+30-757+10 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS260 | STAB290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.3 Construction: Phase 1: Stage 1: I-275 SB: 834+76.00 to 839+49.92: MSE Wall W-21A, 21B, 21C, 21D | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-21A, 21B, 21C, 21D - SB: 834+76.00-839+49.92 - Ph1-S1 | Stabilization - NB: 815+20-839+61 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS360 | DEMO1670 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | 3462-FDOT-Owner-12.4.P1.1.4.3.3.4.3 Construction: Phase 1: Stage 1: I-275 SB: MLK Ramp D | Form / Reinforce / Pour Moment Slab - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 470+18.63-472+02.74 - Ph1-S1 | Demo / Grade - MLK Ramp D - Ph1-S1 | 0 | CONCRETE | DEMO
MS130 | STAB170 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-2A, W-2B - NB: 721+10.81-721+55.81 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
MS320 | DEMO1660 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | 3462-FDOT-Owner-12.4.P1.1.4.3.5.4.3 Construction: Phase 1: Stage 1: I-275 SB: Hillsborough Ramp A | Form / Reinforce / Pour Moment Slab - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | Demo / Grade - Hillsborough Ramp A - Ph1-S1 | 0 | CONCRETE | DEMO
MS240 | DEMO1630 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | Form / Reinforce / Pour Moment Slab - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | 0 | CONCRETE | DEMO
MS270 | DEMO1650 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.4.2 Construction: Phase 1: Stage 1: I-275 Ramps: SB: Hillsborough Ramp D | Form / Reinforce / Pour Moment Slab - MSE Wall W-20A - RAMP HILLSD: 824+88.73-827+09.88 - Ph1-S1 | Demo / Grade - Hillsborough Ramp D - Ph1-S1 | 0 | CONCRETE | DEMO
MS160 | STAB180 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.2.2.2 Construction: Phase 1: Stage 1: I-275 NB: 746+69.47 to 747+09.82: MSE Wall W-5C | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.2 Construction: Phase 1: Stage 1: I-275 NB: 735+00.00 to 746+91.13: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-5C - NB: 746+69.47-747+09.82 - Ph1-S1 | Stabilization - NB: 735+46-746+91 - Ph1-S1 | 0 | CONCRETE | EW-CEM
TCC110 | EGC120 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.1 Construction: Phase 1: Stage 1: I-275 NB: 748+29.85 to 757+10.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 748+30-757+10 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC130 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.2.1.2 Construction: Phase 1: Stage 1: I-275 NB: 757+10.00 to 759+97.10: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 757+10-759+97 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC140 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC300 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.1 Construction: Phase 1: Stage 1: I-275 SB: 735+00.00 to 746+91.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 735+46-746+91 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC310 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.1.1.2 Construction: Phase 1: Stage 1: I-275 SB: 721+43.00 to 735+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 722+83-735+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC280 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.1 Construction: Phase 1: Stage 1: I-275 SB: 757+10.00 to 759+97.10: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 757+10-759+97 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC290 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.2.1.2 Construction: Phase 1: Stage 1: I-275 SB: 748+29.85 to 757+10.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 748+30-757+10 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC270 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.1 Construction: Phase 1: Stage 1: I-275 SB: 767+00.00 to 773+41.84: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 767+00-773+42 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC260 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.3.1.2 Construction: Phase 1: Stage 1: I-275 SB: 761+67.10 to 767+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 761+67-767+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC240 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.1 Construction: Phase 1: Stage 1: I-275 SB: 780+00.00 to 786+69.29: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 780+00-786+69 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC250 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.4.1.2 Construction: Phase 1: Stage 1: I-275 SB: 774+86.84 to 780+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 774+82-780+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC220 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.1 Construction: Phase 1: Stage 1: I-275 SB: 800+00.00 to 813+15.64: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 800+00-813+16 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC230 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.5.1.2 Construction: Phase 1: Stage 1: I-275 SB: 786+69.29 to 800+00.00: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 788+09-800+00 - Ph1-S1 | 0 | TRAFFIC | EW-SML
TCC110 | EGC210 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.6.1 Construction: Phase 1: Stage 1: I-275 SB: 815+19.64 to 839+61.49: Grading & Underground | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Excavation/Embankment to Grade - SB: 815+20-839+61 - Ph1-S1 | 0 | TRAFFIC | EW-SML
MS150 | STAB170 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | 3462-FDOT-Owner-12.4.P1.1.4.2.1.4.1 Construction: Phase 1: Stage 1: I-275 NB: 709+50.00 to 735+00.00: Roadwork | Form / Reinforce / Pour Moment Slab - MSE Wall W-4A, W-4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | Stabilization - NB: 722+83-735+00 - Ph1-S1 | 0 | CONCRETE | EW-CEM
TCC110 | MSE1070 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC110 | MSE890 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC110 | MSE190 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.2 Construction: Phase 1: Stage 1: I-275 NB: 721+10.81 to 721+55.81: MSE Wall W-2A, 2B | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-2A, 2B - NB: 721+10.81-721+55.81 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC110 | MSE260 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.5 Construction: Phase 1: Stage 1: I-275 NB: 604+00.00 to 606+52.91: MSE Wall W-4A, 4B (RAMP FLORC) | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-4A, 4B - Ramp FLORC: 604+00.00-606+52.91 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC110 | MSE610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC110 | MSE750 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC140 | MSE750 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.4 Construction: Phase 1: Stage 1: I-275 SB: 423+56.61 to 827+09.88: MSE Wall W-20A, 20B | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | Install Leveling Pad - MSE Wall W-20A, 20B - RAMP HILLSD: 423+56.61-827+09.88 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC140 | MSE610 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.6.2.2 Construction: Phase 1: Stage 1: I-275 NB: 405+73.05 to 408+39.85: MSE Wall W-19A (RAMP HILLSC1) | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | Install Leveling Pad - MSE Wall W-19A - RAMP HILLSC1: 405+73.05-408+39.85 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC140 | MSE890 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.5.2.4 Construction: Phase 1: Stage 1: I-275 SB: 801+14.79 to 202+81.71: MSE Wall W-16A, 16B | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | Install Leveling Pad - MSE Wall W-16A, 16B - SB: 801+14.79-202+81.71 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC140 | MSE1070 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.3.2.4 Construction: Phase 1: Stage 1: I-275 SB: 468+72.82 to 472+02.74: MSE Wall W-11A, 11B, 11C | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | Install Leveling Pad - MSE Wall W-11A, 11B, 11C - RAMP MKLKD: 468+72.82-472+02.74 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC140 | MSE1110 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.3.2.2.3 Construction: Phase 1: Stage 1: I-275 SB: 102+15.61 to 104+50.80: MSE Wall W-6A, 6B | MOT Shift Ramp Traffic to Temp Ramp Diversions - Ph1-S1 | Install Leveling Pad - MSE Wall W-6A, 6B - RAMP MLKA: 102+15.61-104+50.80 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
TCC110 | MSE230 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | 3462-FDOT-Owner-12.4.P1.1.4.2.1.2.3 Construction: Phase 1: Stage 1: I-275 NB: 722+53.95 to 723+02.10: MSE Wall W-3B | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | Install Leveling Pad - MSE Wall W-3B - NB: 722+53.95-723+02.10 - Ph1-S1 | 0 | TRAFFIC | SUB-ST-MSE
MSE790 | MSE830 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.5 Construction: Phase 1: Stage 1: I-275 SB: 815+09.64 to 817+00.00: MSE Wall W-18A, 18B | 3462-FDOT-Owner-12.4.P1.1.4.3.6.2.6 Construction: Phase 1: Stage 1: I-275 SB: 812+95.64 to 813+25.64: MSE Wall W-17B | Install Leveling Pad - MSE Wall W-18A, 18B - SB: 815+09.64-817+00.00 - Ph1-S1 | Install Leveling Pad - MSE Wall W-17B - SB: 812+95.64-813+25.64 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
MSE990 | MSE1030 | FS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.3 Construction: Phase 1: Stage 1: I-275 SB: 785+50.00 to 786+90.29: MSE Wall W-13G | 3462-FDOT-Owner-12.4.P1.1.4.3.4.2.4 Construction: Phase 1: Stage 1: I-275 SB: 777+38.56 to 780+80.00: MSE Wall W-14A, 14B | Install Leveling Pad - MSE Wall W-13G - SB: 785+50.00-786+90.29 - Ph1-S1 | Install Leveling Pad - MSE Wall W-14A, 14B - SB: 777+38.56-780+80.00 - Ph1-S1 | 0 | SUB-ST-MSE | SUB-ST-MSE
CG100 | MS-P1S1S | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.2 Construction: Initial Phase 1: Site Preparation | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Clearing & Grubbing / Tree Protection / Pruning - Project Limits - IPh1 | Start of Phase 1, Stage 1 | 0 | SUB-EW-C&G
MS-P1S1S | TCC110 | SS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.4.1 Construction: Phase 1: Stage 1: Traffic Control | Start of Phase 1, Stage 1 | MOT Shift I-275 Traffic Inside to Phase 1, Stage 1 Configuration - Ph1-S1 | 0 |  | TRAFFIC
M1900 | EGC500 | SS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | Start of Phase 1, Stage 2 | Excavate / Grade - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | 0 |  | EW-SML
EGC470 | EGC480 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.IP1.6.1.1 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1A: 737 - 739 | 3462-FDOT-Owner-12.4.IP1.6.1.2 Construction: Initial Phase 1: Swales - Drainage - Pond 2: NB: Swale 1: 801 - 805 | Excavate / Grade Swale 1A - NB: 737 - 739 - IPh1 | Excavate / Grade Swale 1 - NB: 801 - 805 - IPh1 | 0 | EW-SML | EW-SML
EGC140 | EGC150 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.1 Construction: Phase 1: Stage 1: I-275 NB: 761+67.10 to 767+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | Excavation/Embankment to Grade - NB: 761+67-767+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC150 | EGC160 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.3.1.2 Construction: Phase 1: Stage 1: I-275 NB: 767+00.00 to 773+41.84: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 767+00-773+42 - Ph1-S1 | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC160 | EGC170 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.1 Construction: Phase 1: Stage 1: I-275 NB: 774+86.84 to 780+00.00: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | Excavation/Embankment to Grade - NB: 774+82-780+00 - Ph1-S1 | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC170 | EGC180 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.4.1.2 Construction: Phase 1: Stage 1: I-275 NB: 780+00.00 to 786+69.29: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.1 Construction: Phase 1: Stage 1: I-275 NB: 788+09.29 to 800+00.00: Grading & Underground | Excavation/Embankment to Grade - NB: 780+00-786+69 - Ph1-S1 | Excavation/Embankment to Grade - NB: 788+09-800+00 - Ph1-S1 | 0 | EW-SML | EW-SML
EGC190 | EGC200 | FS | Completed | Completed | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.1.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Grading & Underground | 3462-FDOT-Owner-12.4.P1.1.4.2.6.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Grading & Underground | Excavation/Embankment to Grade - NB: 800+00-813+16 - Ph1-S1 | Excavation/Embankment to Grade - NB: 815+20-839+61 - Ph1-S1 | 0 | EW-SML | EW-SML
MS-P1S1S | M1900 | SS | Completed | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.2.1 Construction: Phase 1: Stage 2: Milestones | Start of Phase 1, Stage 1 | Start of Phase 1, Stage 2 | 0
DEMO1630 | EGC330 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.2 Construction: Phase 1: Stage 1: I-275 NB: Hillsborough Ramp C1 | 3462-FDOT-Owner-12.4.P1.2.2.6 Construction: Phase 1: Stage 2: Hillsborough Ramp C1 | Demo / Grade - Hillsborough Ramp C1 - Ph1-S1 | Excavate / Grade - Hillsborough Ramp C1 - Ph1-S2 | 0 | DEMO | EW-SML
BW1220 | BW1240 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P2.4 Construction: Phase 2: I-275 Median: NB & SB: Station: 748+30 to 759+97 | 3462-FDOT-Owner-12.4.P2.5 Construction: Phase 2: I-275 Median: NB & SB: Station: 761+67 to 773+42 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 748+30-759+97 - Ph 2 | Form / Pour Median Barrier Wall Footing - NB & SB Median: 761+67-773+42 - Ph2 | 0 | BARRIER | BARRIER
CP270 | CP290 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.4.2.5.4.2 Construction: Phase 1: Stage 1: I-275 NB: 800+00.00 to 813+15.64: Roadwork | 3462-FDOT-Owner-12.4.P1.1.4.2.6.4.1 Construction: Phase 1: Stage 1: I-275 NB: 815+19.64 to 839+61.49: Roadwork | Concrete Shoulder - NB: 800+00-813+16 - Ph1-S1 | Concrete Shoulder - NB: 815+20-827+00 - Ph1-S1 | 0 | CONCRETE | CONCRETE
MS-SC | FDOTP | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.0 Project Milestones | 3462-FDOT-Owner-12.0 Project Milestones | Substantial Completion | FDOT Develop & Issue Punch List | 0
EGC500 | EGC390 | FS | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.2.2.1 Construction: Phase 1: Stage 2: Floribraska Ramp NE Swale 1B | 3462-FDOT-Owner-12.4.P1.2.2.11 Construction: Phase 1: Stage 2: Floribraska Ramp NE | Excavate / Grade - Swale 1B - SB: Side Between East Lake & MLK - Ph1-S2 | Excavate / Grade - I-275/SB / Floribraska Ramp NE - Ph1-S2 | 0 | EW-SML | EW-SML
R730 | MS-P1S1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.3.1.6 Construction: Phase 1: Stage 1: Step 1 & 2: Step 1: South: Hillsborough Ave - Southside | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | Form / Pour Sidewalk @ E. Hillsborough Ave.- South Side - Ph1-S1-S1 | End of Phase 1, Stage 1, Step 1 | 0 | FLATWORK
MS-P1S1S2F | MS-P1S1F | FF | Not Started | Not Started | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12 | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | 3462-FDOT-Owner-12.4.P1.1.1 Construction: Phase 1: Stage 1: Milestones | End of Phase 1, Stage 1, Step 2 | End of Phase 1, Stage 1 | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Day DateFormat=M/d/yyyy CurrencyFormat=Dollar