# Progress Made This Month

## Activities Started This Month

* D5190 - Revise and Resubmit - Interchange Modification Report (IMR)

## Activities Completed This Month

* D5180 - Review and Approve - Interchange Modification Report (IMR)
* D5190 - Revise and Resubmit - Interchange Modification Report (IMR)

# Activities/Progress/Events Anticipated to Affect the Critical Path in the Next 30 Days

Progress of the following activities at or above the scheduled rate is essential to avoid float degradation.

* D2740 - Develop and Submit - 90% Roadway Plans - R3

# Activity and Relationship Modifications

## Activity Name

|  |  |  |  |
| --- | --- | --- | --- |
| Activity ID | Activity Name | Old Activity Name | New Activity Name |
| D1230 | Develop and Submit - Interchange Modification Report (IMR) | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | Develop and Submit - Interchange Modification Report (IMR) |

## Added Activities

|  |  |
| --- | --- |
| Activity ID | Activity Name |
| D5200 | Review and Approve - Interchange Modification Report (IMR) Second Submittal |
| D5190 | Revise and Resubmit - Interchange Modification Report (IMR) |
| D5180 | Review and Approve - Interchange Modification Report (IMR) |

## Deleted Activities

|  |  |
| --- | --- |
| Activity ID | Activity Name |

## Added Successor Activity Relationships

|  |  |  |  |
| --- | --- | --- | --- |
| Predecessor Activity ID | Predecessor Activity Name | Successor Activity ID | Successor Activity Name |
| D5180 | Review and Approve - Interchange Modification Report (IMR) | D5190 | Revise and Resubmit - Interchange Modification Report (IMR) |
| D1230 | Develop and Submit - Interchange Modification Report (IMR) | D5180 | Review and Approve - Interchange Modification Report (IMR) |
| D5200 | Review and Approve - Interchange Modification Report (IMR) Second Submittal | Admin-1090 | Complete project - Critical Path (under development) |
| D5190 | Revise and Resubmit - Interchange Modification Report (IMR) | D5200 | Review and Approve - Interchange Modification Report (IMR) Second Submittal |

## Deleted Successor Activity Relationships

|  |  |  |  |
| --- | --- | --- | --- |
| Predecessor Activity ID | Predecessor Activity Name | Successor Activity ID | Successor Activity Name |
| D1230 | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | Admin-1090 | Complete project - Critical Path (under development) |
| D1100 | Perform Geotechnical Investigations - Roadway | D1190 | Perform Geotechnical Investigations - Retaining Walls |

## Original Duration

|  |  |  |  |
| --- | --- | --- | --- |
| Activity ID | Activity Name | Old Original Duration | New Original Duration |
| Admin-1090 | Complete project - Critical Path (under development) | 994 | 965 |
| Admin-1110 | Complete Project - Remaining activities (under development) | 915 | 900 |