# Progress Made This Month

## Activities Started This Month

* D1180
* D5180

## Activities Completed This Month

* D1160
* D1230
* D3380

# Activities/Progress/Events Anticipated to Affect the Critical Path in the Next 30 Days

Progress of the following activities at or above the scheduled rate is essential to avoid float degradation.

* D5190

# Activity and Relationship Modifications

## Activity Name

|  |  |  |
| --- | --- | --- |
| Activity ID | Old Activity Name | New Activity Name |
|  |  |  |
| D1230 | Prepare and Submit Interchange Modification Report (IMR) for FDOT review | Develop and Submit - Interchange Modification Report (IMR) |

## Added Activities

|  |  |
| --- | --- |
| Activity ID | Activity Name |
|  |  |
|  |  |
|  |  |
| D5200Review and Approve - Interchange Modification Report (IMR) Second Submittal |  |

## Deleted Activities

|  |  |
| --- | --- |
| Activity ID | Activity Name |
|  |  |

## Added Successor Activity Relationships

|  |  |  |  |
| --- | --- | --- | --- |
| Predecessor Activity ID | Predecessor Activity Name | Successor Activity ID | Successor Activity Name |
|  |  |  |  |

## Deleted Successor Activity Relationships

|  |  |  |  |
| --- | --- | --- | --- |
| Predecessor Activity ID | Predecessor Activity Name | Successor Activity ID | Successor Activity Name |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| P1510 | Procure Girders - Bridge 8 | Admin-1090 | Complete project - Critical Path (under development) |

## Original Duration

|  |  |  |
| --- | --- | --- |
| Activity ID | Old Original Duration | New Original Duration |
|  |  |  |
|  |  |  |
| Admin-1110 | 915 | 900 |